## AusAID_Grant_Allocation
Appendix 1
INITIAL AusAID GRANT ALLOCATION
| Category | Initially Allocated |  | Contingency 2.5% | Available Budget | % Financed by AusAID
|  | AUD | USD | USD | USD
1 | Goods and Consultants' Services | 82000 | 53620.62 | 1340.5155 | 52280.1045 | 100
2 | Works | 2310042 | 1510559.5642 | 37763.9891 | 1472795.5751 | 70
3 | Goods, Works and Consultants' Services for Flood Prevention Emergency Works | 225000 | 147129.75 | 3678.2438 | 143451.5063 | 100
| Total | 2617042 | 1711309.9342 | 42782.7484 | 1668527.1859
Source: MPWT
http://www.oanda.com/convert/classic
Monday, December 1, 2008
| USD 1 = | 1.5293
| AUD 1 = | 0.65391

## ProcPlan-FY08-09
Ministry of Public Works and Transport
Department of Roads
Road Maintenance Programme-Phase 2 - MP-8(2008/09)
(Supplementary AusAID Grant Contribution to RMP-2 for Periodic Maintenance of National and Provincial Roads)
PROPOSED PROCUREMENT PLAN
Date: | 2008-12-22
REVISED PROCUREMENT PLAN
Component/ |  | Activities | Firm/ | Procurement | Procurement | Procuring | Cost Estimate | AusAid |  | RMF |  | Provincial Govt. |  | Remark
Sub-Component |  |  | Individual | Method | Review | Agency's Name | in total (USD) | % | Amount | % | Amount | % | Amount
A |  | National Roads |  |  |  |  | 1009916.9761 |  | 706941.8761 |  | 302975.1
| A.1 | Spot Improvement of National Road 9 | Firm | NCB | Prior | RAD/DoR | 617017 | 70% | 431911.9 | 30% | 185105.1
| A.2 | Rehabilitation of National Road 1C | Firm | NCB | Post | RAD/DoR | 0 | 70% | 0 | 30% | 0
| A.3 | Periodic maintenance of Road 11 | Firm | NCB | Post | RAD/DoR | 350000 | 70% | 245000 | 30% | 105000
| A.4 | Maintenance of Bridges | Firm | NCB | Post | RAD/DoR | 42900 | 70% | 30030 | 30% | 12870
B |  | Provincial Roads (Periodic Maintenance, MP8) | Firm | NCB | Prior | LRD/DoR | 1094076.7129 | 70% | 765853.6991 | 20% | 218815.3426 | 10% | 109407.6713
C |  | Civil Works Supervision | Individual | CQ | Prior | PMD/DoR | 52280.1045 | 100% | 52280.1045
D |  | Flood Prevention Emergency Works (Vientiane Capital) |  |  |  | MPWT | 143451.5063 | 100% | 143451.5063 |  |  |  |  | retroactive financing
E |  | Contingencies |  |  | Prior | DoR | 42782.7484 | 100% | 42782.7484
TOTAL: | [6 empty] | 2342508.0481 |  | 1711309.9342 |  | 521790.4426 |  | 109407.6713
Proportion:
| http://www.oanda.com/convert/classic |  |  |  |  | NRN | 48
| Monday, December 1, 2008 |  |  |  |  | LRN | 52
USD 1 = AUD 1.52926
AUD 1 = USD 0.65391

## ProcPlan-FY09-10
Ministry of Public Works and Transport
Department of Roads
IDA Credit No. 3944-LA: Lao PDR; Road Maintenance Programme Phase 2 (RMP2);
Supplementary AusAID Grant to RMP2; TF093204
REVISED PROCUREMENT PLAN FOR PERIODIC MAINTENANCE PROGRAM - FY 2009/10 ON THE NRN & PRN
Revised Date: 7 Jan 2010
Component/ |  | Activities | Firm/ | Procurement |  |  | Cost Estimate | AusAID |  | RMF |  | Provincial Govt. |  | Remark
Sub-Component |  |  | Individual | Method | Review | Agency | in total (USD) | % | Amount | % | Amount | % | Amount
A |  | National Roads
| 1 | Spot Improvement of National Road 9 | Firm | NCB | Post | DPWT | 227071.4286 | 70% | 158950 | 30% | 68121.4286
B |  | Provincial Roads
| 1 | Periodic Maintenance on Prov. Road No.3204 | Firm | NCB | Post | DPWT | 101428.5714 | 70% | 71000 | 20% | 20285.7143 | 10% | 10142.8571
| 2 | Periodic Maintenance on Prov. Road No.3908 | Firm | NCB | Post | DPWT | 107142.8571 | 70% | 75000 | 20% | 21428.5714 | 10% | 10714.2857
| 3 | Periodic Maintenance on Prov. Road No.4502 | Firm | NCB | Post | DPWT | 214857.1429 | 70% | 150400 | 20% | 42971.4286 | 10% | 21485.7143
E |  | Contingencies |  |  | Prior | DoR |  | 100% | 50000
TOTAL: | [6 empty] | 650500 |  | 505350 |  | 152807.1429 |  | 42342.8571
AUD 1 = USD 0.8995
USD 1 = LAK 8,500

## NRN-Progress
Ministry of Public Works and Transport
Department of Roads
IDA Credit No. 3944-LA: Lao PDR; Road Maintenance Programme Phase 2 (RMP2);
Supplementary AusAID Grant to RMP2; TF093204
Progress of Contract Implementation
Updated: 9 April 2010
No | Contract Number | Road No | Works Length (km) | Section of Works |  | Province | Location | Type of Works | Estimation (USD) |  |  | Selling Rate 28 days be for Bid opening (Clause 14.2) | buying Rate 28 days be for Bid opening (Clause 14.2) | Contract Price |  | Variation Order | Total Contract price + Variation Order (LAK) | Contract Price (LAK) |  | Contractor's Name | Submission and Minister/Governor approval |  | Submission of Bid Evaluation Report to WB | Submission of Contract Document to WB | Contract Period | Letter of Acceptance Issued | Contract Signed | Expected Completion date | Actual Progress
[9 empty] | Total | Local | Foreign |  |  | (LAK) | (USD) |  |  | RMF | Foreign |  | Submission for approval | Approval | [6 empty] | Financial | Physicial
I | FY2008-2009 |  | 75 | [5 empty] | 1009917 | 302975.1 | 706941.9 |  |  | 8654742300 | 1018204.9765 | 0 | 8654742300 | 2596422690 | 6058319610 | [9 empty] | 99.58% | 100%
1 | SVK01-0809-PM-NR02 | 9 | 30 | 54+000 | 106+000 | Savanakhet | Seno-Vietnam Brd | Spot Rehabilitation | 617017 | 185105.1 | 431911.9 | 8514 | 8482 | 5332000000 | 627294.1176 |  | 5332000000 | 1599600000 | 3732400000 | Road No.8 State enterprise Company | N/A | 465/Gov,SVK, 15 May 2009 | 2009-03-13 | 2009-06-03 | 75 days | 2009-04-29 | 2009-05-18 | 2009-12-03 | 100% | 100%
2 | VTE01-0809-PM-NR03 | 11 | 45 | 130+000 | 204+000 | Vientiane | Sanakham-Khok khao do | Resealing | 350000 | 105000 | 245000 | 8499 | 8458 | 2959900000 | 348223.5294 |  | 2959900000 | 887970000 | 2071930000 | Panyathilat Road & Bridge Const,Co.,Ltd | N/A | 0378/Gov,VTE, 23 March 2009 |  |  | 120 days | 2009-03-23 | 2009-03-24 | 2009-12-23 | 99.83% | 100%
3 | VAR01-0809-PM-NR04 | 13N & 11 | N/A | NR 13N: Km 166+100 Houeyphong (VTE) & NR 11: Km 6+900 Nammoune; Km 13+500 Namsai; Km 20+700 Houey Ngang; Km 22+100 Houey Dane (VTC) |  | Vientiane Province and Vientiane Capital | Vientiane Brd-Luanpabang Brd; Sikhay Junct-Numsung Bridge | Bridge Repair | 42900 | 12870 | 30030 | 8499 | 8458 | 362842300 | 42687.3294 |  | 362842300 | 108852690 | 253989610 | Thavisok Road & Bridge Const,CoLtd | N/A | 0383/Gov,VTE, 23 March 2009 |  |  | 30 days | 2009-03-23 | 2009-03-24 | 2009-04-23 | 100% | 100%
II | FY2009-2010 |  | 1.18 | [5 empty] | 229519 | 68855.7 | 160663.3 |  |  | 1919063150 | 225772.1353 | 0 | 1919063150 | 575718945 | 1343344205 | [9 empty] | 0% | 100%
1 | SVK01-0910-PM-NR02 | 9 | 1.18 | Km 112+209 to Km 182+326 |  | Savanakhet | Ban Doneyang-Ban Phonxay | Spot Rehabilitation | 229519 | 68855.7 | 160663.3 | 8499 | 8473 | 1919063150 | 225772.1353 |  | 1919063150 | 575718945 | 1343344205 | Khounxay Pattana Construction Co.,Ltd | N/A | 245/Gov,SVK , 25 Feb 2010 |  |  | 120 days | 2010-02-10 | 2010-03-10 | 2010-06-10 | 0% | 100%
| Total |  | 76.18 | [5 empty] | 1239436 | 371830.8 | 867605.2 |  |  | 10573805450 | 1243977.1118 | 0 | 10573805450 | 3172141635 | 7401663815
| UAD 1 | = | 8500