## Sheet1
Appendix 6
KEY PROJECT PERFORMANCE INDICATORS
Arrangements for results monitoring
(Ref: Schedule 6 of Development Credit Agreement, IDA Cr. 3944-LA
for Road Maintenance Program-Phase 2 (RMP 2) between Lao PDR and IDA dated 27 August 2004)
No. | No. | Performance Indicators | Baseline | Annual Output |  |  |  |  | Accumulative Outcome | Data Source | Remarks
|  |  |  | 2004/05 | 2005/06 | 2006/07 | 2007/08 | 2008/09
I. |  | Outcome Indicators
1 | 1 | 80% of the national road network (network 7,233 km of which 3,530 km paved) remains in exellent to good condition | 73% |  |  | 85% | 83% | 83% |  | PTI | Survey has not been carried out for FY 2008/09
2 | 2 | 30% of the provincial road network (7,255 km) remains in good to fair condition. | 23% | 43% | 39% | 46% | 46% | 51% |  | LRD/DoR | RMP2
3 | 3 | Routine maintenance on at least 90% of the national road network is funded by domestic revenues | 80% |  | 86% | 82% | 82% | 91% |  | RAD/DoR | The progress for FY 08/09 increased to 91%
4 | 4 | Periodic maintenance and rehabilitation on at least 8% of the national road network is funded by domestic revenues. |  | 3% | 3% |  |  | 1% | 7% | RAD/DoR
5 | 5 | Routine maintenance on at least 90% of provincial road network is funded by domestic revenues |  |  |  |  | 58% | 80% |  | LRD/DoR | Only data of FY 08/09 of 17 provinces was provided by DPWTs during this reporting period. The Consultant (SweRoad) is now collecting the remaining data
6 | 6 | Periodic maintenance and rehabilitation on at least 8% of the provincial road network is funded by domestic revenues. |  | 2% | 4% |  | 2% | 2% | 10% | LRD/DoR
II. |  | Result Indicators
7 | 7 | 2,000 km of national road network are subject to periodic maintenance by the end of the Project |  | 778 km | 630 km |  | 216 km | 216 km | 1,974 km | RAD/DoR | No survey carried out in 2008-09
| 8 | 2,000 km of provincial road network are subject to periodic maintenance by the end of the Project. |  | 453 km | 948 km |  | 540 km | 373 km | 2,313 km | LRD/DoR | Work in FY 2008-09 under RMP2 but funded by AusAID
9 | 9 | Road maintenance fund annual revenue reaches LAK100bi by 30 September 2008 | LAK 34 bil. | LAK 55 bil. | LAK 81 bil. | LAK 121 bil. | LAK 151 bil. | LAK 206.52 | LAK 648.52 bil. | RMF | RMF disbursements limited by MPWT budget
10 | 10 | An integreted vehicle and driver registration system (VRDLS) to be established by 30 September 2006 | Estabished in one province |  |  |  | Pilot test is completed in December 2008 | VRDLS is under the process of approval |  | DoT | VRDLS to be trailed in 4 provinces
11 | 11 | Current level of compliance is retained (incidence of overloading exceeding 20% remains less than10% during the project implementation period. | 10% | 18% | 19% | 5% | 6% | 12.53 |  |  | For FY 08/09, data was provided by 16 provinces except Saravan where weigh scales have not yet been installed
12 | 12 | Road Safety audit mainstreamed for national road network by 30 September 2007 | Ongoing for one road |  |  | NR9 (savanaket) and NR3(Luangprabang and Bokeo) | R1 and 5 main roads in Vientiane Capital NR8 (Bolikhamsay) | Inventory (Kasi-Vernkham NR 13 |  | DoR | Changing of speed limit in community area to 50 km/h
13 | 13 | A program of hazardous location improvement is implemented, as per annual work program by September of each year | As per annual work program |  |  |  | Main roads in Vientiane capital | Installed guardrail NR8 200m at 4 location |  | DoT
14 | 14 | Performance levels in priority MPWT/DPWT functions attain the targets specified in the capacity building strategy by end of Project | To be established by Sept 2005
15 | 15 | Process of the project is kept within target of estimated cost (related to project implementation plan), every semester until the end of the Project | As per PIP |  |  |  |  | 64,127,266.25 USD |  | DD,PMD/DoR | Detail in Q4-Progress Report FY08/09 PDD/DoR
Source: MPWT
Key words RMF Road Maintenance Fund
Network
Budget