## Sheet1
Code | ACTIVITY | Unit | Qty | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
COMPONENT
1 | COUNSELLING, LEGAL ASSISTANCE AND SUPPORT SERVICES
OUTPUT
1.1 | Counselling and Support Services
ACTIVITIES
1.1.1 | Centre-based counselling | counselling | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
1.1.2 | Mobile counselling on Efate & during | counselling | 17 | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
CAVAW visits
1.1.3 | Referrals & follow-up with other | support | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
agencies (custom courts, police, courts & medical)
1.1.4 | Weekly counsellor meetings | meetings | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
1.1.5 | Record client cases | records | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
1.1.6 | Client Support Fund | finance | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
1.1.7 | Safe House (funded by NZAID) | counselling | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
OUTPUT
1.2 | Legal Assistance
ACTIVITIES
1.2.1 | Provide information to clients on laws, | counselling | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxxx
| Police procedures, Court Orders & Courts | info
1.2.2 | Documentation for Police & Courts | legal assist | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxxx
1.2.3 | Lawyer accompanies/represents clients in | legal | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxxx
| Court | assistance
1.2.4 | Legal assistance with out of court | legal | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxxx
| settlements | assistance
1.2.5 | Court Fees Fund | legal assist | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxxx
OUTPUT
1.3 | Counsellor Training
ACTIVITIES
1.3.1 | Annual counsellor training in Vila | training | 2 | Oct: xxx; Jan: xxx
1.3.2 | Counsellor training attachment overseas | training | 1 | Oct: xxx
1.3.3 | In-house counsellor training | training | 3 | Aug: xxx; Nov: xxx; Jan: xxx
Code | ACTIVITY | Unit | Qty | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
COMPONENT
2 | BRANCHES AND CAVAWs
OUTPUT
2.1 | SCC Branch Activities (SCC funded by NZAID)
ACTIVITIES
2.1a | SCC Counselling and Support Services
2.1.1 | Counselling (centre-based, mobile & phone) | counselling | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
& referrals to VWC
2.1.2 | Referrals & follow-up with other | support | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
agencies (custom courts, police, courts & medical)
2.1.3 | Weekly counsellor meetings | meetings | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.4 | Record client cases | records | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.5 | Provide information to clients on laws, | counselling | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| Police procedures, Court Orders & Courts | info
2.1.6 | Documentation for Police & Courts | legal assist | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.7 | Court Fees Fund | legal assist | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.8 | Client Support Fund | finance | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1b | SCC Community Education, Awareness and CAVAWs
2.1.9 | Community awareness talks & workshops | CA | 6 | July: xxx; xxx Aug: xxx; xxx Sep: xxx; xxx Oct: xxx; xxx Mar: xxx
2.1.10 | Special events campaigns (SCC 6 per year) | campaigns | 6 | July: xxx; xxx Aug: xxx; xxx Sep: xxx; xxx Nov: xxx; xxx Dec: xxx; xxx Mar: xxx; xxx May: xxx
2.1.11 | Radio programs (SCC 40 per year) | CA | 40 | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.12 | Library | library | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.13 | Networking with & ongoing support to | network | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| CAVAWs for counselling, community | support
awareness, legal assistance & networking with local agencies
2.1.14 | Monitor implementation & enforcement of | monitoring | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
DV/FP court orders & the FPO Act
2.1.15 | Follow up male advocates | monitoring | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.16 | Data collection (M&E framework, police, | data | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
health & correctional centres)
Code | ACTIVITY | Unit | Qty | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
2.1c | SCC Branch Management
2.1.17 | Staff collective meetings | meetings | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.18 | Staff performance reports (SCC 1 per year) | review | 1 | Jun: xxx
2.1.19 | Local staff training (in Santo) | training | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.20 | Annual audits of SCC included with VWC. | audits | 1 | July: xxx; Aug: xxx; Sep: xxx
2.1.21 | Network with provincial government, | network | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
community leaders & CSOs
2.1.22 | Monthly reports to VWC (SCC 12 per year) | reports | 12 | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.23 | NZAID/SCC/VWC development of next | planning | 1 | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
phase of funding
2.1.24 | SCC Project Completion Report | report | 1 | Apr: xxx
Code | ACTIVITY | Unit | Qty | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
2.1 | TCC Branch Activities (TCC funded in this program by AusAID)
ACTIVITIES
2.1a | TCC Counselling and Support Services
2.1.1 | Counselling (centre-based, mobile & phone) | counselling | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
& referrals to VWC
2.1.2 | Referrals & follow-up with other | support | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
agencies (custom courts, police, courts & medical)
2.1.3 | Weekly counsellor meetings | meetings | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.4 | Record client cases | records | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.5 | Provide information to clients on laws, | counselling | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| Police procedures, Court Orders & Courts | info
2.1.6 | Documentation for Police & Courts | legal assist | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.7 | Court Fees Fund | legal assist | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.8 | Client Support Fund | finance | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1b | TCC Community Education, Awareness and CAVAWs
2.1.9 | Community awareness talks & workshops | CA | 6 | July: xxx; Aug: xxx; Sep: xxx; Oct: xxx; Dec: xxx; Jan: xxx
2.1.10 | Special events campaigns (TCC 5 per year) | campaigns | 5 | July: xxx; Sep: xxx; Nov: xxx; Dec: xxx; Mar: xxx; xxx May: xxx
2.1.11 | Radio programs | CA | 24 | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.12 | Library | library | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.13 | Networking with & ongoing support to | network | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| CAVAWs for counselling, community | support
awareness, legal assistance & networking with local agencies
2.1.14 | Monitor implementation & enforcement of | monitoring | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
DV/FP court orders & the FPO Act
2.1.15 | Follow up male advocates | monitoring | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.16 | Data collection (M&E framework, police, | data | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
health & corrections)
2.1c | TCC Branch Management
2.1.17 | Staff collective meetings | meetings | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.18 | Staff performance reports (TCC 1 per year) | review | 1 | xxx Jun: xxx
2.1.19 | Local staff training (in Tanna) | training | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.20 | Annual audits included with VWC | audits | 1 | July: xxx; Aug: xxx; Sep: xxx
2.1.21 | Network with provincial government, | network | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
community leaders & CSOs
2.1.22 | Monthly reports to VWC (TCC 12 per year) | reports | 12 | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
Code | ACTIVITY | Unit | Qty | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
2.1 | Torba Branch Activities (funded in this program by AusAID)
ACTIVITIES
2.1a | Torba Counselling and Support Services
2.1.1 | Counselling (centre-based, mobile & phone) | counselling | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
& referrals to VWC
2.1.2 | Referrals & follow-up with other | support | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
agencies (custom courts, police, courts & medical)
2.1.3 | Weekly counsellor meetings | meetings | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.4 | Record client cases | records | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.5 | Provide information to clients on laws, | counselling | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| Police procedures, Court Orders & Courts | info
2.1.6 | Documentation for Police & Courts | legal assist | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.7 | Court Fees Fund | legal assist | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.8 | Client Support Fund | finance | cont | July: xxx; Aug: xxx; Sep: xxx; Oct: xxx; Nov: xxx; Dec: xxx; Jan: xxx
2.1b | Torba Community Education, Awareness and CAVAWs
2.1.9 | Community awareness talks & workshops | CA | 6 | July: xxx; Aug: xxx; Sep: xxx; Oct: xxx; Feb: xxx; Mar: xxx
2.1.10 | Special events campaigns (5 per year) | campaigns | 5 | xxx | xxx | xxx | xxx |  |  |  | xxx | xxx | xxx |  | xxx
2.1.11 | Radio programs | CA | no activity
2.1.12 | Library | library | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.13 | Networking with & ongoing support to | network | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| CAVAWs for counselling, community | support
awareness, legal assistance & networking with local agencies
2.1.14 | Monitor implementation & enforcement of | monitoring | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
DV/FP court orders & the FPO Act
2.1.15 | Follow up male advocates | monitoring | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.16 | Data collection (M&E framework, police, | data | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
health & corrections)
2.1c | Torba Branch Management
2.1.17 | Staff collective meetings | meetings | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.18 | Staff performance reports (1 per year) | review | 1 | Jun: xxx
2.1.19 | Local staff training (in Torba) | training | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.1.20 | Annual audits included with VWC | audits | 1 | July: xxx; Aug: xxx; Sep: xxx
2.1.21 | Network with provincial government, | network | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
community leaders & CSOs
2.1.22 | Monthly reports to VWC (12 per year) | reports | 12 | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
Code | ACTIVITY | Unit | Qty | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
OUTPUT
2.2 | VWC Support to Branches (SCC funded by NZAID and TCC funded in this program by AusAID)
ACTIVITIES
2.2.1 | Monitoring visits to Branches | support/tr'g | 6 | Aug: SCC; Sep: ToCC; Nov: TCC; Jan: TCC; Mar: SCC; May: ToCC
2.2.2 | Legal training visits to Branches | training | 4 | Sep: SCC; Nov: ToCC; Dec: TCC; Apr: ToCC
2.2.3 | Branch attachments to VWC | training | 6 | Sep: ToCC; Nov: all; Dec: all; Jan: SCC; Apr: all; May: all
2.2.4 | Ongoing counselling support, training & | training | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| supervision & referrals from Branches | monitoring
2.2.5 | Ongoing support for Branch community | training | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| awareness activities | monitoring
2.2.6 | Ongoing training & support in centre | training | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| management | monitoring
2.2.7 | Financial management & training | monitoring | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.2.8 | Training & support in data collection | training | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
Code | ACTIVITY | Unit | Qty | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
OUTPUT
2.3 | CAVAW Activities
ACTIVITIES
2.3.1 | Counselling & referrals to VWC & Branches | counselling | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.3.2 | Provide information to clients on laws, | counselling | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| Police procedures, Court Orders & Courts | info
2.3.3 | Documentation for Police & Courts (some | legal | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| CAVAWs only) | assistance
2.3.4 | Monitor implementation & enforcement of | monitoring | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
DV/FP court orders & the FPO Act
2.3.5 | Community awareness & special events | CA | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.3.6 | Follow up male advocates | monitoring | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.3.7 | Network with provincial government, local | network | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
community leaders & CSOs
2.3.8 | CAVAW collective meetings | meetings | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.3.9 | Data collection & annual reports to VWC | reports | 1 | Aug: xxx
OUTPUT
2.4 | VWC Support to CAVAWs
ACTIVITIES
2.4.1 | CAVAW training visits & male leaders wkshps | training | 6 | Aug: xxx; Sep: xxx; Oct: xxx
2.4.2 | Legal training & assistance visits | training | 3 | Aug: xxx; Sep: xxx; Nov: xxx
2.4.3 | Annual CAVAW training | training | 1 | Aug: xxx
2.4.4 | Attachment of CAVAWs to VWC | training | 4 | Aug: xxx; Nov: xxx
2.4.5 | CAVAWs to FWCC Regional Training Prog | training | 3 | Oct: xxx
(3 each per yr from AusAID & NZAID funds)
2.4.6 | Monitor CAVAW Activities Fund | monitoring | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
2.4.7 | CAVAW Honorariums | finance | 1 | Aug: xxx
2.4.8 | Update CAVAW manual | manual | 1 | July: xxx; Aug: xxx; Sep: xxx; Oct: xxx; Nov: xxx; Dec: xxx
2.4.9 | Ongoing support to CAVAWs for | support | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| counselling, community awareness, legal | training
| assistance & networking with local agencies | monitoring
2.4.10 | Establish Torba Branch | branch | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
Code | ACTIVITY | Unit | Qty | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
COMPONENT
3 | COMMUNITY EDUCATION AND AWARENESS
OUTPUT
3.1 | Community Awareness
ACTIVITIES
3.1.1 | Initiate & respond to requests for talks | talks | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| & workshops | workshops
3.1.2 | National Conferences on violence against | plan, review | 1 | Nov: xxx
women
3.1.3 | Radio programs | CA | 40 | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
3.1.4 | Special events campaigns | campaigns | 5 | July: xxx; Sep: xxx; Nov: xxx; Dec: xxx; Mar: xxx; May: xxx
3.1.5 | Media campaigns | campaigns | 5 | July: xxx; Sep: xxx; Nov: xxx; Dec: xxx; Mar: xxx; May: xxx
3.1.6 | Update/reprint VWC brochure | brochure | no activity
3.1.7 | Produce newsletters | n/letters | 4 | Sep: xxx; Dec: xxx; Mar: xxx; Jun: xxx
3.1.8 | Produce CE & legal literacy materials | materials | 9 | July: xxx; Aug: xxx; Oct: xxx; Nov: xxx
3.1.9 | Review of IEC'S | review | no activity
3.1.10 | Dissemination of Research findings | research | 1 | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
OUTPUT
3.2 | DATA COLLECTION AND RESEARCH
ACTIVITIES
3.2.1 | Data collection & analysis (implement | statistics | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
| monitoring & evaluation framework) | analysis
3.2.2 | Baseline research on prevalence, incidence | research | 1 | July: xxx; Aug: xxx; Sep: xxx; Oct: xxx; Nov: xxx
| & community attitudes on violence against | analysis
women & children
3.2.3 | Research on custom, violence against | planning for | 1 | Jan: xxx; Feb: xxx; Mar: xxx; Apr: xxx; May: xxx; Jun: xxx
| women & children, & women's human rights | research
3.2.4 | Client feedback surveys | research | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
3.2.5 | Research on economic cost of Violence against women. | research | 1 | Jan: xxx; Feb: xxx; Mar: xxx; Apr: xxx; May: xxx; Jun: xxx
Code | ACTIVITY | Unit | Qty | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
COMPONENT
4 | LEGAL ADVOCACY, LOBBYING AND HUMAN RIGHTS TRAINING
OUTPUT
4.1 | Legal and human rights advocacy
4.1.1 | Monitor the implementation & enforcement | monitor | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
of the Family Protection Order Act & Domestic
Violence/Family Protection Court Orders
4.1.2 | Lobby with other agencies to ensure that | lobby | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
international human rights commitments are
included in national legislation
4.1.3 | Monitor government's implementation of | monitor | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
international commitments to human rights
& gender equality (CEDAW, CRC, DEVAW)
4.1.4 | Gender relations, violence & human rights | training | 1 | Oct: xxx
training for other agencies
OUTPUT
4.2 | Male Advocacy on Women's Rights
ACTIVITIES
4.2.1 | Male advocacy training & workshops | training | 2 | Sep: xxx; Feb: xxx
4.2.2 | Follow up & monitoring of male advocates | monitoring | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
Code | ACTIVITY | Unit | Qty | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
COMPONENT
5 | MANAGEMENT AND INSTITUTIONAL STRENGTHENING
OUTPUT
5.1 | Organisational Management
ACTIVITIES
5.1.1 | Staff performance reports | review | 1 | Jun: xxx
5.1.2 | Annual staff training retreat | training | 1 | Sep: xxx
5.1.3 | Legal literacy training for VWC/Branch staff | training | 1 | Aug: xxx
5.1.4 | Staff training | training | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
5.1.5 | Annual audit | audit | 1 | July: xxx; Aug: xxx; Sep: xxx; Oct: xxx
5.1.6 | Management committee meetings | meetings | 4 | Sep: xxx; Dec: xxx; Apr: xxx; Jun: xxx
5.1.7 | Staff Collective Meetings | meetings | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
5.1.8 | Networking locally & internationally | network | cont | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
5.1.9 | Annual public meeting | meetings | 1 | May: xxx
OUTPUT
5.2 | Program Management
ACTIVITIES
5.2.1 | Monitoring visits by FWCC | monitoring | 2 | Dec: xxx; May: xxx
5.2.2 | Progress Reports | reports | 1 | Dec: xxx
5.2.3 | Program Coordination Committee meetings | PCC | 2 | Jan: xxx; Jun: xxx
5.2.4 | Annual Plans (planning, review of design, | plan | 1 | May: xxx
| risk management & M&E frameworks) | review
5.2.5 | Joint VWC/AusAID/NZAID Review | review | no activity
5.2.6 | Planning for next phase of funding | plan | 1 | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx | xxx
5.2.7 | Project Completion Report | report | 1 | Apr: xxx
OUTPUT
5.3 | VWC Building
ACTIVITIES
5.3.1 | Develop proposal for permanent premises | proposal | 1 | Aug: xxx; Nov: xxx
5.3.2 | Transfer to new building |  | no activity
Note on B73: user: