
Australia-Pacific Technical College

Stage II Design

Annexes
25 November 2010
Annexes
	A
	APTC Stage II Design Terms of Reference
	1

	B
	People and Organisations Consulted
	27

	C 
	Reference Documents 
	32

	D 
	Pacific TVET Context 
	34

	E
	APTC Draft 2010/11 Course Profile
	46

	F
	APTC Stage II Scholarship Policies and Procedures
	56

	G
	APTC Stage I Cost Structure Analysis 
	67

	H
	APTC Stage I Cost Benefit Analysis
	82

	I 
	APTC Stage II Implementation Schedule
	99

	J
	APTC Stage II Reporting Plan
	102

	K 
	APTC Stage II Performance Assessment Framework
	104

	L
	Draft Job Descriptions for APTC Chief Executive Officer and School Director roles
	123

	M 
	APTC Stage II Education Management Information System High-Level Requirements
	126

	N
	Draft APTC Stage II Fee for Service Policy
	128

	O 
	APTC Stage II Budget Estimates
	130

	P
	APTC Stage II Risk Management Matrix
	131

	Q
	Draft TOR for Feasibility Study for delivering APTC training in the SoIomon Islands
	146

	R
	APTC Stage III Scoping Study Considerations
	153

	S
	APTC Stage II Scope of Services
	155

	T
	APTC Stage II Basis of Payment
	182


Annex A: Terms of Reference

1. Guiding Statement

AusAID is undertaking a design process for Stage II of the Australia Pacific Technical College (APTC), which is scheduled to operate over four years, commencing in July 2011 and finishing in June 2015. 

Australia is committed to long-term support for the APTC – subject to ongoing demand for its services and its continued good performance. Stage II is conceived as a transition stage in which the benefits of APTC Stage I are to be sustained, extended and enhanced alongside making changes that will create a conducive environment for Stage III (2015 and beyond).

Over the course of the next four years, Australia would like the APTC to develop in the following ways.

(a)
Maintain a clear focus on the delivery of quality assured Australian qualifications in areas of demonstrated regional demand at Australian Certificate III and IV levels.
 

(b) 
Enhance the contribution of the APTC to Pacific regional integration while complementing national skills development efforts.

(c)
Become more efficient, effective and sustainable.

(d)
Expand the scope, accessibility and flexibility of its training services and assure their quality.

(e)
Support the proposed longer-term transition of the APTC from a wholly Australian owned training provider to one which is jointly owned by Australia and other interested Pacific Island countries, donors and possibly other stakeholders. 

AusAID wishes to engage a design team comprising a range of specialists to assist the agency to define the steps that will be necessary to meet these objectives. 

2. Background

The Australia-Pacific Technical College (APTC) is an innovative development program intended to facilitate regional economic growth and labour mobility through demand-driven and quality-assured technical and vocational skills development. 
The Australian Government made an initial commitment to the establishment of a technical college for the Pacific in October 2005. In October 2006, the Government announced a proposal for the development of the APTC to assist skills development in the Pacific with an initial allocation of AUD$149.5 million over four years.
 
Leaders of the Pacific Islands Forum (PIF) supported the proposal and expected it to make a significant contribution to developing a skilled and competitive Pacific workforce.
 The first students commenced in July 2007, with a target of 3,000 graduates with Australian vocational qualifications by June 2011.

The APTC was established to achieve three Goals:
(a) 
Training: Increased supply of skilled workers in targeted sectors in the Pacific region.

(b) 
Employment: Pacific Islander women and men with Australian qualifications realise improved employment opportunities nationally, regionally and internationally in targeted sectors.

(c) 
Productivity: Increased productivity of individuals and organisations in targeted industries and sectors.

The Purpose of the APTC is to:

(a) 
provide Pacific Islander women and men with Australian qualifications that present opportunities to be able to find employment in targeted sectors nationally and internationally; and

(b) 
support skills development in the Pacific in response to labour market requirements. 

AusAID contracted three organisations to implement the APTC over four years (2007-2011). 

(a)
Two Australian Registered Training Organisations (RTOs) provide APTC training and assessment services and award Australian qualifications. These RTOs established and currently manage the five Schools of the APTC within the policies and frameworks established by the APTC and within boundaries established by AusAID. 
· Box Hill Institute of TAFE (BHIT) manages the School of Tourism and Hospitality (STH) and the School of Health and Community Services (SHCS).
· Sunshine Coast Institute of TAFE (SCIT) manages the Schools of Automotive, Construction & Electrical and Manufacturing (SACEM).

(b)
A Managing Contractor (Sinclair Knight Merz - SKM) manages the APTC Coordination Office (CO) in Nadi. The mandate of the CO is to assist the APTC General Manager and the Schools achieve the APTC goals and purpose by providing college-wide coordination and services, monitoring and evaluating APTC performance, management of the APTC Scholarships scheme and a unified College identity and marketing of services. 
An APTC Advisory Group, chaired by AusAID, has been established, with membership drawn from eight Pacific island Countries (PICs) and Australia, and from both industry and government organisations. Its principal responsibility is to provide advice to AusAID on a range of industry and TVET issues in the Pacific region including the overall strategic direction of the APTC, APTC policy directions and on future demand for TVET in the region. 
APTC follows a flexible, results-oriented approach to the direct delivery of primarily Australian Certificate III and IV training to clients - defined as employers (private and public) and individual students. APTC training is open to all 14 Pacific Island Forum (PIF) developing countries, and is currently delivered in workplaces and institutions in four campus countries – PNG, Fiji, Vanuatu and Samoa. All APTC training facilities have been established in partnership with either local firms or local training institutions. 
Students enter the APTC as fee-paying, employer sponsored or scholarship students. A AUD$10m Scholarships Program was established within APTC to facilitate participation by students from non-campus countries, particularly small island states. As at December 2009, 1,468 students (60% of enrolments) have received a scholarship to study at the APTC. Twenty three percent of these scholarship students are from non-campus countries. Of the APTC’s student intake to date, 15% is from non-campus countries. 
3. APTC Progress – Assessments to Date

3.1 Mid-term Review

A mid-term review (MTR) of the APTC was conducted in the first half of 2009. It concluded that in a relatively short space of time, the APTC had found a unique and respected niche at the middle to top end of the regional vocational skills supply chain by providing quality-assured Australian training that meets the productivity demands of employers and bridges the gap between national and international standards. It found that the APTC was performing well against its goals and key results areas, and was yielding both anticipated and unanticipated benefits for individuals, firms and for national training institutions. It recommended the continuation of the APTC beyond June 2011 and that Pacific regionalism was, and should remain a touchstone for the APTC in the future.

It made a range of recommendations grouped into four broad change strategies.

(a)
Make operational improvements to achieve greater efficiency and effectiveness.

(b)
Enhance the contribution of the APTC to Pacific regional integration.

(c)
Expand the scope and reach of APTC training and assure its quality and sustainability.

(d)
Commit to engaging in a broad-based discussion with Pacific stakeholders over the next 2-3 years about the long-term structure and governance of the APTC.

3.2 Pacific Heads of Education

The annual Pacific Heads of Education meeting (Nadi, 4 November 2009) discussed the progress and future of the APTC. AusAID, NZAID and the Pacific Islands Forum Secretariat participated in this discussion. Consensus was that the APTC is filling a critical gap in service provision, as it provides a significantly higher quality of training than previously available in the region. In addition, the APTC is having a positive demonstration effect on national training institutions. The disparity of resources available to the APTC in comparison to national institutions was noted as a concern. Without exception, the Pacific Heads of Education strongly urged Australia to continue the APTC.

3.3 APTC Advisory Group

The APTC Advisory Group discussed the future directions of the APTC at their fourth meeting in Nadi on 27 - 28 August 2009. The Group noted the major benefits of the APTC as the quality of training delivered and the confidence members have in the capacity and professionalism of the current RTOs. The Advisory Group strongly supported the MTR’s recommendation that the APTC continue beyond 30 June 2011.

4. Context

4.1 Pacific Labour Markets and Skills Development

The Pacific Island Countries (PICs) differ in their access to natural resources, geography, population and level of economic development but their labour markets share several characteristics.

(a)
There is a mismatch between training supply and the demand for skilled labour. Although there are relatively skilled and qualified workers across the Pacific, the majority of PICs have a shortage of adequately skilled people and an oversupply of unskilled workers. Expatriate workers (including Australians and New Zealanders) fill many skilled positions. These skills shortages and mismatches affect all sectors of the economy and constrain labour productivity, economic growth and the employment of nationals in available skilled jobs. 
(b)
Most PICs are labour surplus countries, with few immediate prospects for providing cash work within the domestic economy for all those who seek it. Private sector growth will not create enough jobs for the large number of school leavers entering the labour market each year and with few marketable skills, many young people are under-employed in informal or subsistence work or openly unemployed. 
(c)
Emigration is on the rise. Prompted by the lack of economic opportunities and insecurity in many PICs, more people are emigrating to countries such as Australia, New Zealand, and United States to find work. While their remittances comprise a high proportion of GDP in many countries of the Pacific and have generally positive impacts, continuing out-migration contributes to widespread skills shortages and discourages some employers from investing in training. 
Many PICs increasingly see improved skills training, accredited nationally or internationally, as one solution to such labour market issues. An increasing number of national education plans are including TVET as a priority sub-sector, in recognition of the importance of employability outcomes for school leavers and private sector productivity for economic growth. However, progress on this front has been slow. Few PICs have clear strategies, long-term plans or resources available to establish effective skills development systems. Quality-assured national skill standards or externally recognised qualifications are rare. Available training is supply-driven and often of low or variable quality. Access to skills development is uneven and favours males in urban areas. With a few exceptions, employer inputs to the direction, content, quality or financing of the skills development system are minimal. 
4.2 Regional Policies and Priorities

In October 2005, the Pacific Island Forum Leaders endorsed the Pacific Plan with the goal of enhancing and stimulating economic growth, sustainable development, good governance and security for Pacific countries through regionalism. It encompasses increased regional service provision as well as market integration. It emphasises the need to strengthen and expand national and, where appropriate, regional vocational educational and training programs and strengthening their links with the labour market. To promote regional integration, the Pacific Plan calls Forum members to: [integrate] trade in services, including temporary movement of labour, into the Pacific Island Countries Trade Agreement (PICTA).

At their meeting in August 2009, Forum Leaders launched negotiations for a new regional trade and economic agreement, known as PACER Plus. Australia is motivated to support PACER Plus because it believes it will help the Forum Island Countries promote their own sustainable economic development. The negotiation of a new regional trade and economic agreement offers opportunities to create jobs, enhance private sector growth, raise standards of living and boost long-term economic growth in Forum Island Countries. On the framework for the PACER Plus negotiations, Forum Trade Ministers agreed in October 2009 that during the preliminary stage of negotiations, within the next 12 months, members would focus on deepening understanding of common priority issues including, inter alia, Regional Labour Mobility beyond Mode 4,
 and discuss other priority issues including Education. Australian Ministers have stated clearly that PACER Plus will include skills development for Pacific Islanders, equipping them for technical work both within the region and globally.

... there is great potential to develop a region wide labour mobility and skills development program for the Pacific, particularly when you think about the large infrastructure projects within the region that are about to come on stream-the PNG LNG project, for example; the Australian Solomons Goldmine, as another example; and the defence initiated infrastructure build-up in Guam.

As regional integration gathers momentum in coming years, the temporary and permanent movement of skilled workers between PICs and from the PICS to Australia, New Zealand, USA and elsewhere will increase. This will particularly affect the skills base of labour exporting countries (‘brain drain’). Labour importing countries such as Australia and New Zealand will need to share the costs of training the skilled labour it imports from the Pacific by helping those countries continuously replenish their own skills pool for both national and international labour markets. 
The Pacific Education Development Framework (PEDF), endorsed by the Forum Education Ministers in 2009, guides the further development of Pacific education. The PEDF is aligned with, and grounded in, the principles of the Pacific Plan and reflects the Pacific concept of regionalism where countries work together for their joint and individual benefit.
 It addresses two broad agendas: (i) the Education for All (EFA) or basic education agenda, and (ii) the training/ employment/economic agenda. The TVET outcome sought is that ...the supply of skills supplied by Pacific TVET systems responds to meet the needs of the informal sector and the changing labour market demands in the formal sector.
4.3 AusAID’s Policy Framework

The Australian Government recognises the power of education as an investment that helps individuals achieve their potential and societies to be stronger and more productive. The poor quality of local education and higher education institutions can undermine gains in building local capacity, income generation, social stability and national development. The Government aims to make further growth in education assistance the centrepiece of Australia’s Official Development Assistance strategy.

Within the Pacific region, AusAID provides development assistance to both formal and non-formal TVET including support for the TVET architecture (policy, planning and organisational development), for local capacity development and for training delivery. 
At the national level, the Pacific Partnerships for Development includes support for economic growth, basic education and for skills development. Almost all such Partnerships identify basic education and technical and vocational education as initial partnership priorities and many have implementation strategies that relate specifically to strengthening TVET (Kiribati, Tonga, Vanuatu and Samoa). The PNG Program is planning to develop an implementation strategy for TVET and AusAID is providing some support to Tuvalu’s TVET system.

At the regional level, Australia’s assistance to education focuses mainly on supporting the development of a Pacific Qualifications Register by the South Pacific Board of Educational Assessment and supporting direct training delivery through the APTC.

AusAID’s draft Pacific Education and Training Agenda  recognises that there are links between the quality and equity of basic education and the impact of higher education and training. It also recognises the potential of the APTC to lead the region in respect to higher level technical and vocational training, while Australia’s bilateral programs strengthen viable local institutions to meet local labour demand and to provide suitable pathways into higher training via the APTC or other national or regional providers. The APTC contributes to achieving the performance target of the draft Framework aimed at increasing the employability of Pacific Islanders and to strengthening post-secondary professional, technical and vocational education and training across the region.

5. Scope of Services
Over the course of the next four years, Australia would like the APTC to develop in the following ways, subject to available resources and demand. The design should incorporate strategies for achieving the following objectives in Stage II.

(a)
Maintain a clear focus on the delivery of quality assured Australian qualifications in areas of demonstrated regional demand at Australian Certificate III and IV levels.
 

(b) 
Enhance the contribution of the APTC to Pacific regional integration by:

(i)
strengthening its linkages with AusAID bilateral programs and AusAID regional education and training strategies;

(ii)
continuing to partner with the private sector as well as with public training institutions and strengthen both types of training partnerships; and

(iii)
identifying new opportunities for the APTC to contribute to labour mobility and regional trade strategies as they evolve.

(c)
Become more efficient, effective and sustainable by:

(i)
expanding and diversifying the APTC’s revenue base through increasing:

· fee for service activities in ways which do not displace the APTC’s core development and equity objectives; 
· the number of fee-paying students in ways consistent with equity principles; and
· the number of employer-sponsored students at APTC;
(ii)
achieving a range of operational efficiencies, including reduction over time in the unit costs of training delivery; 

(iii)
achieving greater coherence in APTC management arrangements and organisational systems, including the APTC Scholarship management system; and

(iv)
annual public reporting of results against a robust set of business indicators.

 (d)
Expand the scope, accessibility and flexibility of APTC training and assure its quality by:

(i)
establishing a demand-based training profile which is affordable and equitable;

(ii)
ensuring equity and access in APTC delivery by:
· increasing access to the APTC from non-campus countries, possibly through the introduction of targeted bridging programs; 

· achieving gender equity in student enrolments and APTC graduates; and
· increasing the opportunities for people with a disability to access APTC;

(iii)
implementing more flexible learning strategies where appropriate and feasible;

(iv)
if feasible, establishing an APTC campus in the Solomon Islands; 

(v)
if feasible, expanding APTC training delivery in PNG commensurate with its size, geography and projected economic growth;
(vi)
expanding the School of Health and Community Services;

(vii)
increasing the contribution of the APTC to the development of the TVET workforce in the Pacific by establishing an APTC School of Professional Development, thus complementing the strategies of AusAID and other donors to improve national capacity to deliver entry-level TVET (Certificate I and II levels) which articulates with APTC and other regional programs; and
(viii)
assuring the APTC’s quality through internal quality improvements and external training audit.

(e)
Support the proposed longer-term transition of the APTC from a wholly Australian owned service provider to one which is jointly owned by Australia, other interested Pacific Island countries, donors and possibly other stakeholders by:
(i)
establishing business-oriented organisational governance and management arrangements for APTC Stage II;

(ii)
creating opportunities for other donors to engage with and/or contribute to the development of the APTC; and

(iii)
creating opportunities for regional private sector firms with a commitment to quality training to engage with and/or contribute to the development of the APTC.

6. Design Mission Objective

AusAID is mobilising a design mission to develop a high quality, cost-effective design for Stage II of the APTC consistent with the Concept Note at Attachment 1 that:

(a) 
will achieve Australia’s objectives as outlined in Sections 1 and 5 above; and 
(b)
provides sufficient flexibility in implementation for APTC to respond to AusAID decisions arising from a separate investigation into options for the future structure of the APTC beyond 2015, which will be undertaken concurrently with the start up of Stage II of the APTC.

7. Design Methodology

7.1 Preparation phase

Because of the significance of this design to AusAID’s Pacific aid program, the preparation phase will be comprehensive and quality assured, involving the following.

(a)
Documentation review. Team members will become familiar with the key reference documents identified in Attachment 2. Initial intra-team discussions will be conducted as necessary via phone/teleconference. 
(b)
AusAID briefing sessions. All team members will participate in a 2-day face-to-face briefing in Canberra to be conducted by AusAID managers; Program Manager, APTC, AusAID Suva; AusAID Pacific education advisers and Current APTC contractors (SKM, Box Hill Institute, Sunshine Coast Institute).
Outputs of preparation phase

Output 1: A brief Inception Note of no more than eight pages (including a comprehensive mission work plan) that reflects the team’s understanding of AusAID’s expectation and of the policy and planning context for the design as well as the data collection and stakeholder consultations required. 
7.2 Fieldwork and Data Collection Phase

The team will consult widely to gather the data and information needed to inform the design. The team will not operate as a whole group during this phase, but different members will work either individually or in sub-teams.

(a)

Fieldwork in Fiji. The Team Leader and the Design Specialist will travel to Fiji to consult with AusAID Suva (which manages the APTC program), the APTC Coordination Office, regional organisations (such as PIFS, SPBEA and the Pacific Islands Private Sector Organisation - PIPSO), and regional offices of other donors and multilaterals with an interest in skills development and labour mobility (including ADB, ILO and NZAID).

(b)
Fieldwork in PNG. The Team Leader, the TVET Specialist and the Education Economist will travel to PNG to identify how Stage II design could better serve the skill needs of PNG, and to test whether the MTR’s recommendation to expand provision in PNG is desirable and feasible. If so, then an initial scoping and costing of the proposed expansion will be undertaken by these members. Key stakeholders to be consulted include the Government of PNG,), AusAID Post, firm and industry representatives, training providers (public and private), the PNG member of the APTC Advisory Group, APTC staff and other donors and multilaterals with an interest in skills development and labour mobility.

(c)
Fieldwork in Solomon Islands. The Team Leader, the TVET Specialist and the Education Economist will then travel to Solomon Islands to undertake an initial study of the feasibility of establishing a new campus in the Solomon Islands in partnership with the Solomon Islands College of Higher Education (SICHE), as recommended by the MTR. If it proves feasible, then the scope and cost of a proposed new campus will be established. Key stakeholders to be consulted include representatives of the Government of Solomon Islands, AusAID Post, major employers, SICHE and other donors and multilaterals with an interest in skills development and labour mobility.

(d)
Consultations with key regional informants (by phone) from home base. Individually or severally, the team will consult with regional members of the APTC Advisory Group and other regional organisations as needed to obtain their inputs to the Stage II design. 
(e)
Consultations with key national informants (by phone or in person) from home base. Individually or severally, the team will consult with Australian members of the APTC Advisory Group and other informants as needed to obtain their inputs to the Stage II design.

(f)
Data collection and analysis. Individual members of the team, especially the Scholarship and Design Costing Specialist, the TVET Finance Specialist and the Education Economist will collect and analyse the technical data needed to deliver their specialist inputs to the design. The TVET Finance Specialist and the Education Economist will need to undertake a joint visit the Sunshine Coast Institute and SKM in Brisbane and Box Hill Institute in Melbourne to discuss cost and other data requirements and, in the case of the Education Economist, available data on benefits. The Scholarship and Design Costing Specialist will need to liaise closely with the APTC Coordination Office in Suva.
Outputs for fieldwork phase

Output 2: A brief note on key issues arising from the consultations to date and the fieldwork that will serve as a debriefing to AusAID following completion of the fieldwork.
7.3 Report writing, review and finalisation phase

(a)
Team retreat to consolidate individual and team findings and prepare Design Outline. This two-day retreat, to be held in Canberra, will provide an opportunity for all members of the team to come together to pool their insights, structure their findings, agree the strategic directions for the design and prepare an outline of the Design Document.

(b)
AusAID-design team workshop: The team will present its findings, proposed directions and a draft Design Outline to AusAID. Through discussion, the Design Outline will be amended if/as needed and agreed between the Design Team and AusAID.

(c)
Preparation of Draft Design Document. The design document will be prepared by the team in accordance with AusAID’s requirements as outlined in Attachment 3. All members of the team will contribute written inputs in accordance with their individual Terms of Reference.

(d)
Initial review of draft Design Document by Program Manager (APTC). If required, the team will amend the draft Design Document in light of feedback from Program Manager (APTC).

(e) 
Independent Appraisal and Peer Review of Draft Design Document. AusAID will ensure rigorous independent and internal appraisal of the Design Document to ensure its quality. The Team Leader and TVET Specialist will participate in the Peer Review meeting.

(d) 
Final draft of Design Document. Following receipt by the team of formal Peer Review feedback from AusAID, the team will finalise the document under the guidance of the Team Leader.

Written Outputs for the report writing, review and finalisation phase

Output 3: Design Outline. This will be a brief (5-6 pages) document. While the format of the Design Outline is a matter for the team to determine, the document should provide AusAID with an overview of the broad directions of the proposed design.
Output 4: Draft Design Document. This document will be in accordance with the requirements of these Terms of Reference; the Concept Note provided at Attachment 1 and will conform to AusAID’s design requirements at Attachment 3. 
Output 5: Final Draft Design Document. The Design Document will be finalised in accordance with AusAID’s direction following the Design Peer Review.

8. Composition and Responsibilities of the Design Team

The design of APTC Stage II will be undertaken by a team of five consultants as follows. 
· Team Leader

· TVET Specialist

· Design and Scholarships Specialist 
· Education Economist

· TVET Finance Specialist

AusAID’s Contracts Manager in Suva will act as the Contracting Specialist for this design and will provided specialist inputs on contracting issues as identified by the Team Leader.

Under the overall direction of the Team Leader, all members are expected to work collaboratively as a team to produce a coherent, high quality and cost-effective design. Each member of the team has individual responsibilities with working days (which includes travel days) allocated accordingly and these are specified below.
	Team Leader
	

	Tasks
	a) Participate in all elements of the mission as per Tables 1 and 2.
b) Provide professional and substantive leadership for the team and ensure a collegial working mode for it.

c) Ensure all the required outputs meet AusAID’s quality requirements and are in accordance with the Concept Note (Attachment 1) and the mission’s Terms of Reference. 
d) Take lead responsibility for identifying within the design how the APTC Stage II can better harness the support, including financial contribution, of other donors.

e) Take lead responsibility for identifying ways that the APTC Stage II can complement AusAID’s bilateral TVET programs more systematically.

f) Take lead responsibility for identifying how APTC could support regional trade strategies as they evolve through PACER Plus discussions.
g) With the assistance of the TVET Specialist and other team members, design business-oriented governance and management arrangements for APTC Stage II consistent with the Guiding Statement in these Terms of Reference.

h) Liaise with AusAID to ensure that Pacific Posts, Pacific Governments, industry, national TVET providers, the current APTC contractors, other donors and other parties as required are consulted as part of the design process.
i) Allocate work responsibilities among the team consistent with their Terms of Reference and expertise.

j) Lead stakeholder consultations during the fieldwork and the team’s presentation of the draft design document at the Peer Review.

k) Coordinate the preparation of and submit the Inception Note (Output 1) and Note on Key Issues (Output 2) to AusAID.
l) Assist with and oversee the preparation and finalisation of the Design Outline (Output 3), and the draft version of the Design Document on behalf of the team (Output 4) and submit them to AusAID.

	Time frame
	The Team Leader will undertake these tasks and deliver these outputs in up to 41 working days. 

	Essential Requirements
	Extensive development experience in the region, including as team leader. Comprehensive knowledge of AusAID design requirements, quality standards and agency policies, including cross-cutting policies. Experience in managing the design of large and complex development programs. Strong interpersonal and communication skills, including writing skills. Teamwork skills.

	TVET Specialist

	Tasks


	(a)
Participate in designated elements of the mission as per Tables 1 and 2.
(b)
Provide strategic and technical guidance to the team in relation to good practice TVET systems including organisational governance and management, policies, planning, training delivery, quality assurance and performance management.

(c)
Scope an APTC School of Professional Development that operates in partnership with local training organisations (public and private) to strengthen the capacity of the TVET workforce across the Pacific and identify achievable and measurable professional development targets in Stage II. 
(d)
Scope an indicative training profile for APTC Stage II together with achievable graduate targets over four years. This will include:

(i)
specifying the process by which the APTC’s annual training profile should be reviewed and adjusted as necessary in response to changing demand;

(ii)
articulating how the APTC should engage with industry in Stage II to ensure it remains flexible and responsive to firm and industry demand;

(iii)
introducing a bridging program that will increase access by technically qualified applicants from small island states who do not meet the English Language, Literacy and Numeracy course entry requirements; and 
(iv)
identifying where flexible delivery modes that respond to the needs of clients (both employers and students) could be used more widely by APTC.
The training profile proposed for Stage II will take into account any recent changes to immigration requirements in key destination countries that could affect the opportunities for migration within the region and internationally for APTC students. 
(e)
Identify ways in which APTC partnerships with local training organisations (private and public) can be strengthened and extended in Stage II.

(f)
In relation to expanding and diversifying the APTC revenue base in Stage II: 
(i)
take lead responsibility for determining the key principles by which fee for service activities should be provided in Stage II, and the broad scope of such activities. 

(ii)
assisting the team, particularly the Scholarship and Design Costing Specialist to approximate revenue that could be generated from fee paying and employer-sponsored students and from fee for service activities and identifying suitable revenue targets.
(g)
Assist the Team Leader to design business-oriented governance and management arrangements for APTC Stage II consistent with the Guiding Statement in these Terms of Reference.

(h)
Review the APTC’s Performance Assessment Framework (PAF) and advise the Design Specialist on changes necessary to ensure the PAF provides a strong evidence base for measuring and reporting on the performance of the APTC in Stage II and assuring its quality.

(i)
Make other contributions to the Mission’s Outputs as requested by the Team Leader.

	Time frame
	The TVET Specialist will undertake these tasks and deliver these outputs in up to 36 working days. 

	Essential Requirements
	Contemporary strategic and operational knowledge of the Australian TVET system and TVET systems elsewhere. Understanding of the governance, management, service delivery and financial systems of quality assured training providers. Experience in working in partnership with industry on skills development issues. Comprehensive understanding of the links between the labour market and skills development. Development experience, preferably within the Pacific. Good interpersonal and communication skills, including writing skills. Teamwork skills.

	Design and Scholarships Specialist Specialist

	Tasks


	a) Participate in designated elements of the mission as per Tables 1 and 2.
Design Tasks
b) Under the direction of the Team Leader and with the advice and written inputs from other team members, draft the Design Outline (Output 3) and the draft Design Document (Output 4) and finalise the final Design Document (Output 5) in accordance with AusAID’s design and quality requirements and in a form suitable for tendering and submit it to AusAID.

c) Provide design advice to the team that ensures that the design for APTC Stage II builds on international good practice in design.

d) Take lead responsibility for the drafting of the risk analysis and risk matrix in the Design Document

e) Work with the TVET specialist to review the APTC’s Performance Assessment Framework (PAF) and then take lead responsibility for making the changes necessary to ensure the PAF provides a strong evidence base for measuring and reporting on the performance of the APTC in Stage II.

f) Liaise with the AusAID Contracting Specialist on the preparation of the Scope of Services and Basis of Payment for inclusion as Annexes in the Design Document.

g) Prepare the Implementation Schedule arising from the design process that should include at least a 3-month handover period between Stage I and Stage II contractors.

h) Make other contributions to the Mission’s Outputs as requested by the Team Leader
Design Costing

i) Take lead responsibility for estimating the total and annual costs for APTC Stage II (broken down by categories of infrastructure, monitoring and evaluation, administration, teaching, training resources, Scholarships etc). Within this over-arching responsibility for costing the design of APTC Stage II:

(i) 
establish a costing framework for all aspects of the design;

(ii)
work collaboratively with the Education Economist to ensure that this over-arching costing framework is applicable to the preparation of estimates of the capital and recurrent costs of:

· any proposed expansion of APTC operations in PNG; and

· establishing an APTC campus in the Solomon Islands.

 (iii)
work collaboratively with other members of the team, particularly the TVET Specialist, to approximate revenue that may be generated from fee paying and employer sponsored students and fee for service activities and identify suitable revenue targets.

(iv)
seek sectoral advice from the TVET Finance Specialist as needed to ensure the design’s budget estimates are realistic and encourage efficiency.

j) Prepare those sections and schedules of the Design Document relating to activity costs.

k) Advise the team on the cost implications of options being considered for Stage II.

l) Provide costing data and information to the AusAID Contracting Specialist to support that Specialist’s preparation of the Basis of Payment for inclusion in the Design Document.

m) Make other contributions to the Mission’s Outputs as requested by the Team Leader.

APTC Scholarships Program
n) Review all aspects of the current APTC Scholarships Program and identify ways of improving its efficiency, effectiveness, accessibility and transparency. This will require close liaison with the APTC Coordination Office.
o) Design a cost-effective Scholarships Program for Stage II of the APTC which:
(i)
 is consistent with the objectives of the overall design for Stage II;

(ii)
is fully costed;

(iii)
ensures access for those who do not have the opportunity to study as a fee-paying or employer sponsored student, particularly those from non-campus countries, women and marginalised groups; and
(iv)
is marketed, managed and coordinated efficiently and effectively at both national (including sub-national) and regional levels. 

	Time frame
	The Design and Scholarships Specialist will undertake these tasks and deliver these outputs in up to 59 working days. 

	Essential Requirements
	Extensive development experience in the region. Extensive experience in designing a range of large-scale development cooperation programs, including new forms of aid and innovative management models. Strong interpersonal and communication skills, including excellent writing skills. Teamwork skills.

Comprehensive knowledge and understanding of the design and management of scholarship programs, including Australian Scholarships, preferably in the Pacific. Strong analytical capabilities and the ability to interrogate complex databases. Extensive development experience in the Pacific. Experience in costing development activity designs and preparing the necessary resource schedules. Good interpersonal and communication skills, including writing skills. Teamwork skills.

	Education Economist

	Tasks


	a) Participate in designated elements of the mission as per Tables 1 and 2.
b) Review the Cost-Benefit Framework for Evaluating APTC (Annex J in the APTC MTR) and other good practice cost benefit and cost effectiveness frameworks.
 
c) Ascertain the current content and results of the student Tracer Studies, Employer Surveys and any other relevant data on benefits currently gathered by APTC.
d) Analyse the APTC budget 2007-2011 and enumerate all cost inputs.
e) Prepare a rigorous and methodologically sound cost-benefit analysis (CBA) or cost-effectiveness analysis (CEA) of APTC Stage I (2007-2011) and prepare a CBA or CEA for APTC Stage II (2011-2015), including a stand-alone analysis of the proposed investment in a Solomon Islands campus. All key assumptions should be presented. These two studies will be included as technical annexes in the Design Document and will assist AusAID to make evidence-based judgements about return on investment and value for money in APTC.
f) In consultation with the Team Leader and the TVET Specialist, prepare an estimate of the capital and recurrent costs of any proposed expansion of APTC operations in PNG.

g) Assist the team to identify ways in which APTC Stage II can achieve greater value for money without reducing quality.

h) Make other contributions to the Mission’s Outputs as requested by the Team Leader.

	Time frame
	The Education Economist will undertake these tasks and deliver these outputs in up to 35 working days. 

	Essential Requirements


	Formal qualifications in Economics, preferably in the field of education and training and/or labour markets. Experience in undertaking cost-benefit and cost effectiveness studies in the field of education and training, preferably in a development context. Extensive knowledge and strong skills in labour market analysis. Development experience, preferably within the Pacific. Good interpersonal and communication skills, including writing skills. Teamwork skills.

	TVET Finance Specialist

	Tasks


	a) Participate in designated elements of the mission as per Tables 1 and 2.

b) Undertake a comprehensive analysis of the efficiency of the APTC by School and Country for calendar year 2009 in terms of:

(i)
government recurrent expenditure per publicly funded annual hour and/or real government recurrent expenditure per hour of publicly funded load pass;

(ii)
the cost of capital per annual hour.

This analysis should produce a credible baseline against which the efficiency of APTC Stage II can be analysed each calendar year. . The analysis will conform to the Australian Vocational Education and Training Management Information Statistical Standard (AVETMISS) in its calculations of government recurrent expenditure, publicly funded hours or load pass, the cost of capital and all other calculations that may be necessary. Relevant comparative benchmark data should be included where appropriate.
This efficiency analysis will be included as a technical Annex in the Design Document and will assist AusAID to make evidence-based judgements about the efficiency of the APTC in Stage II.

c) Provide advice to the team on where operating efficiencies may be achieved in Stage II relative to Stage I. 

d) Provide sectoral advice on costing and efficiency issues as requested by the Scholarship and Design Costing Specialist preparing the Stage II budget. 

	Time frame
	The TVET Finance Specialist will undertake these tasks and deliver these outputs in up to 19 working days. 

	Essential Requirements


	Formal qualifications in the field of accounting or finance. Extensive experience in financial management and analysis within the Australian TVET sector. Experience in preparing AVETMISS compliant financial and hours data and/or undertaking AVETMISS data audits. Strong analytical, interpersonal and communication skills, including writing skills. Teamwork skills.

	AusAID Contracting Specialist

	 Tasks
	a) Participate in designated elements of the mission as per Tables 1 and 2.
b) Provide advice to the team on contracting issues and good practice options for streamlining the contracting model for the APTC.
c) Work with the Design Specialist to draft the Scope of Services for inclusion in the Design Document.
d) Prepare the Basis of Payment for inclusion in the Design Document in consultation with the Design Specialist and the TVET Finance Specialist.

	Time frame
	As part of their AusAID duties, the Contracting Specialist will undertake these tasks as agreed with the Team Leader.

	Essential Requirements
	Comprehensive knowledge of AusAID’s contracting processes and requirements. Knowledge of the range of good practice contracting models that could be activated for Stage II of the APTC. Teamwork skills.


Attachment 1: APTC Stage II Concept Note

1.
Introduction
1.1
This concept note outlines necessary considerations for AusAID as it moves towards designing the second stage (2011-2015) of the Australia-Pacific Technical College (APTC). The note draws on the findings and recommendations of the APTC mid-term review (conducted in early 2009), consultations with the APTC Advisory Group and a formal discussion at the Pacific Heads of Education Meeting held in Nadi in November 2009. 
1.2
The APTC is a relatively young initiative that, according to the Mid-term Review, is progressing well in terms of meeting its goals and purpose. This concept note is premised on an understanding within AusAID that the strategic role of the APTC in the region should remain unchanged. It should continue to promote and provide high-level Australian qualifications across the Pacific and, by doing so, increase the employability of its graduates and strengthen the quality of the labour pool nationally, regionally and internationally. This note argues that, even with its early successes, the APTC can be improved and streamlined, and its reach and offerings expanded. The objective of any modification to the current APTC model would be to ensure that APTC becomes more responsive to demand, more effective in meeting its goals and an institution that provides world-class training at a reasonable cost.

1.3
This concept note acknowledges that in order for the APTC to be sustainable in the longer-term, it will need to graduate to a regional training institution. It is unclear at this stage in what form this should occur but is an issue that will need to be considered early in Stage II in preparation for continuation of the College beyond 2015. Due to the size of such an exercise, it is felt this investigation should occur concurrently to the start up of Stage II rather than as part of the design of the APTC 2011-2015. This will allow adequate time for all parties (AusAID, Pacific Island Governments, Pacific Islands Forum, and other donors) to make the decisions without hampering the delivery of APTC’s highly demanded Australian Certificate III and IV qualifications. 
1.4
It is intended that this note will form the basis of a Submission to Minister Smith that seeks approval of the direction set out below for the APTC Stage II.

2.
Background
2.1
The APTC was established in July 2007, following the then Prime Minister’s announcement at the 2006 Pacific Islands Forum, with an initial allocation of AUD$149.5 million (2007/08 to 2010/11). At that time, the Australian Government committed to continuation of the College for as long as there was sufficient demand for its services.

2.2
The APTC provides training at Australian standards in order to:

i. increase the supply of skilled workers in targeted sectors in the Pacific region, 

ii. help Pacific Islander women and men with Australian qualifications realise improved employment opportunities nationally, regionally and internationally in targeted sectors 

iii. increase productivity of individuals and organisations in targeted industries and sectors.

2.3
The APTC delivers Australian Certificate III and IV skill training in five industry sectors: automotive, manufacturing, construction and electrical, tourism and hospitality and health and community services (refer to Attachment A). Flexibility exists for the APTC to add or remove courses, campuses and training partners in response to changing regional skills demands. A key feature of the College, and a major contributor to its success to date, is its partnerships with private sector groups, industry and local institutions to complement existing public and private investment in the sector. 
2.4
APTC qualifications can only be issued by Australian Registered Training Organisations (RTOs). Box Hill Institute of TAFE and Sunshine Coast Institute of TAFE were appointed through a restricted tender.

2.5
Students enter the APTC as fee-paying, employer sponsored or scholarship students. It was anticipated that other donors would contribute funding to the APTC and that fee for service activities would generate income. A AUD$10m scholarships program was developed to facilitate participation by students from non-campus countries, particularly small island states. As at December 2009, 1,468 students (60% of enrolments) have received a scholarship to study at the APTC. 23% of these scholarship students are from non-campus countries. Of the APTC’s entire student intake, only 15% is from non-campus countries. 
3.
APTC Progress – Assessment to Date

Mid-term Review

3.1
The mid-term review (MTR) of the APTC was very positive about the impact of the College over a relatively short period of operation and recommended that it continue to a next stage and beyond. APTC’s success is largely attributed to finding a previously unfulfilled niche in the Pacific. The MTR found that the APTC is performing well against its goals and key results areas, and is yielding unanticipated benefits for individuals and national institutions. The APTC is moving from a supply driven intervention to one that is successfully responding to demand for services.

3.2
In brief, the MTR reports that the APTC has performed positively against goals one and two. Specifically, the MTR points out that the APTC is achieving its purpose and as a result: 

· is increasing the supply of skilled workers in targeted sectors in the Pacific region

· will enhance the future employment and promotion prospects of its graduates

· is having a growing impact on national and regional training capacity through the highly successful Certificate IV in Training and Assessment training, enrolment of industry and institutional trainers in APTC programs and a positive demonstration effect

· has a positive reputation with its clients

· has strong partnerships with its industry training partners

· has had an effective start up due to the RTO’s experience and expertise in TVET training. 

3.3
The MTR noted that it is too early to measure progress against goal three and indentified some areas that should be addressed to maintain and enhance the effectiveness of the APTC, including:

· APTC’s profile in non-campus countries is still low. 

· Some national public TVET institutions maintain that resources for the APTC should be directed to them

· Poor English language, literacy and numeracy standards remain a challenge.

· Maintaining a pipeline of students from non-campus countries

· Adding a campus in the Solomon Islands

· Expanding the courses offered in PNG and Samoa

· The role and composition of the APTC Advisory Group

· An over reliance on scholarships to fund students.

3.4
The full list of MTR recommendations is contained in the report’s Executive Summary (see Attachment B).
 
Pacific Heads of Education
3.5
The annual Pacific Heads of Education meeting (Nadi, 4 November 2009) discussed the progress and future of the APTC. AusAID, NZAID and the Pacific Islands Forum Secretariat participated in this discussion. Consensus was that the APTC is filling a critical gap in service provision, as it provides a significantly higher quality of training than previously available in the region. In addition, the APTC is having a positive demonstration effect on national training institutions. The disparity of resources available to the APTC in comparison to national institutions was noted as a concern. Without exception, the Pacific Heads of Education strongly urged Australia to continue the APTC.

Advisory Group
3.6
The APTC Advisory Group (AG) discussed the future directions of the APTC at their fourth meeting in Nadi on 27 and 28 August 2009. The Group noted the major benefits of the APTC as the quality of training delivered and the confidence members have in the capacity and professionalism of the current RTOs. The AG strongly supported the MTR’s recommendation that the APTC continue beyond 30 June 2011.

4.
Context
Training in the Pacific

4.1
Many Pacific Island Countries (PICs) see improved skills training as one solution to their labour market issues. However, many do not have quality-assured national skill standards; available training is supply-driven and of low or variable quality; and employer inputs are rarely solicited. 
4.2
Skill shortages are widespread across the PICs, resulting in loss of productivity, lower quality output, inability to grow, lower profits, problems with equipment maintenance and loss of markets. Access to TVET opportunities is often limited outside the capital and in the outer islands.

Regional Policies
4.3
In October 2005, the Pacific Island Forum Leaders endorsed the Pacific Plan with the goal of enhancing and stimulating economic growth, sustainable development, good governance and security for Pacific countries through regionalism. It encompasses increased regional service provision as well as market integration. 

4.4
To promote regional integration, the Pacific Plan calls Forum members to 

[integrate] trade in services, including temporary movement of labour, into the Pacific Island Countries Trade Agreement (PICTA)

4.5
The Pacific Agreement on Closer Economic Relations (PACER Plus) regional trade negotiations will create a regional trade area between Australia, New Zealand and the PICs. Australian Ministers have stated clearly that PACER Plus will include skills development for PICs, equipping them for technical work in the region and globally.

4.6
The Pacific Education Development Framework (PEDF), endorsed by the Forum Education Ministers, guides the further development of Pacific education. The PEDF addresses two broad agendas: (i) the Education for All (EFA) or basic education agenda, and (ii) the training/ employment/economic agenda. The PEDF is aligned with, and grounded in, the principles of the Pacific Plan and reflects the Pacific concept of regionalism where countries work together for their joint and individual benefit.

4.7
An increasing number of national education plans are including TVET as a priority sub-sector, in recognition of the importance of employment outcomes for school leavers and private sector productivity for economic growth.

4.8
The APTC can be viewed as a successful experiment in its approach to the regional provision of services. However, while it provides specialised high-level training regionally, it is not a regional provider, and currently does not have the characteristics of a Pacific ‘club’ in the sense of shared governance, ownership and financing, such as the University of the South Pacific (USP).

4.9
It is unlikely that private or national public sector agencies will be able to deliver equivalent vocational training over the medium-term. Whether, and under what conditions, the APTC should make a transition from an Australian development program to a regional training institution will be a major strategic choice in the coming years. This is not an issue that should be addressed in the Stage II design. Instead, it is a major exercise that will be considered concurrently to the start up of Stage II of the APTC.

4.10
The APTC is successfully responding to regional priorities to facilitate the trade in services, movement of labour and improve the quality of national training providers.
AusAID’s Policy Framework

4.11
AusAID is providing a range of assistance to formal and non-formal TVET and to policy and organisational development as well as capacity development for training delivery. The Pacific Partnerships for Development include support for economic growth, basic education and skills development. Many also have implementation strategies that relate specifically to strengthening TVET (Kiribati, Tonga, Vanuatu, Samoa). The PNG Program is also planning to develop an implementation strategy for TVET.

4.12
AusAID’s draft Pacific Education Framework recognises that there are links between the quality and equity of basic education and the impact of higher education and training. It also recognises the potential of the APTC to lead the region in respect to higher level technical and vocational training, while Australia’s bilateral programs strengthen viable local institutions to better meet local labour demand and to provide suitable candidates for higher training via the APTC or other national or regional providers.

4.13
Developing the knowledge and skills necessary for life and productive livelihoods is of growing importance in the Pacific given the poor local employment prospects for rapidly expanding youth populations. Populations with high levels of education and skilled workers adapt more rapidly to changing environments and respond more quickly to economic and market opportunities.

4.14
The APTC contributes to achieving performance target 2 of the draft PEF aimed at increasing the employability of Pacific islanders and to strengthening post-secondary professional, technical and vocational education and training across the region.

5.
Design of APTC 2011 – 2015
5.1
The findings of the MTR, feedback from the Pacific Heads of Education, the APTC AG and the region, and the Australian Government’s interest in supporting labour mobility under the Pacific Plan, PICTA and PACER Plus, strongly support continuation of the APTC. Subject to Ministerial approval, the College will continue into a second phase that will run from 1 July 2011 – 30 June 2015. 

5.2
The success of the APTC may be attributed to its tight focus on its niche of delivering demand-based, high quality, high-end training. Expanding the College beyond this scope risks the APTC losing its clear direction and the delivery of real benefits for the Pacific. For this reason, the design of the College for 2011-2015 will look to improve its efficiency and effectiveness rather than consider major expansion. 

5.3
High quality technical training is widely sought after as evidenced by the demand for APTC places in all areas, particularly from the larger Pacific countries. The College’s slow start in attracting fee-paying students, limited fee for service training, limited training facilities and the lack of interest by other stakeholder to fund the APTC are constraining major expansion and will be addressed in the design of Stage II. 
5.4
The APTC must be viewed as one part of AusAID’s range of support for TVET in the Pacific. It is clear that the APTC’s Australian qualifications in training and assessment are extremely welcomed and play a role in building the capacity of national institutes. However, other bilateral and/or regional TVET strengthening initiatives must operate to improve the quality of national TVET systems, including the delivery of Certificate I and II. Such assistance is crucial for assisting countries achieve their own development goals, addressing the youth bulge, building the national skill base, creating a pipeline for the APTC and ideally, developing quality national TVET systems that remove the need for the APTC. 

5.5
Accordingly, the goals and purpose of the APTC will remain unchanged.

Goals

Training: Increased supply of skilled workers in targeted sectors in the Pacific region.

Employment: Pacific Islander women and men with Australian qualifications realise improved employment opportunities nationally, regionally, and internationally in targeted sectors.

i. Productivity: Increased productivity of individuals and organisations in targeted industries and sectors.

Purpose

To:

provide Pacific Islander women and men with Australian qualifications that present opportunities to be able to find employment in targeted sectors nationally and internationally, and 

support skills development in the Pacific in response to labour market requirements.
Shape of the APTC
5.6
The APTC is a large-scale and innovative development program delivering internationally recognised technical and vocational programs in targeted industry sectors in the Pacific region. While the RTOs are allowed a degree of flexibility in the APTC’s operation, the APTC is not intended to become too country-specific in its operation or offerings. However, it is anticipated that there will be some flexibility in Stage II to allow the contractor(s) and Posts to address some individual country training demands so long as their provision does not detract from the APTC’s core business of delivering Australian Certificate III and IV qualifications.

5.7
It is important that during Stage II the APTC be able to continue to operate with the flexibility adequate to allow the College to add or remove courses, and increase training locales in response to changing labour market demands. The process and requirements for adding to or subtracting courses from the College will be articulated in the design of the next stage.

5.8
The APTC will continue to offer Australian Certificate III and IV training that responds to national, regional and international labour market demands. It is intended that Stage II will maintain the successful achievements of Stage I by offering the current courses in automotive, construction, electrical, manufacturing, tourism, hospitality, health and community services and Certificate IV in Training and Assessment, and also being able to offer other courses in response to demand. The Diploma in Training and Assessment will be offered from 1 July 2011. A School of Professional Development will be created for the in-service development of the Pacific TVET workforce.

5.9
It is envisaged that the APTC will operate in five campus countries of Samoa, Fiji, Vanuatu, PNG and Solomon Islands. The implementing RTO(s) will be responsible for designing the new campus in the Solomon Islands and will assess whether the APTC should expand the courses offered in PNG and Samoa as recommended in the MTR. 

5.10
Partnerships between the APTC and national training institutions and industry are critical to the APTC’s success. It is thus intended that the nine current partnerships with training institutions and industry partners will remain in place.
 In addition, it is anticipated that new partnerships will be developed in response to new courses and training locations to ensure the APTC remains effective (for example, with the LNG industry in PNG). It is essential that the design for Stage II looks at how, along with complementary bilateral and regional initiatives, the APTC can improve its relationships with the national training institutions to diminish any resentment and ensure that benefits accrue to both parties. The design will also look at how to strengthen the relationships with industry partners and consider if more scope should be provided for these in Stage II.

5.11
It is clear that the APTC needs to expand and AusAID needs to consider how large the APTC should become. Given this, the design will look at to what extent the APTC can expand without it becoming unwieldy, financially unsustainable, and the costs of operation exceeding the benefits.

Access

5.12
It is recognised that the APTC currently disproportionately benefits the larger countries. It is anticipated that significant demand for places will continue to be from Fiji and PNG, and will increase from the Solomon Islands when a campus is established there. Without substantially better in-country preparation, it is expected that students from the smaller island states will continue to struggle to meet the College’s entry requirements. 
5.13
The APTC scholarships program will continue to ensure access for those, particularly from non-campus countries, who do not have the capacity to study as a fee-paying or employer sponsored student. The design team will look at how it can be refined to better ensure its efficiency and support of non-campus country students. 
5.14
An English language, literacy and numeracy (ELLN) training program will be introduced. This program will support access by technically qualified applicants from small island states who do not meet the ELLN course entry requirements.

5.15
New entrant and women only courses, and flexible part-time delivery will continue to be a feature of the APTC. Flexible delivery modes (mix of face to face and distance and technology learning) will be introduced in Stage II and should help access by women and people with a disability. The design for Stage II will consider what else can reasonably be done to support participation by women and people with a disability. 
5.16
Workplace training will continue, as far as possible, to be delivered in-country. Some in-Australia workplace training may be necessary, particularly for the licensed trades such as plumbing and electrical. The Stage II implementing RTO(s) will continue to pursue partnerships with industry bodies, such as the Master Plumbers Association and Electrical Contractors Association, and industry interlocutors, such as the Australian Chamber of Commerce and Industry, to help facilitate any necessary in-Australia workplace training.

5.17
The APTC will increase its intake of fee paying and employer sponsored students and pursue more fee for service activities. The design team will explore methods for encouraging the contractor(s) to increase the number of fee-paying students. They will also be asked to carefully consider how to balance this increase with continuing to provide places to students, particularly from non-campus countries, which would not otherwise have the opportunity to obtain Australian qualifications. 
Fee for Service Activities
5.18
There is strong demand in the Pacific for training related services that cannot be met by national and regional providers. The APTC is well placed to respond to much of this demand. Fee for service activities are a key avenue for generating revenue that will enable the APTC to expand and reduce its reliance on Australian Government funding. In accordance with the recommendations of the MTR, it is intended that scope for fee for service activities will increase in Stage II of the College. The pursuit of such activities must be carefully balanced with ensuring the APTC continues to deliver its core business of Certificate III and IV training. 
5.19
Fee for service activities will be provided at cost for other AusAID programs. All profits from fee for service activities will go back to the APTC.

5.20
Under fee for service, the APTC will be able to deliver:

· Tailored training at Certificate level III or above for either Australian Quality Training Framework (AQTF) qualifications or AQTF Statements of Attainment, in response to employer demand, that fall within the current scope of the APTC courses and the RTO’s scope of registration. 
· Training needs analysis for firms and agencies and skills assessment services.

Management Structure
5.21
There are currently three separate contracts for the APTC:

· One contract with SKM for the Coordination Office in Nadi (headed by a General Manager), supported by country offices, with responsibilities including overall management and governance arrangements and student services.

· Two contracts with Box Hill Institute of TAFE and Sunshine Coast Institute of TAFE for the APTC Schools to deliver the training.

5.22
This structure has enabled the contractors to work to their comparative advantage. Management of the Coordination Office by a Managing Contractor has delivered a number of benefits such as adding development-focussed views, encouraging robust discussion, ensuring development considerations are incorporated into the running of the APTC, and improving the awarding of scholarships. The RTOs have delivered the high quality, high-end training that they are renowned for.

5.23
The MTR argued that the APTC’s management structure was sound and should continue in Stage II of the College with the current contractors, particularly the RTOs, if possible. However, it is understood that Stage II of the APTC will need to be tendered on the basis that:

· The original tender stipulated the contracts would only be for the period 2007-2011.

· APTC courses are delivered in accordance with the Australian Qualifications and Training Framework meaning all Australian RTOs could potentially deliver APTC courses and qualifications.

· The value of APTC Stage II is estimated at approximately AUD$152 million.

· Increased fee for service training affords benefits to the RTOs beyond those gained through the current APTC specific contracts.

5.24
It is proposed that this basic structure remains in place, although the implementers may change and more efficient management strategies may be identified during the Stage II design process.
 Thus, the next stage of the APTC should continue to have a central office in Nadi (headed by a General Manager and supported by country offices) and Schools in the campus countries. The contract(s) for the APTC will be streamlined where possible to improve cohesion. They will also provide flexibility to respond to changing demands and enable sub-contracting of an Australian provider where necessary to deliver requisite training and/or fee for service activities. The design for Stage II will consider who (RTO, Contractor etc) will implement Stage II of the APTC.

Governance
5.25
The Advisory Group (AG) was established to advise AusAID on a range of industry and TVET issues in the Pacific region, including the overall strategic vision of the APTC, APTC policy directions and on future demand for TVET in the region. The AG comprises senior people from the Pacific region and Australia but has not been used as effectively as it could be. The membership and specific functions of the AG will be revisited as part of the design of Stage II.

6.
Sustainability

6.1
The Australian Government is committed to supporting the APTC. Funding for the APTC has been built into AusAID’s funding base. 
6.2
The MTR recommended that in the longer-term, AusAID should consider the future state of the APTC. Given the scale of such an exercise, and the imperative to have at least a three-month handover for APTC Stage II, it is felt that this work should be conducted separately from the design of the APTC 2011-15. Therefore, early in Stage II, but separate from the design of Stage II, AusAID will commission an investigation into options for the future state of the APTC beyond 30 June 2015. In this study, consideration will be given to options such as amalgamating the APTC with a regional training institution like the University of the South Pacific, or establishing it as an independent legal entity. The study will also consider whether, “Australia” needs to be removed from the College’s name to facilitate change, as suggested in the MTR.

6.3
The design for 2011-2015 will consider how the APTC can gain cost efficiencies so that it achieves maximum output for minimum cost. Delivering professional, high-end technical training, particularly in trades and construction, is expensive. The current average cost of training of AUD$35,000 per student is high for short-term training, compared to ARDS of AUD$20,000 per student per annum and ADS of AUD$41,000 per student per annum. 

6.4
Costing of the APTC is an in-depth exercise. On face value, it is estimated that Stage II of the APTC will cost AUD$152 million (approximately AUD$38 million per year), based on 2009/10’s estimated expenditure of AUD$37 million. It is important to note that while 2009/10’s estimate more accurately reflects operation at full capacity, it encompasses a larger student intake that compensates for the slow student enrolment at start up and ensures the APTC reaches its 3,000 graduate target. It is likely that the design will establish a lower estimated annual cost given that the student intake for Stage II will be more evenly spread across 2011-2015. That said, additional courses and facilities that will be added in Stage II would attract further costs. 
6.5
While the design team will look carefully at APTC’s costs, there are few current indications that the costs can be significantly reduced over the coming years - even after capital development costs are met. Although costs are high, the APTC is providing a high quality product that cannot be matched in the region and that will facilitate many benefits such as higher remittances, higher individual and employer productivity, higher earning streams for APTC graduates, and increased youth employment. 
7.
Risks

7.1
There are a number of key risks that will be addressed in the design of Stage II and managed by the implementing contractor(s). Continuation of the APTC will be reliant on complementary bilateral and/or other regional initiatives that build the capacity of national training institutions to produce quality graduates. Without such initiatives, the pipeline for the APTC may dry up in the medium-term and countries will not be able to replace the capacity lost as a result of labour migration. In addition, resentment of APTC’s partner local training institutes will grow due to feelings of neglect and could diminish their support of the APTC.

7.2
It is anticipated that demand for APTC services from larger countries will continue to remain high. Without improvements in the quality of education (including post-secondary training) and financial assistance for those from small island states who wish to participate in the APTC, citizens from the larger countries will continue to dominate APTC’s enrolment. The scholarships and ELLN programs will help address this. However, bilateral education and TVET strengthening programs will also have a significant role to play in addressing this disparity.

7.3
The APTC must reduce its reliance on Australian Government funding in order to grow and be sustainable. The APTC contractor(s) cannot rely on scholarships to supply APTC students. Pursuit of fee for service activities, increasing fee paying and employer sponsored students, and engaging the support of other donors will be critical to generating revenue for and supporting expansion of the APTC. However, in moving forward, the APTC must ensure that an increase in fee for service activities does not divert the College from delivering its core business. It must also ensure that the APTC continues to assist attendance by those, particularly from small island states, who do not have the capacity to attend on a fee paying or employer sponsored basis.

8.
Design of Stage II
8.1
This concept note does not propose a major departure from the current operation of the APTC. Extensive design documents were produced for the APTC Schools, Coordination Office and scholarships program at the beginning of the current phase. The costs of building facilities and campuses have been established by the current RTOs through the creation of the APTC. The MTR provides a thorough examination of the College’s performance and key issues, and provides extensive recommendations on the future of the College. 
8.2
Given the wealth of information available, it is considered unnecessary for the design of Stage II to be developed via a major traditional design exercise. It is proposed that the Stage II design will largely be an in-Australia desk-based design, conducted by a 3 – 4 person team. Teleconferences will be held with Posts and the current APTC contractors as necessary. There may also be face-to-face meetings with the RTOs, Contractor and the APTC Senior Management Team and a few in-country visits as required. The design team will be required to develop a design plan as their first output. This plan will set out the process necessary to deliver the design of Stage II of the APTC. 

Annex B: People and Organisations Consulted

	Name
	Position/Organisation
	Country

	Aileen Croghan
	First Secretary, AusAID
	Solomon Islands

	Alan Tira
	Principal, POMTECH
	PNG

	Alex Wilson
	General Manager, Gateway Hotel
	PNG

	Amber Yates
	Hilton Denarau
	Fiji Islands

	Ana Nasilasila
	Hilton Denarau
	Fiji Islands

	Angus Barnes
	Senior Manager, International Development, Sinclair Knight Merz
	Fiji Islands

	Anne Lopena
	Lamana Hotel
	Papua New Guinea

	Antoine Barnaart
	General Manager, APTC Coordination Office
	Fiji Islands

	Arvind Shrivastav
	Heritage Park Hotel Honiara
	Solomon Islands

	Barbara O’Dwyer
	Gender Adviser, AusAID 
	Australia

	Bill Costello
	Assistant Director General, Pacific Branch, AusAID 
	Australia

	Calvin Ziru
	Solomon Islands Chamber of Commerce & Industry
	Solomon Islands

	Caroline Tupoulahi - Fusimalohi
	Planning Adviser, Secretariat of the Pacific Community
	Fiji Islands

	Cathy Eminoni
	Programme Officer, European Union 
	PNG

	Charles Mabia
	Office of Higher Education
	PNG

	Chris Graham
	Second Secretary, AusAID
	PNG

	Christelle Thieffry
	Senior Program Officer, AusAID 
	Vanuatu

	Colleen Peacock-Taylor
	M&E Officer, APTC Coordination Office
	Fiji Islands

	Corinne Tarnawsky
	Disability Inclusive Development Team, AusAID 
	Australia

	Damien Rapese
	Deputy Secretary, National Department of Education
	PNG

	Dave Culley
	Fletcher Kwaimani Joint Venture
	Solomon Islands

	David Conn
	Port Moresby Chamber of Commerce and Industry
	PNG

	David Hayward
	Ela Motors
	Solomon Islands

	David Slade
	Director, Manufacturers Council of PNG
	PNG

	David Thomas
	Ela Motors
	PNG

	David Twiggs
	Boroko Motors
	PNG

	Debbie Bowman
	Director, Human Development Section, Pacific Branch, AusAID 
	Australia

	Dr Tagi
	Office of Higher Education
	PNG

	Elena Down
	Disability Inclusive Development Team, AusAID 
	Australia

	Emily Hazelmann
	Coordinator, PATVET 
	Fiji Islands

	Emma Ferguson
	Senior Country Specialist ADB
	Fiji Islands

	Fiona Ramsey
	Second Secretary, European Union
	Fiji Islands

	Garry Holmes
	Managing Director, Motor Corporation (SI) LTD
	Solomon Islands

	Geno Rua
	Labour Statistician, Department of Labour and Industrial Relations
	PNG

	Gertrude Kilepak 
	Policy Officer, Department of National Planning and Monitoring
	PNG

	Goini Loko
	Business Council of PNG
	PNG

	Gordon Wilson
	Tanoa Hotel Group
	Fiji Islands

	Greg Anderson
	PNG Chamber of Mining and Petroleum
	PNG

	Heni Dembis
	Planning and Development Officer, Papua New Guinea Tourism Promotion Authority
	PNG

	Ian Bignall
	Counsellor, AusAID 
	Samoa

	Ian Wallwork
	Hastings Deering
	PNG

	Ian Wells
	Project Director, APTC SACEM
	Australia

	Iconey Samuel
	Assistant Secretary, Multilateral, Department of National Planning and Monitoring
	Solomon Islands

	Isabel Salatiel
	Director of Child Welfare, Department of Community Development
	PNG

	James Knynenburg
	Product and Content Manager, APTC SACEM
	Fiji Islands

	James Wini
	Solomon Kitano Mendana Hotel
	Solomon Islands

	Jane Lake
	Senior Associate, Pacific Branch, AusAID 
	Australia

	Janice Febey
	Branch Manager, DEEWR
	Australia

	Jayasundara Banda
	Acting Assistant Secretary, Department of Education
	PNG

	Jerry Agus
	PNG Tourism Promotion Authority
	PNG

	Jerry Strudwick
	Education Adviser, AusAID 
	Australia

	Jim Irwin
	Country Manager, APTC STH 
	Fiji Islands

	Joelson Anere
	Senior Aid Coordinator, AusAID
	Solomon Islands

	John Leahy
	PNG Chamber of Commerce and Industry
	PNG

	Jone Usamate
	Chief Executive Officer, TPAF
	Fiji Islands

	Juan Carlos Hinojosa
	Attache - Social, European Union 
	Solomon Islands

	Julie Delforce
	Director, Economics and Growth, AusAID 
	Australia

	Juliette Brassington
	Counsellor, AusAID 
	Solomon Islands

	Justin McGann
	General Manager, Curtain Brothers
	PNG

	Kaye Schofield
	TVET Adviser, AusAID 
	Australia

	Kentaro Suekane
	Head of Education Sector, JICA
	Fiji Islands

	Kevin Yaxley
	Executive Director, Airways Hotel
	PNG

	Lawrence Waiman
	Assistant Director, Department of Labour & Industrial Relations 
	PNG

	Lia Maka
	Director, SPC
	Fiji Islands

	Lindy Fisher
	First Secretary, Education, AusAID 
	PNG

	Lynette Kulkula
	Transition Manager, AusAID 
	Fiji Islands

	Maria Kopkop
	Chair of Governing Council, POMTECH
	PNG

	Martin Korokan
	Aid Coordinator, Department of Planning
	PNG

	Martin. B. Sam
	Solomon Islands Electricity Company
	Solomon Islands

	Mary Hicks
	Director Education & Training, ACCI
	Australia

	Megan Lilly
	Associate Director, Education & Training, AIG
	Australia

	Megan McCoy
	Second Secretary (Development), NZAID
	Fiji Islands

	Meipo Meredith-Anitema
	Activity Manager, AusAID 
	Samoa

	Meli Kivung
	Director, Department of Labour & Industrial Relations
	PNG

	Michelle Lowe
	Director Program Quality and Review PNG Branch
	Australia

	Mollie Willie
	Deputy Secretary, Department of Community Development
	PNG

	Morrie Wintringham
	Divisional Manager, APTC
	PNG

	Nanise Young
	Program Officer, JICA
	Fiji Islands

	Nicci Simmonds
	First Secretary, New Zealand High Commission
	Solomon Islands

	Noel Lyons
	Vice President, Box Hill Institute
	Australia

	Pedro G. Cortez
	Superintendant of Curriculum, Department of Education 
	PNG

	Phil Bradford
	Island Enterprises Limited
	Solomon Islands

	Phil Frethey
	Manager - Training Services, PNG LNG Project
	PNG

	Richard Babovic
	SACEM, APTC 
	Fiji Islands

	Robin Scott-Charlton
	Chief of Operations, AusAID
	PNG

	Romaine Kwesius
	Counsellor, AusAID 
	Fiji Islands

	Ross Hepworth 
	Institute Director, Sunshine Coast Institute of TAFE
	Australia

	Russell Holden
	Air Terminal Services, Nadi Airport
	Fiji Islands

	Samuel Namosimalua
	Director Labour Policy and Productivity, Ministry of Labour
	PNF

	Setareki S Macanawai
	Chief Executive Officer, Pacific Disability Forum
	Fiji Islands

	Sir Peter Barter
	Madang Resort
	PNG

	Stan Motolova
	National Training Council
	PNG

	Stephanie Copus-Campbell
	Minister Counsellor, AusAID
	PNG

	Susan Ryle
	First Secretary, AusAID
	PNG

	Taro Morrison
	APTC SACEM
	Fiji Islands

	Tessa Temata
	Manager, NZAID
	PNG

	Tina Seniloli
	APTC Program Manager, AusAID 
	Fiji Islands

	Trevor Birney
	IEA College of TAFE - Ela Beach
	PNG

	Trevor Riordan
	Director, International Labour Organization
	Fiji Islands

	Virginia Battye
	Staff & Systems Development Adviser (Short Term), APTC
	Fiji Islands

	Health and Community Services Industry Groups/Employers 
	Nadi
	Fiji Islands

	Trade Industry Groups/Employers 
	Suva
	Fiji Islands


Annex C: Reference Documents 
AusAID Documents

Policy and Guideline Documents
· AusAID Guideline ‘Integrating Environment into Aid Activity Design’. Feb. 2003

· Environmental Management Guide for Australia’s Aid Program. Feb. 2003

· AusAID Policy: Gender equality in Australia’s aid program – why and how
· AusAID Policy: Development for All: Towards a disability-inclusive Australian aid program 2009-2014 
· AusAID Guideline ‘Integrating Gender Equality into Aid Activity Design’
· AusAID Child Protection Policy and Manual. March 2008
· AusAID Performance Assessment and Evaluation Policy. Dec. 2007
· AusAID Quality Reporting System for Aid Initiatives. 2008 

· AusAID Design Team Kit. July 2009

· AusAID APTC Stage II Concept Note. 19 February 2010

· Pacific Partnerships for Development: Kiribati, Tonga, Samoa, PNG, Solomon Islands, Nauru

· AusAID website information on Pacific Partnerships for Development (http://www.ausaid.gov.au/country/partnership.cfm )

· Draft Pacific Education and Training Agenda . June 2010

APTC Related Documents

· Activity Design Document: School of Tourism and Hospitality. April 2007

· Activity Design Document: School of Health and Community Services. April 2008

· Design Document: School of Automotive, Construction, Electrical and Manufacturing. April 2007

· Design Document: Coordination Office and Country Program. 14 February 2007

· Design Document: APTC Scholarships Program. June 2007

· APTC HIV and AIDS Framework Policy and Strategy 2007-2011. November 2007

· APTC Gender Access and Equality Policy Framework. November 2007

· Estimated APTC Scholarships Costs. October 2009

· Schofield et al. APTC Mid-Term Review. 22 June 2009

· APTC Six-Month Report to AusAID. April – September 2009

· APTC Scholarships Policy and Procedures Manual. April 2010
· Draft APTC Fee for Service Policy. Feb. 2010

· APTC Performance Assessment Framework. Feb. 2010

· Draft APTC 2010/11 Annual Plan. June 2010

Background Documents 

Asian Development Bank – Commonwealth Secretariat (2005). Toward a New Pacific Regionalism, an Asian Development Bank–Commonwealth Secretariat Joint Report to the Pacific Islands Forum Secretariat, http://www.adb.org/Documents/Reports/Pacific-Regionalism/default.asp
ADB-PIFS (2008). Skilling the Pacific: Technical and Vocational Education and Training in the Pacific. Pacific Islands Forum Secretariat, Fiji. Asian Development Bank May 2007. http://www.adb.org/Documents/Books/Skilling-Pacific/default.asp
ILO (2008). Conclusions on skills for improved productivity, employment growth and development. International Labour Conference, 2008

ILO (2008). Skills for improved productivity, employment growth and development, International Labour Conference, 97th Session, 2008, Report V, International Labour Office, Geneva. http://www.ilo.org/public/english/ employment/ skills/download/ilcreport.pdf
Pacific Islands Forum Secretariat (2005) The Pacific Plan for Strengthening Regional Cooperation and Integration, Suva: Pacific Islands Forum Secretariat

Pacific Islands Forum Secretariat (2009). Pacific Education Development Framework. 2009-2015

Pacific Islands Forum (2009). Forum Communiqué. Fortieth Pacific Islands Forum. Cairns Compact on Strengthening Development Coordination in the Pacific. August 2009. 

Annex D: Pacific TVET Context

1. Pacific Development Context

1.1 Pacific Country Diversity

The 2008 Asian Development Bank (ADB) Skilling the Pacific report suggests that the Pacific countries be grouped, for the purposes of analysis, into three groups, taking into consideration the considerable diversity in the region and different stages and prospects for development. ADB has grouped the Pacific countries into the following groups: 
1: land-rich, low-income countries—namely, Papua New Guinea (PNG), Solomon Islands, and Vanuatu; 

2: small, vulnerable island states—namely, Kiribati, Republic of the Marshall Islands, Federated States of Micronesia, Nauru, and Tuvalu; and 

3: “advanced” island states—namely, Cook Islands, Fiji Islands, Palau, Samoa, and Tonga. 

The countries in group 1 have low social and economic indexes, but positive agricultural potential. The vulnerable island states, group 2, face severe economic constraints, few economic prospects, and issues of sustainability. Countries in 
group 3 have relatively good prospects from tourism, remittances from abroad, and emigration.
1.2 Demographics 

Annual population growth in the Pacific is estimated at about 3.1%, and if sustained, will lead to a doubling of the Pacific Islands population in 23 years (from 9.2 million at present to 18.3 million by 2033). The Pacific region has high birth rates and a high proportion of young people, with a median age of approximately 21 years old. This sustained population growth will result in significant and sustained pressure on infrastructure and provision of health, education and social services. The Pacific faces issues related to shortage of schooling opportunities, inadequate educational and training outputs, lack of access to waged employment, and inadequate supply of skilled human resources required for economic growth and poverty reduction. 

Migration from rural to urban centres and emigration (or the movement of people from the country of origin and settlement in another country - generally Australia, New Zealand and the USA), has become a major labour market factor in most PICs, except for PNG, Vanuatu and Solomon Islands
. The impacts of emigration vary according to its duration, with long-term emigration having implications for economic growth and social cohesion and resulting in a substantial loss of the skilled workforce in the country of origin. Women and children are especially vulnerable to the impacts of emigration and urbanization because of changing values and standards, disruption of social support systems and loss of income opportunities derived from non-formal sector employment on which subsistence economies are mainly based. 

1.3 Gender

AusAID’s 2007 gender policy (Gender equality in Australia’s aid program – why and how) identifies four key interrelated factors that need to be addressed in development programs: a) access to economic and other resources; b) participation and leadership in decision making; c) respect for the human rights of women and; d) an increased capacity to tackle gender inequalities. The policy indicates that greater focus is needed on the transition from school to employment, and on technical and vocational education to address youth unemployment and gender-based occupational segregation, for both young men and women. This policy recognises that achieving employment equity, necessary to improve the standard of living and reduce poverty, requires targeted interventions with government and industry leaders to ensure female graduates find suitable employment with equitable remuneration. 

Education is critical to advancing women’s knowledge and skills, expanding opportunities for their economic and social development, and that of their families, and increasing their participation and representation in all levels and spheres of society. Achieving gender-balanced participation in education assists not only in promoting social justice, but it is also a matter of good economics and sound sectoral management. Investment in gender equality, particularly in health and education, yields to some of the highest returns of all development investments
.
There is further growing awareness and recognition in the Pacific region of the need to improve the situation of women’s lives, and of the benefits that will be gained when women and men are able to participate as equals in all aspects of economic, social, cultural and political life. Gender equality has become a key objective and cross-cutting issue in most Pacific Island country-level and regional development plans including the Pacific Plan endorsed by Forum Leaders in 2005. Many PICs have endorsed Equal Opportunity Legislation and committed to the achievement of the Millennium Development Goals which include to “Promote Gender Equality and the Empowerment of Women”. 

In contrast with general education, where in most PICs gender parity is almost reached, the TVET system generally favours males over females. Internal and external constraints in the TVET system, as well as gender imbalance in access to and successful completion of skills training, serves to amplify marginalization of women and other disadvantaged groups. Research indicates that there are multiple causes of female under-enrolment in TVET including public perception, cultural values, parental bias, employer preferences and lack of equal employment policies and enforcement. Factors internal to the TVET system also discriminate against girls and women including the lack of female boarding facilities, community support services, security issues and the low proportion of female teachers. 
The 2008 ADB Skilling the Pacific study also identifies a widespread gender bias when it comes to the types of informal sector training provided to men and women in the Pacific; men tend to monopolize technical and trades training while women are found almost exclusively in home economics and domestic science-related programs. The exception is in the tourism industry where hospitality-related courses provided in local vocational centres are in good demand from local hotels and resorts, resulting in a high proportion of female students in some schools. 
Because many females lack the basic skills to be considered employable in some jobs, this directly limits their ability to improve their own welfare and that of their families. Regional statistics indicate that women are also marginalized by lower wages, sexual harassment and occupational discrimination. Marginalization is further compounded by the lack of female participation on advisory boards and decision-making processes in most PICs. These factors, especially when combined, seriously constrain women’s ability to start their own businesses or compete for jobs in local and international labour markets, making it extremely difficult for women to lift themselves out of poverty. Some countries have identified specific targets in relation to increasing participation of women in leadership and decision-making processes. For example, the Fiji Government MDG reports stipulate that by 2005, 50% of people on government boards and other public bodies should be women. At present, however, women make up only about 19% of these total appointments and these are concentrated on minor health and welfare boards and committees
.

1.4 HIV and AIDS 

AusAID is developing a new International HIV Strategy for Australia to build on the overarching aims, priorities and principles established in Meeting the Challenge: Australia’s International HIV/AIDS Strategy (2004). 

There are important development links in the Pacific context accentuated by HIV and AIDS prevalence. HIV and AIDS cannot be considered in isolation of other issues such as gender inequalities, including violence against women, which increases women’s vulnerability to HIV in the Pacific. The high rates of STIs in Pacific countries, and the lack of STI treatment services, all contribute to an increasing risk of infection across the region.

Of the PICs, PNG has a generalised epidemic (prevalence consistently over 1% in pregnant women nationwide) and overall prevalence estimated at between 40,000 and 60,000 people currently infected with HIV. This is the fourth highest prevalence rate in the Asia Pacific Region. No other PICs apart from PNG have reported more than 300 HIV+ cases since testing commenced; however, infection rates are thought to be rising in other nations
. For example, only one quarter of persons deemed at-risk of HIV infection in Fiji, Kiribati and Vanuatu, know how to prevent HIV infections and do not harbour major misconceptions about HIV transmission. In Samoa, Solomon Islands and Vanuatu, 9% of young men said they had bought sex in the previous 12 months, yet only one in ten of them reported using condoms consistently during commercial sex. Only about 12% of young men said they used condoms consistently with casual partners
. 

Even in low HIV prevalence PICs, high prevalence of STIs already imposes a significant disease burden on young adults. Measures to reduce STIs (e.g. treatment or condoms) will also help to reduce the likelihood of an expanding HIV epidemic. Issues of pregnancy and relationships are also very important and can seriously impact on young adult learners. Family Planning service providers in the Pacific (both government and non government) can be an important source of education and information on pregnancy and relationships as well as HIV and STIs. 

Mobility of students between and within countries can lead to greater social and personal freedom resulting in increased experimentation in personal relationships, particularly those within the most sexually active age group (15-49 years). Mobility of students between countries is a concern because of the risks involved in students moving between high and low prevalence HIV countries. 

Gender inequalities make women and girls particularly vulnerable to contracting HIV and AIDS when their ability to negotiate safer sex or ward off unwanted sexual attention is compromised. Risk of infection is also increased for women who are away from home and without access to their usual support systems. 

Without more intensive prevention and surveillance, teenage pregnancy and sexually transmitted diseases, including HIV/AIDS, are expected to increase. The effectiveness of reproductive health programs is constrained by the “culture of denial”; the lack of public awareness about family planning and the need for safe sex; inadequate “youth-friendly” outreach services; and lack of inter-agency coordination. When students are deprived of information on reproductive health, sex education, and access to appropriate health services, the risk of increased transmission remains high. 

When it becomes particularly severe, HIV and AIDS can damage the supply, demand and quality of education. HIV/AIDS can affect the supply of education through its impact on teaching and other education personnel, and by making increasing demands on limited financial resources. The demand for education is impacted by the affects of HIV/AIDs on students and their families, reducing enrolments through a combination of illness, death, and the need for students to stay at home to provide care for relatives (noting that home care for the sick is usually a role for women rather than men). It affects the quality of education by diverting resources and by absenteeism of staff and learners.

2. TVET in the Pacific

2.1 National TVET Provision

Skills development is important for both economic efficiency and social equity. The right kind of skills development has a positive impact on long run economic growth, individual earnings and the distribution of income. It makes people more employable and makes them more productive at work. Strengthening national TVET capacity will both strengthen the national skills pool and strengthen entry level competencies and pathways for students. 

In addition to pre-vocational course offerings (industrial arts and home economics) in secondary schools, most PICs have both public and private (primarily church-based but also for-profit) vocational training centres and post-secondary technical institutes offering technical and vocational training. The latter include the Fiji Institute of Technology (FIT), Vanuatu Institute of Technology (VIT), National University of Samoa – Institute of Technology (NUS-IOT) and the Solomon Islands College of Higher Education (SICHE) offering certificate-level training and, in some cases, degrees as well (FIT). These institutions vary significantly in size with 7600 EFTS enrolments at FIT, compared to 500 at VIT and 225 at the Kiribati Institute of Technology. 

Financing for the provision of TVET comes from multiple sources. Public financing constitutes the majority source through ministry budgets – however, in many cases, this is declining. Private financing through tuition charges and fees is also important in about half of the PICs, while production activities partly finance the costs of some non-profit training providers. Three levy systems exist, but only one, Fiji Islands, puts a significant amount of financing directly into training. Almost all countries depend on external financing for capital expenditures. However, in the past, TVET in most Pacific countries has not received the same priority for capital or recurrent budget support as primary (and tertiary) education. Most TVET institutions in the Pacific suffer from common shortcomings, including poor teacher skills with inadequate industry experience, obsolete equipment and curricula, funding shortages and deteriorating infrastructure. Moreover, they have limited capacity and it is estimated that they would serve no more than 10% of the eligible population.

A considerable amount of skills development also takes place within enterprises, often via apprenticeship arrangements. PNG and Fiji have the most developed programs, enrolling some 900 and 650 apprentices a year respectively. Instead of TVET graduates, many employers prefer to hire secondary school graduates with the right attitude and train them in-house to get the skills they need.

The ADB study
 concluded that in the Pacific, access by school leavers to technical and vocational education and training is low. Not only are the number of participants low, but there is an inequitable distribution across geographical areas, income groups and especially gender, resulting in widespread “poverty of opportunity”. 

There are gender and regional disparities in access to training opportunities. Technical institutes enrol a low proportion of females – about 30% in PNG, 37% at FIT and 42% at VIT – except in commerce, hospitality and tourism programs. Access to TVET opportunities is also limited outside capitals and in the outer islands, though some countries (Solomon Islands and Vanuatu) have established networks of rural training centres to serve remote rural communities. These centres are poorly funded and the quality of their training is low.

Many PICs increasingly see improved skills training, accredited nationally or internationally, as one solution to labour market issues such as skill shortages and emigration. An increasing number of national education plans are including TVET as a priority sub-sector, in recognition of the importance of employability outcomes for school leavers and the importance of private sector productivity for economic growth. However, progress on this front has been slow. 

While the relative emphasis given to vocational training in schools and post-secondary (tertiary) TVET in such national plans varies - as does the relative emphasis given to TVET for the formal and informal labour market - there is a general trend to give the development of technical and vocational skills a higher priority. In the main this is not able to be matched by significant budget allocations and it remains the “poor relation” within the education sector in many Pacific countries.

Few PICs have clear strategies, long-term plans or resources available to establish effective skills development systems. Quality-assured national skill standards or externally recognised qualifications are rare. Available training is supply-driven and often of low or variable quality. Access to skills development is uneven and favours males in urban areas. With a few exceptions, employer inputs to the direction, content, quality or financing of the skills development system are minimal. 
The Pacific Education Development Framework (PEDF), endorsed by the Forum Education Ministers in 2009, guides the further development of Pacific education. The PEDF is aligned with, and grounded in, the principles of the Pacific Plan and reflects the Pacific concept of regionalism where countries work together for their joint and individual benefit
. It addresses two broad agendas: (i) the Education for All (EFA) or the basic education agenda, which covers the foundation years of education, and (ii) the training/employment/economic agenda. The TVET outcome sought is that ...the supply of skills supplied by Pacific TVET systems responds to meet the needs of the informal sector and the changing labour market demands in the formal sector. 
The mutual recognition of qualifications between PICs is a related discussion item under the Pacific Island Countries Trade Agreement agenda, as there is a need to identify what formal qualifications will permit free movement of people. The role that the South Pacific Board for Educational Assessment (SPBEA) might play in skills recognition will need to be considered, given its work on a Regional Qualifications Register. For those without formal qualifications but with considerable experience, the situation is far less clear, and skills recognition as distinct from recognition of formal qualifications, will be a challenge. 
2.2 AusAID Support for Pacific TVET 

Australia recognises the power of education to help individuals reach their potential and societies to be stronger and more productive. Australia also recognises that poor quality post primary education and training can undermine gains made in basic education, national capacity, income generation, social stability and national development. 

Pacific Partnerships for Development (PPD) signed between Australia and many of the PICs anchor Australia’s development assistance to the individual countries of the region. The PPDs make reference to the Paris Declaration principles, common approaches and partnerships among donors under national coordination and leadership, and to report transparently on implementation. Many of the PPDs include Australian support for the education sector, support for gender equality and support for “the pursuit of sustainable economic growth strategies encompassing private sector and infrastructure development, economic reform, regional economic integration and pursuit of mutually-beneficial regional trade liberalisation". 
Almost all such Partnerships identify basic education and technical and vocational education as initial partnership priorities and many have implementation strategies that relate specifically to strengthening TVET (Kiribati, Tonga, Vanuatu and Samoa). The PNG Program is planning to develop an implementation strategy for TVET and AusAID is providing some support to Tuvalu’s TVET system.

AusAID’s 2010 Pacific Education and Training Agenda (PETA) guides AusAID’s education program in the region focusing on improving learning outcomes and increasing employability. The framework also provides guidance on interventions and strategies to deliver on priorities including the importance of partnerships, strengthening accountability for service delivery outcomes and promoting evidence based decision making. The PETA states that AusAID “will assist partner governments to ensure that Pacific islanders have access to regionally accepted and/or internationally recognized post-secondary professional, technical and vocational education and training across the region”.

Within the Pacific region, AusAID provides development assistance to both formal and non-formal TVET including support for the TVET architecture (policy, planning and organisational development), for local capacity development and for training delivery. At the regional level, Australia’s assistance to TVET focuses mainly on supporting the development of a Pacific Qualifications Register by the SPBEA and supporting direct training delivery through the APTC. The PETA recognises the potential of the APTC to lead the region in respect to higher level technical and vocational training. Meanwhile, Australia’s bilateral programs strengthen viable local institutions to meet local labour demand and provide suitable pathways into higher training via the APTC or other national or regional providers. 

2.3 Other Donor Support 

The international community – both donors and recipients – have made a series of commitments to changed approaches to aid delivery. These are most clearly articulated in the Paris Declaration on Aid Effectiveness and the Accra Agenda for Action which provide a point of reference for development co-operation. These statements cover a broad range of principles relating to aid effectiveness, including working within partner governments, strengthening country ownership over development and the medium-term predictability of aid. 

Nine of the PIF members
 are adhering to the Paris Declaration and are increasingly active in ensuring that the Paris Principles and the Accra Agenda are reflected in their national development policies and strategies
. 

Australia is widely seen as a lead donor in skills development, with a comparative advantage in relation to planning and delivering demand-driven, workplace relevant, standards-based and quality assured skills development. Australian and New Zealand qualifications are mutually recognised, and both are internationally recognised. The following other donors/multilateral agencies are active in supporting TVET in the Pacific:

· the European Community provides bilateral support in Vanuatu and Solomon Islands and regionally through support to the SPBEA
;

· the ADB operates mainly at regional level to support the implementation of the priority actions identified in its Skilling the Pacific report;

· the International Labour Organization provides support primarily through its national Decent Work Programs but also regionally. It has a keen interest in a range of skills issues including the development of labour market information systems with national labour departments; 
· NZAID supports TVET in Tonga (jointly with AusAID) and in other countries through in-country training and scholarships to New Zealand; 

· JICA supports TVET in various countries through technical training in Japan as well as in-country advisers in some countries including Samoa (NUS-IOT) and PNG (Lae and Port Moresby Technical Colleges); and

· the World Bank has provided support in the past for the development of National Skills Training Plan for the Solomon Islands.
3. Pacific Labour Markets

3.1 Pacific Employment 

The 2008 ADB report outlines the importance of providing 
post-training support in the transition from training to productive working activity. In particular, the study stresses the need for assistance in linking participants with potential employers, facilitating access to information on new products, markets, technical and business advisory services, and micro-credit. There is also a need to focus on the transitional needs of women and other student groups who may experience additional challenges securing work due to gender biases, family responsibilities and geographic isolation. 

Reliable, comprehensive and up-to-date statistics on the size of the formal wage employment sectors of the Pacific Islands, and on the relative importance of and growth in the relevant middle-level occupations, are not available. One of the most recent compilations is summarized in the following table:

Table 1 Selected employment statistics for Pacific Island countries

	Country
	Working-age population

 (15-54 years)

 in 2004
	Estimated total formal sector employment
	Estimated percentage of working age population employed in formal wage economy
	Estimated percentage of wage employees in occupational categories

	
	
	
	
	Craft, trade and related workers
	Sales and service workers

	Cook Islands
	7,300
	5,900
	81
	10
	18

	Fiji
	487,500
	120,000
	25
	11
	13

	Kiribati
	
	
	
	8
	17

	MI
	29,600
	10,300
	35
	
	20

	FSM
	61,800
	15,100
	25
	
	

	Nauru 
	
	
	
	15
	13

	Palau
	
	
	
	
	

	PNG
	3,320,200
	187,200
	6
	15
	14

	Samoa
	91,100
	57,100
	63
	12
	11

	Solomon Islands
	239,400
	22,177
	9
	6
	21

	Tonga
	51,800
	34,600
	67
	
	

	Tuvalu
	
	
	
	
	10

	Vanuatu
	111,000
	16,300
	15
	3
	18


Source: ADB Skilling the Pacific, 2008, Tables A.3.2 and A.3.4

As discussed earlier, the high birth rate and proportion of young people across the Pacific is expected to create mounting pressure on infrastructure and provision of health, education and social services throughout the region. In some PICs, youth unemployment is as high as 80% and the gap between the labour force and available wage positions is expected to widen further unless new jobs are created and skills needed for employment are developed. Unemployment is a key variable underpinning non-adaptive social behaviour such as substance abuse, crime and domestic violence, which are rapidly increasing in many PICs. Poverty levels and social tensions can be expected to rise where resources and opportunities do not match the growing number of young people and their aspirations.
Youth often face a multitude of interwoven issues that can trap them in a cycle of poverty. There is mounting public concern for this “lost generation” and a strong desire to stop the downward spiral across the region. The increasing pressure to better equip youth for employment has further intensified an already positive climate for strengthening basic education, upgrading training services and ensuring that qualifications earned are of value to the national and regional labour markets
. 
3.2 Market characteristics

As discussed, the PICs differ in their access to natural resources, geography, population and level of economic development; however, their labour markets share several characteristics:

· the majority of the Pacific Island workforce is engaged in informal subsistence work. The formal wage sector in most PICs is relatively small and a substantial share is accounted for by the public sector;

· most PICs are labour surplus countries, with few immediate prospects for providing cash work within the domestic economy for all those who seek it. Private sector growth will not create enough jobs for the large number of school leavers entering the labour market each year - the so called “youth bulge”. With few marketable skills, many young people are under-employed in informal or subsistence work or openly unemployed;

· there is a mismatch between training supply and the demand for skilled labour. The oversupply of unskilled workers co-exists in many PICs with shortages of appropriately skilled people. Many positions are filled by expatriate foreign workers (including Australians and New Zealanders), who are employed not only in managerial and professional roles but also as technicians and skilled tradespersons, and usually at a higher pay rate than national labour. These skills shortages and mismatches affect all sectors of the economy and constrain labour productivity, economic growth and the employment of nationals in available skilled jobs; and

· emigration is on the rise. Combined with the lack of economic opportunities and insecurity in many PICs, many people are emigrating to countries such as Australia, New Zealand, and the United States to look for work. While their remittances comprise a high proportion of GDP in many Pacific countries and have generally positive impacts, continuing out-migration contributes to widespread skills shortages and discourages some employers from investing in training. 
In many countries in the region most of the formal wage sector jobs are in public administration, with the private sector employing only very small numbers. However, as public sector employment is maintained at current levels or progressively reduced through privatisation, future jobs growth in the Pacific will be dependent on a private sector committed to creating employment opportunities for skilled Pacific Islanders. The private sector has a key role not only as a client of vocational training but also as a provider of both on- and off-the-job training and as the primary employer of apprentices and skilled workers in most PIFCs. 

The 2008 ADB report notes that skill shortages are widespread across the PICs and attributes this issue to three main factors:

· sector-specific growth in demand in the mining sector of PNG and in tourism in the Cook Islands, Fiji, Samoa, Tonga and Vanuatu has created rising demand for skilled labour, especially in hospitality and construction. In these countries, there is demand for skills in management, supervision and trades occupations capable of working to international standards;

· the low supply and quality of graduates from the TVET sector has also contributed to skill shortages across the region. Tradespersons are often unable to work competently in their trades despite holding formal qualifications - they often graduate without the core competencies that employers’ value such as reliability, teamwork and problem solving; and 

· there is also a demand for appropriately qualified workers to replace skills lost through emigration.

These skill shortages are creating bottlenecks for certain sectors. A high proportion of employers cited a variety of adverse consequences from skill shortages including loss of productivity, lower quality output, inability to grow, lower profits, problems with equipment maintenance and loss of markets. 
4. Pacific Regionalism

A 2005 report to the Pacific Islands Forum Secretariat Towards a New Pacific Regionalism, prepared jointly by the ADB and the Commonwealth Secretariat supported an approach to regional integration that went beyond the previous focus on regional cooperation and market integration to address some of the problems of governance confronted by PICs
. The report argued that in the Pacific and elsewhere, the largest benefits of regionalism have come from focusing on the type of regionalism that addresses their fundamental challenge, and that Pacific regionalism must move beyond regional cooperation in a range of fields if significant benefits are to be achieved.
 
In order for PICs to reap the benefits of labour migration while avoiding welfare losses, the report proposed that Forum members ensure, as far as possible, that labour flow from PICs to Australia and New Zealand be “additional” (that is, ensure that there is adequate national capacity to both train and replace migrating labour). Substantial attention to skills formation in PICs should also be central to a plan to generate the maximum benefits for all Forum members from enhanced labour market access.

In October 2005 the Pacific Island Forum (PIF) Leaders endorsed the Pacific Plan, with the goal of enhancing and stimulating economic growth, sustainable development, good governance and security for Pacific countries through regionalism. The Plan encompassed increased regional provision of services as well as market integration.

The document emphasises the need to strengthen and expand national and, where appropriate, regional vocational educational and training programs and strengthen their links with the labour market. To promote regional integration, the Pacific Plan calls on Forum members to: [integrate] trade in services, including temporary movement of labour, into the Pacific Island Countries Trade Agreement (PICTA).

At their meeting in August 2009, Forum Leaders launched negotiations for a new regional trade and economic agreement, the Pacific Agreement on Closer Economic Relations known as PACER Plus. Australia is motivated to support PACER Plus because it believes that it will help the Forum Island Countries to promote their own sustainable economic development. The negotiation of a new regional trade and economic agreement will create a regional trade area between Australia, New Zealand and the PICs. This offers opportunities to create jobs, enhance private sector growth, raise standards of living and boost long-term economic growth in FICs. Australian Ministers have stated clearly that PACER Plus will include skills development for PICs, equipping them for technical work both within the region and globally. In March 2009, Australian Trade Minister Simon Crean stated that he wanted to ensure PACER Plus would:

… create an environment in which the work force can be mobile within the region in the knowledge that we will assist in the training, through the training colleges, through our aid program, in developing the skills that are necessary, not only is there employment opportunities, but you are equipping a work force with a skill that they can use themselves within their own countries … a great example, not of using a trade agreement to simply open markets of getting a circumstance of which you are genuinely building the skill-base and the work force in a lasting sense for the region. 
... there is great potential to develop a region wide labour mobility and skills development program for the Pacific, particularly when you think about the large infrastructure projects within the region that are about to come on stream - the PNG LNG project, for example; the Australian Solomons Goldmine, as another example; and the defence initiated infrastructure build-up in Guam.

The recent round of PICTA negotiations led to a draft schedule of commitment and a draft conceptual framework for the Temporary Movement of Natural Persons (TMNP) (labour mobility) amongst the fourteen developing country members of the Forum. The first priority has been to tackle the higher end of occupational skill shortages – including doctors, other health professionals, academics, teachers and accountants. The Forum Trade Ministers agreed in October 2009 that during the preliminary stage of negotiations, within the next 12 months, members would focus on deepening understanding of common priority issues including, inter alia, regional labour mobility beyond Mode 4
, and discuss other priority issues including education. 

As regional integration gathers momentum in coming years, the temporary and permanent movement of skilled workers between PICs and from the PICS to Australia, New Zealand, USA and elsewhere will increase. This will particularly affect the skills base of labour exporting countries in what is commonly known as “brain drain”. This will require greater assistance to increase PICs supply side competitive capacity in a number of areas, including through the training and up-skilling of the Pacific workforce; capacity building support for technical training to broaden job opportunities for younger people at home and abroad; mutual recognition and; where possible, harmonisation of standards and qualifications. 

Annex E: APTC Draft 2010/11Course Profile

APTC Training Partners (as at June 2010)

	School
	Location
	Training Partners

	Tourism & hospitality
	Fiji
	Training and Productivity Authority of Fiji

Tanoa Hotels Group

	
	Samoa
	National University of Samoa – Institute of Technology

	
	Vanuatu
	Vanuatu Institute of Technology

	Automotive
	Fiji
	ASCO Motors

	
	PNG
	Ela Motors Port Moresby

Hastings Deering Port Moresby

Ok Tedi Mining Limited (Tabubil)

Boroko Motors

	
	Samoa
	National University of Samoa – Institute of Technology

	Manufacturing
	PNG
	Port Moresby Technical College

Ok Tedi Mining Limited (Tabubil)

New Britain Palm Oil Ltd

	
	Samoa
	National University of Samoa – Institute of Technology

	Construction & electrical
	Fiji
	Training and Productivity Authority of Fiji

Ministry of Works, Transport and Public Utilities

	
	PNG
	Port Moresby Technical College, 

Ok Tedi Mining Limited (Tabubil)

	
	Samoa
	National University of Samoa – Institute of Technology

	Health & community services
	Fiji
	Training and Productivity Authority of Fiji

	
	Vanuatu
	Vanuatu Ministry of Education


2010/11 APTC Courses under consideration (June 2010)

	SACEM Courses

	Fiji 

	BCG 30603 Painting and Decorating

	BCG 31303 Wall & Floor Tiling

	BCG 30203 Carpentry

	AUR 30405 Auto Mech Tech - ASCO Motors

	MEM 30205 Eng Mech Diesel Fit

	TAA Training and Assessment

	PNG POMTECH

	UEE 08 Systems Electrician

	BCG 30203 Carpentry

	AUR 30405 Auto Mech Tech

	MEM 30305 Engineering M Fab

	MEM 30305 Engineering Mechanics

	MEM 30205 Engineering Diesel Fit- Hasting Deering

	PNG – New Britain Palm Oil Limited (Kimbe)

	BCG 30203 Carpentry

	MEM 30205 Engineering Diesel Fit

	PNG – Ela Motors

	AUR 30405 Auto Mech Tech

	PNG – Boroko Motors

	AUR 30405 Auto Mech Tech

	UMW Lae

	MEM 30205 Engineering Diesel Fit

	Allied/Simberi Gold

	MEM 30205 Engineering Diesel Fit

	MEM 30205 Engineering Combined Mech & M Fab

	Samoa

	AUR 30405 Auto Mech Tech

	BCP 30103 Plumbing

	MEM 30205 Eng - Mech

	BCP 30103 Plumbing - Short Course - Gas and Roofing

	MEM 30205 Eng - Ref & A Cond

	MEM 30305 Eng - M Fab

	UTE 31199 Systems Electrician


	STH Courses

	Vanuatu

	Cert III in Children's Services

	Diploma of Children's Services

	Samoa

	Cert IV in Disability 

	Cert III in Children's Services

	Cert III in Aged Care

	Fiji

	Cert III in Children's Services

	Diploma of Children's Services

	Diploma of Community Services Work

	Cert III in Aged Care

	Cert IV in Disability


	SHCS Courses

	Vanuatu

	Cert III in Hospitality - Operations

	Cert III in Hospitality - Commercial Cookery

	Cert IV in Hospitality - Supervision

	Cert III in Tourism

	Samoa

	Cert III in Hospitality - Operations

	Cert IV in Hospitality – Supervision

	Cert III in Tourism - Operations

	Cert III in Hospitality - Commercial Cookery

	Fiji

	Cert III in Hospitality - Commercial Cookery

	Cert III in Hospitality - Patisserie

	Cert III in Tourism - Operations

	Cert III in Hairdressing

	Cert III in Hospitality - Operations


APTC Enrolment as at 28th April 2010 by Campus, by School, by Citizenship by Course

	SCHOOL/CITIZENSHIP/COURSE
	CAMPUS COUNTRY

	
	Fiji
	Kiribati
	PNG
	Samoa
	Vanuatu
	Total

	AUTOMOTIVE, CONSTRUCTION, ELECTRICAL AND MANUFACTURING

	Fiji CITIZENS

	Cert III Auto Mech Technology
	19
	
	
	8
	
	27

	Cert III Eng- Mechanical Trade
	46
	
	
	37
	
	83

	Cert III Eng-Fabrication Trade
	
	
	
	14
	
	14

	Cert III Painting/Decorating
	39
	
	
	
	
	39

	Certificate III in Carpentry
	46
	
	
	
	
	46

	Cert III Plumbing
	
	
	
	19
	
	19

	CIII Electrotech Sys Electricn
	
	
	2
	51
	
	53

	CIII Wall and Floor Tiling
	20
	
	
	
	
	20

	CIV Training and Assessment
	46
	
	
	
	
	46

	Non Accredited Program
	33
	
	
	8
	
	41

	Fiji Total
	249
	
	2
	137
	
	388

	Kiribati Citizens

	Cert III Auto Mech Technology
	1
	
	
	2
	
	3

	Cert III Eng- Mechanical Trade
	4
	
	
	1
	
	5

	Certificate III in Carpentry
	1
	
	
	
	
	1

	CIII Electrotech Sys Electricn
	
	
	
	1
	
	1

	Kiribati Total
	6
	
	
	4
	
	10

	Nauru Citizens

	Cert III Auto Mech Technology
	1
	
	
	
	
	1

	Cert III Eng- Mechanical Trade
	1
	
	
	
	
	1

	Non Accredited Program
	
	
	
	1
	
	1

	Nauru Total
	2
	
	
	1
	
	3

	Niue Citizens

	Cert III Auto Mech Technology
	1
	 
	 
	 
	 
	1

	Cert III Eng- Mechanical Trade
	2
	 
	 
	 
	 
	2

	CIII Electrotech Sys Electricn
	 
	 
	 
	1
	 
	1

	Niue Total
	3
	 
	 
	1
	 
	4

	PNG Citizens

	Cert III Auto Mech Technology
	 
	 
	90
	 
	 
	90

	Cert III Eng- Mechanical Trade
	 
	 
	171
	1
	 
	172

	Cert III Eng-Fabrication Trade
	 
	 
	9
	 
	 
	9

	Cert III Painting/Decorating
	4
	 
	 
	 
	 
	4

	Certificate III in Carpentry
	 
	 
	34
	 
	 
	34

	Certificate III in Plumbing
	 
	 
	 
	6
	 
	6

	CIII Electrotech Sys Electricn
	 
	 
	22
	 
	 
	22

	CIV Training and Assessment
	 
	 
	17
	 
	 
	17

	Non Accredited Program
	 
	 
	46
	 
	 
	46

	PNG Total
	4
	 
	389
	7
	 
	400

	Samoa Citizens

	Cert III Auto Mech Technology
	12
	 
	 
	17
	 
	29

	Cert III Eng- Mechanical Trade
	5
	 
	 
	21
	 
	26

	Cert III Eng-Fabrication Trade
	 
	 
	 
	28
	 
	28

	Certificate III in Carpentry
	6
	 
	 
	 
	 
	6

	Certificate III in Plumbing
	 
	 
	 
	3
	 
	3

	CIII Electrotech Sys Electrician
	 
	 
	 
	1
	 
	1

	CIII Electrotech Sys Electricn
	 
	 
	 
	21
	 
	21

	Non Accredited Program
	2
	 
	 
	11
	 
	13

	Samoa Total
	25
	 
	 
	102
	 
	127

	Solomon Is. Citizens

	Cert III Auto Mech Technology
	 
	 
	11
	 
	 
	11

	Cert III Eng- Mechanical Trade
	 
	 
	2
	 
	 
	2

	Certificate III in Carpentry
	 
	 
	5
	 
	 
	5

	Certificate III in Plumbing
	 
	 
	 
	1
	 
	1

	CIII Electrotech Sys Electricn
	 
	 
	6
	 
	 
	6

	CIV Training and Assessment
	1
	 
	 
	 
	 
	1

	Non Accredited Program
	 
	 
	4
	 
	 
	4

	Solomon Is. Total
	1
	 
	28
	1
	 
	30

	Sri Lanka Citizens (TAA) 

	CIV Training and Assessment
	 
	 
	1
	 
	 
	1

	Sri Lanka Total
	 
	 
	1
	 
	 
	1

	Tonga Citizens

	Cert III Auto Mech Technology
	2
	 
	 
	1
	 
	3

	Cert III Eng- Mechanical Trade
	 
	 
	 
	2
	 
	2

	Cert III Eng-Fabrication Trade
	 
	 
	 
	1
	 
	1

	Tonga Total
	2
	 
	 
	4
	 
	6

	Tuvalu
	 
	 
	 
	 
	 
	 

	Cert III Auto Mech Technology
	4
	 
	 
	 
	 
	4

	Tuvalu Total
	4
	 
	 
	 
	 
	4

	Vanuatu Citizens

	Cert III Auto Mech Technology
	4
	 
	 
	5
	 
	9

	Cert III Eng- Mechanical Trade
	 
	 
	 
	6
	 
	6

	Cert III Eng-Fabrication Trade
	 
	 
	 
	1
	 
	1

	Cert III Painting/Decorating
	4
	 
	 
	 
	 
	4

	Certificate III in Carpentry
	6
	 
	 
	 
	 
	6

	Certificate III in Plumbing
	 
	 
	 
	2
	 
	2

	CIII Electrotech Sys Electricn
	 
	 
	 
	10
	 
	10

	Non Accredited Program
	 
	 
	 
	1
	 
	1

	Vanuatu Total
	14
	 
	 
	25
	 
	39

	SACEM Total
	310
	 
	420
	282
	 
	1012


	HEALTH AND COMMUNITY SERVICES

	Fiji Citizens

	Certificate III in Children's Services    
	25
	 
	 
	 
	 
	25

	Diploma of Children's Services      
	20
	 
	 
	 
	 
	20

	Diploma of Community Services Work     
	12
	 
	 
	 
	 
	12

	Fiji Total
	57
	 
	 
	 
	 
	57

	Kiribati Citizens

	Certificate Iii In Children's Services    
	 
	 
	 
	 
	1
	1

	Kiribati Total
	 
	 
	 
	 
	1
	1

	Nauru Citizens

	Diploma of Community Welfare Work      
	 
	 
	 
	 
	2
	2

	Nauru Total
	 
	 
	 
	 
	2
	2

	Samoa Citizens

	Diploma of Community Services Work     
	5
	 
	 
	 
	 
	5

	Diploma of Community Welfare Work      
	1
	 
	 
	 
	1
	2

	Samoa Total
	6
	 
	 
	 
	1
	7

	Tonga Citizens

	CERTIFICATE III IN CHILDREN'S SERVICES    
	 
	 
	 
	 
	1
	1

	DIPLOMA OF COMMUNITY WELFARE WORK      
	1
	 
	 
	 
	2
	3

	Tonga Total
	1
	 
	 
	 
	3
	4

	Vanuatu Citizens

	CERTIFICATE III IN CHILDREN'S SERVICES    
	 
	 
	 
	 
	26
	26

	DIPLOMA OF CHILDREN'S SERVICES (EARLY CHILDHOOD ED. & CARE) 
	 
	 
	 
	 
	24
	24

	DIPLOMA OF COMMUNITY WELFARE WORK      
	 
	 
	 
	 
	14
	14

	Vanuatu Total
	 
	 
	 
	 
	64
	64

	HCS Total
	64
	 
	 
	 
	71
	135


	SCHOOL OF TOURISM AND HOSPITALITY

	Fiji Citizens

	CERTIFICATE III IN HAIRDRESSING      
	12
	 
	 
	 
	 
	12

	CERTIFICATE III IN HOSPITALITY      
	36
	 
	 
	2
	 
	34

	CERTIFICATE III IN HOSPITALITY (COMMERCIAL COOKERY)  
	42
	 
	 
	 
	 
	42

	CERTIFICATE III IN HOSPITALITY (OPERATIONS)    
	3
	 
	 
	 
	 
	3

	CERTIFICATE III IN HOSPITALITY (PATISSERIE)    
	12
	 
	 
	 
	 
	12

	CERTIFICATE IV IN HOSPITALITY (SUPERVISION)    
	2
	 
	 
	 
	 
	2

	CERTIFICATE IV IN TRAINING AND ASSESSMENT    
	 
	 
	 
	1
	 
	1

	Fiji Total
	107
	0
	0
	3
	0
	106

	Kiribati Citizens

	CERTIFICATE III IN HOSPITALITY      
	5
	 
	 
	 
	 
	5

	CERTIFICATE III IN HOSPITALITY (COMMERCIAL COOKERY)  
	2
	 
	 
	 
	1
	3

	CERTIFICATE IV IN TRAINING AND ASSESSMENT
	 
	1
	 
	 
	 
	1

	Kiribati Total
	7
	1
	 
	 
	1
	9

	Marshall Is. Citizens

	CERTIFICATE III IN HOSPITALITY      
	1
	 
	 
	 
	 
	1

	Marshall Is. Total
	1
	 
	 
	 
	 
	1

	Nauru Citizens

	CERTIFICATE III IN HOSPITALITY (COMMERCIAL COOKERY)  
	1
	 
	 
	 
	 
	1

	Nauru Total
	1
	 
	 
	 
	 
	1

	Niue Citizens

	CERTIFICATE III IN HOSPITALITY (COMMERCIAL COOKERY)  
	 
	 
	 
	1
	 
	1

	Niue Total
	 
	 
	 
	1
	 
	1

	Palau Citizens

	CERTIFICATE III IN TOURISM      
	 
	 
	 
	1
	1
	2

	CERTIFICATE IV IN HOSPITALITY      
	 
	 
	 
	1
	 
	1

	Palau Total
	 
	 
	 
	2
	1
	3

	PNG Citizens

	CERTIFICATE III IN HAIRDRESSING      
	2
	 
	 
	 
	 
	2

	CERTIFICATE III IN HOSPITALITY (OPERATIONS)
	9
	 
	 
	8
	19
	36

	CERTIFICATE III IN HOSPITALITY (COMMERCIAL COOKERY)  
	 
	 
	 
	2
	13
	15

	CERTIFICATE III IN HOSPITALITY (PATISSERIE)    
	2
	 
	 
	 
	 
	2

	CERTIFICATE III IN TOURISM      
	 
	 
	 
	5
	16
	21

	CERTIFICATE IV IN HOSPITALITY      
	 
	 
	 
	8
	 
	8

	PNG Total
	13
	 
	 
	23
	48
	84

	Samoa Citizens

	CERTIFICATE III IN HOSPITALITY (OPERATIONS)    
	 
	 
	 
	32
	 
	32

	CERTIFICATE III IN HOSPITALITY (COMMERCIAL COOKERY)  
	 
	 
	 
	20
	 
	20

	CERTIFICATE III IN TOURISM (OPERATIONS)    
	 
	 
	 
	17
	 
	17

	CERTIFICATE IV IN HOSPITALITY      
	 
	 
	 
	8
	 
	8

	CERTIFICATE IV IN TRAINING AND ASSESSMENT    
	 
	 
	 
	17
	 
	17

	Samoa Total
	0
	0
	0
	94
	0
	94

	Solomon Is. Citizens

	CERTIFICATE III IN HOSPITALITY      
	 
	 
	 
	2
	4
	6

	CERTIFICATE III IN HOSPITALITY (COMMERCIAL COOKERY)  
	1
	 
	 
	 
	5
	6

	CERTIFICATE III IN HOSPITALITY (PATISSERIE)    
	1
	 
	 
	 
	 
	1

	CERTIFICATE IV IN HOSPITALITY      
	 
	 
	 
	3
	 
	3

	Solomon Is. Total
	2
	 
	 
	5
	9
	16

	Tonga Citizens

	CERTIFICATE III IN HOSPITALITY      
	 
	 
	 
	4
	 
	4

	CERTIFICATE III IN HOSPITALITY (COMMERCIAL COOKERY)  
	 
	 
	 
	6
	 
	6

	CERTIFICATE III IN TOURISM      
	 
	 
	 
	6
	 
	6

	Tonga Total
	 
	 
	 
	16
	 
	16

	Tuvalu Citizens

	CERTIFICATE III IN HOSPITALITY      
	3
	 
	 
	 
	 
	3

	CERTIFICATE III IN HOSPITALITY (COMMERCIAL COOKERY)  
	2
	 
	 
	 
	 
	2

	CERTIFICATE III IN HOSPITALITY (PATISSERIE)    
	2
	 
	 
	 
	 
	2

	Tuvalu Total
	7
	 
	 
	 
	 
	7

	Vanuatu Citizens

	CERTIFICATE III IN HOSPITALITY (OPERATIONS)    
	 
	 
	 
	 
	56
	56

	CERTIFICATE III IN HOSPITALITY (COMMERCIAL COOKERY)  
	 
	 
	 
	 
	38
	38

	CERTIFICATE III IN TOURISM (OPERATIONS)    
	 
	 
	 
	 
	20
	20

	CERTIFICATE IV IN HOSPITALITY (SUPERVISION)    
	 
	 
	 
	 
	13
	13

	CERTIFICATE IV IN TRAINING AND ASSESSMENT    
	 
	 
	 
	 
	3
	3

	Vanuatu Total
	0
	0
	0
	0
	130
	130

	STH Total
	138
	1
	 
	144
	189
	472

	Grand Total
	512
	1
	420
	426
	260
	1619


Annex F: APTC Stage II Scholarships Policies and Procedures
5. APTC Scholarships Overview

1.1 Goal and Principles

APTC Scholarships are administered strategically to support APTC’s overall goals: to increase the supply of skilled workers in targeted sectors in the Pacific region; to improve national, regional and international employment opportunities for Pacific Islander women and men with Australian qualifications in targeted sectors; and to increase the productivity of individuals and organisations in targeted industries and sectors. 

The specific goal of the APTC Scholarships is to promote access to the APTC, especially for individuals from smaller island states where APTC does not have a campus and for those without other means of financial support. This is achieved through providing financial support for Pacific Islanders to attend the APTC, to upgrade their vocational skills and receive an Australian qualification.

The scheme objective is to administer scholarship procedures that maximise opportunities for students from all Pacific Forum countries to access and successfully complete APTC programmes with a particular focus on redressing gender, isolation and income discrimination and ensuring that student health and welfare concerns are proactively and professionally addressed.

The key principles for the way in which the APTC Scholarships should be implemented are that they should:

· adhere to principles of transparency and merit;

· ensure access and equity, including sensitivity to gender and disability;

· complement and not duplicate other sources of financial sponsorship for students including from the private sector, other donors, and Pacific governments; 

· support flexibly structured award delivery to reflect the varied training schedules of APTC schools; and

· be structured to be cost-effective in order to maximise the number of awards that can be offered.

1.2 Consistency with Existing AusAID programs

In delivering development assistance, the Australian Government recognises that capacity building forms an important part of supporting effective government and is committed to helping enhance the capacity of partner countries to manage their own affairs. The Australian aid program will also have an ongoing focus on gender equality and helping marginalised and disadvantaged groups. Australian Scholarships seeks to promote sustainable development and excellence in education in the Asia-Pacific region. Through the provision of scholarship opportunities, Australia seeks to contribute to long-term development, stability and security of Australia’s partner countries and establish and maintain mutually beneficial linkages. Australia also recognises the important role that alumni networks have in meeting these objectives and improving overall effectiveness of the scholarship program.

In their approach to scholarships, AusAID actively pursues quality, access and equity throughout the management cycle, with a strong emphasis on improving the front-end of award management through clear and effective targeting, effective promotion and the ability to measure effectiveness. AusAID’s approach maximises transparency and accountability in the application, shortlisting and selection process, and emphasises a stronger engagement with alumni.

To reflect the APTC goals and objectives, the APTC scholarship policies and processes vary from the core bilateral Australian Scholarships for the Pacific. Given its labour mobility objectives (unlike the long-term Australian Development Scholarships (ADS) and the Australian Regional Development Scholarships (ARDS) schemes), the APTC awards do not have a requirement for graduates to return home for two years on completion of their training and before they can apply for migration to Australia. Whilst ADS/ARDS are long-term awards, the APTC application and selection processes and scholarship benefits have been designed to match the shorter term, block structure and flexible delivery of many of the APTC courses. 

APTC Scholarships are also managed wholly by the APTC, rather than as for most of the major AusAID scholarship scheme where the scheme is managed by a separate contractor to that providing the training. A student may receive a number of consecutive APTC awards to enable them to progress through to the highest level of the course available at the APTC. The APTC awards also have a number of different levels of award entitlements to reflect the higher proportion of awardees that are studying in their home country.

2. Access and Equity

2.1 Overview

APTC Scholarships are open to all citizens of PIF countries (except Australia and New Zealand), who over the age of 18 and meet the technical entry (and English language/numeracy) requirements for specific APTC courses. As far as practical, APTC Scholarships seek to incorporate a principle of equity to seek that all target applicants (including women and persons living with disabilities) are offered equivalent opportunities to be offered awards. This means actively assisting historically disadvantaged groups to compete with those who may not need assistance to apply or receive a scholarship. This does not mean that sub-standard applicants will be ‘allowed through’ the selection process. Only those applicants who meet all necessary requirements (once assistance has been applied) will be offered awards.

The APTC is responsible for delivering training that is responsive to industry needs in order to secure employer funding for workers to attend the APTC. As a result, not all APTC places will be funded through the scholarship scheme. APTC Scholarships should not be provided to applicants who have alternative sources of financial support to attend the College (for example funded by larger employers, other donors, or home governments). 
Other APTC policies with respect to gender equity, disability, HIV/AIDS and other cross-cutting issues detailed in the APTC Stage II design apply equally to the APTC Scholarships. Indeed the scholarships provide an enabling mechanism for addressing such issues, particularly with regard to increasing female participation at the APTC.

5.1 Scholarships Allocation Model

As in Stage I, the APTC Awards will be managed as a regionally competitive scholarship scheme, allowing flexibility to offer awards to reflect course availability, applicant demand, provide equitable access for all PIF countries and to make any adjustments necessary to realise program outcomes. The APTC Chief Executive Officer is responsible for developing and implementing agreed guidelines to ensure that the APTC Awards are allocated across countries, schools and gender in an equitable, transparent and standard manner. 

A Scholarships Allocation Model was developed during Stage I to assist in determining the fair allocation of scholarship awards across countries. This model uses a natural logarithm methodology to determine scholarship allocation based on each PIC’s population size and GDP. This approach results in a distribution of awards positively favouring those countries that are smaller, less economically developed and that do not have an APTC campus (so face a higher relative cost of attending APTC courses overseas and reduced opportunity for employer funded access). External criteria for geographic distribution of scholarships may also need to be applied to take into consideration AusAID’s diverse range of existing and potential commitments across the Pacific. 
5.1.1 Gender Equity

To support gender equity, APTC Scholarships promote equal access to the APTC for both men and women. Pre-award processes, including scholarship advertisement and selection, are targeted to promote gender equity in students undertaking APTC training courses. While some training sectors are traditionally dominated by one gender (e.g. men in trades areas, or women in the health sector), marketing materials are targeted so that women and men are actively encouraged to apply for training in all schools, particularly for courses which are not traditional areas of employment for their gender. During selection, efforts are made to allocate APTC awards evenly between eligible female and male candidates. For example, in training courses dominated by male applicants, awards are allocated evenly between males and females until no further females are eligible for placement/award.

5.1.2 Rural and Economically Disadvantaged

Students from rural or economically disadvantaged backgrounds are encouraged to undertake training at the APTC through the availability of APTC Scholarships and targeted marketing campaigns. At this stage, however, the majority of APTC courses are necessarily targeted at applicants who have work experience and are in employment so that they are able to undertake the required work experience/assessment components of their course. Where possible, the APTC will also conduct courses for candidates with work experience or technical qualifications who are not currently employed. 

Experience from other scholarships programs in the Pacific suggests that it is difficult to verify students’ claims to disadvantage and, as such, the APTC Scholarships selection criteria cannot directly target rural or economically disadvantaged students. In practice, where there are two students of equal technical merit, the APTC should prioritise the applicant with proven links (through birth, schooling or employment) to a rural/remote area for a scholarship. The Partial Awards levels provide a higher level of allowances for students from rural areas.
6. Management and governance arrangements

AusAID is the principal Australian Government body responsible for the oversight of the APTC. AusAID Suva or the other Pacific Posts do not take on day-to-day management or coordination of APTC Scholarships. Scholarship reporting to AusAID Suva is included in the regular APTC reporting. Where requested by the AusAID Post in campus countries, the APTC will provide regular briefings and may also seek advice from the Post as to any country-specific implementation issues. The APTC will also be guided by the Post with respect to any civil or natural emergency situations.

AusAID and the APTC GM have responsibility for high level consultations on APTC matters with senior representatives of the various Pacific governments. As the APTC Scholarships are managed as regional scheme, Pacific governments are not involved in the selection of awardees or administration of other aspects of the scheme. In Stage II, Pacific governments will be consulted on the APTC Annual Training Profile and their country’s training and scholarship priorities through regular consultation and the development of APTC Country Strategies.

The Advisory Group may also be consulted on scholarship matters, and will be provided with relevant scholarship statistical reports. 

AusAID will contract the management and implementation of the APTC Scholarships to the APTC Stage II Contractor, as part of the broader APTC contract. The APTC CEO has delegated responsibility from AusAID for the overall strategic development, management and coordination of the APTC Scholarships. The GM will ensure that all aspects of the scheme are managed in a way that is consistent, transparent, fair and merit based. The GM will be assisted in scheme management by the Scholarships Coordinator, and APTC staff in the campus and selected non-campus countries as required to:

· provide strategic advice to AusAID on future directions; 

· develop and implement scholarship policies, procedures and operational guidelines (including selection and eligibility criteria);

· determine indicative scholarship numbers by country/gender/school for each selection round;

· undertake the communication and marketing of scholarships information; 

· administer the scholarship application and selection processes;

· offer scholarship awards to successful applicants (and advise unsuccessful applicants);

· mobilise awardees (including visas and pre-departure briefings) and provide advice to awardees on arranging passports and health checks;

· organise and pay for student travel (at start/end award and between blocks of training);

· arrange awardee accommodation;

· meet awardees at campus country airports (including those transiting from one country to another);

· provide orientation on scholarship specific matters (allowances, award conditions etc);

· arrange health insurance;

· pay scholarship allowances or stipends to awardees; 

· administer financial management of other scholarships related expenditure; 

· approve award variations (e.g. changes to award lengths, terminations, student appeal process);

· manage end award processes; and

· maintain and provide data for the reporting, monitoring and evaluation of the scholarships (as integrated into the overall APTC Performance Framework).

For reasons of transparency, there should wherever possible be separation of scholarship responsibilities between the Schools and APTC Corporate and Student Services (CSS).The direct responsibilities of the APTC Schools with respect to scholarships include:

· assessment of technical merit and ELLN competency of scholarship applications;

· provision of a ranked shortlist (by course/country) of scholarship applications and any selection recommendations to APTC CSS; and

· recommendations for award variations.
Responsibilities for scholarship functions should be clearly clarified for campus countries, non-campus countries with APTC representation and other non-campus countries. The Contractor will update the Stage I APTC Scholarships Policy and Procedures Manual during the transition period to reflect any changes to management processes and responsibilities. 
7. Award Eligibility and Benefits

7.1 APTC Courses

To reflect the range of APTC course lengths and delivery modes, scholarships will be offered for the courses annually approved within the APTC Training Profile. Awards may be provided to support a student to undertake a single short-term course or to enable a student to undertake either a longer-term course (of a year or more) or back-to-back short-term courses where a student will progress though a number of short-term courses to graduate with an APTC qualification. The progression between course levels would not need to be continuous, in consideration of workplace or family demands where they exist, but should be structured to minimise travel costs for overseas students.
No scholarships will be offered for Certificate TAE4 training, as these courses will be delivered on a fee for service basis. 

The APTC does not provide scholarships for Certificate I and II level training. Alternative sources of funding need to be used to provide education and training at this level either in-country or overseas. 
7.2 Award Eligibility

To be eligible for APTC Scholarship an applicant must:

· have citizenship in a Pacific Island Forum country;
· not have citizenship or permanent residency of New Zealand or Australia, except where their country does not issue passports and they hold New Zealand passports (i.e. citizens of Cook Islands, Niue or Tokelau);

· not hold dual citizenship with a country outside of a Pacific Island Forum country;

· be over the age of 18; 

· satisfy the admission requirements of APTC School’s course entry (including technical, English language/literacy and numeracy requirements); 

· not have access to another source of funding (e.g. through their employer) that would offer support for a similar standard of training;
· not have had an Australian or New Zealand Government scholarship that has been terminated; 

· if they have had an ARDS award, have completed that award (applicants are eligible to apply for an APTC Scholarship directly after completion of their ARDS award. This will not negate any of their other ARDS award conditions, including the ARDS requirement to return home to work in their country for at least two years following completion of their APTC training); and
· be able to take up the award at the start of the course for which it is offered.

A student may receive a number of consecutive APTC awards to enable them to progress through to the highest level of the course available at the APTC.
7.3 Award Levels

To promote access to the College for those without alternative financial support, whilst maximising the number of students who will benefit from the scheme, two levels of scholarship are offered: Full Awards and Partial Awards (Levels 1, 2, or 3).

The Full and Partial Award entitlements and the basis for calculation should be the same across all campus countries. However, as costs for the same item will vary between countries, cash entitlements such as the Full Award Stipend and Supplementary Training Benefit need to be calculated separately for each campus country. The benefits should be increased annually by an agreed price rise index, or recalculated should there be extraordinary price movements in a country. Changes to the amount of the allowance need to be approved in advance by AusAID and factored into annual budget plans.

7.4 Full Award Entitlements
Full Awards are provided for students undertaking full-time training at an APTC campus not located in their home country. Full Awards are not only for students from Non Campus Countries (NCCs) but also for students from campus countries having to travel overseas to attend a specific APTC course.
The Full Award entitlements include a number of components:
· Tuition fees – tuition fee waiver;

· Travel - including international air travel
 and domestic air, road and/or boat travel to the international airport. This applies to awardee travel on award commencement, between training blocks and on completion of their award. CSS will either directly book and fund this travel or compensate the student on production of receipts;
· Pre-departure Costs - which covers visa costs, but does not cover pre-departure costs such as passport purchase, police and health checks. These costs may be reimbursed through the Supplementary Training Benefits (STB), with awardees responsible for meeting these costs upfront;
· Supplementary Training Benefits – which include cash payments covering the costs associated with international travel including excess baggage or unaccompanied luggage (in- and out- bound), passport, medical and police check (if necessary), international banking fees associated with your APTC payments and unexpected costs associated with international travel. The STB also includes in-kind contributions covering initial required consumables, learning materials, and equipment;
· Living costs - including basic living costs such as accommodation, food and transport (paid as a stipend). 
· Health Insurance - basic health insurance; and
· Compassionate travel - payment for once-off compassionate travel is provided for under special circumstances and compassionate reasons concerning an immediate family member which includes a student’s parents, spouse or children.
7.5 Partial Award Entitlements 

The three levels of the Partial Award allow for the broader application of allowances and recognise the diverse circumstances and needs of local students. For local students undertaking APTC courses at a campus located within their home country:

· Level 1: provides support for students who live/work in remote locations and need extra support to relocate to an APTC campus within the campus country; 
· Level 2: provides support for students who are required to travel some distance to an APTC campus within the country on a daily basis. It includes proportional meal allowance for lunches and also supports additional transport costs; and

· Level 3: provides support for students who live close to an APTC campus within the country. The level of support is closely aligned to the equivalent standard minimum daily wage and is designed to compensate the student for daily expenses, particularly when they are required to take ‘leave without pay’ to attend APTC classes. 

The table below indicates the entitlements for each of the Partial Award levels with respect to tuition fees, in-country travel, living allowance and Supplementary Training Benefits.
Table 1: Partial Scholarship Entitlements (d)

	Level of Partial Scholarship
	Tuition Fee Waiver
	In-country travel(a)
	% Total Stipend (b)
	Supplementary Training Benefits (c)

	Level 1 
	· 
	· 
	100%
	No cash applicable. In - kind benefits provided by Schools

	Level 2 
	· 
	
	40%
	No cash applicable. In - kind benefits provided by Schools

	Level 3 
	· 
	
	25%
	No cash applicable. In - kind benefits provided by Schools


(a) Travel: domestic sea and air travel to and from point of departure to campus location

(b) A fortnightly stipend to cover a proportion of living costs including accommodation, meals, living costs, and incidentals
(c) Supplementary Training Benefits: may include required consumables, learning materials, and equipment (called an Establishment Allowance in other scheme

(d) Part time students are also eligible for a Partial Scholarship and receive pro rata benefits according to study load, e.g. a student studying 2 days would receive 0.4 of applicable full time study benefits.

7.6 Ancillary Awards

Eligible SIS students in the ELLN bridging program will receive support for their training, through an ‘Ancillary Award’. Those undertaking the bridging program in a campus country will receive the same level of financial support as under a Full Award. Students undertaking the program in their home country will be provided with basic financial support provided equivalent to that of the Partial Scholarships Level 3. The APTC should ensure that the financial value of the Ancillary Awards is consistent with other in-country training support provided by AusAID.
8. Scholarship Processes

8.1 Pre-Award 

8.1.1 Annual Allocations by Country

The Contractor will review the Scholarships Allocation Model during the transition period and annually for the Annual Report/Plan, to ensure the continuing equitable distribution of scholarships between countries/schools. 
The APTC GM will annually review the number of scholarships awarded to each country. This will enable appropriate promotion of awards in order to redress any imbalances in scholarship allocations for the forthcoming year. Over the course of the year, the Contractor should also monitor total scholarship expenditure so that available funding and course places are effectively utilised. The planned allocation of awards is indicative and the average scholarship costs are highly variable. The distribution of awards may also need to be varied in the second selection cycle to reflect demand considerations and the quality of applicants in each category. Any reasons for significant and consistent variations will need to be addressed by the APTC in the Annual Report/Plan. Where necessary, the Scholarships Allocation Model may need to be varied with AusAID approval.
8.1.2 Marketing and Communication

Promoting an APTC "brand" with a distinct Australian identity is a key priority in operating the APTC. APTC Scholarships promotion will be undertaken in conjunction with overall APTC marketing in accordance with the overall APTC communication strategy. While APTC Scholarships are managed separately from other awards funded by the Australian Government, the scholarships should remain clearly and unambiguously an initiative of the Australian Government. The marketing and communication should focus on increasing the visibility, impact and equity of the APTC Scholarships; provides strategies for increased participation of women and for addressing the needs of people living with disabilities. Specific focus should be placed on the strategy for marketing the scholarships to the SIS with no APTC representation and to other rural/isolated locations.

8.1.3 Application/Selection Process

The scholarship application process is integrated with the application process for entry into APTC courses. There will be two scholarship selection rounds each year, which will enable progressive entry into College courses starting at varying times throughout the year. Applications from all eligible APTC candidates enter competitive pools for each course available for the upcoming training period. The number of new scholarships to be offered each year will be based on funding availability including consideration of the funding required for continuing awardees.

The award of scholarships will be guided by the Scholarships Allocation Model (the indicative allocation of awards by country), the Annual Training Profiles (the target number of Full/Partial scholarship places by course), and the Country Strategies (country priorities for training). Within these guides and ensuring gender equity where possible, scholarships are offered to the most technically qualified applicants. 

RTOs are responsible for assessing awardee course entry eligibility based on their ability to meet the relevant School and course criteria and their English language/numeracy competency, reflecting their ability to pass the course with the assistance of concurrent English language/numeracy support, if required. 
The School will provide a technical ranking of the applications for each course by student, home country, and gender. They may also make specific recommendations for applicants based on other relevant factors. Unsuccessful scholarship applicants from previous selection rounds will be carried over into the ranking where appropriate.

The APTC CSS will then determine a list of successful scholarship applicants to be offered scholarships during the selection cycle, ensuring a geographic and gender equity balance across all scholarships. In doing so, they should also take into consideration the impact on labour supply if too many awardees are selected from one employer/location in the SIS at the same time. They may also recommend adjustments to the number of scholarship places available in each course (within limits initially agreed with the Schools). The scholarships list will then be reviewed and signed-off by the APTC Senior Management Team or other delegated senior staff. The shortlist of awards for Fiji citizens should be sent to AusAID for approval before scholarships are awarded.
It is noted that the Stage II design includes for reintegration plans to be trialled at the APTC. During Stage II, the Contractor should assess whether reintegration plans should be included as part of the selection process for existing workers, so that scholarships are allocated where there is most likelihood of training skills being utilised back in the workplace.

Scholarship offers should also be over-programmed to allow for candidate deferral, with this initial percentage to be adjusted with program experience. The successful applicant may defer offer of course place and scholarship in a few circumstances: where they face a serious family problem, serious medical or mental health condition; where the applicant is pregnant or is hospitalized for more than three weeks during the course time; or where an employer requests a deferral, which would be assessed on a case by case basis. A scholarship can be deferred only once, and after that deferral the applicant must reapply.

Given the large demand for scholarships in campus countries, combined scholarship/course applications can be accepted and assessed for technical merit and entry to the APTC on an ongoing basis throughout the year, and then considered for scholarship within the relevant period.

8.1.4 Scholarship Application/Selection Cycle

Scholarships commenced before July 2011 will continue into Stage II and awardees will need to be advised of any changes to their support/contact points within the APTC. Arrangements will also need to be made for awardee stipend payments to be continued without interruption. There are no changes to scholarship award policies that affect continuing students.

From Stage II, the number of scholarships to be offered for each course will be based on the number of places specified in the Annual Training Profile. 

For new Stage II scholarships for training commencing between July-December 2011, the APTC will continue to follow the Stage I rolling application process.

For new Stage II scholarships for training commencing January 2012, the following process will apply:

· Assessment of scholarship applications will be undertaken during two scholarship selection cycles a year.

· Within a context of balancing gender and SIS access, applicants with the highest technical merit for each course/campus will be offered scholarships. 

· Where there is high demand for scholarships for a course, a shortlist (indicatively 300% of the available scholarship places in a course) of applications will be identified for technical merit assessment as part of the scholarships process. 

· Scholarship applications assessed as meeting course entry requirements but not awarded a scholarship for the forthcoming period will be advised that:

· they can take up a tuition fee only place;

· they will be included on a waitlist for awardee withdrawals; and

· their application will roll-over to the next scholarship selection period (but will be assessed against new applications).

· Where possible, applicants from SIS with eligible technical merit but not meeting ELLN requirements will be provided with ELLN bridging programs 

The two selection rounds will be managed as per the indicative timing below:

[image: image1.wmf]Submission of proposed training profile for next FY  (Jul-Jun)

Jan

Update training profile for next period (Jan-Jun)

July

 

Advertise courses for next period

Aug

Feb

Scholarship Application Closing date

Mid Sep

Mid Mar

Scholarship Application Screening

Sep

Apr

Scholarship Application Assessment

Oct-Nov

Apr-May

Scholarship Ranking and Selection

Nov-Dec

May-Jun

Award Offer

Dec

Jun

Mobilisation

Dec-May

Jun-Nov

Training Period

Jan-Jun

Jul-Dec


8.1.5 Mobilisation/demobilisation

The Contractor will develop a mobilisation plan for each awardee, including facilitating logistics, arranging and paying for health insurance and travel to and from the study country and return and facilitating for lodging visa applications. Passports are the responsibility of each applicant. Once the applicant has accepted the scholarship offer they must gather all relevant documents for their passport and visa application. 

The Contractor will also arrange a pre-departure briefing (PDB) for individuals or groups of awardees. PDBs provide essential information that students need upon arrival in their study country, such as advice from APTC alumni, the AusAID Post and other sources about living and studying overseas. It is expected that the PDB will help the awardees to quickly settle into the APTC, thereby enhancing their ability to complete their studies within the duration of their award. PDBs also provide an opportunity to remind students of their scholarship entitlements and obligations. Where possible, students should arrive up to 7 days prior to the start of their course.

8.1.6 On-Award Support

Duty of Care is an APTC wide responsibility from mobilisation to de-mobilisation. The APTC Contractor is responsible for awardee reception and orientation on arrival in the campus/host country. They will also arrange secure awardee accommodation, pay the awardee their allowances and make any approved reimbursements. The Contractor will arrange and pay for travel between training blocks and provide pastoral health and welfare support to all scholarship students. Additional support may be required for students living away from home/overseas for the first time. Special needs assistance may be required for people with a disability. The APTC should manage awardee compassionate leave on a case by case basis.
8.1.7 Post-Award

APTC scholarship (and non-scholarship) graduates will be part of the APTC alumni network. The establishment of an APTC alumni network will support and promote program objectives through:

· facilitating the provision of contact information for M&E purposes; 

· accessing alumni for operational purposes, such as the provision of practical assistance and mentoring to new awardees and as a resource in other key areas;

· a forum for active discussion and exchange of ideas/expertise relevant to the achievement of the APTC objectives; and

· enabling alumni to exchange knowledge and skills. 

Annex G: APTC Stage I Cost Structure Analysis

Analysis Notes

i. There is no consolidated APTC financial database. 
ii. The figures used in this analysis are those supplied to the team in April 2010 on request from the Stage I contractors: SKM, SCIT and BHI. 
iii. The contractors were asked to provide details of design, capital and recurrent costs, by year (actual and planned), for each school and program, as well as for the management and support facilities in-country and in-Australia. 
iv. It was found that the financial classification systems used are not uniform, and not all data was supplied. 
v. The total figure does not include the AUD$8.8 million set aside for AusAID support, or the AUD$10 million scholarship component. Even including these figures, the total expenditure data falls short of the AUD$150 million budget for the College.
Summary Analysis

· Table 1 shows: 

· an imbalance in the development costs between the three contractual partners

· difference in the civil works components, due mainly to the SACEM development at the PoMTech site and the STH development in Vanuatu

· the almost identical expenditures on teachers and trainers by the two RTOs, and the similar expenditures on other operational items such as staff travel, teaching materials and utilities;
· the ‘other operational costs’ component for the CO includes staff wages, salaries and other personnel expenses

· Over fifty percent of the recurrent costs of APTC were allocated to management and support. This proportion would be an even higher percentage if all Coordination Office (CO) running costs are included, and if the AusAID support figure is also factored in (see Table 4). The bulk of this management and support is for RTO operations in Australia

· The conclusion that the whole APTC program could be delivered for significantly less than in Stage I – for example there is obviously great scope for cost-efficiencies in management and support – is difficult to escape. 

· Figures 3 and 4 show that there has been no ‘typical’ year during Stage I. Indeed, the impact of the APTC being a four year program with significant start-up costs is clear. 2009 is the only year to date that has had anything like a full schedule of activity, and is therefore the one used in the calculation of per-student and per-training hour costs – see Tables 6 and 7 and 8.

· More details of costs per student and per training hour are shown in Table A.4. The way in which the cost estimates for the cost per student and cost per training hour are arrived at is shown in Annex H. Cost per student estimates are used in the CBA calculations, whilst cost per training hour can be used as the basis for setting contract costing norms for tendering purposes.

Table 1: APTC Stage I cost of operations (AUD)

	category and location
	Coordination Office
	School
	Total

	
	
	SACEM
	STH
	SHCS
	

	Design and development costs
	79,844
	96,076
	706,726
	597,634
	1,480,280

	Capital costs
	
	
	
	
	

	 
	civil works
	-
	9,266,662
	2,012,735
	11,279,397

	 
	equipment and machinery
	414,785
	1,745,973
	726,193
	2,886,951

	 
	Total capital
	414,785
	11,012,635
	2,738,928
	14,166,348

	Recurrent costs
	
	
	
	
	

	 
	management and support
	
	
	
	
	

	 
	in-country
	6,461,035
	12,975,798
	2,920,238
	22,357,070

	 
	in-Australia
	
	8,476,664
	11,114,605
	19,591,269

	 
	sub-total
	6,461,035
	21,452,461
	14,034,843
	41,948,339

	 
	teachers and instructors
	-
	10,389,631
	10,314,874
	20,704,505

	
	transport and travel
	299,667
	2,864,992
	500,619
	3,665,278

	 
	rental and hiring charges
	146,802
	1,516,057
	1,058,865
	2,721,724

	 
	other operational costs
	4,346,322
	2,411,446
	4,437,521
	11,195,289

	 
	Total recurrent
	11,253,826
	38,634,587
	30,346,722
	80,235,135

	Total costs of operation
	11,748,455
	49,743,298
	34,390,010
	95,881,763


Source Table A.1

Table 2: APTC Stage I capital expenditure, by school and location (AUD)

	Category and location
	Coordination Office
	School
	Total

	
	
	SACEM
	STH/SHCS
	

	Civil works
	
	
	
	

	
	Australia
	
	
	
	-

	
	Fiji
	
	
	299,571
	299,571

	
	PNG
	
	7,137,280
	
	7,137,280

	
	Samoa
	
	2,129,382
	529,377
	2,658,759

	
	Vanuatu
	
	
	1,183,787
	1,183,787

	
	Total
	-
	9,266,662
	2,012,735
	11,279,397

	Machinery and equipment
	
	
	
	

	
	Australia
	
	116,975
	
	116,975

	
	Fiji
	414,785
	159,587
	393,325
	967,697

	
	PNG
	
	895,844
	
	895,844

	
	Samoa
	
	573,567
	155,001
	728,568

	
	Vanuatu
	
	
	177,867
	177,867

	
	Total
	414,785
	1,745,973
	726,193
	2,886,951

	Total capital works
	
	
	
	

	
	Australia
	-
	116,975
	-
	116,975

	
	Fiji
	414,785
	159,587
	692,896
	1,267,268

	
	PNG
	-
	8,033,124
	-
	8,033,124

	
	Samoa
	-
	2,702,949
	684,378
	3,387,327

	
	Vanuatu
	-
	-
	1,361,654
	1,361,654

	
	Total
	414,785
	11,012,635
	2,738,928
	14,166,348


Source Table A.1

Table 3: APTC Stage I recurrent expenditure by category and location (AUD)

	Category and location
	Coordination Office
	School
	Total

	
	
	SACEM
	STH/SHCS
	

	Management and support
	
	
	
	

	
	Australia
	
	8,476,664
	11,114,605
	19,591,269

	
	Fiji
	6,461,035
	2,851,435
	1,067,901
	10,380,371

	
	PNG
	
	6,640,694
	
	6,640,694

	
	Samoa
	
	3,483,669
	889,342
	4,373,011

	
	Vanuatu
	
	
	962,995
	962,995

	
	Total
	6,461,035
	21,452,461
	14,034,843
	41,948,339

	Teachers and instructors
	
	
	
	

	
	Australia
	
	
	
	-

	
	Fiji
	
	2,909,053
	3,738,039
	6,647,092

	
	PNG
	
	4,384,732
	
	4,384,732

	
	Samoa
	
	3,095,845
	2,558,278
	5,654,123

	
	Vanuatu
	
	
	4,018,557
	4,018,557

	
	Total
	-
	10,389,631
	10,314,874
	20,704,505

	Transport and travel
	
	
	
	

	
	Australia
	
	
	
	

	
	Fiji
	299,667
	647,340
	166,817
	1,113,825

	
	PNG
	
	1,687,205
	
	1,687,205

	
	Samoa
	
	530,447
	125,145
	655,592

	
	Vanuatu
	
	
	208,657
	208,657

	
	Total
	299,667
	2,864,992
	500,619
	3,665,278

	Rental and hire charges
	
	
	
	

	
	Australia
	
	193,600
	
	193,600

	
	Fiji
	146,802
	494,359
	387,624
	1,028,785

	
	PNG
	
	593,533
	
	593,533

	
	Samoa
	
	234,564
	160,140
	394,704

	
	Vanuatu
	
	
	511,101
	511,101

	
	Total
	146,802
	1,516,057
	1,058,865
	2,721,724

	Other operating expenditure
	
	
	
	

	
	Australia
	
	
	
	-

	
	Fiji
	4,645,989
	911,520
	1,829,304
	7,386,814

	
	PNG
	-
	3,215,845
	-
	3,215,845

	
	Samoa
	-
	1,149,073
	1,285,006
	2,434,079

	
	Vanuatu
	-
	-
	1,823,830
	1,823,830

	
	Total
	4,645,989
	5,276,438
	4,938,140
	14,860,568

	Total Recurrent Expenditure
	
	
	
	

	
	Australia
	-
	8,670,264
	11,114,605
	19,784,869

	
	Fiji
	11,253,826
	7,166,368
	7,022,868
	25,443,062

	
	PNG
	-
	14,834,805
	-
	14,834,805

	
	Samoa
	-
	7,963,150
	4,892,766
	12,855,916

	
	Vanuatu
	-
	-
	7,316,483
	7,316,483

	
	Total
	11,253,826
	38,634,587
	30,346,722
	80,235,135


 Source Table A.1

Table 4: APTC Stage I recurrent expenditure by category (percent of total)

	Cost category
	Coordination Office
	School
	Total

	
	
	SACEM
	STH/SHCS
	

	
	management and support
	
	
	
	

	
	in-country
	} 57.4%
	33.6%
	9.6%
	27.9%

	
	in-Australia
	
	21.9%
	36.6%
	24.4%

	
	sub-total
	57.4%
	55.5%
	46.2%
	52.3%

	
	teachers and instructors
	
	26.9%
	34.0%
	25.8%

	
	transport and travel
	2.7%
	7.4%
	1.6%
	4.6%

	
	rental and hiring charges
	1.3%
	3.9%
	3.5%
	3.4%

	
	other operational costs
	38.6%
	6.2%
	14.6%
	14.0%

	
	Total recurrent
	100.0%
	100.0%
	100.0%
	100.0%


Source Table A.1

Figure 1: APTC Stage I recurrent expenditure by category

(AUD$million)

[image: image2.wmf]0

10

20

30

40

50

CO 

ACEM

STH/SHCS

teachers and instructors

transport and travel

rents and hire charges

other operating costs

in

-

country management and support 

in

-

Australia management and support


Source Table w

Figure 2: APTC Stage I recurrent expenditure by category

(percent of total)

[image: image3.wmf]0%

20%

40%

60%

80%

100%

CO 

ACEM

STH/SHCS

teachers and instructors

transport and travel

rents and hire charges

other operating costs

in

-

country management and support 

in

-

Australia management and support


Source Table g

Figure 3: APTC recurrent expenditure, 2007 to 2010 (AUD)

[image: image4.wmf]0

2

4

6

8

10

12

14

16

18

20

2007

2008

2009

2010

M

i

l

l

i

o

n

s

Coordinating Office

ACEM

STH/SHCS


Figure 4: APTC recurrent expenditure by category, 2007 to 2010 (AUD)

[image: image5.wmf]0

1

2

3

4

5

6

7

8

9

10

2007

2008

2009

2010

M

i

l

l

i

o

n

s

in

-

country management and support

in

-

Australia management and support

teachers and instructors

transport and travel

rental and hiring charges

other operational costs


Table 5: APTC recurrent expenditure by category, 2009

	
	
	AUD$
	percent of total

	Coordination, management and support 
	
	

	 
	Coordination Office
	1,988,835
	6.7%

	 
	RTO in-Australia management and support
	6,892,286
	23.3%

	 
	RTO in-country management and support
	6,383,371
	21.6%

	Total coordination, management and support 
	15,264,492
	51.6%

	RTO operations
	
	

	 
	teachers and instructors
	9,154,191
	30.9%

	 
	transport and travel
	1,761,305
	6.0%

	 
	rental and hiring charges
	1,038,191
	3.5%

	 
	other operational costs
	2,360,387
	8.0%

	Total RTO operations
	14,314,074
	48.4%

	Total APTC expenditure
	29,578,566
	100.0%


Figure 5: APTC recurrent expenditure by category, 2009 (AUD)

[image: image6.wmf]0

1,000,000

2,000,000

3,000,000

4,000,000

5,000,000

6,000,000

CO

ACEM

STH/SHCS

other operational costs

rental and hiring charges

transport and travel

teachers and instructors

in

-

country management and support

in

-

Australia management and support


Figure 6: APTC recurrent expenditure by category, 2009 (percent)

[image: image7.wmf]Coordinating 

Office

7%

RTO in

-

Australia 

management and 

support

23%

RTO in

-

country 

management and 

support

22%

teachers and 

instructors

31%

transport and 

travel

6%

rental and hiring 

charges

3%

other operational 

costs

8%


Costs per student and per student hour

Table 6: APTC estimated average annual costs per student in 2009 (AUD)

	
	 Fiji 
	 PNG 
	 Samoa 
	 Vanuatu 
	 All 

	 SACEM 
	
	
	
	
	

	 Automotive 
	12,690
	16,752
	23,527
	
	16,409

	 Construction and electrical 
	14,194
	19,217
	19,362
	
	17,287

	 Manufacturing 
	
	19,298
	18,013
	
	19,261

	 TAA 
	12,513
	9,596
	
	
	11,443

	 All SACEM programs 
	13,800
	17,431
	19,410
	
	16,806

	 STH 
	
	
	
	
	

	 Tourism and hospitality 
	13,233
	
	15,205
	12,979
	13,611

	 SHCS 
	
	
	
	
	

	 Children's and Community Services 
	13,037
	
	
	12,784
	12,912

	 All APTC programs 
	12,674
	17,431
	17,136
	11,357
	14,699


Table 7: APTC estimated total average costs per student training hour in 2009 (AUD)

	
	Fiji
	PNG
	Samoa
	Vanuatu
	All 

	SACEM
	 
	 
	 
	 
	 

	Automotive
	31.2
	44.4
	45.4
	
	41.3

	Construction and electrical
	30.3
	36.9
	49.1
	
	37.2

	Manufacturing
	
	23.8
	44.6
	
	30.9

	 TAA 
	66.4
	26.3
	
	
	45.2

	All SACEM programs
	35.0
	34.6
	46.8
	
	37.2

	STH
	
	
	
	
	

	Tourism and hospitality
	25.4
	
	33.9
	27.2
	27.9

	SHCS
	
	
	
	
	

	Children's and Community Services
	33.1
	
	
	32.4
	32.8

	All APTC programs
	30.8
	34.6
	42.0
	28.5
	33.9


Table 8: APTC estimated average direct program delivery costs in 2009 (AUD)

[image: image8.wmf]program 

recurrent cost

enrolments

average cost per 

enrolled student

training hours

training hours 

per enrolled 

student

average cost 

per training 

hour

$

$

$

Automotive

Fiji

436,195

             

 

88

                     

 

4,957

                 

 

35,788

               

 

407

                   

 

12.2

                

 

PNG

1,693,889

          

 

249

                   

 

6,803

                 

 

93,950

               

 

377

                   

 

18.0

                

 

Samoa

411,173

             

 

34

                     

 

12,093

               

 

17,635

               

 

519

                   

 

23.3

                

 

Vanuatu

Total

2,541,257

          

 

371

                   

 

6,850

                 

 

147,373

             

 

397

                   

 

17.2

                

 

Construction & Electrical

Fiji

1,141,519

          

 

180

                   

 

6,342

                 

 

84,230

               

 

468

                   

 

13.6

                

 

PNG

1,410,918

          

 

153

                   

 

9,222

                 

 

79,585

               

 

520

                   

 

17.7

                

 

Samoa

1,089,831

          

 

126

                   

 

8,649

                 

 

49,730

               

 

395

                   

 

21.9

                

 

Vanuatu

Total

3,642,269

          

 

459

                   

 

7,935

                 

 

213,545

             

 

465

                   

 

17.1

                

 

Manufacturing

Fiji

114,666

             

 

-

                    

 

PNG

993,396

             

 

112

                   

 

8,870

                 

 

90,840

               

 

811

                   

 

10.9

                

 

Samoa

653,292

             

 

96

                     

 

6,805

                 

 

38,790

               

 

404

                   

 

16.8

                

 

Vanuatu

Total

1,761,353

          

 

208

                   

 

8,468

                 

 

129,630

             

 

623

                   

 

13.6

                

 

Training and Assessment 

Fiji

360,887

             

 

69

                     

 

5,230

                 

 

13,005

               

 

188

                   

 

27.7

                

 

PNG

40

                     

 

-

                    

 

14,590

               

 

365

                   

 

-

                  

 

Samoa

Vanuatu

Total

360,887

             

 

109

                   

 

3,311

                 

 

27,595

               

 

253

                   

 

13.1

                

 

All ACEM Programs

Fiji

2,053,267

          

 

337

                   

 

6,093

                 

 

133,023

             

 

395

                   

 

15.4

                

 

PNG

4,098,203

          

 

554

                   

 

7,397

                 

 

278,965

             

 

504

                   

 

14.7

                

 

Samoa

2,154,296

          

 

256

                   

 

8,415

                 

 

106,155

             

 

415

                   

 

20.3

                

 

Vanuatu

Total

8,305,766

          

 

1,147

                 

 

7,241

                 

 

518,143

             

 

452

                   

 

16.0

                

 

Tourism and Hospitality

Fiji

1,485,339

          

 

261

                   

 

5,691

                 

 

117,946

             

 

452

                   

 

12.6

                

 

PNG

Samoa

1,099,097

          

 

158

                   

 

6,956

                 

 

62,644

               

 

396

                   

 

17.5

                

 

Vanuatu 

1,342,591

          

 

243

                   

 

5,525

                 

 

100,007

             

 

412

                   

 

13.4

                

 

Total

3,927,027

          

 

662

                   

 

5,932

                 

 

280,597

             

 

424

                   

 

14.0

                

 

Health and Community Services

Fiji

529,259

             

 

93

                     

 

5,691

                 

 

33,708

               

 

362

                   

 

15.7

                

 

PNG

Samoa

-

                    

 

-

                    

 

Vanuatu 

513,831

             

 

93

                     

 

5,525

                 

 

33,708

               

 

362

                   

 

15.2

                

 

Total

1,043,090

          

 

186

                   

 

5,608

                 

 

67,416

               

 

362

                   

 

15.5

                

 

Total APTC

Fiji

4,067,865

          

 

691

                   

 

5,887

                 

 

284,677

             

 

412

                   

 

14.3

                

 

PNG

4,098,203

          

 

554

                   

 

7,397

                 

 

278,965

             

 

504

                   

 

14.7

                

 

Samoa

3,253,393

          

 

414

                   

 

7,858

                 

 

168,799

             

 

408

                   

 

19.3

                

 

Vanuatu 

1,856,422

          

 

336

                   

 

5,525

                 

 

133,715

             

 

398

                   

 

13.9

                

 

Total

13,275,883

         

 

1,995

                 

 

6,655

                 

 

866,156

             

 

434

                   

 

15.3

                

 


Excluding capital and management/support costs

Appendixes 
Table A.1: Expenditure on APTC operations, 2007 to 2011*

	category and location
	Coordination Office
	School
	Total

	
	
	SACEM
	STH*
	SHCS
	

	Design and development costs
	
	
	
	
	

	
	Australia
	79,844
	96,076
	706,726
	597,634
	1,480,280

	Civil works
	
	
	
	
	

	
	Australia
	
	
	
	
	-

	
	Fiji
	
	
	299,571
	
	299,571

	
	PNG
	
	7,137,280
	
	
	7,137,280

	
	Samoa
	
	2,129,382
	529,377
	
	2,658,759

	
	Vanuatu
	
	
	1,183,787
	
	1,183,787

	
	Total
	-
	9,266,662
	2,012,735
	-
	11,279,397

	Machinery and equipment
	
	
	
	
	

	
	Australia
	
	116,975
	
	
	116,975

	
	Fiji
	414,785
	159,587
	393,325
	
	967,697

	
	PNG
	
	895,844
	
	
	895,844

	
	Samoa
	
	573,567
	155,001
	
	728,568

	
	Vanuatu
	
	
	177,867
	
	177,867

	
	Total
	414,785
	1,745,973
	726,193
	-
	2,886,951

	Total capital costs
	
	
	
	
	

	
	Australia
	-
	116,975
	-
	-
	116,975

	
	Fiji
	414,785
	159,587
	692,896
	-
	1,267,268

	
	PNG
	-
	8,033,124
	-
	-
	8,033,124

	
	Samoa
	-
	2,702,949
	684,378
	-
	3,387,327

	
	Vanuatu
	-
	-
	1,361,654
	-
	1,361,654

	
	Total
	414,785
	11,012,635
	2,738,928
	-
	14,166,348

	Other infrastructure expenditure**
	
	
	
	
	

	
	Australia
	
	193,600
	
	
	193,600

	
	Fiji
	146,802
	494,359
	387,624
	
	1,028,785

	
	PNG
	
	593,533
	
	
	593,533

	
	Samoa
	
	234,564
	160,140
	
	394,704

	
	Vanuatu
	
	
	511,101
	
	511,101

	
	Total
	146,802
	1,516,057
	1,058,865
	-
	2,721,724

	Teachers and instructors
	
	
	
	
	

	
	Australia
	
	
	
	
	-

	
	Fiji
	
	2,909,053
	3,738,039
	
	6,647,092

	
	PNG
	
	4,384,732
	
	
	4,384,732

	
	Samoa
	
	3,095,845
	2,558,278
	
	5,654,123

	
	Vanuatu
	
	
	4,018,557
	
	4,018,557

	
	Total
	-
	10,389,631
	10,314,874
	-
	20,704,505

	Transport and travel
	
	
	
	
	

	
	Australia
	
	
	
	
	-

	
	Fiji
	299,667
	647,340
	166,817
	
	1,113,825

	
	PNG
	
	1,687,205
	
	
	1,687,205

	
	Samoa
	
	530,447
	125,145
	
	655,592

	
	Vanuatu
	
	
	208,657
	
	208,657

	
	Total
	299,667
	2,864,992
	500,619
	-
	3,665,278

	Other operating expenditure
	
	
	
	
	

	
	Australia
	
	
	
	
	-

	
	Fiji
	4,346,322
	264,180
	1,662,487
	
	6,272,989

	
	PNG
	
	1,528,640
	
	
	1,528,640

	
	Samoa
	
	618,626
	1,159,861
	
	1,778,487

	
	Vanuatu
	
	
	1,615,173
	
	1,615,173

	
	Total
	4,346,322
	2,411,446
	4,437,521
	
	11,195,289

	Management and support
	
	
	
	
	

	
	Australia
	
	8,476,664
	11,114,605
	
	19,591,269

	
	Fiji
	6,461,035
	2,851,435
	1,067,901
	
	10,380,371

	
	PNG
	
	6,640,694
	
	
	6,640,694

	
	Samoa
	
	3,483,669
	889,342
	
	4,373,011

	
	Vanuatu
	
	
	962,995
	
	962,995

	
	Total
	6,461,035
	21,452,461
	14,034,843
	-
	41,948,339

	Total Recurrent Expenditure
	
	
	
	
	

	
	Australia
	-
	8,670,264
	11,114,605
	-
	19,784,869

	
	Fiji
	11,253,826
	7,166,368
	7,022,868
	-
	25,443,062

	
	PNG
	-
	14,834,805
	-
	-
	14,834,805

	
	Samoa
	-
	7,963,150
	4,892,766
	-
	12,855,916

	
	Vanuatu
	-
	-
	7,316,483
	-
	7,316,483

	
	Total
	11,253,826
	38,634,587
	30,346,722
	-
	80,235,135

	Total expenditure
	
	
	
	
	

	
	Australia
	79,844
	8,883,315
	12,418,965
	
	21,382,124

	
	Fiji
	11,668,611
	7,325,955
	7,715,764
	
	26,710,330

	
	PNG
	-
	22,867,929
	-
	
	22,867,929

	
	Samoa
	-
	10,666,099
	5,577,144
	
	16,243,243

	
	Vanuatu
	-
	-
	8,678,137
	
	8,678,137

	
	Total
	11,748,455
	49,743,298
	34,390,010
	
	95,881,763


Table A.2: APTC Stage I recurrent expenditure by year (AUD)

	
	
	2007
	2008
	2009
	2010
	2011

	
	Coordination Office
	
	
	
	
	

	 
	management and support
	
	
	
	
	

	 
	in-country
	926,278
	899,605
	899,605
	2,281,526
	1,454,020

	 
	in-Australia
	
	
	
	
	

	 
	sub-total
	926,278
	899,605
	899,605
	2,281,526
	1,454,020

	 
	teachers and instructors
	-
	-
	-
	-
	-

	 
	transport and travel
	16,486
	58,918
	58,918
	68,266
	97,080

	 
	rental and hiring charges
	18,958
	30,092
	30,092
	50,838
	16,821

	 
	other operational costs
	97,411
	1,000,220
	1,000,220
	1,434,153
	814,317

	 
	Total recurrent
	1,059,134
	1,988,835
	1,988,835
	3,834,784
	2,382,238

	
	SACEM
	
	
	
	
	

	 
	management and support
	
	
	
	
	

	 
	in-country
	997,182
	5,602,895
	5,545,457
	830,264
	-

	 
	in-Australia
	1,314,162
	3,065,313
	3,651,728
	445,460
	

	 
	sub-total
	2,311,344
	8,668,209
	9,197,185
	1,275,724
	-

	 
	teachers and instructors
	512,959
	2,922,169
	5,639,808
	1,314,695
	-

	 
	transport and travel
	173,853
	1,005,455
	1,484,764
	200,920
	-

	 
	rental and hiring charges
	123,397
	561,089
	714,885
	116,686
	-

	 
	other operational costs
	23,046
	1,141,639
	1,181,194
	65,567
	-

	 
	Total recurrent
	3,144,599
	14,298,560
	18,217,835
	2,973,592
	-

	
	STH/SHCS
	
	
	
	
	

	 
	management and support
	
	
	
	
	

	 
	in-country
	156,643
	654,431
	837,914
	882,795
	388,455

	 
	in-Australia
	599,619
	2,288,428
	3,240,558
	3,275,000
	1,711,000

	 
	sub-total
	756,262
	2,942,859
	4,078,472
	4,157,795
	2,099,455

	 
	teachers and instructors
	165,543
	1,706,465
	3,514,383
	3,492,033
	1,436,450

	 
	transport and travel
	61,287
	-136,059
	276,541
	200,550
	98,300

	 
	rental and hiring charges
	15,000
	263,559
	323,306
	292,000
	165,000

	 
	other operational costs
	64,977
	919,955
	1,179,193
	1,546,985
	726,411

	 
	Total recurrent
	1,063,069
	5,696,779
	9,371,895
	9,689,363
	4,525,616

	
	Total APTC
	
	
	
	
	

	 
	management and support
	
	
	
	
	

	 
	in-country
	2,080,103
	7,156,932
	7,282,976
	3,994,584
	1,842,475

	 
	in-Australia
	1,913,781
	5,353,741
	6,892,286
	3,720,460
	1,711,000

	 
	sub-total
	3,993,884
	12,510,673
	14,175,262
	7,715,045
	3,553,475

	 
	teachers and instructors
	678,502
	4,628,634
	9,154,191
	4,806,728
	1,436,450

	 
	transport and travel
	251,626
	928,314
	1,820,222
	469,736
	195,380

	 
	rental and hiring charges
	157,355
	854,740
	1,068,283
	459,525
	181,821

	 
	other operational costs
	185,434
	3,061,814
	3,360,607
	3,046,706
	1,540,728

	 
	Total recurrent
	5,266,801
	21,984,175
	29,578,566
	16,497,739
	6,907,854


Table A.3 APTC recurrent expenditure by category, 2009

	
	
	AUD$
	percent of sub-total
	percent of total

	
	Coordination Office
	
	
	

	 
	management and support
	
	
	

	 
	in-country
	899,605
	45.2%
	3.0%

	 
	in-Australia
	
	0.0%
	0.0%

	 
	sub-total
	899,605
	45.2%
	3.0%

	 
	teachers and instructors
	-
	0.0%
	0.0%

	 
	transport and travel
	58,918
	3.0%
	0.2%

	 
	rental and hiring charges
	30,092
	1.5%
	0.1%

	 
	other operational costs
	1,000,220
	50.3%
	3.4%

	 
	Total recurrent
	1,988,835
	100.0%
	6.7%

	
	SACEM
	
	
	

	 
	management and support
	
	
	

	 
	in-country
	5,545,457
	30.4%
	18.7%

	 
	in-Australia
	3,651,728
	20.0%
	12.3%

	 
	sub-total
	9,197,185
	50.5%
	31.1%

	 
	teachers and instructors
	5,639,808
	31.0%
	19.1%

	 
	transport and travel
	1,484,764
	8.2%
	5.0%

	 
	rental and hiring charges
	714,885
	3.9%
	2.4%

	 
	other operational costs
	1,181,194
	6.5%
	4.0%

	 
	Total recurrent
	18,217,835
	100.0%
	61.6%

	
	STH/SHCS
	
	
	

	 
	management and support
	
	
	

	 
	in-country
	837,914
	8.9%
	2.8%

	 
	in-Australia
	3,240,558
	34.6%
	11.0%

	 
	sub-total
	4,078,472
	43.5%
	13.8%

	 
	teachers and instructors
	3,514,383
	37.5%
	11.9%

	 
	transport and travel
	276,541
	3.0%
	0.9%

	 
	rental and hiring charges
	323,306
	3.4%
	1.1%

	 
	other operational costs
	1,179,193
	12.6%
	4.0%

	 
	Total recurrent
	9,371,895
	100.0%
	31.7%

	
	Total APTC
	
	
	

	 
	management and support
	
	
	

	 
	in-country
	7,282,976
	24.6%
	24.6%

	 
	in-Australia
	6,892,286
	23.3%
	23.3%

	 
	sub-total
	14,175,262
	47.9%
	47.9%

	 
	teachers and instructors
	9,154,191
	30.9%
	30.9%

	 
	transport and travel
	1,820,222
	6.2%
	6.2%

	 
	rental and hiring charges
	1,068,283
	3.6%
	3.6%

	 
	other operational costs
	3,360,607
	11.4%
	11.4%

	 
	Total recurrent
	29,578,566
	100.0%
	100.0%


Figure A.1: APTC recurrent expenditure by category, 2007 to 2009 (AUD)

[image: image9.wmf]-

1,000,000 

-

1,000,000 

2,000,000 

3,000,000 

4,000,000 

5,000,000 

6,000,000 

2007

2008

2009

CO in

-

country management 

and support

CO transport and travel

CO rental and hiring charges

CO other operational costs

CO other operational costs

ACEM in

-

country management 

and support

ACEM in

-

Australia 

management and support

ACEM teachers and instructors

ACEM transport and travel

ACEM rental and hiring 

charges

ACEM other operational costs

ACEM other operational costs

STH/SHCS in

-

country 

management and support

STH/SHCS in

-

Australia 

management and support

STH/SHCS teachers and 

instructors

STH/SHCS transport and travel

STH/SHCS rental and hiring 

charges

STH/SHCS other operational 

costs


Table A.4: Estimated costs per student and per training hour

APTC programs and campuses, 2009

	
	total enrolments
	total training hours
	training hours per student
	total cost of training  (AUD$)
	cost per student  (AUD$)
	cost per training hour   (AUD$)

	SACEM

	Automotive
	
	
	
	
	
	

	Fiji
	88
	35,788
	407
	1,116,697
	12,690
	31.20

	PNG
	249
	93,950
	377
	4,171,185
	16,752
	44.40

	Samoa
	34
	17,635
	519
	799,914
	23,527
	45.36

	Total
	371
	147,373
	397
	6,087,795
	16,409
	41.31

	Construction and Electrical
	
	
	
	
	
	

	Fiji
	180
	84,230
	468
	2,554,987
	14,194
	30.33

	PNG
	153
	79,585
	520
	2,940,172
	19,217
	36.94

	Samoa
	126
	49,730
	395
	2,439,668
	19,362
	49.06

	Total
	459
	213,545
	465
	7,934,827
	17,287
	37.16

	Manufacturing
	
	
	
	
	
	

	Fiji
	
	
	
	115,657
	
	

	PNG
	112
	90,840
	811
	2,161,343
	19,298
	23.79

	Samoa
	96
	38,790
	404
	1,729,291
	18,013
	44.58

	Total
	208
	129,630
	623
	4,006,290
	19,261
	30.91

	SACEM Training and Assessment
	
	
	
	
	
	

	Fiji
	69
	13,005
	188
	863,426
	12,513
	66.39

	PNG
	40
	14,590
	365
	383,824
	9,596
	26.31

	Samoa
	
	
	
	
	
	

	Total
	109
	27,595
	253
	1,247,251
	11,443
	45.20

	All SACEM Programs
	
	
	
	
	
	

	Fiji
	337
	133,023
	395
	4,650,766
	13,800
	34.96

	PNG
	554
	278,965
	504
	9,656,524
	17,431
	34.62

	Samoa
	256
	106,155
	415
	4,968,873
	19,410
	46.81

	Total
	1,147
	518,143
	452
	19,276,163
	16,806
	37.20

	STH

	Tourism and Hospitality
	
	
	
	
	
	

	Fiji
	261
	117,946
	452
	2,991,022
	13,233
	25.36

	Samoa
	158
	62,644
	396
	2,125,272
	15,205
	33.93

	Vanuatu
	243
	100,007
	412
	2,723,780
	12,979
	27.24

	Total
	662
	280,597
	424
	7,840,074
	13,611
	27.94

	SHCS

	Children's and Community Services
	
	
	
	
	
	

	Fiji
	93
	33,708
	362
	1,115,650
	13,037
	33.10

	Samoa
	
	
	
	
	
	

	Vanuatu
	93
	33,708
	362
	1,092,318
	12,784
	32.41

	Total
	186
	67,416
	362
	2,207,968
	12,912
	32.75

	APTC

	All programs
	
	
	
	
	
	

	Fiji
	691
	284,677
	412
	8,757,439
	12,674
	30.76

	PNG
	554
	278,965
	504
	9,656,524
	17,431
	34.62

	Samoa
	414
	168,799
	408
	7,094,145
	17,136
	42.03

	Vanuatu
	336
	133,715
	398
	3,816,097
	11,357
	28.54

	Total
	1,995
	866,156
	434
	29,324,205
	14,699
	33.86


Annex H: APTC Cost Benefit Analysis

The Economic Rate of Return (ERR)

Calculation requires estimates of the costs associated with APTC training and of the benefits that are derived from it. Costs are in the form of, on the one hand the direct costs of training provision, and on the other its indirect costs, in the form of the opportunities foregone by students whilst undertaking training. The benefits are also both direct and indirect – the direct benefits are conventionally taken as the earnings differential between those who undertake the training and those that do not (as an indication of the additional productivity generated by the training), whilst the indirect benefits comprise any further economic benefits and other development benefits that are directly attributable to the additional training. The returns that these benefits generate over the costs are then set against the returns that could reasonably be expected on the investment of similar amounts on alternative projects or programs.

At this point there is a dearth of statistical information available upon which to calculate the ERR to any degree of precision. What follows is at best indicative, based as it is on the information readily to hand in April/May 2010, and upon a set of assumptions experience has shown to be reasonable.

1. Costs of APTC training

1a. Direct costs

· Estimates are based on average annual cost per student in 2009. The APTC expenditures from which they are derived are analysed in Annex H

· 2009 figures were used because so far, this is the only year for which APTC has been fully operational – 2007 and 2008 were years when programs were still being established, 2010 figures are perforce incomplete and 2011 figures provided by RTOs are forecasts only.

· Per student enrolments in APTC were used rather than per graduate estimates because even in 2009 it was too early for most APTC programs to have a full set of graduate figures, which could be taken as a measure of a ‘normal’ year of an ongoing training institution. Using annual student enrolments as the denominator instead of annual graduates in the ERR calculus yields a higher cost figure for courses that run longer than one year (as is typically the case on SACEM and SHCS programs) and lower figures for those that last less than a year (as is typical on STH programs). In both instances, however, they under-estimate the costs of producing graduates by a greater degree the higher the percentage of those who are enrolled fail to go on to graduation. 
· Actual annual expenditure figures provided by the two RTO’s and by SKM for the Coordination Office (CO) have been used. Each was asked to provide capital and (actual and projected) recurrent expenditure figures, by school and program, for each year 2007 to 2011. Figures for management and other support expenditures were also requested.

· SKM provided CO expenditures are apportioned between the schools on the basis of target graduate numbers – see Table 1. 

· RTO provided capital and annual recurrent expenditures were apportioned between schools and, in the case of SACEM, between programs, on the basis of 2009 enrolment numbers. This is not an ideal basis upon which to pro-rata expenditures, but it was considered the best available.

Table 1: APTC 2007-2011 targets, by school

	School
	Target
	Percent of Total

	SACEM
	1,183
	42.9

	STH
	1,360
	49.3

	SHCS
	217
	7.9

	Total
	2,760
	100.0


· Capital costs – expenditure on infrastructure and machinery and equipment – are amortised over the presumed length of asset lives. In the case of infrastructure this was estimated to be twenty years, and for machinery and equipment, it was estimated to be ten years. Rates of amortization are assumed to be 2.5 and 5.0 percent respectively.

Table A.1 provides the estimates of average per student costs for each year of Stage I, by school and by program. 
For the purposes of the ERR calculations, and with no estimates of the average length of programs available, it is assumed that SACEM and SHCS programs last two years, and STH and programs last one year
. Table 3 shows the estimated direct per student costs of APTC program provision.

1b. Indirect costs

It is assumed initially that the only indirect costs incurred are the earnings foregone by students whilst they are on APTC programs. Airfares and other travel expenses for students travelling from non-campus countries are already factored into the direct cost calculations, and scholarships are a means of financing programs and not a direct resource cost of APTC provision.

Table 2: Per-student costs of provision used in the ERR calculations

	Aus dollars
	Fiji
	PNG
	Samoa
	Vanuatu

	SACEM
	
	
	
	

	Automotive
	
	
	
	

	year 1
	13,918.28
	18,000.66
	25,005.08
	-

	year 2
	13,918.28
	18,000.66
	25,005.08
	-

	Total
	27,836.56
	36,001.32
	50,010.17
	-

	Construct& Elect
	
	
	
	

	year 1
	15,417.67
	20,409.44
	20,666.97
	-

	year 2
	15,417.67
	20,409.44
	20,666.97
	-

	Total
	30,835.34
	40,818.88
	41,333.94
	-

	Manufacturing
	
	
	
	

	year 1
	-
	20,531.20
	19,368.56
	-

	year 2
	-
	20,531.20
	19,368.56
	-

	Total
	-
	41,062.40
	38,737.12
	-

	STH
	
	
	
	

	Total
	13,232.86
	-
	15,204.87
	12,978.72

	SCHS
	
	
	
	

	year 1
	13,037.11
	-
	-
	12,783.52

	year 2
	13,037.11
	-
	-
	12,783.52

	Total
	26,074.22
	-
	-
	25,567.04


Source; Table A.1

2. Benefits of APTC training

2a. Direct economic benefits

These are conventionally measured by the observed earnings differential between those who have undertaken the extra training (in this case Certificate 3 training at APTC) over those who were similarly trained and experienced but who did not undertake the extra training (at the APTC). This is taken as a measure, on the one hand, of the extra productivity the graduates bring to the labour force and, on the other, the extra income that is available to the graduates and their families to improve their livelihoods.

Reliable up-to-date information on earnings in Pacific island countries is hard to come by. In most cases there are no official estimates that can be used. To build, therefore, estimates of age/experience/earnings profiles, by level of training, indicative data have to be resorted to. Three sources of this type of information have been used in this exercise: 

· For Papua New Guinea payroll information provided by one hotel group. 
· For the Solomon Islands information provided in discussions with major employers and employer organizations. 
· For Fiji schedules of minimum wages gazetted by the Fiji Government Ministry of Labour.

Tables A.2 to A.4 summarise the earnings data gleaned from these sources and used in this exercise. Figures 1 to 3 show the indicative earnings profiles that have been constructed using this data. They have been built on the basis of what could be considered a reasonable trajectory of earnings over time for a typical worker. 
Figure 1: Indicative earnings profiles for semi-skilled and skilled tradespersons in Solomon Islands, 2010
[image: image10.wmf]-

1,000 

2,000 

3,000 

4,000 

5,000 

6,000 

1

3

5

7

9

11

13

15

17

19

21

23

25

27

29

31

A

u

s

 

$

years beyond commencement of training

semi

-

skilled 

workers

skilled workers


Source; Table A.2

Figure 2: Indicative earnings profiles for selected tradespersons, PNG 2010
[image: image11.wmf]0

1000

2000

3000

4000

5000

6000

7000

8000

9000

1

3

5

7

9

11

13

15

17

19

21

23

25

27

29

31

A

u

s

 

$

years beyond commencement of training

semi

-

skilled worker

welder

carpenter

electrician

tiler

painter

AC technician


Source; Table A.3

Figure 3: Indicative earnings profiles for selected hotel staff, PNG 2010
[image: image12.wmf]0

1000

2000

3000

4000

5000

6000

7000

8000

9000

10000

1

3

5

7

9

11

13

15

17

19

21

23

25

27

29

A

u

s

 

$

years beyond commencement of taining

waitress

room attendant

kitchen hand

restaurant supervisor 

housekeeping supervisor

commis (novice) chef 

pastry chef

baker


Source; Table A.4

Figure 4: Indicative earnings profiles for selected tradespersons, Fiji 2009
[image: image13.wmf]0

1000

2000

3000

4000

5000

6000

7000

1

3

5

7

9

11

13

15

17

19

21

23

25

27

29

31

A

u

s

 

$

years beyond commencement of training

unskilled worker

general 

tradesperson 

/foreman


Tables 3 to 6 show indicative ERR for APTC training programs on the basis of the above data and assumptions regarding per-student costs and indicative earnings profiles. They presume that all graduates from each of the selected programs find full-time employment in their home countries in the occupations, and at a level, for which they have been trained. In this sense these figures represent the most optimistic set of return calculations, provided that graduates return to their home states and find employment there. 
Table 3: Estimated economic rate of return on Solomon Islanders undertaking training with SACEM
	SACEM program
	campus country
	estimated ERR

	Automotive 
	Fiji
	7.8%

	
	PNG
	5.8%

	
	Samoa
	3.5%

	Construction and electrical
	Fiji
	7.0%

	
	PNG
	4.9%

	
	Samoa
	4.8%

	Manufacturing
	Fiji
	

	
	PNG
	4.9%

	
	Samoa
	5.3%


Table 4: Estimated economic rate of return on PNG workers undertaking selected training programs with SACEM in PNG

	Occupation
	Estimated ERR

	Welding/handyman
	5.98%

	Carpentry/handyman
	6.38%

	Electrical/handyman
	3.64%

	Tiling/handyman
	0.31%

	Painting/handyman
	> 0

	air-conditioning/refrigeration/handyman 
	8.68%


Table 5: Estimated economic rate of return on PNG workers undertaking training on selected STH programs

	Occupation
	Estimated ERR

	
	campus country

	
	Fiji
	Samoa
	Vanuatu

	commis (novice) chef/kitchen hand 
	7.0%
	6.2%
	7.1%

	pastry chef/kitchen hand
	6.0%
	5.2%
	6.1%

	baker/kitchen hand
	2.4%
	1.6%
	2.5%

	housekeeping supervisor/room attendant
	20.2%
	18.6%
	20.4%

	restaurant supervisor/waitress 
	14.2%
	12.7%
	14.4%


Table 6: Estimated economic rate of return on Fiji workers undertaking training on SACEM programs in construction and electrical trades
	Occupation
	Estimated ERR

	general tradesperson-foreman/unskilled worker
	2.2%


There was strong anecdotal evidence from the field mission, backed up by what little information there is available as yet from the APTC tracer studies, that not all graduates are able to find full-time employment in the occupations and at the levels for which they have been trained. If this is the case, it would have the effect of inflating the estimates of the direct economic benefits of the APTC training programs, and hence of the ERR they yield in the tables above. 

Tables 3 to 5 show that employment of graduates only in their home states, with the possible exception of some courses in STH, yields comparatively low direct rates of economic return. 
An important rationale for the establishment of APTC was that the Australian certificate level 3 and 4 training would enhance the mobility of graduates, not only across the labour markets of the region, but further afield, especially into the labour markets of Australia, New Zealand and on the west coast of United States. 
The ERR can be modified to allow for limited access to these markets, in this instance, to the Australian labour market. Estimates for gross and net average annual earnings, by selected occupations and industries in Australia in 2009, are summarized in Table A.6. 
The following ERR calculations have been made taking account of the following variables:

· the proportion of graduates who find employment in Australia;
· the length of time they are employed in Australia;
· the timing of that employment – whether it is immediately after graduation, or after an interval of employment in their home states; and
· the level of remittances back to their island states from their net earnings in Australia.
Table 7 shows the resulting ERR when different assumptions are made regarding these variables and are applied to one selected group of APTC graduates - Solomon Island APTC graduates from SACEM in PNG who find work in the Australian construction industry. Similar patterns would emerge when they are applied to graduates of other APTC programs. 
The base case analysis assumes 25% of graduates find work in the Australian construction industry soon after graduation, staying for ten years and remitting 40% of their net earnings while abroad. This would generate a direct economic rate of return on the investment in the APTC of just under twelve percent. The limited information available suggests APTC graduates are keen to access overseas employment, and if 50% of graduates were to obtain employment in Australia the ERR jumps to 19.8%.
What is clear from Table 7 is that, compared to the estimated ERR of less than 5 percent if all graduates only found work in the Solomon islands, even a comparatively short period (five years) of employment in Australia and a relatively low remittance rate (25 percent of net earnings) employment in Australia significantly adds to the ERR on the APTC program. If that short period of employment is available immediately after graduation, rather than delayed, even by five years, the payoff is even higher. 
The lower ERR for employment only in home countries highlights the importance of the APTC rationale to facilitate labour mobility as a means of enhancing employment and income opportunities. It also reinforces the importance of the APTC training profile retaining a tight focus on industry demand, domestically and regionally, so as to facilitate labour mobility.

Table 7: ERR on Solomon Islanders undertaking SACEM training, with periods of post-graduation employment in Australia factored in

	Assumptions about the proportion of graduates employed in Australia, its duration and the level of remittances
	Estimated ERR

	
	Timing of Australian employment

	
	straight after training
	after 5 years in SI

	25 percent of graduates work in Australia for 5 years and remit 25 percent of net earnings
	6.7%
	5.8%

	25 percent of graduates work in Australia for 10 years and remit 25 percent of net earnings
	7.6%
	6.3%

	25 percent of graduates work in Australia for 5 years and remit 40 percent of net earnings
	8.9%
	7.2%

	25 percent of graduates work in Australia for 10 years and remit 40 percent of net earnings
	11.6%
	8.5%

	50 percent of graduates work in Australia for 5 years and remit 25 percent of net earnings
	8.7%
	6.7%

	50 percent of graduates work in Australia for 10 years and remit 25 percent of net earnings
	10.8%
	7.6%

	50 percent of graduates work in Australia for 5 years and remit 40 percent of net earnings
	14.7%
	9.4%

	50 percent of graduates work in Australia for 10 years and remit 40 percent of net earnings
	19.8%
	11.7%


2b. Broader developmental benefits of the APTC initiative

The rates of return calculated using direct economic costs and benefits underpin a broader return AusAID can expect in developmental terms in the Pacific on its investment in APTC.

Many of the benefits identified below are inherently non-quantifiable, and/or are difficult to ascribe only to the investment in APTC. Even those that are in principle quantifiable cannot be readily given a monetary value due to the paucity of data across the region.

Indirect economic benefits

· Certificate 3 and 4 level training adds to the stock of workers in the Pacific whose skills are of an internationally competitive type and level. Building up a critical mass of such skilled workers will be an essential pre-condition for investment and infrastructure projects throughout the region, whether they be aid driven or private sector initiated. 
· Currently many investment and infrastructure projects have to rely on the use of foreign skilled workers. As more and more APTC graduates come on stream the necessity to depend upon these foreign workers should diminish. Most countries in the region collect administrative data on people entering their countries on employment visas. So far, however, little of this information is published in statistical form. The design team asked for this information in each of the countries visited on their recent field mission, but so far it has not received any replies. Such information would be extremely useful to both planners in the region and for APTC profile planning purposes. 
· Information available to date indicates that only a very small number of APTC graduates have moved outside the region to seek employment. As we have seen, however, the potential for foreign remittances to add to the ERR on APTC programs is significant. So too, however, is the multiplier effect that these remittances can have on local communities in the home countries. The additional income received by recipient families has the potential to create flow-on employment opportunities locally. 
· For graduates working in their home countries, especially if they are working in occupations and at levels for which they are trained, there is the potential for the ‘sitting-by-Nellie’ effect on the productivity and work habits of fellow employees. The importance of this demonstration and mentoring effect on fellow workers should not be underestimated. Of related importance is the ‘exemplar’ effect – the incentive for others around them to undertake similar training and receive the rewards that entails. 
· APTC itself is having an exemplar effect upon national TVET institutions and systems. By setting an international standard in TVET training, APTC is providing a good example and it is ‘raising the bar’ in terms of what quality TVET delivery is all about. There is a practical element to this assistance to national TVET systems as well: 

· some APTC graduates are finding employment as teachers and instructors in national TVET institutions;

· teachers and instructors in national TVET institutions are upgrading their technical skills by undertaking APTC programs;

· skilled workers and national TVET institute teachers and instructors are undertaking APTC TAE4 programs. 
· The presence of APTC is helping to raise, if not the prestige then at least the acceptability, of TVET as a viable post-school/career enhancing option. This has the consequence of more and better educated students seeking TVET enrolments. It can also help persuade national governments that it is worthwhile giving greater support to their TVET institutions, especially in the critical area of recurrent expenditure allocations. 
2c. Non economic benefits

· In the longer term an institution like APTC has the effect of bringing more Pacific islanders into the global competitive labour markets. The more islanders have globally competitive skills, the more choices they have – the more mobility and flexibility they have in making lifetime career decisions. The more, in other words, they become fully fledged global citizens. 
· An institution such as APTC promotes regionalism in the Pacific and provides a tangible response to the Pacer-Plus objectives.

· Through its scholarship program APTC is enhancing greater equality in training opportunities across gender, disability and minority groups and for those from the more remote islands and regions of the Pacific. 
What is an acceptable rate of return on APTC?

Target rates of return on similar projects, with the same degree of risk, are typically set by aid donors at between 12 and 15 percent. That range should be expected on the PNG component of the APTC investment, but perhaps something more modest, say, around 10 percent would be acceptable for the broader Pacific region

Risks and assumptions

· There is a risk that the so-far high completion rates on all APTC programs will not be sustained as the programs continue and the backlog of well-trained workers eligible to apply for places declines and are not replaced by new entrants.

· There is a risk that the high level of competence that is required to be demonstrated in order to be awarded Certificate 3 and 4 cannot be maintained and that increasingly the quality of graduates will decline.

· There is a risk that, given the relatively small size of the formal wage economies in most Pacific island states, increasing numbers of APTC graduates will fail to find employment in occupations and at levels for which they are trained. To the extent that this happens, the ERR on APTC training programs will decline.

· There is a risk that the greater mobility of labour across the region that Pacer-Plus requires will not occur, and that nation states will continue to maintain barriers of entry into local labour markets. 
· Even though there is plenty of anecdotal evidence that Pacific islanders would be willing to come to Australia to work, even on limited work permits, the number actually doing so remains small, primarily because of immigration restrictions imposed by Australia. This situation has been recently exacerbated by the removal from the Department of Immigration and Citizenship’s Skills-in-Demand list of a number of the occupations for which APTC trains, especially through STH and SHCS. As indicated above, for the ERR on the APTC investment to reach acceptable levels, the assumption of a graduates being able to work in Australia has to be factored in.

· Further to this point, there is a risk that those that do come to Australia for work (a) do not remit at high enough levels, and or (b) stay permanently.

Conclusions

The economic rates of return that have been estimated above, are perforce very sketchy and only, therefore, of indicative value. There is a lot more work to do on the cost side to get accurate figures of how much each graduate from the APTC programs costs on average. This task will become easier as more information becomes available over time and some changes are made the way in which college data are collected and presented. The big problem, however, is on the benefit side of the calculus. There simply is not enough up-to-date and reliable information available for any of the variables that a proper CBA exercise requires.

Having said that, it is clear from the rates that can be calculated, that the economic returns on most APTC courses are low if only direct economic benefits are included and if APTC graduates can only find employment in their own home countries. 
For the ERR to be brought up to a level that could be considered acceptable, two key assumptions have to be made - one is that a percentage of the graduates are able to find employment in Australia in the occupations and at the levels for which they are trained, and that they then remit a significant portion of their earnings back home, and/or secondly the indirect economic benefits and non economic benefits of the APTC initiative are significant. Given the difficulties of putting a monetary value on these additional benefits, this becomes a matter of judgment. 
Future cost-benefit analyses of APTC

Centralised APTC data relating to student enrolments and graduations on an annual basis have to be made clear and unambiguous. This will no doubt happen in the course of time and with further work on a comprehensive student data base. 
Expenditure data used in this exercise had to be drawn from three different sources (the three contractual parties to the APTC) and they, the data, were not everywhere compatible. This, again, will need to be rectified with the establishment of a uniform consolidated financial data base for the college. 
Efforts will have to be made, especially by the CSS and its country representatives, to systematically collect information regarding occupational earning patterns, employment patterns (in particular with respect to the occupations covered by the APTC programs), trends in foreign worker employment, and any other labour force and economic data, in each of the participating Pacific island countries. Some of this information may be provided by a revised and upgraded program of tracer studies and employer surveys. However, much more effort will need to be made to collect relevant information from wherever it is possible in much the same way, and from much the same sources, as the mission team was able to recently.

Putting all of this information together from every source on a routine basis should be part of the terms of reference of the CSS, in preparation for its annual reporting on APTC operations and prospects. 

Table A.1: APTC program costs per enrolled student

	
	Australian dollars

	
	2008
	2009
	2010
	2011

	SACEM
	
	
	
	

	Automotive
	
	
	
	

	Fiji
	45,261
	13,918
	5,997
	34,743

	PNG
	30,706
	18,001
	7,035
	15,606

	Samoa
	
	25,005
	6,136
	23,498

	Vanuatu
	
	
	
	

	Total
	36,276
	17,679
	6,659
	18,563

	Construction & Electrical
	
	
	
	

	Fiji
	35,346
	15,418
	6,308
	4,218

	PNG
	24,884
	20,409
	9,325
	7,071

	Samoa
	20,822
	20,667
	5,808
	2,566

	Vanuatu
	
	
	
	

	Total
	26,036
	18,526
	6,934
	4,091

	Manufacturing
	
	
	
	

	Fiji
	
	
	
	

	PNG
	47,923
	20,531
	16,317
	

	Samoa
	37,556
	19,369
	4,905
	6,120

	Vanuatu
	
	
	
	

	Total
	42,491
	20,566
	8,118
	13,864

	Training and Assessment
	
	
	
	

	Fiji
	
	13,739
	5,741
	

	PNG
	10,139
	10,684
	
	

	Samoa
	
	
	
	

	Vanuatu
	
	
	
	

	Total
	24,323
	12,619
	8,633
	

	All SACEM Programs
	
	
	
	

	Fiji
	43,847
	15,036
	6,244
	7,062

	PNG
	28,413
	18,649
	9,184
	15,091

	Samoa
	28,837
	20,768
	5,495
	4,104

	Vanuatu
	
	
	
	

	Total
	31,145
	18,060
	7,126
	7,815

	STH
	
	
	
	

	Tourism and Hospitality
	
	
	
	

	Fiji
	8,588
	13,233
	20,428
	18,076

	PNG
	
	
	
	

	Samoa
	14,274
	15,205
	13,998
	21,239

	Vanuatu
	14,521
	12,979
	14,605
	25,406

	Total
	11,729
	13,611
	16,028
	21,111

	SHCS
	
	
	
	

	Health and Community Services
	
	
	
	

	Fiji
	22,882
	13,037
	12,414
	11,325

	PNG
	
	
	
	

	Samoa
	
	
	
	

	Vanuatu
	27,718
	12,784
	16,749
	17,748

	Total
	25,254
	12,912
	14,324
	13,895


	Table A.2: Estimated average earnings of Solomon Islands tradespersons

	
	
	
	
	

	
	SI $
	AUD$

	
	per hour
	per fortnight
	per year
	per year

	semi- skilled tradesperson
	6
	480
	12,480
	1,835

	newly trained skilled tradesperson
	10
	800
	20,800
	3,059

	experienced skilled tradesperson
	18
	1,440
	37,440
	5,506


Source: mission team discussions with employers

	Table A.3: Average gross earnings for selected tradespersons, PNG 2010

	
	
	
	

	
	PNG Kina
	AUD$

	
	per fortnight
	per year
	per year

	semi skilled tradesperson
	
	
	

	handyman
	206
	5,356
	2,678

	observed range for skilled tradespersons
	
	

	welder low
	332
	8,632
	4,316

	welder high
	500
	13,000
	6,500

	carpenter low
	348
	9,048
	4,524

	carpenter high
	510
	13,260
	6,630

	electrician low
	217
	5,642
	2,821

	electrician high
	452
	11,752
	5,876

	tiler low
	298
	7,748
	3,874

	tiler high
	326
	8,476
	4,238

	painter low
	252
	6,552
	3,276

	painter high
	276
	7,176
	3,588

	AC technician low
	361
	9,386
	4,693

	AC technician high
	622
	16,172
	8,086


Source: payroll data provided by an employer 

	Table A.4: Average gross earnings for selected occupations in the hospitality sector, PNG 2010

	
	
	
	

	
	PNG Kina
	AUD$

	
	per fortnight
	per year
	per year

	semi skilled occupations
	
	
	

	waitress low
	114
	2,964
	1,482

	waitress high
	243
	6,318
	3,159

	room attendant low
	174
	4,524
	2,262

	room attendant high
	210
	5,460
	2,730

	kitchen hand low
	226
	5,876
	2,938

	kitchen hand high
	236
	6,136
	3,068

	trainee commis 3
	243
	6,318
	3,159

	observed range for skilled occupations
	-
	-

	commis (apprentice/novice) chef low
	260
	6,760
	3,380

	commis (apprentice/novice) chef high
	411
	10,686
	5,343

	pastry chef
	385
	10,010
	5,005

	baker
	315
	8,190
	4,095

	sous chef
	1,373
	35,698
	17,849

	housekeeping supervisor low
	308
	8,008
	4,004

	housekeeping supervisor high
	700
	18,200
	9,100

	restaurant supervisor low
	370
	9,620
	4,810

	restaurant supervisor high
	494
	12,844
	6,422


Source: payroll data provided by an employer 
Table A.5: Minimum wage rates set by wage regulations in Fiji, 2009

	
	Fiji dollars
	Aus dollars annual

	
	hourly
	weekly
	annual
	

	Building, civil and electrical engineering trades
	
	

	Foreman
	4.20
	189.00
	9,828
	5,897

	Leading Hand
	3.60
	162.00
	8,424
	5,054

	Tradesman Class 1
	3.45
	155.25
	8,073
	4,844

	Tradesman Class 2
	3.30
	148.50
	7,722
	4,633

	Tradesman Class 3
	3.20
	144.00
	7,488
	4,493

	General Tradesman
	3.05
	137.25
	7,137
	4,282

	Watchman
	2.16
	97.20
	5,054
	3,033

	Clerk
	3.05
	137.25
	7,137
	4,282

	Unskilled Workers
	2.55
	114.75
	5,967
	3,580

	Driver Light Goods
	2.90
	130.50
	6,786
	4,072

	Driver Heavy Goods
	3.45
	155.25
	8,073
	4,844

	Heavy Plant Operator
	3.63
	163.35
	8,494
	5,097

	Light Plant Operator
	3.50
	157.50
	8,190
	4,914

	Hotel and catering trades
	
	
	
	

	Barman
	2.65
	119.25
	6,201
	3,721

	Clerk
	2.60
	117.00
	6,084
	3,650

	Cook
	2.70
	121.50
	6,318
	3,791

	General Worker
	2.50
	112.50
	5,850
	3,510

	House Worker
	2.50
	112.50
	5,850
	3,510

	Kitchen Hand
	2.50
	112.50
	5,850
	3,510

	Laundry Hand
	2.50
	112.50
	5,850
	3,510

	Night Attendant
	2.50
	112.50
	5,850
	3,510

	Outdoor Worker
	2.50
	112.50
	5,850
	3,510

	Waiter
	2.50
	112.50
	5,850
	3,510

	Watchman
	2.50
	112.50
	5,850
	3,510


	Source Ministry of Labour, Industrial Relations and Employment, Fiji

	http://www.labour.gov.fj/erp.htm



Table A.6: Estimated average incomes in Australia in 2009 

- by selected occupations and sectors

	
	Gross Monthly Average Income - USD 2005 constant prices (2)
	gross average annual USD 2005
	gross average annual AUSD 2005
	gross average annual AUSD 2009
	net average annual AUSD 2009

	Occupation
	
	
	
	
	

	Miner average income
	6,933
	83,196
	109,071
	132,576
	106,061

	Carpenter average income
	4,151
	49,812
	65,304
	79,377
	63,502

	Bus Driver average income
	3,851
	46,212
	60,584
	73,641
	58,913

	Garment Cutter average income
	3,679
	44,148
	57,878
	70,352
	56,281

	Car Mechanic average income
	3,308
	39,696
	52,042
	63,257
	50,606

	Wood Grinder average income
	3,280
	39,360
	51,601
	62,722
	50,177

	Office Clerk average income
	3,239
	38,868
	50,956
	61,938
	49,550

	Furniture Finisher average income
	3,083
	36,996
	48,502
	58,955
	47,164

	Auxiliary Nurse average income
	2,945
	35,340
	46,331
	56,316
	45,053

	Baker average income
	2,942
	35,304
	46,284
	56,258
	45,007

	Salesperson average income
	2,850
	34,200
	44,837
	54,499
	43,599

	Hotel Receptionist average income
	2,833
	33,996
	44,569
	54,174
	43,339

	Chambermaid average income
	2,696
	32,352
	42,414
	51,554
	41,243

	Sector
	
	
	
	-
	-

	Mining-Quarrying average income
	6,144
	73,728
	96,658
	117,489
	93,991

	Gas-Electricity-Water average income
	4,769
	57,228
	75,026
	91,195
	72,956

	Manufacturing average income
	4,065
	48,780
	63,951
	77,733
	62,186

	Construction average income
	4,056
	48,672
	63,809
	77,561
	62,049

	All Sectors average income
	3,848
	46,176
	60,537
	73,583
	58,867

	Hotels-Restaurants average income
	2,935
	35,220
	46,174
	56,125
	44,900


1) The net average income in "constant 2005 US$" is computed using the Interbank nominal exchange rate [a] and the U.S. inflation rate [d]. The net average income in "constant 2005 US$" at PPP is computed using the OECD PPP exchange rates for actual individual consumption [l] and the U.S. inflation rate [d]. The latter reflects the purchasing power in the United States in 2005.

2) The gross monthly average income is based on data supplied by the Australian Bureau of Statistics to the International Labour Organization [9]. The average income includes the salaries and wages of paid employees. Employees include both men and women unless otherwise noted.

3) The compulsory deductions are obtained from the Australia income tax calculator [t] and reflect the 2005 income tax rates in Australia and Medicare levy withholdings for a single-earner married couple without child. The deductions exclude the occupational pension (voluntary).

4) The weekly hours are based on data supplied by the Australian Bureau of Statistics to the International Labour Organization. The hours reported by job correspond to the hours paid for, which may not necessarily be the number of hours actually worked.

Source: http://www.worldsalaries.org/australia.shtml 

Annex I: APTC Stage II Implementation Plan 
[image: image14.png]Key Result Area Activity Month Jun-11 ‘ Jul-11 ‘ Aug-11‘ Sep-11‘ Oct-11‘ Nov-11 ‘ Dec-11 ‘ Jan-ﬂ‘ Feb-ﬂ‘ Mar-ﬂ‘Apr-ﬂ‘ May-ﬂ‘ Jun-ﬂ‘ Jul-ﬂ‘ Aug-ﬂ‘ Sep-ﬂ‘ Oct-ﬂ‘ Nov-ﬂ‘ Dec-ﬂ‘ Jan-H‘
1 [Marketing Review/update Marketing and Recruitment and Communications strategies By Jun-11 *
1 [Marketing Implement Marketing and Recruitment and Communications strategies From Jul 11

1 [Marketing Maintain website From Jul-11

1 [Marketing Provision of course information and advice From Jul-11

1 [Marketing Recruit fee paying students From Jul-11

1 [Marketing Update 2011/12 course calendar July; Jan

1 [Marketing Undertake roadshows to NCCs Aug; Feb

2 |Partnerships Mgt of agreement and relationships with training partners. From Jul-11

2 |Partnerships Consultation with industry associations and employers From Jul-11

2 |Partnerships Undertake in-country consultations. From Jul-11

2 |Partnerships Progressively develop/update APTC Country Strategies From Jul-11

3 |Teaching & Learning | Conduct feasibility studies into SHCS & hospitality courses (f not done before transition) |By Jun-11 *
3 [Teaching & Learning |Confirm 2011/12 Training Profile By Jun-11 *
3 |Teaching & Learning |Conduct courses as per Annual Training Profile From Jul-11

3 [Teaching & Learning |Establish Centre for Professional Development By Sep-11

3 |Teaching & Learning | Design and deliver "APTC to work” program By Sep-11

3 |Teaching & Learning |Assess College applicants (technical merit and ELLN) From Jul-11

3 |Teaching & Learning |Arrange work attachments From Jul-11

3 |Teaching & Learning | Conduct workplace assessments From Jul-11

3 |Teaching & Learning | Provide concurrent ELLN support to all students as required From Jul-11

3 [Teaching & Learning | Design and eliver SIS ELLN bridging program By Dec-11

3 |Teaching & Learning |Manage ELLN Bridging Program Ancillary Awards From Jul-11

3 |Teaching & Learning |Provision & maintenance of training facilities & equipment From Jul-11

3 |Teaching & Learning | Establish new courses in Training Profile As required





[image: image15.png]Key Result Area Activity Month Jun-11| Jul-11|Aug-11| Sep-11| Oct-11| Nov-11|Dec-11|Jan-12| Feb-12| Mar-12|Apr-12| May-12| Jun-12|Jul-12| Aug-12|Sep-12| Oct-12| Nov-12|Dec-12| Jan-13|
4 [Student Mt Review/update Alumni Association Strategy By Sep-11 *

4 [Student Mt Review/update Gender Access and Equality Policy Framework By Dec-11 *

4 [Student Mt Review/update Disability Strategy By Dec-11 *

4 [Student Mt Review/update HIV and AIDS Framework Policy and Strategy By Dec-11 *

4 [Student Mt Review/Update Student Pastoral Care Plan By Dec-11 *

4 [Student Mt Provide pastoral support to all students From Jul-11

4 [Student Mt Facilitate access for people with a disability From Jul-11

4 [Student Mt Conduct Graduation ceremonies From Jul-11

4 [Student Mt Conduct Alumni Association activities From Jul-11

4 |Scholarship Mgt Review/update Indicative Scholarship Allocation Policy Jan

4 |Scholarship Mgt Update Scholarship Policy Manual and review Scholarships Allocation Model By Jun-11 *

4 |Scholarship Mgt Advertise courses for next period Feb; Aug * * *

4 |Scholarship Mgt Scholarship applications close date Mar; Sep * * *

4 |Scholarship Mgt Screen/eligibility checking of scholarship applications Mar; Sep * * *

4 |Scholarship Mgt Assessment testing scholarship applications Apr-May; Oct-Nov * * * * * *
4 |Scholarship Mgt Make Scholarship offers May-Jun; Nov-Dec * * * * * *
7

7

7

7

7

7

7

7

Scholarship Mgt Facilitate Awardee mobilisation From Jul-11
Scholarship Mgt Provide pre-departure briefing for awardees From Jul-11
Scholarship Mgt Provide orientation for new awardees From Jul-11
Scholarship Mgt Make awardee alowance payments From Jul-11
Scholarship Mgt Arrange awardee accommodation From Jul-11
Scholarship Mgt Arrange awardee travel From Jul-11
Scholarship Mgt Manage award variations From Jul-11
Scholarship Mgt Complete end award activities From Jul-11





[image: image16.png]Key Result Area Activity Month Jun-11| Jul-11| Aug-11| Sep-11| Oct-11| Nov-11|Dec-11| Jan-12| Feb-12| Mar-12|Apr-12| May-12| Jun-12|Jul-12| Aug-12|Sep-12| Oct-12| Nov-12|Dec-12| Jan-13
5 Mgt & Governance [Transition of Stage 2 training venues. By Jun-11 *

5 Mgt & Governance | Conduct feasibility study into PNG hospitality SChool (f not done before transition) By Jun-11 *

5 Mgt & Governance |Review/update College Business Development Strategy By Jun-11 *

5 Mgt & Governance |Develop Tuition Fee policy By Jun-11 *

5 Mgt & Governance |Review/update Fee for Service policy By Jun-11 *

5 Mgt & Governance | Develop staff localisation strategy By Sep-11 *

5 |Mgt & Governance |Develop Labour Market Action Plan By Sep-11 *

5 |Mgt & Governance |Undertake Feasibility Study for Solomon Islands training venues By Sep-11 *

5 Mgt & Governance |Review/update Emergency and Evacuation Plan (and as needed) Jan; Apr; Jul; Oct * * * * * * *
5 |Mgt & Governance |Provide Secretariat for Advisory Group meetings Jan and as required * *

5 |Mgt & Governance | Conduct SMT and other APTC management meetings. From Jul-11

5 Mgt & Governance |Recruit, performance manage APTC staff From Apr-11 *

5 Mot & Governance | Conduct staff training across all College operations From Jul-11

5 |Mgt & Governance | AusAID-Contractor meetings Feb; May; Aug; Nov * * * * * *

5 Mgt & Governance |Independent AQTF auditing TBD

5 Mgt & Governance |Review/update Environmental Management Plan By Dec-11 *

5 Mgt & Governance |Review/update Risk Management Matrix Jun-11 *

5 Mgt & Governance | Submit Annual Training Profile Jan * *
5 Mgt & Governance |Review Annual Training Profile Jul * *

5 Mgt & Governance |Establish new training partnerships and facilities [As required

5 Mgt & Governance |Facilitate Mid-Term Review 2013

5 Mgt & Governance | Conduct fee for service activities (incl. RPL) |As contracted

[T [P Fom s S O N
5 [ICTMIS Integrated APTC student database fully operational By Dec-11 *

5 [ICTMIS Integrated APTC FMIS fully operational By Dec-11 *

5 [ICTMIS Integrated APTC staff database fully operational By Dec-11 *

5 [ICTMIS Integrated APTC Asset register and other APTC MIS fully operational By Dec-11 *

5 |Reporting/M&E Conduct M3E activities From Jul-11

5 |Reporting/M&E Submit Annual Report/Plan Jan *

5 |Reporting/M&E Update PAF (incl. risk management) Jan *

5 |Reporting/M&E Submit Six Monthly Progress Reporting Jul, Jan *

5 |Reporting/M&E Submit Quarterly Financial Reporting Jul, Oct, Jan, Apr * * * * *

< [aroighE (S Eor i e S O N
5 |Reporting/M&E Commence trial of 'back to work' plans Jan-12 *

5 |Reporting/M&E Review of reintegration plans. Jan-13 *
5 |Reporting/M&E Submit End contract reporting Mar15






Annex J: Reporting Plan

An Annual Report/Plan will be submitted for AusAID approval on 15 January each year. The Annual Report/Plan will focus on training outcomes including skill utilisation, employment and alumni outcomes in the preceding year and include a work program for the following financial year. It will address issues affecting implementation plans and strategies covering gender equity; access by people with a disability; the scholarships scheme; access by SIS; risk management; quality assurance; promotions and communications; and other cross-cutting issues. The report will not only summarise the findings from the PAF but will also report on the progress made in applying the framework itself.

The Annual Report/Plan will include the following Annexes:

· Annual Training Profile (for the next Australian financial year);

· Workplan and budget (for the next financial year);

· Six monthly progress report for the previous July to December period; 
· Reporting against the Performance Assessment Framework;
· Marketing and Communications Plan;

· Risk Management Plan;

· APTC policies updated during the period;

· Quarterly Financial Reports;

· Gender Analysis;

· Fee for service activities; 

· Advisory Group Minutes;

· Senior Management Meeting Minutes;

· Any Audit Reports; and
· Change frame indicating proposed changes to the contract for consideration.

A Six-Monthly Progress Report on both progress and issues arising in relation to implementation of the program, as well as a summary analysis of key statistical information. The report is to be submitted annually on 15 January (covering the previous July-December period) as an annex to the Annual Report/Plan and 15 July (covering the previous January-June period). The data should include, but be not limited to:

a) a summary of enrolment and graduate numbers disaggregated by course, campus, country of origin, gender and scholarship status. This data should present data for the previous period/year and cumulative data since contract commencement;

b) a summary of scholarship applications, awards offered, deferrals, withdrawals, extensions, suspensions and terminations;
c) a summary of ELLN bridging programs conducted during the period (and cumulative since contract start);

d) major procurements in the period;

e) a table indicating progress of activities implemented, or scheduled to have been implemented, in the past quarter, including progress in accordance with the Annual Training Profile; 
f) any proposed changes to the Annual Training Profile; and
g) monitoring and reviewing risks and assumptions (including evaluation of new risks as they emerge with recommendations for their management/treatment).

Quarterly Financial Reports, to be submitted within two (2) weeks of the end of each Quarter, are to include the following:

a) total expenditure to date;

b) disaggregated expenditure to date identifying all categories of expenditure including the Management Fees, Personnel and Other Reimbursable item components;

c) income from tuition fees, fee for service activities for the previous quarter; and

d) acquittal of total expenditure for the previous quarter; and

e) forward expenditure and expenses by category for the next quarter, including details and estimated costs of proposed courses and an updated annual expense projection.
Exception reports are to be provided as soon as possible after critical APTC program issues (such as fraudulent activities, unfavourable media reports etc, and scholarship scheme issues) are identified and need to be brought to the prompt attention of AusAID. They will incorporate proposed responses to issues that have emerged and will not be seen as progress reports. 

A Completion Report shall be submitted three months before the Contract End Date. The report should be prepared in accordance with any written instructions that may be issued by AusAID and address the following issues:

a) confirm that the APTC has been implemented according to the processes specified;

b) examine actual achievements against the APTC goal and objectives;

c) provide a full reconciliation and acquittal of funds;

d) document lessons learned from the APTC; and

e) advise of any implications from this Stage for future Stages of the APTC.

Annex K: APTC Stage II Performance Assessment Framework

Project Goals

	Training
	1. Increased supply of skilled workers in targeted sectors in the Pacific region

	Employment
	2. Pacific Islander women and men with Australian qualifications realise improved employment opportunities nationally, regionally and internationally in targeted sectors

	Productivity
	3. Increased productivity of individuals and organisations in targeted industries and sectors


Key Result Areas and Objectives
	Component
	Objective

	Component 1: 

Marketing, Reputation and Image
	Design and deliver a targeted, multi-level communication and marketing strategy that maximizes exposure by prospective students and industry to APTC programs and builds brand awareness and reputation across the Pacific region

	Component 2: 

Partnerships
	Collaborate with Australian and Pacific Island industry associations, firms, private training providers and government training institutions to deliver sustainable, value-added Australian Quality Standard vocational and technical education in prioritized skill deficient areas in the Pacific region.

	Component 3: 

Quality Learning
	Produce ‘work-ready’ graduates for national, regional and international labour markets through delivery of locally responsive, demand-driven technical and vocational education and training (TVET) to Australian standards.

	Component 4:

Student and Scholarship Management
	Provide support to all APTC students and administer scholarship procedures that maximise opportunity for students from all Pacific Forum countries to access and successfully complete APTC programmes with particular focus on redressing gender, isolation and income discrimination and ensuring that student health and welfare concerns are proactively and professionally addressed.

	Component 5: Management and Governance
	Utilize exemplary human and financial resource management practices to ensure project goals are achieved on time and within budget and institutionalize good governance processes at all levels of the project compliant with APTC operating principles and AusAID guidelines for performance reporting.


APTC PERFORMANCE ASSESSMENT FRAMEWORK

Data to be disaggregated by Campus Country, School, Course, student country, gender, age, and entrant type (new entrant/existing worker) where possible

	Ref
	Outcomes
	Verifiable Indicators
	Means of Verification
	Responsibility
	Data Source

	1
	Training

Increased supply of skilled workers in targeted sectors in the Pacific Region
	1.1 Graduate numbers disaggregated by country, gender, and other characteristics:


	APTC Database

Student Monthly

Six-Monthly Reports

School records


	CSS/Schools 
	AVETMISS compliant School records 

	2
	Employment

Pacific Islander women and men with Australian qualifications realise improved employment opportunities nationally, regionally and internationally in targeted sectors
	2.1 80% of students and employers who complete the End Of Course and Employer surveys report improved employment outcomes
	Integrated Set of Employer and Student surveys along with other information gathered under the Labour Market Intelligence function of the APTC CSS
APTC Employer and Student Surveys

 Tracer Studies one year after graduation (Occupations pre and post training should be classified using SCO08 three-digit categories)

Employer Survey results (of APTC students and graduates)

Research conducted on national, regional and international labor market needs and trends with relevance to APTC
	CSS collects, consolidates and reports on data 


	Surveys

	
	
	2.2 80% of graduates who complete the tracer survey report improved employment outcomes within one year after graduation 

2.3 Percentage of graduates working in occupations, and at levels, in which they were trained


	
	
	APTC Database



	
	
	
	
	
	Focus Group Discussion Notes



	3
	Productivity

Increased productivity of individuals and organisations in targeted industries and sectors
	3.1 80% of graduates who complete the tracer study report increased productivity as a result of the completion of an APTC 

3.2 80% of graduates who complete the tracer study report increased weekly/ monthly gross earnings as a result of the completion of an APTC courses
	
	
	Surveys

	
	
	3.2 80% of employers of APTC graduates who complete the Employer Satisfaction Survey report increased productivity as a result of the completion of an APTC course


	
	
	APTC Database

	
	
	3.3 Results of labour market studies incorporated in Annual Training Profile with modifications to courses/locations as required


	
	
	PIF Country and Regional Statistics and Reports


	KRA 1: MARKETING, REPUTATION AND IMAGE 
Objective: Design and deliver a targeted, multi-level communication and marketing strategy that maximizes exposure by prospective students and industry to APTC programs and builds brand awareness and reputation across the Pacific region

	Ref
	Outputs
	Verifiable Indicators
	Means of Verification
	Responsibility
	Data Source
	Risks
	Risk Management

	1.1
	APTC earns a reputation for offering valued training appropriate to Pacific Islander needs at an affordable price
	1.1.1 Student Satisfaction Survey at exit indicate an overall satisfaction rate greater than 80% 
	1.1.1 Student End of Course (EOC)survey results for minimum 50% of APTC students 
	Schools collects data; CSS consolidates and reports
	Student Database
	
	Effective student learning and welfare provided to students (See Component 4)
Annual marketing strategy focussed on target groups 

	
	
	
	1.1.2 Student and 
Scholarship Management Work Team reports to SMT
	CSS 
	
	
	Training partner expertise used to design and deliver culturally sensitive training 

Review and incorporation of 2007 Marketing Strategy 

	
	
	1.1.2 Business Satisfaction Survey indicates satisfaction with APTC training greater than 80% 
	1.1.2 Annual Employer Survey results for minimum 50% employers

1.1.2b 

Feedback from key stakeholders including Advisory Group members and during country consultations

	Schools collects data; CSS consolidates and reports

CSS gather data consolidates and reports
	APTC Employer Database

AG minutes


	Misleading information and inappropriate marketing practices (Breach of AQTF compliance) 
	Labour market intelligence used to develop responsive Annual Training Profile

Lessons Learned identified in Annual Audit of marketing materials and Annual Plans with corrective action

Tuition fee pricing policy implemented

	
	
	1.1.3 Number and distribution of positive articles in PIF/regional media & publications, promotional materials and website usage


	1.1.3 Press Clipping Portfolio

1.1.3a Website access by month/country

1.1.3b Material production and distribution records
	CSS 
	APTC Marketing records

Marketing Work Team 

 Reports to SMT 
	Schools unable to attract diverse applicants due to inadequate marketing coverage and/or economic and cultural barriers to TVET participation

Lack of internal monitoring of stakeholder feedback results in reactive programming
	Training provided for all APTC staff involved in marketing activities

and committed to sharing feedback and lessons learned to improve effectiveness

Develop and maintain corporate culture where staff are comfortable

	
	
	1.1.4 Communications Registry indicates positive feedback, formal complaints and actions taken


	1.1.4a Register developed and kept up-to-date

1.1.4b Evidence that complaints are addressed and systems adapted for improved practise
	CSS 

SMT Directives
	Communications Register

APTC Marketing records

Marketing Work Team reports to SMT
	
	

	
	
	1.1.5 APTC marketing materials widely accessible in user-friendly formats 


	1.1.5 Annual audit of marketing materials and procedures compliant with AQTF policy and contractual requirements

	CSS 
Gender Advisory Group 
	Reports to SMT

Marketing Work Team reports

Gender Advisory Group Minutes
	
	

	1.2
	APTC recognised by PIF citizens and organisations as a value-adding vocational educational option
	1.2.1 Demand exceeds scheduled program for annual delivery targets


	1.2.1 Applicant numbers disaggregated by gender, course, school and country 

1.2.1a Number of individual or industry funded places
	Schools collect data and report, six month and annual reports.
	Student Database
	Negative publicity and perceived biases 

APTC substitutes for existing TVET capacity

Non-partner government agencies feel marginalized

Adverse affect on local

society and/or environment

due to APTC operations

Inadequate number of eligible trainees to meet School targets 

Inability for new entrants to self-fund and/or unwillingness of employers to subsidize costs


	Annual Marketing Strategy and Recruitment Plan focuses on under-represented and fragile PIFs

Strong relationship management (see Component 2) together with rigid focus on complementarities with local institutions in course design and marketing

Dialogue established by Schools with non-partner agencies as part of industry consultation processes

Dialogue established with Government agencies on issues human resource development planning, labour mobility, employment conditions for graduates 

Ensure compliance with local laws and regulations.

Environmental Management Plan developed for all locations

	
	
	1.2.2 APTC featured in industry, government and regional plans for TVET
	1.2.2 Official policy and planning documents of industry and government
	School’s provide industry data to CSS; CSS correlates and reports on PIF and regional plans
	APTC Marketing Database 
	
	

	1.3
	APTC uses gender sensitive marketing and targeted student recruitment strategies
	1.3.1 Number of positive gender achievement stories appearing in PIF media and publications
	1.3.1 Press Clipping Portfolio and APTC website featuring female students

1.3.2 Targeted campaigns delivered and reviewed annually 

1.3.3 Focus Group 

Discussions
	CSS
	Marketing Work Team reports to SMT

Minutes of Gender Advisory Group Meetings 

CSS/School six month and annual reports
	Marketing and recruitment activities may not penetrate sufficiently to achieve targets

Socio-cultural and economic factors constrain female participation


	Local networks identified and engaged to identify women and other marginalized students 

Target Course-specific gender equality targets as per APTC Gender Policy

Strategies to reduce cultural and gender barriers to TVET in place

	1.4
	APTC uses targeted strategies to promote awareness of the APTC in NCCs and isolated and remote locations
	1.4.1 Number of positive APTC promotion and achievement stories appearing in SIS media and publications
	1.4.1 Press Clipping Portfolio and APTC website featuring SIS and remote location students
	CSS including NCC Country Coordinators
	Marketing Work Team reports to SMT

APTC six month and annual reports
	Marketing and recruitment activities may not penetrate sufficiently to achieve targets

Socio-cultural and economic factors constrain SIS participation
	Country coordinators established in NCC of Kiribati, Tonga and Nauru.
Regular schedule of APTC visits to SIS including development of targeted Country Strategies
SIS representation on Advisory Group

SIS alumni used to promote awareness of APTC


	KRA 2: Partnerships 

Objective: Collaborate with Australian and Pacific Island industry associations, firms, private training providers, government training institutions and Pacific Governments to deliver sustainable, value-added Australian Quality Standard vocational and technical education in prioritised skill deficient areas in the South Pacific region

	Ref
	Outputs
	Verifiable Indicators
	Means of Verification
	Responsibility
	Data Source
	Risks
	Risk Management

	2.1
	Agreements with partner training institutions in PIF countries in place and managed
	2.1.1 Formal agreements include procedures for monitoring and problem-resolution 
	2.1.1 Signed Agreements


	GM 
	Agreements

Contract Register
	Changes in training partner commitment, motivation or capacity to be an effective partner

Lack of systematic engagement with training partners


	Develop and maintain close and supportive relationships with PIF Governments, PIF Partner Executives, staff and Boards through formal mechanisms (i.e., Project Team Round Table) and informal mechanisms (newsletters, social events, APTC sponsored professional development of PIF managers and staff) 

Maintain dialogue with alternative candidates for partner training institutions.

Courses duplicated in other countries; contingency plans for replacement partners; alternative use of institution partners



	
	
	2.1.2 Regular partner consultations to minimise formal dispute notices
	2.1.2 Reports and records of meetings


	Schools

CSS
	School Consultation Notes 
	
	

	
	
	2.1.3 Annual review of agreements to review partnership progress and consider the need for any variation
	2.1.3 Minutes of Annual Review Meetings and Variations


	Schools

CSS
	Minutes of Annual Meetings 
	
	

	2.2
	Agreement / support by employers sending employees to Schools
	2.2.1 Formal instruments of agreement where applicable
	2.2.1. Signed agreements and amendments


	Schools
	School & Employer Agreements
	Lack of or change in commitment, motivation or capacity of individual employers or industry as a whole to engage with APTC

Employers lose confidence and withhold applications 

Employers not willing to pay APTC tuition fee
	Develop and maintain close and supportive relationships with individual employers and industry bodies through formal mechanisms (industry advisory groups, periodic labour market surveys) and informal mechanisms (in-country managers to participate in the activities of employer /industry associations and network informally)

Tuition fees set at market rate as per the Tuition Fee Policy

	
	
	2.2.2 Employer endorsement of application for admission for students currently employed
	2.2.2 All applications endorsed by employer where applicable


	Schools
	Employer Agreement Forms
	
	

	2.3
	APTC has access to information and advice on industry trends in the Pacific region
	2.3.1 Summary Labour market information is sourced, analysed and utilised in APTC forward planning


	2.3.1 CSS six- summary reports to SMT

2.3.1a Register of research source and data repository

2.3.1b APTC engagement with PIF/regional labour focused organizations


	CSS
CSS
CSS/Schools
	PIF/regional labour market analysis, HRD plans, householder surveys, census reports
	APTC does not respond to emerging PIF labour requirements leading to under/over supply

Insufficient participation from well disposed and well informed members 

Lack of cohesion amongst industry in PIFs

National and regional bodies not strong mechanisms for industry

Schools do not fully conform to AQTF standards in course delivery or in graduation standards resulting in graduates who do not have adequate skills to meet industry requirements

AG not sufficiently across the labour market or vocational training issues to be addressed to be able to give effective advice and direction

APTC does not fully respond to AG advice and direction.
	Close co-ordination with industry associations as per Partnerships Component 2

Labour Market Intelligence (LMI) systematically collected and recorded including through consultation and data collection with Australian/NZ industry associations and through visits to PIFCs

Provide sufficient information to AG on APTC and PIF employment related data to enable strategic input on program directions

APTC staff maintain contact with AG members when in PIF’s

AG has strong Australian and Pacific industry representation

Annual Training Profiles to explicitly reference LMI in recommending course profile

Medium-term labour market information collected and analysed

Partnership Engagement Strategies developed as part of Annual planning process

	
	
	2.3.2 Industry and partner government consultation informs planning and course delivery


	2.3.2 Compliance with AQTF Industry consultation requirements

2.3.2a Revisions to training and assessment models

2.3.2b Industry moderation

2.3.2c Trainer profile maintained

2.3.2d College affiliated with national and regional level TVET stakeholders

2.3.2e Annual Stakeholders mapping and engagement exercises
	Schools

Schools/CSS
AG
	School AQTF data repositories

AG Minutes

Annual Plan Meeting Minutes
	
	

	2.4
	APTC has support of Pacific Governments
	2.4 Formal instruments of agreement signed and extended where applicable


	2.4.1. Signed agreements and amendments


	CSS
	Agreements

Contract Register
	Lack of understanding of role of the APTC in regional TVET strengthening and its value to economic growth and productivity
	Develop and maintain close and supportive relationships with PIF Governments. 
Inclusion of PIF Government representatives on APTC Advisory Group

Regular consultation during in-country visits

AusAID to raise awareness of APTC during relevant bilateral and regional donor and education forums.

AusAID bilateral programs to be involved in developing partner government relationships/agreements

	2.5
	APTC provides support to national TVET institutions
	2.5.1 Training provided by APTC Centre for Professional Development
2.5.2 Formal and informal training and support for partner and other TVET institution institutions
	2.5.1 Records of enrolments and graduations from Centre
2.5.2a Records of agreements for formal support of partner and other TVET institutions

2.5.2b Satisfaction with support provided
	APTC Centre for Professional Development
Schools

National TVET Institutions
	School records
Student database

Agreements with national TVET institutions

Survey of institutions; Feedback at Advisory Group meetings; Institution/APTC meeting records
	Number of enrolments limited by Pacific government and AusAID/other donor funding
Support provided detracts from core purpose of APTC to deliver Cert III/IV courses.

Support is not integrated with or conflicts with other (AusAID) capacity building initiatives.

APTC working (at cross) purposes to the PNG bilateral program


	APTC and AusAID to promote awareness of Professional Development courses with Pacific Governments, national TVET institutions and other donors. AusAID to consider including APTC Professional Development training in their bilateral programs for TVET strengthening.
Support to be documented, monitored and reported.

Formal support for other institutions to be discussed with AusAID prior to commencement to ensure consistency with AusAID’s overall TVET program of support



	KRA 3: Quality Learning

Objective: Produce ‘work-ready’ graduates for national, regional and international labour market through delivery of locally responsive, demand-driven technical and vocational education and training (TVET) to Australian standards

	Ref
	Outputs
	Verifiable Indicators
	Means of Verification
	Responsibility
	Data Source
	Risks
	Risk Management

	3.1
	Provision of quality training and assessment across all APTC operations in compliance with AQTF 2010 Standards.


	3.1.1 Collection and analysis of data for continuous improvement of training and assessment


	 3.1.1a Scope of Registration documentation for School’s

3.1.b Records of staff, planning & moderation meetings
3.1.1c Student and Employer Satisfaction Surveys

3.1.1 d Records of industry consultation

3.1.1e Internal and external audit reports

3.1.1f Staff performance reports

3,1,1g Course completion rate

3.1.1h Average student contact hours per course

3.1.1i AQTF Learning Engagement indicator


	Schools
	AQTF 2010 Standards

School records

Student database
	Candidates do not have necessary qualities to achieve appropriate standards

Inadequate assessment at recruitment leads students to the wrong courses

Training records not kept up to date by trainers and/or students

Schools do not fully conform to AQTF standards in entry criteria leading to high attrition rates

Courses not designed to meet Pacific/international industry requirements


	Targeted recruitment program aimed at candidates with most relevant background

All candidates go through examination of prior learning, prior experience and literacy and numeracy tests to appropriate 

standards 

Schools ensure skills testing is conducted by experienced staff

Schools subject to Quality Management processes whereby periodic AQTF audits are to used to identify system improvements and develop remedial action processes and strategies, and monitor progress 

Design of “sandwich courses”, and work experience parts of curriculum especially for students with no prior work experience

Schools design programs in consideration of socio-cultural influences

	
	
	3.1.2 a Training and assessment strategies meet training package requirements within a Pacific context

3.1.2b Work placements provided to local and overseas students as per training package requirements


	3..1.2a Program Training and Assessment Strategies

3.1.2b Internal and external audit reports

3.1.2c Student and Employer Satisfaction Surveys 

3.1.2d Delivery plans and schedules

3.1.2e Individual student training plans (include reasonable adjustment strategies developed in consultation with individuals and industry)
	Schools

Schools

Schools/
CSS
Schools

Schools
	AQTF 2010 Standards

School records
	Insufficient work placements available particularly for overseas students
	APTC to foster positive relations with employers so that they provide workplace assessments for local and overseas students.

APTC to work with AusAID and partner governments to resolve any legal, regulation and visa issues for work placements by overseas students.

The Annual Training Profile to detail the arrangements made for adequate work placements for any new courses to be established.

	
	
	3.1.3 Staff, facilities and equipment and materials meet training package requirements


	3.1.3a Training Staff profiles documented and regularly updated

3.1.3b Audit of training equipment and facilities against training package requirements

3.1.3c Staff Induction and professional development records


	Schools
	AQTF 2010 Standards

School records
	RTO unable to recruit or attract suitably qualified and experienced staff

Facilities are not renovated in time to utilise for teaching

Equipment available in country does not meet training package requirements

Occupational, Health and Safety of staff/students compromised
	Consortium approach to project to ensure larger pool of experienced and qualified trainers in the nominated fields. Effective promotion of career benefits / employment packages.

Building works are closely monitored and professionally project managed. Availability of alternative facilities negotiated with Partner Institutes and local businesses if required.

Negotiations held with local restaurants and hotels for use of equipment if required until appropriate equipment can be brought in from Australia or New Zealand

Annual Training Profile agreed at least five months before course start

	
	
	3.1.4 Trainers and assessors meet qualification and experience requirements of National Quality Council

and AQTF 


	3.1.4a Training Staff profiles documented and regularly updated

3.1.4b Staff Induction and professional development records


	Schools
	AQTF 2010 Standards

School records
	
	

	
	
	3.1.5 Assessment, including RPL meets training package requirements


	3.1.5a Self Assessment documentation

3.1.5b RPL documentation

3.3.5c Training Plan documentation


	AQTF 2010 Standards

Schools
	AQTF 2010 Standards

School records
	
	

	3.2
	APTC adheres to the principles of access and equity and maximises outcomes for its students and industry clients in compliance with AQTF 2010 Standards and AusAID guidelines
	3.2.1 All APTC information reflects the principles of access and equity
	3.2.1 Audit of promotional, application, induction materials, student handbooks learning and assessment materials


	CSS and School
	AQTF 2010 Standards 

Schools records

APTC Gender Access and Equality Policy
	Annual Scholarship targets established based on agreed distribution guidelines and monitored on 6 monthly basis to ensure equitable access by female and NCC applicants

Non-adherence to Gender Policy 
	Marketing and admissions strategies strive for an appropriate balance between local and incoming students.

Student Management Work Group monitors implementation of Gender Policy using inputs from stakeholders

	
	
	3.2.2 Benchmark APTC student outcome against AQTF and NCVER data


	3.2.2 Comparative Assessment commissioned and completed annually


	CSS
	
	Delivery modes unsuitable to meet student needs or Pacific Island learning styles

APTC graduates perform poorly in relation to Australian & overseas students

Remedial literacy and numeracy assistance is not available to enable student entry and success in APTC programs
	Responsiveness and flexibility of M&E system to identify and support programme redesign as needed

Collaborate with agencies providing literacy upgrading assistance

Ensure student training programs provide individualized learning support as required

	
	
	3.2.3 Students and employers report positive change in skills and work practices


	3.2.3a Student and Business Satisfaction surveys

3.2.3b AQTF Employer Satisfaction indicator
	Schools/CSS
	Student Database 

Survey Database


	 Students do not find or sustain employment after graduation
	Partnership agreements with employers regarding graduate employment and skill utilisation

	
	
	3.2.4 Programs initiated for prospective students unable to meet literacy and numeracy requirements of AQTF Level III programs
	3.2.4 Records of applicants who meet technical skills but do not have ELLN skills for entry to course 

3.2.4b Annual Planning addresses literacy constraints 
	CSS
	Student Database
	Reduced participation, especially in SIS
	Stage II commencement of ELLN Bridging Programs in SIS and Ancillary Awards



	
	
	3.2.5 All enrolled students are provided with access to literacy, numeracy and other learning support
	3.2.5a Records of referrals for ELLN support by Schools

3.2.5b Student Training Plans, student handbook, timetables and records of referral


	Schools
	School Records
	Students not able to communicate in English at a sufficient level to pass their course or to meet employer expectations


	Accurate context-based ELLN testing of applicants

Sufficient ELLN support provided at each campus

	3.3
	Effective, high quality male and female instructional and support staff with good understanding of the Pacific context engaged and retained
	3.3.1 Student Outcome Data provides an 80% or higher satisfaction with staff level

3.3.2 Proportion of instructional staff that are female

3.3.2 Proportion of support staff that are female


	3.3.1 Student and Employer Satisfaction Survey reports
3.3.1a Evidence of data use by Schools for continuous improvement 

3.3.1b Evidence of unit or cluster use of data for continuous improvement:


	Schools/CSS
SMT Minutes

School six month reports aggregated by CSS 
	
	Unable to recruit and retain suitably qualified and experienced trainers

Trainers unable to adapt teaching methods to local context

Female trainers unwilling to live in specific situations due to security concerns

Trainers engage in unlawful, unprofessional or inappropriate conduct of personnel
	Competitive and well structured expatriate remuneration strategies

Secondment from PI agencies

Transfer trainers between campus countries 

Staff pre-departure and orientation programs and ongoing support provided to instructors on cross culture relations, gender dynamics, security, isolation 

Schools provide staff with training and support in meeting AQTF requirements

Teacher Codes of Conduct enforced

Staff selection criteria to include previous experience operating abroad or in a multi-cultural environment



	
	
	3.3.4 Staff orientation and in-service includes cultural issues, gender dynamics, violence, substance abuse, working with disabilities, HIV/AIDS and child protection
	3.3.4 Contractor records including results off pre-post assessment


	School’s & CSS
	
	Inadequate data and analysis leads to inequitable distribution of APTC services

Availability of trainers and facilities does not keep pace with demand
	Disaggregated data reports mandatory in six monthly and annual report

	
	
	3.3.5 Disaggregated data is analysed and reported to comply with APTC targets for gender and nationality
	3.3.5 Contractor and School records


	Schools & CSS
	Student Database

APTC Gender & Equality Policy
	
	

	
	
	3.3.6 Level of interruptions to training programs is managed and minimised
	3.3.6 School Delivery Schedules


	Schools
	School records
	
	

	3.4
	Appropriate housing and learning facilities provided to all students
	3.4.1 Facility development according to capital works and programmed maintenance plans


	3.4.1a School Reports

3.4.1b Student Satisfaction Surveys


	Schools

Schools/CSS
	
	Equipment/ infrastructure not delivered and installed in time

Inadequate housing arrangements lead to drop-out

Services not provided in accordance with Programmed Maintenance Plan or inadequate facilities provided by partner organisations
	Accountable project management framework established 

Realistic lead times established and training delivery planned around realistic resource availability dates

Establish and monitor formal contract arrangements for funding maintenance of APTC facilities and for partner facilities provision



	
	
	3.4.2 Adequate, accessible, and secure accommodation for women housing arranged for overseas scholarship awardees


	3.4.2a School Staff TORs include responsibility for appropriate housing 

3.4.2b Student Satisfaction Surveys

3.4.2c Results of Annual Audit
	Schools
	APTC Gender & Equality Policy
	
	

	
	
	3.4.3 System in place for addressing student complaints
	3.4.3 Schools and CSS records
	Schools/CSS
	Communications Registry and Grievance Procedures
	
	


	KRA 4: Student and Scholarship Management

Objective: Provide support to all students and administer scholarship procedures that maximise opportunity for students from all Pacific Forum countries to access and successfully complete APTC programmes with particular focus on redressing gender, isolation and income discrimination and ensuring that student health and welfare concerns are proactively and professionally addressed.

	Ref
	Outputs
	Verifiable Indicators
	Means of Verification
	Responsibility
	Data Source
	Risks
	Risk Management

	4.1
	Equitable access for under-represented groups including women, citizens of non-campus countries, rural and remote locations and students with disabilities
	4.1.1 Update the APTC Scholarship Policy and Procedures Manual by end June 2011 and review/revise on annual basis including targets for distribution of scholarship awards with consideration of gender, NCC access and urban/rural distribution across PIFs
	4.1.1 Annual Scholarship Strategy with agreed distribution targets 

4.1.1a Successive Scholarship Manuals compiled including results against targets and lessons learned


	CSS/SMT 

SMT appointed Scholarship Committee 
	Student Database

APTC Gender and Equality Policy;
Scholarship Design

Annual Plans


	High cost of reaching under- represented groups 

Scholarships awarded to students with easiest access and greater financial means

Imbalance of award given to students from campus countries

Under-represented groups are unable to meet College admission requirements quotas for scholarship and small PIC participation rates not achieved 

Delays in admission due to travel documentation 

Numbers of applicants do not allow for genuine selection

Documentation of students past local qualifications not available or not adequate 

Students may perceive selection processes is inequitable or biased
	Develop low cost, high penetration marketing outreach strategies in small island states and remote areas 

Indicative scholarship allocation by country to be approved annually by AusAID

Assist motivated students to become initially engaged in national trades training systems to prepare them for APTC entry in later intakes

Visa and entry protocols developed in all sending and receiving PIFs 

Marketing programme design against target application rate

Selection process decisions and accessible to students on request

Marketing and admissions strategies strive for an appropriate balance between local and incoming students.



	
	
	4.1.2 Scholarships scheme benefiting students who would otherwise not have attended

4.1.3 Increase in number of women applying, graduating and receiving scholarships

	4.1.2 Disaggregated student participation and application data on the following categories: Individually funded; Industry funded; Full and partial assistance; Existing worker/New Entrant

4.1.2a 6-monthly reviews of scholarship policy and processes to arrive at equitable allocations of scholarship funds by country, gender and school issues

4.1.3 School Admission Records
	CSS/Schools

SMT appointed Scholarship Committee

Schools


	Student Database

Scholarship Design Document

Manual versions

Student Exit Surveys 

Tracer Studies

Student Database
	
	

	
	
	4.1.4 Number of students with a disability enrolled at APTC
	4.1.4 School Admission Records
	Schools
	Student Database


	
	

	4.2
	Admission, appeals and grievance processes comply with AQTF 2010 Standards
	4.2.1 Admissions, appeals and grievance process are documented and readily available


	4.2.1 School Admission Process and Records


	CSS/Schools 
	APTC Grievance and Appeal Policy

AQTF 2010 Standards 
	Student, government or industry appeals are not transparent and become politicised
	Establish complaints handing process

Students given access to records and complaints handling system in place

	4.3
	Students able to make the most of their study opportunity 
	4.3.1a Students receive access to support services to meet their individual needs and achieve training outcomes as required by AQTF 2010 Standards and APTC welfare policies

4.3.1b Percentage of scholarship extensions

4.3.1c Percentage of scholarship terminations

4.3.1d Satisfaction of scholarship awardees with scholarships management (including allowance payments and travel arrangements)


	4.3.1 Orientation documentation and sign-off checklists, incident reports

4.3.1a Campus Scholarship/ Welfare Officer employed, providing and reporting on services provision

4.3.1b Effective mechanism for coordination of Scholarship Officers 

4.3.1c Student Satisfaction Surveys

4.3.1d Staff feedback

4.3.1e Agreements in place with local specialist welfare support service providers


	Schools

Schools/CSS
Schools/CSS
	AQTF 2010 Standards

APTC Gender Access and Equality Policy

APTC HIV/AIDS Framework Policy

AusAID Child Protection Policy

Minutes of Campus-Country Gender and HIV/AIDS Advisory Groups

Minutes of Scholarship Coordination Meetings

School contracts with local service providers

Student Database
	High proportion of incoming students means student support services stretched

.

Complexity of student travel causes problems for overseas students

RTO motivation or capacity to provide support services is limited, or not equipped for culturally appropriate responses

RTO/CSS Staff duty of care obligations breached


	Schools develop specific procedures for handling overseas student arrivals and departures.

Learning and student support funded as an integral part of program delivery

Schools to recruit suitable staff for student support roles, utilising local training partners extensively to ensure responses are culturally sensitive

Guidelines provided by Schools to staff on duty of care requirements and formally addressed as part of pre departure briefing and in regular meetings and in staff appraisals.



	4.4
	Students receive support in APTC-to work enhancement

	4.4.1 Programs embed and/or include work placement components
	4.4.1 Work placement records, career fairs, training plans


	Schools
	School Reports

Student Database
	Insufficient labor market knowledge by graduates

Insufficient awareness of employers to student competencies

Graduates not ready for the study-to-work transition


	Dedicated student services resources with access to labour market research, and integrally involved in employer partnerships. On-campus employer presentations and interview

	
	
	
	4.4.1a Relevant approvals in place to facilitate work placement


	SMT


	Exit Surveys


	
	

	
	
	
	4.1.1b Relevant insurance policies taken out and maintained to cover students in work placement


	CSS
	Tracer Studies


	
	Employee partnership arrangements (see Component 2)

	
	
	
	4.1.1c Membership of Alumni Association as proportion of all graduates
	CSS
	Alumni Association records
	
	 

	4.5
	APTC students comply with Code of Conduct and Student Rules


	4.5. Implement and review APTC Student Code of Conduct and Student Rules


	Student Code of Conduct and Student Rules endorsed by SMT and publically available


	Schools/CSS
SMT
	APTC Code of Conduct and Student Rules
	Students engage in inappropriate behaviour (including inappropriate or dangerous sexual behaviour) compromises student safety and College reputation

Inconsistency across the College in dealing with breaches in Student Rules creates disharmony and inequity
	 Student Code of Conduct established by Schools (with appropriate disciplinary procedures), with briefing during orientation and constantly reinforced

Number and type of breaches documented and reported to SMT



	
	
	4.5.2 Students sign to confirm that he/she will comply with the Code of Conduct and Student Rules
	4.5.2 Student records


	Schools
	Student Files
	
	

	
	
	4.5.3 Non-compliance with Code of Conduct issues are recorded by the School and addressed with the student
	4.5.3 Incident Reports

4.5.3a Consolidated report on number and type of incident provided by Student Management Working Group to SMT


	Schools

CSS
	School Records
	
	


	KRA 5: Management and Governance

Objective: Utilize exemplary human and financial resource management practices to ensure project goals are achieved on time and within budget and institutionalize good governance processes at all levels of the project compliant with APTC operating principles and AusAID guidelines for performance reporting.



	Ref
	Outputs
	Verifiable Indicators
	Means of Verification
	Responsibility
	Data Source
	Risks
	Risk Management

	5.1
	College-wide governance and coordination arrangements are agreed, documented, reviewed and adjusted
	5.1.1 APTC governance and management operating guidelines implemented to guide all College activities, through a continuous improvement process 
	5.1.1a Policies and procedures catalogued 
	GM, SMT
	AQTF 2010 Standards
	SMT fails to provide coordinated overall governance and leadership to the APTC

Responsibilities of the CSS, Schools, including country and campus offices, and work teams are not clearly defined, documented and functional across all areas
	A Governance and Structure Manual and supporting material be prepared and GM tasked with ensuring that management and governance arrangements are in place in compliance with AusAID and best practice requirements 

	
	
	
	5.1.1b Internal and external audits
	
	
	
	

	
	
	
	5.1.1c Minutes of SMT meetings: evidence of revision and version control for continuous improvement, quality operations systems
	CSS
	AusAID Quality Assurance Protocols
	
	

	
	
	
	5.1.1d Annual Planning Meeting to review lessons and establish priorities held prior to submission of annual plans
	CSS/Schools
	Annual Plan Meeting Notes
	
	

	
	
	
	5.1.1e Submission of six-month reports and annual plans AusAID on time consistent format following endorsement by SMT
	Schools/CSS
CSS
SMT
	SMT Minutes
	
	

	
	
	
	5.1.1f APTC Governance and Structure Framework prepared and endorsed by SMT
	GM

SMT
	Governance and Structure Manual
	
	

	
	
	5.1.2 Responsibilities of the CSS including CPCs, NCCCs and Work Teams clearly defined, documented and functional across the following areas:

· Planning 

· Financial management 

· Governance

· Logistical support

· Scholarships management

· Fees 

· Strategic / Brand Marketing 

· Monitoring and evaluation and risk management
	5.1.2aToRs developed and agreed

5.1.2b Policies, procedures, work instructions developed and endorsed by SMT and implemented by CSS

	CSS
SMT
	TORs for CPCs, NCCs, CSS staff and Work Teams


	Functional roles and responsibilities of School and CSS staff in campus and non-campus countries is not well understood or effectively utilized

College wide policies and procedures are not consistently applied

Work Teams are not well coordinated and managed leading to poorly informed policy and decision-making 
	Regular review of ToRs of all ATC corporate and training staff and adjustment as needed to meet College needs 

Six monthly review of APTC policies and procedures with staff training as required

Mentoring and monitoring of Work Teams to ensure effectiveness in problem analysis and identification of operational solutions

	
	
	5.1.3

Responsibilities of the Schools, including country and campus offices, local training providers and organizational partners and work teams are clearly defined, documented and functional across these areas:

· Planning 

· Financial management 

· Training and assessment 

· Student and scholarship management

· Recruitment Marketing 

· Monitoring and evaluation and risk management
	5.1.3a Policies, procedures, work instructions developed and endorsed by SMT and implemented by Schools

5.1.3b Letters of agreement / partnership agreements ,contractual arrangements are documented and reviewed on an annual basis 

5.1.3c Nominated staff are identified for team / functional responsibilities across common areas and provide recommendations for SMT endorsement


	Schools
	TORs for School Administrators and other nominated staff

School Policy and Procedures 
	
	

	
	
	5.1.4 SMT provides overall governance and leadership, accountability to the APTC program


	5.1.4a Monthly SMT meetings 

5.1.4b SMT Minutes and agreed actions are documented, distributed and implemented


	SMT

CSS
	SMT TORs

SMT Minutes
	SMT does not have sufficient information to provide leadership in achieving project goals

SMT does not provide adequate management support to ensure effective delivery and efficient use of resources

CSS does not provide adequate secretarial support to the SMT in carrying out its functions

SMT appointed Work Groups do not fulfil their ToRs or provide adequate/ accurate information to enable proactive policy making 
	Effective monthly SMT meetings and timely communications prior to and post meetings

Effective means of monitoring follow-up on assigned tasks and emerging issues

Use of Annual Plans and Lessons Learned documentation as basis for planning and monitoring 

Use of the PAF on systematic basis to assess College activities, outputs and risks

	
	
	5.1.5 CSS provides logistical support and secretariat services to the Advisory Group
	5.1.5a Evidence of support to the AG in a timely manner through minutes and other communications

 
	CSS
	AG Minutes

AG Member Feedback

SMT Minutes
	
	

	
	
	
	5.1.5b Information and advice arising from AG meetings is distributed for action to Schools as appropriate 
	CSS
	
	
	

	
	
	
	5.1.5c Schools receive and consider advice arising from AG meetings
	Schools
	
	
	

	
	
	
	5.1.5d Invitations to AG members to attend functions and events e.g. School Graduations
	GM/Schools
	
	
	

	5.2
	APTC policies and procedures comply with: AusAID requirements; AQTF 2010 Standards; Australian and relevant PIF legislation, regulations and statutory obligations; and good practice principles 
	5.2.1 APTC policies and procedures are developed and implemented and addressed. These include but are not limited to: 

· HIV/AIDS

· Gender Access and Equity

· Disabilities 

· Fraud

· Privacy

· Environmental Management

· Child Protection

· Scholarships

· Student and Teacher Code of Conducts

· Internet and Email Policy

· Partner Affiliation Policy
	5.2.1 Up-to-date policy register 

5.2.2 Policies are publicly available

5.2.3 Periodic sample reviews of the degree of implementation effectiveness of policies processes and procedures (e.g. Minutes of Work Teams)


	CSS, Schools


	Policy Register

APTC Procedure Manuals

Cross Cutting Policies

Work Team Minutes and Reports to SMT
	Ineffective or inconsistently applied policies and procedures for staff and implementing agents impedes effective management, project delivery and the achievement of project objectives


	CSS and Schools establish Procedures Manuals in core business areas approved by the SMT and updated regularly 
CSS and Schools ensure that ATPC policies and procedures are implemented and adhered to, and that the manual is available for recruitment and pre-departure briefings, and is used regularly in the operation of the College

	5.3 
	APTC adheres to human resource management best practices within the Pacific region 
	5.3.1 APTC builds capacity of human resources throughout the college for improved service delivery


	Contractor records including evidence of 

· Timely staff recruitment and induction 

· Learning and professional development opportunities for all staff

· Structured capacity building activities for local staff
· Performance management 

· Succession planning for sustainability 

· In-country support for staff (local and expatriate)

· Mentoring

· Provision of training for local staff
· Staff exchange 

· Staff development activities

· Staff and affiliates comply with Staff Code of Conduct 
	Schools, CSS
	APTC HR database

CSS and School HRD Strategies

Annual Plans

Staff contracts reference APTC Staff Code of Conduct 
	Lack of suitable local personnel hinders localisation 

Trained local trainers choose other options

High staff turnover

Staff lack appropriate skills and competencies for efficient and effective operations


	Selection of people expert in their field.

Offer competitive salaries and conditions 

Identify staff professional development needs and ensure appropriate training support

	
	
	5.3.3 Safe environment provided for staff and students
	5.3.3 Student satisfaction with training and study country environment
	CSS, Schools


	Student EOC survey
	Staff/student security decreased due to civil emergency/natural disaster
	Emergency and Evacuation Plan regularly updated and communicated to students and staff

	5.4
	ICT system enables efficient and reliable communication across the College
	5.4.1 A service level agreement established for email and internet endorsed by SMT
	5.4.1 Report against agreed service targets 


	CSS, Schools


	
	Interruption, loss of data or complete failure of ICT system

ICT system does not meet required performance standards


	Back up processes in place including remote storage of data to ensure effective retrieval of data within set timeframes.

Monitoring of compliance with back up procedures on a regular basis.

Close liaison with Schools in system design and implementation

	5.5
	APTC establish an EMIS complete with a fully integrated set of databases covering

· Students (from initial application to graduation)

· Graduates (tracking employment and migration outcomes)

· Staffing/HR functions

· Courses (scheduling, course numbers, assessment, etc)

· Asset register

· Materials inventories

· Finances and expenditures (FMIS)
	5.5.1 Development and maintenance of a robust and functional consolidated databases that produce accurate and rapid reports 

disaggregated by: course, school, campus, citizenship, age and gender as appropriate
	5.5.1a Database generates regular statistical reports 

5.5.1b All enrolled students included on individual RTO databases

5.5.1c RTOs transfer student data in an agreed format 

monthly/quarterly/annual
	CSS with mandatory and routine inputs from schools
	EMIS databases

 Six-Monthly Progress Report and Annual Report/Plans
	· Faulty database design

· Lack of APTC coding and classification manuals, leading to data inconsistencies

· Incorrect and/or incomplete data entry

· Poor data interrogation and analysis skills in APTC CSS
· ITC problems interfere with access and reliability
· Breach of data privacy
	Close liaison with Schools in system design and implementation 

Employment of a fully qualified EMIS manager, with appropriate supporting staff

APTC officer responsible for monitoring and improving data quality 

Engage suitable ICT advice in setting up technical (hardware and software) aspects of EMIS and conduct regular ICT maintenance 

Regular staff training in entering data into APTC databases

CSS provides reliable, high speed access to database for end-users

Security provisions in place to safeguard confidential student data 


	5.6
	Financial management information system (FMIS) provides accurate and timely data on operations
	5.6.1 Regular and accurate financial reporting as per contractual obligations

5.6.2 Timely notification of pressures on budget
	5.6.1 Reports provided to AusAID on time and in compliance with contract obligations

5.6 .2 Single APTC Asset Register


	CSS, Schools
	Financial Reports from FMIS

Asset register
	Ineffective budget control

Insufficient funding to achieve outputs

Adverse exchange rate movements

Theft, fraud or

corruption and failure

to comply with Commonwealth fraud control guidelines

Unqualified audits

Inconsistent financial reporting between contractor partners

Inability to separate training delivery from other costs 
	Regular budget monitoring and review processes in place

Internal and external auditing functions in place 

Exchange rate exposure managed in accordance with AusAID contract structure

Staff trained in compliance

requirements

Auditing functions to ensure

Compliance

Ensure compliance with AusAID policies on fraud and corruption control

Standards for financial recording and reporting implemented

	5.7
	APTC manages its activities within an appropriate risk management framework 

 
	5.7.1 Integrate risk management in PAF for ongoing review and adjustment in program delivery, policy and procedures in response to changed circumstances and lessons learned
	5.7.1 Evidence of ongoing review of risks and mitigation strategies in Work Team reports, SMT Minutes, six-monthly reports and Annual Plans


	CSS, Schools
	PAF

Work Team Reports to SMT

SMT Minutes

Six-month and Annual Plans


	Changed political and security situation in PIF’s impacts on program deliverables and the health, wellbeing and security of APTC staff and students
	Integrated risk management approach adopted by CSS and schools to regularly review and adjust program delivery, policy and procedures in response to changed circumstances and lessons learned

	5.8
	Reduced dependence on AusAID funds over time
	5.8.1 Fee for Service and Tuition income as a proportion of total APTC training delivery income (including from AusAID)
5.8.2 Number of tuition fee enrolments as a proportion of total enrolments
	5.8.1 Fee for service and Tuition fee income/enrolments reported on in Six-Month and Annual Plans


	GM/SMT
	Financial Reports 

Student Data Base
	College is not sustainable over long term without ongoing major share funding by AusAID

Fee for service activities distort services provided to scholarship/SIS students 

 
	Implement College Development Strategy in collaboration with PIF governments, private sector partners and other donor agencies

Implement Fee for Service Policy. Annual Training Profile stating places available for scholarship students

	
	
	5.8.2 Degree of substitution of Australian staff resources (Localisation)
	5.8.2a Proportion of total administrative/management staff that are local

5.8.2b Proportion of total trainer staff that are local

5.8.2c Sustainability reported on in Six-Month and Annual Plans 
	Schools/CSS
	APTC Staff database
	 APTC accused of “poaching local staff”

Loss of “Australian” branding of APTC

Recruitment of inexperienced local staff reducing training quality 
	Participate in regional dialogue with organizations that have vested interest in TVET development in the Pacific

APTC training of TVET staff in TAE4 (on fee for service basis)



	
	
	5.8.3 Operational efficiency
	5.8.3a Cost per student (contact hour, enrolled, graduate)

5.8.3b Average class occupancy (percentage)

5.8.3c Unit and Course competency completion rate (AQTF indicator)
5.8.3d %Invalid/ineligible applications

5.8.3e Admin: training delivery cost ratio (excluding scholarships and capital works)

5.8.3f Travel expenditure per annum

5.8.3g Student:staff ratio


	Schools/CSS
	Annual Report/Plan

Student database

Quarterly Financial Reports
	Cost efficiencies achieved at reduction of training quality
	Major changes in operations to be improved through Annual Report/Plan

Course quality and student satisfaction to be closely monitored


Annex L: Draft Job Descriptions for APTC Chief Executive Officer and School Director Roles
APTC Chief Executive Officer

The APTC Chief Executive Officer (CEO) has overall responsibility for ensuring the successful operation of the APTC against its goals and objectives, including discussion with AusAID and other key stakeholders on the strategic and longer-term operation of the APTC. The CEO will have a leadership and senior management role in supporting the APTC to provide industry-responsive, work ready AQF Certificate and Diploma graduates in the Pacific.
The CEO, APTC School Directors, and others nominated by the CEO, will be part of the APTC Senior Management Team.

Key Responsibilities
· Provide professional leadership, management, guidance and support to all APTC personnel (including long and short term and locally employed) to develop an organisational culture that focuses on the achievement of APTC goals, objectives and performance requirements through partnerships, teamwork, co-operation and client focus;
· Primary relationship management with AusAID, including with its regional and bilateral programs, the Advisory Group, Pacific government, donors, industry groups and national TVET institutions;

· Represent the APTC at high-level official meetings and functions, the APTC Advisory Group and at other meetings as required with AusAID, Pacific governments or other external stakeholders;
· Adhere to and ensure all APTC personnel adhere to the APTC Code of Conduct, including the APTC corporate values, principles and good practices of employment equity, access and gender equity, ethical conduct and workplace health and safety;

· Manage the provision of secretariat services to the Senior Management Team and to the APTC Advisory Group; 
· Manage APTC staff and human resources in accordance with contractual requirements of AusAID, including ensuring staff are employed in accordance with local national labour laws and awards;

· Manage the provision of the cost-effective functioning of APTC staff and human resources, finance and accounting, ICT and MIS, marketing, monitoring and evaluation, labour market analysis, quality assurance and the APTC Scholarship Scheme;

· Coordinate consistency of planning, management, implementation and reporting processes across Corporate and Student Support (CSS) and APTC Schools;
· Manage the staff and functions of Corporate and Student Services;

· Supervise and support the School Director(s) to provide industry-responsive, work ready APTC graduates including meeting the requirements of AQF and AQTF standards;

· Manage any feasibility and design studies for the establishment of new training venues, schools and courses;

· Monitor the implementation of the APTC Fee for Service policy by APTC Registered Training Organisations;

· Manage analysis and assessment of labour market demand for VET in the Pacific region and coordinate the APTC response, including in preparation of the Annual Training Profile;

· Manage monitoring of APTC performance through implementation of the Performance Assessment Framework to meet AusAID reporting requirements;

· Manage the compilation of financial reports, six-monthly progress annual workplans/ reports, specified milestone reports, and AusAID and other reporting requirements for the APTC; and

· Improve the financial sustainability of the APTC through improving cost-effectiveness of APTC administration and training delivery and increasing revenue from fee-paying students. 
___________________________________________________________________

Director of School

The School Director will have a leadership and senior management role in supporting the APTC to provide industry-responsive, work ready AQF Certificate and Diploma graduates in the Pacific.

The School Director will be responsible to the APTC CEO for the overall management of the designated School in all its locations and for the delivery of APTC training at AQTF standards within the School. Together with the CEO, other School Directors, and others nominated by the CEO, the Director of School will be part of the APTC Senior Management Team.

Key Responsibilities
· Provide effective leadership, senior management and VET knowledge to establish and maintain the strategic direction of the APTC School as a leading provider of industry-responsive, work ready graduates in the Pacific;

· Coordinate and supervise the teaching and learning programs and activities of the School across all APTC countries;
· Ensure the AQTF standards are maintained in the School by encouraging an environment where high quality work is achieved and supported by the adherence to and development of quality system documentation;

· Provide technical and professional leadership, management, guidance and support to all School training delivery and administrative personnel (including long and short term and locally employed) in developing an organisational culture that focuses on the achievement of APTC goals, objectives and performance requirements through partnerships, teamwork, co-operation and client focus;
· Adhere to and ensure all School personnel adhere to the APTC Code of Conduct, including the APTC corporate values, principles and good practices of employment equity, access and gender equity, ethical conduct and workplace health and safety;

· Conduct and participate in workshops, seminars and advisory groups and foster and maintain positive relationships with industry and institution partners, government representatives, Pacific TVET institutions and related industry sectors;
· Project manage the establishment of new partnerships, training venues and courses of the School;

· Advise the CEO on APTC responses to labour market demand for VET in the Pacific region, including assisting in preparation of the Annual Training Profile;

· Advise the CEO on resource requirements to enable the School to meet current and future programs and serviced needs; 
· Provide support to the CEO in preparation of financial reports, six-monthly progress reports, annual plans/reports, M&E including assessment against the APTC Performance Assessment Framework, specified milestone reports, and AusAID and other reporting requirements of the APTC;

· Participate in marketing campaigns to promote the APTC/School and recruit fee-paying and scholarship student enrolments;
· Support the CEO to improve the financial sustainability of the APTC through improving cost-effectiveness of training delivery and increasing revenue from fee-paying students; and
· Represent the School/APTC at high-level official meetings and functions, the APTC Advisory Group and at other meetings as required with AusAID, Pacific governments or other external stakeholders.

Annex M: APTC Education Management Information System High-Level Requirements
Student and Scholarship database 

Applications – applicants’ names, addresses, age, sex, nationality, education records, employment records, previous training, course preferences, etc

Offers of places – school, campus, course, RPL etc

Fee basis - school, campus, course (full-fee, partial fee, employer sponsorship, fee waiver, part scholarship, full scholarship) 

Enrolments – school, campus, course, modules, commencement dates, status (part-time/full-time, etc)

Student progress – school, campus, course, assessment details, module completions, deferments, drop-outs, etc

Completions - school, campus, course, graduation dates, transcripts, etc 

Scholarships - Applications, offers, level of award, progress, completions, etc, by school, campus, course, sex, nationality, etc

Alumni database
 
Alumni contact details, association membership, current employment etc

Survey database 

Student end-of-course surveys

Graduate tracer studies

Employer surveys

Program profile database

Core programs and courses - by school and campus, scheduling, module completions, training hours, assessments, etc

Fee-for-service courses

Financial database

Funding 

AusAID milestone payments, etc

Fee income for core programs

Income from FFS programs

Other income

Expenditures

Design and development

Capital program

Procurement, etc

Recurrent expenditures

Personnel 

Transport and travel

Maintenance and operating expenses (MOE)

Development and marketing, etc

Payments to industry and institutional partners

Management and support

Scholarships fund

Staffing database

Teachers and instructors - school, campus, course, sex, nationality, length and terms of contract (including remuneration, accommodation, allowances, etc), deployments, etc

Other college staff – international and locally engaged

Staff travel schedules

Asset register 

School, campus, program furnishings, machinery, equipment and vehicles acquired

Supply inventories 

School, campus, course teaching and other materials, etc

Annex N: Draft APTC Stage II Fee-for-Service Policy
1.
Purpose

The purpose of this policy is to provide clear direction on procedures to follow for Fee-For-Service (FFS) delivery of services to Australia-Pacific Technical College (APTC) clients by the College. 

2.
Scope

This policy covers APTC’s approach to marketing, sourcing, costing, pricing, bidding, implementation and reporting of all full fee-for-service activities.
3.
Principles and Approach

a) A FFS activity is an activity undertaken by the APTC which is not included within the scope of the respective management contract with AusAID and is fully funded from outside the existing contract.

b) A FFS activity will only be considered if it relates to training or training support services within the industries represented by the five schools that make up the APTC.

c) FFS activity will only be considered if it involves training in Australian qualifications at Certificate III level or above, leading to full qualifications or customised programs within such courses, consistent with the core purposes of the APTC to provide level III and IV Australian qualifications and to enhance productivity and regional labour mobility.

d) FFS activities will supplement core-funded training. FFS activity will not be at the expense of delivery of core training operations and access by potential students.

e) The APTC will not openly market for FFS activities, however may respond to direct requests for FFS activity or provide response to tender opportunities.

f) APTC FFS activities will not compete unfairly with commercial activities of national or regional training providers or private sector providers fully observing principles of competitive neutrality. 

g) APTC FFS activities will be offered to external parties only on a full cost recovery basis (including all direct delivery costs, administrative and management costs, overhead costs taking into account the principles of competitive neutrality). APTC facilities and resources may be used for FFS activities provided use of the APTC facilities is fully costed in the proposal and the activity does not interfere with scheduling of core training programs. For AusAID bilateral or regional programs the costing will take into account existing AusAID funding for capital and the organisational infrastructure of the APTC.

h) APTC RTOs will not bid for FFS activities in competition with the APTC. 
i) APTC may bid for FFS activities in partnership with other Australian RTOs subcontracted through the APTC.

j) All proposals for FFS activities must be approved in advance by the APTC Senior Management Team (SMT), and any bid over AUD$1,000,000 must receive advance approval by AusAID Suva. 

k) Acceptance of FFS activities must be based on a minimum rate of return of 12%; and include an allocation of profit to APTC on a 50:50 basis after accounting for all costs associated with the activity.

l) All profit allocated to the APTC from its FFS activities will be placed in a special purpose account. All profit allocated to the APTC will be utilised for training and scholarship purposes or other activities deemed to support the development of APTC, including reductions in the cost of delivery of AusAID funded programs or provision of additional programs and enrolments. 

m) The APTC will, on an annual basis as part of the budget process, make recommendations to AusAID on expenditure against the APTC revenue earned from FFS activities.

n) The APTC personnel responsible for the FFS activity will provide progress reports to the SMT on the activity at agreed stages. A final report, including a financial acquittal of the activity will be provided to the SMT when the activity has been completed. 
o) Intellectual Property (IP) derived from APTC FFS activities remain the property of APTC through AusAID and the use of any IP needs AusAID’s approval on advice from SMT. 

p) All enrolments and graduations from FFS activities will be recorded in the APTC MIS but separately identified from the core-funded training.

q) SMT may consider and recommend for AusAID approval, FFS requests outside of the above principles taking into consideration clear benefits to be derived by APTC in undertaking the activities. 

Annex O: APTC Stage II Budget Estimates

Note: Significant caveats on the financial data used in this estimate are common to those detailed for the Cost Structure and Cost-Benefit Analysis (Annexes G and H).

[image: image17.png]APTC Stage Il Budget AUD $m |Assumptions (a) (b)
Capital and Establishment
Civil Works (training venues) 3.179 | Potential S| campus, Hospitality School in PNG
Machinery, equipment and vehicles 2.078 | Replacement of Stage | equipment and new course equipment
(training venues)
Other refurbishment (CSS offices) 0.103 | Accommodation design/refurbishment
Transition period 1.493 | Stage Il contractor costs and management fee in transition period May|
Feasibility Studies 0.440 | Course review (health and community services and hospitality);
New course design 0.585 | ELLN Bridging, APTC to work, new course customisation
APTCMIS 0.300 | Establishment of integrated MIS
Sub-total 8.178
Corporate and Student Support
Staff/Related 23.000 | Salaries, per diems and allowances
Staff travel 1.049
Office accommodation and utilities 0.394 | Assumes rented offices in Fiji, Samoa, Vanuatu, PNG and Fiji; with SI
Vehicle rental, maintenance and fuel 0.408 | Office to be expanded in 2012
Office furniture, equipment 0.351
IT services 0.164
Office consumables 0.109
Official functions 0.110 | Graduation ceremonies, official entertainment etc
NCC representation 0.475 | Assumes representative offices in Kiribati, Nauru and Tonga and short-
Staff training/professional development 0.456
Marketing and Publications 0.386
M&E and LMI costs 0.040 | Survey and other non-salary/travel costs
Other operational costs 0.200
Sub-total 27.141
Direct Training Delivery
Teachers and instructors 41.911 | Assumes course profile remains similar to Stage | (ie same distribution
Transport and travel 7.410 | ©f high and low course cost enrolments). Assumes 15% increase in
. L enrolments;
Partnership, rental and hiring charges 5.139 X . . - .
. Costing derived from actual 2009 direct training delivery costs (as per
Other operational costs 11683 | pnnex , Table 8)
Sub-total 66.143
Other Program Activities
Scholarships 16.800 | Stage | budget, minus estimated $1m in savings on full scholarships for
the Solomon Islands, plus Ancillary Awards
Alumni Network 0.118
Advisory Group 0.286 | 6 meetings over Stage Il
APTC to work program 0.480 | One week course for each student
ELLN bridging program 0.633 | For SIS students with weak ELLN skills
Sub-total 18.317
Management Overheads
Contractor 23.956 | Contractor program management costs and profit
AusAID 8.029 | 80% Stage 1 Budget.
Sub-total 31.985
Total 151.764
Notes:

(a) Where budget derived from actual Stage I costs, prices adjusted for inflation and where appropriate an efficiency dividend. Some costs

also adjusted for increased role of CSS

(b) Actual costs will vary dependent on decisions as to the establishment of a Solomon Island campus, the mix of local and expatriate staff,
the continuance of venue partnerships from Stage I, and the extent of the introduction of new courses





Annex P: APTC Stage II Risk Management Matrix

The APTC General Manager/Senior Management Team is responsible for managing all risks indicated below, with exception to those otherwise specified.

The timing of the risks is ongoing from the transition phase until the end of Stage II, unless otherwise indicated.

	Goal
	Major Risk1
	L
	C
	R
	Risk Minimisation/Risk Treatment

	Increased supply of skilled workers in targeted sectors in the Pacific region
	Limited number of people in SIS with work experience/ ELLN skills relevant for entry to APTC Certificate III courses 
	C
	3
	H
	APTC to provide training suitable for new entrants as well as existing workers.

APTC course profile to flexibly meet a variety of training needs.

ELLN bridging or pre-course programs to be provided to SIS applicants with technical skills.

	
	Lack of pipeline of Certificate I/II graduates in Smaller Island States
	B
	3
	H
	AusAID to support complementary bilateral and/or other regional initiatives that build the capacity of national Pacific training institutions to produce qualified graduates.

	
	Serious disruption to APTC training in partner institutions
	C
	3
	H
	Ensure all options are explored before committing to training partner. Partnering only with ethical and committed industry partners (with sound financial background) and demonstrably well governed government training institutions.
Minimise investment in fixed capital with private venture companies. Ensure teaching equipment provided is modular/ moveable.

Implement partner feedback mechanisms/”health check” for early identification and resolution of any difficulties. 

Develop and maintain close and supportive relationships with Pacific governments and industry associations. 

Maintain dialogue with alternative partners for backup training locations.

	
	Minimal uptake of tuition fee paying places (to complement scholarship places)
	B
	3
	H
	APTC to form close partnerships with industry, particularly multinational organisations, to promote employment of APTC graduates.

Tuition fees to be set at market sustainable rate (whilst not competing with local institutions).

Contractor to meet tuition fee income targets from the second year.

	
	APTC contractor does not meet performance standards
	D
	5
	H
	Contractor with relevant TVET and Pacific experience selected through rigorous tender process.

Training to be of AQTF standard and externally audited.

Accountable management structure in place which monitors performance under a Performance Assessment Framework for early identification and resolution of underperformance. 

	Pacific Islander women and men with Australian qualifications realise improved employment opportunities nationally, regionally and internationally in targeted sectors
	APTC graduates do not find or

maintain employment in occupations and at levels for which they have been trained, (particularly in SIS where there is a relatively small formal wage sector)


	B
	4
	H
	Monitoring of graduate employment outcomes to inform annual course profile planning.

Maintain industry and government feedback mechanisms to ensure course profile and content is targeted to meet employer requirements. 

Promote value proposition for employment of APTC graduates.

On-campus employer presentations and interviews. 

Maintain close industry relationships to promote employment of APTC graduates.

Focus on training of existing workers, especially for SIS where employment growth is limited.

APTC to include some APTC-to-work training near the end of course completion.

APTC alumni association to assist graduates to network to identify employment opportunities. 

AusAID to support Pacific government agencies in human resource development planning, employment generation and managing labour mobility issues (e.g. through PACER Plus).

	
	Overseas employment of graduates (in occupations and at levels for which they have been trained) limited by non-APTC related constraints
	B
	4
	H
	Labour market intelligence on short to medium-term regional and international employment opportunities to be collected and reflected where possible in APTC course profile.

Monitoring of graduate employment outcomes to inform annual course profile planning.

APTC to form close partnerships with industry, particularly multinational organisations, to promote employment of APTC graduates.

AusAID to work with other Australian government departments and Pacific governments to accelerate the capacity of Australia and the PICs to take advantage of closer regional labour mobility.

	Increased productivity of individuals and organisations in targeted industries and sectors
	Skills gained during APTC training not utilised in the workplace
	B
	4
	H
	Annual review of APTC training profiles to ensure courses and skills learnt remain relevant to employers, and to actual and projected skill shortages.

APTC to include some APTC-to-work training near the end of course completion.

Maintain close industry relationships to promote skill utilisation of APTC graduates.


	Major Risk
	Potential Impact 
	L
	C
	R
	Risk Minimisation/Treatment

	Marketing, Reputation and Image Risks (KRA 1)

	Lack of understanding of role of the APTC in the Pacific
	APTC seen as elitist and focused on Australian skill requirements not Pacific Island needs.

Decreased PIFC support for APTC’s continued presence in individual countries/region.
	C
	4
	H
	AusAID to maintain stronger bilateral and regional engagement with Pacific/PNG governments to raise awareness and understanding about the APTC.

Annual/biennial APTC Forum involving planning/consultation with individual Pacific governments/industry to commence in Stage II.

AusAID to undertake an investigation early in Stage II into options for continuing the APTC beyond June 2015.

	Unlawful, unprofessional or inappropriate behaviour by APTC staff (including inappropriate involvement in local political or religious affairs)
	Negative publicity and damage to APTC reputation. 
	C
	3
	H
	Effective recruitment of staff including police and referee checks. 
Extensive pre-departure briefing and orientation/induction program to include addressing country-specific cultural behaviour

Staff Code of Conduct, including Child Protection Policy, included and enforced in local and international staff contracts.

In-service reinforcement of policies and practices to educate personnel about Codes of Conduct, including the reporting of suspected misconduct.

Critical incidents to be reported to local AusAID Post and to AusAID Suva.

Implement APTC media and communication plan in the event of adverse publicity.

	Schools unable to attract diverse applicants due to inadequate marketing coverage and/or gender, economic and cultural barriers to TVET participation
	Inadequate number of eligible trainees to meet APTC goal of increased supply of skilled workers.
	D
	3
	M
	APTC Country Strategies to identify gender, economic and cultural barriers to TVET participation.
Annual Marketing Strategy and Recruitment Plan includes strategies for promoting the APTC in under-represented PIFCs and addressing barriers to TVET participation.

	Access for under-represented groups and non campus countries is perceived as inadequate
	Negative publicity for the APTC.

Decreased regional political support for APTC to continue to operate in region.
	C
	3
	H
	APTC Scholarships provide opportunities for candidates from all PIF countries. 

Indicative scholarship allocation by country weighted towards the SIS and approved through Annual Report/Plan process.

Scholarships marketing to target all 14 PIF countries, and the SIS in particular.

AusAID to report on APTC enrolments and scholarships in bilateral and regional forums.

	APTC courses duplicate existing national TVET capacity 
	Decreased Partner Government and local training institution support for APTC continued presence in individual countries.
	D
	3
	M
	Annual planning process, where training profile that does not duplicate local TVET offerings, is agreed in advance with AusAID.

APTC to implement a Tuition Fee Policy that does not compete with local providers. 

	Partnership Risks (KRA 2)

	Reduced PG support for APTC in campus countries
	Difficulty in continued operation. 

Potential for campus location to be closed. 

Impact on training outcomes.
	C
	4
	H
	AusAID to have regular high-level dialogue with PG in campus countries.

APTC to ensure compliance with local laws and regulations.

APTC to record and report on difficulties experienced with PGs and local institutions. 

	Agreements with partner training institutions not managed effectively


	Disruption/cancellation of partnership contract resulting in APTC not meeting its training targets and damage to APTC reputation. 

Financial/equipment loss.
	D
	4
	H
	Ensure that training partners are fully aware of the program and their responsibilities at time of agreement.

Close liaison between APTC and training partners prior to and during agreement.

Specific and monitorable agreements, and procedures for reviewing their functioning, are in place by commencement/extension of new partnership.

	Reduced training partner commitment, motivation or capacity (including business failure) to be an effective partner 


	Disruption/cancellation of partnership contract resulting in APTC not meeting its training targets and damage to APTC reputation. 

Delays in student course completion/intakes while alternative training providers identified
	C
	3
	H
	Ensure all options are explored before committing to training partner. Partnering only with ethical and committed industry partners and demonstrably well governed government training institutions, including checks for financial stability.

Minimise investment in fixed capital with private venture companies. Ensure teaching equipment provided is modular/ moveable.

Implement partner feedback mechanisms/”health check” for early identification and resolution of any difficulties. Encourage industry partners to inform the project of their business environment and risks through close liaison and ensuring the confidentiality of commercial information. 
Maintain dialogue with alternative partners for backup training locations.

	Local training institutions resent APTC presence (within institution or with industry training partner)
	Diminished local support of the APTC 
	C
	3
	H
	APTC courses and tuition fees do not compete with local providers.

Centre for Professional Development to enable local institutions to benefit from APTC presence.

APTC to formalise and record support to local institutions.
Local trainers to be involved in APTC training (e.g. as tutors) and use of facilities, wherever possible.

AusAID to provide other support to local institutions/trainers through the bilateral program (e.g. through the TAE4 course).

	Lack of APTC engagement with private sector
	Employees not supported to attend APTC (lack of support for tuition fees, work release, or supervised work attachments). 


Employers do not value or utilise APTC graduate skills.


Revenue generation reduced.

Reduced employment and productivity outcomes.
	C
	4
	H
	Formal or informal agreements are documented and working.

Communication Plan to give guidance regarding communication with private sector.

Develop and maintain close and supportive relationships with individual employers and industry bodies through formal (industry advisory groups, periodic labour market surveys) and informal mechanisms (site visits, participation in the activities of employer /industry associations).

Establish strong partnerships and clearly address release and student payment issues.

Employer satisfaction surveys to be regularly conducted/evaluated and any necessary adjustments to training delivery made.

	Lack of coordination of donor input to TVET sector 
	Duplication or lack of complementarity of TVET support in region.
	D
	3
	M
	AusAID TVET Strategy to ensure harmonisation of donor inputs.

APTC Communication plan to include joint AusAID/APTC meetings with other regional donors to increase other donor understanding and support for the APTC. 

	Teaching and Learning Risks (KRA 3)

	Limited or poor quality training facilities provided by partner industry or institutions
	Unsuitable training environment evolves over time.

Staff and students placed at risk.
	C
	3
	H
	Clear contractual MOU and Service Level Agreement with partner training institution as to set-up/ongoing resources to be provided by APTC/partner. 
Regular Occupational Health and Safety Audits to be undertaken.
Regular monitoring of staff and student satisfaction with training facilities/equipment. 

	Equipment/ infrastructure

not delivered and installed in time
	Delay to course start.

Reduction in training quality.
	C
	3
	H
	Establish realistic lead times through Annual Training Profile planning to accommodate resource purchase, shipping and installation.

Back-up plans for loss of training time to be in place. Training designed to fit theory up-front so that it is mobile in the early stages.

	Schools do not fully conform to AQTF standards in course delivery or in assessment of competency standards
	Training outcomes compromised and graduates do not have adequate skills to meet industry requirements.

Employers are dissatisfied with APTC training, resulting in loss of potential fee-paying enrolments.
Reputation of APTC and Australian training diminished with students and employers.
	C
	4
	H
	Competitive tender process to engage qualified and experienced training providers.

Contracts are clearly defined regarding the application of AQTF standards and penalties/recourse measures, including cancellation for poor performance.

Performance monitoring of delivery quality through formal student and employer feedback.

AusAID to commission Independent Audits of the RTOs performance against the AQTF 2007 Essential Standards for Registration by State Training Authorities.

	Insufficient workplace attachments available


	Risk to reputation of some APTC courses where training is only institution based (particularly for non-campus country students)

	B
	3
	H
	APTC to foster positive relations with employers so that they provide workplace assessments for local and overseas students.
APTC to work with AusAID and partner governments to resolve any legal, regulation and visa issues for work placements by overseas students.
The Annual Training Profile to detail the arrangements made for adequate work placements for any new courses to be established.

Where insufficient work placements are available, the APTC will need to modify the training venue and course delivery to simulate workplace environments and maximise the use of industry practitioners in delivery and assessment. 

	Delivery modes unsuitable to learning styles
	Disgruntled students and poor skill learning outcomes.

Low completion rates. 

Reduced demand for APTC.
	D
	3
	M
	Design of courses to consider cultural influences, responsiveness and flexibility. 

AusAID to engage contractor experienced in delivery to Pacific Islanders.

	Graduates not ready for the study-to-work transition


	Reduced employment outcomes.

Employer dissatisfaction.
	C
	3
	H
	APTC to include APTC-to-work training near the end of course completion.

	APTC receive poor advice and information on industry training needs in the region and internationally


	APTC courses lack relevance to needs of industry sectors being targeted.

APTC does not respond to emerging PIF labour requirements leading to under/over supply.


	C
	4
	H
	APTC to develop and maintain a plan for formally collecting and analysis of labour market intelligence including with employers, industry associations, labour market research and AG meetings. 

APTC to have active engagement with private/NGO sectors regarding their training needs.

Independent analysis of industry trends by APTC to identify unrealistic market expectations.

	New courses in training profile that should be undertaken through FFS activities
	Potential criticism that APTC is subsidising private company training.

APTC resources diverted from core profile training.
	D
	3
	M
	AusAID to approve Annual Training Profile including justification for conducting new courses. 

Ongoing monitoring of implementation of the Fee for Service policy.

Reporting to AusAID on Fee for Service activities.

	Majority of courses continue to be for trade apprenticeships
	Lack of APTC training opportunities for female students.
	C
	3
	H
	Monitoring of APTC Gender Access and Equality Policy.

Annual Training Profile to include details as to expected gender balance of each course.

Targets set for female participation across APTC courses.

	Pressure to broaden the scope of APTC to include other than Cert III, IV and Diploma courses
	Loss of clear focus for the APTC and reduced progress to achievement of its goals.

Local institutions no longer supportive of an APTC which is competing with its activities.

Bilateral institution strengthening projects compromised.
	C
	4
	H
	AusAID to develop and communicate a TVET Strategy clearly stating the role of the APTC in TVET in the Pacific region.


	Pressure on APTC to place more courses in PNG (within Stage I budget)
	Decrease in access to APTC by other countries (as visa access to PNG is constrained).

Perception by other countries that APTC is supporting those most able to afford to pay for their own training.
	B
	4
	H
	APTC to be targeted to increase fee-paying students in PNG.

AusAID to ensure though annual planning process that there is no decrease in scholarships available to other countries.

AusAID to work with PNG government to improve visa access by students from other Pacific countries to study in PNG.

	Pressure for PNG APTC to operate separately from the rest of the APTC
	Loss of opportunity for regionally integrated approach to TVET training and labour mobility.

Loss of access to PNG training centres for other Pacific Islanders
	C
	3
	H
	AusAID to adopt a unified Pacific regional and PNG approach to discussions with PNG stakeholders about APTC. 
AusAID to pursue accelerated efforts to support TVET development in PNG. 


	Emigration of APTC graduates exceeds the training of replacements
	National skills pools in PICs less than when the APTC started. 
	D
	3
	M
	APTC to hold regular consultations with PICs to monitor impact of overseas migration of APTC graduates.

AusAID to support PIC government agencies in managing human resource development planning, employment generation and labour mobility issues. 

	Students and Scholarships Management Risks (KRA 4)

	Pressure to provide access to APTC for school leavers and others (particularly from the SIS) that do not have the technical, motivational or other required skills to successfully complete the course
	Decreased completion rates and graduate number targets not achieved.

Inadequate workplace skills demonstrated. 

Compromised employability.

Training outcomes and eventual program effectiveness are compromised.
	B
	4
	H
	APTC objectives clearly communicated to stakeholders and broader community.

Selection criteria for entrance to APTC courses explicitly detail minimum entrance criteria.

Quality assured technical assessment testing of applicants. Test results recorded on APTC student database.

Appropriate and regular monitoring to identify students in need of additional support. 

Provision of student mentoring and counselling.

Accept additional students into courses in anticipation of student withdrawals.

	Inadequate English language, literacy and numeracy (ELLN) ability of target applicants (especially from SIS)
	Enrolment targets from SIS not able to be met.
	C
	3
	H
	Quality assured ELLN testing of applicants. Test results recorded on APTC student database.

Bridging programs to be commenced in SIS during Stage II.

On arrival/concurrent ELLN support during training.

	Low number of applications from quality candidates
	APTC courses may not be run at full capacity with subsequent reduced program cost-effectiveness and impact.
	C
	3
	H
	Annual Plan to include review of targeted promotional strategies. 

Annual review and revision of indicative country allocations.

Reserve lists of local applicants to be maintained to enable shortfalls to be managed.

	Scholarships awarded to students with easiest access and greater financial means
	Development goals of providing access to the disadvantaged not achieved.
	C
	3
	H
	Scholarship allocation policy and selection procedures maintained and enforced.

Separation of responsibilities between scholarship selection and applicant recruitment/assessment.

Six monthly reporting to AusAID on scholarship allocation. 

	Scholarship selection procedures are seen as not transparent or efficient 
	Lack of confidence in the APTC as an equal opportunity training provider.


	C
	3
	M
	Application and scholarship scheme provide clear selection and admission procedures with opportunity for complaints resolution. 

Procedures put in place for reporting and dealing with approaches for preferential selection. 

Staff Code of Conduct to include penalties for corrupt admission/ scholarship selection practices.

	Inadequate student learning and pastoral support 
	Low completion rates.

Lack of student and employer satisfaction. 

Damage to APTC image.
	D
	3
	M
	Learning and student support funded as an integral part of program delivery.

Recruitment of culturally aware staff, supported with country-specific cultural orientation. 

Provision of student services and welfare for APTC students including access to specialist counselling services. 

RTOs to provide clear guidelines to staff on duty of care requirements as part of pre departure briefing and in regular meetings.

Use of student feedback (surveys and focus groups) to identify performance issues.

	Failure in duty of care relating to the safety and welfare of the APTC students (including risks to children)
	Illness, injury or death of staff or students.

Disruption to program delivery.

Damage to APTC reputation.


	C
	3
	H
	Ensure RTOs have preventative maintenance plans in place with local training partners.

OH&S built into management responsibility in APTC and partner training institutions. 

Student and Staff Codes of Conduct and Child Protection policy implemented.

Emergency procedures established and monitored. 

	Socio-cultural and economic factors constrain female participation


	AusAID and APTC development goals of gender equity not achieved.
	B
	3
	H
	Local networks identified and engaged to identify women and other marginalised students. 

APTC Gender Equality Strategy implemented to overcome cultural and gender barriers.

Gender-specific courses run as required. 

	Students engage in inappropriate behaviour (including inappropriate or dangerous sexual behaviour) 
	Compromises student safety and APTC reputation.
	C
	3
	H
	Implement APTC Student Code of Conduct (with appropriate disciplinary procedures), with briefing during orientation and constantly reinforced.

Non-compliance with Code of Conduct issues are recorded by the school and addressed with the student.

Number and type of breaches documented and reported to SMT.

	Planning, Management and Governance Risks (KRA 5)

	APTC General Manager and Senior Management Team fails to provide coordinated overall governance leadership and accountability to the APTC


	Lack of effective delivery and efficient use of resources reduce achievement of project goals and outcomes.
	D
	4
	M
	A Governance and Structure Manual and supporting material are prepared and GM tasked with ensuring that management and governance arrangements are in place in compliance with AusAID and best practice requirements. 

Effective monthly SMT meetings and timely communications prior to and post meetings.

Use of Annual Plans and Lessons Learned documentation as basis for planning and monitoring.

Use of the PAF on systematic basis to assess APTC activities, outputs and risks.

	APTC policies and procedures do not comply with: AusAID requirements; AQTF 2007 standards; Australian legislation, regulations and statutory obligations; and good practice principles
	De-registration of RTO.

Damage to APTC and AusAID reputation.


	D
	4
	H
	APTC policies and procedures are developed, implemented and addressed. 

Independent audit of APTC policies to ensure compliance with AusAID and AQTF standards.



	Breach of PIFC legislation, regulations and statutory obligations laws (including with respect to registration, employment etc) 
	Potential legal threat to APTC staff.

Damage to APTC reputation. 

Diversion to management efforts.
	C
	4
	H
	Accurate identification of contractual, accreditation and legislative requirements relevant to each country. 

Development of APTC employment terms and conditions in line with local labour requirements. 

Training of APTC staff in local legal requirements.

	Human Resource Management
	
	
	
	

	Lack of clarity of respective roles within the APTC
	Inadequate communication between different organisations working under the one contract with AusAID. 

Duplication or gaps in responsibilities.

Reduced APTC effectiveness.
	C
	3
	H
	RFT selection criteria to include statement as to how effective communication and work practices will be maintained.

Responsibilities of all work units and staff to be clearly defined, documented and functional across all areas by Contractor as per of their tender response. 
Ongoing monitoring of relationships and performance of all parties. 

Regular review of ToRs of all staff and adjustment as needed to meet College needs.

	Staff lack appropriate skills and competencies for efficient and effective operations within the Pacific country environment 
	Failure to deliver training outcomes. 

Low productivity. High staff turnover. 

Negative student and employer

perceptions of APTC/Australian training institutions.
	C
	4
	H
	RFT selection criteria to include previous experience operating training institution abroad or in a multi-cultural environment. 

Recruitment of staff with appropriate training skills and suitability for working in a culturally diverse environment.

In-country orientation programs and on-going cultural awareness training delivered by local experts.

Implementation of performance management function. 

	Lack of suitable local personnel hinders localisation 


	Higher cost (travel, accommodation, allowances etc).of positions filled by overseas staff (travel, accommodation etc).

Reduced opportunity for capacity development of local staff.

Perception that the APTC is a solely Australian institution and not integrated to the Pacific environment.
	C
	3
	H
	Recruitment strategy to identify local personnel that are expert in their field. 

Identify potential trainers during courses.

Offer competitive salaries and conditions.

Identify staff professional development needs and ensure appropriate training support (e.g. through TAE4) for potential trainers.


	Financial and Economic Management Risks (KRA 6)
	
	
	
	

	AusAID unable to provide guarantee of continuity of funding for an APTC Stage III
	APTC closed before long-term outcomes and impact achieved.
	C
	4
	H
	APTC design has long term vision over 14 years.

APTC performance assessment to collect and analyse data on outcomes and impact justifying continued investment.

	Relative high unit cost of some delivery models
	Reduction in graduate outcomes for available budget.

Decreased sustainability of the College.
	B
	3
	H
	Regular review of delivery models to identify lower-cost options. 

Assessment of the workplace component of the APTC training program, especially where it involves APTC staff travelling to home islands to assess small numbers of students.

	High cost of attracting and assessing applicants rural and remote locations and from non-campus countries
	Insufficient funding to achieve target graduate output.

Potential lack of equitable access for these groups.
	B
	3
	H
	Develop low cost, high penetration marketing outreach strategies in small island states and remote areas

Marketing and admissions strategies (course profiles) strive for an appropriate balance between local and overseas students.

	Ineffective financial management systems 
	Lack of accurate and timely data on operations as per contractual obligations.

Project expenditure not in line with budget.
	C
	4
	H
	Single APTC FMIS.

Recruitment of experienced financial personnel. Financial policies and procedures in place. Regular staff training.

Effective budget monitoring and review processes in place.

Exchange rate exposure managed in accordance with AusAID contract.

	Theft, fraud, misappropriation of equipment or corruption and failure to comply with Commonwealth fraud control guidelines


	Financial loss impacting on APTC to deliver future programs. 

Delay in running training whilst replacement equipment sourced.

Reputation damage for APTC/AusAID.
	D
	5
	H
	Ensure financial procedures and monitoring are in place. 

Staff trained in compliance requirements. Zero tolerance with fraud and corruption clause in staff contracts. 

Ongoing reinforcement of the importance of vigilance against fraud and theft

Regular audits conducted by both internal and external providers 

Reporting to AusAID on any cases of fraud and corruption

	APTC does not meet its fee-paying student target 


	Continued dependence on AusAID funds over time. 

Insufficient funds available for APTC expansion. 

College may not be sustainable.


	C
	3
	H
	College Development Strategy including the generation of tuition fee income developed and endorsed by SMT

Training provided for all APTC staff involved in marketing activities.

APTC Tuition Fee Policy enable setting of tuition fees at a realistic market rate.

Annual Training Profile indicates expected proportion of tuition fee course places. Scholarships not awarded to applicants who have access to self or employer funded training.

Tuition fee income (and places) reported in Six-Month and Annual Plans.

	Fee for Service activities divert APTC from delivering its core business.
	Reduced graduate output and quality.

Poor delivery outcomes from fee for service activity damages APTC reputation.
	C
	3
	H
	Ongoing monitoring of implementation of Fee for Service policy.

AusAID advance approval required for large fee for service activities.

Fee for service activities and income reported in Six-Month and Annual Plans.

	Pressure to put expand APTC campuses to new locations/countries 
	Diversion of APTC management activities from core business.

Potential non-sustainable increase in delivery costs.
	B
	4
	H
	Independent Feasibility Study including cost-benefit analysis to be undertaken before new site commissioned.

	Lack of interest by other donors/stakeholders in funding or providing scholarships to the APTC 
	Constraint to APTC expansion.

Reduced sustainability of the APTC.
	B
	2
	M
	APTC Communication plan to include joint AusAID/APTC meetings with other regional donors to increase their understanding and support for the APTC. 

	Political and Natural Changes
	
	
	
	

	Changed political and deteriorating security situation in campus countries.

Natural disaster (earthquakes, cyclones etc)/health pandemic.


	Health and well-being risk to APTC staff and students.

Suspension of classes affecting achievement of training outputs and outcomes.

Potential loss of income from fee paying students. 

Disruption to scholarship scheme. 
	C
	4
	H
	Security and disaster preparedness is given a high priority in pre-departure briefings. 

Contractor to closely monitor events on an ongoing basis and ensure security plan and contingency/action plans (evacuation policy) in place for staff and students.

Integrated risk management approach adopted by APTC to regularly review and adjust program delivery, policy and procedures in response to changed circumstances and lessons learned. 

Courses run in multiple locations to reduce reliance on single campus.

AusAID to advise Contractor of security updates.

	Information and Communication 
	
	
	
	 

	ICT systems do not meet performance requirements 


	Viruses and/or computer faults destroy source materials and information systems.

Lack of ability to verify student participation, assessment, module completion resulting in interference to program.

Inefficient and unreliable communication within the APTC and with other partners.
	D
	3
	H
	APTC to develop and maintain a Strategic IT plan, and appropriately resource and train staff in ICT and MIS systems.

IT support mechanisms established both locally and remotely to enable reliable, high speed access to database, communication and other systems.

Contingency plans in place for business critical systems, including remote storage of data to ensure effective retrieval of data.

	APTC unable to report on student, staff, financial and asset data across the whole College 


	Inefficient program management.

Inaccurate reporting, weak accountability and unreliable M&E.
	C
	3
	H
	Contractor to establish integrated HR, asset and financial management systems across the College.

	Lack of integration between APTC student and scholarship MIS and RTO data requirements 
	Program management delays.

Duplication of data entry. 

Inaccurate data, reporting and unreliable M&E.
	C
	3
	H
	Prior to Stage II, AusAID to commission design of the functional requirements for a robust consolidated student and scholarship MIS that produces accurate and rapid reports required for program management, accountability and M&E.

During RFT process, Contractor to indicate which MIS will be used by the College that effectively and efficiently integrates all APTC MIS requirements with RTO TAFE data requirements.

Contractor to establish integrated student and scholarship MIS during transition phase.

	Unreliable and incomplete APTC MIS data (including on student applications, enrolments and completion)
	Unreliable data on which to base training/scholarship management.

Inaccurate and incomplete reporting and M&E.
	C
	3
	H
	Contractor to provide for sufficient data entry staff and regular training. 

CSS to include data quality officer.

Security provisions in place to safeguard confidential student data. 

	Environmental 
	 
	 
	 
	 

	Adverse affect on environment due to APTC operations
	Negative environmental impact of excess staff travel. 

Perceptions by PIFC stakeholders of waste and inefficiency.


	C
	3
	H
	APTC to develop/update an Environmental Management Plan for all APTC offices and training locations. 

Staff in campus countries to have sufficient seniority to reduce the need for travel from the Fiji CSS].

Use of web and video-conferencing where possible.


1Risk Estimate Matrix

	 
	CONSEQUENCES

	 LIKELIHOOD
	Insignificant (1)
	Minor (2) 
	Moderate (3)
	Major (4) 
	Severe (5)

	A (Almost Certain)
	M
	H
	H
	VH
	VH

	B (Likely)
	M
	M
	H
	H
	VH

	C (Possible)
	L
	M
	H
	H
	H

	D (Unlikely)
	L
	L
	M
	M
	H

	E (Rare)
	L
	L
	M
	M
	H


	VH: very high risk; immediate action required

	H: high risk; senior management attention needed

	M: Moderate risk; management responsibility must be specified

	L: low risk; manage by routine procedure


Annex Q: Draft Terms of Reference – Feasibility Study for delivering APTC training in the Solomon Islands

1. Background

The Australia-Pacific Technical College (APTC) was established in July 2007, following the then Prime Minister’s announcement at the 2006 Pacific Islands Forum, with an initial allocation of AUD$149.5 million (2007/08 to 2010/11). The APTC provides training at Australian standards in order to:

i. increase the supply of skilled workers in targeted sectors in the Pacific region; 

ii. help Pacific Islander women and men with Australian qualifications realise improved employment opportunities nationally, regionally and internationally in targeted sectors; and 

iii. increase productivity of individuals and organisations in targeted industries and sectors.

The APTC delivers Australian Certificate III and IV skill training in five industry sectors: automotive; manufacturing; construction and electrical; tourism and hospitality; and health and community services. During Stage I, training was delivered in the four campus countries of Samoa, Fiji, Vanuatu and PNG. APTC training delivery in these countries is to continue in Stage II.
The Concept Paper for the APTC Stage II design noted that flexibility exists for the APTC to add or remove courses, campuses and training partners in response to changing regional skills demands. It also noted the demand for APTC training from the Solomon Islands (SI), the third most populous country of the Pacific, after PNG and Fiji. With a population of over 500,000, the size of the formal economy, while small, has grown and firm productivity is important to its economic growth. A study by the World Bank in 2007 found that 53 percent of larger, formal-sector firms in the Solomon Islands were understaffed
. Demand for APTC training from private sector employers is strong, as is demand for skills upgrading of teachers and trainers from the network of rural training centres that serve rural communities and outlying provinces. At the time of the 2009 Mid-Term Review, around 100 different employers in the Solomon Islands had been served by the APTC, 71 percent from the private sector and 4 percent from the education and training industry. Solomon Islanders comprised 11 percent of all enrolments and 16 percent of all scholarships awarded. Solomon Islander applicants ranked highly compared to other countries on technical skill and English language and numeracy assessments. 
Given this expressed student demand, the Mid Term Review indicated that a feasibility study for establishing a training venue in the Solomon Islands (SI) should be undertaken. Although there is strong student demand and indicative government support for an APTC campus, expansion (and contraction) of the APTC schools, campuses and courses should be based on industry demand and economic drivers, nationally and internationally. This need and demand, however, is difficult to assess, as current training gaps are likely to reflect a progressive decline in effectiveness of the Solomon Islands College of Higher Education (SICHE), and economic growth from the presence of RAMSI and a large expatriate community. The economy is only now slowly recovering from a period of major disruption, although there may be some demand from the trades area and in the formal economic sector (the Gold Ridge mine is a possibility) and in projected donor infrastructure investments. As there is little reliable or up-to-date statistical information or labour market analysis available for the Solomon Islands, this would need to be collected and analysed in the feasibility study.
Further investigation of possible partnership arrangements and delivery models – industry and institutional - in the Solomon Islands is required. Solomon Islands has only one tertiary institution, SICHE, which has six established Schools (Industrial Development, Education, Marine and Fisheries Studies, Finance and Administration, Nursing and Natural Resources) and a new School of Tourism and Hospitality. SICHE has been neglected over many years, and would require substantial investment to rehabilitate. Support for revitalisation of SICHE is being actively considered by the SI Government, AusAID and other donor partners. Establishment of a training venue at SICHE would need to take account of complementary development activities there. Opportunities for industry-based training in the Solomon Islands are limited, so arrangements with industry partners for training venues or work placements would need to be carefully established and maintained.
2. Objective

To determine the feasibility including cost-effectiveness of conducting APTC courses in the Solomon Islands. In particular, this will require examination of viability of options in detail, including identification of training venues, local industry and institution partners, the range of AQF courses to be offered, expected student numbers and indicative costs and timeframe.
3. Scope

The Feasibility Study will assess:

· Future levels of employment growth in areas within the scope of the APTC delivery and demand for skilled workers at AQF Certificate III and IV;

· Future levels of demand for workforce retraining\upskilling within the scope of delivery of the APTC and demand for skilled workers at AQF III and IV;

· The cost effectiveness of providing APTC training in the Solomon Islands, relative to delivery under current training/scholarship models

· The potential for partnerships with SICHE, having regard to any bilateral programs that will improve the facilities and staff capacity at the institution;
· Opportunities for partnerships with local employers; and
· Models for flexible and work-based delivery, including the capacity to adjust the level and pattern of delivery in response to changing demand.

Based on the above, the study will develop an indicative profile for delivery by the APTC in the Solomon Islands or through delivery in other countries and undertake a cost benefit comparison of delivery under either model. 
The study will be based on surveys and interviews with employers, government agencies and instrumentalities, and aid agencies. It will include an analysis of facilities and equipment at SICHE and in local enterprises and assess options for co-location with SICHE, for a stand-alone facility or for workplace partnerships and delivery models employed in other locations by the APTC.

4. Issues to be Addressed
Rationale and Support

· confirm and fully develop the rationale for delivery of APTC courses in the SI, including confirmation of partner government, industry and other stakeholder willingness to support the development of training venues. 
Courses to be Offered

· determine the initial courses/qualifications to be offered by the College in each of the Schools, including requirements for the award of qualifications;

· advise on quality assurance issues and conformance with the requirements of the

Australian Quality Training Framework (AQTF) including assuring quality of delivery and assuring consistency in assessment;

· identify venue(s) for delivery of training in industry, private sector providers and/or government institutions (such as the Solomon Islands College of Higher Education), considering venues outside of the SI capital, as appropriate;

· advise on appropriate partnership arrangements for APTC training and structured workplace attachments consistent with Australian requirements;

· advise on willingness of the partner to adopt gender equality practices; and
· consider delivery models including alternative modes of delivery (such as flexible delivery, outreach and distance learning).

Student Demand/Access

· establish course demand in the SI over APTC Stage II and likely demand into any Stage III;

· determine the student segments to be targeted (new entrants/existing workers), entry requirements and proposed intake numbers by course;

· consider issues of access (and accommodation) for students from remote locations in SI

· advise on access to APTC training in the SI by people from different countries (including accommodation and visa issues);

· undertake a gender analysis of demand for APTC training in the SI and how participation by females can be maximised;

· advise on the criteria for the award of full/partial scholarships and the appropriate rate of allowance payments; and
· consider bridging requirements including numeracy and literacy programs.
Costing/resourcing requirements

· prepare cost estimates to establish the training venue(s) to AQTF standards and annual operating costs (factoring in financial support from any other sources); 

· determine the cost benefit of delivering training in the SI compared to an existing overseas campus;

· advise on appropriate tuition fee structures to reflect costs and the local market;

· determine the market potential for fee-paying intake (by privately-funded, employer sponsored, or donor-funded students);

· identify other options for cost recovery including access to local training levies, or fee-for- service business;

· assess staffing requirements, including the need (and duration) for expatriate teachers and assessors, the availability of qualified local teachers and management/administrative staff, teacher training and professional development, induction and mentoring requirements, and other essential capacity development requirements;

· advise the most appropriate organisational structure of an APTC presence in SI;

· assess equipment and infrastructure needs, including refurbishment and upgrading of training facilities;

· assess the impact of establishing a campus in the SI on the viability of APTC courses/campuses in other countries; 

· assess the impact on resourcing requirements of APTC Corporate and Student Services;

· determine the expected commencement date and identify any required preparatory activities, including consideration of a phased approach to course commencement;

· assess communications network and technology requirements for administrative and teaching purposes; and
· assess the likelihood of SI Government, industry, AusAID bilateral program and other donor contributions to establish and operate training venues in the SI.

Other

· consider apprenticeship and trade testing systems, licensing and other legislative and regulatory issues relevant to APTC operations in the Solomon Islands;

· consider how the APTC can support SI TVET institutions and plans for development of the sector by the SI Government and donor partners, including AusAID;

· advise on ways to promote SI Government, industry and other stakeholder support for the APTC;

· develop strategies for ensuring a clear Australian identity and profile for the College;

· recommend any supplementary programs to increase graduate success and employment; improve student recruitment and student services;

· undertake a full risk assessment for establishing a campus in the SI and recommended strategies to minimise these;

· advise on any changes that would be required to the APTC risk management plan, Performance Assessment Framework or other APTC policies and procedures;

· advise on any environmental impact issues that may require a full environmental impact assessment or management plan; 

· make recommendations with respect to a strategy for achievable and sustainable outcomes for an APTC training centre in SI;

· advise on any other cross-cutting and sectoral issues and requirements; and
· advise on any indirect benefits/risks from establishing a training venue(s) in the SI.

5. Study Team

The Team will consist of up to four team members, of which at least one member will be nominated by the Solomon Islands Government. The Team, to include a Team Leader, Labour Market Analyst and Gender Specialist, is expected to have combined skills and experience in the following areas:
· demonstrated expertise and experience in Australian TVET, the TVET sector in developing countries and more broadly in workforce development; 

· expertise and experience in capacity development relevant to the Solomon Islands TVET context;
· proven expertise in strategic design and analysis;
· proven expertise in gender analysis; 

· proven expertise in labour market analysis;
· expertise and experience in preparing costing budgets; and
· extensive experience working in the Solomon Islands, including knowledge of the formal economic sector and whole of government systems and processes.
Under the overall direction of the Team Leader, all members are expected to work collaboratively as a team to produce a coherent, high quality and cost-effective feasibility study. The team will have:

· a high standard of report writing skills;
· ability to work collaboratively in a team;
· ability to liaise and communicate effectively with government officials and key stakeholders including industry stakeholders; and
· ability to work collaboratively in a team.
6. Duration and Phasing 

The Feasibility Study will be undertaken between July to September 2011, or as otherwise agreed with AusAID. It is expected to take up to a maximum of 25 days including in-country consultations and a field visit to the Solomon Islands as follows:
	Task
	Inputs (up to)

	-Background reading and data collection

- Preparation of detailed work program (feasibility study mission plan) 
	3 days

	Travel to Fiji and the Solomon Islands (as required)
	4 days

	Consultation with AusAID Suva and APTC Corporate and Student Services in Fiji 
	1 day

	In-country mission:

- Data collection

- Consultations with institution/industry/SI Government stakeholders

- Presentation of Aide Memoire 
	9 days

	Write-up and submission of the draft Feasibility Study report
	5 days (Team Leader); 3 days (other team members)

	Appraisal Peer Review
	3 hours (Team Leader)

	Finalise and submit final Feasibility Study report
	2 days (Team Leader); 1 day (other team members)


7. Reporting Requirements
The following reports are to be provided by the agreed dates:

a. Output 1: Feasibility Study Plan to be confirmed with all team members, finalised and approved by AusAID prior to the in-country mission

b. Output 2: Aide Memoire (maximum 4 pages). The Aide Memoire should give a brief and clear summary of the process and include preliminary conclusions. It should be presented to AusAID and key project stakeholders prior to the study team’s departure from the Solomon Islands.

c. Output 3: Draft Feasibility Study Report (maximum of 40 pages plus annexes) which should be submitted to AusAID by the agreed date.

d. Output 4: Final Feasibility Study Report (maximum of 40 pages plus annexes) which will be finalised in accordance with AusAID direction following a Peer Review process. The final document is to be provided to AusAID within 5 days of receipt of comments. 
Appendix A. Key Reference Documents

Policy Documents and Guidelines
· Pacific Partnerships for Development: Solomon Islands. 
· AusAID website information on Pacific Partnerships for Development (http://www.ausaid.gov.au/country/partnership.cfm)

· Draft Pacific Education and Training Agenda 
· AusAID Policy: Gender equality in Australia’s aid program – why and how

· AusAID Policy: Development for All: Towards a disability-inclusive Australian aid program 2009-2014 

· AusAID Guideline ‘Integrating Gender Equality into Aid Activity Design’

· AusAID Guideline ‘Integrating Environment into Aid Activity Design’

· AusAID Child Protection Policy and Manual

· Environmental Management Guide for Australia’s Aid Program

· AusAID’s guidance note on activity design
APTC Documents

· APTC Mid-Term Review, June 2009

· APTC Stage II Concept Note, February 2010

· Design Document : APTC Stage II, September 2010

· APTC Six Month/Annual Reports to AusAID

· APTC Policies
· APTC Student database reports (for statistics on SI applications and enrolments)

Background Documents 

Asian Development Bank – Commonwealth Secretariat (2005) Toward a New Pacific Regionalism, an Asian Development Bank–Commonwealth Secretariat Joint Report to the Pacific Islands Forum Secretariat, http://www.adb.org/Documents/Reports/Pacific-Regionalism/default.asp.
Asian Development Bank (2007). Skilling the Pacific.

Pacific Islands Forum (2009) Pacific Education Development Framework (PEDF) 2009-2015.

Annex R:
APTC Stage III Scoping Study Considerations
While the APTC provides specialised high-level training regionally, it is not a regional provider, and currently does not have shared governance, ownership or financing with other government or industry partners. 

The MTR concluded that in order for the APTC to be sustainable in the longer-term, it will need to graduate from a wholly Australian-owned training provider to a regional training institution, which is jointly owned by Australia and other interested Pacific Island countries, donors and possibly other stakeholders. To facilitate any such transition, the Stage II design supports the proposed longer-term transition to a regional institution. However, due to the size and scope of the consultations required to consider options for the future of the APTC beyond 2015, AusAID decided that a scoping study should not be part of the Stage II design, but would be undertaken by AusAID as a separate exercise during 2011.

Possible Options

The MTR identified two realistic options for the APTC for the long-term, although indicated that others may arise in coming years as discussions about the long-term future of the APTC continues, regionalism evolves and labour mobility patterns in the Pacific are more clearly defined.  

Option 1 is to continue beyond 2015 with the arrangements decided for 2011-2015, with the APTC continuing to be a wholly-owned Australian aid program. 

Option 2 is to establish the APTC as a legal entity.  As a legal entity, the APTC would have a business structure that allows it to operate with autonomy within its rules of incorporation, allowing it to respond to the continuously changing needs of the labour markets of the Pacific and to enter into long-term partnerships. Two variants of Option 2 were considered.
Option 2A would involve the APTC (possibly by another name) becoming a “regional club” of interested PIF countries which is self-sustaining because the benefits of membership exceed the costs of full national provision of internationally recognised vocational training services at Australian Certificate III level and above. 

Option 2B would be to establish the APTC as a company with a Constitution (Memorandum and Articles) that binds each member to all others, provides for legal relationships between two or more members, allows for rules at a number of levels, and provides for decision-making structures. It also has business and presentational advantages.  

Issues to be considered 

The Stage III Scoping Study would, through extensive and staged consultation with Australian and Pacific governments, industry partners and other donors, and in the context of APTC progress and achievements to date, determine whether there is strong support for continuance of the APTC in some form.  If there is support, the study would consider and make recommendations as to the ownership, funding, legal and governance structures and scope of the APTC beyond 2015. If there is no support, the study would make recommendations for an exit strategy at the end of Stage II.

In examining each of the options proposed by the MTR, and any other emerging options/models raised during initial consultations, the following issues should be considered:

· the relevance to broader Australian and Pacific government skills development policies and agendas, including support for the Pacific concept of regionalism where countries work together for their joint and individual benefit;

· the extent to which the institution would contribute to integrated TVET skills development programs nationally and across the region;

· the flexibility of the institution to operate with a higher degree of autonomy to respond to the continuously changing needs of the labour markets of the Pacific and to enter into long-term partnerships;

· its likely ownership/membership and shareholder arrangements;

· ongoing management of the relationship with and expectations of the Pacific education and training community;

· other donor support and coordination;

· the impact on equity of access, including from the smaller island states;

· whether a different model would be more relevant for PNG; 

· changes that would be required to APTC objectives;

· governance and management structures;

· legal entity and any legislative and regulatory issues;

· funding structures where the benefits and costs can be assigned equitably among participating countries; 

· impact on the cost-effectiveness of operating the institution, including ensuring the costs of working cooperatively (including for new bureaucracies and travel costs etc) do not overwhelm the benefits;

· its fiscal sustainability (from AusAID, other donors, private industry, Pacific Island governments, fee-paying students and fee for service activities);

· the optimal size of the institution (considering venues, partners and students);

· the level and range of qualifications awarded (and their relation to national and regional qualification frameworks);

· the extent of Australian branding of the institution (including naming, qualifications awarded and staffing);

· the continuance of strong relationships with industry to enable demand-driven training to be provided;

· lessons learnt from establishment and management of similarly structured organisations in the region (or elsewhere); and

· any other assumptions, constraints or risks.

Annex S: APTC Stage II Scope of Services

PART 3 - SCOPE OF SERVICES

AUSTRALIA-PACIFIC TECHNICAL COLLEGE STAGE II
Note to Tenderers: This Part forms a key Schedule of the Contract Conditions. It reflects the most current version of the Services required of the Contractor but may be updated by AusAID during contract negotiations, particularly in light of information included in the Tenderer’s response to the RFT.

SCHEDULE 1 – Scope of Services

AUSTRALIA-PACIFIC TECHNICAL COLLEGE STAGE II

1. ABBREVIATIONS, ACRONYMS AND DEFINITIONS

1.1 The following abbreviations, acronyms and definitions are used in this Scope of Services and Basis of Payments:

	AG
	Advisory Group (APTC)

	APTC 

	Australia-Pacific Technical College, reference to the APTC throughout this Scope of Services and Basis of Payment is to the Contractor

	APTC DD
	APTC Stage II Design Document

	AQF
	Australian Qualifications Framework 

	AQTF
	Australian Quality Training Framework

	AUD
	Australian Dollars

	Campus countries 
	A country that has one or more APTC training venues. 

	ELLN
	English Language, Literacy and Numeracy 

	CSS 
	Corporate and Student Services (of the APTC)

	ILO
	International Labour Organization

	FFS
	Fee-for-Service

	LMA
	Labour Market Analysis

	LMI
	Labour Market Intelligence

	Long Term Personnel 
	Personnel working continuously for more than six (6) months 

	New entrant
	Students with Certificate II level qualifications, who meet the theory requirements for entry into a course but have limited to no practical work experience

	PAF 
	Performance Assessment Framework 

	PIC
	Pacific Island Country

	PIF
	Pacific Island Forum (Member countries include Australia, Cook Islands, Federated States of Micronesia, Fiji, Kiribati, Nauru, New Zealand, Niue, Palau, Papua New Guinea, Republic of Marshall Islands, Samoa, Solomon Islands, Tonga, Tuvalu and Vanuatu)

	Program Start Date
	Refers to the 1 July 2011

	RPL
	Recognition of Prior Learning

	RTO
	Registered Training Organisation

	School 
	Refers to the grouping of relevant training courses, such as the School for Hospitality and Tourism

	Services Start Date
	The date in Part A Program Specific Contract Conditions Clause 2.2

	SHCS
	School of Health and Community Services

	Short Term Personnel 
	Personnel working less than six (6) months continuously 

	SIS
	Small Island States (Countries include: Cook Islands, Federated States of Micronesia, Kiribati, Republic of the Marshall Islands, Nauru, Niue, Palau and Tuvalu)

	STH
	School of Tourism and Hospitality

	TAE4
	Certificate IV in Training and Assessment 

	Training Venue(s)
	Venue(s) that can accommodate the delivery of theory and practical components of a course. Such venues are generally facilities of industry partners and/or public training institutions.

	VET
	Vocational education and training


2. BACKGROUND
2.1 At the 2006 Pacific Islands Forum (PIF), Australia announced support for the establishment and operation of the Australia-Pacific Technical College (APTC). Working in partnership with industry and regional governments, the APTC would facilitate regional labour mobility through demand driven, internationally recognised and portable technical and vocational skills development in the formal wage economy. The APTC commenced operations in July 2007 to complement existing training in the region. 

2.2 The mandate of the APTC was, and still is, to boost economic growth in the Pacific by helping to develop a more competitive regional workforce and to assist mobility of skilled workers between the Pacific and developed countries with the provision of an internationally recognised qualification.

Stage I 

2.3 Initial funding of approximately A$150 million was provided for the establishment and operation of the APTC for its first four years, up to 30 June 2011. Approximately 3,000 Pacific islands students graduated from the College with Australian qualifications in the first four years. Courses were offered through five separate schools: hospitality and tourism; health and community services; automotive trades; manufacturing; and construction and electrical trades. Training sectors were chosen after consultations in the region to reflect occupations in demand in Pacific Island countries at the time.

2.4 Two Australian Registered Training Organisations (RTOs) contracted directly to AusAID, delivered courses through the College training centres. A Contractor with development expertise was engaged directly by AusAID to oversee the College and to ensure consistency in the approach between the RTOs. 

2.5 APTC followed a flexible, results-oriented approach in the direct delivery of primarily Australian Certificate III and IV training. The College was open to citizens of PIF countries, excluding Australia and New Zealand. 

2.6 Training courses were delivered in workplaces and institutions in four campus countries – PNG, Fiji, Vanuatu and Samoa. All APTC training facilities were established in partnership with either local firms, government agencies or training institutions. 
Stage II (1 July 2011 – 30 June 2015)

2.7 Key to the continuing success of the APTC is its close association with industry in the region. The APTC will engage with industry at national, regional and international levels to ensure that the continuation of training services it provides are relevant and meet Australian Quality Training Framework (AQTF) standards and industry demand. 

2.8 It is intended that the APTC continue a focus on the schools of Automotive, Construction and Electrical and Manufacturing (SACEM), Tourism and Hospitality (STH) and Health and Community Services (SHCS) as established in Stage I. However, in the delivery of training, the APTC will take into consideration the strategic directions of key stakeholders within the Pacific region. These include industry organisations and corporations which operate within each country and across the region; relevant industry and technical and vocational government agencies in each of the participating countries and multi-lateral; and bilateral aid agencies operating in the region.

2.9 A major change from Stage I is a re-structure of the APTC to adopt a whole-of-College model. AusAID will engage one legal entity, which in Stage II will manage both College operations and provide all Australian accredited training delivery (at the Certificate III, IV and Diploma level). In the provision of training the Contractor may chose to enter into sub-contracts with Australian Registered Training Organisations (RTOs) to deliver specific courses or, if accredited under the AQTF, deliver courses itself. [to be updated in accordance with the preferred tenderers approach] This model reflects the structure of Australian RTOs operating domestically and internationally.

2.10 In Stage II, AusAID will continue to retain ownership of the APTC name, and the RTO(s) responsible for training delivery will continue to certify qualifications under their own institution name and the APTC brand.

2.11 In Stage II, APTC Corporate and Student Services (CSS) (formally known as the Coordination Office in Stage I) will have an expanded role. It will support the delivery of training through the provision of, among other things: corporate services and systems; management of partnerships, including contractual arrangements, with all training venues such as industry and Pacific vocational training centres; management representation across the region and ensuring equity of access through the management of a scholarships program. In the delivery of these administrative services, CSS will also ensure the governance arrangements and that the performance of the APTC is responsive to changing industry demands. The CSS will further ensure the APTC adheres to all legal requirements and industry standards, across implementation jurisdictions and that delivery RTO’s have and maintain current AQTF registration. 

2.12 Under each of the Schools, all training delivery will be undertaken by the RTO(s). At the direction of the CSS, the Schools will be tasked to:

(a) plan and resource courses approved in the Annual Training Profile;

(b) customise new courses as required;

(c) assess technical and English Language, Literacy and Numeracy (ELLN) competency of APTC applicants;

(d) deliver AQTF training at Certificate III level and above;

(e) provide concurrent ELLN and other learning support to enrolled students;

(f) organise work placements and maintain effective work place assessment and quality assurance to ensure the integrity of the APTC qualification and brand;

(g) award APTC Australian Qualifications Framework (AQF) qualifications (under a RTO name) to students meeting the required competency standards;

(h) deliver the ‘APTC to work’ course; and

(i) conduct and enter into contractual arrangements for fee-for-service training activities (including Recognition of Prior Learning (RPL) and Certificate IV in Training and Assessment (TAE4) courses).

3. PRECEDENCE OF CONTRACT OVER THE APTC STAGE II DESIGN DOCUMENT

3.1 This Scope of Services outlines the role of the Contractor in supporting the implementation of the APTC and should be read in conjunction with the APTC Stage II Design Document (APTC DD) dated September 2010. The APTC DD sets out the context, scope, objectives and principles of APTC and is the primary reference document from which to gain an understanding of the intent, purpose and features of APTC. Where there is an inconsistency between the APTC DD and the Contract, the Contract will take precedence.

4. DEVELOPMENT GOAL OF APTC 

4.1 The Goal of the APTC is:

(a) Training: Increased supply of skilled workers in targeted sectors in the Pacific region.

(b) Employment: Pacific Islander women and men with Australian qualifications realise improved employment opportunities nationally, regionally and internationally in targeted sectors.

(c) Productivity: Increased productivity of individuals and organisations in targeted industries and sectors.

4.2 The Purpose of the APTC is to:

(a) provide Pacific Islander women and men with Australian qualifications that present opportunities to be able to find employment in targeted sectors nationally and internationally; and

(b) support skills development in the Pacific in response to labour market requirements. 

5. SERVICES

5.1 The Contractor shall perform the following Services in accordance with the terms and conditions of this Contract, associated annexes and agreed operating policies and procedures. The Contractor’s performance in the delivery of these Services will be assessed against the Performance Assessment Framework which will be updated annually in accordance with Clause 16.2:

Component 1: Marketing, Reputation and Image 

5.2 The Contractor will deliver a targeted, multi-level communication and marketing strategy that maximises exposure to industry and prospective students of APTC programs and builds brand awareness and reputation across the Pacific region.

5.3 The APTC Marketing Strategy, among other things, will include activities which promote:

(a) awareness in Small Island States (SIS) in accordance with Clause 5.11(b) and (c) below; and 

(b) the Scholarships Scheme in accordance with Clause 5.12(a).
Component 2: Partnership Development

5.4 The Contractor will develop partnerships with Australian and Pacific Island industry associations, firms, private training providers and government training institutions to deliver Australian qualifications in a range of locations across the PIF countries to meet prioritised skill deficient areas in the Pacific region.

5.5 In developing these partnerships, the Contractor will foster the establishment of industry advisory mechanisms for the APTC with broad-based representation to ensure APTC training provides skills and competencies relevant to industry and government employer needs.

5.6 The Contractor, through the CSS, will establish and maintain appropriate contractual arrangements with industry and public/private sector institution training partners for the implementation of the APTC courses. All contractual arrangements for training venues will set out, amongst other things detailed in Clause 8.6 – 8.9 below, the use of facilities and other services required for training delivery. 

(a) Except for entering into contracts for Fee-for-Service activities (refer Clause 10), sub-contracted RTOs will not enter into contractual arrangements with industry or government/private institutions for the provision of training space, equipment or placements.

Component 3: Quality Learning (Training Delivery) 
5.7 The Contractor will:

(a) ensure flexible delivery of training (including course and curricula design, course delivery, assessment and certification), with the support of industry, through a network of established, refurbished and/or new training facilities; and
(b) provide work-ready graduates relevant to the needs of national, regional and international labour markets with AQF Vocational Education and Training qualifications in accordance with the AQTF. 

5.8 In providing flexible course delivery, the Contractor will:

(a) conduct Communication and Literacy Assessments (or their equivalent) and design or tailor (as required) and deliver a cost effective bridging program for potential SIS students who meet technical skill requirements but fall short of ELLN requirements. In addition, the Contractor will provide all enrolled students with concurrent support for communication, literacy and numeracy needs. 

(b) trial the development of Reintegration Plans with selected partners and other larger employers and their employees. Reintegration Plans should promote effectiveness by indicating how the student’s training will be utilised in the workplace, the student’s career path and how the training will improve business productivity or otherwise contribute to the business objectives of their employing organisation. The Contractor will need to follow up with employers/graduates after six (6) months to assess whether the plans have been implemented and whether the employment/productivity objectives achieved. The Contractor will provide an assessment on how effective the Reintegration Plans are in the Annual Report, due 15 July 2012, with a recommendation on whether use of this tool should continue and be expanded. 

APTC training venues 

5.9 The Contractor will construct/refurbish and/or lease facilities for training
, student accommodation, office space and staff facilities which: 

(a) meet standards required under the AQTF; 

(b) are considerate of gender issues; and 

(c) where required, ensure physical access for students with disabilities.

APTC equipment 

5.10 The Contractor will: 

(a) identify and source training resource needs;

(b) procure, lease, install and maintain required plant and equipment; and 

(c) select and procure library resources.

APTC Personnel and Appraisal Processes

5.11 The quality of the teachers in the classroom is the most important attribute of a successful College. Cross-cultural competence and HR management skills will underpin skills for all staff as the program works with students, employers, Pacific governments and other stakeholders from across the Pacific. The Contractor must therefore ensure that there is a balance between personnel with vocational education and training (VET) expertise and development understanding. 
5.12 The CSS will require a team that possess experience in program management and skills suitable to a development context including: VET management and administration; training delivery and management; student and scholarships policies and management; labour market analysis; communication, presentation and public relations; financial management; contract and program management; and planning with an emphasis on analytical reporting, monitoring and evaluation, innovation and improvement. Human resource development skills will be an essential requirement to plan and assess VET course training initiatives and to support and further develop and manage alumni reintegration processes. 

5.13 All staff recruitment will align with equal employment opportunity principles and seek to maintain a gender balance for teaching and CSS staff for both Australia-based and offshore roles. Expatriate and local staff will be used as appropriate, depending on the level, qualifications and experience required for each role. The Contractor will prepare position descriptions for each role including specific requirements relative to AusAID contractual needs. 

5.14 The Contractor will develop detailed procedures for the mobilisation of both long-term and short-term staff to the campus countries. This will include processes for pre-departure briefings including cultural and gender sensitivity training, establishment allowance, travel and health insurance, travel arrangements, accommodation (initial versus long term), on-arrival orientation; basic language training for long-term expatriate staff. Briefing and orientation will be extended to family members when accompanying the staff member. 

5.15 The Contractor should manage its resources through a cost-effective mix of Australian and local staff. By June 2012, the Contractor will have implemented a Localisation Strategy, as approved by AusAID. This Strategy will include approaches on how to increase the employment of qualified/experienced local staff where possible and explore options on how local VET trainers can obtain the necessary qualifications and experience to deliver AQTF courses. 

5.16 The Contractor will conduct annual performance reviews of all long-term APTC personnel. 

Component 4: Student and Scholarship Management


Student Management 

5.17 The Contractor will:

(a) develop and implement systems that maximise the opportunity for students from all PIF countries to access and successfully complete APTC programs as ‘work ready’ graduates;

(b) provide and maintain a centralised student database;

(c) recruit students through appropriate marketing and promotion of courses;

(d) assess and recognize prior learning and current competency standards of students; 

(e) provide a suite of student services, including among other things: course information and advice for students, student welfare services such as orientation, teacher consultations, learning support, counselling and organisation of vocational placements when and where required;
(f) develop within the first six (6) months of the Program Start Date, a Student Pastoral Care Plan which will ensure students are supported in their learning and that any emerging issues (language proficiency related, personal or interpersonal) are identified immediately and handled appropriately. APTC staff will be trained to identify and provide an initial gender sensitive response to students requiring pastoral care. A formal escalation process should be included to ensure access to a trained counsellor, as required; 

(g) undertake assessment and concurrent training of English language and numeracy skills for students, as required;
(h) promote access for students from Small Island State including through:

(i) regular recruitment activities in all the SIS including marketing, student recruitment, promotion of scholarship availability, applicant skills assessment, and facilitation of applications by prospective students;

(ii) marketing and recruitment strategies tailored to the SIS market; and

(iii) application assessment and selection processes sensitive to the special circumstances of SIS applicants.

(i) maximise opportunities for work experience and work placements for students; and

(j) as necessary work with AusAID and Pacific governments to resolve any legal, regulation and visa issues for study and work placements by APTC students. 

Scholarship Management

5.18 The Contractor will manage APTC Scholarships to maximise opportunities for students from all PIF countries to access and successfully complete APTC qualifications with a particular focus on redressing gender, isolation and income discrimination. In doing this the Contractor will:

(a) market and disseminate scholarship applications;

(b) assess, rank and select scholarship applicants;

(c) assist with awardee mobilisation (including visas) and pre-departure briefing;

(d) provide Scholarship awardee reception, orientation and accommodation arrangements in the campus countries;

(e) pay award stipend and allowances; 

(f) make award offers and approval of award variations; 

(g) maintain scholarship data and reporting; 

(h) organise student travel during training, including the payment of all associated costs such as airport and departure taxes; and

(i) facilitate airport transfers on transit, arrival and departure.

Component 5: Management and Governance 
5.19 The Contractor will:

(a) ensure compliance with AusAID and any Australian or Pacific government legislative requirements relating to the operation of the College, including appropriate accreditation and certification for the delivery of agreed training courses with relevant government authorities

(b) implement transparent quality management and administrative systems and processes that ensure:

(i) effective and efficient delivery of training courses (including governance arrangements, human resource development, student services, provision of infrastructure and equipment, etc); and 

(ii) achievement of APTC objectives on time, within budget and structured to meet reporting requirements;

(c) establish planning, human resource management, accounting and financial management systems;

(d) maintain all APTC office and training infrastructure including, but not limited to, facilities in Fiji, Vanuatu, Papua New Guinea and Samoa;

(e) provide adequate CSS representation for the delivery of services across multiple countries, including in Tonga, Kiribati and Solomon Islands in accordance with Clause 8.11;
(f) ensure staff are employed in accordance with relevant national labour laws and awards;

(g) track all payments and receipts and produce financial reports to meet AusAID requirements using an integrated financial management system;

(h) ensure accurate and on time payment of all APTC staff (payroll management), non salary items and purchase of assets;

(i) manage an assets register which tracks all APTC assets;

(j) ensure all policies and procedures are available on the APTC intranet (and internet where appropriate);

(k) establish systems for the collection of student tuition, RPL and any other fees in accordance with the APTC Tuition Fee Policy;

(l) provide on-going monitoring and evaluation including assessing the impact of APTC training on livelihoods through monitoring changes in industry, sector and national productivity, poverty levels and the provision of data for the APTC Performance Assessment Framework;

(m) develop, update, implement and comply with all APTC policies and procedures including but not limited to those listed in Annex A and as approved by AusAID;

(n) establish relevant measures to mitigate fraud and due process to deal with instances of fraud;

(o) manage all APTC contracts and obligations;

(p) establish and maintain an information and communication technologies system, with necessary hardware and software to allow for effective communication between training venues, CSS and Australian offices, the APTC staff and students email, APTC education management information systems, and intranet and internet sites. High level requirements for the Information Management System are provided at APTC DD Annex M;
(q) manage all information requirements of the APTC, including but not limited to: 

(i) course data - including locations of where the courses are being delivered and whether they are through a industry/local institution arrangement;

(ii) student data – student details, RPL, enrolments, results, completions, applications received, assessment data, waiting lists, and disaggregated by gender and country of origin;

(iii) scholarships data – level of scholarship, start and end of award dates and award variations;

(iv) financial data - including scholarships expenditure,, income received and expenses by course/school;

(v) asset data - by office, school and course; and
(vi) human resource data – staff details (broken down by staff type, gender, country of origin) and classes taught.
Alumni and Post Award Support 

5.20 To improve APTC graduate employment rates and productivity, the Contractor will develop an ‘APTC to work’ preparation program to be provided to students near the end of their training. This program will be developed for approval by AusAID within the first three (3) months of Program Start Date. This would include generic and country-specific tailored topics such as: 

(a) Curriculum Vitae development;

(b) how to identify employment opportunities;

(c) applying for work (domestically and overseas); and 

(d) strategies to introduce new skills into the workplace; interview skills; and where to access resources for starting a new business etc. 

5.21 In addition, the Contractor will support an APTC Alumni Network to promote the program’s objectives in key areas. The Alumni Network will contribute to the sustainability of linkages between Australia and APTC graduates in the Pacific and:

(a) provide a forum for active discussion and exchange of ideas/expertise relevant to the achievement of the APTC objectives; 

(b) enable alumni to exchange knowledge and skills; 

(c) facilitate the provision of contact information for Monitoring and Evaluation (M&E) purposes; and

(d) provide access to alumni for operational purposes (e.g. for assisting with pre-departure briefings, mentoring to new students and graduates, access to labour market intelligence etc). 

5.22 The Contractor will:

(a) develop and maintain an alumni database of all APTC graduates (including scholarship and fee-paying students) with relevant contact, employment and other post-award details for each graduate;

(b) submit an annual costed workplan for alumni activities as part of their annual work-plans. Activities could include organising or conducting a range of cost-effective alumni events, such as social and professional networking events arranged around graduations and/or relevant Australian VIP visits or school-based professional development seminars. Alumni activities in non-campus countries should coincide with existing visits to those countries for other APTC activities; and

(c) establish and manage an APTC website which can be used as a forum for alumni networking activities (e.g. notice boards, email groups, chat rooms, and/or notice of forthcoming alumni events).

5.23 The Contractor will also investigate partnerships with Australian industry bodies, such as the Master Plumbers Association and Electrical Contractors Association, and industry interlocutors, such as the Australian Chamber of Commerce and Industry, to review viability, and if appropriate, obtain sponsorship for any necessary in-Australia workplace training for Australian registration requirements. This is in an effort to facilitate access to Australian employment for those trades which are restricted by national and state registration requirements.

Analysis of Labour Market Data 

5.24 For the APTC to effectively achieve its mandate to build up the internationally competitive skill base of the Pacific, it must base its policy and strategic operational decisions on improved labour market intelligence (LMI). It must be based on the best information the Contractor can gather on middle-level skill requirements (in the trades, technician and equivalent level service delivery occupations) of the formal economic sectors in each country of the region, and in the metropolitan countries outside the region that APTC graduates are likely to find employment in, notably Australia and New Zealand.

5.25 The Contractor will therefore identify sources of market labour information, though for example industry consultations and networks. The Contractor will systematically collect this data and analyse it to inform the Annual Training Profile and ensure course relevance to industry demand domestically, regionally and beyond. 
5.26 A Labour Market Analysis Action Plan (LMA Action Plan) will be developed within three (3) months of the Program Start Date for AusAID approval. In developing the LMA Action Plan the Contractor will identify key stakeholders in industry and government who are in a position to provide labour based information. The LMA Action Plan will be fully costed and specify who and how regularly consultation should occur in order to obtain country specific information on industry trends, emerging skills gaps, training requirements and priorities. The Contractor must ensure that consultations are regular enough to provide up-to-date industry information to assist in developing the Annual Training Profile. 

6. TRAINING PROFILE

6.1 The specific courses to be delivered by the Contractor each year on a College wide basis will be detailed in the Annual Training Profile. The Annual Training Profile is based on analysis of industry demand. To remain relevant, it is essential that APTC course delivery is labour market demand-based and able to flexibly respond to emerging opportunities. This is particularly the case in PNG, given the level of economic growth and development in that country. The need for flexibility also flows from the industry partnerships delivery model, where the APTC will need to be able to adjust delivery to specific enterprise needs. There may also be emerging needs and opportunities from AusAID and other donor programs, for example, upgrading the qualifications of staff from national VET institutions. In addition, further adjustments to the profile may be appropriate as economic and labour market needs change in the Pacific, Australia, New Zealand and other countries offering employment opportunities. 

6.2 The courses provided by the APTC will be reviewed at least annually by the Contractor, based on systematic labour market intelligence gathering and whole of College analysis to ensure course delivery clearly reflects national and regional training priorities for enhanced employment and productivity. 

6.3 Course planning needs to be undertaken sufficiently in advance of the training so that new courses can be customised, equipment purchased and transported, and staffing arranged. There also needs to be sufficient lead-time for the courses to be promoted, applicants assessed, scholarships awarded and awardees mobilised before the training period commences. 

6.4 Enrolment and graduate targets will be determined for each school and detailed in the Annual Training Profile. AusAID approval of the Annual Training Profile is required prior to implementation; refer to Clause 16.2(a). 
6.5 Indicative courses, student and graduate numbers in 2010/11 are detailed in the APTC DD Annex E. Confirmation of the continuation of these courses, and enrolment/graduate numbers for 2011/12 will be negotiated with AusAID during the transition period. The scheduling of these courses will be confirmed in the first Annual Plan, refer to Clause 16.2(a). 

7. ENROLMENT AND GRADUATE TARGETS FOR STAGE II

7.1 Whilst it is anticipated that a minimum of 3,000 graduates will be achievable over the four year period of Stage II, enrolment numbers and therefore graduate numbers will be based on an industry demand analysis. This analysis will be undertaken on an annual basis and enrolment and graduate targets will be identified for each School and agreed in advance by AusAID. 
7.2 To maximise training outputs and outcomes, focus on upgrading and certifying skills of existing workers in the formal labour market will continue into Stage II. The Contractor will also allow flexibility to train ‘new entrants’ throughout Stage II, particularly those from the SIS where work experience opportunities are limited. This will also provide a pathway for Certificate II graduates from national institutions.

7.3 Students will enter the APTC as tuition fee paying, employer/other donor funded or scholarship students. 

8. LOCATION OF APTC 

Corporate and Student Services (CSS)

8.1 The CSS will support the delivery of training through the provision of, among other things, corporate services and systems;, management of partnerships, including contractual arrangements with Pacific industry and vocational training centres; representation across the region and ensuring equity of access through the management of a scholarships program.

8.2 In the delivery of the APTC services, the CSS will also ensure the governance arrangements and performance of the APTC is responsive to changing industry demands and adheres to all legal requirements and industry standards across implementation jurisdictions and that AQTF registration of all RTOs involved in the delivery of courses is maintained. 

8.3 Given the delivery of training is to be coordinated across at least four (4) countries, through a diverse range of partners, and that access is provided to applicants from all PIF countries, it is essential that priority is given to the development and maintenance of systems which creates an integrated functioning organisation. 

8.4 The CSS should therefore be located where:

(a) reliable physical and information technology infrastructure is available;

(b) regular flight services are provided to both campus and non-campus countries; and 

(c) physical and personal safety is assured. 

8.5 At present, Nadi, Fiji is considered the best location for the CSS. 

Training Venues

8.6 Partnerships with local industry are the foundation of the APTC delivery model. Strong industry linkages are essential to building the reputation of the APTC and to ensure course delivery is demand based. These linkages help ensure that training provision is relevant to employer needs, and also to access industry equipment and facilitates, source part time lecturers and trainers and provide workplace attachments. 

8.7 Training venues, as defined under Clause 1, have been established in four countries: Fiji, Vanuatu, Samoa and Papua New Guinea. Subject to negotiation, in Stage II the current contractual arrangements will be renewed or new arrangements established, in partnership either with local firms or local training institutions. A summary of existing training venue partners is provided in the APTC DD Annex E.
New Training Venues

8.8 It is not anticipated that there will be significant capital expenditure on permanent infrastructure in the establishment of any new Stage II training venues. In the selection of training venues for AusAID approval, the Contractor will need to address the following considerations:

(a) given most courses are delivered on a competency basis, that access is available to industry partners who can either provide facilities to conduct courses and or work placements for both domestic and international students;

(b) availability and ease of obtaining relevant visas to allow for study and work placements;

(c) evidence of domestic industry demand for the course;

(d) costs of establishing a training venue including any refurbishment and/or construction, shipment of supplies, or travel costs for external students;

(e) physical and personal safety needs of, respectively, APTC assets, staff and students; and

(f) that adequate accommodation and welfare needs of international or out of town students can be satisfactorily catered for.

8.9 In negotiating partnerships for training venues, the Contractor will typically provide trainers, consumables for the particular trade, and placements for partner employees. It is expected that the partner will provide the physical infrastructure including equipment for the delivery of the course and access to premises for an agreed number of external students. Financial agreements should include recognition of any fee-waivers provided to the partner organisation.

APTC Representative Offices

8.10 In Stage I, the APTC established representative offices in Tonga, Kiribati and Solomon Islands. This was in response to the demand for APTC training, and to assist equitable access in SIS. This presence will continue in Stage II, unless the representation and support services (including application distribution, scholarship promotion, and facilitation of testing and student mobilisation) can be more effectively managed from the CSS offices in one of the campus countries.

Solomon Islands

8.11 Within the first three (3) months of the Program Start Date, or as otherwise agreed with AusAID, the Contractor will undertake a detailed feasibility study for the establishment of APTC training venue(s) in the Solomon Islands. With a population of over 500,000, the Solomon Islands is the third most populous country of the Pacific, after PNG and Fiji. The size of the formal economy, while small, has grown and firm productivity is important to its economic growth.

8.12 The Terms of Reference for the Feasibility Study, APTC DD Annex Q, should first be confirmed by the Contractor with AusAID. Subject to confirmation, the Contractor should provide recommendations as to:

(a) which APTC courses would be delivered in the Solomon Islands based on an industry demand analysis;

(b) appropriate training venues (through industry partnerships and/or the Solomon Islands College of Higher Education) in consideration of the issues listed in Clause 8.8 above;

(c) how a presence in Solomon Islands will complement the Solomon Island Government and AusAID bilateral program plans for strengthening the Solomon Islands VET sector; 

(d) the flow-on effects on student numbers in other campus countries;

(e) costs of establishing APTC training in the Solomon Islands, compared to sending Solomon Islanders overseas to complete courses; and 

(f) indirect benefits from an APTC presence in the Solomon Islands. 
9. CENTRE FOR PROFESSIONAL DEVELOPMENT

9.1 The Contractor will establish a Centre for Professional Development within Corporate and Student Services. This Centre will coordinate demand-driven TAE4 course delivery by individual Schools and provide specialist support to VET staff from national institutions undertaking TAE4 courses. It will also provide, if appropriate, centralised professional development programs through the APTC, including support to APTC staff to ensure that they are abreast of changing developments in teaching and learning practices and AQTF requirements. 

9.2 The Contractor will deliver TAE4 courses on a fee-for-service basis on request by sponsoring organisations (e.g. donors and Pacific governments) and delivered in addition to the Annual Training Profile. Pricing to organisations of these courses should reflect their intended development outcomes, and that they are likely to be funded by donors and Pacific governments. As AusAID already provides core funding for the APTC, the Contractor should consider setting cost-recovery prices for courses funded through AusAID bilateral programs for upgrading of national VET capacity in Pacific Island Countries.

10. FEE-FOR-SERVICE

10.1 A Fee-for-Service (FFS) activity is defined as ‘an activity undertaken by the APTC which relates to training or training support services within the industries represented by the schools that make up the APTC; is fully funded from external parties; and involves training in Australian qualifications at Certificate III level or above, leading to full qualifications or customised programs within such courses.’

10.2 The Contractor must approach marketing, sourcing, costing, pricing, bidding, implementation and reporting of all FFS activities in accordance with the most recent Fee-for-Service policy agreed by AusAID (refer to APTC DD Annex N). 

10.3 APTC share of revenue from FFS activities will be retained in a central account and applied to AusAID approved non-recurrent discretionary costs such as additional scholarships and upgrading of facilities/equipment. 
10.4 The RTO undertaking the training delivery for a FFS activity will hold the commercial contract and carry the associated risks. 
10.5 Reporting on FFS activities and income will be included in Quarterly Financial Reports, and Six-Monthly and Annual Reports. 

11. PERFORMANCE, MONITORING AND EVALUATION

11.1 The Contractor is responsible for the consistency of performance information and promotion of a high performance culture within the APTC. 

11.2 The Contractor is responsible for collecting, storing and disseminating data on the outcomes and impact (goal and purpose) of the APTC and for appropriate allocation of risk management.

11.3 A Performance Assessment Framework (PAF) has been developed for the first year of the APTC Stage II, at APTC DD Annex K. Using a range of quantitative and qualitative data, the Contractor will provide ongoing analysis of the effectiveness, efficiency, relevance and sustainability of all activities. Data should be provided on a disaggregated basis, by enrolment and graduate numbers by school, campus, student home country, gender, and disability.

11.4 The PAF will be reviewed annually by the Contractor, including the program logic, indicators, sources and definitions, and provided to AusAID for approval with the Annual Plan/Report. 

11.5 The Contractor is to include progress reports using the PAF as a monitoring tool in the Six-Monthly and Annual Reports.

11.6 AusAID may undertake a performance review after the first two (2) years of Stage II, in mid-2013. The Contractor is to cooperate with and facilitate the work of the performance review team.

11.7 In addition, AusAID will be undertaking a scoping study into longer term arrangements for the APTC. The Contractor is to cooperate with and facilitate the work of this team once mobilised. 

12. APTC GOVERNANCE STRUCTURE 

12.1 On an operational basis the Contractor will be managed by and report to AusAID. On a strategic level, the Contractor will take advice from AusAID and the APTC Advisory Group. 

AusAID

12.2 AusAID is the principal Australian Government agency responsible for oversight and funding of the APTC. AusAID will be responsible for:

(a) confirming availability of budget based on forecasts and acquittals provided by the Contractor;

(b) endorsing Annual Training Profiles and the Annual Plan/Report;

(c) monitoring, reviewing and evaluating the performance of the Contractor and APTC outcomes; 

(d) managing the contractual relationship with the Contractor;

(e) advocating the role and focus of the APTC with Australian and Pacific government agencies, donors and regional and Australian industry bodies; 
(f) as necessary, facilitating relevant registration and certification of APTC operations; 

(g) determining the long term structure of the APTC; and 

(h) where necessary, directly requesting the Contractor to undertake additional services outside the agreed Annual Training Profile and Annual Plan process. 

12.3 As part of the overall management process, AusAID will meet the Contractor every six (6) months, in January and July each year, and as required. The purpose of such meetings is to provide an update on progress, address any issues that may have arisen in the delivery of APTC courses, and to acknowledge good and address poor performance. 

12.4 AusAID Posts in campus countries may also play an advisory role as required (e.g. with respect to graduation ceremonies) and facilitate APTC relationships and protocols with the Pacific governments. 
Advisory Group 

12.5 The APTC Advisory Group (AG) will provide strategic advice to the APTC and AusAID on:

(a) national, regional and international issues and trends impacting regional training priorities;

(b) culturally appropriate training strategies; 

(c) marketing, promotion and communication strategies; 

(d) the draft Annual Plan and proposed Annual Training Profiles; 

(e) access to scholarships;

(f) APTC progress and performance; and

(g) accessing industry networks and government. 

12.6 Members of the Advisory Group would be expected to contribute relevant sector expertise regarding Pacific and regional industry trends, market intelligence and training requirements, as well as a capacity to provide an advocacy role at the country level. As such, membership of the AG should comprise representatives of Pacific Island Country (PIC) governments; Pacific industry, industry associations and/or private sector; and Australian/New Zealand industry associations or key stakeholders.
12.7 The Advisory Group should comprise a maximum of 10-12 members (with alternates as appropriate) plus observers and should preferably be chaired by a Pacific industry or industry association representative. Observers could include representatives from AusAID, other regional donors and regional organisations. 

12.8 The Advisory Group will meet once a year, for up to two (2) days. Attendance of PIFC representatives would be funded from APTC program costs however Australian members would fund their own attendance. Meeting venues should rotate to enable the AG to observe APTC training, and raise the profile of the APTC throughout the region through their presence. To ensure scope for substantive input, the date of meetings should be established at least six (6) months in advance and be scheduled to enable strategic advice on finalisation of key APTC reports (e.g. Annual Report/Plan, Annual Training Profile development).

12.9 Additional meetings, as agreed by AusAID, may be held as required to consider urgent matter such as significant policy changes, major issues and/or the Stage III scoping study report. Where possible, the Advisory Group will be asked to consider matters out of session and/or delay considerations until the next annual meeting. 

12.10 To develop and maintain the Advisory Group, the Contractor will:

(a) identify potential members for AusAID approval;

(b) provide travel and accommodation arrangements for AG members; and

(c) provide secretariat support to the AG, including:

(i) providing of a draft agenda two (2) months prior to the meeting;

(ii) providing relevant papers for consideration at least two (2) weeks before meeting;

(iii) providing meeting minutes within one month of the meeting date; and

(iv) ensuring timely follow up on AG decisions.

Other APTC stakeholders 

Pacific Governments

12.11 The Contractor has a responsibility to raise awareness and understanding of the Pacific governments and Pacific Regional Organisations as to the regional focus, rationale/role and long term nature of the APTC. The Contractor, where possible, should highlight linkages between bilateral and regional VET programs, particularly complementary efforts to upgrade local VET institutions at Certificate I and II levels. 

12.12 The Contractor will undertake this role through:

(a) developing and implementing a regional communications strategy to increase understanding of the APTC role in VET in the region;

(b) engagement with Pacific government representatives at Advisory Group meetings;

(c) regular face-to-face meeting in campus countries with Pacific government agencies, industry sectors and regional organisations;

(d) formal consultations with all, and particularly SIS, countries to identify potential areas of industry demand, to ensure responsiveness to government priorities, to get input into the courses being offered by the APTC and in the development of Country Strategies as referred in Clause 12.13(e) below; 

(e) provision to Pacific governments of regular information, in the form of Country Strategies which include statistical APTC country summaries on enrolments, scholarships and graduates; and

(f) increased visibility and strengthening of APTC management capacity in both campus and non-campus countries. 

National VET Institutions and Bilateral VET Programs

12.13 AusAID is working with a number of PICs to strengthen their national VET systems. Whilst the APTC is not primarily an instrument for the capacity building of national VET institutions, it can still play a direct role in supporting AusAID bilateral VET programs and partner VET institutions. Where possible, the Contractor should therefore provide: 
(a) work attachments to the APTC of trainers from national VET institutions;

(b) national VET institutions with access to the APTC curriculum, instructional materials, industrial quality equipment and resources;

(c) flexible course delivery at national VET institutions in non-campus countries, including involvement of local trainers;

(d) APTC trainers as mentors to local teachers and trainers;

(e) opportunities for informal interaction between APTC and local institution teachers, particularly where they share facilities, resources and materials; and

(f) fee-for-service TAE4 training of national VET staff.

12.14 Any formal APTC support for national VET institutions should be discussed with AusAID to ensure alignment with AusAID’s support and overall approach to VET capacity development in the country. 

Industry Sectors

12.15 Strong industry linkages are an essential component for the APTC in order to increase the relevance of training provision with employer needs, build the standing and reputation of the APTC, gain access to specialised equipment and facilities too expensive to provide within the college, as a source of part-time lecturers and trainers, and to provide workplace attachments and post-training employment for students. These linkages are also important for the APTC to be responsive to changing employment trends and training needs and to develop fee-for-service markets. The Contractor therefore needs to implement strategies to develop and maintain these partnerships, which would for example, include regular meetings with target industry employers and attendance at industry association forums. 

Other Donors


12.16 A number of donors and multilateral organisations are active throughout the Pacific in providing support for VET, either at a regional or bilateral level, including the European Commission, NZAID, Japanese International Cooperation Agency, Asian Development Bank and the International Labour Organization (ILO). 

12.17 While core funding of the APTC by other donors may not be realistic in the short term, there is certainly greater scope for promoting the APTC to donors as an opportunity for sponsoring student placements and for providing FFS training to support their activities in the region. Key bilateral donors such as New Zealand and the European Commission and other multilateral organisations should be encouraged to attend Advisory Group meetings in an observer role. 

12.18 Additionally, other innovative and cooperative practices may be possible. For example, within bilateral programs, where infrastructure programs are funded, there may be an opportunity to provide relevant training and work placements for APTC students, particularly where local industry work- place opportunities are limited. Such opportunities need to be considered by the Contractor in the development of the Annual Training Profile. 

13. ISOLATION, GENDER AND DISABILITIES

13.1 The Contractor has to demonstrate that particular consideration has been given to assuring equitable access for potential students from Small Island States, rural and remote communities, females and students with disabilities. 

13.2 Equitable access to the APTC can be facilitated in a number of ways including for example:

(a) assistance in submission of application forms and supporting documentation, considering remote location, literacy levels and available media;

(b) application assessment and selection processes sensitive to the special circumstances of applicants;

(c) provision of English literacy and numeracy training to students from SIS; and

(d) other means of support, including the APTC scholarship program. 

13.3 The Contractor has to address access issues for disadvantaged groups in each Annual Plan/Report. 

14. HIV/AIDS, NATURAL DISASTERS, PERSONAL SAFETY 

14.1 The physical safety and health of all APTC staff and students is a priority. Given the location of campuses the Contractor will have to ensure appropriate procedures are in place to mitigate risks to students, staff and infrastructure from natural disasters, security, HIV/AIDs and other health issues. 

14.2 The Contractor will ensure access to and continually update relevant procedures for responding to HIV/AIDS, natural disasters and personal and property safety issues. Induction training for staff and students must cover these topics adequately. 
15. TRANSITION PERIOD

15.1 It is anticipated that the APTC training profile for 2011/12 will include courses delivered in 2009 and 2010 which are expected to have ongoing industry demand and sound graduate employment outcomes. In the first three (3) months after the Services Start Date, the Contractor will work closely with the existing Stage I APTC Coordination Office to confirm the 2011/12 training profile and initiate several feasibility studies including:

(a) an assessment of potential SHCS expansion in the areas of allied health, childcare, aged care and community development to reflect expected domestic, regional and international demand for skilled workers, particularly women, in these sectors;

(b) a review of the School of Tourism and Hospitality, including assessment of the demand for hospitality graduates given indications of the limited employment opportunities elsewhere in the Pacific for APTC graduates in this sector; and the removal in May 2010 of related occupations from the Skilled Occupation List for migration to Australia; and

(c) feasibility of establishing a new training venue in PNG in partnership with local hotels to respond to the strong labour demand resulting from the planned growth in hotel accommodation in PNG.

15.2 In addition, during this transition period, the Contractor will:

(a) establish or transfer partnership arrangements with existing institutional/industry partners as referred in the APTC DD Annex E;

(b) register Stage II courses with relevant Pacific government training authorities to ensure regulatory requirements are met in campus countries;

(c) recruit and train CSS and training delivery staff (including any transfer of APTC Stage I staff);

(d) arrange for the handover of CSS/training venue equipment and resources;

(e) establish the Stage II ICT and management information systems;

(f) arrange for the continuity of ongoing training courses from Stage I; 

(g) prepare for the implementation of new arrangements from the start of Stage II; 

(h) develop a College Business Development Strategy which outlines how the APTC will reduce college costs and increase its revenue in Stage II;

(i) undertake an analysis of tuition fees and make recommendations to AusAID to establish a Tuition Fee Policy, based on market prices, with respect to every course. Currently, even where paid by students, tuition fees are heavily subsidised and well below cost recovery. The pricing policy might for example allow different pricing structures for different categories of students. The study should consider issues of cross-subsidisation, within and between courses, campuses and schools, and under what circumstances subsidised tuition fees/courses should continue to be offered, and the implications for AusAID funding; and

(j) update and/or revise the following key policies and procedures: Advisory Group Terms of Reference and Membership List, Natural Disaster Emergency Procedures, Student database overview/manual, Data Management Protocols, Risk Management Plan, Scholarships Policy and Procedures Manual and Fee-for-Service Policy for AusAID approval. A list of APTC procedures and policies is at Annex A. Those policies not identified for updating in the Transition Period will be updated as required or at the least on an annual basis. 
16. REPORTING REQUIREMENTS

16.1 The Contractor must provide and keep current all the procedures and policies appropriate to running an efficient, effective and safe training institution in the Pacific. A list of Stage I procedures and policies for the APTC is provided at Annex A. 

16.2 In addition, the Contractor must provide AusAID the following reports by the date indicated:

(a) An Annual Report/Plan by 15 January each year, which focuses on training outcomes including skill utilisation, employment and alumni outcomes in the preceding year and includes a Plan for the following Australian financial year (July to June). The Annual Report/Plan will include: 

(i) a review of progress to date, including all the information under Clause 10.2 (b), covering the six (6) month period from 1 July to 31 December and addressing any issues affecting implementation;

(ii) a summary of findings from the Performance Assessment Framework and a report on the progress made in applying the framework itself;

(iii) issues, strategies and approach to addressing gender equity; access by people with disabilities; the scholarship scheme; access by Small Island States; quality assurance; promotions and communications; and other cross cutting issues; 
(iv) a Financial report on expenditure to date and accurate estimates for the coming year; 

(v) revisions to any policies and procedures. At a minimum this would include an updated risk management plan; 

(vi) Annual Training Profile for the next Australian financial year incorporating any lessons from the review of progress to date, providing rationale for the proposed profile of courses and explanation of the expected outputs and development benefits of the Annual Training Profile. The Annual Training Profile must be supported by industry and include the courses to be conducted at each training venue (new and ongoing), the number of student contact hours, the start/end date of course blocks and the expected number of places for female, scholarship, SIS and existing workers/new entrant students. It should also be accompanied by a rationale for the proposed courses and explanation of the expected outputs and development benefits, including:

(I) evidence of sufficient industry demand;

(II) a proposed delivery model for each new course or improvements in the delivery of existing courses;

(III) cost efficiencies in recognised prior learning processes and whether new entrants can be accommodated;

(IV) availability of work placements by course; and

(V) target numbers of fee paying and scholarship students and equity/access targets (gender, SIS and disabilities).

(vii) as required, a change frame indicating proposed changes to the contract for consideration.

(b) Six-monthly progress reports between each Annual Report/Plan. The six-monthly progress report covers the period 01 January – 30 June and is to be submitted to AusAID by 15 July. It will include: 

(i) a summary of enrolment and graduate numbers disaggregated by course, campus, country of origin, and gender and scholarship status. Data should be provided for the previous period and cumulative since contract commencement; 
(ii) a summary of scholarship applications, awards offered, deferrals, withdrawals, extensions, suspensions and terminations;
(iii) a summary of ELLN bridging programs conducted during the period (and cumulative since contract start);

(iv) a summary of FFS activities, progress to date and future fee for service opportunities; 

(v) major procurements in the period;

(vi) a table indicating progress of activities implemented, or scheduled to have been implemented, in the past quarter, including progress in accordance with the Annual Training Profile; and

(vii) a section monitoring and reviewing risks and assumptions (including evaluation of new risks as they emerge with recommendations for their management/treatment).

(c) Quarterly Financial Reports – are due to AusAID within two (2) weeks of the end of each quarter. Quarterly Financial Reports are to include the following:

(i) total expenditure under this Contract to date;

(ii) disaggregated expenditure under this Contract to date identifying all categories of expenditure including the Management Fees component and Reimbursable items;

(iii) income from tuition fees, FFS activities for the previous quarter; 

(iv) acquittal of total expenditure for the previous quarter; and

(v) forward expenditure and expenses by category for the next quarter, including details and estimated costs of proposed courses and an updated annual expense projection.

(d) Risk Management Plan and Performance Assessment Framework will be revised and updated in line with annual and periodic program reporting processes, and in any case annually and annexed to the Annual Plan. Revision of the Risk Management Plan and PAF will be agreed by AusAID. 

(e) Exception Reports are to be provided as soon as possible after critical APTC issues, such as fraudulent activities, scholarship scheme issues and unfavourable media reports are identified and need to be brought to the prompt attention of AusAID. They will incorporate proposed responses to issues that have emerged and will not be seen as progress reports.
(f) Other APTC procedures and policies will be reviewed and updated as required, or at the very least annually. 

(g) Completion Report - will be submitted three (3) months before the Contract End Date. The Completion Report should be prepared in accordance with any written instructions that may be issued by AusAID and address the following issues:

(i) confirm that the APTC has been implemented according to the processes specified;

(ii) examine actual achievements against the APTC goal and objectives;

(iii) provide a full reconciliation and acquittal of funds;

(iv) document lessons learned from the APTC; and

(v) advise of any implications from Stage II for future Stages of the APTC.

16.3 All reports must: 
(a) be provided in accordance with the specification under Standard Condition Clause X (Reports);

(b) be accurate and not misleading in any respect;

(c) be prepared as directed in writing by AusAID;

(d) allow AusAID to properly assess progress under the Contract;

(e) be provided in the format, number and on the media approved or requested by AusAID;

(f) not incorporate either the AusAID or the Contractor’s logo; 

(g) be provided at the time specified in this Schedule; and

(h) incorporate sufficient information to allow AusAID to monitor and assess the success of the Services in achieving the objectives of AusAID’s Gender and Development Policy.

Annex A

LIST OF KEY STAGE I APTC POLICIES AND PROCEDURES

This is not an exhaustive list. These policies will be updated by the Contractor in the Transition Period or prior to December 2011 as required to reflect the Stage II design and implementation of the Scope of Services.

	Advisory Group terms of reference and membership list 
	Risk Management Plan 

	Student database overview/manual 
	Natural Disaster Emergency Procedures 

	Draft Fee-for-Service Policy 
	Data Management Protocols 

	APTC Communication Plan/ Strategy
	School Student Rules 

	Assets register
	APTC Code of Conduct 

	Student Pastoral Care Plan 
	Student Induction Program

	HIV/AIDS Mainstreaming Strategy/ Framework
	Disabilities Policy/Action Framework



	APTC Marketing Plan
	APTC Gender Access and Equality Strategy/ Policy Framework 

	Graduation Policy and Schedule
	 Child Protection Policy 

	Grievance and Appeal Procedures
	

	Scholarships Policy and Procedures Manual 
	


Annex T: APTC Stage II Basis of Payment

schedule 2 - BASIS OF PAYMENT

AUSTRALIA-PACIFIC TECHNICAL COLLEGE 
Phase II

17. TOTAL AMOUNT

17.1 The maximum amount payable by AusAID to the Contractor shall not exceed the sum of A$XXXX plus GST, if any up to a maximum of A$XXX.

17.2 AusAID shall not be liable for any Costs or expenditure incurred by the Contractor in excess of this amount. 

18. SUMMARY OF PAYMENTS

18.1 Subject to the provisions of this Basis of Payment, AusAID will pay the Contractor the following Fees, Costs, and Milestone Payments (up to the maximums specified in 
Table 1):

(a) APTC Management Fee comprising:

(i) APTC Management Fee, including administrative costs, overheads and profit - Clause 3;

(b) Reimbursable Costs comprising: 

(i) Capital and Establishment Costs, including lease costs, construction and refurbishments costs – Table 3;
(ii) APTC Personnel Costs, including Trainers/Assessors, Tutors, Administrative and Management Personnel – Annex 1, Table 3, 4 and 5 and Clause 5; 

(iii) Direct Training Delivery Costs, including capital and consumable costs relating to training delivery, specific training programs and feasibility studies – Table 3; and.

(c) Scholarships Funding – provision of scholarships in accordance with the most recent AusAID approved policy, Clause 7.

Table 1: Maximum Contract Amount 

	Costs and Fees
	Summary of Estimated Costs
exclusive of GST

A$

	APTC Management Fee 

	70% of APTC Management Fee: reimbursable on prorated monthly basis 
	

	30% of APTC Management Fee: payable on milestones 
	

	Reimbursable Costs 

	Capital and Establishment Costs
	

	Corporate and Student Support (CSS) Costs
	

	Direct Training Delivery Costs 
	

	Personnel: CSS Management/Administrative and Trainers/Assessors and Tutors
	

	Scholarship Funding 

	Scholarships 
	

	TOTAL 
	


19. APTC MANAGEMENT FEE

19.1 The maximum amount payable by AusAID to the Contractor for APTC Management Costs is up to A$XXXXX plus GST up to a maximum of A$XXXX. 

19.2 The Annual APTC Management Fee will be paid as follows:

(a) 70% reimbursed on a monthly pro-rata basis in accordance with Table 2; and 

(b) 30% on satisfactory completion of milestones in accordance with Table 6.

Table 2: Annual APTC Management Fee (Tenderers to propose)

	Annual APTC Management Fee
	2010/11

	2011/12
	2012/13
	2013/14
	2014/15

	
	
	
	
	
	


19.3 The APTC Management Fee is fully inclusive of, but not limited to, the following Contractor costs:

(a) All management support costs for all nominated personnel;
(b) all Contractor and any consortium member administrative and Head Office staff and overheads; 

(c) in-country based preparation (pre mobilisation), personnel briefings in Australia or in-country for all Personnel;

(d) head office and any consortium travel costs associated with management and oversight of the APTC contractual obligations; 

(e) health, medivac, worker’s compensation, liability and indemnity insurance;

(f) financial management costs and financing costs, if any

(g) Freight and other finance costs, associated with any subcontracting and procurement of goods and services

(h) all domestic and international communications costs;

(i) corporate overheads and all aspects of profit, including commercial margins for all personnel;

(j) all legal costs;

(k) taxation, as applicable;

(l) costs of complying with the Contractor’s reporting and management obligations under the Contract;

(m) costs associated with maintaining AQTF compliance of APTC courses;

(n) security costs for all personnel;

(o) allowances for, risks and contingencies; and

(p) all escalators for costs for the term of the Contract. 

but exclusive of

(q) any Australian Goods and Services Tax (GST) as referred to in Clause X.X of the Standard Contract Conditions.

20. MILESTONE PAYMENTS

20.1 Milestone Payments shall be paid progressively, within thirty (30) days of the satisfactory achievement of milestones and the acceptance by AusAID in writing of achievement of milestones and as specified in Table 6.

20.2 The criteria for “satisfactory completion” of an identified output will be as specified in Table 6 as the “verifiable indicators”. 

20.3 Where a Milestone Payment is to follow acceptance of a report, AusAID shall not be obliged to make payment until all of the outputs to be achieved by the Contractor in the period covered by the report have been achieved. 

20.4 It is AusAID corporate practice to inform Contractors as soon as reasonably possible, and in any case within 30 days of receipt of notice of the completion of an identified output or provision of a report whether or not that output or report is accepted. 
21. REIMBURSABLE COSTS 

21.1 The maximum amount payable by AusAID to the Contractor for Reimbursable Costs is up to A$XXXXX plus GST up to a maximum of A$XXXX. 

21.2 Reimbursable Costs incurred for approved items detailed in Table 3 will be paid by AusAID to the Contractor on a monthly basis and subject to a correctly rendered invoice.

21.3 Specified upper limits for each reimbursable component shall not be exceeded without prior written approval from AusAID. When expenditure reaches 80% of the limits for each component specified in Table 3, the Contractor will advise AusAID of the remaining commitments and whether the upper limits are likely to be exceeded and, if so, provide justification.

21.4 The Contractor may vary the sums assigned against individual line items within the Component Upper Limit in Table 3. Changes to the value of line items, within Component Limits, will not require a contract amendment. 

21.5 Reimbursable components include: 

(a) Corporate and Student Support; 

(b) Capital and Establishment Costs;

(c) Direct Training Delivery Costs; and 

(d) Personnel Costs, including long and short-term CSS management/administrative and training personnel.

Long Term Personnel 

21.6 Classification levels for teaching, tutorial and administrative positions at the APTC will be determined in accordance with the work level standards and corresponding salary levels in Annex 1. 
21.7 If personnel are absent for any period, aside from the periods of leave permitted, the monthly salary rate for Long Term Personnel will be varied based on the following formula:

Adjusted monthly = 
(no. of worked days) x monthly fee

payment 

(no of working days in relevant month)

21.8 The Monthly Salary Rates, as payable directly to the Contractor to, or on behalf of, the personnel, are fully inclusive of: 

(a) all personnel related taxes and levies incurred in Australia or overseas; 

(b) all statutory salary on-costs, if any, as appropriate;

(c) approved leave periods;

(d) superannuation levy, if any, as appropriate;

but exclusive of: 

(e) any profit, overheads, administration or management fee or any other mark-up on the part of the Contractor; 

(f) all allowances as defined in Clause 5.16 below and

(g) any Australian Goods and Services Tax (GST) as referred to in Clause 21 of the Standard Contract Conditions. 
21.9 Allowances will be provided for long term personnel only. Allowances for long term personnel will vary given individual circumstances, in particular if someone is engaged locally or if the individual is accompanied. Given the circumstances of each personnel an allowance will be calculated based on the rates provided in Annex 1. 

Short Term Personnel 

21.10 Daily Fee Rates listed in Annex 1 will be payable on actual days worked. Daily Fee Rates are based on an eight (8) hour working day. Any additional work undertaken within any one twenty-four (24) hour period shall not be claimed.

21.11 The Daily Fee Rates, as payable directly to the Contractor to, or on behalf of, the personnel, are fully inclusive of: 

(a) all personnel related taxes and levies incurred in Australia or overseas; 

(b) all statutory salary on-costs, if any, as appropriate;

(c) superannuation levy, if any, as appropriate;

but exclusive of: 

(d) any profit, overheads, administration or management fee or any other mark-up on the part of the Contractor; 

(e) all per diem and accommodation rates as defined in Clause 15.5 below and

(f) any Australian Goods and Services Tax (GST) as referred to in Clause 21 of the Standard Contract Conditions. 
21.12 Short Term Personnel, providing Services away from their home base, will be provided with a per diem and accommodation rate for the duration of their Services. Annual per diem and accommodation rates for Short Term Personnel are provided at Annex 1. This Table will be updated annually by AusAID on the anniversary of the Contract Start Date. 

21.13 An estimate of Personnel Costs will be included in each Annual Work Plan for AusAID approval. 
Leave 

21.14 Four (4) weeks leave per annum will only be accrued for Long Term Personnel. Short Term Personnel will not be entitled to leave. Accrual of leave during the assignment shall be taken within each twelve (12) month period of the personnel’s commencement date and in the relevant year it falls due. Except Locally Engaged Personnel for whom the local national labour laws and awards shall apply. 

Allowances

21.15 Allowances will be provided for long term staff only based on Clause 5.16 below. Short term staff, providing Services away from their home base, will be provided with a per diem and accommodation rate for the duration of their Services. Annual per diem and accommodation rates per country for short term staff and long term personnel on work related travel are provided at Annex 1.

21.16 Allowances for long term staff will vary given individual circumstances, in particular if someone is engaged locally or if the individual is accompanied. Given the circumstances of each staff member an allowance will be calculated based on the rates provided in Annex 1. 

Escalation of Personnel Salary 

21.17 A fixed escalation rate of [X% as agreed in preferred tenderer’s proposal] will be applied to all Long and Short Term Personnel Salary Rates as of 1 July each year of the contract period.

21.18 The application of this rate will be applied to the 2010/11 rate, in the first instance, and then applied annually as described above. 
21.19 The escalation rate will be applied to salary costs in Annex 1 and Table 4 and 5 below. 

22. STUDENT FEES AND OTHER APTC REVENUES

22.1 Student Fees, Fees for Service and Other APTC Revenues collected are to be managed by the Contractor and expended in accordance with the relevant revenue policy. 
22.2 Revenues should be deposited in a sub-account titled ‘APTC Revenues’ and collection and expenditure should be declared in the relevant Quarterly Financial Report and the Annual Report. 

22.3 If, upon premature termination of the Contract or at the end of the Contract, collected APTC Revenue remains, the Contractor shall dispose of these funds (including any accrued interest) as directed by AusAID in writing.

23. SCHOLARSHIPS FUNDS

23.1 The maximum amount payable by AusAID to the Contractor for Scholarships is up to a maximum of A$16,800,000 plus GST up to A$1,680,000.

23.2 Scholarship funds will be used in accordance with the APTC Scholarships policy as updated from time to time and the relevant Annual Work Plan. Scholarship costs will be reimbursed on a monthly basis on receipt of a correctly rendered invoice. 

24. CLAIMS FOR PAYMENT

24.1 The Contractor’s tax invoices must be submitted when due pursuant to this Schedule in a form identifiable with the Services and in accordance with Standard Conditions Clause headed Payment in the Contract.

24.2 All tax invoices must include a certification by the proper officer of the Contractor or their delegate:

(a) that the invoice has been correctly calculated; and

(b) that the Services included in it have been performed in accordance with the Contract. 

24.3 All claims for payment must be made out to:
Chief Finance Officer
Australian Agency for International Development

GPO Box 887
CANBERRA ACT 2601

24.4 Tax invoices should be sent to the above address. Alternatively, AusAID will accept electronic tax invoices. These can be sent to accountsprocessing@ausaid.gov.au cc. Agreement Manager.

24.5 Invalid tax invoices will be returned to contractors. Information on what constitutes a valid tax invoice can be found at http://www.ato.gov.au/business/content.asp?doc=/content/50913.htm 

Table 3: Reimbursable Costs (Tenderers to confirm and add as required)
	Reimbursable Costs 
	Upper limits

2010/11 to 2013/14

(A$)

	1
	Capital and Establishment Component 

	
	Civil works (training venues)
	3,280,000

	
	Machinery, equipment and vehicles (training venues) 
	2,080,000

	
	Feasibility Studies (refer to Schedule 1 Clause X.X) 
	440,000

	
	New course design, such as ELLN bridging, APTC to work, customisation of new courses
	585,000

	
	APTC Management Information System [tenderers to cost based on high-level requirements in APTC DD Annex M] 
	[tenderer’s to include]

	
	[tenderer to add items as required]
	[tenderer’s to include]

	
	Component Sub Total 
	[tenderer’s to include]

	2
	Corporate and Student Support Component 

	
	CSS Management and Administrative Personnel Travel 
	1,050,000

	
	Office leases and utilities, including Fiji, Samoa, Vanuatu, PNG (and the Solomon Islands if approved) 
	395,000

	
	Vehicle Running Costs such as rental, maintenance and fuel 
	410,000

	
	Office Furniture and Equipment 
	350,000

	
	Office Consumables 
	110,000

	
	IT services
	165,000

	
	Official Functions 
	110,000

	
	CSS representation in Kiribati, Tonga and other short term assistance in Non-Campus Countries
	475,000

	
	Staff Training and professional development 
	455,000

	
	Marketing and Publications
	385,000

	
	M&E and Labour Market Intelligence Costs 
	40,000

	
	Alumni Network
	120,000

	
	APTC Advisory Group 
	285,000

	
	APTC to work program 
	480,000

	
	ELLN bridging program 
	635,000

	
	[tenderer to add items as required]
	[tenderer’s to include]

	
	Component Sub Total
	[tenderer’s to include]

	3 
	Direct Training Delivery Component

	
	Transport and Travel of training staff
	7,410,000

	
	Rental and hiring charges (training venues) 
	5,140,000

	
	Other costs associated with training such as course materials, small equipment, student and work place safety equipment etc 
	11,685,000

	
	[tenderer to add items as required]
	[tenderer’s to include]

	
	Component Sub Total
	[tenderer’s to include]

	4 
	Personnel 

	
	Administrative and Management Personnel Costs (including fees, allowances, all personnel related taxes and levies incurred in Australia or overseas, approved leave periods, superannuation, if any, and as appropriate) in accordance with Tables 4 and 5.
	

	
	Trainers/Assessors and Tutor Costs (including fees, allowances, all personnel related taxes and levies incurred in Australia or overseas, approved leave periods, superannuation, if any, and as appropriate) in accordance with Annex 1. 
	41,910,000

	
	Component Sub Total
	[tenderer’s to include]

	TOTAL UPPER LIMIT 
	[tenderer’s to include]


Table 4: CSS Management and Administrative Personnel (Long Term Personnel Costs 2010/11 and 2011/12)* (Tenderers to propose)
	Position
	Name
	Base Salary
	Total Base Salary

(A$)
[(c) x (d)]
	Travel (mob/demob)*
	Total Travel Costs

(A$)

[(f) x (g)]
	Allowance (Monthly Rate)
	Total Allowances

[(c) x (i)]
	Total Costs (A$)

[(e) + (h) + (j)]

	
	
	No. Mths
	Mthy Rate
	
	No. flights
	Flight Costs (A$)
	
	
	
	

	(a)
	(b)
	(c)
	(d)
	(e)
	(f)
	(g)
	(h)
	(i)
	(j)
	(k)

	Management Personnel 

	APTC CEO
	
	
	
	
	
	
	
	
	
	

	School Director- Automotive, Construction and Electrical 
	
	
	
	
	
	
	
	
	
	

	School Director- Tourism and Hospitality 
	
	
	
	
	
	
	
	
	
	

	School Director - Health and Community Services 
	
	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	
	
	

	[add/ delete rows as required]
	
	
	
	
	
	
	
	
	
	

	Administrative Personnel 

	[add/ delete rows as required]
	
	
	
	
	
	
	
	
	
	

	SUB TOTAL
	
	SUB TOTAL
	
	SUB TOTAL
	
	

	TOTAL
	


* Annex 1 has been used as the basis for the provision of costings in this Table.

** Return economy flight from home residence to Nadi, Fiji.

Table 5: CSS Management and Administrative Personnel (Short Term Personnel Costs 2010/11 and 2011/12)* (Tenderers to propose)
	Position
	Name
	Base Salary
	Total Base Salary

(A$)

[(c) x (d)]
	Travel (mob/demob)**
	Total Travel Costs

(A$)

[(f) x (g)]
	Per Diem (Daily Rate)
	Accommodation (Nightly Rate)
	Upper Limit Allowances

[(d) x ((i) + (j))]
	Total Costs (A$)

[(e) + (h) + (k)]

	
	
	No. Days
	Daily Rate
	
	No. rtn flights
	Flight Costs (A$)
	
	
	
	
	

	(a)
	(b)
	(c)
	(d)
	(e)
	(f)
	(g)
	(h)
	(i)
	(j)
	(k)
	(l)

	Management Personnel 

	[add/ delete rows as required]
	
	
	
	
	
	
	
	
	
	
	

	Administrative Personnel 

	[add/ delete rows as required]
	
	
	
	
	
	
	
	
	
	
	

	SUB TOTAL 
	
	SUB TOTAL
	
	SUB TOTAL 
	
	

	TOTAL
	


* Annex 1 has been used as the basis for the provision of costings in this Table.

** Return economy flight from home residence to Nadi, Fiji

Table 6: Milestone Payments

	Milestone
	Indicative Date of achievement 
	Description
	Maximum 
	Verifiable Indicator
	Milestone Amount

	
	
	
	Value A$
	
	

	1
	Jan 2011
	Annual Report/Plan 
	
	Document accepted by AusAID in writing.
	

	2
	July 2011
	Six Monthly Progress Report
	
	Document accepted by AusAID in writing.
	

	3
	Jan 2012
	Annual Report/Plan 
	
	Document accepted by AusAID in writing.
	

	4
	July 2012
	Six Monthly Progress Report
	
	Document accepted by AusAID in writing.
	

	5
	Jan 2013
	Annual Report/Plan 
	
	Document accepted by AusAID in writing.
	

	6
	July 2013
	Six Monthly Progress Report
	
	Document accepted by AusAID in writing.
	

	7
	Jan 2014
	Annual Report/Plan 
	
	Document accepted by AusAID in writing.
	

	8
	July 2014
	Six Monthly Report/Progress Report
	
	Document accepted by AusAID in writing.
	

	9
	Jan 2015
	Annual Report 
	
	Document accepted by AusAID in writing.
	

	10
	March 2015
	Activity Completion Report
	
	Document accepted by AusAID in writing.
	

	 
	 
	Total
	
	 
	 


Annex 1

PERSONNEL FEES FOR LONG TERM PERSONNEL

Work Level Standards

Work Level Standards are based on the role and context in which services will be delivered. They also take account of representational activities, a personnel’s specific and relevant management responsibilities, skills, understanding, knowledge, experience and qualifications expected to undertake the specified duties. 

[Tenderers to provide a description of work level standards which will correlate with the salary bands provided below]

Table A: Long Term Personnel Salary Bands (Tenderers to propose)

	Position/Job Title and Salary Bands
	Work Level Standard
	Monthly Salary Bands

(A$)

2011/12

	
	
	Minimum
	Maximum 

	Training Personnel 
	
	
	

	 [insert/ delete rows as required]
	
	
	

	Management/Administrative Personnel 
	
	
	

	 [insert/ delete rows as required]
	
	
	


Table B: Allowances for Long Term Personnel in 2011/12 (Tenderers to propose)

	Allowance item 
	Fiji
	Samoa
	Vanuatu
	PNG


	
	Monthly Rates

	Housing (incl. utilities, security and house help)
	
	
	
	

	[insert additional allowance items as required]
	
	
	
	

	
	
	
	
	

	
	Once off payments

	Mobilisation Allowance, payable on signing of personnel contract (incl. hotel accommodation up to two (2) weeks on arrival, shipment and storage of goods)
	
	
	
	

	Demobilisation Allowance, payable two (2) month prior to departure (incl. hotel accommodation up to two (2) weeks on return, shipment of goods and storage of goods) 
	
	
	
	

	[insert additional allowance items as required]
	
	
	
	

	
	
	
	
	


Table C: Short Term Personnel Salary Bands (Tenderers to propose)

	Positions and Salary Bands
	Daily Salary Bands (A$)

2011/12

	
	Minimum
	Maximum 

	Training Personnel 
	
	

	 [insert/ delete rows as required]
	
	

	Management Administrative Personnel 
	
	

	 [insert/ delete rows as required]
	
	


Table D: Short Term Personnel: Allowances (AusAID still to confirm rates)
	Position
	2011/12 (A$)

	
	Accommodation
 (per night) 
	Per Diem

(per day)

	Cook Islands
	
	

	Federated States of Micronesia 
	
	104

	Fiji 
	142
	77

	Kiribati 
	100
	82

	Marshall Islands
	
	

	Nauru 
	100
	91

	Niue
	
	

	Palau 
	
	

	Papua New Guinea
	450
	137

	Samoa
	264
	131

	Solomon Islands
	218
	104

	Tonga
	134
	99

	Tuvalu 
	
	

	Vanuatu
	262
	143

	New Zealand – Auckland 
	191
	121

	New Zealand - Wellington
	190
	121

	Australia - Adelaide
	171
	109

	Australia – Brisbane
	231
	117

	Australia – Canberra
	180
	131

	Australia – Darwin
	115
	101

	Australia – Hobart
	113
	101

	Australia - Melbourne
	195
	128

	Australia – Perth 
	192
	129

	Australia – Sydney 
	    236
	137


� 	Noting that there will be circumstances where Diploma level qualifications are also delivered.


� 	Since the original allocation, APTC funding has been rolled into AusAID’s baseline funding at the current level, assuring that the APTC will continue to be funded beyond June 2011 at the same level as that for 2010-2011.


� 	Pacific Islands Forum, Forum Communiqué 24‐25 October 2006.


� 	Under the General Agreement on Trade in Services (GATS) framework, Mode 4 refers to the movement of persons across borders for the purpose of supplying services. It is typically oriented to mobility of professionals and inter-company transfers. In many cases PIC professionals with recognised qualifications are already able to gain access to the Australian, New Zealand and other job markets. The type of agreement that may be of most interest to the majority of PICs is one that covers those without formal qualifications (so-called ‘unskilled workers), or various categories of so-called ‘semi-skilled’ workers.


� 	The Hon. Simon Crean, MP, Ministerial Statement, ‘Commencement of PACER Plus Negotiations’, 18 August 2009.


� 	Pacific Islands Forum (2009) Pacific Education Development Framework (PEDF) 2009-2015.


� 	Noting that there will be some circumstances where Diploma level qualifications are also delivered such as the currently offered Diploma in Children's Services and the Diploma of Community Welfare Work and the proposed Diploma of Training and Assessment.


� 	The conditions under which the APTC could or should make a transition from an Australian development program to a regional training institution will be a major strategic issue in the coming years but is not one to be investigated in the Stage II design.


� 	Such as World Bank Project Appraisal Document for its TVET project in India available at � HYPERLINK "http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2007/05/16/000020953_20070516114954/Rendered/PDF/39697.pdf" ��http://www-wds.worldbank.org/external/default/WDSContentServer/WDSP/IB/2007/05/16/000020953_20070516114954/Rendered/PDF/39697.pdf�. (p. 73); and The Allen Consulting Group (2008) ‘The Complete Package, The Value of TAFE NSW’ available at � HYPERLINK "https://www.tafensw.edu.au/news/the-complete-package/The-Complete-Package.pdf" ��https://www.tafensw.edu.au/news/the-complete-package/The-Complete-Package.pdf� .


� 	The consultant will determine which efficiency indicator best reflects the efficiency of the APTC or whether both (or others) should be included. The Australian Department of Employment, Education and Workplace Relations reports against the indicator ‘Government recurrent expenditure per publicly funded annual hour’ as a measure of VET efficiency. (See DEEWR [2009] ‘Annual National Report of the Australian Vocational Education and Training System 2008’). The Australian Productivity Commission reports against the indicator ‘Real government recurrent expenditure per publicly funded load pass’ as an indicator of VET efficiency. This is defined as the cost to government of each successfully completed VET module or unit of competency, i.e. the cost per successfully achieved output (See Productivity Commission [2010] ‘Report on Government Services 2010’).


� 	Targeted sectors for Stage 1 of the APTC are automotive, manufacturing, construction, electrical, tourism, hospitality, health, and community services.


� 	Copies of the full report are available on AidWorks under the attachments for Initiative INH016 – Australia Pacific Technical College.


� 	Pacific Islands Forum (2009) Pacific Education Development Framework (PEDF) 2009-2015


� 	National training institution partners are the National University of Samoa – Institute of Technology, Port Moresby Technical College, Vanuatu Institute of Technology, Training and Productivity Authority of Fiji and Vanuatu Ministry of Education. Industry training partners are ASCO Motors, Ela Motors Port Moresby, Hastings Deering Port Moresby, Ok Tedi Mining Limited (Tabubil).


� 	See recommendations and sections of the MTR.


� Asian Development Bank (2008). Skilling the Pacific.


� AusAID (2007). Gender equality in Australia’s aid program – why and how. 


AusAID (2006). Australian aid: Promoting growth and stability. A White Paper on the Australia Government’s overseas aid program. 


� Asian Development Bank (2006). Country Gender Assessment, Republic of the Fiji Islands 


� APTC (2007) HIV and AIDS Framework Policy and Strategy, 2007-2011. 


�UNAIDS (2007). AIDS Epidemic Regional Summary: Oceania. http://data.unaids.org/pub/Report/2008/jc1533_epibriefs_oceania_en.pdf.


� Asian Development Bank (2008). Skilling the Pacific 


� 	Pacific Islands Forum (2009). Pacific Education Development Framework (PEDF) 2009-2015


� 	Australia, Cook Islands, Fiji, New Zealand, PNG, Samoa, Solomon Islands, Tonga & Vanuatu. See �HYPERLINK "http://www.oecd.org/document/22/0,3343,en_2649%20_3236398_36074966_%201_1_1_1,00.html"�http://www.oecd.org/document/22/0,3343,en_2649 _3236398_36074966_ 1_1_1_1,00.html�


� 	PNG, for example, has localised the Paris Declaration in its PNG Commitment on Aid Effectiveness, agreed between the Government of PNG and its Development Partners.


� 	EC has also provided support in the past to the Kiribati (formerly Tarawa) Institute of Technology 


� AusAID (2010). Pacific Education and Training Framework. Draft version June 2010.


� 	Warner (2008), p.167.


� 	ADB-Commonwealth Secretariat (2005). Toward a new Pacific regionalism: an Asian Development Bank-Commonwealth Secretariat joint report to the Pacific Islands Forum Secretariat.


� 	The Hon. Simon Crean, MP, Ministerial Statement, ‘Commencement of PACER Plus Negotiations’, 18 August 2009.


� 	Under the General Agreement on Trade in Services (GATS) framework, Mode 4 refers to the movement of persons across borders for the purpose of supplying services. It is typically oriented to mobility of professionals and inter-company transfers. In many cases PIC professionals with recognised qualifications are already able to gain access to the Australian, New Zealand and other job markets. The type of agreement that may be of most interest to the majority of PICs is one that covers those without formal qualifications (so-called ‘unskilled workers), or various categories of so-called ‘semi-skilled’ workers.


� Demobilisation to same point of mobilisation.


� To the extent that average course lengths are shorter than this these figures are an over-estimate. However, to the extent that those who enrol fail to graduate, these figures under-estimate the cost of producing a graduate.


� World Bank (2007).


� Refer to Clause 8.6 and 8.9 for further considerations in leasing training space. 


� It is assumed that the transition period will fall in 2010/11. At this stage AusAID is working towards a mobilisation date of 01 March 2010. This is subject to negotiation. 


� Accommodation rate is reimbursed at lesser of actual cost incurred or up to the rates provided in Table D.


� A Per Diem is a non acquittal daily rate for breakfast, lunch, dinner and daily incidentals.






