## Sheet1 (hidden)
|  | 11 |  | 2012 | [11 empty] | 2013 | [11 empty] | 2014
|  |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Component I: Building capacity for budget execution | bar: Q2 A to Q4 D
Inception Phase | bar: Q2 A to Q2 J
Sub-component 1.1: | Building capacity for budget execution in key service delivery ministries | bar: Q3 J to Q3 S
Output 1.1.1: | Financial management processes are streamlined and based upon clear policies. | bar: Q3 J to Q4 N; Q2 M to Q3 S; Q2 A to Q2 J
Output 1.1.2: | Policy and planning officers are equipped with a clear and simple framework for development project design and implementation | bar: Q3 J to Q1 J; Q2 M to Q1 J; Q2 M to Q3 S
Output 1.1.3: | Finance officers are equipped with a clear and simple framework for development of procurement and financial plans in line with PFM best practice | bar: Q3 S; Q4 D to Q2 A; Q2 J; Q3 S; Q4 N to Q1 M; Q2 J; Q3 S
Output 1.1.4: | Finance officers and program managers are equipped with tools for monitoring and analysis of budget execution data, in line with financial management standards | bar: Q3 J to Q4 D; Q1 F to Q4 D; Q1 F to Q3 S
Output 1.1.5: | Ministry Internal Budget Committee equipped with a framework for regular meetings and relevant decision-making | bar: Q3 J to Q3 A; Q4 O to Q4 D; Q1 F to Q2 A; Q3 J; Q3 S to Q4 N; Q1 F to Q2 A; Q3 J; Q3 S
Sub-component 1.2: | Strengthening Budget execution Directorate key Sectors in Ministry of Finance | bar: Q3 J to Q3 S
Output 1.2.1: | Budget Execution officers are equipped with the tools necessary to enable them to implement budget process, as defined by budget policy officers | bar: Q3 J to Q3 S
Output 1.2.2: | Budget Execution officers support work of the Internal Budget Committees in the targeted line ministries | bar: Q3 J to Q3 A; Q4 O to Q4 D; Q1 F to Q2 A; Q3 J; Q3 S to Q4 N; Q1 F to Q2 A; Q3 J; Q3 S
Evaluation Phase | bar: Q4 O to Q4 D
Component II: Streamlining procurement processes
Sub-component 2.2: | Capacity building in the line ministries
Refer to: “Project Paper on a Proposed ARTF Grant in the Amount of US$ 73 mil to the GIRoA for a Second Public Finance Management Reform Project (PFMR II)”, of May 25, 2011, Annex 2: Results Framework and Monitoring
Component III: Facilitating accounting and budget process in Uruzgan
Project review | bar: N to D
Contract amendemeds | bar: Q1 J
Adisers mobilization | bar: Q1 F to Q1 M
Sub-component 3.1: | Strengthening Provincial Budget Unit, Kandahar regional office | bar: Q2 A to Q4 D
Official training for the regional office in the Minitry of Finance in Kabul | bar: Q2 A to Q2 J
Output 3.1.1: | Finance officers in the key service delivery directorates and Moustufiat understand key budget processes as per Ministry of finance’s policies and guidelines | bar: Q3 J to Q4 D
Official training for the regional office in the Minitry of Finance in Kabul | bar: Q2 A to Q2 J
Sub-component 3.2: | Facilitating the budget process in key line directorates | bar: Q2 A to Q4 D
Output 3.2.1: | The finance officers and management in the key line directorates are equipped with tools for budget preparation, execution and monitoring, in with financial standards | bar: Q3 J to Q4 D
Inception Phase

## Long version
Annex II: Implementation Schedule
|  | 1391 | [8 empty] | 1392 | [11 empty] | 1392 | [11 empty] | 1394
|  | 2012 | [5 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
|  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3
|  | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
Component I: Building capacity for budget execution
Inception Phase: | Identify the budget execution framework that is most likely to be used in the long-term, assess indicators of success that will drive the right kind of capacity building and develop consensus will all the stakeholders | bar: Q3 J to Q3 S
Outcome 1.1: | Building capacity for budget execution in key service delivery ministries | bar: Q3 S to Q3 J
Project planning and design activities | bar: Q3 S to Q3 J
Design templates and guidelines for project design and appraisal documents development | bar: Q3 S to Q4 D
Develop and deliver generic training in developing project design documents - Concept Note, Pre-Feasibility study, Appraisal document and Implementation plan | bar: Q4 D to Q1 J
Conduct training need assessment and feed into training strategy | bar: Q1 J to Q1 F
Develop and deliver customized training in developing project design documents - Concept Note and Pre-Feasibility study | bar: Q1 M to Q2 A
Provide on-the-job support to Policy and Planning department staff in developing concept notes and pre-feasibility studies for 1393 BC2 budget submission | bar: Q2 A to Q2 M
Develop and deliver training in developing project design documents -Appraisal document and Implementation plan | bar: Q3 A to Q3 S
Provide on-the-job support to Policy and Planning department staff in developing appraisal documents and implementation plans for proposed development projects for 1393 BC2 budget submission | bar: Q3 S to Q4 N
Assess quality of the submissions and if required revise templates and guidelines | bar: Q4 D to Q1 J
Conduct training need assessment and identify any gaps | bar: Q1 F
Develop and deliver refresher course training in development of Concept notes and Pre-feasibility studies, if required | bar: Q2 A
Supervise and provide on-the-job support to Policy and planning officers for development of the Concept notes and Pre-feasibility studies for 1394 BC1 budget submission | bar: Q2 A to Q2 M
Develop and deliver refresher course training in development of Appraisal document and Implementation plans, if required | bar: Q3 A
Supervise and provide on-the-job support to Policy and planning officers for development of appraisal documents and implementation plans for proposed development projects for 1394 BC2 budget submission | bar: Q3 S to Q4 N
Assess quality of the submissions and if required revise templates and guidelines | bar: Q1 F to Q1 M
Monitor the work of Policy and planning department and assess capacity gaps | bar: Q2 A to Q2 J
Provide advice to management on the way forward | bar: Q3 J
Developing annual financial implementation plans | bar: Q3 S to Q3 J
Design templates and guidelines for procurement schedules and financial plans development | bar: Q3 S to Q4 O
Conduct training needs assessment and develop training strategy | bar: Q4 O to Q4 N
Develop and deliver training in developing procurement schedules and financial plans | bar: Q4 D to Q1 J
Provide on-the-job support to Finance and program departments staff in developing procurement schedules and financial plans development for 1392 budget | bar: Q1 J to Q1 M
Assess accuracy of the financial plans | bar: Q2 M to Q2 J; Q3 A to Q3 S; Q4 N to Q4 D
Support Finance department and program departments staff in revising financial plans | bar: Q2 J; Q3 S; Q4 D
Prepare lessons learned report and if required revise templates and guidelines | bar: Q4 N to Q4 D
Conduct training need assessment and identify any gaps | bar: Q4 N to Q4 D
Develop and deliver refresher course training in development of procurement schedules and financial plans, if required | bar: Q1 J
Supervise and provide on-the-job support for Finance department and program department staff for development on financial plans for 1393 budget | bar: Q1 J to Q1 M
Support monitoring of the financial plans implementation | bar: Q2 A to Q2 M; Q3 J to Q3 A; Q4 O to Q4 N; Q1 J to Q1 F
Support Finance department and program departments staff in revising financial plans | bar: Q2 J; Q3 S; Q4 D
Supervise and provide on-the-job support for Finance department and program department staff for development on financial plans for 1394 budget | bar: Q1 J to Q1 M
Assess quality of the submissions and if required revise templates and guidelines | bar: Q2 A to Q2 M
Monitor the work of Finance department and assess capacity gaps | bar: Q2 M to Q3 J
Provide advice to management on the way forward | bar: Q3 J
Streamlining administrative and financial management activities | bar: Q3 S to Q3 J
Map budgeting, allotment, procurement and payment processes in the line ministry | bar: Q2 A to Q2 M
Assess inefficiencies, recommend streamlining of processes and develop revised process maps | bar: Q2 J to Q3 J
Discuss changes with the management and obtain approval | bar: Q3 A
Develop and deliver training in the new processes for the relevant staff | bar: Q3 S to Q4 O; Q4 D to Q1 J; Q1 M to Q2 A
Provide on-the-job support to ensure implementation of the new processes | bar: Q2 A to Q3 S
Monitor the work of Finance department and assess capacity gaps | bar: Q2 M to Q3 J
Provide advice to the management on the way forward | bar: Q3 J
Strengthening budget execution analysis and monitoring functions | bar: Q3 S to Q3 J
Conduct assessment of the current practices in Finance and program departments, capacity gap and develop training strategy | bar: Q3 S to Q4 O
Develop basic tools for budget execution data analysis | bar: Q4 N to Q4 D
Develop and deliver customized training for Finance and program department staff in budget execution data assessment and analysis | bar: Q2 A to Q2 M
Provide on-the-job support to Finance and program department staff in monitoring, assessing and analyzing budget execution data | bar: Q2 M to Q2 J; Q3 A to Q3 S; Q4 N to Q4 D
Support Finance department in developing reports with analysis of budget execution, identification of issues and recommendations to address issues | bar: Q3 J; Q4 O; Q1 J
Conduct training need assessment and identify any gaps | bar: Q1 F to Q2 A
Develop and deliver refresher course training in budget execution data assessment and analysis | bar: Q2 M
Supervise and provide on-the-job support for Finance department and program department staff for budget execution data assessment and analysis | bar: Q2 J to Q1 M
Monitor the work of Finance department and assess capacity gaps | bar: Q2 M to Q3 J
Provide advice to management on the way forward | bar: Q3 J
Strengthening internal coordination and communication of budget planning and execution issues | bar: Q3 S to Q3 J
Assess current functions of Internal Budget Committee, if it exists in the line ministry | bar: Q3 S to Q4 O
Define roles and responsibilities of its members | bar: Q4 O to Q4 N
Identify counterpart in the Finance Department to preform role of a Secretary to the Internal Budget Committee
Support Finance Department in its role as a Secretariat to the Internal Budget Committee - support preparation of regular reports and updates
Support Finance Department in its role as a Secretariat to the Internal Budget Committee - ensure regular meetings are organized and relevant members participate | bar: Q4 O to Q4 N; Q1 J to Q1 F; Q2 A; Q3 J; Q4 O to Q4 N; Q1 J to Q1 F; Q2 A; Q3 J; Q4 O to Q4 N; Q1 J to Q1 F; Q2 A
Monitor the work of Internal Budget Committee and assess capacity gaps | bar: Q2 M to Q3 J
Provide advice to management on the way forward | bar: Q3 J
Outcome 1.2: | Ministry of Finance Budget Execution Directorate has increased capacity to support budget implementation in Line Ministries | bar: Q3 S to Q3 J
Strengthening budget analysis | bar: Q4 N to Q3 J
Conduct assessment of the existing policies, templates and current practices in Budget Execution Directorate; develop training strategy | bar: Q4 N to Q4 D
Design templates and tools for analysis of the budget submissions | bar: Q4 D to Q1 J
Develop and deliver generic training in conducting analysis of budget submissions - policy proposals, budget costings, cost/benefit analysis etc. | bar: Q1 F to Q1 M
Conduct post-training assessment | bar: Q1 M
Develop and deliver customized training in assessing Budget Circular No 1 submissions (baseline costing and new policy funding requests) and calculating budget ceilings | bar: Q2 A to Q2 M
Provide on-the-job support to Sector staff in analyzing budget submissions and calculating budget ceilings | bar: Q2 M to Q2 J
Develop and deliver training in assessing Budget Circular No 2 submissions (economic value, NPV, cost/benefit analysis, unit-based costing, costing assessment, budget efficiency etc.) | bar: Q3 S to Q4 O
Provide on-the-job support to Sector staff in conducting BC2 budget submission analysis | bar: Q4 O to Q4 N
Support Sectors in developing budget hearing briefs | bar: Q4 N to Q4 D
Conduct assessment of the quality of budget ceilings calculation, budget hearing briefs, assess training needs and identify any gaps | bar: Q1 F to Q1 M
If required revise tools and templates | bar: Q1 M
Conduct training need assessment and identify any gaps | bar: Q1 M
Develop and deliver refresher course training in assessing Budget Circular No 1 submissions (baseline costing and new policy funding requests) and calculating budget ceilings | bar: Q2 M
Supervise and provide on-the-job support for assessing Budget Circular No 1 submissions (baseline costing and new policy funding requests) and calculating budget ceilings | bar: Q2 M to Q2 J
Develop and deliver refresher course training in assessing Budget Circular No 2 submissions (economic value, NPV, cost/benefit analysis, unit-based costing, costing assessment, budget efficiency etc.) | bar: Q3 S
Supervise and provide on-the-job support for assessing Budget Circular No 2 submissions (economic value, NPV, cost/benefit analysis, unit-based costing, costing assessment, budget efficiency etc.) | bar: Q3 S to Q4 N
Supervise and provide on-the-job support for Sectors in developing budget hearing briefs | bar: Q4 N to Q4 D
Assess quality of the briefs and if required revise templates and guidelines | bar: Q1 M
Monitor the work of Budget Execution department and assess capacity gaps | bar: Q2 A to Q2 J
Provide advice to management on the way forward | bar: Q3 J
Strengthening budget execution processes | bar: Q3 S to Q3 J
Conduct assessment of the existing policies, templates and current practices in Budget Execution Directorate; develop training strategy | bar: Q3 S to Q4 O
Design templates and tools for development analysis of the procurement schedules and financial plans | bar: Q4 O to Q4 D
Develop and deliver generic training in developing procurement schedules and financial plans and analysis of the financial plans | bar: Q4 D to Q1 F
Provide on-the-job support to Sector staff in analyzing financial plans | bar: Q1 F to Q2 A
Assess accuracy of the financial plans (budget execution against financial plans) | bar: Q2 J to Q3 J; Q3 S to Q4 O; Q4 D to Q1 J
Support Sector staff in communicating to line ministries budget execution issues | bar: Q2 J; Q3 S; Q4 D
Support Sector staff in developing briefs for the senior management on budget execution status | bar: Q3 J; Q4 O; Q1 J
Support Sector staff in actively participating and supporting meetings of the Budget Steering Committee (Government level) | bar: Q3 J; Q4 O; Q1 J
Prepare lessons learned report and if required revise templates and guidelines | bar: Q4 D to Q1 J
Conduct training need assessment and identify any gaps | bar: Q1 J to Q1 F
Develop and deliver refresher course training in development and assessment of procurement schedules and financial plans | bar: Q1 F
Supervise and provide on-the-job support for Sector staff in monitoring financial plans implementation and analysis of budget execution against the plans | bar: Q1 F to Q1 J
Supervise and support Sector staff in actively participating and supporting meetings of the Budget Steering Committee (Government level) | bar: Q3 J; Q4 O; Q1 J
Assess effectiveness of the process and if required revise policy, templates and guidelines | bar: Q1 F to Q1 M
Monitor the work of Budget Execution department and assess capacity gaps | bar: Q2 A to Q2 J
Provide advice to management on the way forward | bar: Q3 J
Communication of budget policies with the targeted line ministries | bar: Q3 S to Q3 J
Develop strategy and procedures for regular communication between Sector staff and respective line ministries | bar: Q3 S to Q4 O
Provide training to Sector staff on effective communication and action plan for the year | bar: Q4 O
Support Sector staff in actively participating and supporting meetings of the Internal Budget committees (ministry level) | bar: Q4 O to Q4 N; Q1 J to Q1 F; Q2 A; Q3 J; Q4 O to Q4 N
Prepare lessons learned report and fine-tune approach if required; revise action plan | bar: Q4 D to Q1 J
Supervise and support Sector staff in actively participating and supporting meetings of the Internal Budget committees (ministry level) | bar: Q1 J to Q1 F; Q2 A; Q3 J; Q4 O to Q4 N; Q1 J to Q1 F; Q2 A
Monitor the work of Budget Execution department and assess capacity gaps | bar: Q2 A to Q2 J
Provide advice to management on the way forward | bar: Q3 J
Evaluation Phase: | Monitor the work of the supported ministries without providing assistance, assess remaining capacity gaps and provide any training to management on addressing the gaps | bar: Q2 J to Q3 S
Component II: Facilitating accounting and budget process in Uruzgan
Inception Phase: | Identify the budget execution framework that is most likely to be used in the long-term, assess indicators of success that will drive the right kind of capacity building and develop consensus will all the stakeholders | bar: Q3 J to Q3 S
Contract mobilization | bar: Q3 J
Official training for the regional officer and provincial budget adviser in the Ministry of Finance in Kabul | bar: Q3 A to Q3 S
Outcome 2.1: | Uruzgan Line Directorates better understand and engage in the national budget process | bar: Q4 O to Q3 J
Facilitating budget planning | bar: Q4 O to Q3 J
Assess existing processes and current practices in the line directorates | bar: Q4 O to Q4 N
Design process maps, define roles and responsibilities and develop action plans | bar: Q4 N
Develop templates and guidelines for the budget submission preparation, including templates for simplified version of project design and development | bar: Q4 D to Q1 J
Support PBU in delivery of customized training to line directorates staff in developing budget submission, based on Budget Circular No 1 requirements | bar: Q1 F to Q1 M
Provide on-the-job support to line directorates staff in developing BC1 budget submissions | bar: Q1 M to Q2 A
Support PBU in delivery of training in developing budget submission, based on Budget Circular No 2 requirements, including development of simplified version of project design documents | bar: Q3 A to Q3 S
Provide on-the-job support to line directorates staff in developing BC2 budget submission, including development of simplified version of project design documents | bar: Q3 S to Q4 O
Assess quality of the submissions and if required revise templates and guidelines | bar: Q4 D to Q1 J
Conduct training need assessment and identify any gaps | bar: Q1 J
Develop and deliver refresher course training in development BC1 submission, if required | bar: Q1 M
Supervise and provide on-the-job support for development of the BC1 budget submission | bar: Q1 M to Q2 A
Support line directorates to communicate their budget request to the central line ministries | bar: Q2 A
Develop and deliver refresher course training in development of BC2 submission including development of simplified version of project design documents, if required | bar: Q3 A
Supervise and provide on-the-job support for development of BC2 budget submission, including development of simplified version of project design documents | bar: Q3 A to Q4 O
Support line directorates to communicate their budget request to the central line ministries | bar: Q4 O
Assess quality of the submissions and if required revise templates and guidelines | bar: Q1 F to Q1 M
Communicate changes to line directorates | bar: Q1 M
Monitor the work of line directorates and assess capacity gaps | bar: Q2 A to Q3 J
Provide advice to management on the way forward | bar: Q3 J
Facilitating budget execution | bar: Q2 A to Q3 J
Map main budget execution (allotment, procurement and payment) processes in the line ministry | bar: Q2 A to Q2 M
Assess inefficiencies, recommend streamlining of processes and develop revised process maps | bar: Q2 J to Q3 J
Discuss changes with the management and obtain approval | bar: Q3 A
Develop and deliver training in the new processes for the relevant staff | bar: Q3 S to Q4 O; Q4 D to Q1 J; Q1 M to Q2 A
Provide on-the-job support to ensure implementation of the new processes | bar: Q2 A to Q3 S
Develop basic tools for budget execution data analysis | bar: Q2 A to Q2 J
Develop and deliver customized training in budget execution data assessment and analysis | bar: Q3 J to Q3 A
Provide on-the-job support to Finance officers and key line directorate staff in monitoring, assessing and analyzing budget execution data | bar: Q3 S; Q4 D
Conduct training need assessment and identify any gaps | bar: Q1 F to Q2 A
Develop and deliver refresher course training in budget execution data assessment and analysis | bar: Q2 A to Q2 M
Supervise and provide on-the-job support for Finance officers and key line directorate staff for budget execution data assessment and analysis | bar: Q2 J; Q3 S; Q4 D; Q1 M
Monitor the work of Finance unit and assess capacity gaps | bar: Q2 A to Q2 J
Provide advice to management on the way forward | bar: Q3 J
Outcome 2.2: | Ministry of Finance Provincial Budget Unit in Kandahar has increased capacity to support provincial Line Directorates | bar: Q4 O to Q3 J
Rolling-out budget planning training to line directorates | bar: Q4 O to Q3 J
Assess capacity of the line directorates to develop budget submissions | bar: Q4 O to Q4 N
Develop training strategy | bar: Q4 D
Develop and deliver generic training in budget request preparation | bar: Q4 D to Q1 F
Conduct post-training assessment | bar: Q1 F
Develop and deliver customized training to line directorates staff in developing budget submission, based on Budget Circular No 1 requirements | bar: Q1 M to Q2 A
Develop and deliver training in developing budget submission, based on Budget Circular No 2 requirements, including development of simplified version of project design documents | bar: Q3 A to Q3 S
Conduct post-training assessment and revise training strategy | bar: Q4 N to Q4 D
Deliver generic training in budget request preparation | bar: Q4 D to Q1 F
Develop and deliver customized training to line directorates staff in developing budget submission, based on Budget Circular No 1 requirements | bar: Q1 M to Q2 A
Develop and deliver training in developing budget submission, based on Budget Circular No 2 requirements, including development of simplified version of project design documents | bar: Q3 A to Q3 S
Conduct post-training assessment and revise training strategy | bar: Q4 N to Q4 D
Deliver generic training in budget request preparation | bar: Q4 D to Q1 F
Assess effectiveness of delivered capacity building program and remaining capacity gaps | bar: Q2 A to Q2 J
Provide advice to management on the way forward | bar: Q3 J
Rolling-out budget execution training to line directorates | bar: Q4 N to Q3 J
Assess capacity of the line directorates to execute budget | bar: Q4 N to Q4 D
Develop training strategy | bar: Q4 D to Q1 J
Develop and deliver generic training in budget execution | bar: Q1 F to Q2 A
Conduct post-training assessment | bar: Q2 A
Develop and deliver customized training to line directorates staff in budget implementation (execution) | bar: Q2 A to Q2 M; Q4 O to Q4 N
Conduct post-training assessment and revise training strategy | bar: Q1 J to Q1 F
Revise (if required) and deliver generic training in budget implementation (execution) | bar: Q1 F to Q1 M
Develop and deliver customized training to line directorates staff in budget implementation (execution) | bar: Q2 M to Q2 J; Q4 O to Q4 N
Conduct post-training assessment and revise training strategy | bar: Q1 J to Q1 F
Revise (if required) and deliver generic training in budget implementation (execution) | bar: Q1 F to Q1 M
Assess effectiveness of delivered capacity building program and remaining capacity gaps | bar: Q2 A to Q2 J
Provide advice to management on the way forward | bar: Q3 J
Rolling-out budget execution training to Moustufiat | bar: Q4 O to Q3 J
Assess capacity of the Moustufiat to execute budget | bar: Q4 O to Q4 N
Develop training strategy | bar: Q4 N
Develop and deliver customized training to Moustufiat staff in budget implementation (execution) | bar: Q1 J to Q1 F; Q2 J to Q3 J
Revise (as required) and deliver customized training to Moustufiat staff in budget implementation (execution) | bar: Q1 J to Q1 F; Q2 J to Q3 J
Conduct post-training assessment and revise training strategy | bar: Q4 D to Q1 J
Revise (if required) and deliver customized training in budget implementation (execution) | bar: Q1 F to Q1 M
Assess effectiveness of delivered capacity building program and remaining capacity gaps | bar: Q2 A to Q2 J
Provide advice to management on the way forward | bar: Q3 J
Evaluation Phase: | Monitor the work of the supported ministries without providing assistance, assess remaining capacity gaps and provide any training to management on addressing the gaps | bar: Q2 J to Q3 S
Component III: Streamlining procurement processes | bar: Q3 J to Q1 F
Sub-component 3.1: | Capacity building in the line ministries | bar: Q3 J to Q1 F
Delivering procurement training programs | bar: Q3 J to Q1 F
Conduct Basic, Intermediate and Advance Procurement Training Courses for Civil Servants of the procurement staff in central ministires | bar: Q3 J to Q1 F
Conduct Basic, Intermediate and Advance Procurement Training Courses for Civil Servants of the procurement staff in Moustufiats | bar: Q3 J to Q1 F
Conduct Procurement Workshop and Awareness campaign for Private Sectors | bar: Q3 J; Q2 M; Q2 M
Develop Advance Procurement Training Materials and Update the current Basic and Intermediate Training Meterials | bar: Q2 A to Q2 J; Q2 A to Q2 J
Conduct Advance Procurement Training for Procurement Controllers and Procurement Capacity Building Officers (PCBOs) | bar: Q3 J; Q2 M; Q2 M
Transfer administrative functions to ACSI | bar: Q3 S to Q1 F
Providing assistance to line ministries in preparing reliable procurement plans | bar: Q3 J to Q1 F
Coordinate, support and administrate line ministries procurement related to development and ordinary budget (as referred to Special Procurement Commission); and | bar: Q3 J to Q1 F
Facilitate procurement process in line ministries through hiring and placement of procurement specialists; | bar: Q3 J to Q1 F
Supervise preparation of procurement plans by the procurement staff in the line ministries. | bar: Q3 S to Q1 F
Supporting more complex procurement | bar: Q3 J to Q1 F
Providing on the job training for procurement staff of the line ministries | bar: Q3 J to Q1 F
Providing procurement faclitiation support to line ministries | bar: Q3 J to Q1 F
Supervise procurement staff of the line ministries in conducting complex procurement of their own | bar: Q3 J to Q1 F

## Short version (hidden)
Annex VI: Implementation Schedule
|  | 11 |  | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
|  |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2
|  | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
Component I: Building capacity for budget execution | bar: Q2 A to Q2 J
Inception Phase: | Develop the right methodologies, identify the budget execution framework that is most likely to be used in the long-term, assess indicators of success that will drive the right kind of capacity building and develop consensus will all the stakeholders | bar: Q2 A to Q2 J
Sub-component 1.1: | Building capacity for budget execution in key service delivery ministries | bar: Q3 J to Q1 M
Output 1.1.1: | Financial management processes are streamlined and based upon clear policies. | bar: Q3 J to Q4 N; Q2 M to Q3 S; Q2 A to Q2 J
Output 1.1.2: | Policy and planning officers are equipped with a clear and simple framework for development project design and implementation | bar: Q3 J to Q1 J; Q2 M to Q1 J; Q2 M to Q1 J
Output 1.1.3: | Finance officers are equipped with a clear and simple framework for development of procurement and financial plans in line with PFM best practice | bar: Q3 S; Q4 D to Q2 A; Q2 J; Q3 S; Q4 N to Q1 M; Q2 J; Q3 S; Q4 N to Q1 M
Output 1.1.4: | Finance officers and program managers are equipped with tools for monitoring and analysis of budget execution data, in line with financial management standards | bar: Q3 J to Q4 D; Q1 F to Q4 D; Q1 F to Q4 D; Q1 F to Q1 M
Output 1.1.5: | Ministry Internal Budget Committee equipped with a framework for regular meetings and relevant decision-making | bar: Q3 J to Q3 A; Q4 O to Q4 D; Q1 F to Q2 A; Q3 J; Q3 S to Q4 N; Q1 F to Q2 A; Q3 J; Q3 S to Q4 N; Q1 F to Q1 M
Sub-component 1.2: | Strengthening Budget execution Directorate key Sectors in Ministry of Finance | bar: Q3 J to Q1 M
Output 1.2.1: | Budget Execution officers are equipped with the tools necessary to enable them to implement budget process, as defined by budget policy officers | bar: Q3 J to Q1 M
Output 1.2.2: | Budget Execution officers support work of the Internal Budget Committees in the targeted line ministries | bar: Q3 J to Q3 A; Q4 O to Q4 D; Q1 F to Q2 A; Q3 J; Q3 S to Q4 N; Q1 F to Q2 A; Q3 J; Q3 S to Q4 N; Q1 F to Q1 M
Evaluation Phase: | Monitor the work of the supported ministries without providing assistance, assess remaining capacity gaps and provide any training to management on addressing the gaps | bar: Q2 A to Q2 J
Component II: Streamlining procurement processes | bar: Q1 J to Q4 D
Sub-component 2.2: | Capacity building in the line ministries | bar: Q1 J to Q4 D
Refer to: “Project Paper on a Proposed ARTF Grant in the Amount of US$ 73 mil to the GIRoA for a Second Public Finance Management Reform Project (PFMR II)”, of May 25, 2011, Annex 2: Results Framework and Monitoring
Component III: Facilitating accounting and budget process in Uruzgan | bar: N to Q4 D
Project review: | Assess progress and review coherence of the project | bar: N to D
Mobilization: | Contract amendemeds and advisers mobilization | bar: Q1 J to Q1 M
Pre-implementation: | Official training for the regional office in the Minitry of Finance in Kabul | bar: Q2 A to Q2 J
Sub-component 3.1: | Strengthening Provincial Budget Unit, Kandahar regional office | bar: Q3 J to Q4 D
Output 3.1.1: | Finance officers in the key service delivery directorates and Moustufiat understand key budget processes as per Ministry of finance’s policies and guidelines | bar: Q3 J to Q4 D
Sub-component 3.2: | Facilitating the budget process in key line directorates | bar: Q3 J to Q4 D
Output 3.2.1: | The finance officers and management in the key line directorates are equipped with tools for budget preparation, execution and monitoring, in with financial standards | bar: Q3 J to Q4 D
Inception Phase
Implementation Phase - Year 1: formal training
Evaluation Phase
Implementation Phase - Year 2: on-the-job support
Implementation Phase - Year 3: embedding activities in day-to-day operations
mobilization Phase
Pre-Implementation Phase
IImplementation Phase