## DV-IDENTITY-0 (hidden)
#REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
#VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #REF! | #VALUE! | #REF! | #VALUE! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | AAAAAG+/+zI= | AAAAAG+/+zM= | AAAAAG+/+zQ= | AAAAAG+/+zU= | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## 2012 WP Budget
Code | Program Description | Measure | Partners | Timeframe | Costs (FJD) | Dependencies/Notes | M&E Cross Reference
Program Goal:
The Goal of the program is: To remain engaged in the Fiji health sector by contributing to the Fiji Ministry of Health’s efforts to achieve its higher level strategic objectives in relation to reducing infant mortality (MDG4), improving maternal health (MDG 5) and the prevention and management of diabetes, as outlined in the MoH's Strategic Plan (2011-2015)
OBJECTIVE ONE: SAFE MOTHERHOOD
Objective: To institutionalise a safe motherhood program at decentralised levels throughout Fiji
To support the Fiji MOH to Institutionalise a Safe Motherhood Program at Decentralized Levels.
Operational Costs
| Travel |  |  | Jan - Dec | 24000 | 2,000 / month
| Workshops and Meetings |  |  | Jan - Dec | 6000 | $500 / month
| Materials |  |  | Jan - Dec | 4200 | $350 / month
| Objective Specific Operating Costs |  |  | Jan - Dec | 6000 | $500 / month
Local Personnel Costs
| TSO - CPG |  |  | Jan - Apr | 9000
| TSO -Facilities |  |  | Jan - Jun | 13500
Output 1.1: Increased Antenatal Coverage - An increasing number of women routinely presenting for first ante-natal check-up [ANC] in the first trimester.
Activities:
1.1.1 | One Media campaign per quarter to deliver a message that incorporates early booking, promoting birth preparation and complication readiness planning. | Four media campaign conducted. | MOH, NCHP, Media Outlets | Mar, Jun,Sep, Dec | 100000 | MOH, NCHP, Media Outlets | Outcome 1.1.1
1.1.2 | Develop and trial a ‘modified’ early booking kit, to include blood (spot) test for Syphilis and Anaemia for nursing stations and health Centres. | Early booking Kit developed. One pilot per division (at subdivision level) completed | MOH | Jan - Jun | 80000 | MOH, Purchasing Company | Outcome 1.1.1
Output 1.2: Increase in Sub Divisional Hospitals Classified as Mother Safe Hospitals.
Activities:
1.2.1 | Develop accreditation criteria for ‘mother safe’ facility, based on WHO 12 point Checklist | Fiji Accreditation Criteria for 'mothersafe' facility developed. | MOH, WHO | May - Jul | 5000 | Contract
1.2.2 | Audit all SDH against the WHO 12 point checklist for ‘mother safe’ facility status. | Audit completed in all SDHs. | MOH, WHO | May - Jul | 20000 | Contract | Output 1.2.4
1.2.3 | Support 4 EmOC workshops (1 training per division x 20 people and 1 National (40). | Four divisional workshops conducted. | MOH, Obs CSN | Jan - Dec | 60000 |  | Output 1.2.2
1.2.4 | Support 5 SDH’s (As prioritised by National CSN) to address the 7 signal functions for Emergency Obstetric Care (as a component of a ‘Mother Safe’ Facility) . Starting with:
1.2.4.1 | Setting up of Post Miscarriage Services | Working Committee on PAS established. | MOH | Jan - Feb | 2000
1.2.4.2 | Developing a National Training package for SDH Doctors to provide Post Miscarriage Services | National Training Package for Doctors on PAS developed. | MOH | Jan - Feb | 10000 |  | Output 1.2.2
1.2.4.3 | Purchasing of Manual Vacuum Aspirators for each of the 5 SDH | Five Manual Vacuum Aspirators purchased. | MOH, FPS | Jan - April | 20000 | MOH, FPS, Purchasing Company. | Output 1.2.3
1.2.4.4 | Supporting the delivery of the training package. | PAS Training Package printed and distributed. | MOH | Feb - April | 20000 |  | Output 1.2.2
Output 1.3 : Higher proportion of deliveries being carried out in SDH or higher level institutions.
Activities:
1.3.1 | Carry out recommendations of Gap Survey (i.e. survey of gaps in specific areas of MCH and obstetric services as SDH's completed in 2011) | MOH |  | Jan - Dec | 100000 |  | Output 1.2.3
1.3.2 | Support development, printing and distribution of Obs. CPG: | MOH, CSN Obs. |  | Jan - April | 50000 |  | Output 1.2.5
1.3.3 | Awareness and training on CPG Obstetric Emergencies at subdivisional level. | MOH |  | March - Oct | 20000 | CSN Obs | Output 1.2.5
Output 1.4: Increased Contraceptive Prevalence
Activities:
1.4.1 | Develop a training package for Family planning for nurses at sub divisional levels (which includes Jadelle implant training) | FP Training Package for Nurses developed. | MOH | 3 months | 50000 |  | Output 1.2.1
1.4.2 | Support distribution, awareness and training of FP Training Package for Nurses | proportion of SDH Nurses training on FP Training Package | MOH | July - November | 20000 | training package at 1.4.1 being developed. | Output 1.2.1
1.4.3 | Media campaign to educate teenagers about safe sex, contraception, prevention HIV/AIDS. | Four divisional media campaign conducted. | MOH, Peer Educators | Jan - Dec | 40000
Output: 1.5 Capacity building and training of health care professionals to ensure the whole spectrum of continuum of care.
Activities:
1.5.1 | Support training for Assessors for Baby Friendly Hospital Initiative (BFHI) to be conducted by the National Nutrition Centre (for 2 staff per subdivision x 20 sub divisions + 5 staff from each divisional hospital) | 3 Divisional Training conducted Fifty-five Assessors completed training. | MOH NFNC | Jan - Sept | 60000 | MOH NFNC | Output 1.2.1
1.5.2 | Monitoring component for the above | Monitoring tool developed. | MOH NFNC UNICEF | May - July | 2000 |  | Output 1.2.2
1.5.3 | Support for re-printing training Manuals for BFHI | BFHI Training Manuals Printed. | MOH, NFNC | Jan - Feb | 15000 | MOH NFNC | Output 1.2.2
1.5.4 | Support existing MOH nurses to undertake Midwifery training using a MOH/FHSSP cost sharing model (FNU 35 places, Sangam 10 places) | 20 Nurses admitted to Midwifery Course. | MOH, FNU, SANGAM | April - Dec | 45000 | MOH, FNU, SANGAM | Output 1.2.2
1.5.5 | Work with Obstetric CSN to draft MOU for FNU/MOH partnership for Nursing and Midwifery training. | MOU developed and endorsed. | MOH, FNU, SANGAM | April - July | 2000 | MOH, FNU, SANGAM | Output 1.2.2
1.5.6 | Obstetric support program that includes attachments from Sub Divisional hospitals and Nursing Posts to Divisional Hospitals, inter divisional hospital exchanges and midwifery outreach activities (including CME, partogram & Auditing activities.) Specifically with the purpose of maintaining skills among midwives and doctors | Five staff per division completed clinical up skilling attachment. Two midwives outreach per division conducted. | MOH | Feb - Dec | 60000 | MOH | Output 1.2.2
1.5.7 | Support for monitoring the above activities | Monitoring tool designed. |  | Feb - Dec | 2000 | MoH | Output 1.2.2
1.5.8 | Support the nationalizing of ‘ visual inspection with acetic acid’ (VIA) – to be further discussed as currently there is a pilot project (finishes in March 2012) in place This is a complimentary service to the Pap Smear program. |  | MOH, CSN Obs | April - Dec | 50000 | MOH, FNA,
TOTAL FOR OBJECTIVE ONE |  |  |  |  | 895700
OBJECTIVE TWO: Healthy Child Program
Operational Costs
| Travel |  |  | Jan - Dec | 10000 | $830 / month
| Workshops and Meetings |  |  | Jan - Dec | 10000 | $830 / month
| Materials |  |  | Jan - Dec | 10000 | $830 / month
| Objective Specific Operating Costs |  |  | Jan - Dec | 6000 | $500 / month
Local Personnel Costs
| Infant and Child Health TSO - WHS |  |  | Jan - Dec | 30000
| Infant and Child Health TSO - CEHS |  |  | Jan - Dec | 30000
| Infant and Child Health TSO - NHS |  |  | Jan - Dec | 28500
Objective: To institutionalise a 'healthy child' program throughout Fiji
2 | To support the Fiji MOH to institutionalise a 'healthy child' program throughout Fiji
Output 2.1: EPI Program strengthening - Systems in place to maintain Expanded Program of Immunisation (EPI) rates greater than 90%
Activities:
2.1.1 | Determine the steps to consolidate and ensure sustainability of the Expanded Program of Immunisation (EPI) program
2.1.1.1 | New vaccine introduction | New vaccines are introduced | WHO, UNICEF, JICA, PIPS, MoH | Jun | 40000 | Identification of an acceptable sustainable financing solution | Outcome 2.1.1
2.1.1.2 | Child Health Week | Vaccination of 1000 vaccine defaulters | WHO, UNICEF, JICA, PIPS, MoH, NZAID | Jun | 90000 |  | Outcome 2.1.1
2.1.1.3 | Support to Basic 3 day EPI training | Training of all nurses new to EPI competed in all 3 divisions | MoH | Jun | 40000 |  | Outcome 2.1.1
2.1.1.4 | Support to Demographic Health Survey (EPI coverage survey) | Coverage data available | WHO, UNICEF, JICA, PIPS, MoH | Sep | 150000 | Planned to be integrated with DHS, however methodology needs to be comparable to previous coverage survey | Outcome 2.1.1 | To be covered out of Unallocated Fund
2.1.1.5 | Micro planning workshops | 3 workshop conducted | MoH | Jun | 15000 |  | Outcome 2.1.1
2.1.1.6 | PIPS workshop | Workshop attended and linages with partners maintained | WHO, UNICEF, JICA, PIPS, MoH | Sep | 10000 | Workshop is held in 2012 | Outcome 2.1.1
2.1.1.7 | Public Health Association of Australia Immunisation Conference & linkages with PHAA established with PHA Fiji established | Conference attended Linkages with PHAA established and sub PHA of Fiji developed | PHAA | Jun | 25000 |  | Outcome 2.1.1
2.1.1.8 | VPD Surveillance Officer to establish system [MoH to take over funding in 2013] | VPD surveillance system established | Mataika House, WHO, MoH | Dec | 25000 | Mataika House must take the lead and MoH to take over funding on 2013 |  | To be covered out of Unallocated Fund
Output 2.2: IMIC Training leads to more secondary paediatric care at Sub-Divisional level - Comprehensive training in IMCI leading to more secondary level paediatric care being safely carried out at SDH level or below
Activities:
2.2.1 | Expand and/or reinforce the Integrated Management of Childhood Illnesses (IMCI) training program
2.2.1.1 | Development of standardised IMCI policies and procedures for nurses [?include in nurses scope of practice] | IMCI protocol included in SOP | MoH | Dec | 10000 | SOP completed in 2012 | Outcome 2.1.1
2.2.1.2 | Train IMCI supervisors [SDHS/SDMO/DHS] to provide essential supervision, assessment and provision of appropriate equipment | IMCI supervisors trained | MoH, UNICEF, WHO | Sep | 20000 | Paediatric department being able to develop a modified IMCI course for supervisors | Outcome 2.2.3
2.2.1.3 | Identify divisional IMCI champions to take over the training | IMCI training is coordinated by divisional public health | MoH | Dec | 0 | Divisions recognise need to lead the IMCI training | Outcome 2.2.3
2.2.1.4 | IMCI facilitators training | Additional 20 IMCI facilitators trained, IMCI successfully being carried out without dependency on CWMH | MoH, UNICEF, WHO | Dec | 25000 |  | Outcome 2.2.3
2.2.1.5 | IMCI training | Training conducted, IMCI trained staff in each sub division | MoH, UNICEF, WHO | Dec | 40000 |  | Outcome 2.2.3
2.2.1.6 | IMCI attachments | Attachments conducted in each division | MoH, UNICEF, WHO | Dec | 25000 | MoH identifies staff who require attachment and can release them from their station for the attachment | Outcome 2.2.3
Output 2.3: Capacity building and training of health care professionals to ensure whole of spectrum of continuum of care
Activities:
2.3.1 | CSN Paediatrics to meetings | CSN meets | MoH | Sep | 15000
2.3.2 | Nutrition | IYCF TOT conducted in each division | MoH, UNICEF, WHO | Oct | 80000 | Nutrition department able to deliver the training | Outcome 2.2.3
2.3.3 | Oral Health | capacity building workshop conducted | MoH | Apr | 20000 | Oral health team able to deliver the training | Outcome 2.2.3
2.3.4 | Child Health Specialist Nurses | 10 Nurses certified at child health specialists | MoH | Dec | 18000 | Specialty to be recognised as a specialist discipline | Outcome 2.2.3
2.3.5 | PLS & APLS training | Training completed | MoH | Dec | 60000 | APLS will require an instructor from Aust | Outcome 2.2.3
2.3.6 | Pocket Book training | Pocket book training conducted and reaches every sub division | MoH | Dec | 30000 | Paediatric department availability | Outcome 2.2.3
2.3.7 | Malnutrition | Reduction in hospitalised malnutrition cases | MoH, UNICEF, WHO | Dec | 20000 | Study results available
Output 2.4: Reduce peri-natal mortality - Child health to be more focused on reducing peri-natal mortality.
Activities:
2.4.1 | Review guidelines and protocols, working with the paediatric team at CWMH to identify and document all existing policies & CPG | Neonatal Guidelines and protocols reviewed and best guidelines identified | MoH, Paed Department | Dec | 5000 |  | Outcome 2.2.2
2.4.2 | Equipment procurement [based on requirements found from 2011 audit]. Funding to be rolled over from 2011. | Decentralised levels are better equipped to treat paediatric clients | MoH, Paed Department | Dec | 315000 | Equipment priorities identified by Paed CSN | Outcome 2.2.1
2.4.3 | Neonatal attachments | Attachments conducted in each division | MoH, Paed Department | Dec | 15000 | Divisions identify those that require attachments | Outcome 2.2.3
TOTAL FOR OBJECTIVE TWO |  |  |  |  | 1042500
OBJECTIVE 3: Diabetes
Facilitator Costs
| Travel |  |  | Jan - Dec | 25000 | $20,80 / month
| Workshops & Meetings |  |  | Jan - Dec | 6000 | $500 / month
| Materials |  |  | Jan - Dec | 5040 | $420 / month
| Objective Specific Operating Costs |  |  | Jan - Dec | 6000 | $500 / month
Local Personnel Costs
| TSO - NCD Tool Kit, SOPD & TNA - North |  |  | Jan - Dec | 21600
| TSO - NCD Tool Kit, SOPD & TNA - West |  |  | Jan - Dec | 21600
| TSO - NCD Tool Kit, SOPD & TNA - Central / Eastern |  |  | Jan - Dec | 21600
| TSO travel & other expenses |  |  | Jan - Dec | 5000
Objective: To strengthen Diabetes and Hypertension prevention and management at decentralized levels
Output 3.1: Population Screening - Improving the detection of undiagnosed DM & HT cases through population screening. Implementing SNAP preventive activities
Activities:
3.1.1 | Auditing of NCD Tool Kits, SOPDs & training needs in eight (8) other SDH and Health Centres | Number of facilities audited | MOH Staff at SDH & HCs | Jan - Dec | 65000 |  | Outcome 3.1.2
3.1.2 | Support the development and implementation of the proposals for upgrade | Number of facilities fully upgraded | MOH Staff at SDH & HCs | Jan - Dec | 120000 | Timely development & submission of proposals by SD & HC | Outcome 3.1.2
3.1.3 | Purchasing & replacing equipment in the NCD Tool Kits in all audited facilities | No of facilities with fully operational NCD T/Ks | MOH Staff at SDH & HCs | Jan - Dec | 100000 | Timely acquisition of equipment (most imported from overseas) | Outcome 3.1.2
3.1.4 | Screening of 'at risk' population commenced in identified sites & developing registers to record SNAP Interventions | No of facilities implementing screening & SNAP registers | MOH Staff at HCs & NS | Jan - Dec | 20000 | Timely development & submission of proposals by SD & HC. Availability of HCW for screening | Outcome 3.1.2
3.1.5 | Reviewing the Green Prescription | Reviewed by August 2012 | MOH Staff at SDH, HCs & NSs | August | 5000 | Availability of participants/ facilitators | Outcome 3.1.2
3.1.6 | Focused population screening during World Health Day (April) & World Diabetes Day (Nov) | No of sites conducting screening | MOH Staff at SDH, HCs & NSs | April & Nov | 30000 | Availability of HCW | Outcome 3.1.2
3.1.7 | Healthy Eating & Physical Activity programs | No of sites conducting this program | MOH Staff at NCHP & Div Level | Jan - Dec | 20000 | Availability of HCW | Outcome 3.1.2
3.1.8 | Support training in & distribution of NCD Tool Kits & related Educational Materials in identified sites | No of sites fully operational | MOH Staff at SDH & HCs | Jan - Dec | 20000 | Availability of participants/ facilitators | Outcome 3.1.2
3.1.9 | Collaborating with major stakeholders to support NCD prevention activities (e.g. HPS) | Meetings attended & support provided | WHO, SPC, community groups | Jan - Dec | 5000 | Details of collaboration not clear at present | Outcome 3.1.2
3.1.10 | Supporting NCD Screening activities & SNAP intervention at workplaces | Meetings attended & support provided | MOH , NCHP, WP OHS Com | Jan - Dec | 15000 | Number of requests received & type of support needed | Outcome 3.1.2
3.1.11 | NCD Awareness Programs (Print and media) | Number of programs conducted | MOH, NCHP, NCD | Apr, Nov | 75000 | Number of requests received & type of support needed | Outcome 3.1.2
Output 3.2: Personal Diabetes Record Book - Introducing a personal Diabetes care record booklet to ensure continuum of care for patients who have a variety of service providers.
Activities:
3.2.1 | Distribution of PDRB to all identified sites. Records kept of distribution to all identified sites and re-prints. | Distribution lists showing progress quarterly | MOH Staff at SDH & HCs | Quarterly | 15000 | Adequate HCW conducting clinics. Adequate handing over when HCW change. | Outcome 3.1.3
3.2.2 | Monitoring & Audit Tool in place. | Tool developed | MOH Staff at SDH & HCs | Quarterly | 1000 |  | Outcome 3.1.3
Output 3.3: Establish Quality Diabetes centres at Sub-divisional Level & major health centres - Strengthening management of Diabetes & its complications at Diabetes (NCD) HUBs, SDH & HC levels. Improving facilities for more advanced diabetic care including outreach diabetic retinopathy & debridement.
Activities:
3.3.1 | More facilities, in all divisions, identified for auditing and upgrade | List agreed to in the first Div Plus meeting | DMOs & SDMOs | Mar | 500 | Agreement by MOH Executive staff | Outcome 3.1.4
3.3.2 | Minimum standards for providing quality diabetes management services established. | Draft standard in place | Diabetes CSN | Jun | 5000 | Agreement by Diabetes CSN & MOH Executive staff | Outcome 3.1.4
3.3.2.1 | Ensuring updated registers of people with DM & HT at SDH & HC SOPDs | No of sites with registers | MOH Staff at SDH & HCs | Jan - Dec | 500 |  | Outcome 3.1.4
3.3.3 | Appropriate training conducted with appropriate tools for documentation and reporting. | 3 per quarter | Diabetes CSN | Jan - Dec | 20000 | Availability of facilitators/ trainers mainly specialist clinicians | Outcome 3.1.4
3.3.4 | Needs assessment for other resource materials conducted | Assessment tool / template developed | SD & HC Staff of MOH | June | 5000 |  | Outcome 3.1.4
3.3.5 | Purchase SNAKE screening equipment & consumables | Proof of agreed list & purchase | Diabetes CSN | Jun | 50000 | Need Diabetes CSN to agree to a minimum standard for equipment | Outcome 3.1.4
3.3.6 | Support an Audit of NCD Care services at Divisional Hospital SOPDs | Audit tool developed | Diabetes CSN | Aug | 5000 | Need Medical CSN to partner with maybe FNU | Outcome 3.2.1
3.3.7 | Support quarterly meetings of the Diabetes CSN | Schedule of Meetings agreed to | Diabetes CSN | Mar, Jun, Sep, Dec | 20000 | Availability of the clinicians | Outcome 3.2.2
Output 3.4: Strengthen the role of the National Diabetes Centre & the NCD HUBs - Strengthening the role of the NDC to function as a focal point for policy & Training, and the support NCD HUBs as specialist referral centres for the divisions.
Activities:
3.4.1 | Support the Implementation of the roles, responsibilities and functions of the NDC & The NCD HUBs as endorsed by NHEC | Draft proposal developed | Medical CSN | Mar | 50000 | Availability of the HR component from MOH before the other components can be implemented
3.4.2 | Support appropriate capacity building | Draft Capacity Building proposal developed | Diabetes CSN | Apr | 20000
3.4.3 | Purchase appropriate equipment & consumables. | Draft list developed | Diabetes CSN | May | 50000
3.4.4 | Strengthen Outreach services through planning and possible transport options. | Draft Plan for outreach developed | Diabetes CSN | Jun | 50000
3.4.5 | Audit and develop appropriate resource materials | Audit tool developed | Medical CSN | Jun | 10000
Output: 3.5: Capacity Building and Training -Training & Capacity building of the health care workers to prevent, screen and manage NCDs (especially DM & HT) effectively & provide continuum of care. Also to provide capacity Building support to the Community Health Workers.
Activities:
3.5.1 | Develop & Implement a training plan for all cadre of HCW at identified health facilities | Draft training plan developed | Medical CSN, SDMOs | Mar | 50000 | Timely input from MOH staff
3.5.2 | Support other identified training such as Podiatry, Clin attachments | Draft plan | Diabetes CSN | Jun, Dec | 40000 | Timely submission from appropriate MOH Staff, TSOs at divisional level will be very helpful.
3.5.3 | Purchasing other identified training & educational tools e.g. Food Models, Charts | Proposed List available | DMOs & SDMOs | Mar | 20000 | Timely submission from appropriate MOH Staff
3.5.4 | Curriculum Development / Dip in Diabetes Management |  | FSMed / MoH | Jun | 5000 | Consultation with FNU, SPC, WHO
3.5.5 | Purchase accredited training from training institutes such as WHO, SPC, FNU, | Proposed List available | DMOs & SDMOs | Mar | 20000 | Timely submission from appropriate MOH Staff. Development of curriculum.
TOTAL FOR OBJECTIVE THREE |  |  |  |  | 1023840
OBJECTIVE 4: COMMUNITY HEALTH WORKER NETWORK
Objective: To revitalise an effective and sustainable network of village/community health workers (VHW/CHW) as the first point of contact with the health system for people at community level
Output 4.1: Revitalisation of V/CHW Training - An effective system of trained and resourced VHW/CHW who are able to promote public health practices and health seeking behaviours, provide basic first aid, and effectively refer patients to the next level of health services
Facilitator Costs
| Travel |  |  | Jan - Dec | 24000 | 2,000 / month
| Workshops & Meetings |  |  | Jan - Dec | 6000 | $500 / month
| Materials |  |  | Jan - Dec | 4200 | $350 / month
| Objective Specific Operating Costs (stationary, cars phones (?) etc) |  |  | Jan - Dec | 6000 | $500 / month
Local Personnel Costs
| TSO - Training Package |  |  | Jan - March | 50000
Activities:
4.1.1 | Support MOH in further strengthening of the CHW training package including tool kits and M&E framework. (A local contractor will be recruited to undertake the translation and current TSO will conduct TOT after endorsement of the manual) | Training package translated, printed and distributed to the training of trainers | MOH, JICA (NBT) | Jan - Mar | 50000 | Timing of endorsement of training manual. | Outcome 4.1.1
4.1.2 | Facilitate the procurement of tool kits | Tool kits procured and available for use | MOH | Nov | 300000 | Non inclusion of clinical set for CWM. | Outcome 4.2.1
4.1.3 | Strengthen partnership with key stakeholders at National and Divisional level | Number of actively engaged key stakeholders in the revitalisation process increase | MOH, GOF, NGOs, FSM, FSN, JICA, WHO, USAID, Peace Corp, Town Councils and etc | Jun | 60000 | Stakeholder engagement.
Output 4.2: Increases community ownership of and engagement in Primary Health Care
Activities:
4.2.1.1 | Provide support to DMO North in facilitating the establishment of health status baseline of four comminutes as part of training of trainers (1 peri-urban setting, 1 non-indigenous remote setting) | Proportion of Community Profile established | MOH, Ministry of Itaukei, Town Councils and the community | Feb - Dec | 25000 | TF with support | Outcome 4.2.4
4.2.1.2 | Training in community health action plan |  | Community Level | Feb - Dec | 25000 | TF with support | Outcome 4.2.5
4.2.2 | Provide support to the implementation of health promotion activities and set up of community support groups. Areas of support inlcude smoke free community, HIV awareness, traditionally sensitive issues, water supply upgraded, backyard garden established and etc (Strengthen water sanitation waste approach) | Number of health promotion activities implemented | MoH | March - Dec | 60000 | Divisional business plans | Outcome 4.2.5
Output 4.3: An increase in the number of VHW/CHW trained - Effectively trained VHW/CHW who are able to meet the health needs of their respective rural and urban communities
Activities:
4.3.1 | Training of trainers | Number of trained CHW trainers, Number of subdivision with trained CHW trainers | MOH | Feb - March | 70000 |  | Outcome 4.1.1
4.3.2 | Roll out of CHW training | Proportion of CHW trained and resourced | MOH, JICA | March - October | 300000 |  | Outcome 4.1.1
Output 4.4: Strengthening supervisors capacity in M&E of CHW program
Activities:
4.4.1 | Training of supervisors |  | MoH, JICA | March - July | 50000 | Based on JICA timing | Outcome 4.2.2
4.4.2 | Monitoring of CHW activities |  | MoH, JICA | July - Dec | 10000 | Based on 4.5.1 | Outcome 4.2.2
TOTAL FOR OBJECTIVE FOUR |  |  |  |  | 1040200
OBJECTIVE FIVE: Targeted systems strengthening
Objective: To strengthen key components of the health system to support decentralised service delivery
5 | To strengthen key components of the health system to support decentralised service delivery.
Output 5.1: Functional Public Health Information System (PHIS). - PHIS provides timely, complete and accurate information for all Fijians that is being used to measure public health outcomes and plan future activities
Facilitator Costs
| Travel |  |  | Jan - Dec | 24000 | 2,000 / month
| Workshops & Meetings |  |  | Jan - Dec | 6000 | $500 / month
| Materials |  |  | Jan - Dec | 4200 | $350 / month
| Objective Specific Operating Costs (stationary, cars phones (?) etc) |  |  | Jan - Dec | 6000 | $500 / month
Local Personnel Costs
| TSO - CSN/CPG Co-ordination M&E |  |  | Jan - Dec | 28000
Technical Assistance
| LTA Monitoring and Planning |  |  | Jan - Dec | 250000
| PHIS STA |  |  | Jan - Dec | 80000
OUTPUT 5.1 FUNCTIONAL PUBLIC HEALTH INFORMATION SYSTEM [PHIS]
5.1 | The Public Health information System provides complete, timely, and accurate information to stakeholders to be used to measure public health outcomes and plan future activities at Central and decentralized levels.
Activities
5.1.1 | Revision of all forms and manuals to ensure they collect information needed to report performance indicators. Print and distribute manuals. | Revised tools endorsed by the NHIC | MOH (HIU) & GMU | Jan – Jun | 63500 | MoH to establish project governance and arrange consultations with all stakeholders | Outcome 5.1.1
5.1.2 | Develop data collation and reporting at tools at Divisional, sub-divisional levels , national levels. Including reporting templates at all levels | Data collation tools in place and providing reports locally and data to national level | MOH – Divisional Level | Apr - Dec | 78000 | MoH to arrange consultations to determine desired functionality at Divisional level | Outcome 5.1.1
5.1.3 | Conduct training in data collection and analysis and use [presentation skills] | Proportion of facilities with trained staff in new process and tools | FNU,MOH, Global Fund | Jul - Dec | 7000 | MoH to identify staff to be trained and provide logistics support for training | Outcome 5.1.1
5.1.4 | Support Development of Data & Indicators Dictionary | Data & Indicators dictionary developed | FNU, MOH and Global Fund | Jul - Dec | 5000 | MOH to release staff time to work on these dictionaries | Outcome 5.1.1
5.2 | Output 5.2: OPERATIONAL RESEARCH PROVIDES INFORMATION TO SUPPORT EVIDENCED –BASED POLICY AND PLANNING OF HEALTH SERVICES IN THE URBAN AND PERIURBAN AREAS.
5.2.1 | Commission initial analysis of scope, key issues, health outcomes and health system impacts of urban and peri urban migration.Develop options for addressing identified impacts and needs. Develop mechanisms for monitoring health status of informal settlement communities.{Develop MoH capacity and build links to local and regional institutions.
Activities
5.2.1.1 | Strengthen long term MoH research capacity through courses and partnering/mentoring with FNU CMNHS Research Unit. Locally engaged TA through FNU. | (i)Support plan endorsed by MoH (ii)mentoring relationship formally established | MOH, FNU(CMNHS) | Jan –Jun | 20000 | MOH & FNU (CMNHS) | Outcome 5.1.4
OUTPUT 5.3 IMPLEMENTATION OF CLINICAL SERVICES PLAN ACTIVITIES
5.3 | Implementation of clinical services plan activities including role delineation, clinical services networks and short term clinical attachment and support Risk management ,Quality improvement in capacity building
ACTIVITIES
5.3.1 | Support Health worker exchange for attachment between hospitals to up skill them | No of exchanges by type of health worker | MoH | Jan – Dec | 15000 | CSn plans and release of officers by MOH
5.3.2 | Support CSN Workshop | Number CSN workshop conducted | MoH | Apr - Nov | 15000 | 10 CSN
5.3.3 | Health Symposium | Health Symposium held | FNU (CMNHS), MOH | Jun | 60000 | FNU & MOH (Core share)
5.3.4 | Support capacity building for Health System Standard in Infection Control, Risk Management & CQI
5.3.4.1 | Attachment to John Hunter Hospital | 1 officers completed attachment & completion report received | MOH –DSHS & PHSS. John Hunter & MoH | Jan – Dec | 15000 | Availability of place at John Hunter
5.3.4.2 | Review of UOR Database | Reports received & actioned | MOH –DSHS & PHSS | Jan – Dec | 5000 | PA HSS to coordinate
5.3.4.3 | RCA Infection Control Workshop/Training of risk management and quality improvement | Workshop conducted | MOH –DSHS & PHSS | Jan – Dec | 15000 | Divisional risk managers
5.3.4.4 | National QI/CSP Meeting | Meeting conducted | MOH –DSHS & PHSS | Mar - Sep | 8000
5.4 | Output 5.4: Support for MOH Planning Process
Activities
5.4.1 | Development of Oral Health strategic plan (taking into account current survey) | Plan endorsed by NHEC | MOH – DSPH, NAOH | Jan – Jun | 10000 | Based on survey results of 2011. | Outcome 5.1.3
5.4.2 | Capacity building for senior staff in policy development, government writing. | a) Long term development plan developed and endorsed b) Number of senior staff attending training / secondment by type | MOH, FNU & PSC | Jan – Dec | 10000 | LTA Planning and Monitoring to take lead role | Outcome 5.1.2
5.4.3 | Annual Corporate Planning development support | ACP 2013 Endorsed | MOH – PPDA | Sep | 20000 | MOH & PSC
5.5 | OUTPUT 5.5: SECTORAL CO-ORDINATION
Activities
5.5.1 | Donor Co-ordination Meeting | 2 meetings conducted | MOH (PPDA) |  | 5000 | MOH & Donor | Outcome 5.1.3
5.5.2 | Divisional Meetings | 4 meetings per division | MOH (PPDA) & Divisional Office (DSPH & DSHS) | Jan - Dec | 40000 | MOH & Divisional Office | Outcome 5.1.3
5.5.3 | Sub-Divisional Meeting | Documented reports from Sub-Divisional heads | Divisional Office & Sub –Divisional Office | Jan - Dec | 10000 | MOH (DSPH & DSHS) | Outcome 5.1.3
5.5.4 | Annual Program Planning | Development of the Program’s Plan for 2013 | FHSSP | Oct | 15000 | MOH & AusAID | Outcome 5.1.3
TOTAL FOR OBJECTIVEFIVE |  |  |  |  | 814700
Total Program |  |  |  |  | 4816940
Unallocated Fund |  |  |  |  | 1724138
Total Program including Unallocated Fun |  |  |  |  | 6541078
*Note - the actitivies being funded from the Unallocated fund are highlighted in pink under their relevant Objective, however the allocation is actually taken into account under the UF line, NOT the total for the Objective.