Papua New Guinea – Australia
Development Cooperation Program

Program of Partnership and Support for 
HEALTH WORKER EDUCATION AND TRAINING 
and SPECIALISED SERVICES in PNG
(the “PNG HWETSS Program”)

Program Design Document

- Final Draft, 30 June 2008

- (AusAID Services Order 11424/24)

TABLE OF CONTENTS

Executive Summary	v

Acronyms and Abbreviations	xii

1	DESIGN APPROACH AND METHODOLOGY	1

1.1	Primary Design Process	1

1.1.1	Terms of Reference	1

1.1.2	Consultations in Papua New Guinea	2

1.2	Review and Revision of the Design	2

2	Context and Problem Analysis	3

2.1	Background	3

2.1.1	Medical School Support Project	3

2.1.2	Tertiary Health Services Project	4

2.2	Sector and Policy Context	4

2.2.1	PNG Policy Context	4

2.2.2	Australian Policy Context	5

2.2.3	Aid Effectiveness and Donor Harmonisation	5

2.3	Problem Analysis	5

2.3.1	Overview	5

2.3.2	Need for a Health Workforce Plan	7

2.3.3	Health Professional Training	8

2.4	Health Professional Training – Lessons Learned	10

2.5	Factors related to the School of Medicine and Health Sciences	11

2.5.1	Constraints facing the School	11

2.5.2	Measures taken by the School to address these Constraints	13

2.6	Conclusion	14

3	SCOPE FOR NEW ACTIVITIES	15

3.1	Scope and Feasibility of new AusAID activities	15

3.1.1	Existing and Emerging Considerations	15

3.1.2	Rationale for a Health Training Support Program	18

3.2	Principles, Concept and Rationale for Australian Support	18

4	DESCRIPTION OF THE PROPOSED PROGRAM	21

4.1	Guiding Principles, Policies and Criteria	21

4.1.1	The SMHS Strategic Plan	21

4.1.2	Principles and Priorities	21

4.1.3	Australian and International Agreements	22

4.2	Selection of the Form of Aid Delivery	23

4.2.1	Preferred Form of Aid	23

4.2.2	Other options examined (but not recommended)	23

4.3	Objective, Rationale and Intended Outcomes	24

4.3.1	Objective	24

4.3.2	Strategic Rationale	25

4.3.3	Intended Program Outcomes	25

4.4	Phasing of Australian Support	27

4.4.1	Transition Phase (6-9 months)	27

4.4.2	Audit and Technical Review (late 2008 or early 2009)	29

4.4.3	Implementation Phase (2009-2010)	29

4.4.4	“Mid-Term” Review (late 2010)	31

4.4.5	Consolidation Phase (2011 onwards)	31

4.5	Proposed Australian Budget	31

5	MANAGEMENT AND FINANCING ARRANGEMENTS	33

5.1	Rationale for Delivery and Financing Modalities	33

5.1.1	Track Record	33

5.1.2	Appropriateness of Accountable Cash Grants	33

5.1.3	Responding to New Demands on SMHS Systems	33

5.1.4	Relationship with the Health SWAp and HSIP	34

5.2	Stakeholder Management of the Program	34

5.2.1 Overview	34

5.2.2 Management by Partners using Accountable Cash Grants	35

5.3	Coordination Agreements and Arrangements	35

5.3.1 Overview	35

5.3.2 Program Implementation Cycle	35

5.3.3 Program Advisory Group	35

5.3.4 Specialty Coordinators’ Group	36

5.4	Financing arrangements, including GOPNG contributions	37

5.4.1 Program Budget	37

5.4.2 Financing arrangements	38

5.4.3 Other Funding Sources	38

6	PERFORMANCE ASSESSMENT	39

6.1	Overview	39

6.1.1 Purpose	39

6.1.2 Approach and Rationale	39

6.1.3 Responsibilities and Technical Resources	39

6.2 Measurement of Program Success	40

6.2.1 Objective Monitoring	40

6.2.2 Stakeholders and Beneficiaries	40

6.3 Data Requirements and Ownership	40

6.3.1 Harmonisation with Existing Systems	40

6.3.2 Arrangements for Collection of Data	41

6.3.3 Reporting Frequency and Schedule	41

6.4 Mid-Term Review at the end of Year Two of the Program	41

6.5 Budget Allocated to Program M&E	42

7	CROSS-CUTTING ISSUES	43

7.1	Corruption	43

7.2	Gender	43

7.3	Environment	44

7.3.1 Medical Waste Management	44

7.3.2 Carbon Emissions	44

7.4	HIV and other Blood Borne Viruses	44

7.5	Intellectual and Genetic Property Rights	45

7.6	Other Cross-Cutting Themes	45

8	Sustainability and RiskS	46

8.1	Sustainability	46

8.2	Feasibility	46

8.3	Key Risks and Responses	46

8.3.1 Risks related to the Health Sector Policy Environment	46

8.3.2 Financing and Financial Risks	47

8.3.3 Risks related to Counterpart Capacity for Program Implementation	48

8.3.4 External Risks	50

8.3.5 Conclusion	50

ANNEXES	51

List of Annexes

- Annex I		Sector and Policy Context

- Annex II		Problem Analysis

- Annex III		Health Professional Training and Curriculum, HR Branch, NDOH

- Annex IV		Problem Tree and Analysis

- Annex Va		Terms of Reference (Design Mission)

- Annex Vb		Terms of Reference (Design Revision)

- Annex Vc		Additional Reference Materials (Design Revision)

- Annex VI		Feasibility Study for a HRH Initiative in Pacific Island Countries

- Annex VII		SMHS Strategic Plan (Synopsis, April 2008)

- Annex VIII		Indicative Budget & Resources Schedule and Phasing

- Annex IX		Risk Management Matrix

- Annex X		Development Partner support to Health Training

- Annex XI		Assessment of Quality at Entry

- Executive Summary

Background

Human Resources for Health in Papua New Guinea –

The health workforce and the preventive and clinical care they provide are central elements of every health system.

Papua New Guinea trains high quality health professionals at both Government- and independently-funded institutions.  Foremost among these is the School of Medical and Health Sciences (SMHS) at the University of Papua New Guinea (UPNG), which has achieved a fine record training health care workers (HCWs) over many years; this has resulted in predominantly national staffing of the health service and the School.

Graduates range from Community Health Workers who serve in rural health facilities right through to tertiary medical specialists working at the Port Moresby General Hospital (PMGH) and some larger Regional facilities.  The SMHS also accepts undergraduate and postgraduate candidates from the Solomon Islands, Vanuatu, Timor Leste and the Federated States of Micronesia (and occasionally from further afield).

Due to financial constraints and ongoing vacancies among academic positions, the SMHS struggles to produce the required number of graduates and provide programs in some key areas (such as public health), and its capacity as a research institution is poor.

Previous Australian Support –

To date, Australian assistance for these elements of the PNG health system has mainly been provided through two mechanisms:

- Direct support to the medical school at UPNG – currently delivered through the Medical School Support Project (MSSP).

- Direct provision of specialist health services – currently delivered by the Royal Australasian College of Surgeons through a Tertiary Health Services (THS) Project.

The THS Project has shown a gradually increasing focus on teaching, training and mentoring for undergraduate and postgraduate students.  This has drawn it functionally closer to the SMHS over time, and demonstrates a transition – albeit an evolving one – from humanitarian assistance to capacity building.

Both the National Department of Health (NDOH) and the SMHS strongly endorse the assistance provided to medical education in PNG, and are seeking a continuation of Australian support.

Development Context

Health Services –

PNG specialists can now provide all but the highest level of tertiary medical services.  However, they are in short supply in most provincial centres outside Port Moresby.

In rural areas, an ongoing shortage of all categories of HCW and the absence of a comprehensive national plan for their training, deployment, retention and continuing education are major constraints to better rural health services and population health outcomes.

Australian and Partner Government Policy Context –

The Government of PNG (GOPNG) Medium Term Development Strategy 2005-2010 and the Papua New Guinea – Australia Development Cooperation Strategy 2006-2010 both highlight health and improved service delivery as key development priorities, and identify partnerships with relevant stakeholders and working within PNG systems as keys to supporting and strengthening national ownership of development processes.

The GOPNG is undertaking a public sector reform process aimed at improving service delivery, and the NDOH is seen as one of four key agencies to achieve this goal.  An immediate and imminent priority under the new reforms is the Health Workforce Summit, to be held on 7-8 July 2008 – this will be the first sector-wide analysis of health workforce and training needs and the capacity of training institutions to meet those needs ever to be undertaken in PNG.

School of Medical and Health Sciences Strategic Plan –

The SMHS is drafting a new Strategic Plan to meet the anticipated demand to train larger numbers of health care workers following the Health Workforce Summit.  The draft Plan still needs to be costed and a prioritised implementation plan, budget and performance assessment framework developed.

Activity Rationale

Within the context of strengthening of the overall health system in PNG, the proposed Program seeks to build on Australia’s long standing assistance for medical training and specialised medical services through a more integrated program of support for immediate and longer term health workforce development needs.

Problem Analysis –

The activities described in this design document will address the following needs:

- The financial, organisational and other capacity constraints facing the SMHS, which it must address if it is to scale up and deliver adequate academic programs and strengthen its research orientation.

- The current and anticipated future shortage of doctors and other categories of HCW in PNG and the Pacific, which affects the availability and quality of health services (particularly in more remote highland and outer island communities).

- The ongoing support needed to maintain higher level in-country specialist services, and clinical training and mentoring for postgraduate academic programs across a range of procedural, non-procedural and non-clinical disciplines (which must be appropriately balanced against broader NDOH, community and development partner efforts to strengthen primary and preventive care).

Figure 2, page 20 shows how each of these areas will link with other Australian-funded assistance for strengthening HRH in PNG and the Pacific.

Activity Description

Form of Aid –

The proposed form of aid is “sectoral” support delivered through key partner institutions in the health sector – predominantly the UPNG School of Medical and Health Sciences.

Strategic Rationale –

The Program’s strategic rationale is to provide core financial and technical support to the UPNG SMHS in accordance with its Strategic Plan, to enable it to:

- address constraints in staffing, organisation and management systems, infrastructure and research capacity;

- strengthen its overall capacity to provide quality training programs that meet the needs of PNG and the Pacific; and

- provide coordinated support for postgraduate training and related specialised services in PNG.

This will help to address the shortage of health care workers in PNG and the Pacific (especially those with a rural health focus), and contribute to the achievement of the health-related Millennium Development Goals.

Objective –

The over-arching objective of the proposed Health Worker Education and Training and Specialised Services (HWETSS) Program in PNG is therefore:

To strengthen the institutional capacity of the UPNG School of Medical and Health Sciences, thereby supporting the implementation of its Strategic Plan and the development of the health workforce in PNG and neighbouring Pacific Island countries.

To achieve this objective, a long-term view is clearly required of all partners.

Approach –

The proposed Program will be implemented using a three-phased approach:

During a preparatory Transition Phase, the SMHS will expand its present MSSP management unit into a strategic Business Management Unit.  It will engage a Manager with skills and experience in the development and management of small- to medium-sized enterprises and/or health and education sector institutions.  The Strategic Plan (including projection and coordination functions for specialised services) will be finalised, costed and budgeted during this time, and an implementation plan and performance assessment framework developed.  With technical assistance from the RACS International Projects Management team in Melbourne, most remaining RACS coordination functions for the THS Project (excluding sourcing and accreditation of individual and team specialists and visiting trainers) will be transferred to the SMHS Business Management Unit.

On completion of the Transition Phase – and subject to a satisfactory preparatory financial audit and technical review of the content and structure of the Strategic Plan – the Program will proceed to a two- to three-year Implementation Phase, with core augmentation funding being provided directly to the SMHS.

Subject to satisfactory financial audits and a Mid-Term Review (MTR), and after any necessary adjustments, the Program will continue into a one- to two-year Consolidation Phase – again, guided by the SMHS Strategic Plan, annual implementation plans and budget.

Guiding Principles –

Important characteristics of the Program include:

- It will be based on the SMHS’s own Strategic Plan

- Ongoing implementation will be managed by the SMHS itself (including planning, budget management, monitoring and evaluation)

- Based on the Strategic Plan, annual implementation plans and budget, core financial support will be provided through periodic accountable cash grants to the School

- Within the annual implementation plans, Australian-funded activities will be prioritised according to the Strategic Rationale, above, with a particular emphasis on rural health

- Annual implementation plans will be realistic and supportable in-country with the resources available

- Where feasible, it will make use of UPNG’s own institutional capacity (including through the School of Business Management)

- Functionally, it will be closely linked with other areas of Australian and WHO support for HRH in PNG and the Pacific

- It will develop and maintain supportive links with Australia-based and international professional and educational organisations (noting also the regional role of Australasian professional colleges in training and accreditation of specialised health workers)

- To support feasible implementation by the School, activities will have low levels of dependency and related risk.

What will success look like?

The following outcome areas are drawn from the present draft of the SMHS Strategic Plan, which will be finalised during the Transition Phase (and therefore potentially subject to some adjustment):

- A Business Management Unit is established at the UPNG SMHS, providing it with stronger organisational management capacity.

- The UPNG SMHS has a stronger academic staffing capacity, better able to train students to meet the needs of PNG and other Pacific countries.

- The SMHS has reviewed its curricula and revised them as necessary, enabling the introduction of a 5-year medical curriculum as an early priority (with an increased practical focus on rural health).

- The SMHS has sufficient accommodation and facilities for clinical lecturers and students to enable it to provide clinical year hospital placements in centres other than Port Moresby, allowing it to increase the number of medical undergraduates from 60 to at least 80 per year.

- The SMHS has established partnerships in place with international professional colleges, societies and educational and research institutions, providing training and technical support for specialised academic programs for medical and other undergraduates and postgraduates, including international placements.

- In partnership with the NDOH, RACS and other professional colleges, the SMHS is coordinating visiting specialised (secondary and tertiary) medical services in PNG, including related training and skill transfer.

A purpose level diagram that shows how each of these outcome areas is inked to the SMHS Strategic Plan and will contribute to the overall Program goal is included at Figure 4, page 30.

Implementation Arrangements and Resourcing

Duration –

The proposed duration of the Program is 4.5 years: about 6-9 months for the Transition Phase, and about four years for the Implementation and Consolidation Phases (with possible extension, subject to satisfactory performance).  This would be the first phase of a longer-term coordinated commitment to strengthening the health workforce and health worker training in PNG.

Partnerships –

The UPNG School of Business Administration is highly regarded in-country and in the region; it represents a valuable but unutilised resource for the SMHS from within the University.  During the Transition Phase, the SMHS will establish a strategic partnership with the School of Business Management; this would bring the added advantage of close mentoring links for the Business Unit Manager from within the Business School.

Activities contributing to Outcome 2 will have the flexibility to leverage off the School’s existing and some new external professional and technical relationships, including with RACS and other professional colleges, the CICH and James Cook University.  Where unfunded through other sources, that support could be reflected and costed within the annual implementation plan and budget.

Budget –

The proposed overall budget is AUD 11 million over 4.5 years, comprising AUD 10 million from the AusAID PNG health program and AUD 1 million from the AusAID Health and HIV Thematic Group (through the Strategic Partnerships for Health Initiative; SPI).  Subject to need and favourable performance, an additional AUD 1 million p.a. may be mobilised through the SPI during Years 2, 3 and 4.

Costs of In-Country Activities –

Funding for in-PNG activities would be provided as 6-monthly acquittable cash grants.

Australia-Based Costs –

Within the overall annual budgets, approximately 35% would be allocated initially to visiting academics, specialists and clinical teams in support of outcome area 6 of the Program.  However, this proportion might vary and/or be used to support outcome area 5, depending on clinical and academic capacity and needs.

A portion of this section of the budget will be retained in AUD and released by AusAID to Australia-based implementing partners (including RACS) on the advice of the SMHS.

SMHS Business Management Unit –

The scope of SMHS management tasks is broader under this new Program than it has been for MSSP and the THS Project.  The School will need to reinforce its administrative and management capacities by employing at least one additional staff member (a Business Unit Manager) – and possibly a second (with specific monitoring, evaluation and reporting skills) – in order to meet these new requirements.  The Unit would also be responsible for developing the operational aspects of the Strategic Plan.

A management cost allowance of up to 10% of Program value is provided (see Budget at Annex VIII).

Overall Strategic Program Coordination –

The SMHS will manage and coordinate the program as an integral and integrated part of its functions as an educational institution and its delegated functions from the NDOH in coordinating visiting specialised services.

The School will be assisted by a Program Advisory Group (PAG), which will report to the SMHS Board and, through the Board, to the vice-Chancellor and UPNG Council.  The PAG will include (but not be limited to) representatives from NDOH, Department of National Planning and Management, AusAID and selected professional, education sector or academic partners.  NDOH will chair the PAG, with the SMHS hosting it and acting as Secretariat.

Performance Assessment

The SMHS has developed sound monitoring and evaluation (M&E) processes during the MSSP and the THS project.

Transition Phase –

At the end of the Transition Phase, it is recommended that a concise external technical review of the Strategic Plan and proposed implementation plan and a preparatory financial audit of the budget are undertaken.

If necessary, the School may engage an external M&E specialist to assist the Business Management Unit to develop its performance assessment framework, based on the Strategic Plan.  This represents a capacity building opportunity for the Manager and staff.

Implementation and Consolidation Phases –

No complex additional information requirements are established under this initiative.  Monitoring will be embedded within Business Unit functions, with data derived from existing budgetary information (familiar to the present MSSP managers).

Reporting would be built around quarterly activity and financial reports by the SMHS to UPNG and AusAID (with these documents partially validated by audits of cash advances).  An Annual Progress Report will be presented to the PAG, the national Board of Health (on which the Dean sits), UPNG and AusAID.

External Technical Assistance –

The overall budget also reserves some resources for audits, technical advisory support to review annual implementation plans, provision of ad hoc advice on emerging issues, and possibly assistance to AusAID and the NDOH to assess and respond to Annual Progress Reports.  Most of this support would be sourced through the AusAID Health Resource Centre and the Education, M&E and Financial Sector Period Offers.  The cost of this technical advice would be limited by an estimated maximum input of two weeks annually.

AUD 300,000 (2.7% of total Program costs over 4.5 years) is allocated to the estimated cost of supplementary monitoring, related technical assistance and the MTR.

Mid-Term Review –

The MTR is proposed for around the end of the third full year of Implementation.

Its timing coincides with an anticipated escalation in Australia’s aid budget.  Subject to satisfactory performance and harmonisation with other NDOH HRH functions, it may be possible to extend Program funding and duration to enable an increase in student intakes with little or no need for further investment in design processes or management capacity building.

Measurement of progress towards the overall Objective of the program will also be included in the TORs for the MTR.

Feasibility, Sustainability and Risk Management

Under MSSP, the SMHS has proven its capacity to manage AusAID funding in the form of acquittable cash grants; accountability has been verified by periodic audits.

Most risks are addressed by strengthening the strategic management capacity within the School, ensuring close coordination with NDOH, and providing funding to maintain supportive relationships with supportive external partner institutions.

The greatest risks to the proposed program are not internal to the type and number of activities or related to the activity managers.  The most significant risks lie external to the program (i.e. within the whole-of-government context), where program managers must rely on the support of third parties.

Stronger SMHS management capacity will provide a framework for increased GOPNG funding support – itself, the best assurance of sustainability in the longer term.

- Acronyms and Abbreviations

ARDE 	Annual Review of Development Effectiveness (AusAID)

ASHM	Australasian Society for HIV Medicine

AusAID	Australia Agency for International Development

BBV	Blood-borne virus

CBSC	Capacity Building Service Centre

CHS	Church Health Service

CHW	Community Health Worker

CICH 	Centre for International Child Health

CMC	Churches Medical Council

DFL 	Distance and flexible learning

DMC	“Directed” Managing Contractor

DNPM	Department of National Planning and Monitoring

DPAG	Design and Procurement Advisory Group, AusAID

DPM	Department of Personnel Management

DPM&NEC	Department of the Prime Minister and National Executive Council

DWU	Divine Word University, Madang

FFL 	Faculty of Flexible Learning (DWU)

FSMed 	Fiji School of Medicine

GDP	Gross Domestic Product

GMO	General Medical Officer

GOPNG	Government of Papua New Guinea

HCW	Health Care Worker

HEO	Health Extension Officer

HHTG 	Health and HIV Thematic Group (AusAID)

HIV 	Human Immunodeficiency Virus

HR	Human Resources

HRH	Human Resources for Health

HSIP 	Health Sector Improvement Program

ICAP	In Country Attachment Program

IMR	Institute for Medical Research, Goroka

M&E	Monitoring and Evaluation

MC	Managing Contractor

MDG 	Millennium Development Goal

MDR-TB 	Multi-drug resistant tuberculosis

HWETSS 	Health Worker Education and Training and Specialised Services (program)

MMed 	Master of Medicine

MMedSci	Master of Medical Science

MONAHP	Medical Officer, Nursing and Allied Health Training Project

MOTP 	Medical Officer Training Program

MPH	Master of Public Health

MTR	Mid-Term Review

MSSP	Medical School Support Project

NDOH	National Department of Health

NGO 	Non-government organisation

NHP	National Health Plan, 2001 - 2010

NRH 	National Referral Hospital (Honiara, Solomon Islands)

ODA 	Official development assistance

ODE	Office of Development Effectiveness (AusAID)

OHE	Office of Higher Education, Department of Education

OT	Operating theatre

p.a.	per annum

PAG	Program Advisory Group

PATTAF	PNG–Australia Targeted Training Facility

PDD	Program Design Document

PDOH	Provincial Division of Health

PHA	Provincial Health Authority

PIC	Pacific Island country

PIP 	“Pacific Islands Project”

PLHIV 	People living with and affected by HIV

PMGH	Port Moresby General Hospital

PNG	Papua New Guinea

PSRMU	Public Sector Reform Management Unit

PSWDI	Public Sector Workforce Development Initiative, 
Department of Personnel Management

RACS 	Royal Australasian College of Surgeons

RANZCOG 	Royal Australian and New Zealand College of Obstetricians and Gynaecologists

SIP	Service Improvement Program, 
Strategic Plan for Supporting Public Sector Reform

SPC	Secretariat of the Pacific Community

SPI 	Strategic Partnerships for Health Initiative

SMHS	School of Medicine and Health Sciences, UPNG

SWAp	Sector Wide Approach

TB	Tuberculosis

THS	Tertiary Health Services (project)

TORs	Terms of Reference

UNICEF	United Nations Children’s Fund

Unitech	University of Technology, Lae

UPNG	University of Papua New Guinea

WHO	World Health Organization

WPRO	Regional Office for the Western Pacific (WHO)

- Financial details

- AUD:			Australian Dollar

- PGK:			Papua New Guinea Kina

- Papua New Guinea financial year:	1 January to 31 December

- Australia financial year:		1 July to 30 June the following year

- Exchange rate (1 May 2008): 		PGK 1 = AUD 0.3871

- DESIGN APPROACH AND METHODOLOGY

## 1.1	Primary Design Process

### 1.1.1	Terms of Reference

The activity design (see Terms of Reference [TORS], Annex Va) took the findings of several Government of Papua New Guinea (GOPNG) and National Department of Health (NDOH) research papers, as well as AusAID project review reports, as its starting point.  A full list of these materials is given at the end of Annex Va.

It also built on a previous Feasibility Study for Human Resources for Health (HRH) in Pacific Island countries (PICs) Initiative, which visited Papua New Guinea from June 11-15, 2007.  The aide memoire from that visit is attached as Annex VI.

The design team, comprising a Medical Education Specialist (Team Leader), a Design Specialist, a NDOH Human Resources (HR) Branch officer, an officer from the Social Sector Planning Branch of the Department of National Planning and Monitoring (DNPM) and AusAID’s Senior Program Officer in Port Moresby, reviewed this written material and conducted in-country consultations in PNG with a broad cross-section of stakeholders in the area of health professional training.  The participation of NDOH and DNPM officers added valuable insights to the Team’s work.

The TORs required that the following issues be considered during the design process:

- recognising the existing links between the current Medical School Support Project (MSSP) and Phase 3 of the Tertiary Health Services (THS) project, the design should investigate how these can be strengthened;

- ensure the “medium-term” program be flexible as ultimately it will need to align with the NDOH National Health Workforce Strategy (once this is finalised);

- support to NDOH to collect and analyse health workforce data, including assistance with registrations (through the responsible professional bodies) should be considered through this Initiative;

- although the new initiative will continue under the existing model, investigate synergies that could be developed with other programs under the sector wide approach (SWAp) for health;

- strengthening the role of Australia partners such as Australian professional colleges (including Royal Australian and New Zealand College of Obstetricians and Gynaecologists; RANZCOG) needs to be considered;

- investigate the feasibility of providing support to other institutions in PNG that provide pre-service training, for not only medical but also health care workers, to play an increasing role in both pre service and continuing education; and

- strengthen regional linkages and possible development of partnerships through closer linkages with the Fiji School of Medicine (FSMed).

It is important to note that the focus of the design TORs is strengthening health systems in PNG by assisting with immediate and long term health workforce development needs.  This is a necessary narrowing of design scope that follows on from the AusAID decision to set a budget of around 2 million Australian dollars (AUD) p.a. for the new initiative.  The approach used also reflects advice given by to the design team by the AusAID Design and Procurement Advisory Group (DPAG) at the team’s pre-departure briefing.

The TORs refer to “medical training”, which indicates training of doctors.  However, the TORs also ask the design team to consider an expanded focus for the new health training initiative, which requires a broader scope than only medical training.  Accordingly, the design refers to “health professional training” or “health care worker (HCW) training” (i.e. including both doctors and other cadres of health professionals), and consideration has been given to the training needs of all groups.

### 1.1.2	Consultations in Papua New Guinea

The team undertook a two-week design mission in PNG, from 23 September to 5 October 2007.  They held initial meetings in Port Moresby with national stakeholders.  They then travelled to Mount Hagen (Western Highlands Province), Lae (Morobe Province) and Madang (Madang Province) before a final round of national level meetings in Port Moresby.  Consultations were made with three Provincial Hospitals, two Church District Hospitals, two Nursing Colleges (one of which was church-run), and one church-run Community Health Worker (CHW) School.

On 4 October 2007, before leaving PNG, the team tested proposals for activities with key counterparts during a de-briefing and presentation of its aide memoire.

## 1.2	Review and Revision of the Design

Prior to peer review, AusAID requested an external assessment of the draft design by a public health physician with experience in the design and implementation of programs of clinical support in low income countries and post-conflict environments; the TORS for this phase of the design are included as Annex Vb.

Key areas for review included:

- options for streamlining the proposed management and governance arrangements, including consideration of interactions of the proposed program with the health SWAp,

- the potential for synergies and streamlining with broader NDOH and development partner initiatives in strengthening HRH in PNG,

- options to support the longer term development of the University of Papua New Guinea (UPNG) School of Medicine and Health Sciences (SMHS) in line with its Strategic Plan and existing management capacity, and

- options for possible expansion of support to UPNG if appropriate, using up to AUD 1 million p.a. in additional funds from AusAID’s new Strategic Partnerships for Health initiative (SPI).

The consultant reviewed the draft design document and some additional reference materials (Annex Vc).  He reviewed the program and its context with the AusAID Health and HIV Thematic Group (HHTG) and PNG health team, the design Team Leader, and key stakeholders at the Royal Australasian College of Surgeons (RACS) and the Centre for International Child Health (CICH).

In Port Moresby, from 27 April to 3 May 2008, he consulted the AusAID PNG health team, senior SMHS and NDOH counterparts, and other development partners.   Adjustments to the design arising from that visit were developed in further consultation with the design team, HHTG, RACS and CIHC.

- Context and Problem Analysis

This Section of the Program Design Document (PDD) provides:

- a situation analysis of the context for the proposed activities, and

- identifies emerging issues that the GOPNG and AusAID will also address through those activities.

This analysis has direct links to the program rationale, intended outcomes and risk analysis detailed later in the PDD.  A detailed problem analysis and analysis tree are attached at Annexes II and IV.

## 2.1	Background

Australia has provided continuing support to medical training in PNG for more than 20 years.  This training has taken two forms: direct support to the medical school at UPNG, and direct supply of tertiary health services (with an emerging capacity building focus).

The TORs for this design required a careful consideration of existing Australian support to medical training in PNG, as well as exploration of possibilities for expansion of the scope of the program and the absorptive capacity of relevant partner organisations.

The proposed design reflects Australia’s ongoing commitment to supporting HRH through health worker training and supporting the delivery of specialised clinical services in PNG.  It also reflects current and emerging priorities of the Australian aid program (see Section 2.2.2, below).

### 2.1.1	Medical School Support Project

Since the late 1980s, the UPNG School of Medicine and Health Sciences has received various forms of support from AusAID – initially through activities like the Medical Officer Training Program (MOTP] and Medical Officers, Nursing and Allied Health Training (MONAHP) Project (which were managed by Australian contractors) and, more recently, through the MSSP (which is managed by UPNG SMHS itself).

Both the NDOH and the SMHS strongly endorse the assistance provided to medical education in PNG, recognising that many achievements would not have been possible without it; they are seeking a continuation of that support.

The objective of MSSP is to assist the SMHS deliver priority education programs to medical and other categories of health worker, and to build sustainable institutional capacity.  Program outputs include: training of academic and administrative staff; teaching support for Master of Medicine (MMed) students provided by visiting medical specialists; and teaching support provided by nursing advisers for students in the Bachelor of Clinical Nursing Program.  It was also intended to prepare the SMHS for a key role in the implementation of the NDOH’s HR Development Strategy.

MSSP is not a “project” as such: it does not have an external Managing Contractor, but rather provides accountable cash grants in 6-monthly tranches of around AUD 250,000.  Financial accountability measures include the submission of financial acquittals by the UPNG SMHS for each of the tranche periods, as well as periodic external audits.

MSSP was initially funded over a three-year period (to December 2005), but has now been extended to June 2008 to allow for the present design of this next phase of support.

### 2.1.2	Tertiary Health Services Project

Targeted Australian support to the tertiary health sector in PNG began in 1996 under the Provision of a Range of Tertiary Health Services to Pacific Island Countries Project (commonly abbreviated as the “Pacific Islands Project”; PIP).  The PIP was primarily a humanitarian activity rather than a development project – i.e. it provided surgical services and procedures that were not normally available in-country, but had only an incidental focus on capacity building.

PNG was included in PIP until 1998, after which time the PNG-specific Tertiary Health Services Project was established.  The purpose of the THS Project is to overcome the shortage of trained and skilled specialists which inhibits PNG from delivering essential tertiary care.  This phase of support was known as “THS Phase 2”, and ran from 1999–2001.   It comprised four components, one of which focussed on on-the-job training of local clinicians (in support of direct service provision under the other components).

THS Phase 3 commenced in 2002 and included a capacity building component.  One objective of Phase 3 was to assist PNG to move toward being self-reliant in providing surgical services.  THS Phase 3 has recently been extended – like MSSP, to accommodate the present design process – and will now finish in September 2008.

The THS project is managed by the Royal Australasian College of Surgeons out of its International Projects Office in Melbourne.  Its budget is around AUD 3.4 million over 5 years, or just under AUD 750,000 per annum.

Mechanisms to ensure effective operation and communication of the Project include a Project Coordinating Group (which meets annually in Port Moresby) and a Tertiary Health Services Committee (which also meets annually to discuss issues arising from team visits and to plan future visits).  A part-time administrative position is also supported in-country.

## 2.2	Sector and Policy Context

This part of the PDD analyses the government and health sector policy contexts within which the proposed AusAID initiative will be implemented.  The broad context is important, because it sets the backdrop to likely future changes in operational circumstances to which any new initiative will need to be able to adjust, and highlights possible future advantages and risks.  It is also an opportunity to evaluate a wide-ranging set of issues in the health sector that impinge on or depend on HR development, to ensure that all possibilities to expand the focus of the new initiative have been canvassed.

A full analysis of these issues is set out in Annex I.

### 2.2.1	PNG Policy Context

The GOPNG Medium Term Development Strategy 2005-2010 highlights health and improved service delivery as key development priorities.

The National Health Plan 2001–2010 (NHP) is the main policy document guiding health sector planning and coordination and the implementation of health services in Papua New Guinea.  It identifies preventive and clinical services, HR management and strengthening partnerships among the 8 priority health concerns for the country.

The GOPNG is undertaking a significant level of public sector reforms aimed at service improvement, and the NDOH is one of four key agencies to achieve this goal.  NDOH is spear-heading its approach through a major restructure of its Executive, to better support the newly appointed Minister and Secretary.

The Provincial Health Authorities Act (2007) is addressing the previous fragmentation of administration and financing of public health and clinical hospital services at the provincial level.

### 2.2.2	Australian Policy Context

The Papua New Guinea – Australia Development Cooperation Strategy 2006-2010 also highlights the importance of the health sector and improved service delivery.

Core priorities of the Australian aid program that are relevant to the proposed Program include:

- Initiatives that help the partner health system to deliver, including in the areas of:

  - strengthening HRH systems (training, supervision and incentives, and the underlying strategic policy, planning and management), and

  - delivery of quality preventive and clinical services (with a focus on the needs of women, children and vulnerable populations).

- Partnerships with relevant stakeholders and working within PNG systems as keys to supporting and strengthening national ownership of development processes.

- A requirement for health systems performance and the effectiveness of development assistance to be measurable and measured

The AusAID gender policy (Gender equality in Australia’s aid program – why and how; 2007) provides guidance on how the Australian Government seeks to implement and monitor its commitment to advancing gender equality in the Asia-Pacific region.

The Parliamentary Secretary for Pacific Island Affairs has identified and communicated to AusAID the importance of Australian support to two key educational institutions in the Pacific region – UPNG and the University of the South Pacific.

### 2.2.3	Aid Effectiveness and Donor Harmonisation

The Paris Declaration on Aid Effectiveness (2005), the Madang Plan of Action (2006), the Pacific Aid Effectiveness Principles (2007) and the Kavieng Declaration on Aid Effectiveness (2008) all map out a framework for:

- national leadership of development activities;

- aligning development partner support with countries’ own national development strategies, institutions and procedures;

- achieving greater harmonisation, transparency and collective effectiveness for donor funded activities; and

- results-based decision-making and accountability in development assistance.

The present design is guided by the core values and principles of these documents.

## 2.3	Problem Analysis

### 2.3.1	Overview

The Problem Statement at the peak of the Problem Tree on page 6 is provided in the TORs for the design, i.e. a shortage of appropriately educated and motivated health care workers is a major obstacle to health system performance.

A more comprehensive statement of the Problem Analysis is made at Annex II, while a more complete Problem Tree with accompanying analysis is provided in Annex IV.

While it is agreed that health system performance suffers from a lack of properly trained and motivated health care workers, there are numerous other systemic shortcomings that will need to be addressed by GOPNG and its larger budget resources if properly trained workers are to be able to perform at the expected levels.

Accordingly – and noting the resources available to this new initiative – the design looks closely at each of the main health care worker cadres and the nature of their health training needs relative to the capacity of the new initiative to effectively and practically address those needs.  The design also identifies strategic points of intervention where other aspects of the AusAID Country Program will be able to synergise with the proposed program and derive the greatest impact for its investment.

### 2.3.2	Need for a Health Workforce Plan

Within the NHP, there is a clear acknowledgement that doctors – along with other health professionals – play a crucial role in the basic health care system in PNG.

The main roles of medical practitioners are: performing critical interventions, enabling referrals, leadership, and supervision and capacity building of other health professionals.  However, there are not enough doctors in rural practice – largely a result of weak intra-sectoral planning and coordination between NDOH, Provinces, Hospitals and Church Health Services (CHSs) as rural health service providers.  Issues such as a lack of funded positions, an absence of housing or transport, poor schooling and limited continuing professional education options for staff in rural settings need to be addressed holistically by all stakeholders to improve rural health services delivery.

Despite the high priority given to HR in the NHP, NDOH is yet to formulate a Health Sector Workforce Plan for the entire health sector, i.e. a plan that takes into account the roles and contributions of Government, Church, other non-government (i.e. NGO) and private sector providers.  Without a Workforce Plan, the links between health facility development, staffing levels and training needs will remain unstructured and clinical and public health needs will not be serviced to the extent defined in the NHP.

Without a sector-wide plan, it is extremely difficult to determine what forms of health training are priorities – or even the level of graduate outputs that are required from health training institutions.  This is also noted in the SMHS Strategic Plan, which notes that “There is currently little discussion as to manpower issues and no regular communication between NDOH and SMHS in relation to student intakes”.

For example, the number of specialist doctors being trained is more than NDOH can currently employ.  NDOH has 60 specialist trainee positions available, but there will be 105 specialist graduates by 2011.  The proposed solution is for NDOH to create an additional 100 specialist positions over the next five years, and then allocate them among the provincial hospitals to ensure a more equitable distribution of specialists into the future.  This assumes that Department of Personnel Management (DPM) will support the creation of these extra positions and cover the additional salary costs.

An immediate priority under the Department’s new reforms is the Health Workforce Summit, to be held on 7-8 July 2008, which represents an opportunity to begin making links between numbers of trained health professionals needed, the types of training that are a priority, and the capacity of existing training institutions to meet these needs over the next five years.  HRH will then be the guiding theme for the national Health Forum and development partner consultations to be held over the subsequent three days, 9-11 July 2008.  This will be the first sector-wide analysis of health workforce and training needs and the capacity of training institutions to meet those needs ever to be undertaken in PNG.

A more comprehensive Health Sector Workforce Plan linking sector wide staffing and training needs alongside the proposed construction and commissioning of District Hospitals would be a high priority outcome of the Health Workforce Summit.

### 2.3.3	Health Professional Training

The design team has reviewed each cadre of health professionals to identify strategic and affordable areas for the new initiative to engage with.  This was necessary because there is no clear health sector strategy to guide or strengthen health professional training (although, as noted above, this will hopefully emerge from the forthcoming Summit).

##### Medical Specialist Officers –

The SMHS currently produces about 11 specialists annually through its Master’s programs.  A total of 164 specialists have graduated since 1976, with 61 specialists currently on the NDOH Specialist payroll under the Curative Health Services Branch, and therefore subject to NDOH appointment to hospitals.  The majority of these are attached to the Port Moresby General Hospital (PMGH).

Not all specialist tertiary services can yet be provided in-country.  However, as a result of three iterations of THS from 1996 onwards, PNG specialists can now provide all but the highest level of tertiary medical services.  This is evidence of the success of the training program and also reflects an organic transition from the delivery of humanitarian support towards capacity building during the 20 year period of Australian support.

A small volume of patient services still need to be met by visiting surgical teams under programs such as THS, or through transfers that are arranged privately or by civic organisations to other countries.  Although the SMHS Post-Graduate Committee is responsible for the majority of specialist training, visiting THS teams also provide valuable academic and clinical training and skill-building opportunities for PNG-based Master's candidates.  Furthermore, the SMHS MMed program has begun to identify lecturing and clinical training roles for members of visiting THS teams.

The combined patient service and capacity building contribution of the THS project make it an affordable complement to any ongoing support for stabilisation and rehabilitation of the SMHS, and this initiative should be continued.  However, if service delivery is to be improved, training aspects of the project need to be framed within a comprehensive Health Sector Workforce Plan.  It also needs to recognise the health system’s need for a broad range of additional human resources, including both procedural, non-procedural and non-clinical specialists, rural medicine practitioners, nurses with specialised postgraduate qualifications and skills (especially in midwifery and paediatrics), pharmacists and laboratory and radiography practitioners.

There is also good potential for PNG specialist teams to commence a regular program of specialist visits to service pre-screened patients at provincial hospitals, funded by the new initiative and complementing international tertiary service team visits.  This service delivery program would need to be coordinated with the Medical Standards Branch, NDOH and supported by standard basic medical supplies, equipment and personnel (including operating theatre [OT] nurses and anaesthesiologists).

The design team considers that this approach is affordable and will support NDOH efforts in improved service delivery across a range or curative and preventive activities.

##### General Medical Officers –

NDOH confirms that there are sufficient training positions to absorb the two-year Residency candidates graduating through the SMHS over the next four years.  However, this is not so much a result of graduate output planning by NDOH and SMHS but more a coincidence that sufficient Resident Medical Officer positions exist in NDOH institutions.

Moreover, NDOH does not promptly remove second-year Residents from the NDOH payroll when they complete their residency program.  This administrative delay by the HR Branch effectively blocks incoming first-year Residents from entering the payroll system for up to 6 months into the following year while second-year residents are found General Medical Officer (GMO) positions in NDOH.

Where GMO positions cannot be found for successful second year Residents, then employment of both first year Residents and GMO candidates cannot progress smoothly within the health system.  NDOH currently recommends that 223 additional positions be established with DPM to meet short-term health sector needs, indicating that there is a shortage of GMO posts into the future.

The design team concludes that the proposed new initiative can afford to continue to support SMHS to train Residents for GMO positions, but that this training program needs to be framed within a comprehensive Health Sector Workforce Plan if service delivery is to be improved and retained in-country.

##### Post-Basic Nursing –

A number of institutions currently offer post-basic training programs (see Annex III, Health Professional Training and Curriculum).

Among these, the Bachelor in Clinical Nursing (Midwifery & Paediatrics) and the Bachelor in Nursing (Acute Care) do not meet Nursing Council registration requirements or the clinical needs of employers (i.e. NDOH, hospitals).

With World Health Organization (WHO) assistance, steps are being taken to extend the Bachelor in Clinical Nursing (Midwifery & Paediatrics) to a two-year post-graduate program, which will provide the necessary clinical training to enable registration.

The Bachelor in Nursing (Acute Care) does not provide for the full needs of OT nurse training, but neither is this course offered at any other training institution.  Given the reported shortage of OT nurses, there appears to be a need to establish a formal in-service program – possibly using distance and flexible learning (DFL) modalities – to enable Health Extension Officers (HEOs), nurses and CHWs with sufficient work experience to upgrade their qualifications to obtain registration as an OT nurse.

Other areas of clinical training need identified during the design mission, which could potentially be met by in-service programs, include:

- Anaesthesiology;

- Post-operative paediatric nursing; and

- Intensive care nursing.

These and other possible in-service training programs need to be explored during and after the forthcoming Health Summit, to be followed by curriculum and materials development for high-priority trainee cohorts.

It may also be possible to revive the system of In-Country Attachment Programs (ICAP) to PMGH, to enable OT nurses and anaesthesiologists from the regional hospitals that will receive visiting specialist visits to train in advance to match the technical requirements of those visits.  This will allow the most effective skill transfers when they eventually work with visiting team members.

##### General Nursing –

General Nursing curriculum and assessment frameworks are overseen by the Health Curriculum Advisory and Education Committees of the PNG Nursing Council.  Ongoing recruitment and registration needs are significant.

Apart from supporting in-service training program development and costs, the design team can identify few affordable opportunities for engagement in training the undergraduate General Nursing workforce within the scope of the proposed program.

##### Health Extension Officers –

The Divine Word University (DWU), Madang currently offers a three-year program leading to a Diploma in Applied Health Sciences (Health Extension).  The course prepares HEOs to work in rural areas and District Health Centres, where they will be responsible for patient care, daily administration of the health centre, and coordination of community health services.  The course is about to be upgraded to a four-year Bachelor’s degree.

The absence of a formal career path leads many HEOs to gravitate towards medical administration.  The future development of the HEO cohort will be the subject of further discussion during the Summit.

##### Community Health Workers –

The curriculum for CHWs was revised by the AusAID-funded Capacity Building Service Centre (CBSC), and has been delivered in training institutions since 2007.  The focus of this curriculum is community based health care, which reduces opportunities for clinical training in district hospitals and health centres.  This community focus may need to be reviewed and widened to include clinical training when the revised CHW curriculum is appraised in 2010.

Given the large numbers of CHWs that would be involved and the lack of monitoring to date to assess the impact of the revised curriculum on health service delivery, there are few affordable opportunities for the new initiative to engage with the training needs of this HCW cadre.

## 2.4	Health Professional Training – Lessons Learned

Health professional training is expensive, and continuing professional development is long-term and needs to be linked to a comprehensive Health Sector Workforce Plan to be most effective and cost-efficient.

Developing mechanisms that properly link health training institutions and health sector workforce planning is the responsibility of NDOH, but these mechanisms are yet to be properly developed.  The 2008 Summit is an opportunity for NDOH and the sector as a whole to take concrete steps towards establishing these links within a comprehensive health sector framework.

It is important to note that existing health professional training institutions in PNG have a long and successful history of producing graduates who are capable of meeting the academic qualification requirements and are technically competent to serve their communities and Pacific Island countries more generally.  This is an important national and regional health sector asset, and is particularly important not only to PNG but also to the Solomon Islands, Vanuatu, Timor Leste and (for anaesthesia training) the Federated States of Micronesia.

The GOPNG continues to support a large number of health training institutions, but the number of graduates that these institutions can produce is limited by their capital development and recurrent budgets.  Currently, the output of these institutions meet PNG health sector staffing requirements and make a modest contribution to HRH development in other PICs.  These constraints limit the role that these institutions can play in both national and regional health sector capacity building.

There is additional in-country capacity to directly manage a larger volume of development funding – at the UPNG SMHS, and possibly also at other health training institutions.  If utilised, this extra capacity would allow a more comprehensive revitalisation of these institutions over a shorter time frame.  The result would be a larger and more timely contribution to health sector workforce development over the next five years, while NDOH reforms are being implemented.  Possible sources of development funding include the Supplementary Budget and development partner support.

The sustainability of these revitalisation and development programs needs to be underpinned by clear and systemic budget support for the increased recurrent and maintenance costs that these programs will create.

To date, AusAID has been a significant donor in HCW education in PNG, and has taken a long-term view of its strategic engagement.  The current programs supported by AusAID reflect 10–20 years of continuous activity and funding to develop key human capacities in the health sector.  The success of this approach is evident, as high-level clinical and technical skills have been developed and largely retained in PNG during this time.  What is not so evident is the organisational support from internal (i.e. GOPNG) resources that will be necessary to sustain these successful clinical and technical achievements into the future.

## 2.5	Factors related to the School of Medicine and Health Sciences

### 2.5.1	Constraints facing the School

The primary limitation facing the School is its inability to increase its intake of medical and other students to meet the HCW needs of regional population centres and rural communities in PNG and of neighbouring PICs.

Numerous contributory constraints can be identified:

##### Financial –

The current GOPNG allocation to the School is approximately PGK 1 million per annum – about AUD 400,000.  While this is supplemented by the MSSP budget and payment for some THS Project administrative functions from RACS, there is an ongoing lack of certainty around cash flow.

This compromises longer term planning, staff recruitment and development, and the ability of the School to absorb increased numbers of undergraduates or to undertake research.  It also places the School at a competitive disadvantage when opportunities arise to undertake consultancy activities or to conduct specific, donor-funded courses.

##### Staff Supply, Demand and Succession Planning –

The Feasibility Study (July 2007; Annex VI) noted several existing and emerging constraints in relation to staffing at the School:

- A loss of key senior academic staff, with others soon approaching retirement.  In key clinical fields some Chairs are either vacant or soon to become vacant.

- A shortage of junior academic staff in some disciplines – most notably in Mental Health and Psychiatry, Pathology and Anatomy.  Clinicians and a Consultant in Medical Education are attempting to fill the gaps.

- Loss of staff in the Division of Public Health, which is responsible for the important community and rural experience in the undergraduate curriculum in medicine.

- Absence of a career path or resources for a career in medical education.  This will require funding and partnership links with overseas institutions.  .

- Succession planning, especially for leadership, is urgently needed, together with supportive funding systems to achieve equivalence between health service and academic salaries.

##### Curriculum Development –

- Ongoing evaluation of the undergraduate program is essential, both through regular review during the undergraduate years and by following-up students in order to track their career experience.  Constraints to funding and staffing currently limit the extent of follow-up.

##### Need to Respond to Emerging Priorities –

- New challenges to the PNG health sector and health systems continue to arise.  For example, teaching about HIV prevention, HIV medicine and the broader issues of Sexual and Reproductive Health is well developed but needs to be adjusted to absorb new approaches and the rapidly evolving guidelines for clinical management in resource limited settings.  This requires sufficient academic staff who can link with the NDOH and external agencies (e.g. WHO, UNICEF, RANZCOG and the Australasian Society for HIV Medicine; ASHM).

- Multi-drug resistant tuberculosis (MDR-TB) is a rapidly emerging public health threat to PNG, the Torres Straits islands and the wider Pacific, and specific diagnostic and management approaches are needed.

- Rural experience, central to this curriculum, has been limited by funds, travel costs and facilities.

##### Infrastructure Limitations –

The Port Moresby General Hospital is the School’s principal affiliated clinical teaching campus.  However, PMGH currently accommodates not only undergraduate and postgraduate medical students, but also candidates from other Divisions and disciplines and nursing students from other institutions; its teaching environment is regarded as being saturated.

An increase in student numbers to meet both domestic and regional needs will only add to the demands on PMGH.

A former clinical teaching campus at Goroka Hospital in the Eastern Highlands closed about 10 years ago due to a lack of funding for clinical lecturers and infrastructure.  The SMHS also takes students from the Solomon Islands, where the National Referral Hospital (NRH) in Honiara has a strong academic tradition but no institutional affiliation.

The development of suitable hospital and student facilities for clinical placement outside Port Moresby is regarded as a priority.  Goroka and Honiara are provisionally identified for this purpose, but the SMHS lacks sufficient funding for both staff and infrastructure to support such a move.

##### The School’s Wider Role in the Pacific –

Neighbouring PICs – especially in Melanesia and the Micronesian archipelago – continue to look to the UPNG SMHS as an important provider of context-appropriate undergraduate and postgraduate training for HCWs.  Without additional resources and development of infrastructure, the School will not be in a position to increase the number of students it takes from the region to a level that would meet the needs expressed by the Pacific Islands Health Ministers.

The situation is exacerbated by a lack of and leakage of highly-trained clinical staff from the wider Pacific region.

### 2.5.2	Measures taken by the School to address these Constraints

- The most significant planning advance in the School is the development of a new Strategic Plan that addresses many of the recommendations the 2007 Feasibility Study.  A synopsis of the latest (April 2008) draft of the Strategic Plan is included at Annex VII.

- Ongoing limitations of the current version of the Strategic Plan are that:

- it does not have an indicative time frame;

- it does not identify the current role of the School in coordination of externally funded “THS-like” specialised services programs;

- it does not have an associated implementation plan;

- it is not costed; and

- it does not address performance monitoring or assessment.

- The Dean has indicated that the School does not have the capacity to address many of the planning, budgeting and performance monitoring aspects of the Plan, and has requested additional technical assistance in these areas.

- In 2003, the School revised its curriculum revision to a Problem Based Learning model, and there have since been four cohorts of graduates from the new program.  This is an important innovation, and the structure and organisation of clinical attachments, assessment, expanded skill development, communication skills and extensive community based experience have all been strengthened.  The content now responds to many of the priority health problems in PNG, and the social and cultural determinants of health and health care.

- The development of the Medical Education Unit has been an excellent achievement.  The Unit has successfully taken responsibility for continuity of project management of MSSP, and has assisted with ensuring the effective deployment of external visiting THS Project and other consultants.  The AusAID Consultant in the Unit is in the process of handing over responsibilities for the running of the medical curriculum to a designated national successor.

- In relation to retention, there are good examples of career development and continuing collegial support – most notably in Paediatrics.

A new MMed in Rural Health will address the needs of rural hospitals, and should be able to incorporate training opportunities in rural hospitals and community clinics.  Synergies with a similar program about to be offered through the Fiji School of Medicine are implicit but have not yet been explored.

- The Dean has satisfactorily addressed the wide differentials between clinical and teaching salaries, and this is receding as a constraint.

## 2.6	Conclusion

Although the indicative budget for the new initiative (AUD 11 million p.a. over five years; see Table 1, page 31 and Annex VIII) directs the design towards smaller, more strategic activities in health training, there will be an opportunity to increase the scope of funding in later years of the program through an additional allocation of AUD 1 million p.a. from the HHTG SPI and as a result of anticipated increases in Australia’s official development assistance (ODA) expenditure by 2010.

Consistent with the development context and AusAID priorities, the new initiative should target health system fundamentals through strengthened HRH training, planning and management.

The breadth of undergraduate and postgraduate courses offered through the UPNG SMHS, the support it offers not just to the PNG health sector but to those of neighbouring PICs, the well-established links between the present MSSP and the THS Project, the strong performance of the School in financial accountability, and the vulnerability of the School to a lack of continued funding have all directed the design team towards considering options for core support for this institution.

External factors potentially influencing performance include:

- comprehensive HRH planning by NDOH, Provincial Governments, Hospitals and Church Health Services,

- the demonstrated budget capacity of health training institutions to sustain existing gains into the future through adequate capital, maintenance and operational budget allocations; and

- quality assurance indicators that can verify that the calibre of health graduates in PNG continues to be high, and so support effective health services delivery in the basic health care system.

We also acknowledge that there are significant dependencies attached to these high-level performance indicators in the PNG health sector.  Not achieving the high-level health sector targets are part of the risk profile for the new initiative.

Performance measures that determine whether the implementing entity has achieved performance targets that are entirely under its direct control are also needed, and must be included in the performance assessment framework developed under this initiative (see Section 6).  These specific performance indicators are important for determining whether the institution can continue to be supported, even if overall health sector performance is not meeting targets.

- SCOPE FOR NEW ACTIVITIES

## 3.1	Scope and Feasibility of new AusAID activities

### 3.1.1	Existing and Emerging Considerations

AusAID flagged 7 issues for consideration when formulating the design.  The following sections summarise the results of our consultations in relation to each of these points and, where relevant, our conclusions on how they are reflected in the present design.

- Strengthening links between MSSP and THS

Over the last 3-5 years, clear links have emerged between core MSSP support for the SMHS and functional support for the MMed Program through the THS Project.  The link is provided by the SMHS coordination role for visiting academic fellows from both sets of activities, who teach and mentor SMHS students (and, in the case of THS, provide specialist trainees with exposure to higher levels of clinical training and experience).

An important difference between the two projects has been the contracting arrangements that govern their day-to-day management – MSSP is managed by the SMHS, while THS has been contracted directly to RACS.

Subject to absorption of THS coordination functions into the SMHS Strategic Plan, both sets of activities could be regarded as components of a new, expanded initiative.

From its sound performance managing the MSSP, SMHS clearly has the capacity to administer the broader set of activities.  AusAID could therefore contract SMHS to manage the comprehensive funding package for both educational and specialised services support, and SMHS could enter into a sub-contract with Australia–based providers (e.g. RACS, other professional colleges) for accreditation, coordination and logistic support for specialised services elements of the new program.

Conclusion: 
Subject to contractual agreement with Australia-based implementing partners, closer alignment between the present MSSP and THS Project functions represents a logical evolution of current approaches, and would further support the integration of development assistance activities into local institutions and structures.

- Alignment with a National Health Workforce Strategy

As previously noted, no comprehensive HRH Strategy currently exists for PNG.  The 2008 Health Workforce Summit presents an opportunity for NDOH to develop that Strategy.

Australian-funded support for the Summit currently includes technical assistance through the AusAID-funded HRH focal point in the WHO PNG office (who has engaged an HRH consultant to undertake background research and guide the preparations of Summit working groups) and a logistics coordinator engaged through CBSC.

After the Summit and a national HRH Strategy is in place, the SMHS will need to maintain close communication with the NDOH HR Branch to ensure that the courses offered and those under development meet the needs and projections of the NDOH.  In particular, curriculum review and enhancement and the development of in-service training and continuing education programs to upgrade the skills of existing staff represent the most strategic and affordable approaches to addressing medium to long-term development needs.  In this way, the leaders of SMHS and other health training institutions can engage in developing the educational elements of the Strategy.

Conclusion: 
Subject to finalisation of a national HRH Strategy, there are logical and adequate opportunities for SMHS curriculum and training course development to proceed in close coordination with the NDOH HR Branch, with technical assistance from the WHO HRH focal point.

- Expanded focus on broader health workforce needs

The TORs propose that two distinct functions are supported through the proposed new initiative:

- clinical and educational service delivery, and

- HRH policy, planning and management.

Delivery of health worker education and training and specialised clinical services is the joint role of the SMHS, the NDOH Clinical Standards Branch and the Provincial Health Authorities (PHAs), while policy, planning and management are core functions of the NDOH.

While it is important to identify how Australian support contributes in both general (i.e. “systems”) and specific ways to strengthening HRH, it would be difficult to identify a single service provider or consortium of service providers that could span both functional areas.  Figure 2 (page 20) identifies the coherence between different channels of Australian support; however, the present design focuses only on the details of the clinical and educational service delivery functions.

Conclusion: 
Broader HSS functions are addressed by other Australian-funded initiatives in PNG.  To avoid dissipating the budget of the proposed Program on too many smaller activities, the Program should retain a core focus on building the capacity of the SMHS to support service delivery aspects of HRH development in PNG – i.e. education, training, and clinical and public health practice.

- Closer alignment with the Health SWAp and HSIP

The GOPNG has implemented a sector wide approach (SWAp) to health sector financing and, in particular, the alignment of donor support with national health policy; donor funding for the SWAp is channelled through a mechanism known as the Health Sector Improvement Program (HSIP).

The HSIP has limited capacity to absorb additional programmatic expenditure and activities, and is currently struggling to maintain timely disbursement of funds under management.

Furthermore, although it trains health professionals, the SMHS falls with UPNG under the Office of Higher Education – an Education Department institution.  While the School remains an important service provider for education and training in the health sector, it would not be appropriate to “force” education sector funding into a health SWAp.

A key issue that must be addressed during implementation is effective communication between all stakeholders – especially between NDOH and the SMHS.  NDOH (Secretary and Deputy Secretaries) have acknowledged the logic of bringing “THS-like” functions under the umbrella of the SMHS Strategic Plan, and are comfortable and confident that the existing close communication between the Department and the School can be maintained.  The schedule for any specialised services visits would simply need to be jointly coordinated between SMHS, the NDOH Curative Health Services Branch and, where relevant, PHAs (or directly with provincial hospitals in those provinces without a PHA).  This would include forward projections of procurement and supply management, logistics and the staff and operating theatre time that are needed to support these visits.

Coordination of visiting professional and academic teams and individuals would need to be based around the SMHS undergraduate and MMed programs, ICAPs at PMGH (i.e. so that provincial hospital OT nurses, anaesthetists and post-operative care nurses can familiarise themselves in advance with the technical needs of the visiting teams) and clinical service and outreach needs.   Ideally, the current annual PNG and RACS tertiary service visits plans would be included and consolidated into a single activity plan for this component of the new program.  This will contribute to effective demarcation and coordination of tertiary services capacity building and patient service delivery in PNG.

Conclusion: 
It is not appropriate to bring donor funding for an education sector institution into a separate funding mechanism for a health SWAp.  Existing communication channels between SMHS and the NDOH Curative Health Services and HR Branches can be readily maintained, and will be supported by the proposed program.

- Strengthening the role of Australian partners

UPNG and the SMHS already have reciprocal relationships and agreements with a large number of Australian and other institutions.  These relationships are important to both the University and the School, and academic leaders have a strong desire to maintain and nurture them.

Existing linkages with Australian professional bodies – not only RACS but also other professional Colleges, Societies, universities, hospitals (for postgraduate placements of advanced medical, nursing and other trainees) and health training institutions – can continue to be developed and strengthened under the proposed new initiative (Outcomes 2, 5 and 6; see Section 4.3.3).  The overall strategic benefit of these linkages would be defined by the SMHS Strategic Plan.

Australian support for broader HRH and HSS strengthening (i.e. through WHO and CBSC) can start to draw in technical assistance for the Nursing Council and Medical Board in PNG from counterpart Australian professional registration bodies.

Conclusion: 
The proposed program will build on existing SMHS agreements with RACS and other partners, and has the potential to broaden the network of “buttressing” academic institutions, in accordance with the priorities of the SMHS Strategic Plan.

- Strengthening regional linkages

Stabilising and reinforcing the capacity of health training institutions to meet domestic PNG needs is currently the priority for SMHS.  Nevertheless, there will be considerable opportunities for regional faculty, academic and clinical training exchanges that will reinforce the capacity of regional health training institutions, including those in PNG (which are among the largest of those organisations).

Exchanges are already under way to optimise cooperation and collaboration between SMHS and FSMed, and the WHO Regional Office (WPRO) has offered to assist in the development of cooperation between the health training institutions in the Region.  Through the HRH focal point in the WHO PNG office, WHO may be able to identify opportunities to bring the NDOH HR Branch closer to the evolving Pacific HRH Alliance (which has its Secretariat at the WHO Office for the South Pacific in Suva, Fiji).

Conclusion: 
The proposed Program has the potential to build on regional linkages for HRH planning, management and training, in accordance with the priorities of the SMHS Strategic Plan.

- Expanded focus

This is included in discussion under issues for consideration 2 and 3, above.

Conclusion: 
The proposed Program will focus more on integration and consolidation of SMHS functions around service delivery in health worker education and training and specialised clinical services.  Australian support will naturally be incremental, but it is also important to maintain a clear focus on the basics of institutional support before becoming too expansive.

### 3.1.2	Rationale for a Health Training Support Program

Provision of health services, especially to vulnerable groups such as women, children and people living with and affected by HIV (PLHIV), requires well trained health professionals to guide diagnosis and treatment, and to lead the process of service improvement.

It is acknowledged that there are many operational shortcomings that adversely impact on rural health service delivery in PNG.  However, addressing these shortcomings needs the involvement of trained health professionals who are capable of judging the minimum standards of care and the best means of delivering them.

Finding ways to resolve the operational impasses that affect rural health service delivery is the responsibility of NDOH and provincial governments, and requires resources that are beyond the scope of the proposed initiative.  However, training targeted groups of future health leaders and ensuring that this training equips them to meet the needs of basic health system planning and development in PNG is within the scope of the new program, and offers a valid means of improving health service delivery in the longer term.

## 3.2	Principles, Concept and Rationale for Australian Support

Discussions in-country and a review of the relevant literature suggest the following guiding principles for the proposed intervention:

##### Activities should build on existing donor and GOPNG initiatives, and be viewed in a long-term context –

Activities should build on past AusAID activities in PNG and the new Minister and Secretary for Health’s desire to shape reforms in the PNG health sector.  It is strongly suggested that activities be viewed for Outcome purposes in at least a 10 year context.

##### Activities should be supported at both a central and a sub-national level –

Without a sound structure and guidance for a Health Sector Workforce Strategy in NDOH, efforts to improve local capacity and implementation is likely to be fragmented and may lead to undesirable outcomes, such as an over-supply of some categories of health worker and an under-supply of others.  Without developing capacity at the sub-national level to deliver services, the service delivery goals of the health sector will remain unrealised.

##### Adoption of an integrated, institutional- and system-strengthening approach, rather than a project form of aid –

The health workforce and the preventive and clinical care they provide are central elements of every health system.

The WHO Framework for Action (2007) defines the “building blocks” of health systems (Figure 1, page 19) that need to be in place to address the urgent need for improved system performance.

Figure 1:

The six building blocks of a health system: aims and desirable attributes

Source: World Health Organization. Everybody’s business: strengthening health systems to improve health outcomes (2007).

The health workforce needs to respond to national policy, the prevailing epidemiological environment and emerging external factors.  The numbers and skill mix among the health workforce should enable health workers to address those national (and potentially also regional) needs, and they should be fairly and equitably distributed, competent, and productive.

Clinical and public health services should deliver effective, safe, quality personal and population-based interventions to those who need them, when and where they are needed, and with a minimum waste of resources.

The present design addresses integrated support for the “Health Workforce” and “Service Delivery” components of the PNG health system (Figure 1).

In PNG, health worker training also needs to be seen in the context of the Government’s public sector and health sector reforms.  Working with and through national partners and institutions is supportive of the GOPNG Medium Term Development Strategy 2005-2010 and consistent with the PNG – Australia Development Cooperation Strategy 2006-2010.

##### Support for a guiding coalition of key stakeholders for HRH policy development –

Under NDOH leadership, the HRH Summit presents an opportunity to bring together a range of key stakeholders: UPNG, DWU, CHSs, other health training institutions, professional registration bodies, Provincial Health Authorities and hospital administrations.

Australian support for this “coalition” would be directed through channels other than the budget attached to the present design.  However, support for SMHS should be seen in the overall context of AusAID support for strengthening HRH and health systems in PNG and the Pacific.

A conceptual framework and rationale for Australian support is summarised in Figure 2.  (Support funded through the present design is indicated by the blue coloured boxes, while support funded through other mechanisms is indicated by the grey boxes).

Figure 2:

Concept and rationale for AusAID support for 
human resources for health in PNG and links to the wider Pacific

AusAID support for HRH in PNG – i.e. the Health Workforce “building block” in the Health System

Revised

Curriculum

Academic Staffing and Research

Training and Service Delivery

Pacific

HRH

Alliance

Improved

Infrastructure

Policy and Planning

UPNG School of Medicine and Health Sciences (support via Strategic Plan)

Specialist Services, Mentoring

Capacity Building Service Centre

HSS and HRH Focal Points at WHO PNG

Training,

Skills Transfer

Corporate

Governance

SERVICE DELIVERY and HRH OUTCOMES

Specialist Services – Improved Training – More HCWs – Better HRH Planning

HR

Branch

Clinical Standards Branch

NDOH

Health Workforce

Planning and Projection

MDGs 4, 5 and 6

Professional Registration Bodies

- DESCRIPTION OF THE PROPOSED PROGRAM

## 4.1	Guiding Principles, Policies and Criteria

### 4.1.1	The SMHS Strategic Plan

The current draft of the Strategic Plan has a primary focus on SMHS capacity and systems development.  It identifies the following as areas of high priority:

- Building the School’s training capacity to address ongoing shortages of trained health professionals in PNG and the Pacific region, which will require:

  - engagement of additional staff and staff training, including through visiting professors and lecturers from affiliated institutions, and

  - establishment of additional clinical teaching campuses, initially at Goroka and subsequently at Honiara.

- Promoting excellence in undergraduate teaching and training, which will entail:

  - progressive curriculum review, including extension of the duration of undergraduate medical training from four to five years,

  - an increased focus on rural health, and

  - continuing professional development for staff.

- Promoting excellence in postgraduate training, across all disciplines (medicine, nursing, dentistry, diagnostic imaging, medical laboratory science and pharmacy)

- Promoting excellence in research, positioning the School as an important regional medical research institution.

The Plan does not currently identify “THS-like” functions.  However, the Dean, key NDOH counterparts and SMHS academic staff all identify this as a natural “fit” for the School and an extension of current functions.

An initial priority of the proposed Program is to finalise development of the Strategic Plan (including coordination and planning of specialised services support) and the associated costs, budget and first annual implementation plan.

### 4.1.2	Principles and Priorities

The proposed program embraces the following core principles and criteria:

- It will be based on the SMHS’s own Strategic Plan, which (in the current draft) has clear links to the NHP and HSIP

- Ongoing implementation will be managed by the SMHS itself (including planning, budget management, and monitoring and evaluation; M&E)

- Based on the Strategic Plan, annual implementation plans and budget, core financial support will be provided through periodic accountable cash grants to the School

- Within the annual implementation plans, activities will be prioritised according to the criteria outlined in Section 4.1.1, above, with a particular emphasis on rural health

- Annual implementation plans will be realistic and supportable in-country with the resources available

- Where feasible, it will make use of UPNG’s own institutional capacity (e.g. through the School of Business Management; see Sections 4.3.3, 4.4.1 and 5.1.3, below)

- Functionally, it will be closely linked with other areas of Australian and WHO support for HRH in PNG; through the Pacific HRH Alliance, it will also develop secondary links to AusAID’s evolving Health Systems Strengthening in the Pacific initiative

- It will maintain close links with RACS, CICH and RANZCOG, given those organisations’ strong interest and established support role secondary and tertiary services and training in PNG, and the role of RACS as the pre-eminent provider of training and accreditation in the procedural specialties in the Asia-Pacific region; RACS’ strong networking among other professional Colleges and Societies also positions it well to provide broader institutional support as the SMHS’s capacity matures

- To support feasible implementation by the School, activities will have low levels of dependency and related risk

### 4.1.3	Australian and International Agreements

- Australian Policy and Priorities for Development Assistance –

In developing the proposed program of support, we have been clearly guided by the relevant current priority placed by the Australian aid program on “investing in people”.  In relation to specific areas of focus for Australian development assistance in the health sector, it addresses HRH development and management, quality of care and supporting country-specific health priorities and, indirectly, reducing vulnerability to emerging infectious diseases and addressing the needs of women and children.

The program also aligns well with recommendations of the Annual Review of Development Effectiveness (ARDE, 2007), which highlights improved service delivery as an evolving, additional priority and a key area of need in the health and education sectors in the region.

- Regional and International Priorities and Agreements –

In seeking to deliver assistance through the SMHS’s own Strategic Plan, we have been guided by the Kavieng Declaration on Aid Effectiveness, the Pacific Aid Effectiveness Principles and other relevant international agreements (see Section 2.2.3), which map out a framework for national leadership of development activities and aligning development partner support with national and institutional priorities, strategies and mechanisms.

Health sector workforce strategies in the Pacific have also been guided by the Pacific Health Ministers Meetings, with the long term support of regional and international agencies like WHO and the Secretariat of the Pacific Community (SPC).  Relevant regional policy and strategic guidance is provided by the WHO Regional Strategy on Human Resources for Health (2006-2015) and the Pacific Code of Practice for Recruitment of Health Workers, and The Migration of Skilled Health Personnel in the Pacific Region (2004).

In supporting HRH development, the program will contribute to the health-related Millennium Development Goals (MDGs 4, 5 and 6).

## 4.2	Selection of the Form of Aid Delivery

### 4.2.1	Preferred Form of Aid

- A Program implemented through Core Funding and Technical Support for SMHS

The Governments of PNG and Australia recognise that support for program approaches does not imply a single or specific means of funding.  A range of aid modalities can be used within a program approach, including traditional projects, technical assistance, earmarked financing, pooled financing, sectoral budget support, and general budget support.

Based on the rationale described in Section 3, and following careful consultation with NDOH, the Vice-Chancellor of UPNG and the SMHS, we believe that it will be feasible to continue to provide core support to the SMHS to develop, finalise and implement its own Strategic Plan.  The goals of this Strategic Plan are aligned with national priorities, and coordination mechanisms already exist between the School and the NDOH Clinical Standards and HR Branches.

Absorption of “THS-like” functions into the Program – i.e. supporting the development of specialised clinical services – would continue the organic process through which the MSSP and the THS Project have been drawing closer over recent years.

To minimise bank charges and exchange rate risk to AusAID and Australia-based technical partners (e.g. RACS and other professional colleges – subject to SMHS’s internal planning and requirements, which may change from year to year) under a SMHS sub-contract,

AusAID would maintain a separate funding agreement (in AUD) with partner colleges and institutions.  SMHS would simply notify AusAID when the partner has satisfied annual planning and/or acquittal of advance requirements, after which AusAID Canberra would release the next tranche of funds to the partner’s operating account.

SMHS and AusAID would retain some provision for independent review, or audit, of contract advances to Australia-based partner institutions.

### 4.2.2	Other options examined (but not recommended)

- A traditional Managing Contractor approach

This involves appointing a technically suitable managing contractor to administer funding, procurement and sub-contracting arrangements on behalf of AusAID and SMHS.  The overhead cost of appointing a managing contractor is consistently 30% of the budget, which would be AUD 3.3 million over 5 years for an AUD 11 million budget.

The design team considers that this is an unacceptable cost in terms of activities that would need to be foregone, and would potentially undermine SMHS capacity growth and reverse the relationship with RACS that has been built during the MSSP and THS projects.

Accordingly, we do not recommend this approach to management and financing arrangements for the new initiative.

- A Directed Managing Contractor approach

Another management option is that of using a “Directed” Managing Contractor (DMC).  Adoption of a DMC model would require AusAID Port Moresby to recruit an in-house Medical Education and Training Advisor to act as Program Director, supported by a technical managing contractor to administer funding, procurement and sub-contracting arrangements of this program.

This approach would provide AusAID with education and training advice as needed, but the existence of both AusAID specialist expertise and a layer of contractor management would substantially increase the overall cost of management inputs – more so than the traditional managing contractor model.  Moreover, this approach is usually adopted for larger value programs with clear political engagement roles for AusAID, which is not the case under the proposed initiative.

We do not recommend the DMC approach to AusAID, as the higher cost is not justified.

- A ‘Facility’ approach

The relatively small value of the proposed program suggests that any management approach that attracts higher overhead costs is not justified.  AusAID’s experience with technical assistance facilities is that they carry significant overheads (30% or more of the value of program activities), and it is sub-economic to establish a facility when the gross value of the program is around AUD 10-11 million p.a.

We support this analysis; we believe that the size of the proposed initiative is too small to warrant establishment of a stand-alone Facility, the cost of doing so is not justified, and that it is too technically specialised to fit under existing AusAID facilities.

- A Charter Board (Trilateral Partnering) approach

The Charter Board (or Partnering) approach to program management was rejected on the grounds that, for a relatively small value but complex activity, this approach would impose a high ongoing management load for GOPNG, AusAID and implementing partners (regardless of whether this was an institutional partner like the SMHS or a managing contractor).

- A “Buttressing” (Twinning or Consortium) approach

The support of regional Institutions will remain important to the School.  However, contracting AusAID assistance directly and exclusively through Australian or other international “twinning” institutions (or a consortium of institutions) carries two important disadvantages:

- it potentially bypasses SMHS leadership in the use of Program resources, and

- it carries the significant potential risk of supply-driven distortions to the intended activities and outcomes.

External institutional relationships continue to provide important support to the School; these include RACS (for post-graduate training and mentoring in the procedural and other specialties), James Cook University (for tropical public health), the CICH at the University of Medicine (for paediatrics and child health) and RANZCOG (for reproductive and maternal health).

We believe that, within the proposed model of core budget support, an adequately resourced SMHS has the capacity to maintain and develop its own institutional relationships (including procuring expertise from other institutions where necessary).

(This is captured under Outcomes 2 and 5, Section 4.3.3, below)

## 4.3	Objective, Rationale and Intended Outcomes

### 4.3.1	Objective

The over-arching Objective of the proposed program is:

To strengthen the institutional capacity of the UPNG School of Medical and Health Sciences, thereby supporting the implementation of its Strategic Plan and the development of the health workforce in PNG and neighbouring Pacific Island countries.

### 4.3.2	Strategic Rationale

Its over-arching strategic aims are:

To provide core financial and technical support to the UPNG School of Medical and Health Sciences, to enable it to:

- address constraints in staffing, organisation and management systems, infrastructure and research capacity;

- strengthen its overall capacity to provide quality training programs for the health workforce that meet the needs of PNG and the Pacific; and

- provide coordinated support for specialised (secondary and tertiary) medical services and related training in PNG,

… in accordance with the SMHS Strategic Plan, thereby helping to address the shortage of health care workers in PNG and the Pacific (especially doctors, and especially those with a rural health focus) and contributing to the achievement of the health-related MDGs.

By supporting the School to achieve the goals and objectives of its Strategic Plan and helping to develop the health workforce in PNG, the proposed program will contribute to the achievement of the Goal of the 2001–2010 NHP:

To improve the health of all Papua New Guineans through the development of a health system that is responsive, effective, affordable, acceptable and accessible to the majority of the people.

### 4.3.3	Intended Program Outcomes

Australian support will contribute to the following outcome areas, which are drawn from the present draft of the SMHS Strategic Plan.

The Strategic Plan will be finalised during the Transition Phase (see Section 4.4), and will therefore be potentially subject to some further adjustment.

- Outcome Area 1 –

A Business Management Unit is established at the UPNG SMHS, providing it with stronger organisational management capacity.

- AusAID support for this outcome area will take the form of direct funding to SMHS to engage a Business Unit Manager, and additional staff and external technical expertise as necessary (including with M&E skills).

- The Business Unit Manager will be engaged in consultation with the UPNG School of Business Management.  An ideal candidate would be a recent graduate from either the Master of Strategic Management or Master of Business Administration program who has a health or education sector background, or a mature (but not necessarily mature-age) student who is currently enrolled in either program.

- This is a new strategic approach to enable the School to:

  - leverage off existing business management expertise and support within the University,

  - manage the increased resources that will accrue from the new program,

  - effectively plan and cost implementation of all elements of the Strategic Plan,

  - monitor and evaluate progress against the Strategic Plan, and

  - respond in a more ‘entrepreneurial’ manner to externally funded training and educational needs and opportunities (e.g. training funded through the Global Fund to fight AIDS, Tuberculosis and Malaria), potentially institutionalising or incorporating the content of those courses into School curricula.

- Outcome Area 2 –

The UPNG SMHS has a stronger academic staffing capacity, better able to train students to meet the needs of PNG and other Pacific countries.

- AusAID support for this objective will take the form of direct funding to SMHS to contract and manage a series of suitable Visiting Professors and other academic staff to meet SMHS short-term teaching needs.

- Funding will also allow the School to proceed with its recruitment campaign for 16 additional academic staff (with appointments being confirmed over the next two years) and address succession planning needs.

- Research capacity will be supported by stronger academic staffing capacity and better opportunities through the Business Management Unit.

- This will maintain and further develop MSSP-like support, especially for identifying gaps and extending support to weaker Divisions in the School.

- Outcome Area 3 –

The SMHS has reviewed its curricula and revised them as necessary.

- This will enable the introduction of a 5-year medical curriculum as an early priority (with an increased practical focus on rural health)

- This will maintain and extend MSSP-like support.

- Outcome Area 4 –

The UPNG SMHS has sufficient accommodation and facilities for clinical lecturers and students to enable it to provide clinical year hospital placements in centres other than Port Moresby (e.g. Goroka, Honiara), allowing it to increase the number of medical undergraduates from 60 to at least 80 per year.

- This will maintain and extend MSSP-like support.

- In addition to increasing the number of medical undergraduates, this will also support possible increases in other categories of health worker trainees.

- Outcome Area 5 –

The SMHS has established partnerships in place with international professional colleges, societies and educational and research institutions, providing training and technical support for specialised academic programs for medical and other undergraduates and postgraduates, including international placements where relevant and suitable.

- In addition to maintaining and extending THS -like support, this will also have the scope to support integrated health service and workforce development in areas like reproductive health (including postgraduate midwifery training), paediatrics, and non-procedural specialties like public health.

- The partnerships will provide support for the SMHS to implement and strengthen its Strategic Plan.

- Partnerships may be with both Australian and non-Australian organisations.

- Outcome Area 6 –

In partnership with the NDOH, RACS and other professional colleges, the SMHS is coordinating visiting support for specialised (secondary and tertiary) clinical patient services in PNG, including related capacity building (through training, skill-building and international placements) in support of senior academic programs for medical and other graduates.

- Relevant coordination functions will be delegated from the NDOH and absorbed into the SMHS Business Management Unit.

- The Business Unit will liaise with national and regional facilities to ensure that the visits of teams and individuals are appropriately aligned with the School’s own under- and post-graduate academic programs and related clinical service needs and demands.

- The Unit will assume reporting responsibilities for individual and team visits.

- RACS and other professional colleges will continue to source and accredit visiting specialists and teams to contribute visiting Fellow services, and will assist in identifying and facilitating international placements for advanced trainees.

- Visits by procedural specialists will take place in the context of PNG clinicians being increasingly able to meet the majority of tertiary patient service needs, and a correspondingly reducing level of need for international team visits.

- Visits to Regional Hospitals outside Port Moresby will need to take into account the ability of the “base” and the hospital being visited to provide equipment, nursing and post-operative care.

- Planning for RACS visits will need to be properly coordinated with:

  - SMHS academic programs;

  - the schedule of PNG specialist team visits to perform tertiary services in Regional and Provincial Hospitals; and

  - a program of advance ICAPs to PMGH for Regional and Provincial Hospital anaesthetists and OT and post-operative nurses to ensure that they gain the requisite skills to support visits by both PNG specialist and RACS teams.

The purpose level causal linkages between Australian funding support, the UPNG SMHS Strategic Plan, continued technical support through professional colleges and societies (including RACS) and the intended Outcomes of the Program are summarised in Figure 4 (page 30).

## 4.4	Phasing of Australian Support

### 4.4.1	Transition Phase (6-9 months)

It is proposed that Australian support for the program be phased incrementally, and will be supported by prospective and regular follow-up audits and technical review.

This is summarised schematically in Figure 3 (page 28).

Figure 3:

Suggested Phasing of Australian Inputs and the Program of Support for 
Health Working Education and Training and Specialised Services in PNG

Audit

Phase 1

Transition

Phase 2

Implement

Review

Phase 3

Consolidate

From July 2008, continuing for ~6-9 months

2009-2010

2011-2012  →

The following activities would be prioritised during a preparatory Transition Phase:

- Liaison with School of Business Management

  - Recruitment of Business Unit Manager

  - Establishment of organisational support and mentoring linkages with the UPNG School of Business Management

- Finalisation of SMHS five-year Strategic Plan

  - Costing of activities

  - Development of first annual Implementation Plan

  - Development of a monitoring and reporting framework for the first annual Implementation Plan (with external technical assistance as necessary), and commencement of 6-monthly reporting in accordance with this framework

- With support from RACS International Project Management Unit, transfer of current THS Project projection, planning, coordination and reporting functions from RACS to the SMHS Business Management Unit

- Engagement of additional staff member(s) for the Business Management Unit (as necessary)

During this time, current MSSP- and THS Project-like services would continue, with base Australian funding maintained at current levels as for those projects (see also Section 4.5, page 31 and Annex VIII).  However, the budget would be augmented to cover the cost of establishing the Business Management Unit, recruiting additional staff and related other costs.

In parallel with establishing the SMHS Business Management Unit, additional resources would also be available to help accelerate the School’s ongoing recruitment campaign for additional academic staff to fill current and projected vacancies, and to engage external technical assistance in performance assessment (as necessary).

### 4.4.2	Audit and Technical Review (late 2008 or early 2009)

Late in the Transition Phase, a financial audit and technical review would be conducted to:

- Review the final draft of the Strategic Plan, first annual implementation plan and budget,

- Review the proposed monitoring and 6-monthly reporting processes against the Strategic Plan, and

- Provide technical support and assistance as necessary to finalise these steps.

The team would include both financial (audit) and technical (development assistance and/or medical education) expertise.

Financial and auditing skills would contribute to a financial “health check” of the proposed implementation plan and budget, while technical expertise would be important to provide necessary support and capacity building for the School in operationalising its Strategic Plan.

### 4.4.3	Implementation Phase (2009-2010)

- Core Funding and Other Support for SMHS –

Subject to a satisfactory audit and review (and following any necessary adjustment), annual tranches of supplementary Australian funding would be made available to augment other resources for implementation of the Strategic Plan.

The value of Australian augmentation funding would be determined by the School’s own budget and balanced against other sources of funding and revenue.

Once new academic appointments are confirmed, the focus for Outcome Area 2 will switch towards providing support for the ongoing professional development of newly appointed faculty members.  The emphasis will be on supervising Doctorate, Masters and other postgraduate programs for these teaching staff.

This transition is an essential one for the program to make, as it shifts the emphasis of Australia’s support from one of capacity delivery under MSSP and the Transition and early Implementation Phase of the program towards capacity development during its final three years.  This is an important systemic development in the health sector, and can only occur where SMHS is able to recruit and fill the 16 vacant academic posts in its establishment.

It is hoped that some early appointments can be made in years one and two, and that academic development can begin more-or-less immediately.

Fiduciary management and implementation during the first full year of implementation would be monitored 6-monthly through the School’s own reporting framework (set up during the Transition Phase) an annual audit in late 2009.

Figure 4:

Purpose level rationale for the new AusAID Program of Support for 
Health Worker and Training and Specialised Services in PNG

Strategic Rationale for Australian Support:  To provide core financial and technical support to the UPNG School of Medical and Health Sciences in accordance with its own Strategic Plan, thereby helping to address the shortage of health care workers in PNG and the Pacific and supporting the quality and availability of specialised (secondary and tertiary) medical services in PNG

Transition Phase

Outcome Area 1

Business Unit established and operational

Annual Implementation Plan

and Budget

SMHS 5-Year Strategic Plan

Budget and M&E Framework

UPNG School of

Business Management

RACS International Projects Management Unit

NDOH
Human Resources Branch

NDOH
Clinical Standards Branch

Implementation Phase

Outcome Area 5
Strategic partnerships

Outcome Area 6
Coordination of specialised medical services, including related training and international placements

Outcome Area 2
Stronger
academic staffing, research capacity

Outcome Area 3
Curricula revised; 
5-year medical curriculum introduced

Outcome Area 4
Clinical campus in Goroka and/or Honiara

Delivery of Academic Programs

Specialised Clinical Services

Corporate Governance

Improved Infrastructure

Revised Curricula

Research

Increased number of medical undergraduates

Support for achieving the Goal of the National Health Plan and
contribution towards achieving MDGs 4, 5 and 6

- Specialised Services and Training –

These activities will continue the maturation of the THS Project towards capacity building of postgraduate specialist doctors, balanced with the provision of tertiary level patient services.  However, it takes place in the context of:

- PNG specialists being increasingly able to meet the majority of tertiary patient services needs (and hence a correspondingly reducing level of RACS team visits being needed), and

- the School addressing key areas where it still struggles to produce the required number of graduates and provide postgraduate programs in areas (e.g. public health, non-medical cadres of health worker).

Activities will be reflected under Outcome Areas 6 and 5; the progressive integration of SMHS coordination functions and RACS service delivery functions (for both training and clinical care) will jointly contribute towards the achievement of Outcome Area 6.

### 4.4.4	“Mid-Term” Review (late 2010)

Towards the end of the second full year of implementation, it is proposed that a formal technical and financial Review be conducted.  The Review team would include:

- a financial management expert (possibly the same domestic or international auditor engaged to conduct the audits at the end of the Transition Phase and in late 2009), and

- a technical expert with expertise in medical education and/or health service delivery in resource-limited settings (to be engaged through the AusAID Health Resource Centre).

As with the review towards the end of the Transition Phase, the purpose of the MTR would be to undertake a financial “health check” of program implementation and to provide technical support and assistance in further developing and continuing to operationalise the School’s Strategic Plan.

### 4.4.5	Consolidation Phase (2011 onwards)

Subject again to a satisfactory audit and Review process (and following any necessary adjustment), implementation would continue to be guided by the SMHS Strategic Plan, annual implementation plans and budget.

It is anticipated that, by this time, additional financial resources would be available through the expanding Australian aid program, and that these could be drawn into the Program budget if the resources defined in this design document have been expended and satisfactorily acquitted.

It is essential that AusAID takes a medium- to long-term view of assistance for the UPNG SMHS – a minimum of 10, and probably 15 years.

## 4.5	Proposed Australian Budget

The present design is for an initial 4.5 year program of support.

The recommended total budget over the duration of the program is AUD 11 million (representing AUD 10 million from the AusAID PNG health sector budget and AUD 1 million from the HHTG Strategic Partnerships Initiative; SPI).

Subject to favourable performance, an additional AUD 1 million p.a. may be mobilised through the SPI during Years 2, 3 and 4.

The overall core budget and its indicative (i.e. approximate) phasing are summarised in Table 1, below.  (A more detailed budget is included at Annex VIII).

Table 1:

Gross Indicative Core Budget (in AUD, excluding possible SPI augmentation in Years 2-4) and approximate Phasing for the new AusAID Program of Support for the UPNG SMHS and Specialised Services in PNG, by Year of Implementation

| Phase (Year) | Outcomes 1-5 (SMHS) | Outcome 6 (RACS, SMHS) | Total |  |
| --- | --- | --- | --- | --- |
| Transition |  |  |  |  |
| July-December 2008 | 425,000 | 425,000 | 850,000 |  |
| Implementation |  |  |  |  |
| January-December 2009 | 1,600,000 | 850,000 | 2,450,000 |  |
| January-December 2010 | 1,750,000 | 850,000 | 2,600,000 |  |
| Consolidation |  |  |  |  |
| January-December 2011 | 1,600,000 | 850,000 | 2,450,000 |  |
| January-December 2012 | 1,500,000 | 850,000 | 2,350,000 |  |
| Audit and Review |  |  | 300,000 |  |
| TOTAL (AUD) | 6,875,000 | 3,825,000 | 11,000,000 |  |

AUD 6.875 million (62.5%) will be directed towards Outcomes 1-5 of the Strategic Plan; AUD 3.825 million (34.8%) will be available to cover the costs of visiting specialists, teams, logistics and clinical placements in Australia, New Zealand or elsewhere; and AUD 300,000 (2.7%) will be reserved for audit costs, technical advisory inputs and the MTR.  The distribution of the budget for Outcome 6 between the SMHS and international technical partners (e.g. RACS, other colleges) will depend on the balance between in-PNG and in-Australia activities and costs; this will be determined during planning and consultation between the School and its partner institutions during the Transition Phase and each subsequent annual planning process.

Funds will be made available to the SMHS on the basis of the budget developed as part of each Annual Implementation Plan.

A degree of flexibility in allocation of funds across priority areas and some year-on-year variation will be necessary; hence, the phasing in the budget in Table 1, above needs to be viewed as indicative only.  It shows annual expenditure being relatively evenly spread over the Implementation and Consolidation Phases, but with a small peak in 2010 and into 2011 to reflect anticipated expenditure on infrastructure for the satellite campuses in Goroka and/or Honiara; we believe this is realistic.

Depending on the evolution of implementation capacity in the School, it may prove possible to expend the budget for future years (e.g. for the Consolidation Phase) earlier than indicated in Table 1 or Annex VIII.  Successful early expenditure of the budget and a satisfactory MTR would potentially trigger the release of additional augmentation funding from AusAID PNG or the HHTG Strategic Partnerships Initiative.

- MANAGEMENT AND FINANCING ARRANGEMENTS

## 5.1	Rationale for Delivery and Financing Modalities

### 5.1.1	Track Record

Since 2003, under the MSSP, the UPNG SMHS has proven its capacity to manage AusAID funding in the form of accountable cash grants.  This capacity for funds and activity management has been maintained by a minimal staffing structure, has proven flexible enough to adapt to emerging needs and changes in schedule, and is very cost effective.  The design team considers that this proven performance reflects an ongoing commitment of SMHS to efficiency, transparency and accountability years, and that this commitment should be supported under the new Program.

### 5.1.2	Appropriateness of Accountable Cash Grants

Accountable cash grants are appropriate when:

- the specific inputs and activities to be funded are not known in advance; and/or

- significant flexibility is required in terms of the timing and scope of financial allocations (but within agreed overall parameters); and/or

- decision making on the allocation and management of funds is to be made by those ‘on-the-ground’; and/or

- there are appropriate systems and safeguards in place to maintain adequate accountability.

The SMHS capacity and the parameters of this design indicate that this is the best funding mechanism to support the selected Form of Aid for this Program.

### 5.1.3	Responding to New Demands on SMHS Systems

The scope of management tasks under this new initiative is broader than under MSSP – it includes higher levels of effective communication and coordination with a wider range of stakeholders.

We therefore believe that SMHS will need to reinforce its administrative and management capacities by employing at least two additional staff (with specific management, liaison, reporting and evaluation skills) in order to meet these new requirements.

We are of the opinion that SMHS is capable of identifying and recruiting such staff to support the development of these additional capacities.  We also believe that the UPNG School of Business Management – which is well regarded in the region and has recently achieved international accreditation – is an unutilised source of potential strategic and management expertise for the SMHS.  We propose that links between the two Schools be developed during the Transition Phase, with a view to engaging as Business Unit Manager – possibly a current candidate or a recent graduate from one of the School of Business Management’s postgraduate programs.

The cost of the additional employees would be funded initially by the new Program, but would migrate on to the UPNG payroll by end-of-program.

### 5.1.4	Relationship with the Health SWAp and HSIP

As noted at Section 3.1.1, while medical education activities are supportive of the health SWAp, there is no imperative or rationale to “forced” funding for them into the HSIP.

Support for clinical service provision that occurs as part of postgraduate professional training would simply need a memorandum of understanding between the NDOH and the Office of Higher Education (OHE), National Department of Education.

## 5.2	Stakeholder Management of the Program

### 5.2.1 Overview

We recommend that the Program be managed as series of AusAID accountable cash grants to SMHS, alongside direct contracting of key services providers.

The various management arrangements called for by the new Program are summarised in the following Table:

Table 2:

Management and Resourcing Arrangements for the new AusAID Program of Support
for the UPNG SMHS and Specialised Services in PNG, by Outcome Area

| Outcome Areas |  | Management Method | Resource implications |
| --- | --- | --- | --- |
| 1-5 | 1 Business Management Unit established at the SMHS, resulting in stronger organisational and management capacity | Accountable Cash Grants to SMHS, acquitted on a quarterly basis and reported against Strategic Plan indicators 6-monthly | SMHS Business Management Unit to manage, in consultation with AusAID Port Moresby |
|  | 2 Stronger academic staffing capacity at SMHS, including strategic institutional partnerships |  |  |
|  | 3 Five-year MB BS curriculum introduced, with increased focus on rural health: other curricula reviewed and revised as necessary |  |  |
|  | 4 Accommodation and facilities for clinical year hospital placements established in centres outside Port Moresby |  |  |
|  | 5 Supportive strategic partnerships established |  |  |
| 6 | 6a SMHS coordinating specialised medical services, including training and international placements for postgraduate academic programs | In-PNG Specialist Visit Annual Activity Plan to be prepared. Accountable Cash Grant to SMHS, acquitted on a quarterly basis and reported against Specialist Annual Activity Plan indicators 6-monthly | SMHS and NDOH Curative Health Services Branch to manage, in close coordination with RACS and consultation with AusAID as necessary |
|  | 6b PNG and international specialist teams teach and deliver clinical and educational services | Accountable Cash Grants to RACS and/or other technical partners, acquitted on a quarterly basis | AusAID and partners to manage; coordination with SMHS and consultation with NDOH as necessary |

### 5.2.2 Management by Partners using Accountable Cash Grants

The release of AusAID grants quarterly in advance will need to be supported by Annual Implementation Plans and 6-monthly revised cash flow estimates, as well as concise quarterly acquittals and activity reporting in a format suitable for both AusAID and the partner institution.

The cost of additional SMHS management costs to administer the new initiative (e.g. for staff with liaison, reporting and monitoring skills) will need to be apportioned between all Outcome Areas, as appropriate.  However, these management costs will need to be clearly and separately identified in each Annual Implementation Plan under a separate budget line that compares the cost of this additional management support with the total value of funds being managed in each year, by Output.

Each Implementation Plan will also need to compare these additional management costs with SMHS budgets for administration and management.  The purpose of this is to demonstrate that SMHS budgets are not being reduced as a result of the additional administrative support available to SMHS through the program (“the displacement effect of aid”), and also to monitor the gradual transition of additional administrative costs on to the SMHS recurrent budget.

This approach is essential for sustainability purposes.

## 5.3	Coordination Agreements and Arrangements

### 5.3.1 Overview

Activities will be implemented under Agreements between AusAID and the Program.  They will be funded under a single budget for the new initiative, which will include regular responsibilities for performance assessment and reporting, and will be subject to a Mid-Term Review.

### 5.3.2 Program Implementation Cycle

The new initiative will be managed and coordinated by the SMHS as an integral and integrated part of its functions as an educational institution and its delegated functions (from the NDOH) in coordinating visiting specialised services.

Its Annual Implementation Plans and budgets will be aligned with the PNG financial year, i.e. the calendar year (from 1 January to 31 December).

### 5.3.3 Program Advisory Group

The SMHS will be assisted by a Program Advisory Group (PAG), comprising representatives from NDOH, DNPM, a representative of the Specialty Coordinators’ Group (see 5.3.4, below) and AusAID, with the School hosting and acting as Secretariat.

The School and NDOH may wish to consider inviting the OHE to also be represented on the PAG

NDOH will chair the PAG, and take reports from all parties responsible for each Outcome (i.e. SMHS for Outcome Areas 1-5 and SMHS and the delegate from the Specialty Coordinators’ Group jointly for Outcome Area 6).

We propose that the first PAG meeting would take place towards the end of the Transition Phase to consider the first Annual Implementation Plan and budget and the findings and recommendations of the prospective technical and financial audit.

A normal activity reporting cycle would then be 6-monthly.  However, given the relatively low value of the program, we recommend a single annual PAG meeting aligned with the PNG financial year.  The reduced management burden for SMHS (as Secretariat of the PAG), AusAID and other stakeholders would justify this approach.

The PAG would then meet each December to:

- evaluate achievements of the year (i.e. the 12 months since the previous PAG meeting, plus any activities ongoing during the present month), and

- consider the current Program year’s achievements;

- consider the overall strategic direction of proposed Program activities for the following year;

- consider in detail the draft Annual Implementation Plans, budget and cash flows for the following year, including reflecting forward PNG NDOH and Education Department budget appropriations and any consultancy (or similar) income alongside AusAID funding; and

- recommend any refinements to NDOH (as Chair) and the SMHS Business Management Unit (as PAG Secretariat) to finalise the Implementation Plan and budget for the following year.

Precise TORs for the PAG would be drafted during the Transition Phase and confirmed at the first PAG meeting.

Immediately after the PAG meeting (and in any case before 31 December), the Secretariat will finalise the Annual Implementation Plan and budget for the following year and prepare and submit a final Annual Report no later than 15 February of the following year.

Adopting an annual PAG review aligned with PNG financial year planning would also require the SMHS Business Unit to consolidate quarterly acquittals and activity reporting from July to the following June to meet AusAID internal program reporting requirements.  Based on the MSSP unit’s existing financial management and reporting systems and performance to date, we do not believe that this will be a significant additional task.

The PAG would report to the School Board.

According to existing University procedures, the Board then reports through the Dean and Senate to the Vice-Chancellor and UPNG Council.

### 5.3.4 Specialty Coordinators’ Group

Under the present THS Project, specialty coordinators from the School and PMGH meet annually to present and review activities and performance in each technical area.

This meeting is likely to continue to fulfil a useful function for the School and the NDOH, albeit in more detail than is appropriate for the PAG.

We propose that a separate Specialty Coordinators’ Group be retained, and that this Group meets immediately prior to the PAG to review and discuss in detail aspects of the program related to Outcome Area 6.  A delegate from the Specialty Coordinators’ Group would be assigned to attend the PAG and present relevant findings from the current year and plans and recommendations for the coming year.

Figure 5 presents a summary of the Program governance arrangements.

Figure 5:

Governance Structure for the new AusAID Program of Support for 
Health Worker and Training and Specialised Services in PNG

Other donors, development partners

SMHS Board 
Reports to Dean and Vice-Chancellor

Program Advisory Group
(SMHS, NDOH, DNPM, AusAID and delegate of Specialty Coordinators Group; 
OHE and other stakeholders as agreed)

Review and approval of work plans

Confirmation of mobilisation of resources

Program review and  performance assessment

Higher order 
performance assessment and technical advice

Stakeholder Reference Group(s)

Monitoring consistency of Program with needs of stakeholders (trainees, clinicians, community)

See Section 6.2.2

Audits and Technical Advisory inputs as scheduled

SMHS Business Management Unit

Acts as Secretariat for PCG

Prepares Annual Implementation Plans and budgets

Coordination support to service provider(s) on implementation of specialist team visits, training, etc

Collection, collation and analysis of M&E data

Specialty Coordinators’ Group

Ongoing 
performance assessment and technical advice

Monitoring individual specialty areas

See Section 5.3.4

## 5.4	Financing arrangements, including GOPNG contributions

### 5.4.1 Program Budget

The proposed program budget is summarised in Table 1, above, and attached in more detail as Annex VIII.

The total indicative budget is AUD 11 million over 4.5 years, expending approximately AUD 2.5 million per year.  However, a MTR towards the end of the Implementation Phase represents an opportunity to appraise the Program performance against indicators and broader development assistance criteria, and to reassess the magnitude and phasing of funding for program activities.

Where the MTR confirms Program achievements, there will be a potential opportunity for to increase both the size of the budget and the pace of implementation, including with additional HHTG SPI funding of up to AUD 1 million p.a.  Accordingly, there is potential for the indicative budget to increase from the second year of the Implementation Phase onwards; budget details in Annex VIII for this year forwards should therefore be regarded as indicative only.

### 5.4.2 Financing arrangements

Financing arrangements will be made in the form of 6-monthly accountable cash advances to the SMHS (in PGK) and to Australia-based technical partners such as RACS (in AUD), based on the prospective, PAG-recommended 12-monthly advance cash flows.

Quarterly acquittal of advances will be supported by revised cash flows to identify the amount of the following advance.  Where agreed by AusAID and SMHS, any unused funds may either be retained (i.e. rolled over) to support later implementation, or may be redirected to other activities and the forward cash flow requirements reduced.

Audits of advances managed by SMHS and Australia-based technical partners will confirm the completeness and accuracy of the advance acquittals.

Hardware and disposables brought in-country as part of visiting RACS and other procedural specialist visits may be assigned according to the Annual Implementation Plan and individual specialist or team work plan, as recommended by the PAG.

The treatment of any other assets created and any unused funds at end-of-program will depend on the agreement between AusAID, SMHS and NDOH.

### 5.4.3 Other Funding Sources

In addition to NDOH and Education Department budget appropriations (which will be reflected in the budget and projected cash flows for the following year alongside AusAID augmentation funding), we anticipate that the program of support will consolidate the SMHS’s ability to seek and undertake consultancy work for a range of funding agencies.  Examples include running courses on the management of severe and complicated malaria or MDR-TB for the Global Fund projects, or in various aspects of HIV medicine for the National AIDS Council, multilateral development partners (e.g. UN agencies) and international NGOs active in supporting the response to the HIV epidemic (e.g. the Australasian Society for HIV Medicine).  Opportunities may also arise from time to time to conduct externally funded in-service training for a range of HCWs.

Such courses would potentially be integrated into the School’s curricula, contributing further to the sustainability of those activities.

Income accruing from those activities would be absorbed on to Program budgets and cash flow estimates, and acquitted in the usual way.

- PERFORMANCE ASSESSMENT

## 6.1	Overview

### 6.1.1 Purpose

Performance assessment is an essential aspect of the Australian aid program.

Monitoring assists the program manager to assess progress towards intended outcomes and objectives; it can also inform risk and sustainability management.

Through the Quality at Implementation process, it also provides a level of accountability to AusAID as the funding agency.

### 6.1.2 Approach and Rationale

In keeping with the principles of the design, responsibility for day-to-day monitoring of AusAID funded activities will rest with the SMHS Business Management Unit.

During the early Transition Phase, this will need to be a specially designated activity.  However, as the Program moves into its Implementation Phase, it is anticipated (and intended) that monitoring will simply become part of the ongoing monitoring of the School’s overall Strategic Plan and Annual Implementation Plan.

As noted above (Section 2.5.2), the current draft of the Strategic Plan does not include clear, measurable performance indicators, timelines or a detailed monitoring framework.  Developing these structures should be viewed as a necessary capacity building activity for the School, not simply as an activity being put in place to satisfy donor requirements.  For this reason, we emphasise that the evolving performance assessment framework should cover the Annual Implementation Plan in its entirety – not just activities funded by this Program of Australian support.  For this reason, no logical framework analysis (“log frame”) of Australian-funded activities is imposed on the design … or the SMHS.

This approach is appropriate to the proposed management model and the relatively smaller annual cost of the Program to AusAID.

However, robust monitoring and accountability are considered important enough for continued AusAID support to be conditional on the establishment of good M&E systems.

### 6.1.3 Responsibilities and Technical Resources

- Monitoring and Evaluation –

The monitoring system proposed is a combination of regular progress reporting by SMHS and Australia-based technical partners who receive direct AusAID funding through the program – quarterly and at the annual PAG meetings.

These documents will be partially validated by audits of cash advances by the UPNG’s internal auditors, and by periodic external audit and review processes.

The initial engagement of a Business Unit Manager (and possibly an additional staff member with experience in M&E) should take place during the first three months of the Program’s Transition Phase.  If necessary – and subject to adequate internal institutional support not being available through the partnership with the UPNG School of Business Management – additional external consultancy support for M&E may also be necessary during the Transition Phase.

- Other Technical Advisory Support –

We also propose to supplement this with additional technical advisory support to review the Annual Implementation Plans and budgets and, where thought necessary by AusAID or the SMHS Business Management Unit, to participate in the PAG.  This mechanism would provide short-term technical assistance to AusAID Port Moresby, and establish a referral capacity for any technical health sector education issues emerging in quarterly reporting.

We expect that no more than two weeks of this type of technical advisory support would be needed each year, at a cost of not more than AUD 40,000.  Specific health expertise is expected to be available through the AusAID Health Resource Centre by late 2008, and other technical assistance would be sourced through the Education, M&E and Financial Sector Period Offers.

## 6.2 Measurement of Program Success

### 6.2.1 Objective Monitoring

Measures of progress towards the six Outcome Areas will be included in the quarterly reports of the Business Management Unit, which will also be provided to AusAID (see also Section 5, above); i.e. alongside financial acquittals, SMHS will also provide a short report of activities contributing to each of the Outcome Areas, an assessment of progress towards outputs and outcomes identified in the Annual Implementation Plan, and a strategic view on the way forward for each of them and recommended adjustments (if necessary) to the Annual Implementation plan.

Specific indicators may be developed by the Business Unit during the Transition Phase.

Measurement of progress towards the overall Objective of the program will be included in the TORs for the MTR and – subject to the findings of the audit and technical review to be undertaken at the end of the Transition Phase – possibly also for technical advisors engaged between those two reviews (see also Section 6.4, below).

### 6.2.2 Stakeholders and Beneficiaries

Measures of progress towards the Program Outcomes will be supplemented by important contextual information obtained from the primary beneficiaries of the Program – undergraduate and postgraduate trainees.  A Stakeholder Reference Group comprising health sector representatives (e.g. trainees, hospital and PHA personnel) will convene once a year to examine available experience and data indicating Program training outcomes and impact.

The MTR will determine the need for a Stakeholder Reference Group comprising down-stream beneficiaries (e.g. patients and community members) to assist with contextual aspects of measuring progress towards the overall goal of the program.   However, this global indicator is also monitored annually by the Independent Monitoring and Review Group, whose ‘state of the sector’ reports may provide adequate data.

## 6.3 Data Requirements and Ownership

### 6.3.1 Harmonisation with Existing Systems

No additional information requirements are established under this approach.

Data for performance monitoring and assessment will come from enhancing existing SMHS systems, and the information requirements will not be additional to those already undertaken by the MSSP management team; most can be derived from existing records.

We conclude that the system and information requirements are reasonable and would be entirely harmonised with SMHS (and therefore GOPNG) systems.

### 6.3.2 Arrangements for Collection of Data

Collection of the proposed M&E data is part of the ordinary course of GOPNG business, and arrangements are already in place.

Some coordination and sharing of data will be required between the SMHS and the NDOH Curative Health Services Branch.

### 6.3.3 Reporting Frequency and Schedule

- Proposed Quarterly Reporting Requirements –

- Acquittals of funding received (i.e. SMHS will need to acquit on a complete and timely basis);

- Revised 6-monthly cash flow projections, taking into account any unused funding and any deferred activities (i.e. to quantify the amount of the next release of accountable cash grant);

- Bank reconciliations for each month of the quarter, including for sub-contractors; and

- A brief activity completion report (e.g. no more than 2 pages), outlining progress against major Annual Implementation Plan targets that quarter.

- Six-Monthly (or Annual) Reporting Requirements –

- SMHS and directly contracted providers should produce either six-monthly, or annual, PAG reports that show achievements to date – the frequency to be determined at the first PAG meeting.  This should include (i.e. alongside Program funding for the past year):

  - an analysis of GOPNG counterpart funding appropriations that have been released and actually spent,

  - the proposed Annual Implementation Plan for the coming year with revised cash flow forecasts; and

  - counterpart GOPNG Budget appropriations.

These documents will form the basis of funding requests to the AusAID Financial Delegate, and will determine the level of funding available for the following year of the Program.

- A concise annual report will also be presented to the national Board of Health (on which the Dean of the SMHS sits), and to UPNG (for the information of the Vice-Chancellor’s office and the School of Business Management).

## 6.4 Mid-Term Review at the end of Year Two of the Program

We strongly recommend that major review be conducted around the end of the second full year of the Implementation phase.

This should take the form of a Mid-Term Review that combines an assessment of progress to date and fiduciary compliance, and also provides the opportunity to review the design, pace of implementation, capacity to absorb an increase in its funding, and prospects to build on achievements over the remaining two years of the Program.

Satisfactory achievement of many of the performance indicators will signal that the SMHS has proven its capacity to manage greater levels of funding, while simultaneously mobilising UPNG resources to make the SMHS initiatives sustainable.  In this setting the systemic improvements needed to better support health professional training will have been attained, and a larger pool of resources to support a wider range of activities over a longer period of time will be justified.

Conversely, delayed progress towards or achievement of intended Outcomes will indicate the need for a more cautious phasing of inputs, and possibly a more strategic approach to the use of technical assistance or institutional partnerships.

The timing of the proposed MTR coincides with for a commitment from AusAID to double the Australian aid program in the same time frame.  The SMHS presents an opportunity for larger funding flows to be absorbed by the health sector with little additional investment in design and management processes by AusAID.  The MTR will be an opportunity to test that capacity (and the underlying hypothesis) and advise AusAID and other stakeholders about the potential for increased funding through these mechanisms.

## 6.5 Budget Allocated to Program M&E

As monitoring and reporting functions will be fully integrated into the work of the SMHS Business Management Unit, we believe that Program costs for M&E should not exceed AUD 40,000 p.a. (including during the Transition Phase) in technical advisory and audit support.

The MTR is estimated to cost AUD 100,000 in late 2010 or early 2011.

This represents 2.7% of total program costs, which is both reasonable and cost-efficient for an activity of this size that also has embedded M&E functions.

- CROSS-CUTTING ISSUES

A number of cross-cutting issues are relevant to the design and to program sustainability.  The team consulted with the relevant AusAID thematic advisors (anti-corruption, gender and environment) to ensure that the proposed approach was in line with AusAID’s cross-cutting priorities.

The SMHS and its Business Management Unit will need to take these factors into account during planning, implementation and monitoring, and be prepared to be accountable for addressing these in periodic reports and AusAID reviews.  (We also note that not all will be of equal importance, and that some early prioritisation is advisable).

## 7.1	Corruption

SMHS has a proven capacity and track record in effective management and reporting of AusAID accountable cash grants.  This has been verified by independent audit.

The SMHS is also subject to regular internal audit and monitoring through UPNG.

The Program design proposes to build on this capacity, noting that SMHS will need to add staff to its administrative cadre (i.e. in the Business Management Unit) to achieve this.

We reinforce the value of periodic audits to validate effective funds management.

## 7.2	Gender

Gender prioritisation for women and children is a central theme of the National Health Plan, the four strategic areas of focus in the National Strategic Plan for Health, and in Australia’s priorities for development assistance in health.

This prioritisation will be reflected in the curriculum materials that are developed for high priority DFL and other in-service training, with a focus on maternal and child health (MCH), nutrition and obstetric management in rural settings.  Medical graduates who are posted to provincial hospitals as Registrars or enrolled in the new the MMed (Rural Health) program will have an important part of their curriculum devoted to community and public health issues and MCH, and this will be reinforced in their subsequent practice through the NSP and vertical program priorities.

The Program will not discriminate by gender for selection of long- or short-term trainees or among patients who are potential candidates for surgical treatment.

Attention will be given to ensuring that women have opportunities to undertake training (and receive appropriate support while they do so); course records will allow participant data to be disaggregated by gender.  Most nurses and CHWs in PNG are women.

Data on the gender of patients treated by visiting specialists and teams and the School’s clinical specialists will be recorded by the Program’s information system.

Any course materials or curriculum content related to HIV medicine and the care, treatment and support of people living with and affected by HIV (PLHIV) will support greater understanding of the diverse and multi-faceted gender dimensions of the HIV epidemic, and include a focus on the monitoring and analysis of gender outcomes.

As most long term care in the community falls on women, their status in society will potentially be improved by a reduction in long term treatable disability and improved efficiency and effectiveness of the health system.

## 7.3	Environment

### 7.3.1 Medical Waste Management

Treatment of medical waste is the key environmental issue where health sector activities provide procedural clinical and public health interventions.

The Public Health curriculum for all health professionals also includes content on proper disposal practices for medical waste.  By strengthening infection control knowledge and awareness in health care settings, the Program will contribute to improvements in existing practices.

Clinicians and visiting teams contributing to Program Outcome 6 will use existing hospital and clinic systems to dispose of medical waste and to scavenge expired gases in the OT.

### 7.3.2 Carbon Emissions

Carbon emissions will be generated by transporting teams of clinicians and heavy medical equipment from Australia to Port Moresby and between population centres in PNG, and also by conducting activities in settings with significant electricity consumption (for lighting, air conditioning and operation of equipment).

Carbon emission monitoring tools and offset schemes are now readily available, including though domestic and international air transport operators.

Remote and off-site activities can be supported using DFL approaches, telemedicine and telepathology, which may reduce the need for physical travel and transportation.

It is recommended that the PAG, with the assistance of the Program Secretariat at the SMHS Business Management Unit, develops an environmental offset policy to minimise the ‘carbon footprint’ of Program activities.  This could include payment of the small carbon offset surcharge on air fares, ‘green fleet’ options for motor vehicles, tree planting to offset electricity use, etc.

## 7.4	HIV and other Blood Borne Viruses

HIV remains a cross-cutting theme for any development assistance activity (especially in the health sector, where there is an omnipresent risk of exposure to blood borne viruses; BBVs).  The current prevalence of HIV in PNG is thought to be around 1.7%.  Studies by WHO and SPC have indicated a prevalence of markers of hepatitis B infection approaching 20% in Melanesian and some other Pacific communities.  The prevalence of hepatitis C is unknown but thought to be low.

Through its further curriculum development, the Program will support and strengthen the application of universal precautions and infection control in the work place and provide technical assistance in the implementation of work place policies and codes of practice in relation to HIV.

Standard RACS policies and protocols for prevention and assessment of occupational exposure and short course post-exposure prophylaxis against HIV infection using two- or three-drug antiretroviral therapy will be available to visiting specialists and team members.

HIV-related risks will be included in pre-departure counselling for PNG postgraduate candidates undertaking placements in international settings, and telephone counselling via a dedicated mentor in PNG, Australia or New Zealand will be available during any placement.

International team members undertaking assignments in PNG will be assessed and counselled regarding occupational exposure to HIV and other BBVs prior to posting, and booster vaccination against hepatitis B provided where appropriate.  These policies will also inform policies for SMHS and NDOH employees.

The School’s curriculum review process (Outcome 3) will routinely include examination of all activities and identification of any HIV-related risks and impact.  Academic staff, students and counterparts will be provided with access to information on HIV, and with referral for voluntary confidential counselling and testing as required.

The rights of HIV infected staff to employment, students to access to education and training and patients to surgical and other procedural treatment, respectively, will be acknowledged and their rights to confidentiality respected and protected.

## 7.5	Intellectual and Genetic Property Rights

Development assistance activities inevitably generate intellectual property.  Clinical and laboratory-based activities may also include guardianship responsibilities for genetic property.

The Government of Australia generally waives intellectual property rights (IPRs) for any materials produced with AusAID funding and technical assistance.  Materials may then be reproduced on condition that their use is on a not-for-profit basis and that the technical contributions of the partner government and any contracted implementing agency and the financial support of the Government of Australia are acknowledged.

To minimise the risk of future disputes – which is a specific risk to the partnerships and institutional “buttressing” relationships that will contribute to Outcome 2 – it is essential that clear agreement be obtained in advance on the ownership and disposition of IPRs and any genetic material retained during Program-supported activities.

The SMHS will take guidance from relevant UPNG policies on IPRs and, where relevant, the ultimate storage of tissue and blood specimens and ownership of genetic property rights.

Under the MSSP and THS Project, there is a long tradition of IPRs deriving from project activities being vested jointly in the SMHS and the Australian partner agency.  It is nevertheless recommended that the School includes details of IPR agreements in their MOUs with all external partner organisations.

Specimens of human tissue referred with Program assistance to the Central Public Health Laboratory or another PNG-based or international pathologist will only be subject to the diagnostic procedures requested by the responsible PNG clinician.  They will not be available for genetic or other analysis or experimentation.  Genetic property rights will remain vested primarily with the individual patient and secondarily with UPNG, the SMHS and the Government and people of PNG.

## 7.6	Other Cross-Cutting Themes

Partnerships, performance orientation and poverty reduction are inherent features of the design.

- Sustainability and RiskS

## 8.1	Sustainability

The proposed activities under this new initiative are capable of being sustained from within UPNG and GOPNG budget resources into the future.  This is because they are extensions of existing activities; and the cost of these additional activities is low when compared to existing SMHS budgets for these activities.

Although the funding and technical relationships and support described in the present design are likely to consolidate the performance of the School over the next 5 years, it is also likely that longer term donor support will be needed and development partners will need to commit to that longer term assistance.  The management structures within the School’s proposed Business Unit will provide a suitable and natural avenue for other donor support, should that be forthcoming.

However, absolute sustainability resulting from the support proposed in this design cannot be assured.  There are political and other issues that remain outside the scope of the design; these are addressed in Section 8.3, below.

## 8.2	Feasibility

As discussed in Sections 2 and 3, we believe that the proposed approach is feasible because it builds on existing functions and capacities within the SMHS and existing relationships with the NDOH and RACS.  This will be achieved in a modest way, providing vital short- to medium-term budget support but without a large component of external technical assistance.

## 8.3	Key Risks and Responses

Like all of AusAID’s work and support in PNG, the proposed Program has identifiable risks.  The key groupings of risks and proposed mitigation strategies are set out in the Risk Matrix at Annex IX.

The principal risks may be summarised as follows:

### 8.3.1 Risks related to the Health Sector Policy Environment

- 1. The HRH Summit (July 2008) does not result in a comprehensive national HRH Plan

While this will compromise medium- to longer-term planning for student intake numbers, much remains to be done in the meantime to strengthen core SMHS capacity to respond to the anticipated national HRH Plan.  Continued dialogue with the NDOH HR Branch will continue to inform the School and AusAID of progress with the Plan, and will potentially identify bottle-necks and capacity constraints that can be addressed by the NDOH or other development partners.

- 2. NDOH, PHAs and Hospitals do not (or are unable to) make budgetary provision to engage sufficient numbers of staff to meet the requirements of the national HRH Plan

The development of a national HRH Plan will not address all HRH needs overnight.  Other central agencies (e.g. DPM, Treasury) and donors will need to be continuously engaged to ensure the Plan is adequately resourced.  There will be a natural lag time between the response of the SMHS and other training institutions to the new Plan, and a need for larger undergraduate intakes and additional capacity is already identified (see Sections 2 and 3 and Annex I).

- 3. NDOH reforms do not proceed due “reform fatigue” in central agencies

We note that some national reforms are already delayed.  As noted at Risk 2, above, increased training capacity must pre-date other structural reforms.  Ongoing dialogue between NDOH, AusAID and other health sector donors and development partners on the one hand and Treasury and DPM on the other should seek to anticipate the surge in reforms that increasing numbers of graduates over the next 5-10 years will be intended to match.

- 4. Diversion of Department of Education and NDOH resources to DWU or other training institutions

We expect that this risk will not arise before the national HRH Summit and adoption of the new national HRH Plan.  Should it emerge, it will be modifiable and manageable through adherence to the new Plan.

- 5. Refusal of PNG Medical Board or Nursing Council or other Pacific registration bodies to accredit revised curricula

Although this is an unlikely risk, it is important that the medical and nursing registration bodies are represented on any curriculum review committee prior to finalisation of any substantial changes, and that MOHs and Public Service Commissions (or their equivalent) in neighbouring PICs are kept well informed about any new curricula before any candidates are referred to the PNG.

### 8.3.2 Financing and Financial Risks

- 6. The Office of Higher Education or UPNG is unwilling to accept a bilateral funding model for the SMHS, resulting in AusAID funds being managed directly through the SMHS

This risk is regarded as unlikely.  The Secretary for Health, the Vice-Chancellor of UPNG and the Dean of the SMHS will all be involved with consultations and negotiation for the proposed MOU between NDOH and the Office of Higher Education.

- 7. SMHS systems are overwhelmed by Program inputs

With current MSSP and THS Project levels of input, reviews of SMHS reporting and financial management systems have been consistently positive.

Under the new Program, the phased nature of implementation, an early “prospective” technical and financial audit, reporting to AusAID on progress and “variances” from the agreed Annual Implementation Plans, further periodic (annual) audits and the MTR are all designed to ensure that the pace of implementation and release of Australian Program funding are matched to the absorptive capacity of the SMHS.  Furthermore, acquittal will be required prior to the release of each subsequent tranche of funds.

A priority under the proposed Program is to augment SMHS corporate capacity at an early stage by establishing and staffing the School’s new Business Management Unit using Program funds.  An additional safeguard for AusAID is provided by participation of the country office (which will presumably be the head of the Port Moresby-based health team) in PAG meetings.

- 8. Negative impact of exchange rate fluctuations on Program budget

At the time of writing, the AUD is approaching parity with the United States dollar.  If the international value of the AUD falls, there will be a potential drop in the value of AusAID assistance.  Improved SMHS capacity is likely to accrue opportunities for consultancy and other income, and an anticipated increase in the size of Australia’s development assistance budget around Year 3 of the Program may bring additional AusAID funding.  The value of AusAID funding for external specialised services inputs will be protected by a direct contractual relationship between AusAID and RACS, without prior deposit of Australian funding for this aspect of the program in a PGK-denominated account.

- 9. PNG Health and Education budgets fall, or are inadequate to maintain counterpart contributions

This will pose potential risks to School salaries, housing for staff and recurrent costs, resulting in Program benefits not being sustained beyond the term of donor funding.  We recommend careful monitoring of the size of national core budget support for the School, including any adverse response to the proposed increase in Australian funding.  The proposed MTR will present a timely opportunity to review any unintended negative consequences of an increasing level of donor support.

- 10. Size of Australian aid program and budget contracts during the term of the Program

This may result in less (or potentially no) additional funding beyond the AUD 11 million proposed in the present design.  This will be a particular risk if the School develops new efficiencies and capacity that allow it to expend Australian funds more rapidly than anticipated by the current phasing of projected inputs.  Again, the MTR presents a good and timely opportunity to anticipate this risk; AusAID PNG will be an important intermediary to ensure that Australian support for the SMHS (and UPNG more broadly) takes a medium- to longer-term view.  Importantly, the proposed program presents an opportunity to put structures in place for attracting and managing increased GOPNG contributions to the School – arguably the strongest contributor to sustainability.

### 8.3.3 Risks related to Counterpart Capacity for Program Implementation

- 11. The SMHS is unable to identify recruit a suitable Manager for the Business Unit

The Dean should make early contact with the Vice Chancellor and the Dean of the School of Business Management to ensure a supportive within-institution relationship and to identify suitable candidates for the role of Business Manager.  If necessary, the Schools may approach the DWU School of Health Sciences or advertise externally to fill the position, but with the same within-UPNG support and mentoring structures that are proposed in the present design; any externally recruited candidate would be encouraged to undertake a postgraduate academic program through the School of Business Management.

Failing identification of a suitable candidate in PNG, the School may need to advertise internationally.  AusAID may also be able to assist with identifying an externally contracted back-up Manager through its own networks.

- 12. A suitable Business Manager is recruited, but appropriate mentoring and support is not available from within the School of Business Management

The School of Business Management is well regarded in PNG and the region, and the Vice Chancellor is particularly supportive of the proposed model.  This risk is considered unlikely but, if it did emerge, the SMHS may be able to draw on external institutional support in parallel with its other “buttressing” relationships (e.g. through the Business Faculties at the University of Melbourne or JCU).

- 13. Loss of key individuals due to retirement, illness or emigration, and failure to attract good academic staff

This remains a risk during the Transition and early Implementation Phases, but will abate as recruitment and retention strategies mature.  However, there is no guarantee that the right individuals will be attracted to apply for vacant positions.  The Program’s strategy to address this in its early years is to identify and fund counterparts from within existing Australian, New Zealand or other “buttressing” universities or institutions.  It is hoped that this will provide candidates the opportunity to experience 2-3 years in an exciting teaching environment without having to completely sever their ties with their parent institution, as might be required if they were to resign to take up full time appointment.  Existing links with Australasian professional Colleges through the THS Project are likely to maintain an interested flow of visiting lecturers for short term attachments (i.e. under Outcome 6).

- 14. Poor coordination with NDOH

The existing strong links between UPNG, the SMHS and the NDOH (including through representation of NDOH on the University Board and the School Council) are likely to mitigate against this risk, which is considered unlikely.  The role of the NDOH as Chair of the PAG will ensure the voice of the Clinical Standards Branch in planning and authorising activities related to Output 6, and of the HR Branch in most other activities.

- 15. Poor coordination with other international programs of assistance

The proposed Program currently represents a channel for Australian support and is not conditional on the commitment of other development partners.  However, the long term viability of the SMHS, and therefore also the likely success of the new Program, will be strengthened by the involvement of other partners in supporting the School.

The proposed Business Unit at the SMHS represents a suitable but evolving mechanism for other donor inputs.  The structure of the proposed Program consolidates Australian support through UPNG’s and the SMHS’s own structures, and may be expected to provide a “signpost” for other donors wishing to add their support to HRH development and training in PNG.

- 16. SMHS and the Program unable (or slow) to identify suitable candidates for overseas specialist medical and nursing placements, or early withdrawal of candidates from training

The specialist workforce in PNG will be enhanced by – but not dependent on – external placements.  The existence of a domestic MMed program means that international placements in Australia, New Zealand or India (among other destinations) would not need to be excessive in duration.  The Program would not be expected or resourced to fund multi-year overseas placements; if candidates were identified for such placements (e.g. leading to an Australian Fellowship qualification), the NDOH HR Branch and SMHS should ensure that funding includes at least annual return air fares and suitable levels of ‘pastoral’ care in the overseas destination.

- 17. Non-availability of consumables or equipment, especially to support visiting teams and specialists

This risk will potentially impede the delivery of high-quality health services, even if good quality training is proceeding – especially for the proposed increase in surgical and other outreach visits to provinces.  Subject to PAG confirmation, the program will have the flexibility to assign some resources to the procurement of consumables and equipment.  However, of greater importance will be the ability of the NDOH and the Business Unit to proactively identify and manage the availability of necessary equipment for visits under Outcome Area 6.

- 18. Disruption of normal hospital routine, especially by visiting teams

The existing coordination functions of the SMHS MSSP Office are adequate to manage this risk.  We expect that those functions will be enhanced, not diminished, under the proposed Program (through the absorption and expansion of those functions into the SMHS Business Management Unit).

### 8.3.4 External Risks

- 19. Unanticipated withdrawal at short notice of Departmental budget or other international programs of assistance

The School is not currently supported by other external donors.  External technical partners like the CICH and RACS have indicated their long-term commitment to the School (noting the high desirability of AusAID or other donor support, but without being completely dependent on it).

- 20. AusAID country office may not have the capacity to function as activity manager

During the Transition and early Implementation Phases, the Program will undoubtedly place additional time demands on the Port Moresby health team.  The AusAID country office will need to review its capacity and, if necessary, take steps to strengthen it during this time.  Determining the appropriate parameters and TORs for the MTR will also involve some careful consultation among stakeholders and with the HHTG, and it will be desirable for the health team to be represented on the MTR team.

We believe that we have made sufficient resources available for periodic audits, review and technical advice through the supplementary budget line (Table 1).

As the Program moves into its Consolidation Phase, demands on the country office should ease.

- 21. Emergence of epidemic or pandemic

The School is advised to develop a preparedness plan for pandemic influenza and related catastrophes.  The PAG and MTR should analyse contextual and global health issues (including the evolving HIV epidemic in PNG) that could potentially affect Program performance; they should advise on necessary modification of design or implementation processes.

### 8.3.5 Conclusion

The greatest risks to the Program are not internal to the type and number of activities proposed, or related to the managers of those activities; they mainly lie external to the Program in the form of dependencies that Program mangers have on third parties to support them within the “whole-of-government” context.

This reality highlights the complexity of capacity development in PNG.

Whereas organisations working with the Program may be effective and play their part in the capacity development process, they will nonetheless be dependent on unrelated whole-of-government partners to move some activities forward.

We note that these whole-of-government partners are not beneficiaries of the Program and that, alongside their technical capacity building, Program partner organisations will need to develop effective advocacy strategies to overcome potential administrative inertia.

- ANNEXES

- Annex I		Sector and Policy Context

- Annex II		Problem Analysis

- Annex III		Health Professional Training and Curriculum, HR Branch, NDOH

- Annex IV		Problem Tree and Analysis

- Annex Va		Terms of Reference (Design Mission)

- Annex Vb		Terms of Reference (Design Revision)

- Annex Vc		Additional Reference Materials (Design Revision)

- Annex VI		Feasibility Study for a HRH Initiative in Pacific Island Countries

- Annex VII		Synopsis of SMHS Strategic Plan (April 2008)

- Annex VIII		Indicative Budget & Resources Schedule and Phasing

- Annex IX		Risk Management Matrix

- Annex X		Development Partner support to Health Training

Annex I –

Sector and Policy Context

This part of the PDD analyses the government and health sub-sector policy contexts within which the proposed AusAID initiative will be implemented.  This broad context is important, because it sets the backdrop to likely future changes in operational circumstances that the program will need to engage with; and highlights possible future advantages and risks to the program.  It is also an opportunity to evaluate a wide-ranging set of issues in the health sector, to ensure that all possibilities to expand the focus of the new initiative have been canvassed by the Design Team.  An expansion of focus was an issue for consideration in the Design TORs.

However, it is important to note that the focus of the Design Team TORs is strengthening health systems in PNG by assisting with immediate and long term health workforce development needs.  This is a necessary narrowing of design scope that follows on from the AusAID decision to set the annual budget for the new initiative at $2m p.a.

Accordingly, although a broad sweep of issues were initially considered by the Design Team, this was reduced to only those activities that were likely to be realistic and achievable within the design parameters.  This approach reflects the advice given by to the Design Team by the AusAID Design and Procurement Advisory Group (DPAG) at the pre-departure briefing.

Whole-of-Government Context

The whole-of-government policy context in PNG is subject to on-going reforms.  This is complex in nature because of decentralisation and the transfer of health functions to provincial management in 1995.  This section attempts to capture the influence of these factors on the design process and choices.

Government Reform Programs –

The GOPNG is pursuing a whole-of-government public sector reform process, led by the Public Sector Reform Management Unit (PSRMU) attached to the Department of the Prime Minister and National Executive Council (DPM&NEC).  These wide-reaching reforms are documented in the Strategic Plan for Supporting Public Sector Reform in Papua New Guinea 2003-2007”.  The key objectives of the Plan are:

- A public sector with a clear sense of direction

- Affordable government

- Improving performance, accountability and compliance

- Improving service delivery

The Strategic Plan recognises that PNG faces a health crisis – due partly to the rapid escalation of the HIV epidemic but also to “… widespread capacity difficulties affecting the efficiency and effectiveness of management and service delivery performance of agencies at central, line and provincial levels”.   A particular concern expressed by NDOH and development partners is the lack of health services – in particular, a shortage of trained health professionals – in the many rural health facilities.

Implementation of the Strategic Plan is through use of Corporate Plans as the primary tool for engaging the Agency Executive in the reform process.  This is followed by an Agency-led process of comprehensive streamlining and rationalisation of public service operations to produce better service delivery outcomes.  The key tool of this process is the Agency Corporate Plan, which directly links its Executive to full accountability for improved services delivery.

The ultimate objective of the Strategic Plan is to have in place “… efficient and effective means for delivering core government services.  Implicit in this objective is a condition that the level of services provided must be one that the community can afford.”  Affordability is a key point that is made in the Plan, highlighted by GOPNG concerns about the high level of waste and duplication in existing national, provincial and district service delivery programs.

It is widely acknowledged and documented that there are significant difficulties in posting trained health professionals to the rural health service.  Major constraints include the deterioration of rural health facilities to the point where trained health professionals cannot access basic equipment to practice their skills for the benefit of the population.  Provincial Governments also offer insufficient or sub-standard housing, unreliable utilities, and very limited communications and transportation infrastructure and services to support the rural posting of health professionals.  Clearly, the scope and scale of these problems have an adverse impact on “… the improvement in the level of nutrition and the standard of public health …” and the “… equalization of services in all parts of the country” that the Preamble to the Constitution calls for; furthermore, it undermines the delivery of basic health services as called for in the National Health Plan.

These long-standing, systemic constraints are outside the scope of the budget of any development partner initiative.  Accordingly, the design team (while taking good note of the impact of these factors) cannot practically propose any activities that address all these long-standing issues.  It is, however, noted that the 2007 Supplementary Budget is a positive opportunity to address many of the infrastructure constraints in the health sector.

The Whole-of-Government reforms are being complemented by a variety of standing working groups in government.  Their role is to improve the delivery of services in the core sectors of Health, Education, Agriculture and Infrastructure.

The Service Improvement Programme (SIP) was established to carry out provincial service improvement.  The first phase of SIP has focused on four pilot provinces – Western Highlands, Milne Bay, Morobe and West New Britain.  In later phases, SIP will be extended to all provinces.

Further, central agency initiatives are also being implemented to support line agencies, e.g. NDOH, to implement their corporate plans.  One such initiative is the Public Sector Workforce Development Initiative (PSWDI), which decentralises the capacity to hire and fire public servants from the Department of Personnel Management to the line agency HR Division.  This is a crucial initiative for Health, where so much service delivery needs to be undertaken by properly trained health professionals in the public service.

The design team found – as is common with any environment of multiple concurrent reforms and initiatives – that few health organisations have a clear vision of how these reforms will impact on their functions, either now or into the future.  Further, the pace of reform implementation is slower than set out in the Strategic Plan.  Many reforms are in their early stages, and some are yet to start.  Again, this is a common outcome of many complex reform initiatives, but it does indicate that further operational changes can be anticipated in the health sector.

It should also be noted that a new Health Minister and a new Secretary for Health were appointed in May 2007.  Both leaders are supportive of the reform process and are likely to take early steps to engage more fully with the whole-of-government initiatives.

Health delivers services in a complex national policy context –

The system provided for under the Organic Law on Provincial Governments and Local Level Governments and the National Health Administration Act is the basis for the organisation and administration of health services throughout PNG.  This legislative framework defines the powers, roles and responsibilities for all levels of government in delivering health services.  The result is two layers of responsibility for health service delivery that operate in different geographic areas and without clear lines of accountability that bridge or link these layers together to properly coordinate health service delivery.

NDOH is a health policy and planning organisation, structured to have a limited services delivery capacity other than through nationally implemented vertical programs.  Examples of recent vertical NDOH programs include the delivery of programs – including one-off training courses – funded by the Global Fund to fight AIDS, Tuberculosis and Malaria and the World Health Organization, and the supplementary immunisation activities funded by WHO and other donors.  The design team considers that vertical programs and one-off activities administered by NDOH cannot substitute for a properly functioning national HRH or provincial health system.  Under the present reforms, NDOH simply does not have the mandate or implementation capacity for this role.

The GOPNG’s decision to activate the SIP recognises the administrative reality that most health services – especially health promotion and prevention – are delivered by the 20 provincial governments.  The 20 Provincial Divisions of Health (PDOH) are each led by a Provincial Health Advisor who comes under the day-to-day administrative responsibility of the Provincial Administrator.  These provincial health officers are national public servants, in that they appear on the national payroll, but are not directly accountable to NDOH and deliver services according to provincial health and funding priorities.

Provincial health priorities are intended to link directly to the National Health Plan 2001 –2010, and to the four Public Health Strategic Directions under the Strategic Plan for the Papua New Guinea Health Sector 2006-2008.  These four directions are:

- Fully immunise every child under 1 year old;

- Reduce malaria prevalence in high malaria endemic districts

- Reduce maternal mortality in the districts with high maternal deaths

- Reduce rate of increase of HIV and STI.

However, provincial linkages to national health priorities are not always clear from the often worsening health indicators and service delivery outcomes reported in the provinces.  Further, NDOH has little legal or official leverage with provinces, other than through its powers of moral suasion as the most senior health agency.

This division of government responsibility for delivering health services is further compounded by the fact that funding for health to the provinces is through a series of separate funding streams, which are also completely different from the funding and fee income stream to the nationally managed hospitals that provide tertiary care in each province.

Legislative Reform for Provincial Health Service Delivery –

Recent efforts to streamline the complexity of managing provincial health services delivery resulted in the introduction (voluntary) of the new Provincial Health Authorities Act.  This allows provinces to establish a single Provincial Health Authority with a Chief Executive Officer who manages both public health and clinical services as a single group, with a conjoined funding package for the province.  This represents a chance to re-establish the link between the different levels of health services delivery in those provinces where it is adopted.  So far, three provinces have taken this option up.

An added complexity is the provincial role of the Church Health Services, which manage 17 District hospitals and 305 District Health Centres through the Churches Medical Council (CMC) under the Christian Health Services Act.  The CMC receives 90% or more of its recurrent funding (i.e. for both salaries and operations) directly from NDOH in the form of quarterly grants, and is directly accountable to NDOH for its program of provincial service delivery.

CHS faces similar shortages of funds, properly trained staff and materials as government health services, yet is not effectively accessing additional development partner funding through NDOH because of a lack of effective coordination between CHS and PDOH in most provinces.  This lack of coordination is adversely affecting health services delivery in PNG.

Conclusion –

The context for health services delivery and their eventual reform is likely to persist throughout the 5-year period of the proposed program … and most likely thereafter.  To ensure effective program implementation, the program needs to insulate itself from these factors to whatever extent possible.  This is not to suggest that these factors should be ignored, but that only realistic and practical interventions that suit the suggested budget of $2m p.a. be considered.

Accordingly, the design does not engage in more general health sector reforms, and addresses health service delivery only where it is reflected in the SMHS Strategic Plan.  What did seem practical was to focus on health sector education linkages to both health reforms and services delivery issues in a targeted way.

Clearly, NDOH is at a turning point in its evaluation of and planning for health workforce needs.  Health workforce planning is a subject that brings the issues of health reforms and service delivery needs together through a single axis that cuts across all areas of the NHP.  The full extent of this process is only likely to be known in late 2008, i.e. after the Health Workforce Summit is concluded, and the scope of the Corporate Plan better known.  In the meantime, existing institutional training capacity cannot be allowed to atrophy, because this capacity may be called on more heavily from 2009 onwards as NDOH implements its Corporate Plan and associated HR and other reforms.  Accordingly, the period 2008 and 2009 represents an opportunity to help refine training needs and initiate curriculum development and extensions (e.g. distance and flexible learning programs for in-service and continuous professional development) to strategically reinforce key health professional training institutions in preparation for implementation of NDOH reforms from 2010 onwards.

The PDD proposes offering relatively small-scale, specialist support to the NDOH reform agenda in a way that does not cut across existing initiatives and adds value to those processes.  In so doing, the program can assess the type and volume of training capacity that these organisations will need to build over the next 5 years.  Furthermore, key health training institutions need ongoing reinforcement so that they can better support national reform initiatives in the health sector from 2010 onwards.

The Health Sector SWAp

Papua New Guinea’s health sector policy is shaped by NDOH’s commitment to a Sector Wide Approach for health planning and financing.  The PNG SWAp – which derives donor funding through a mechanism known as the Health Sector Improvement Program – calls for clear and direct alignment between national health policy and any donor support to the health sector.  It also seeks to reduce the impact of managing donor activities by using national implementation capacity and systems wherever possible.

Many of the PNG health training organisations tasked to implement these new health training and support activities are Department of Education institutions that fall under the Office of Higher Education; they are therefore not included under the umbrella of the SWAp, which is focussed on central NDOH functions and health service delivery.  As a result, few functional links exist between health training and service delivery organisations to support SWAp- supported health training programs.  Recent reviews of HSIP call into question its capacity to absorb and deliver any greater volumes of activity.  For these reasons, the HSIP / SWAp mechanism is not a natural or logical fit for supporting the financing and management needs of any new HRH and training initiative.

This underpins the proposal to directly utilise the delivery capacity of PNG health training institutions wherever possible.  The proposed activities are clearly linked to NHP priorities, but will not overwhelm the existing absorptive capacity of the PNG implementing partner agencies.  There is additional absorptive and management capacity in the UPNG SMHS that is not being used by the existing program because of the limited level of funding available under MSSP.

SMHS’s absorptive capacity may be further utilised for potential future increases in AusAID funding later in the Papua New Guinea – Australia Development Cooperation Strategy cycle.

Impact of Government reforms on NDOH

National Department of Health is one of four “core” service delivery areas for early take-up of reforms.  This is evidenced by the early support that PSWDI has given to the NDOH HR Branch.  The first cycle of awareness-raising and training for decentralised HR management of public servants has already been completed for NDOH HR officers, and a payroll-audit completed (to reduce “ghosts” and other payroll anomalies in NDOH ahead of the transfer of DPM responsibilities to NDOH).

Discussions with central GOPNG agencies indicate that NDOH is seen to be lagging in the area of internal uptake of reforms.  Specific examples to support this perception include:

- NDOH has yet to draft a Corporate Plan that clearly assigns accountability for implementing reforms to senior officers.  This is considered a major short-coming in NDOH’s commitment to reform.

- The Secretary Health is focussed on completing an Executive-level restructure in NDOH by early 2008 before considering development of the NDOH Corporate Plan.

- NDOH use of PGK 185 million in 2007 Supplementary Budget funding remains unclear due to limited planning and implementation capacity in the Department.

- NDOH HR management capacity is not considered strong enough to manage the short-term public service demands of the reforms.  Another major challenge for the HR Branch is to develop a comprehensive health sector workforce plan that identifies health sector staffing needs as defined by minimum service delivery standards and links these to available and needed positions in PDOHs and hospitals, and to the current and future training outputs of national health professional training institutions.

It is clear that the NDOH will be in a much stronger position to draft and implement a realistic Corporate Plan once the Secretary for Health is properly supported by a newly appointed and tasked Executive.  This process is likely to be completed by early 2008, barring any delays arising from industrial disputes around the selections and appointments process in DPM.  A Corporate Plan could reasonably be expected for 2009, at the earliest.  In the meantime, NDOH, Provinces, hospitals and their related health training institutions must continue to meet health service needs.

There is no regular forum – other than the PNG Vice-Chancellors’ Committee meetings (which excludes some Church-run health training facilities – at which the important links between future health sector workforce planning needs of NDOH, PDOH, Hospitals, CHS and health education training capacities can be considered.  All senior parties consulted during the design process identified a need for this type of forum to be established.

The Secretary has now taken the positive step of calling for a Health Workforce Forum in July 2007, as a guiding theme for the subsequent National Health Summit.  This represents the first opportunity for a comprehensive, properly coordinated health sector training and education Forum to demonstrate its ability to add value to health sector workforce planning.

With WHO technical assistance and CBSC logistic support, the HR Branch is in the process of defining the thematic groups and their background data and research needs to support theForum.

Accordingly, this program proposes an activity to support the NDOH Workforce Forum and Summit as part of the NDOH reform effort.  Clearly, this activity will need to link closely to any CBSC TA working on the Forum and the Summit.

Annex II –

Problem Analysis

PNG Whole-of-Government Reforms

The whole-of-government policy context in PNG is subject to on-going reforms; this process is complex in nature because of decentralisation and transfer of the health function to provincial management in 1995.

The first section of this Annex summarises the more extensive discussions of the reform process in Annex I before going on to examine the direct implications for health sector education and training.

Government Reform Programs –

The Government of Papua New Guinea is pursuing a whole-of-government public sector reform program, led by the Public Sector Reform Management Unit attached to the Department of Prime Minister and the National Executive Council.  These wide-reaching reforms are documented in the Strategic Plan for Supporting Public Sector Reform in Papua New Guinea 2003-2007.

The key objectives of this plan are:

- A public sector with a clear sense of direction

- Affordable government

- Improving performance, accountability and compliance

- Improving service delivery

The Strategic Plan recognises that PNG faces a health crisis – due partly to the rapid escalation of the HIV epidemic but also to “… widespread capacity difficulties affecting the efficiency and effectiveness of management and service delivery performance of agencies at central, line and provincial levels”.  A particular concern expressed by NDOH and development partners is the lack of health services – in particular, a shortage of trained health professionals – in the many rural health facilities.

Health delivers services in a complex national policy context –

The system provided for under the Organic Law on Provincial Governments and Local Level Governments and the National Health Administration Act is the basis for organisation and administration of health services in the country.  This legislative framework defines the powers, roles and responsibilities for all levels of government in delivering health services.  The result is two layers of responsibility for health service delivery that operate in different geographic areas and without clear lines of accountability that bridge or link these layers together to properly coordinate health service delivery.

NDOH is a health policy and planning organisation, structured to have a limited services delivery capacity other than through nationally implemented vertical programs.  Examples of recent vertical NDOH programs include the delivery of programs – including one-off training courses – funded by the Global Fund and WHO, and the supplementary immunisation activities funded by WHO and other donors.  The design team considers that vertical programs and one-off activities administered by NDOH cannot substitute for a properly functioning national HRH or provincial health system.  Under the present reforms, NDOH simply does not have the mandate or implementation capacity for this role.

Conclusion –

The complexity of both the context for health service delivery and its eventual reform will persist throughout the 5-year period of the proposed program … and most likely thereafter.  The design needs to reflect only realistic and practical interventions that suit the suggested budget of $2m p.a.

Accordingly, the design does not engage in more general health sector reforms, and addresses health service delivery only where it is reflected in the SMHS Strategic Plan.  What did seem practical was to focus on small-scale, specialist support to the NDOH reform agenda to assess the type and volume of training capacity that these organisations will need to build over the next 5 years, and to support ongoing reinforcement of key health training institutions.

The Health Sector SWAp

Papua New Guinea’s health sector policy is shaped by NDOH’s commitment to a SWAp) for health planning and financing.  The SWAp – known in PNG as the Health Sector Improvement Program – calls for clear and direct alignment between national health policy and any donor support to the health sector.  It also seeks to reduce the impact of managing donor activities by using national implementation capacity and systems wherever possible.

However, many of the PNG health training organisations tasked to implement these new health training and support activities are Department of Education institutions that fall under the Office of Higher Education; they are therefore not included under the umbrella of the SWAp, which is focussed on central NDOH functions and health service delivery.  Accordingly, few functional links exist between training and service delivery organisations in the health sector to support SWAp-supported health training programs.

The SWAp approach has shaped the design team’s decisions on activity levels and activity management.  The approach and activities proposed in the design are clearly linked to NHP priorities, and will not overwhelm the existing absorptive capacity of any of the proposed PNG partner agencies.

Moreover, the Design Team considers that SMHS has the capacity to manage a greater volume of funding and activity than is proposed here – an absorptive capacity that may be utilised for the likely 2008-09 and 2009-10 budget initiative of increasing Australia’s official development assistance expenditure towards the United Nations target of 0.7 percent of gross domestic product (GDP) by 2010.

Policy Context for Health Worker Education – Degree Level Courses

Since 2004, a number of policy steps have been taken towards greater quality assurance in health training institutions; and to upgrade health professional training courses from Certificate and Diploma to Degree level.

These steps have been implemented in 2005 and 2006 by either aligning or amalgamating Nurse Training Schools with Universities.  This allows University quality assurance systems to be applied to the curriculum, clinical practice and academic assessment programs of the Nursing Schools as they upgrade to a three-year, residential degree course in General Nursing.  In principle, this should make certification and registration of nursing training easier as higher standards have been applied to assessment and documentation of training.

Government fully funds a set number of tertiary training places in health training institutions.  This applies to Universities and Schools of Nursing.  However, funds for nursing training are managed differently from university funding.

Funding for nursing training is managed through the Office of Higher Education budget, which pays all Student Subsidies for board, tuition and allowances directly to the training institution’s operating bank account.  Nursing school operating costs are also paid by OHE; either directly to the training institution’s operating bank account where it is affiliated with a University; or to the University for disbursement to the School of Nursing, where it is amalgamated into the University.

This transition has not always been smooth, with funding issues affecting the transition of the Port Moresby Nursing School to UPNG and Lae School of Nursing through the University of Technology, Lae (Unitech).  In both cases, needed funding was not released and the nurse training programs have been negatively affected.

Policy Context for Health Worker Education – Registration

The Medical Registration Act 1980 addresses the requirement for registration of all health professionals in PNG.  It establishes the:

- Papua New Guinea Medical Board for the registration and discipline of medical practitioners, dental practitioners and allied health workers; and

- Papua New Guinea Nursing Council for the registration and discipline of nurses and nurse aides.

Registration is a vital national quality assurance function.  It is designed to reassure the people of PNG that any person presenting themselves as a qualified health professional has in fact met the minimum education and clinical safety standards established by these Boards.  The Boards’ proper functioning is vital to maintaining public confidence in health professions and systems.

Registration of Nurses –

A further issue of concern is the registration of trained General and Post-Basic Nurses under the University assured training programs.  No nurses have been registered by the Papua New Guinea Nursing Council in 2006 and 2007, due to perceived deficiencies in the documentation of 1500 hours of required clinical practice training by the training hospitals and nurse training institutions.  This is adversely affecting nurse employment, health services delivery and public confidence.

There are a number of meetings scheduled in late 2007 to resolve this impasse in Nurse Registration.  The Design Team does not propose any activities in this area, as nursing has had considerable recent support from donors in the past; and is currently the focus of an enlarged NZAID program design initiative.  Further, nursing is subject to considerable union and labour politics in PNG; and it is considered better to let national institutions manage these processes.

The Nursing Council is supported by National Framework for Accreditation and M&E adopted in 2005 with assistance from the Health Services Support Program (HSSP).  The Council is significantly under-resourced through the NDOH budget.  The Nursing Council secretariat has only two staff and very limited office space that does not include electronic registration databases, or sufficient funding to administer any disciplinary cases.  The Nursing Council also needs to develop Assessment Framework Tools to support Registration of Nurses into the future.

The Design Team emphasises the need for continued support to the Nursing Council to improve its capacity to accredit, register and monitor General and Post-basic Nursing graduates, and to better manage any disciplinary cases for this vital cadre of health care workers into the future.  We recommend that this be maintained through the existing support of the WHO Representative Office in PNG.

Registration of doctors and all other health professionals –

All other Health Professionals are registered by the Papua New Guinea Medical Board under the terms of the Medical Registration Act 1980.  It is responsible for registering and disciplining all medical practitioners, dental practitioners and allied health workers, both nationally trained and foreign-trained who seek to practice in PNG.

The Design Team finds that this Board is also significantly under resourced when the scope and scale of its registration task is considered.  This Board lacks a functional and sustainable secretariat through the NDOH Budget.  Its office is inadequate for its needs.  Further, the recently revised Medical Registration Act has not been passed in Parliament; and does not allow realistic registration fees to be collected by the Board to support its work (doctor registration is PGK 20 p.a.; HEO registration is PGK 5 p.a.).

The Board is receiving support from WHO-WPRO and the PNG Office to develop better registration forms ahead of adopting a new electronic registration database.

As with the Nursing Council, we have not recommended supporting the Medical Board under the new initiative as WHO is already active in this field.

Policy Context for Health Worker Education – Distance and Flexible Learning

The health sector is making an emerging commitment to distance and flexible learning modalities for health professionals, as supported since 2001 by Meetings of Ministers of Health for the Pacific Island Countries; and as set out in the National Policy on Human Resources in the Health Sector.  For example, the Health Professional Education Unit (Formerly Medical Education Unit) at SMHS supports developing a distance learning capacity for health professionals upgrading.

The Design Team found that earlier success had been achieved with distance learning approaches in the health sector, but that some of these had not been sustainable within the health training institutions after a development partner program concluded.  Examples of these models include:

- Diploma in Anaesthetic Sciences, UPNG – Since 2003 this is offered as four weeks in-school with 48 weeks in-service training.  Can be used to upgrade a General Nursing Diploma/ Degree.  Limited candidates to date;

- Pharmacy Bridging Course, UPNG – Hospital Dispensary staff were able to upgrade to this Diploma level in this course.  Eight out of the first 25 candidates graduated (32%); too little time was allowed for study by their employing hospitals;

- HEO upgrading course, Medical Officer, Nursing And Allied Health Science Training Project – has been continued at DWU, Madang, and is in the process of being further enhanced to a degree course;

- General Nurse Diploma upgrade to Bachelor of Nursing Degree, MONHAP/ UPNG – distance education capacity has not been retained due to lack of academic staffing and

- Nurse Teacher Training to support upgrade to Bachelor of Nursing Degree in nursing schools, PNG-Australia Targeted Training Facility (PATTAF) – not continued after development partner support ceased in 2004.

The Design Team concludes that the distance learning modality has much to offer the Health sector to enhance skills of serving health professionals, leading to higher Registration and salary / career advancement opportunities for these already-employed staff.  Levels of rural health service delivery can also be expected to improve as these staff are already on the payroll and living in rural health facilities.  However, more work will need to be done to:

- Develop stronger linkages between distance learning facilities, such as the UPNG Open College and DWU Faculty of Flexible Learning, and health training courses for in-service personnel.  The UPNG Open College supports five provincial university centres and five franchise study centres located throughout the country.  The five open campuses are equipped with study facilities including a computer laboratory in each for student use.  The DWU Faculty of Flexible Learning (FFL) is in the forefront of the Pacific outreach program.  Solomon Islands and Nauru receive DWU's educational services through this medium.  These facilities can be considered to support larger health sector in-service up skilling programs in PNG.

- Identify priority cadres of health professionals needing early upgrading; and prepare particular curriculum and delivery materials to support this training;

- Promote equity of opportunity by enabling as many health professionals as possible to access these programs through their provincial governments via health education scholarships that may be funded out of the Supplementary Budget; and

- Mobilise Development Partner funding to support health professional training programs of greatest need under this in-service, distance learning modality.

The undergraduate Degree courses that are being offered by Nursing Schools and Universities have more to offer to school-leavers, who will seek to enter the health profession for the first time after qualification.

Accordingly, the Design Team proposes that the SMHS curriculum development activities to be funded through the new Program (Outcome 3) properly research and develop sustainable links between DFL facilities, existing health training institutions and courses, and identified in-service training needs for existing health cadres.

Activity Context

The health sector in PNG employs a significant number of health professionals; most are in the government sector (1,269  at NDOH + 3,597 at Health Centres + 1,547 at Aid posts, or 6,413 in total).  Smaller numbers are employed in CHS (2,909) and the private sector (around 200).  This total of approximately 9,500+ workers makes the health sector workforce the second largest in PNG; the biggest workforce is managed by the Teaching Service Commission that supports the education sector.

It needs to be noted that Government health and CHS employees work in closely related systems.  Both groups of staff are trained in the same institutions, the same Standard Treatment Manuals are used to support diagnoses, pharmaceuticals and medical supplies are provided by the NDOH Medical Supplies Branch via Area Medical Stores in the provinces and the same logistics difficulties are confronted in remote areas.  Both services struggle to recruit doctors in remote areas, with the CHS having an advantage due to their ability to attract Volunteer doctors to remote facilities, but these expatriate staff often work without PNG counterpart doctors to transfer skills to.  This is an important training opportunity lost to the PNG health sector in many cases.

Two major differences are the CHS capacity to manage and pay staff according to agreements not linked to Public Service conditions; and to mobilise 6% to 10% additional resources through fund-raising and fees for services.  These differences offer CHS the tools to better manage their staff and facilities, but better management in CHS is practically achieved as a result of closer supervision of CHS staff by senior managers.

Better training and supervision of all health sector staff is vital to improved rural health services delivery, but the numbers of employees involved indicate that this is a major task for Government; and outside the resource envelope of the development partners.

However, key health professional cadres can be identified for in-service training to better support the essential work of maternal and child health care.  This approach is endorsed in the National Health Plan as follows “The health of the children and the welfare of the entire family are integrally linked to the health of the mother.  Therefore basic services for women and children must be protected and promoted as a priority.  This will be achieved through the development of a strong primary health system, with a focus on fostering a culture of good nutrition, hygiene and sanitation, parental skilling, reproductive health, providing quality neonatal care and safe motherhood.”.  Further.  “Papua New Guinea is one of the signatories to the Convention on the Rights of the Child (1989) and is committed to the global effort of ensuring children’s survival, protection and development.  Children have a right to basic health care and Papua New Guinea is committed to ensuring the provision of necessary health care to all children.”

The Design Team is advised that Community Health Workers, Nurses and HEOs are the front-line groups responsible for delivering these services, but all currently suffer from a lack of:

- medical supervision that supports clinical diagnoses and to confirm the need for patient referrals; and

- formal, in-service opportunities to develop their skills and progress their careers.

The lack of doctors in rural facilities is the principal cause of the lack of supervision; and poor linkages between health workforce planning and health training institutions is responsible for the lack of formal in-service opportunities for serving health professionals.

Role Definition and Demand in the Basic PNG Health Care System

The Role of Doctors –

The emphasis given to promotional and preventative health as a major part of the PNG basic health care system, such as is emphasised in the quotations from the NHP above, has also given currency to the idea that doctors are too few and expensive to be a rural health service resource; and therefore do not have a leading role in PNG’s basic health care system.

These ideas are not correct; and do not reflect the reality of the national health plan.  The NHP clearly recognises that the ability to refer patients up to tertiary level health services is a very real and necessary part of the basic health care system.  This is evidenced by the following quotation concerning rural based patient care “Rural-based patient care includes management of patients by health workers based at aid posts, health centres, clinics and rural hospitals.  Staff at these levels mainly include community health workers, nurses, health extension officers, laboratory technicians and medical officers.  The types of equipment and medical supplies available at these facilities are suited to diagnose and support management of common health problems.  Those patients who cannot be managed at these facilities are therefore referred to the larger, better equipped and staffed public hospitals.”

The reasons for the NHP recognising a key role for doctors are clear.  Firstly, rural PNG is largely agrarian, involving heavy manual work with tools.  Serious injuries and accidents do happen and medical intervention is necessary to treat these cases.  Further, social and cultural conflict can and does lead to violence-related injuries, which also require medical intervention.  Finally, the pathology of the population is also reflected in rural patients, who need access to medical intervention.  Premature births are a clear example of the need for medical intervention to support maternal and child health, as is HIV/AIDS treatment and obstetrics complications.

Some of these rural health needs can be met by effective patient transfer systems.  The HSIP Trust Account does have development partner funding available to support emergency transfers of delivering mothers.  However the cost and administrative function of this system means that only limited numbers of cases will benefit.  A far more effective and sustainable solution is the training and placement of doctors in rural health facilities.

The Curative Health Services Branch, NDOH supports this view with the following quote from its recent report on the need for more effective manpower planning “The very important leadership role doctors’ play in hospitals and other curative facilities and as technical advisors on clinical public health programmes cannot be over emphasized.  These important roles are not fully realized because there are inadequate numbers and not equitably distributed.”  NDOH advises that the current health sector workforce was established at a time that the population was 3 million; and is inadequate to effectively service the current population of 6 million.

The fact that GOPNG has been slow to establish, equip and staff rural hospitals with doctors, also known as District Hospitals, does not negate the clear need that exists in the NHP for more doctors to go into rural service.  The 2007 Supplementary Budget is a once-in-a-generation opportunity to begin addressing the need to build District Hospitals; and to staff these rural health facilities with properly trained doctors.

It is also important to note that the new Secretary for Health has also highlighted the need for health services delivery to the urban poor as well as the rural majority.

Finally, Medical Officers (doctors) can also serve as leaders in health planning and health resources mobilisation in the provinces.  This is in part due to their status within the basic health care system, and to their understanding of the provincial epidemiology that basic health data are indicating.  CHS recommends that all rural doctors receive conflict resolution and community development training as part of their public health curriculum, to become more effective health sector leaders.

Master of Medicine (Rural Health) –

To respond to the need to provide comprehensive medical care and supervision of health teams in rural areas SMHS has developed a MMed (Rural Health) and hopes to offer this in 2008.

The aim is “to provide a recognized career structure in Rural Health with specialist status equivalent to all other Disciplines.  The graduate will be able to take final responsibility for whatever clinical, public health or management problem presents him/her at a rural hospital”

The curriculum is structured in the same way as other specialty MMed programmes, with in this case a broad experience in key specialties through the established components and, in addition, in Management and Public Health.

Rural hospitals will be the home base for individual trainees, will provide most of the training as supervised general clinical experience, and as necessary will enable them to obtain specialty experience through short term secondment.  Training will be supported by distance learning and access to electronic media, for which provision must be made.  Trainees will be supervised mentored and rigorously assessed.  At all times trainees will be providing service to the community.

Graduates may work in Church Hospitals or Rural hospitals as key components of health services as they widen into rural and remote areas.  Key partners in development and implementation are Discipline Heads of SMHS, Divine Word University, Church Hospitals, and provincial hospitals.  The Royal Australian College of General Practice (Rural Division) has offered support to distance learning through provision of curriculum materials staff development and exchange of experience.

The June 2007 Feasibility Study strongly recommended support for this programme.

The Demand for Doctors –

The following quotation and table are from the Curative Health Services Branch NDOH.

There are approximately 420 clinical doctors working in Papua New Guinea in the public sector and in church organizations.  Of these doctors 372 (89%) are in the hospitals, of which 120 are specialists with the distribution as in the table below, 91 are registrars, 78 are general medical officers and 79 are residents.  Of the 124 general medical officers 78 (64%) are in hospitals and 46 in rural areas.  Forty-six (37%) are in district health services, out of which 19 are in government facilities and 27 in church facilities.  The issue however is how they are distributed and currently they are not equitably distributed.  Firstly there is a variation among hospitals in that Port Moresby General Hospital (PMGH) has the highest number and secondly, distribution highly favours urban minority.

| Hospital | Doctors |  |  |  | Rural Hospital/ Health Centre |  | 0ther | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | SMOs | Registrar | GMOs | RMOs | Government | Churches |  |  |
| Daru | 1 |  | 5 |  | Balimo/Kiunga - | Rumginae, ECP x1 | Ok Tedi x3 | 10 |
| Kerema | 1 |  | 1 |  | Kikori x2, | Kanabea, Kapuna x 2 UC |  | 6 |
| PMGH | 52 | 56 |  | 36 | NCD x3, Kupiano, Tapini - | Bereina | many | 146 |
| Popon-detta | 2 | 1 | 4 | - | Kokoda, | St Mary’s |  | 7 |
| Alotau | 6 | 1 | 9 |  | Misima, Lousia |  |  | 16 |
| Goroka | 10 | 9 | 15 | 11 | Kainantu x2, Lufa x1, Okapa x1, Henganofi x1 | SIL x1, New Tribes x1 | UOG x1 | 53 |
| Kundiawa | 3 | 1 | - | - |  | Mingende, church x1 |  | 4 |
| Hagen | 5 | 2 | 9 | 3 |  | Tinsley/Bayer- Kudjip x 4 |  | 24 |
| Wabag | 1 | - | 9 | - | Liagam x1, Kandep, Pogera x2 | Sopas, Kompiam x1, Mambisanda x1 |  | 15 |
| Mendi | 2 |  |  |  | Tari x1,Ialibu | - |  | 3 |
| Vanimo | 2 | - | 1 | - | Aitape x 2 | Teleformin x 1 Baptist |  | 6 |
| Wewak | 5 | - | 6 | 3 | Angoram x1 Maprik x 1 | - |  | 16 |
| Madang | 8 | 3 | 4 | 7 | - | Gaubin x 1 Yagaumx 2 Bogea x 1 |  | 26 |
| Lae | 12 | 12 | 4 | 17 | Bulolo- | Braun x 3 Etep x 2 |  | 50 |
| Kimbe | 2 | 1 | 5 | 2 | - | - | 0il Palm x1 | 11 |
| Rabaul | 8 | 3 |  |  | Palmalmal x 1 | Vunapope x 5 |  | 17 |
| Kavieng | 2 | - | 3 | - | Namatanai | - | Lihir x 3 | 5 |
| Lorengau | - | - | 1 | - | - | - |  | 1 |
| Buka | 2 | 2 | 2 | - | Arawa, Buin - | - |  | 6 |
| Total | 124 | 91 | 78 | 79 | 19 | 27 | 8 | 426 |

A general medical officer is a registered medical officer after residency training.  This is the much needed manpower required at the rural hospitals and in districts.  They also play an important role in providing service in hospitals.

There are currently 130 general medical officers in service at the moment.  Out of  these 78  are in public hospitals, 19 in rural health services under government, 25 are in rural health under church run facilities and 8 others (see Table above).  If on rough calculations we need 3 doctors per district a minimum of 267 doctors are required to fully staff rural facilities and may be more based on population size.  We already have 44 in rural areas and therefore a further 223 doctors are needed.  Based on the population size, and basing on the population ratio anything up to 1200 doctors are needed.  We know we already have over 400 doctors and a further 800 are needed to have the total numbers required to man all health facilities.

This extract from a recent NDOH of medical officer needs is clear.  At an output of approximately 50 medical graduates per year, and a further two years of training in Residency needed to develop a GMO, it will take SMHS at least 18 years to provide 800 additional doctors, not allowing for any retirements or other loss of staff.  This is not a response time that meets either the requirements of GOPNG reforms, or the health services needs of the people of PNG.

The Design Team considers that reinforcing SMHS capacity to produce greater numbers of doctors into the future, at an affordable cost, is a sound strategy for supporting rural health services delivery in PNG.

Cost / Benefit Analysis for Medical Training in PNG

The Strategic Plan for Supporting Public Sector Reform in Papua New Guinea 2003-2007 stresses the need for service delivery levels to be affordable.  As noted above, there are some views that doctors are not affordable in the PNG basic health care system.

These views are not borne out by cost/benefit analyses.  It is recognised that UPNG SMHS produces a high-quality medical graduate, capable of going on to specialisation in later years.  This reality is evidenced by the ability of UPNG trained doctors to successfully emigrate to other countries and practice medicine there.  The cost of a 5-year medical undergraduate medical degree at UPNG SMHS is estimated at PGK 136,000  plus approximately AUD 75,000 in MONAHP/ Medical School Support Project (MSSP) funding from AusAID (or about AUD 130,000 at mid-2008 exchange rates).  The equivalent fees-only cost of 5-year medical undergraduate degree offered to overseas students at University of New South Wales is AUD 251,750.  Another AUD 90,000 needs to be added to this for living costs for each overseas student, making the total cost for each undergraduate medical degree in Australia up to AUD 341,750.

Simply put, GOPNG can develop 2.6 doctors at SMHS for the cost of one doctor trained at an Australian university.  Furthermore, the SMHS trained doctors will undertake their residency in PNG facilities; learn relevant national epidemiology and treatment regimes; and develop a clear understanding of their roles in the complex national public health service delivery context.

Where UPNG addresses urgent housing, equipment, materials and salary needs at SMHS, it is expected that the cost of each medical graduate will rise.  However, the increased cost is highly unlikely to equal that of an Australian medical undergraduate degree.  On this analysis the Design Team considers that the SMHS medical undergraduate is both affordable to GOPNG; and appropriate in terms of academic training and residency experience.

Conversely, doctors trained in Australia will be prepared for the Australian public health service context and will be more readily absorbed into that system upon graduation.  Overseas undergraduate training can undermine retention strategies for PNG doctors, many of whom are already under emigration pressure.

For these reasons, the Design Team considers that reinforcing SMHS capacity to train doctors to current standards, in larger numbers into the future if possible, is a central objective to supporting better rural health services into the future.  Given the budget available to the new health initiative, it is the most cost-effective health development option that the Design Team could identify; and most capable of meeting rural health service delivery needs into the future.

It is appreciated that this strategy has numerous dependencies and risks.

Most notable of the dependencies are that NDOH and Provincial Government will coordinate to provide effective leadership on building District Hospitals and staff housing with the 2007 Supplementary Budget funding of PGK 185 million.

Most notable of the risks is that the Health Workforce Plan that emerges out of the Health Summit in 2008 will identify numbers of doctors needed for specific District Hospitals over the next five to 10 years, but that budgetary provision may not be made by all parties, NDOH/ Provinces/ Hospitals so that doctors can be reliably appointed to and effectively retained by the rural health system.  Funding will be needed for materials and logistic support in addition to the required doctor and other health professional positions.

GOPNG Commitment to Health Professional Training

GOPNG funds a considerable level of undergraduate and post-graduate health professional training.  See Annex III – Health Professional training and curriculum, supplied by the HR Branch, NDOH.  This indicates a major commitment to health training going forward.

As noted previously, the opportunities for formal in-service training via distance/ flexible modality remains under-developed at this time.  However, the need for this capacity is clear and the Design Team recommends that this be researched under the new initiative; and reported to the Health Summit 2008.

Further, training of health professionals in PNG has received considerable support from development partners in recent years.  See the table attached as Annex IX – Development Partner Support to Health Professional training in PNG.

The UPNG School of Medical and Health Sciences –

Unlike Fiji, where there is now a move to create two schools of medicine, one privately funded by a faith-based group (Hindu), PNG is encouraging economies of scale by permitting only one medical school to service the training needs of the country.

However, UPNG SMHS has been in academic distress for some time.  The last academic appointment was in 1997; and there are currently 16 senior academic vacancies being advertised (21% of total academic posts) with their recruitment urgently needed if the school is to maintain its capacity to produce graduates in 2008 and 2009.  The Public Health Division is most at risk, with 66% of the academic posts vacant; and a number of former SMHS faculty now at DWU to support its emerging health professional training programs.

These staffing deficits have been overcome in the past through the use of visiting/ adjunct professors from Port Moresby General Hospital, NDOH and through MSSP and the Tertiary Health Services Project visiting teams, but this is not a long-term solution to SMHS academic staffing needs.

One major factor that hampered earlier recruitment programs has been lack of salary parity between academic and clinical doctors with equivalent qualifications.  The Design Team is advised that salary parity has been resolved and funded in the 2008 UPNG Budget; and forms the basis for the current SMHS academic recruitment program.

Another factor affecting recruitment is UPNG housing availability.  It needs to be noted that two recent Professorial appointments to Nursing and Surgery could not be sustained due to the lack of suitable, secure UPNG housing for these staff.  Housing shortages at UPNG continue; and threatens to undermine the current academic recruitment program if this constraint cannot be satisfactorily resolved by UPNG Council and the Vice-Chancellor.

Other constraints on the capacity of SMHS that need to be recognised are:

- lack of building maintenance for halls of residence and campus buildings;

- shortages of consumable supplies to support academic, post-graduate research programs;

- lack of materials and equipment in the newly built nursing school; and

- a need to recapitalise technical and scientific equipment laboratories.

Similarly to the Ministry of Health and NDOH, the Vice Chancellor of UPNG and the Dean of SMHS are new appointments and very development minded.  Both express strong commitment to the school; and an understanding of the challenges that lie ahead for the school to restore its full capacities in national and regional health care.

SMHS is actively looking at new ways to improve the schools capacity and sustainability; and seeks longer term partners in this effort.  SMHS has developed a strategic proposal that identifies the extent of support that will be needed to overcome the existing constraints; and to meet likely future demands for trained doctors and other health professionals.  The SMHS strategic proposal is coherent with the recommendations made in the recent Feasibility Study for Human Resources for Health Initiative in Pacific Island Countries - Aide-Memoire to AusAID regarding meetings with the School of Medicine and Health Sciences, University of Papua New Guinea June 11-15, 2007.  See Annex 12 for the full text of this Aide Memoire.

The Design Team also notes that UPNG has a history of improving student gender ratios towards national Year 12 gender statistics.  Since 1992, SMHS has increased the number of female medical undergraduates from 10% to 35%, which is consistent with recent Year 12 female enrolments of 35%.  Nursing undergraduates are 95% female by gender.

The Design Team considers that SMHS has available absorptive capacity to directly manage a larger budget of rehabilitation work.  However, a key issue will be to set internal recruitment and budget performance targets for UPNG and SMHS to ensure that the sustainability of any rehabilitation programme is reflected in the on-going capital, equipment and maintenance Budget appropriations.  The commitment expressed by the Vice Chancellor UPNG in assuring support to the revitalisation of SMHS foreshadows success with this task.  Where this support is practically demonstrated, there will be sufficient sustainability evident to support a bigger investment in upgrading the school.

The Design Team strongly supports the concept that SMHS is capable of absorbing greater funding immediately, but recognises that the budget limits of the new initiative do not allow for this at this time.  There is a clear opportunity to increase the level of support to SMHS following the Mid-Term Review and as AusAID seeks to double its aid to PNG.

NDOH In-Service Training College, Laloki –

NDOH has a purpose built in-service training college at Laloki, about 30 Km outside Port Moresby in Central Province.  This facility is currently standing idle, but has the potential to host formal in-service residential schools into the future.

Effective use of this facility needs to be explored and developed under the new initiative in the lead-up to the Health Workforce Summit 2008.

Divine Word University, Madang –

The Divine Word University (DWU) is a national University with Catholic tradition.  It was established by an Act of Parliament as the Divine Word Institute in 1980, and later established as a University in 1996. It is privately administered with GOPNG support.

The Faculty of Health Sciences comprises Departments of Health Management, Physiotherapy, Environmental Health, Health Extension, and affiliated nursing colleges.  It has a close association with the Modilon Hospital, Madang as a clinical teaching facility.  The Faculty of Flexible Learning currently offers DFL courses to Bachelor level in public sector management, education, and counselling and conflict resolution.

Annex III –

Health Professional Training and Curriculum - HR Branch, NDOH

| INSTITUTION and PROGRAMS OFFERED |  | Program Level | Entry level | Category of Health workers targeted |  |
| --- | --- | --- | --- | --- | --- |
| 1. | UNIVERSITY OF PAPUA NEW GUINEA SCHOOL OF MEDICINE, TAURAMA CAMPUS NCD |  |  |  |  |
| i | MBBS Program | Degree | Grade 12 | Science foundation year, completed |  |
| HEALTH SCIENCES |  |  |  |  |  |
| ii | Bachelor in Pharmacist | Degree | Grade 12 | Science foundation year completed |  |
| iii | Bachelor in Medical Laboratory Sciences | Degree | Grade 12 | Science foundation year completed |  |
| iv | Bachelor in Oral & Dental Surgery | Degree | Grade 12 | Science foundation year completed |  |
| v | Bachelor in Medical Imaging | Degree | Grade 12 | Science foundation year completed |  |
| vi | Diploma in Anaesthetics | Diploma | Grade 12 | Science foundation year completed certificate of area of study (HEOs and Nurses) |  |
| vii | Diploma in Community Health | Diploma | Grade 12 | Science foundation year and certificate of area of study (Drs, HEOs, E.HOs and Nurses) |  |
| viii | Masters in Public Health | Masters | Post Graduate | Medical Officers, HEOs & Nurses |  |
| NURSING |  |  |  |  |  |
| ix | Bachelor in Clinical Nursing Midwifery & Paediatrics | Degree 1 year | Post Graduate | Registered General Nurses with minimum of 6 months work experience in Labour and Paediatric Ward. |  |
| x | Bachelor in Nursing Administration & Education | Degree 1 year | Post Graduate | Registered General Nurses with minimum 6 months of work experience in Nursing Management job including Teaching. |  |
| xi | Bachelor in Nursing Acute care | Degree 1 year | Post Graduate | Registered General Nurses with minimum 6 months work experience in Acute care areas (ICU, Accident and Emergency and Operating Theatre) |  |
| xii | Bachelor in Nursing Mental Health | Degree 1 year | Post Graduate | Registered General Nurses with minimum 6 months experience in working in Psychiatric or Mental Health Unit. |  |
| xiii | Bachelor in Nursing Community Health | Degree 1 year | Post Graduate | Registered General Nurses with minimum 6 months work experience working in Nursing Community Health Management. |  |
| 2. | FACULTY OF HEALTH SCIENCES DIVINE WORD UNIVERSITY MADANG |  |  |  |  |
| i | Health Extension Officer | Diploma 3years | Grade 12 | Science foundation year - HEOs |  |
| ii | Environmental Health Officer | Diploma 3years | Grade 12 | Science foundation year - EHOs |  |
| iii | Physiotherapy | Degree 3years | Grade 12 | Science foundation year - Physio workers |  |
| iv | Health Management | Diploma 4years | Grade 12 | All category Health workers |  |
|  | Lutheran School of Nursing (affiliated with DWU): |  |  |  |  |
| v | Registered General nurse | Diploma 3years | Grade 12 | Pre- service RPL: CHW and Nurses with Certificate qualification. |  |
|  | Midwifery | Degree 1year | Post Graduate | Registered General Nurses RPL: Other Health Workers |  |
| 3 | UNIVERSITY OF GOROKA EHP |  |  |  |  |
| i | Diploma Health Teaching | Diploma 1year | Post Graduate | All category Health workers |  |
| ii | Diploma Health Education | Diploma 1year | Post Graduate | All category Health workers |  |
| iii | Degree Maternal Child Health | Degree 1year | Post Graduate | All category Health workers |  |
|  | Highlands Regional College of Nursing (affiliated with UOG): |  |  |  |  |
| iv | Registered General nurse | Diploma 3years | Grade 12 | Pre- service RPL: Other Health Workers |  |
| 4 | PACIFIC ADVENTIST UNIVERSITY. Central Province |  |  |  |  |
| i | Diploma in General Nursing | Diploma 3years | Grade 12 | Pre- service RPL: Other Health Workers |  |
| ii | Degree in Maternal & Child Health Nursing | Degree 1year | Post Graduate | All category Health workers |  |
| 5 | OTHER NURSING SCHOOLS |  |  |  |  |
|  | Lae School of Nursing (affiliated with University of Technology): |  |  |  |  |
| i | Registered General nurse | Diploma 3years | Grade 12 | Pre- service RPL: Other Health Workers |  |
|  | St Mary’s School of Nursing Vunapope (affiliated with DWU): |  |  |  |  |
| ii | Registered General nurse | Diploma 3years | Grade 12 | Pre- service RPL: Other Health Workers |  |
|  | Nazarene College of Nursing (affiliated with the Christine Nursing Consortium of Nazarene Universities): |  |  |  |  |
| iii | Registered General nurse | Diploma 3years | Grade 12 | Pre- service RPL: Other Health Workers |  |
|  | St Barnabas School of Nursing, Alotau (affiliated with DWU – in process): |  |  |  |  |
| iv | Registered General nurse | Diploma 3years | Grade 12 | Pre- service RPL: Other Health Workers |  |
|  | Mendi School of Nursing: |  |  |  |  |
| v | Suspended since 2003 |  |  |  |  |

Annex IV –

Problem Tree and Analysis

Annex Va –

Terms of Reference: Design Mission for Support to Medical Training and Tertiary Health Services in Papua New Guinea

- Background

General

The Government of Papua New Guinea (GoPNG) Medium Term Development Strategy 2005-2010 (MTDS) highlights health as a key development priority.  The Health Sector National Strategic Plan (2006-2008) (NSP) focuses the broader objectives outlined in the Health Sector Medium Term Expenditure Framework (2004-2006) and the National Health Plan (2001-2010) into seven key strategic directions: childhood immunisation; reduction in malaria; reduction in maternal mortality; reduction in rate of increase of STI and HIV; reduction in TB; improving leadership and management; and improving organisational performance.  The objectives of the Australian program closely align with those of the Government of PNG; the AusAID goal is to support improved service delivery and stability through assisting health systems reform and supporting delivery of the Health Sector NSP.

With the support of both Government and Development Partners, the health sector has spearheaded the sector wide approach (SWAp), in PNG, referred to as the Health Sector Improvement Program (HSIP).  The primary aim of the HSIP is to provide leadership in coordinating and managing donor assistance to the health sector.  This allows the GoPNG and the NDOH to coordinate and prioritise donor funded interventions in health, with the intention to strengthen government systems rather than work around or parallel to them.

Since signing the HSIP partnership agreement in 2002, AusAID has supported the move to a SWAp through reducing the number of stand-alone projects; channelling more funding through the HSIP trust account; and combining technical assistance into one mechanism – the Capacity Building Service Centre (CBSC).  Australia recognises that whilst it is the whole of PNG Government responsibility to address issues constraining improvement in the health outcomes of PNG citizens, AusAID can assist by strengthening national service delivery mechanisms and helping facilitate a stronger relationship with Central Agencies by utilising other programs operating at the central level.

The White Paper on Australia's Overseas Aid Program and Health Policy: Helping health systems deliver both state that Australia will significantly increase support to improve the health and well-being of people in the Asia-Pacific region, with the health policy providing a primary focus on strengthening health systems.  The shortage of appropriately educated and motivated health care workers (HCWs) is a major obstacle to health system performance and the Australian Government aims to strengthen health systems in PNG by assisting with immediate and long term health workforce development needs.

Medical School Support Project (MSSP)

Since the late 1980s, the University of Papua New Guinea, School of Medicine and Health Sciences (UPNG SMHS) has received various forms of support from AusAID – initially through projects, Medical Officer Training Program (MOTP) and Medical Officers, Nursing and Allied Health Sciences Training Project (MONAHP), managed by Australian contractors, and more recently through the MSSP managed by UPNG SMHS.  Both the National Department of Health (NDOH) and the SMHS have strongly supported the assistance provided to medical and health education in PNG recognising that many of the advances would not have been possible without donor support.

MSSP was initially funded over a three year timeframe, to be completed in December 2005, at a cost of $1,800,000.  It was subsequently extended until December 2006 and then until December 2007, a further extension to 30 March 2008 is planned to allow for the design of the next phase of support.  An additional $1,000,000 was provided to cover this two year extension totalling $2,800,000 from 2003 to 2007.

The objective of the UPNG MSSP is to assist the SMHS deliver priority health education programs as well as to build sustainable institutional capacity.  Program outputs include: training of academic and administrative staff; teaching support for Master of Medicine students provided by visiting medical specialists; and teaching support provided by nursing advisers for students in the Bachelor of Clinical Nursing Program.  It was also intended to prepare the SMHS for a key role in the implementation of the NDOH Human Resource Development Strategy.

MSSP is not a “project” as such; it does not have an AMC but rather provides accountable cash grants in six-monthly tranches.  Financial accountability measures include the submission of financial acquittals by UPNG &HS for each of the tranche periods, as well as external audits.

Other AusAID’s support to pre-service training has been provided primarily through the Women’s & Children’s Health Project (WCHP) and the Health Services Support Program (HSSP).  At the country program level, AusAID also provided education and training through the PNG Australia Targeted Training Facility (PATTAF).

Tertiary Health Services Project (THS)

The purpose of the project is to overcome the shortage of trained and skilled specialists which inhibits PNG from delivering essential secondary and tertiary care.

Targeted Australian support to the tertiary health sector in PNG began in 1996 under the Provision of a Range of Tertiary Health Services to Pacific Island Countries Project (PIP).  The PIP provided services and training to ten Pacific Island Countries and aimed to improve access to adequate tertiary health services in specialised areas.  The PIP was primarily a humanitarian project; it provided surgical procedures not normally available in-country (rather than focussing on capacity building).

PNG was included in PIP until 1998, after which time a PNG-specific Tertiary Health Services (THS) project was established.  This phase of support ran from 1999 – 2001, and was known as THS Phase 2.   THS 2 was made up of four components, one of which focussed on on-the-job training of local clinicians (in support of direct service under other components).

THS 3 commenced in 2002 and included a capacity building component.  One objective of THS 3 was to assist PNG to move toward being self-reliant in providing surgical services.  THS 3 has recently been extended for nine months and will now finish in March 2008.   Funding for THS 3 (June 2002 – March 2008) is $4,242,247.

The Project is managed by the Royal Australasian College of Surgeons (RACS).  Processes to ensure effective operation and communication of the Project  includes the establishment of a Project Coordinating Group, which meets annually in Port Moresby and a Tertiary Health Services Committee which also meets annually to plan visits and to discuss issues arising from these visits.  A part-time administrative position is also established in-country.

Reviews

- Pre- Service Training Review.   In 2005 a rapid review of pre-service training, defined as undergraduate training in technical or health-specific fields (medicine, nursing, community health workers, health administration etc.) and post-basic nursing courses in such priority areas as midwifery and paediatrics, provided through AusAID activities in the PNG health sector and an assessment of critical pre-service training needs was conducted.   The review included the identification of options for AusAID’s future support for pre-service training over the next five years.  .

- Concept Peer Review.   The Pre-Service Training Review underwent a Concept Peer Review, which recommended a number of studies be conducted before moving to design.   These studies have not been undertaken as other priorities within the NDOH have taken precedence.   The current Public Sector Workforce Development Initiative (PSWDI) has now focussed the NDOH on these issues and AusAID’ assistance has been requested.

- Tertiary Health Services Review.   A review of tertiary health services was undertaken in April 2007.   The review team produced a report of their findings as well as an Options Paper on alternatives and recommendations for future support to tertiary health services in PNG.

- New Initiative

AusAID determined that given the strong relationship between the THS and MSSP programs in supporting the training of various categories of health workers, and supporting tertiary health services that future support should be through a new Initiative that would bring the two activities closer together.   In developing the design for this initiative the issues, recommendations and options from the reviews should be considered.

- Timeframes

It is planned that the Initiative will commence in March 2008 and finish in March 2013.  However, a phased approach with the flexibility to respond to the outcomes of the GoPNG Health Workforce Summit (October/ November 2008) and other policy developments is desirable.

- Funding

Subject to approval, it is planned that AusAID would allocate a budget of approximately AUD$10 million over five years for this Initiative.

- Issues for consideration in the initiative to support medical training and tertiary health services in PNG

The overall aim of the Initiative will be to contribute the strengthening of medical training and tertiary health services in PNG.   In designing a program for future support for both medical training and tertiary health service delivery there are seven key issues based on the recommendations of the review, to be explored.

- Strengthening links between the two projects

Recognising the existing links between the current MSSP and THS 3 programs, the design should investigate how these can be strengthened.   The design should consider whether this could be done through a single activity encompassing both functions (e.g. a broad program of development and assistance for Health Professionals), or through greater information sharing and coordination between two separate Activities under one Initiative.  The design should also, in proposing how these linkages can be strengthened, address any potential management and contracting implications of the recommended future Initiative.

- Alignment with a broader PNG National Health Workforce Strategy

National Department of Health is planning to host a Health Workforce Summit in October/November 2008.  The likely theme of the Summit is Rural Workforce.  We anticipate the Summit will have a focus on longer term issues, and will involve all relevant agencies and donors.   It is hoped that a key outcome of the Summit will be progress towards a PNG National Health Workforce Strategy.  Although this is a long-term endeavour, AusAID hopes to obtain some initial guidance through the Summit regarding the priorities and how we can best contribute.  It is important that the “medium-term” program be flexible as ultimately it will need to align with the National Health Workforce Strategy, once this is finalised.

- Expanded focus to include broader health workforce needs

Support to the NDOH to collect and analyse health workforce data, including assistance with registrations (through the responsible professional bodies), and succession planning, career and other development, remuneration should be considered through this Initiative.

- Closer alignment with the sector wide approach (SWAp)

As AusAID strengthens its contribution to the SWAp, stand-alone projects such as MSSP and THS become more and more anachronistic.   However these projects are highly valued, including by the University of PNG and hospitals throughout the country.   In consideration of this, the review of THS 3 stated that “it is acceptable to have a project within a SWAp” and that the issue is about bringing ownership closer to PNG.  This includes having PNG government, institutions and staff drive the timing and priorities for external visits and assistance.  The review proposed continuing under the existing model, investigating synergies that could be developed with other programs under the SWAp.   The challenge is to ensure the effectiveness of this support without undermining the principles of the SWAp.

- Strengthening the role of Australia partners

The RACS has supported the tertiary sector in PNG, including as managing contractor for THS.  Other Australian professional colleges (including Royal Australian & New Zealand College of Obstetrics & Gynaecology (RANZCOG)) have also had involvement.   Others such as the Royal Australian College of General Practitioners (RACGP) have indicated an interest in becoming involved with this sector.   Other potential “partners” include professional organisations and NGOs.

- Strengthening regional linkages and possible development of partnerships

The notion of a regional approach to supporting medical schools and/or tertiary health services in the Pacific has been raised within AusAID and by RANZCOG.   This would involve fostering closer linkages with the Fiji Medical School (FMS).  The extent of such linkages could range from enhanced communication between the two schools to the amalgamation of funding.   The Pacific Branch recently undertook a feasibility study to inform development of an Initiative on Human Resources for Health.  The study report should inform the design team.

- Expanded focus

Australia has provided core funding to the UPNG SMHS over a number of years.  However, there are other institutions in PNG that provide pre-service training for not only medical but also health care workers.  The Initiative should investigate the feasibility of providing support to these institutions to play an increasing role in both pre service and continuing education.   There may be a need to develop a strategy for support of these institutions for the medium to longer term.

- Design Mission

- Objectives of the Design Mission

The objective of the Design Mission is to produce a Design Document for a flexible Initiative to support medical workforce training and tertiary health services in Papua New Guinea from March 2008 to March 2013.

- Scope of Services of Design Mission

- In addressing the objectives of the Design Mission, team members are required to meet the following requirements:

- Preliminary Consultation Phase (Team Leader only)

Briefing

Attend briefing in Port Moresby with AusAID PNG Health Team

Consult

Attend PNG Medical Symposium 3-7 September and undertake preliminary consultations with stakeholders

Debrief

Debrief AusAID PNG Health Team on consultations

- In Australia –Planning, Review and Consultation Phase 
(Australian members only)

Briefing

Attend a preliminary briefing with PNG Health Program via video link to :

- review design mission Terms of Reference;

- discuss the roles and responsibilities for both Design Team and PNG Health Program;

- discuss the conduct of the Planning, Review and Consultation Phase; and

- discuss the In-Country Consultations Phase, including:

    - compiling a checklist of information to gather during the in-country consultations;

    - review  the draft program for the In-Country Consultation Phase; and

    - review travel and accommodation arrangements.

Review

- Review available data and reports listed at Attachment A;

- Research and review other information deemed relevant by the Design Team or the AusAID PNG Health Program on:

- current and future workforce requirements in PNG;

- the capacity of current systems/institutions in PNG to meet future needs; and

- the likely impact of HIV/AIDS on pre-service training needs.

Consult

Consult either face-to-face, by telephone or email with the following organisations/individuals:

  - Jim Tulloch, AusAID Principal Health Adviser;

  - AusAID Health and HIV/AIDS Thematic Group;

  - AusAID Design and Procurement Advisory Group;

  - The Royal Australian College of Surgeons (RACS);

  - The Royal Australian and New Zealand College of Gynaecologists (RANZCOG);

  - The Royal Australian College of General Practitioners (RACGP); and

  - Any other stakeholders deemed relevant by the Design Team or the AusAID PNG Health Program.

- Consultations must be structured to address the issues outlined in Issues for Consideration in the Initiative to Support Medical Training and Tertiary Health Services in PNG.

- In–Country Mission

Briefing

Attend a face-to-face briefing, before commencing the In-Country Consultation Phase, with the AusAID PNG Health Program to:

- Discuss progress of the design mission during the Preliminary Planning and Consultation Phase;

- Review and confirm the In-Country Consultation Program; and

- Review travel and accommodation arrangements.

Consult

Consult either face-to-face, by telephone or email with the following organisations and individuals:

- The AusAID PNG Health Team;

- The National Department of Health (NDOH);

- The Department of National Planning and Monitoring (DNPM);

- Port Moresby General Hospital;

- Provincial Hospitals as selected by the AusAID PNG Health Program;

- The University of PNG School of Medical and Health Sciences;

- The Divine Word University;

- Development Partners, including:

  - The World Health Organisation

  - NZAID

- Any other stakeholder deemed relevant by the Design Team or the AusAID PNG Health Team.

- Consultations must be structured to address the issues outlined in Issues for Consideration in the Initiative to Support Medical Training and Tertiary Health Services in PNG.

Debrief

Draft and present an Aid Memoire at a debriefing in Port Moresby with to the AusAID PNG Health Team and other stakeholders outlining:

- Design Mission objectives;

- Review and consultation process;

- Key findings; and

- Recommendations for new Initiative.

Drafting and Review Phase (All team members)

The Design Team must draft a design document and participate in the quality and review processes outlined in 3.  Design Document Requirements and 4.  Quality and Review Processes of the Design Document.

- DESIGN DOCUMENT REQUIREMENTS

The Design Document is required to outline a single Initiative with Activities to support:

- tertiary health services; and

- medical workforce training;

in PNG from March 2008 to March 2013 within an overall budget of AUD$10 million.

The Design Document must outlined a phased approach which will allow the Initiative to be flexible to the outcomes of the GoPNG Health Workforce Summit (October/ November 2008) and other policy developments.

The Design Document must provide:

- a realistic Initiative goal;

- clear and measurable objectives;

- an analysis of available aid delivery mechanisms and a recommendation as to the most appropriate mechanism for this intervention; and

- monitoring and evaluation arrangements which effectively measure progress towards objectives.

The Design Document must also include:

- an appropriate management, coordination and governance structure that is responsive to GoPNG needs, including clearly defined roles for all implementing partners and stakeholders;

- clear reporting mechanisms that will feed back into the monitoring and evaluation framework and respond to AusAID’s internal reporting requirements;

- an analysis and plan to address gender, sustainability, HIV-AIDS, anti-corruption and environmental issues;

- details of what, if any, technical assistance that will be required and associated Terms of Reference for any TA positions;

- an analysis of possible risks and constraints to implementation, and strategies to address these risks; and

- proposed implementation and costing schedules for the Initiative.

In drafting the Design Document consideration must be given to:

- addressing the recommendations of the three existing Reviews.

- addressing the seven key issues outlined in 2.  Issues for Consideration in the Initiative to Support Medical Training and Tertiary Health Services in PNG.

- Quality and Review Processes of the Design Document

AusAID requires the Design to undergo the following quality and review process:

- The draft Design will be reviewed by an Independent Appraiser, who will also complete a Quality at Entry Report.

- The Draft Design will also be appraised through an Appraisal Peer Review meeting.

- Design Team Members are required to attend (for all but Team Leader via telephone is acceptable) the Appraisal Peer Review.

- The Design Team will be required to incorporate Independent Appraisal and Appraisal Peer Review comments, as agreed to by peer reviewers and directed by PNG Health Team, into the Final Design.

- Design Team

The composition and responsibilities of Design Team members is outlined below:

All team Members must also possess strong analytical skills, cross cultural communication and interpersonal skills and the ability to present information coherently and succinctly.

| Team Member: | Responsibilities within the team: |
| --- | --- |
| Medical Education Specialist /Team Leader. |  |
| Has experience working with medical schools and tertiary health services. Has experience in the development context. | - providing leadership, including strategic direction and advice, to the Design Team - devising, in consultation with the AusAID PNG Health Team, a program of consultations - attend briefing, consultation and debriefing meetings in Australia and PNG - leading the preparation of, and subsequent presentation of the Aide Memoire at the debriefing meeting PNG - coordinating team member’s input into the Draft Design - contribute to the drafting of the Draft Design document - attending Appraisal Peer Review - incorporating of Appraisal Peer Review, Independent Appraisal and Quality at Entry comments into Final Design Draft - submission of Final Design |
| Design Specialist |  |
| Has strong writing skills and experience in designing development programs in the health and/or education field. | - providing strategic direction and advice to ensure the overall coherence of the various components of the Design - ensuring the Design meets AusAID design, quality and procurement guidelines - providing input to the program of consultations - attending briefing, consultation and debriefing meetings in Australia and PNG - lead the drafting of the Design document - attending the Appraisal Peer Review meeting (by telephone is acceptable) |
| A nominated representatives from the PNG National Department of Health |  |
| Understands the development context in PNG and has expertise or demonstrated knowledge in Medical Education; or tertiary health services; or health service delivery; or HR and workforce planning and training. | - attending briefing, consultation and debriefing meetings in PNG - providing strategic direction and advice from the perspective of the National Department of Health - providing input into Design documents as directed by the Team Leader - attending the Appraisal Peer Review meeting (by telephone is acceptable) |
| A nominated representative from the PNG National Department of Planning and Monitoring |  |
| Understands the development context in PNG and has expertise or demonstrated knowledge in priorities within PNG’s development cooperation program. | - attending briefing, consultation and debriefing meetings in PNG - providing strategic direction and advice from the perspective of the National Department of Planning and Monitoring - providing input into Design documents as directed by the Team Leader - attending the Appraisal Peer Review meeting (by telephone is acceptable) |

- Reporting requirements

The Design Team will produce all reports and other written outputs using Microsoft Office (for windows) software.  The written outputs of the mission and timing of reports are the responsibility of the Team Leader.

The following reports are required to be submitted to the AusAID PNG Health Team:

| Aide Memoire | 5 October 2007 |
| --- | --- |
| Draft Design Document – Draft 1 | 7 November 2007 |
| Final Design Document: incorporating Appraisal Peer Review comments as directed by the AusAID PNG Health Team | 21 December 2007 |

- Duration and Phasing of design mission

        - The following timetable is anticipated:

| Number of days | Location | Tasks/Events | Date |
| --- | --- | --- | --- |
| Preliminary Consultation Phase |  |  |  |
| 5 days + 2 days travel | PNG | Team Leader – Meetings with AusAID, PNG team members and contacts via the Medical Symposium | 3 - 7 Sept 2007 |
| Planning, Review and Consultation Phase |  |  |  |
| 5 days | Australia | Australian Team Members - Review documents - Participate briefing AusAID PNG Health Team via video videoconference - Consult with AusAID stakeholders - Consult with Australian based partners and other stakeholders | 17 - 21 Sept 2007 |

| In-Country Consultation Phase |  |  |  |
| --- | --- | --- | --- |
| 11 days + 2 days travel for Australian members | PNG | Full Team - Participate in briefing with AusAID PNG Health Team - Stakeholder consultations including provincial trips - Presentation of Aid Memoire to AusAID, GoPNG and other stakeholders | - 24 Sept 2007 - 24 Sept – 4 Oct 2007 - 4 Oct 2007 |
| Drafting and Review Phase |  |  |  |
| Up to 12 days plus 2 days Travel | Australia & PNG | Team Leader & Design Specialist - Coordinate team members input into Draft Design and submit to AusAID - Attend Peer Review – PNG - Incorporate Independent Appraisal, Quality at Entry and Peer Review comments as directed by the PNG Health Team and submit Final Design to AusAID | - 7 Nov 2007 - 30 Nov 2007 - 21 Dec 2007 |

Attachment A	   Reading List – to be provided to Design Team

Health Sector Monitoring and Review Group, Review of In-Service Training in the Health Sector of PNG, September 2003

HSSP, Training and Evaluation Review, July 2002

Iain W.  Aitken (Management Sciences for Health), PNG Training Institution Review report to HSSP, January 2002.

Ministerial Taskforce under the Chairmanship of Dr Isaac Ake, The Future of Pre-service Nurse and Community Health Worker Education, February 2002

NDOH (Whittaker and Ake), Human Resources In The Health Sector – Potential Issues Arising From The HIV/AIDS Epidemic In Papua New Guinea.  (Draft), August 2004

NDOH, Competency Standards Forum Minutes and Papers, February 2002

NDOH, Human Resource Development Strategy, September 2002

NHASP, Training Impact Assessment and Evaluation, Milestone 78 Part 1 Report, February 2005.

WCHP, Review of In-service training, September 2004

World Federation for Medical Education, External Peer Review of the Medical Course of the School of Medicine and Health Sciences at UNPNG, March 2004

Review of Capacity in the Health Sector, Papua New Guinea: A Stocktake, March 2005

Review of the Human Resource Management Branch, National Department of Health, Papua New Guinea, March 2005

Reference List: Capacity of the Health Sector, Papua New Guinea, January 2005

PNG National Training Council, National Training Priorities 2000-2001, January 2000

AusAID PNG Education Sector Affordability Studies Paper 2: Financing of Tertiary Education, September 2003

Activity Completion Report – MSSP 2004

Pre Service Training Review – RAMP 2005

Activity Completion Report – THS 3 2007

Independent Review THS and Option Paper

Medium Term Expenditure Framework

Strategic Plan for the PNG Health Sector 2006 - 2008

NDOH, National Policy on Human Resources in the Heath Sector 2007

Annex Vb –

Terms of Reference: Design Revision for Support to Medical Training and Tertiary Health Services in Papua New Guinea

Background

AusAID is seeking to establish a new program of support for health professional training and tertiary services in PNG, to commence at the beginning of the 2008/09 financial year.  This program will draw together what have in the past been two separate AusAID projects (the "Medical School Support Project"  [MSSP] and the "Tertiary Health Services Project" [THS]).  In addition the new program will broaden the scope of support to include training for a wider range of clinical health professionals (e.g. nurses, rural health workers) in addition to medical graduates and undergraduates; previously, the focus has been on specialist doctors only.

This proposed new approach was agreed in principle within AusAID in mid 2007.  Two independent consultants were engaged to develop a design for implementation.  As part of the design process they met with a broad range of stakeholders, both in Australia and in PNG, and also reviewed a number of previous studies and reports.

The independent consultants submitted a draft design for the new program, titled Support to Health Professional Training and Tertiary Services, to AusAID in November 2007.  AusAID requested a number of amendments to this draft design, and in particular sought to align the new program more closely with the PNG health SWAp.  An updated version was provided in February 2008.

Since then, AusAID has continued to consider the most suitable model of support, and in particular how best to maximise the effectiveness of the new program and meet the needs of all stakeholders.   It is clear that whilst the current draft has captured a vast array of information and is a constructive step forward, there is still scope to improve some aspects.  In particular the proposed management arrangements are complex.  Whilst the need to work within the SWAp whenever possible remains important, this must be balanced against other considerations (such as operational efficiency and existing relationships between stakeholders).

Since the existing draft of the design was completed the HHTG has committed to provide additional funding of up to $1m per annum to the UPNG SMHS under the Strategic Partnership Initiative (SPI). These funds would augment the support provided through the PNG program within the parameters of the broader program of support. The intention of the SPI is to support the longterm development of UPNG SMHS as an institution with a focus on supporting the organisations strategic plans and existing management structures.

A number of Australian institutions (professional colleges and medical schools) already have strong relationships with the UPNG SMHS. The School has also been working with Divine Word University and other institutions within PNG to develop a shared approach to rural training. An issue of interest to AusAID is how these relationships can best be supported within the parameters of the School’s capacity.

Given the importance and significant resources associated with this program, it is vital that its design and management framework be of the highest quality.  AusAID has therefore committed to reconsidering aspects of the draft design and revisiting some of these issues outlined above.

This Terms of Reference outlines a process for undertaking these revisions.  The revised design will subsequently undergo an AusAID peer review, with a view to operationalising the new program in July 2008.

Specific aims and objectives

The independent consultant will revisit the existing draft design, focussing on the following aspects:

- Options to support the long term development of the UPNG SMHS in line with the Strategic Plan and existing management capacity

- Options for streamlining the proposed management and governance arrangements, including consideration of HSIP mechanisms

- Options for possible expansion of support to UPNG using funds from AusAID’s new Partnerships for Health initiative, if appropriate

Another important element of the design revision will be to engage in further consultation with both UPNG and NDOH.  In particular AusAID seeks to lay solid foundations for ongoing collaboration with these organisations.

Methodology

The Design Revision will be undertaken by an independent consultant, with some administrative support by AusAID (Health Team, Port Moresby and Health and HIV Thematic Group, Canberra).

Information collection will be via consultation with stakeholders, including an in-country mission, as well as a review of existing literature and reports that are relevant.  This includes, but is not limited to, the following:

The in-country mission will take place in April over a period of approximately five days (3 days in-country and 2 days for travelling).  It is anticipated that all consultations will take place in Port Moresby, with an option to schedule a side trip to Goroka if needed.  Consultations will focus on the aims and objectives identified above, along with other relevant issues that emerge throughout the process.  Administrative arrangements for the mission will be undertaken by AusAID’s PNG Health Team, with support from the Health and HIV AIDS Thematic Group in Canberra. AusAID representatives may also participate in some of the consultations, as deemed appropriate.

Stakeholders to be consulted through this revision process are as follows:

- PNG’s National Department of Health

- Staff of the UPNG SMHS

- The Royal Australian College of Surgeons

- Other stakeholders as deemed necessary by the independent consultant in consultation with AusAID

It is noted that there are a number of additional stakeholders who have contributed to the first draft of this Design, not listed above.  The views and information provided by these stakeholders remain relevant and useful, and further consultation is not required as part of the current revisions.

Desired Outcome

The key output from this revision will be an updated design document in a format suitable for peer review.  This document will amend the existing draft to address issues outlined above.

Annex Vc –

Additional Reference Materials: Design Revision Phase
Support to Medical Training and Tertiary Health Services in 
Papua New Guinea

AusAID.  Pre-Service Training Rapid Review and Assessment Mission, Papua New Guinea (2005)

AusAID.  Strengthening Capacity of the Fiji School of Medicine: A Program within AusAID’S Health Systems Strengthening in the Pacific Initiative (Design Document, 2008)

Concept International Ltd.  Human Resource Management and Payroll Project: Implementation Planning Study (2001).

National Department of Health.  Human Resources Branch Three Year Capacity Improvement Action Plan, January 2007 – December 2009 (2006)

National Department of Health.  National Policy on Human Resources in the Health Sector (undated)

National Department of Health.  One System Tasol: Creating a Provincial Health Authority (2008)

Tefuarani N, Vince J, Hawker R et al.  Operation Open Heart in PNG, 1993-2006 (unpublished manuscript, 2006).

Watters DAK, Kapitgau WM, Kaminiel P et al.  Surgical capability and surgical pathology in Papua New Guinea in the year 2000.  Aust NZ J Surg, 2001; 71: 274-280.

Watters DAK, Scott DF.  Doctors in the Pacific.  Med J Aust, 2004; 181: 597-601.

Watters DAK, Thiele DE.  Progress of surgical training in Papua New Guinea to the end of the 20th century.  Aust NZ J Surg, 2000; 70: 302-307.

Whittaker M, Jayasuriya R.  Program Nine: Human Resource Development (Health Services Support Program Briefing to AusAID; 16 January 2004).

Annex VI –

Feasibility Study for a Human Resources for Health Initiative
in Pacific Island Countries – Aide Memoire

Aide-Memoire to AusAID

regarding meetings with the School of Medicine and Health Sciences,

University of Papua New Guinea June 11-15, 2007

BACKGROUND

As part of the AusAID feasibility study for a Human Resources for Health initiative, Professor John Hamilton (Consultant), Dr Juliet Fleischl (Health Systems and Human Resources Focal Point, WHO South Pacific, Suva) and Kye Taylor (AusAID) undertook meetings with AusAID Post at PNG, WHO, Government of PNG, Department of Health (GOPNG, NDOH), and staff of all sectors of the School of Medicine and Health Sciences (SMHS.)

PROPOSED HUMAN RESOURCES FOR HEALTH INITIATIVE IN THE PACIFIC

AusAID commissioned the feasibility study to explore options for areas of support under an HRH initiative.  The overall aim of the initiative will be to contribute to the strengthening of health systems in Pacific Island countries.  It is anticipated that regional cooperation on health workforce training, planning and recruitment will improve the stability and capacity of that workforce, and have a positive impact on health indicators over time.

The purpose of the initiative will be to:

- Improve the availability of quality health care.  Depending on the outcome of the feasibility study this will be accomplished through increased numbers of skilled doctors and, increased numbers of other types of health care workers (including health managers, biomedical engineers, etc); and

- Improve the capacity of countries in the Pacific region in human resource management including health workforce planning, monitoring and retention.

During the in-country visit to PNG the team was asked to examine and comment upon

- an assessment of institutional issues and operational capacity issues;

- the demand for and potential role of UPNG in supporting HCW education in other PICs; and.

- the demand for UPNG’s involvement.  For example, is there a case for UPNG to support HRH in the Pacific more broadly? What is the current capacity of UPNG facilities and systems to increase the intake of students into their medical and allied health streams? What further assistance may be required?

Support for the UPNG is provided through PNG’s bilateral health program, specifically the Medical Schools Support Project (MSSP), which is due to end on 31st December 2007.  With the current MSSP is soon to finish, the visit was also an opportunity to consider concerns expressed in-country and by Australian institutions and professional bodies about the school’s long term capacity and staffing, and provide recommendations to PNG Branch and the AusAID post.  Documents reviewed included successive health strategy plans, progress reports and external reviews of the School of Medicine and Health Sciences (SMHS), MONAPH, and the MSSP.

SUMMARY OF FINDINGS

The School of Medicine and Health Sciences (SMHS) of the University of Papua New Guinea (UPNG) has a fine record over many years in training national health care workers, resulting in a predominantly national staffing of the health service and the Faculty.

During the past twenty-five years AusAID and its predecessors have supported UPNG, SMHS, most recently, from 1989, through the Medical Officer Nursing and Allied Health Professionals Project (MONAHP) and, the Medical School Support Project (MSSP).  Reviews have confirmed the positive impact of the curriculum conversion of the curriculum to a problem based approach and the role of the Medical Education Unit (MEU).  Experienced clinicians commend the improved performance of graduates from the new curriculum.

These must be built upon.  But they are threatened by major difficulties which are well recognized by the Dean.  Loss of academic staff in a number of key clinical and basic science disciplines.  Others are approaching retirement.  Health service clinicians always contribute to teaching.  But in some disciplines such as Mental Health and some areas of basic sciences and pathology there are no academics

Succession planning for academic leadership is required urgently.  Local and promising graduates identified by SMHS leadership are attracted to an academic career, but their interest founders on the issue of salary.  The difference is mainly to do with on call and other clinical allowances which had been agreed to be extended to academics but had never provided.  This can only be addressed and solved within PNG.  But if it is not solved the School will be in jeopardy, and be dependent on recruitment from countries outside the region, turning back the achievements of the last several decades.

Medical Staff within the health service are also in short supply, especially in some clinical specialties in Port Moresby General Hospital (PMGH), the main teaching hospital.  This weakens clinical care, and teaching.  Both recruitment and retention are involved.

In relation to recruitment, some recent graduates from M Med programmes have expressed frustration at the conditions of service and rigidity of the Public Service Commission rules, and some have returned or remained overseas.  This needs urgent attention.

In relation to retention, there are good examples of career development and continuing collegial support, notably in Paediatrics.  The NDOH and SMHS have a stake for all groups, and SMHS should be provided with resources to support continuing medical and professional education.  Partnerships with other health professional training institutions in PNG.

To counteract the shortage of staff there is pressure to increase enrollments in medicine.  To make this possible, current academic shortages must be dealt with and Clinical Schools should be set up in selected Level 2 and 3 Hospitals.

A proposed M Med in Rural Health to address the needs of rural hospitals should be progressed and training opportunities provided in rural hospitals and community clinics.  Co-operation with a counterpart programme in Fiji School of Medicine (FSMed) would be a clear benefit.

Provided progress is made in correcting the core staffing problems discussed above, UPNG should expand its role in training for Pacific Islands.  There are already students from Melanesia.  The planned clinical school in Honiara should be progressed.

Research:  SMHS should continue to co-operate with the Institute of Medical research in Goroka for research co-operation and academic career development.

For other health professions their highly supportive outside partnerships should be progressed and involved in career development of local graduates for future academic leadership.

International co-operation and partnerships have been a mainstay of UPNG since its foundation.  Comments from staff in UPNG about how they might be progressed to provide for lasting benefit are noted in the body of the report.

In Conclusion, it is vital for the health of Papua New Guinea and nearby pacific Islands that UPNG, FAHS recover from present constraints and thrive as a key contributor to Human Resource Development for Health.  There is no alternative institution and both it and FSMed are essential.  There is benefit in close co-operation between them, but without losing their independent identities.

Some issues, such as salary discrepancies can only be handled by GOPNG.  External funding is urgently recommended for

- Academic staff development in clinical and Health professional disciplines, basic sciences and medical education,

- Strengthening and expanding the scope of the Medical Education Unit

- Expanding student intake for PNG and for Pacific Islands, and the opening of clinical schools in level 2 and 3 Hospitals

- Bridging appointments and clinical staff development for health services and their educational capacity

- Training for rural health care through M Med Rural Health

FINDINGS & OBSERVATIONS WITH RESPECT TO MEDICINE CURRICULUM

In 2003 the curriculum revision to a Problem Based Learning (PBL) format was completed, and there have since been four cohorts of graduates from the new programme.  Problem Based Learning is an important innovation, but not the only one, and the structure and organization of clinical attachments, assessment, expanded skill development, communication skills and extensive community based experience have all been strengthened.  The content reflects closely the priority health problems of PNG, the social and cultural aspects of health and health care.  The appointment of national academic staff has been active and successful.

Students have a five year curriculum, but Year 1 is a science preparation year, provided outside the Faculty.  Years 2 to 5 are spent in the SMHS.  The workload is considerable, and the academic year at 42 weeks is longer than in many other schools.

To develop the capacity of students for self-directed learning a number of successful strategies have been introduced, such as students running tutorials as facilitators, and a limited provision of electronic learning resources.  This also reduces to a small degree the use of staff time, but this alone will not combat the dire loss of senior academic staff (to be addressed below).

Medical Education Unit

The development of the Medical Education Unit has been a fine achievement.  It has been an admirable central resource and driving force for change, has assisted and advised widely and has ensured effective deployment of external visiting consultants.  The AusAID Consultant in Medical Education is in the process of handing over responsibilities for the running of the medical curriculum, extending the experience of the designated national successor.  The Unit has successfully taken responsibility for continuity of project management of MSSP.  There are new roles to be considered that will require young graduates with an interest in medical education to take full or part time roles in the Unit.  These roles will be identified below.

Support systems essential for this or any other form of curriculum have been successfully built up.  For example:

- The Medical Education Unit comprises an effective and experienced administrative team of national staff.  This has been successfully incorporated into SMHS establishment;

- Library development with modern systems and electronic access and improved holdings;

- IT capacity with a potential for distant learning for students on community and rural placements and continuing professional education;

- Systems of tutor training and staff development for both academic and health service staff; and

- Systems of student assessment for which, in the longer term, secure facilities will be advisable.

Recommendation 1: That achievements in curriculum reform in undergraduate medicine and institutional strengthening be recognized as major and positive achievements.

Imperatives for Maintenance of the Undergraduate Curriculum

Before considering the issue of SMHS’ capacity to enlarge student intake, it must be recognized that the capacity to maintain the current situation is under strain.  This affects both undergraduate and postgraduate teaching and training.  The constraints are:

- A loss of key senior academic staff, with others soon approaching retirement.  In key clinical fields some Chairs are either vacant or soon to become vacant.  The 2003 World Federation for Medical Education (WFME) report called attention to the problem; one further chair has been vacated since then.

- No junior academic staff in some disciplines.  In Mental Health and Psychiatry, a clinician has generously stepped in, supported by colleagues, but with no relief to her routine clinical duties.  There is a similar situation in some branches of Pathology, and in Anatomy.  At the moment clinicians and the Consultant in Medical Education are attempting to fill the gaps.  Academic development through a combined M BioMedical Science and Clinical Graduate Diploma or Diploma has been proposed as the route for career development for young graduates to provide clinically relevant basic science and pathology teaching, ideal for an integrated curriculum.

- Loss of staff in Public Health.  NDOH staff have filled some gaps and have much to offer, but academic staff need to be recruited.  At the same time the NDOH and the academic arms of public health should be drawn together for optimum co-operation and productivity.  The Division of Public Health is responsible for the important community and rural experience in the undergraduate curriculum in medicine, and as such, strengthening its capacity is an urgent priority.

- Some young graduates are interested in a career that includes medical education.  A programme for career development is under consideration through the Medical Education Unit and partnership links with overseas institutions.  This will require funding.

- Succession Planning, especially for leadership, is urgently needed.  The development of some academics from graduates of SMHS has been achieved already; however, many are discouraged by the wide differentials between health service and academic salaries.  A young trainee with full allowances might earn more than the professor of the clinical discipline who might carry a full clinical load and post-graduate teaching.  This situation similarly threatened academic medicine in Australia but was resolved by funding systems to achieve equivalence.  The Dean SMHS has the matter in hand, noting that there was an earlier agreement to extend clinical allowances to academics which has never been enacted.

- Ongoing evaluation of the undergraduate programme is essential, both through regular review during the undergraduate years and by following-up students in order to track their career experience.  The Medical Education Unit has identified this as an important and enduring role, but constraints of funding and staffing limit the extent of follow-up, especially of graduates during their postgraduate years.

- New challenges arise as the health situation of PNG evolves.  As an example, teaching about HIV/AIDS, and the larger issue of Sexual and Reproductive Health is well developed, but needs to be adjusted as new approaches and guidelines for management are published.  This requires sufficient academic staff who can link with outside agencies and NDOH.  The benefit flows on to all training programmes, including postgraduate and career.

- Rural experience, central to this curriculum, has been limited by funds and travel costs.  The matter of postgraduate training for rural practice will be addressed below.

Recommendation 2: That the constraints with respect to staffing, succession planning and recruitment of young national graduates to academic careers be addressed with the utmost urgency to ensure that recent achievements are sustained and to enable the Faculty to expand its response to the health needs of PNG and Pacific Islands.

The Role of UPNG in Undergraduate Training for the Pacific Islands

The purpose of the mission was to look at UPNG’s role in training medical workforce in the region and possible capacity to increase the intake from other PICs.  UPNG already has a steady flow of undergraduates from Pacific Islands, mostly from Solomon Islands.  This preference on their part reflects closeness of distance and culture, and similarity of health issues.

In considering the capacity to increase enrolment there is a concern that the current hospitals and staff are fully stretched in clinical teaching.  There is evidence of this in the recent experience of a higher than usual number of students in Year 4, resulting from re-entry of a larger cohort of students who had taken a year out for a Bachelor of Medical Science.  This led to problems in the clinical clerkship, with patient fatigue and overstretching of staff capacity.

An increase in enrolment beyond a small number would be unwise unless the current constraints are successfully addressed as follows:

- The current constraints of staffing are lessened, and

- As proposed by the school, new clinical schools are opened in Level 2 and 3 hospitals.  Candidates have been identified and a costed-plan requested.  Additional funding would be required for:

- student accommodation and teaching academic facilities,

- logistic and travel support,

- IT linkages and adaptation of curriculum support to distance learning, and

- new academic staff appointments.

- There would be a collateral benefit of creating a site for vocational and post graduate training appropriate to rural settings, which might be acceptable for support by donors and benefit from partnerships with those academic and professional groups in Australia who have offered their experience and commitment to rural health.

Recommendation 3: Before any increase in student intake can occur strengthen the Faculty (Recommendation 2) and open new clinical schools.

The option of creating a clinical school in Honiara is under consideration.  If that were set up then a small increase in Pacific Island students could be undertaken.  The Honiara proposal should be progressed.

Interns from the Islands should return for internship to limit the cost of intern salaries to GOPNG, NDOH.

Recommendation 4: UPNG should promote its role in training Pacific Island undergraduates in consultation with Fiji School of Medicine.  Provision for experience in Solomon Islands should be progressed through the present close links and the development of a clinical school in Honiara.

Retention of Medical Staff in the Health Service & Continuing Professional Development

There has been an increase in the previously small loss of graduates to other countries and to the increasingly lucrative private and commercial sector.  This brings forward an important priority of ensuring satisfaction with careers in the public sector.  Both UPNG and NDOH have a role to play in continuing education for graduates of medicine and for all other health workers.  This is identified in a number of previous reports.

All practitioners of any degree of specialization need continuing professional development, and professional groups, universities and training centres all have a role to play.  There is a particular need to ensure optimum career development of medical officers who do not wish to specialize.  They are a group similar to Career Medical Officers in Australia.

This would require careful educational planning and distance learning, for which an ideal resource could be set up within the Medical Education Unit, with dedicated staff including staff from other major professions, such a nursing.

Recommendation 5: That the faculty co-operate with NDOH to develop a plan for continuing medical education, using the Medical Education Unit.

Postgraduate Training

Postgraduate Diplomas are awarded in major specialties.  The Masters of Medicine, awarded in a wide range of clinical specialties and sub-specialties, is the main route for specialty qualification.  Support and experience in overseas centres, mainly Australasia, is provided on an ad hoc basis, promoted by particularly committed individuals.  However, the staff deficits that impinge on the undergraduate teaching also impinge on the postgraduate training.

Recommendation 6: That postgraduate training in specialties and sub-specialties be sustained, with particular effort to address deficits in staffing.  These are essentially the same deficits as for undergraduate medicine.

Training for Rural Health and the M.  Med.  Rural Health

The team noted that the proposal for a Masters of Medicine in Rural Health has received much support and offers of help for placements, especially from Church groups, and a partnership with Divine Word University appears to be a possibility.  Furthermore, support for this initiative has been offered by the Rural Division of the Royal Australasian College of General Practice.

The need for distance learning and continuing professional development has been acknowledged.  Also, the proposed outcome qualities of the graduates - a combination of clinical, public health and management skills, and the capacity to supervise health teams - are all vital.  The graduates would be most effective if embedded in a team, with appropriate facilities.

This is an important initiative and should be progressed as a priority.

Recommendation 7: That the proposed Masters of Medicine in Rural Health be progressed as a priority.

Other Health Professional Training

Responsibilities for healthcare worker training are shared with other institutions such as NDOH, Devine Word University and the Adventist College.  Positive co-operation and partnership should be encouraged.

SMHS remains as the main training route for staff for many of the other programs, including undergraduate awards for Pharmacy, Medical Laboratory Technology, Medical Imaging, Dentistry and post-basic Nursing.  All face common difficulties of staff retention, reliance on overseas help, and poor hospital facilities or staff for clinical placements.

Dentistry has been rebuilt with enthusiastic support from colleagues in Australia.  A problem now arises with the retirement of the main leader in the Partnership.

Proposals are under consideration for Masters programs to enable the professions to develop their own academic staff.  Partnerships and placements now active in Australasia will all be of value for a Masters.

Recommendation 8: The professional training programs will continue to be the main source of training for health workers in some professions.  Strengthening of staff and facilities for clinical placements are priorities shared with medicine.  The proposal to commence Masters programs should be supported.

Research

A research agenda is vital for the academic maintenance of any medical school, the scientific rigour of its teaching, its capacity to provide for academic development of its staff and future staff, its capacity to contribute to national policy formulation and evaluation, and its interaction with the international academic community.

The realities in most developing countries make it difficult to aspire to the level of research in better resourced countries, but this can be offset by effective research partnerships with institutions with a research capacity and an interest in research into global health problems.

UPNG is fortunate in its association with the Institute of Medical Research (IMR) in Goroka.  It is free standing, but associated with the University.  It provides an ideal opportunity for research for intercalated B Medical Science students, a well recognised first step for a future academic career.  It also would provide for staff development in research for future academics upon whom the School must depend for its future leadership.

The Faculty is already benefiting from these links and they should be promoted and strengthened.  International partnerships should be used to widen the scope of Faculty research and to build capacity.

Not all research needs can be catered for in IMR and the Faculty should continue to encourage research within Port Moresby, and extend it, in particular in Public health, in rural areas, in co-operation with the NDOH.

Recommendation 9: The research capacity of the Faculty be progressed through increasing co-operation with IMR, overseas partners and international agencies.  Priority themes should relate to health needs of PNG and PICs.

International Cooperation & Support

The same issues arise as for FSMed.  The following section is equally applicable to FSMed as to SMHS, UPNG.

International co-operation has been a mainstay of UPNG from its foundation, mainly with institutions, Universities and Royal Colleges in Australia and New Zealand and international aid.  These same institutions have indicated concern for the continuing welfare of both medical schools, and willingness to assist in addressing future priorities in cooperation with AusAID and NZAID.  Current partnerships are indicated in the sections above on Research and Other Health Professions and Postgraduate Training.

For the future some principles should guide partnership support and funding.  These comments reflect frequent observations by individuals in both countries during the review.

Most effective and efficient partnerships depend on committed individuals, mutual benefits and ensuring that capacity is built in country to last.  This includes management capacity, and there should be a minimum of expenditure outside the country for management.

For benefits to last a long time scale of support is essential.  A five year cycle is too short and initiatives falter.  Although funding cycles in donor agencies have to be respected, assurance of continuity of funding should as far as possible be built in.

Governments should be encouraged and supported in tackling the factors that lead to loss of the benefit of development initiatives, in this case the “push factors” of limited opportunities in career development, salary equity between academic and health service, continuing education and reliability in health service provision.  Direct aid support is appropriate to tackle these issues, and again, requires a long term perspective.

Overseas institutions would help their Pacific Island trainees and colleagues by continuing contact and involvement.  A particular point was made that Royal Colleges should incorporate their M.  Med.  trainees through a Pacific Chapter and give them access to continuing education and other collegial benefits.

The AusAID Partnerships for Health initiative could provide support for the development of Australian capacity building as partners in the Pacific.

Recommendation 10: In Planning support and co-operation from overseas institutions the comments and principles presented to the review should be taken into account to ensure optimal long term impact and local capacity building.  The AusAID Partnerships for Health initiative could provide a framework for co-operation.

##### Summary of Recommendations

| No. | Recommendation |
| --- | --- |
| 1 | The achievements in curriculum reform in undergraduate medicine and institutional strengthening in its support be recognized as major and positive achievements. |
| 2 | That the current situation with respect to staffing, succession planning and constraints recruitment of young national graduates to academic careers be addressed with the utmost urgency to ensure that recent achievements are sustained and to enable the Faculty to expand its response to the health needs of PNG and Pacific Islands. |
| 3 | That an increase in student intake be positively addressed, recognizing the need to strengthen the Faculty (Recommendation 2), and for new clinical schools to be opened. |
| 4 | UPNG should promote its role in training Pacific Island undergraduates in consultation with Fiji School of Medicine. Provision for experience in Solomon Islands should be progressed through the present close links and the development of a clinical school in Honiara. |
| 5 | That the faculty co-operate with GOPNG, NDOH, to address the factors contributing to loss of health service staff, and develop a plan for continuing medical education, based on the Medical Education Unit, to sustain professional development. |
| 6 | That postgraduate training in Specialties and sub-specialties be sustained, with particular effort to address deficits in staffing. These are essentially the same deficits as for undergraduate medicine. |
| 7 | That the proposed M. Med. in Rural Health be progressed as a priority. |
| 8 | The professional training programs will continue to be the main source of health workers in some professions, and of staff for all institutions involved in health worker training. Strengthening of staff and facilities and clinical placements are priorities shared with medicine. The proposal to commence Masters programs to train national staff for the future should be supported. Partnerships and co-operation with other institutions involved in Training the health workforce should be encouraged. |
| 9 | The research capacity of the SMHS Faculty be progressed through increasing co-operation with IMR, overseas partners and international agencies. Priority themes should relate to health needs of PNG and PICs. |
| 10 | In planning support and co-operation from overseas institutions the comments and principles presented to the review should be taken into account to ensure optimal long term impact and local capacity building. The AusAID Partnerships for Health initiative could provide a framework for co-operation. |

Annex VII –

SMHS Strategic Plan 
Synopsis, April 2008

Capacity building and staff training

- Negotiate with NDOH to ensure all NDOH contracts for all Health Professionals include a commitment to (requirement for) undergraduate and postgraduate teaching. Ensure this is supported with (UPNG) Conjoint academic appointments.

- Establish full-time academic positions in disciplines not currently represented within the School establishment, notably Psychiatry.

- Support Visiting Professors in key disciplines to provide interim leadership and training. Move towards focussed in-country training with visiting specialists working side-by-side with local graduates for short (recurrent) periods and providing an ongoing (longitudinal) mentoring role.  This would supplement existing training attachments in eg pathology.

- Review training options available through MMed, MMedSci, MPH and expand Graduate Certificate/Diploma courses to allow graduates to train in disciplines such as Pathology, Anatomy, Physiology whilst developing relevant clinical practice skills (e.g. Microbiology with Infectious diseases, Biochemistry with Endocrinology).

- Fast-track post-graduate training by identifying relevant training programmes delivered by distance learning and providing funding for junior staff to enrol in such programmes.

- Address infrastructure deficiencies (particularly internet access) to facilitate staff training (and continuing education) by distance learning programmes.

Fulfilling rural and regional roles and responsibilities

- Establish a Clinical School in Goroka to enhance basic clinical training, promote rural primary-care practice as a long-term career option and support Rural MMed training.

- Establish a Clinical School in Honiara to “localise” clinical training of SI students to the SI health system and to increase recruitment of SI students into medicine and other health professional programmes.

- Explore the feasibility of accepting East Timorese students into our programmes, as the clinical experience in PNG would be appropriate to their eventual practice.

- Negotiate with regional health authorities for an appropriate share of residency training to be undertaken in the graduates’ country of origin (Cost of RMO salaries for 4 years a limiting factor in intake of medical students).

The additional clinical schools will also allow an increased intake of PNG students into the MB BS, an essential step if national manpower shortfalls are to be addressed.  The Schools would also be able to take on increasingly important roles in other health professional disciplines and in postgraduate training.

Excellence in teaching and learning for all health professional disciplines

- Ensure each professional group (Course) has at least one teaching and/or assessment workshop each year.  These may be organised through UPNG (good value but inevitably generic [e.g. lecturing skills]) or the Medical Education Unit (e.g. assessment of clinical skills, small-group tutoring, informatics).

- Promote research into educational initiatives and ensure funding is available for two academics each year to attend an international meeting with an educational emphasis (e.g. ANZAME or a discipline-based meeting with an education component).  Funding should be competitive, with a requirement that a paper will be presented.

- Facilitate continuing education of staff in skills which will enhance both their teaching capacity and their ongoing research endeavours, e.g. information technology, search techniques, evidence based practice.

- Discipline of Medical Education to work with other disciplines to ensure all written assessments are criterion-based, that clinical (practice) assessments have good face validity and reliability, that results are subject to appropriate analysis and review, and that remedial activities are in place.

Postgraduate training

- M Med – Review the part 1 MMed to achieve a more consistent and interactive programme, with basic training in research skills and increased utilisation of distance learning materials.  Complete design and resource planning for the MMed Rural Health.  Increase ability to offer new, flexible training programmes, particularly combined basic and clinical sciences.

- Public Health – Develop combined, in-country public health and clinical training e.g. MPH with Postgraduate Diploma in Medicine (HIV medicine, diabetes).  Access international public health programs available in distance-learning mode; with support for course fees, travel.

- Medical Science – The MMedSci is an established pathway for Bachelor’s of Medical Laboratory Science graduates.  To attract clinical graduates into basic sciences, we need to support combined MMedSci training with a Postgraduate Diploma in Medicine (e.g. infectious disease, toxicology) or Surgery.

- Nursing – Establishing an in-country Master’s degree will be deferred until the basic Bachelor degrees are fully secured.  Postgraduate Diplomas in special areas are envisaged.

- Dentistry – The Master of Dental Sciences has been established, with candidates enrolled in 2008.

- Pharmacy – Two Bachelor of Pharmacy graduates have completed a MMedSci in Pharmacology; a Master’s degree in Pharmacy is being established.

- Medical Imaging – Development of postgraduate training options awaits the appointment of a medically qualified academic and a review of the current undergraduate course.

The School also has provision for MD and PhD degrees.  There are now two MD graduates.

Research

- To build on the current interactions between IMR and SMHS

- To actively seek involvement in international research initiatives which have the potential to contribute to in-country training and resource development.

- To increase the level of research training for all postgraduate disciplines

Enabling goals

- Further development of the Medical Education Unit to enable an increased contribution to all undergraduate courses, delivery of staff workshops, review of postgraduate courses and development of a system of continuing education for all Health Professionals.  Additional support staff and a further academic will be required.  The possibility of incorporating the current Medical Learning Resources Unit will be considered.  The Unit will be renamed the Health Professional Education Unit.

- The Medical Library has fulfilled an enhanced role in the last 5 years and staff members take responsibility for the informatics curriculum and a number of Domain 4 assessments (MB BS).  Basic infrastructure and services need to be further improved.  Provision of reliable Internet access is a priority.

- Provision of on-campus staff accommodation is a matter of urgency as the issue is impacting severely on staff efficiency and well-being, and is limiting staff recruitment.

- Student accommodation is currently at capacity; there is a need for a new accommodation block if there is to be any increase in student numbers.

Long term aspirations

- Infrastructure – Expansion of tutorial and seminar rooms, provision of clinical skills laboratories, permanent installation of multimedia facilities.

- Increased primary care training – For the MB BS, this would require an extension of the course to 5 years, with students spending 12 weeks in a regional hospital, 12 weeks in urban and rural primary care and 12 weeks in a health facility close to their own village.  A change of this magnitude is not within the power of the School; however, it would represent an entirely appropriate investment for a country with many isolated communities and major health care access challenges.  The model would be developed to include Nursing and Dentistry.

- Establishing continuing professional development programmes by distance learning for all health professionals.

Annex VIII –

PNG HWETSS PROGRAM – Indicative Budget (AUD) and Resource Schedule, July 2008 to December 2012

| Outcome(s) and Description |  | Resource | Transition (6-9m) | Implementation |  | MTR | Consolidation (indicative) |  | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Year 1 | Year 2 |  | Year 3 | Year 4 |  |
| 1-5 | Organisational strengthening of core SMHS functions | Accountable cash grants to SMHS via Business Mgmt Unit | 382,500 | 1,440,000 | 1,575,000 | Opportunity for re-programming, re-balancing budget or extending Consolidation Phase beyond Year 4 | 1,440,000 | 1,350,000 | 6,187,500 |
| 1 | Business Unit Established | Balance between activities to be determined through initial (Transition Phase) and annual planning processes |  |  |  |  | Balance between activities to be determined through annual planning process |  |  |
| 2 | Academic staffing, institutional partnerships and research capacity |  |  |  |  |  |  |  |  |
| 3 | Curriculum review and implementation |  |  |  |  |  |  |  |  |
| 4 | Accommodation and facilities at other campuses |  |  |  |  |  |  |  |  |
| 5 | Increased number of medical and other graduates |  |  |  |  |  |  |  |  |
| SMHS specific management costs (maximum 10%) for coordination, M&E and report-writing |  | Additional SMHS staff with relevant skills | 42,500 | 160,000 | 175,000 |  | 160,000 | 150,000 | 687,500 |
| Total for Core SMHS Strengthening |  |  | 425,000 | 1,600,000 | 1,750,000 |  | 1,600,000 | 1,500,000 | 6,875,000 |
| 6 | Specialised clinical services and related postgraduate training activities (including international placements) | Accountable cash grants to SMHS via Business Mgmt Unit, direct to RACS, etc | 416,500 | 833,000 | 833,000 |  | 833,000 | 833,000 | 3,748,500 |
|  |  |  | Balance between in-PNG and direct Australia-based funding to be determined through initial (Transition Phase) and annual planning processes |  |  |  | Balance between in-PNG and Australia-based funding determined through annual planning processes |  |  |
| SMHS specific management costs (maximum 2%) for coordination, M&E and report-writing |  | Additional SMHS staff with relevant skills | 8,500 | 17,000 | 17,000 |  | 17,000 | 17,000 | 76,500 |
| Total for Specialised Services and Postgraduate Training |  |  | 425,000 | 850,000 | 850,000 |  | 850,000 | 850,000 | 3,825,000 |
| M&E | Audits and technical reviews | Health Resource Centre; Period Offers | 40,000 | 40,000 | 40,000 |  | 40,000 | 40,000 | 200,000 |
| M&E | Mid-Term Review |  | ― | ― | 100,000 |  | ― | ― | 100,000 |
| Total for Program, including M&E costs |  |  | 890,000 | 2,490,000 | 2,740,000 |  | 2,490,000 | 2,390,000 | 11,000,000 |

Annex IX –

PNG HWETSS PROGRAM – Risk Management Matrix

| Source of Risk | Risk | Impact of Risk on Program and Sector | L | C | R | Risk Mitigation Strategy | Responsibility |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Risks related to the Health Sector Policy Environment | HRH Summit (July 2008) does not result in a comprehensive national HRH Plan | Numbers, role definitions and “train-maintain-retain” strategies not in place; health training institutions unable to project future student intakes, continue to “supply” HCWs independently of “demand | 3 | 3 | H | Motivate and lobby both NDOH HR Branch and WHO PNG HRH Focal Point to follow through on Summit. Engage additional technical support through CBSC as necessary | SMHS Executive, WHO, NDOH; engagement of DNPM, AusAID PNG Health Team and/or CBSC as necessary |
|  | NDOH, PHAs and Hospitals do not (or are unable to) make budgetary provision to engage sufficient numbers of staff to meet the requirements of the national HRH Plan | Health professionals trained though local institutions seek alternative employment in PNG or find employment internationally (either in the Pacific or further afield) – and are lost to PNG | 3 | 4 | H | Ensure Treasury, DNPM, PHAs and other higher level stakeholders remain involved in Health Summit and outcomes | SMHS Executive, WHO, NDOH; engagement of AusAID PNG Health Team as necessary |
|  | NDOH reforms do not proceed due “reform fatigue” in central agencies | NDOH restructure falls behind schedule, constraining the new Minister’s and Secretary’s ability to implement large-scale changes in support of better service delivery | 3 | 4 | H | Program to follow and respond to priorities of national HRH Plan; monitor reversion to donor funded “project” form of aid | Business Unit, AusAID PNG (Counsellor, in consultation with Minister Counsellor) |
|  | Diversion of Department of Education and NDOH resources to DWU or other training institutions | UPNG SMHS becomes fully dependent on donor and contractual (consultancy) funding, weakening ability to maintain present reforms and limiting sustainability of Program support | 2 | 3 | M | Program to follow and respond to priorities of national HRH Plan | SMHS Executive, Business Unit, curriculum development office |
|  | Refusal of PNG Medical Board or Nursing Council or other Pacific registration bodies to accredit revised curricula | Graduates from revised curricula unable to secure post-internship employment; may seek other career paths or employment overseas | 1 | 3 | M | Involvement of relevant registration bodies in all curriculum review processes | Dean, academic staff; assistance and advice from WHO PNG (HRH focal point) |
| Financing and Financial Risks | Office of Higher Education or UPNG is unwilling to accept a bilateral funding model for the SMHS, resulting in AusAID funds being managed directly through the SMHS | Potential weakening of within-UPNG relationships, including that with the School of Business Management; potential withdrawal of Education Department funding | 1 | 2 | L | Early consultations, negotiation and MOU between Secretary for Health, Vice-Chancellor of UPNG / SMHS Dean and the Office of Higher Education | Dean, Vice-Chancellor, supported and monitored by AusAID PNG Health Team |
|  | SMHS systems are overwhelmed by Program inputs | SMHS unable to move ahead with recruitment, curriculum review and development of additional campuses within the duration of the Program. Funds unexpended at end-of-Program; AusAID reluctant to maintain current level of funding | 2 | 3 | M | Correct phasing of inputs as per design, ensuring Business Unit, Strategic Plan and implementation plans firmly in place; avoid attempting unplanned ad hoc expansion of School’s activities | Business Unit Manager, Dean, Division Heads |
|  | Negative impact of exchange rate fluctuations on Program budget | Loss of competitiveness of SMHS salaries for academic staff; cost of placements outside Australia increases (but cost of assistance sourced from Australia unchanged) | 3 | 2 | M | Maintain separate AUD budget for RACS inputs (and potentially other Australia-based partners). Explore possibility of AusAID or other donor top-up if AUD falls | Business Unit; AusAID PNG Health Team |
|  | PNG Health and Education budgets fall, or are inadequate to maintain counterpart contributions | Loss of longer term sustainability of Program achievements due to increased donor dependence | 1 | 3 | M | Careful monitoring by AusAID and SMHS, with early consultation with Treasury | AusAID, NDOH, Dean |
|  | Size of Australian aid program and budget contracts during the term of the Program | Paring of Program budget, with possible loss of staff positions, reduced ability to undertake activities | 1 | 4 | H | Monitor during MTR. School to maintain dialogue and comply promptly with reporting schedule | MTR, Business Unit Manager |
| Risks related to Counterpart Capacity for Program Implementation | The SMHS is unable to identify recruit a suitable Manager for the Business Unit | Delays in commencing Transition Phase, with significant stress to current THS Project activities | 2 | 3 | M | Early, active engagement with School of Business Management | Deans and Executives of SMHS and Business School |
|  | A suitable Business Manager is recruited, but appropriate mentoring and support is not available from within the School of Business Management | Business Unit Manager may be working in isolation, or may need to expend Program resources on unanticipated external technical assistance | 1 | 3 | M | Maintain option of seeking external mentoring and support for Business Manager, e.g. through visiting auditors and technical advisers | Dean, with monitoring and support from AusAID PNG Health Team |
|  | Loss of key individuals due to retirement, illness or emigration, and failure to attract good academic staff | Loss of leadership within SMHS, resulting in less strategic guidance for Business Manager and Unit; need to extend recruitment campaign for new staff beyond Implementation Phase | 2 | 3 | M | Early, aggressive, adequately resourced recruitment campaign to fill unfilled vacancies on Faculty staff. Development of succession strategy during Transition | Dean and Senior Academic Staff; Business Unit Manager |
|  | Poor coordination with NDOH | SMHS intakes may drift out of alignment with HRH Strategy; coordination of clinical services support may continue in isolation | 2 | 2 | L | NDOH to be represented on PAG (as Chair); Dean to present annual Program report to Board of Health | Deputy Secretary (National Health Service Standards); SMHS Dean |
|  | Poor coordination with other international programs of assistance | Parallel implementation of similar activities by UPNG SMHS and other health training institutions, with reduced alignment with HRH Strategy and potential for gaps and overlaps in health workforce. Artificial Competition for NDOH and Department of Education funds created. Content of ad hoc training not integrated into curricula. | 2 | 2 | L | Encourage all international partners to channel support for SMHS through business Unit, not through stand-alone projects. Strengthen coordination and collaboration with DWU and other health training institutions | Dean, SMHS Business Unit |
|  | SMHS and the Program unable (or slow) to identify suitable candidates for overseas specialist medical and nursing placements, or early withdrawal of candidates from training | Pace of postgraduate training falls behind projected needs of HRH Plan. Patients suffer due to fall in treatment quality. | 1 | 3 | M | Overseas placements funded by Program limited to 3-12 months’ duration. Program to ensure adequate pastoral care and communications available to trainees | SMHS Business Unit, international partners and host organisations |
|  | Non-availability of consumables or equipment, especially to support visiting teams and specialists | Effectiveness of visiting teams and individuals and outreach visits to regional and provincial centres is reduced; visits may not be able to proceed | 3 | 2 | M | Proactive and early monitoring of the equipment and consumable needs for visiting teams and individuals. The program also represents a maturation of approach away from procedural visits that are more infrastructure-dependent | SMHS Business Unit, NDOH, international partners and Provincial Hospitals, Health Offices or Authorities |
|  | Disruption of normal hospital routine, especially by visiting teams | Non-training activities unable to proceed, so routine service provision suffers during team visits | 3 | 1 | L | Maintain MSSP and THS coordination functions in Business Unit | Current MSSP/THS team (on absorption into Business Unit |
| External Risks | Unanticipated withdrawal at short notice of Departmental budget or other international programs of assistance | Program and SMHS become dependent on AusAID funding, again compromising the sustainability of activities under Strategic Plan | 2 | 4 | H | Business Unit to develop scalable budget and implementations plan, and to explore opportunities for consultancy income | Business Unit Manager, Dean |
|  | AusAID country office may not have the capacity to function as activity manager | Lack of strategic and policy guidance to Business Unit from donor’s perspective; Program activities may deviate from Program design without adequate consultation among all partners. Scheduled reviews and technical assistance deferred. Program may continue in spite of sub-optimal performance | 2 | 3 | M | AusAID to maintain continuity of Health Team staff, especially during Transition and early Implementation Phases. PNG Health Team to make use of available resources in budget to secure necessary financial and technical assistance | AusAID PNG Health Team Manager |
|  | Emergence of epidemic or pandemic | School functions shut down due to need for trainees to become involved in response. International staff and technical partners unable or unwilling to travel to or stay in PNG. Diversion of NDOH, SMHS and donor resources to crisis | 1 | 5 | H | School to develop preparedness plan for pandemic influenza and other catastrophes. PAG and MTR should monitor and analyse global environment, and advise on necessary modifications | SMHS PAG, MTR team |

Ranking and Analysis of Risk Levels

| L = Likelihood 5 (Almost certain) – expected to occur in most circumstances 4 (Likely) – will probably occur in most circumstances 3 (Possible) – might occur at some time 2 (Unlikely) – could occur at some time 1 (Rare) – may occur only in exceptional circumstances | C = Consequences 5 (Severe) – would stop achievement of functional goals and objectives 4 (Major) – would threaten goals and objectives; requires close management 3 (Moderate) – would necessitate significant adjustment to the overall function 2 (Minor) – would threaten an element of the function 1 (Negligible) – routine procedures sufficient to deal with the consequences |
| --- | --- |
| R = Risk level Extreme (E) risk – most likely to occur and prevent achievement of objectives, causing unacceptable cost overruns or schedule slippage. High (H) risk – could substantially delay the activity schedule or significantly affect technical performance or costs, and requires a plan to handle. Medium (M) risk – requires identification and control of all contributing factors by monitoring conditions and reassessment at activity milestones. Low (L) risk – normal control and monitoring measures sufficient |  |

Annex X –

Development Partner Support to Health Training

(AusAID advised the officinal design team that it would supply this table)

Annex XI –

Assessment of Quality at Entry
Support to Medical and Health Professional Training and 
Specialised Clinical Services in Papua New Guinea

(AusAID to insert final comments / ratings / minutes of
 Peer Review meeting as required )

Strategic Plan for School of Medicine and Health Sciences (draft of October 2007).

Page 8, Medical Manpower, Submission to Senior Executive Management NDOH.  Curative Health Services Branch, 7 May 2007.

Ibid.

Page 7, Medical Manpower, Submission to Senior Executive Management NDOH.  Curative Health Services Branch, 7 May 2007.

Note regarding terminology: the term ‘transition’ is sometimes applied to the current extension of funding to RACS to maintain THS Project inputs while the present design is being developed – we regard that funding as simply for an Extension Phase for current THS activities.  Our use of the term Transition refers to the establishment of the Business Unit at the SMHS, finalisation of the Strategic Plan and related functions, and the migration of projection, coordination and management functions for specialised training and services from Australia-based (i.e. at the RACS International Project Management Unit) to within-PNG (i.e. at the SMHS Business Management Unit), as proposed in this design document.

An Agreement is an arrangement between AusAID and a partner to pursue a particular course of action.   Agreement is a broad term that covers a wide variety of arrangements.   Some Agreements are contractual and therefore legally enforceable; some are non-contractual, representing understandings or intentions that are not legally enforceable.   Some Agreements result in a financial commitment between AusAID and a payee to pay for goods or services and some do not.

Based on seroprevalence among antenatal clinic attendees (Health Sector Independent Monitoring Group draft report, 2008; M Douglas, personal communication).

See, for example: Watters and Thiele (Aust NZ J Surg, 2000); Watters, Kapitgau, Kaminel et al (Aust NZ J Surg, 2001); and Watters and Scott (Med J Aust, 2004).

Strategic Plan for Supporting Public Sector Reform in Papua New Guinea 2003-2007.  http://www.publicsectorreform.gov.pg/Strategic%20Plan%20English%20Web%20Version%20V04.mht, accessed 23 October 2007.

Ibid.

Introduction, National Health Plan 2001-2010.  Papua New Guinea National Department of Health, 2000.

Independent Review and Monitoring Group, PNG Health Sector Improvement Programme - Aide-Memoire October 2007.

“Training the types of health workers (like nurse practitioners and non-physician practitioners) that are most suitable for country needs, increasing the capacity of existing training institutions or setting up new ones (such as the Divine Word University in Papua New Guinea) and strengthening the continuing education of health workers through flexible/open learning were some of the steps being taken by Pacific Island Countries to increase the number of health workers.  The Pacific Open Learning Health Network has an important role in the continuing education of workers.  Kiribati and Solomon Islands have signed agreements with Cuba for the recruitment of Cuban doctors to serve in their national health services and the training of their doctors in Cuba.”  Page 12, Meeting of Ministers of Health for the Pacific Island Countries Port Vila, Vanuatu 12-15 March 2007.  World Health Organization, Regional Office for the Western Pacific Region, 13 August 2007

Summary of Expenditure by Program Structure, Department of Health.  Papua New Guinea Treasury, 2007 National Budget.

National Inventory of Health Facilities 2000

Church Health Services  Salary Budget 2008.

Page 64, National Health Plan 2001-2010.  Papua New Guinea National Department of Health, 2000.

Page 3, Medical Manpower, Submission to Senior Executive Management NDOH.  Curative Health Services Branch, 7 May 2007.

Master of Medicine (Rural Health). UPNG SMHS, 2007. J. Vince, Dean of Postgraduate Studies

Ibid.

Bursar UPNG, email 23 October 2007.  Based on a graduate output of 42 to 58 annually from SMHS.

University of New South Wales – Faculty of Medicine, 2007 Fees Schedule.  https://my.unsw.edu.au/student/fees/Medicine2.html, accessed 29 October 2007.

UPNG SMHS paper identifying strategic issues and proposals.  Presented to AusAID and Design Team on 2 October 2007.

Table 36, Page 23, PNG Education Sector Affordability Studies, Paper 1 - Financing Elementary, Primary and Secondary Education.  AusAID, September 2003

The affiliated nursing colleges are: the Lutheran School of Nursing, Madang; the College of Allied Health Sciences, Madang; St Mary's School of Nursing, Vunapope; and St Barnabas' School of Nursing, Alotau.

While we would ideally like to include undergraduate nursing education, budget constraints necessitate starting in a more targeted way