| KASTOM GADEN |  |  |  |  |
| --- | --- | --- | --- | --- |
| STRENGTHENING FOOD SECURITY FOR RURAL LIVELIHOODS PROGRAM |  |  |  |  |
| LOGFRAME (final) 2011-2014 |  |  |  |  |
| NUMBER | PROGRAM DESCRIPTION | VERIFABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
|  | PROGRAM GOAL |  |  |  |
|  | Self reliance of rural people through sustainable agricultural development |  |  |  |
|  | PROGRAM LEVEL OBJECTIVE |  |  |  |
|  | To strengthen family food security and income generation through a livelihoods approach | Processing and distribution of information Increased market sales Recognition of KGA's relevance to national politics Donor recognition of KGA | KGA Board minutes Component reports Review mission reports Government plans and agreements KGA involvement in donor project design and implementation | Stability in external environment (socio-economic, political, infrastructure etc) Success of complementary government policies and programs |
|  | INTERMEDIATE OUTCOMES |  |  |  |
|  | Farmers have access to relevant technical services for food security and income generation Increased capacity of KGA and rural farmer organisations to deliver services to their membership | Realisation of the aims of individual components | Component reports M&E information Biennial Farmers conference report Review mission reports Baseline and final survey report | Farmers put into practice the technical information provided Membership of KGA remains a value add to farmers |

|  | COMPONENT 1 | VERIFABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
| 1 | Partner Capacity Building & Networking |  |  |  |
|  | COMPONENT OBJECTIVE |  |  |  |
|  | To improve the capacity of KGA partner organisations and networks to provide advice and information to rural households | Increased locally driven networks exchanging information, ideas and technologies improving livelihood of rural households | KGA records and reports. Review of M&E indicators PMN database | Other initiatives in the agricultural/rural development make a complementary contribution. Farmer test and adopt the measures advocated. |
| 1.1 | OUTPUT: |  |  |  |
|  | Decentralising of KGA extension program to PMN farmers organisations. | 15-20 prioritised agreements signed (10 in year one) By end of year 5 partners are providing services to 50% of PMN members across SI | Signed Partnership Agreements Partnership review reports Partnership activity reports Agreements Partnership review reports Partnership activity reports | The farmer schools are supported by donors and the training is used by the farming community Farmers’ organisations and networks able to absorb the skills required to build sustainable entities in order to assist the broader community |
|  | ACTIVITIES: |  |  |  |
| 1.1.1 | Review and improve partners selection criteria (design farmer field school criteria), including partner agreements, explore different level of support to partners and assessment of potential partners to participate in the partnership program. | Different levels & types partnership defined and implemented as appropriate | Review report, Assessment report. Activity reports |  |
| 1.1.2 | Coordinate partnership signing arrangements | 15 partners entered into partners arrangement 50% of PMN farmers from each of the target province access to partners services. | Partners agreement report. Partnership signed agreements, Confirmed list partners. | 5 partners able to continue to implement their program after the program completed. |
| 1.1.3 | Coordinate KGA and Partners quarterly and annual planning meeting | Partners and KGA activities approved according to AWP and budget and being implemented. | Quarterly and annual meeting report. Approved work plan and budgets. |  |
| 1.1.4 | Train Partners coordinator on annual report writing | 15 partners produced annual plan and report on a timely fashion. | Training reports Evaluation reports |  |
| 1.1.5 | Conduct governance training for partner board members. | Partners local governance improved. | Governance report Evaluation report. Participant lists on PMN database | Improved accountability and transparency of partner programs |
|  | OUTPUT: |  |  |  |
| 1.2 | Training of trainers program for partners trainers / staff well established. | A number of ToT workshops on training facilitation skills and farmer to farmer extension methodologies; Trained farmers have the facilitation skills to train effectively and are training farmers in areas defined by KGA rural livelihood surveys & by PMN Conferences. | ToT evaluations Farmer school workshop schedules Interviews with trainees Reports of Conferences Participant lists on PMN database | The farmer schools are supported by donors and the training is used by the farming community Farmers’ organisations and networks able to absorb the skills required to build sustainable entities in order to assist the broader community |
|  | ACTIVITIES: |  |  |  |
| 1.2.1 | Conduct training needs assessment (TNA) for partner staff and trainers. | Partners needs identified and addressed. Partners extension services improved Quality and quantity of services provided to local farmers by partner | Training needs assessment reports Partners staff annual review report. PMN / farmer evaluations of training provided |  |
| 1.2.3 | Development of partners training and learning manual (Pest and Disease and Community facilitation trainers manual) to be tested out as well as Climate awareness information will be tailored into partners training manuals. | Rural farmers access to new information and technologies. Households production increased | Distribution manuals, baseline survey reports, monitoring reports Training reports |  |
| 1.2.4 | Building capacity of master trainers on P&D on plant health clinic with selected partners including establishment of facilities. | Farmers knowledge of Pest and disease increased. Household production increased. Farmers able to carry out control measures to reduce pest and disease problems. | Training reports and evaluation report, activity reports. Participant lists on PMN database List of farmers access to information. Baseline survey reports. Field monitoring reports, farmers stories documented. | Trainers are available to attend courses to become master trainers |
| 1.2.5 | Capacity building support to master trainers to carry out farmer to farmer visits, market, garden visit , this is also including support of training kits to local trainers. |  | Training reports, evaluation and monitoring reports Participant lists on PMN database |  |
| 1.2.6 | Conduct planning and facilitation skill training to partners, trainers and trainees. Including team-building and skill training. | Organisation management skills/ practices improved. | Training reports Evaluation reports Partner performance review reports Participant lists on PMN database |  |
|  | OUTPUT: |  |  |  |
| 1.3 | KGA- Local Partner Organisations is well-established and operational. | A number of networks supported (e.g. local area PMN members around each of the partners, highlands and seed and planting material exchange – PMN National) relevant to the needs of farmers, meeting regularly to exchange ideas, materials & plan advocacy & facilitate member’s access to KGA, government (& other) services Increasing level of PMN services delivered through partners | Minutes of the meetings; plans; guidelines Membership records (PMN) –new members and subscriptions paid PMN Conference reports |  |
|  | ACTIVITIES: |  |  |  |
| 1.3.1 | Assist local partners to develop an effective organisational structure/ procedures and processes for the management of partner program services. | Local partners become locally registered organisation. | Activity reports Mid-term review reports Annual reports. |  |
| 1.3.2 | Provide small grant scheme for PMN program for lead farmer training of farmers and related activities. | Household income improved. Training models established. Farming practices shared and adopted by other farmers. | Approved applications Monitoring reports List of awarders Baseline survey report. Participant lists on PMN database |  |
| 1.3.3 | Provide mentoring support to partner staff to conduct monitoring and impact assessment of their program quarterly . | Lesson learned shared among farmers. Partners carrying out PMN household surveys in their area – evidence of adoption from surveys Information widely spread to other farmers. Farmers livelihoods improved. | Impact assessment reports Activity reports PMN household surveys . |  |
| 1.3.4 | Attachment program of partner trainers to VRTC college including FUI organic farming. | Lead trainers knowledge increased. Farmers access to new information and practices. Household production improved. | Attachment program reports, PMN baseline survey reports Impact assessment reports (uploaded to KGA info. System) |  |
| 1.3.5 | Carry out partner organisational capacity and performance assessment including partners, staff and local trainers/trainees. | Partners program delivery improved. Rural farmers have access to quality information and trainings. New PMN members around partner areas | Assessment report Monthly reports uploaded to KGA info system Baseline survey reports uploaded to KGA info system. |  |
|  | OUTPUT: |  |  |  |
| 1.4 | Farmer network through partners and national networking activities of PMN established. | A number of networks supported (e.g. local area PMN members around each of the partners, highlands and seed and planting material exchange – PMN National) relevant to the needs of farmers, meeting regularly to exchange ideas, materials & plan advocacy & facilitate member’s access to KGA, government (& other) services Increasing level of PMN services delivered through partners. Increasing level of PMN membership/annual subscription payment in areas serviced by partners. | Minutes of the meetings; plans; guidelines Membership records (PMN) –new members and subscriptions paid PMN Conference reports |  |
|  | ACTIVITIES: |  |  |  |
| 1.4.1 | Conduct diversity fairs and exchanges programs | Farmers access to new planting materials and seeds. Farmers adopted new practices and technologies gained from exchange visits. Farmers empowered by learning from other farmers. Local farming practices improved. | PMN survey reports. Distribution of planting materials and seeds. Exchange reports. Participant lists on PMN database |  |
| 1.4.2 | Conduct PMN annual provincial PMN Members meetings and bi-annual national farmers’ conference (November 2011 and October 2013). Development of provincial and national PMN network plans. | PMN members recommendations and plans are implemented by KGA and partners. Farmers issues are presented to relevant bodies. Farmers empowered by learning from other farmers. Increased rural programs. | Provincial PMN conference reports Bi-annual PMN national conference reports. Participant lists on PMN database Government reports. Media reports |  |
| 1.4.3 | Farmers (PMN members) share information, technologies, planting materials among network groups. | Farmers practices of sustainable agriculture increases. Household food production increased. | Information documented. Monitoring reports. PMN household survey reports. |  |
| 1.4.4 | Advocate on market infrastructure (roads) for rural farmers. | increased recognition of the need to improve market access infrastructure | Advocacy reports News upload in KGA website/ Local news papers and media reports |  |

|  | COMPONENT 2 | VERIFABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
|  | Food Crops and Organic Farming |  |  |  |
|  | COMPONENT OBJECTIVE |  |  |  |
|  | To strengthen sustainable organic food production by provision of elite germplasm and information on new appropriate technologies particularly for sustainable land management | Rural households targeted by providing them with access to a number of new technologies and improved planting materials through farmer schools and exchange networks | KGA records & reports Germplasm centre records & reports Observations at farmer schools & germplasm centres Participatory evaluation report | That there are complementary contributions from other programs Government targets infrastructure as a priority Environmental factors remain the same |
|  | OUTPUT: |  |  |  |
| 2.1 | Shared seeds & staple food crops, alternative cash crops, fruit and nut trees are available and distributed to farmers through PMN, partners and farmer germplasm centres network | A number of farmer schools, germplasm centre’s & exchange networks, conserving & distributing local & introduced varieties of vegetables & staple crops | 6-monthly reports Inspections of farmer schools Community germ plasm Centres | Farmers use the planting materials and information supplied People eat more local vegetables (rural & urban) Expenditures on imported foods decrease & there is increase in expenditure on local foods (HIES surveys) |
|  | ACTIVITIES: |  |  |  |
| 2.1.1 | Collection and bulking of planting materials (root crop, vegetable, fruit and nut trees and alternative cash crops in collaboration with PMN farmers. | Collection & Bulking of crops: - Sweet potato - Cassava - Kakake - Wild yams & Pana African yam - Fruit & Nut trees - Vegetables - Banana - Kava - Black pepper | PMN Collection (plant passport and accession details) and bulking records & maps Number of varieties available Quality of planting materials distributed (germination rates for seed, storage periods etc) | There are enough planting materials for distribution to partners & farmers. |
| 2.1.2 | Distribution of planting materials (crop root, vegetable seeds, fruit and nut trees) to farmers, partners & germ plasm centre. | Distribution of the 7 different crops to 10 partners, 5 germplasm centres and 3,000 farmers done in - Markets - Friends - Lead farmers - Other existing networks | PMN Distribution records. Monthly reports. Follow up reports. Usefulness of new varieties to farmers Evidence farmers are saving or maintaining varieties and sharing with other farmers | Farmers have diversity of crops and varieties of crops in their gardens. |
| 2.1.3 | Develop farmer run germplasm centres | 10 partners, 5 germ plasm centers. | Copy of agreements Monthly reports from GP centres Lists of collections maintained by germplasm centres | Planting materials were distributed to more farmers and well kept. |
| 2.1.4 | Establish management system or guidelines for growing, distribution and monitoring of the crops for germplasm centres (including partners) | Distribution forms for seeds, root crop, fruit trees, spices and other collection, growing and monitoring and Evaluation. Conservation strategy for each of the key crops | From s / records of distributions, growing and monitoring reports Plant passport data for all collections is in PMN database | Farmers able to give feedback reports on activities implemented. |
| 2.1.5 | Research other possible spices and root crops for isolated areas eg weather coasts | 3 different root crops import from SPC and looking for 2 -3 different spices. | Import permit Records of crops | Farmers from Isolated areas involve more in farming spices & root crop. |
| 2.1.6 | Established trials plots with partners of the SPC sweet potato varieties. | 11 trial plots established with 10 partners and central link Gene bank. | Maps of the plots Pictures of the trial plots Yield records Activity report | Farmer access to the best and most suitable varieties of sweet potato. |
| 2.1.7 | Evaluation of the SPC sweet potato varieties. | Evaluations of the SPC varieties. With 10 partners | Evaluation reports | The farmers adopted more SPC varieties. |
| 2.1.8 | Establish promotional stall at the central market (awareness and promotion of KGA activities. | 4 times in a year | Promotional market report KGA Website posting | More people join PMN through suggest program. |
| 2.1.9 | Partners to establish promotional stall at the market during diversity shows (awareness and promotion of KGA activities), exchange advice, varieties etc | 10 diversity shows in 5 provinces 2 in each province. Malaita – Auki Western – Gizo Makira – Kirakira Choiseul – Taro Guadalacanal – Central Market | Activity report Participants lists on PMN database Record of planting materials shared and distributed Pictures of the show | More people join PMN and more farmers aware of the important of food security. |
| 2.1.10 | Liaise with MAL for import permit for planting materials from SPC | Agreements with MAL for port permits for KGA. | Minutes of meetings & contacts notes. Copy of agreements. | Strong relationship with MAL |
| 2.1.11 | Liaise with SPC and CIP to determine best way to pathogen-index best local sweet potato varieties | Plan for the virus clean up 5 varieties a year trial(s) of farmer crossing of best varieties using seed | List of varieties Resuts of seed crossing of farmers best sweet potato varieties | More varieties send for virus clean up. |
| 2.1.12 | Comparison of PT and Non PT varieties | 2 varieties of sweet potato on trials for comparison | Report on results /outcome of the comparison plots (yield) Pictures of the garden. | The PT varieties will do better compare to the non-PT one’s. |
| 2.1.13 | Contract lead farmer for involvement in seed saving activities - build skills to produce seeds for PMN. | 3 lead farmers from 3 provinces At least one train in a year. | Copy of contract Training report Picture of seed Garden Amount of seed produce Records of seed producers on PMN database | More seed produce for PMN distribution. |
| 2.1.14 | Identify list of dedicated expert PMN farmers to help in distributions monitoring of crop varieties and contracted. | Carry out monitoring at least 4 times a year in all provinces | Copy of reports Monitoring reports/ forms. | More information was gathered and shared. |
| 2.1.15 | Look and learn visit for OF staff to Vanuatu (see plant breeding program). | 1 visit for 1 staff | Visit report | Gain more & new technical knowledge on plant breeding and train the farmers. |
| 2.1.16 | Liaise with CIP, AVRDC, MAL, SPC & TC, AQIA | Continue work with CIP, AVRDC, MAL | Meetings of meetings Contact notes & numbers | Relationship getting strong with the other organization. |
| 2.1.17 | Deliver training on Pest and disease to PMN members | Training for 10 partner and farmers. | Training reports. Participant lists on PMN database | Farmer’s awareness about different pest and insect attacking crops. |
| 2.1.18 | Collect, preserve and identify most common and important pests and disease. | Samples of insects, pests are in the office for farmer to see. | Leaf lets of common pest & disease were printed and distributed to farmer. List of farmers received information. | Farmers able to identify different pests and diseases. |
| 2.1.19 | Training on Kava, Coffee and black pepper for Isolated farmers. | Training conducted (Makira & Gudalacanal & Kwaio) | Training report Participant lists on PMN database | More farmers have knowledge in farming cava & coffee. |
| 2.1.20 | Exchange program for isolated farmers for Cava & coffee farmers | Exchange program (Makira & Gudalacanal & Kwaio) | Activity report Participant lists on PMN database | Farmer gain skills and knowledge |
| 2.1.21 | Exchange programs for lead farmers. | Exchange visit occurred | Exchange visit report Participant lists on PMN database | Farmer gains skills and knowledge and put into practices what they learn. |
|  | OUTPUT: |  |  |  |
| 2.2 | Indigenous knowledge documented & shared | A number of local techniques collected by farmers, documented, tested & widely distributed using different media | Innovations on KGA website O Radio programs o Reports | That some of the information provided is useful and is taken up by farmers |
|  | ACTIVITIES: |  |  |  |
| 2.2.1 | Data system for seeds, root crop and fruit trees disseminated from KGA to partners and partner to individual farmers. | Continues uploading the distribution information’s in the system. | Information system | All distribution information are in the information system |
| 2.2.2 | Document and share successful stories, information on farmer experiences, innovations, resistant plants. | At least document 5 a quarter | Copy of the documented stories Stories posted on KGA website List & picture of farmer’s participant. | More stories collected and share with other farmers and farmer learn from the stories. |
| 2.2.3 | Identify & Database of lead farmers with different models gardens. | Number of PMN household surveys completed for initial selection of lead farmers. 10 lead farmers a year. | List of lead farmers with their different model gardens. Number of PMN members surveyed | The list increases year after year. |
| 2.2.4 | Organic farming training | Conducted to all partners at least 3 partner a year. | Training reports Participants lists on PMN database | More farmers practice organic farming methods. |
|  | OUTPUT: |  |  |  |
| 2.3 | Intensification of agricultural systems | A number of farmer demonstrations - use of legumes, conservation of organic materials, retention of soil loss, pest control, at farmers’ schools & lead farmers | Site visits to farmers’ schools (other partners) | That the methods are used by farmers |
|  | ACTIVITIES: |  |  |  |
| 2.3.1 | Distribute legume plants to farmers | Distribute Makuna beans, Gliricidias & other legume plants. | List of farmers Distribution records on PMN system Activity report | Increase in no of farmers used legume trees to improve soil. |
| 2.3.2 | Set up demonstration model gardens on different organic garden practices with lead farmers & partners. | At least 5 models a year | List of farmers and type of model garden Pictures of the garden. | More farmers practice organic farming methods. |
| 2.3.3 | TOT training for Organic master trainers. | 10 lead organic trainers | Activity reports Participant lists on PMN database | Lead farmers gain more skill and knowledge |
| 2.3.4 | Exchange program with farmers | At least 3 lead farmers a year | Activity report Participant lists on PMN database | Farmers gain more knowledge and improved their farming models. |
| 2.3.5 | Farmer to farmer attachments | 5 farmer each year | Participant lists on PMN database Activity report | Farmers able to learn and share skills, knowledge and planting materials. |
| 2.3.6 | Farmer research on impacts of legumes on the soil - small trials on most degraded land areas | At least 3 trials a year 10 reach trials for 3 years | List of trials Pictures of the trials Results of trials posted on KGA website and PMN newsletter | More farmers adopted the Technology. |
|  | OUTPUT: |  |  |  |
| 2.4 | Disaster/emergency awareness | Awareness through x number MAL & VBMS radio programs, newspaper articles, inclusion in curricula of farmer & Govt. schools on the need on increasing stocks of wild yam, log Taro (edu) breadfruit, kakake, Long term Bananas etc | Documentation: radio programs, articles, curricula | That farmers plant the crops required to assist in times of emergency |
|  | ACTIVITIES: |  |  |  |
| 2.4.1 | KGA to form partnership with Church of Melanesia Program working on atolls (led by PMN member Jasper Bonie) | Partnership agreement Sharing of planting materials, training resources and expertise with COM atoll program Assessment for Lord Howe atoll | Agreement and reports planting material distribution records | Activities continue with the PMN members. |
| 2.4.2 | Support germplasm centre for testing crop varieties adapted to low and high rainfall and to atolls | 3 germ plasm centers Number of varieties tested and distributed Number of PMN members benefitting | List of crops & varieties collected /bulked (PMN plant passport data) PMN distribution records | More crops for distribution to farmers. |
| 2.4.3 | Program development activity | At least 1 lead farmer to involved in seed production | Training reports | More seeds fro distribution to farmers |
| 2.4.4 | Seed production | Material needed was bought. | Materials brought | Improve in seed production |
| 2.4.5 | Collection and distribution of fruit tree seeds & wild food crops for Isolated farmers. | Targeting weather cost Makira, Guadalcanal & Kwaio Bush. | List of farmers received planting materials – on PMN database Activity report Collection and distribution records | Farmers have enough food for consumption. |
| 2.4.6 | Trial plots on salt tolerant varieties for atolls | 2 garden one on Russel Islands and one on St Catalina Island Makira | Evaluation reports | More farmers on the atolls received the 15 varieties. |

|  | COMPONENT 3 | VERIFABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
|  | Small Livestock |  |  |  |
|  | COMPONENT OBJECTIVE |  |  |  |
| 3 | To develop and disseminate technologies to improve low input management systems for pigs and poultry (chickens and ducks) | Rural smallholders producing & selling increased numbers of livestock using sustainable technologies. # Number of PMN members with more than 10 chickens increases by 20%; usage of housing for chickens increases by 20% Number of PMN members with problems with their livestock is reduced. | KGA reports & surveys of farmer schools & village producer KGA PMN member surveys. # Lists of participants on PMN database | Sufficient cash in rural areas to provide basis for livestock industry over the long term Increased numbers of pigs does not lead to increased damage of food gardens or disputes where stealing is widespread. |
|  | OUTPUT: |  |  |  |
| 3.1 | Viable farmer research and training centres for small livestock | Number of key partners and farmers being identified and established. Number of PMN livestock farmers being trained. Number of trials completed and results of those trials documented and shared Evidence of farmers putting new knowledge into practice. Sustainability of livestock centres as commercial enterprises | Site visits and follow up Evaluations of training Field monitoring and KGA reports, Research/trial reports % of PMN members who have access to small livestock farmer research and training centres # Trial results published on KGA website and in PMN newsletter # Lists of PMN members trained at centres | Results from trials translated into appropriate messages Farmers adopts the methods New technologies and marketing strategies widely adopted by rural households |
|  | ACTIVITIES: |  |  |  |
| 3.1.1 | Develop partnerships with three livestock models) to be lead training and research venues for PMN members. Assist them to become commercially viable enterprises. | Establishing of poultry and piggery models: - Improve Burns creek current poultry model with ZaiNaTina Organic Farm(poultry) - Gwaunafiu FFS(Pig /poultry) - Vanga RTC (Pig/Poultry) Each model has a business plan. Models are self financing by year 5. | Made a contract with each partner or lead farmer/s. Contract focus is on sustainable business operation of the model and training and research commitments. Financial reports linked to business plan targets Lists of people trained on PMN database Photos of models | Link with Poultry specialist Information shared and review the Burns Creek current poultry. Link with marketing component for business plan development and training in record keeping |
| 3.1.2 | Undertake research trials of relevance to low, medium and high care livestock farmers (at Burns creek, Guanafiu, Vanga and with other lead farmers in livestock network). | Undertake number of feed trials @burns creek, vanga, GFFS and other three lead farmers. Establish livestock research trials advisory committee to approve trial priorities including PMN members, MAL Livestock Division and SICHE. At least 3 trials completed per year. | Trial reports posted on KGA website and in PMN newsletter Advistory committee meeting minutes Lesson learned. Photos and reports of trials Evidence that results of trials lead to improvement for rural farmers | Resources to do the trials and network with lead farmers. |
| 3.1.3 | Farmer visits to PMN members identified with more intensive livestock systems or who are experiencing livestock problems. Visits are carried out by Livestock centre resource people where possible. Focus on women and Youth. | Number of farmers and youths will be benefit from visits. No of visits done by KGA staff and livestock centre resource people Farmers/youths will be identified based on criteria and using PMN database. % Farmers visited who adopt improved housing and management | List of farmers and youth visits Visitation reports./ PMN member surveys | More skills and knowledge being gathered. |
| 3.1.4 | Assist KGA partners to established livestock models (Capacity Building) | 2 key partners in livestock and 3 other partners get support. Identification will be based on performance of partners (no of PMN members reached, effectiveness of trainers and experience in livestock). And the overlap with Livestock research centres established. | Partners report on assistance Name of partners received support No Of PMN members and other farmers who receive training Follow up and evaluation of training – what is put into practice | Network of partners and components. |
| 3.1.5 | Review current piggery models @ Vanga RTC (Partner) | Improvements based on assessments for Vanga Piggery model. Business, training and research plan for Vanga Piggery model. | Review report produced. Plans produced. Based on challenges and lesson learned. | Improvements of learning models and farmers equipped with information. |
|  | OUTPUT: |  |  |  |
| 3.2 | A network of skilled livestock trainers with improved pig and poultry models (low, medium and high care examples) are accessible for local farmer to farmer training and demonstration. Strong focus on isolated areas where livestock is one of few cash earning options. | Number of farmers in each category (low, medium and high care and pig/poultry) who are identified as members of the livestock sub network of PMN Number of lead farmers (PMN members with existing pig and poultry units) trained to upgrade their skills. Review the criteria for selecting lead farmers integrating it with PMN database. Number of farmers trained in isolated areas. Number of models in isolated areas. | PMN members recorded as being part of livestock network. Publication and dissemination of relevant livestock information’s through the livestock network, PMN newsletter, KGA website and on Radio programs Local livestock knowledge and innovations documented in PMN newsletter and on KGA website. | New technologies and skills adopt from rural household. Farmers transfer skills and applied those skills to the rural people. |
|  | ACTIVITIES: |  |  |  |
| 3.2.1 | Identify Lead Livestock farmers (based on criteria and using results of PMN household surveys). | Number of lead farmers been identified, | List of key lead farmers identified and recorded on PMN database Activity report / household survey of the member | Farmers being improve. |
| 3.2.2 | Develop training course content and materials/ manuals / handouts for lead farmers | 5 handbooks and pamphlets developed and tested. For training purposes and documentation. | Types of training course developed. Activity report. Evaluations by participants | More information being gathered to developed. |
| 3.2.3 | Conduct lead farmer training courses - held at livestock model centre/s or lead farmer models. | No, of Lead farmers improve their skills and have shared their skills and knowledge with other farmers. Increase support to farmers and number of lead farmers access basic information. % of PMN members with livestock who are reached by training. | Participant lists on PMN database Training report. Evaluation by farmers List of lead farmers produced. | Farmers access and equipped with basic knowledge and skills. |
| 3.2.4 | Undertake follow up visits to the farmers trained at the lead farmer models and to other PMN members. | Visitation to farmers in the rural areas – by KGA staff and lead farmers. Evidence of changes to farmer practices with livestock | Follow up reports. List of farmers visited. PMN household surveys Participant lists on PMN database Success stories posted on KGA website | Information sharing for farmers during the visits. |
| 3.2.5 | Support lead farmers to conduct local area training of PMN members through 1 day workshops and field visits. | Improve the farmers in low external input management of their livestock. Number of farmers trained or exposed to models. | List of farmers and trainers Supported. Participant lists on PMN database Activity report. | Farmers improve and increase their production. Farmers shared basic information’s. |
| 3.2.6 | Facilitate exchange visits /look and learn. | Farmers improve their skills and knowledge by look and learn. Number of visits and look and learn. Number of visits organised by partners/ farmer research centres/ lead farmers / kga staff | Copy of farmers visited. Activity reports. Participant lists on PMN database | Farmers equipped with skills and learn from each other. |
|  | OUTPUT: |  |  |  |
| 3.3 | Distribution, sharing and conservation of different livestock breeds across farmer network | Number of farmers exchanging of different local and improved breeds of pig and Poultry between lead farmers. Livestock Diversity fairs held for lead farmers. Farmers received information’s on livestock. | Introduced and shared different local breeds of pig and poultry. Information being documents for new generations. | Farmers increase their production of pig and poultry and improve their income from their livestock. Farmers access to different breeds of livestock. |
|  | ACTIVITIES: |  |  |  |
| 3.3.1 | Hold livestock diversity fairs (2?) where farmers bring together and display local breeds of pigs and poultry. | Number of diversity fairs held. Number of participants. New knowledge and changes in attitudes to livestock breeds by participants Number of breeds documented (photos and stories) Plans developed at diversity fairs | PMN participant lists Activity reports Stories on KGA website and PMN newsletter |  |
| 3.3.2 | Distribute different breeds (of pigs and chickens suited to low input systems) from KGA and other livestock model to farmers, farmers to KGA, and farmers to farmers.. | Different breeds both local and commercials/cross bred breeds being distributed to farmers. Clear reasons for why breeds are being distributed. Increase number of breeds being distributed and shared among farmers (with a focus on youths.) | List and descriptions of different types of breeds distributed. List of farmers who receive breeds – entered on PMN database Distribution report. Stories of breed collection and sharing on KGA website and newsletter | Farmers increase their production for income generation. |
|  | OUTPUT: |  |  |  |
| 3.4 | Information available to PMN members and other farmers on improved management of pigs and poultry, including documentation of local farmer knowledge on livestock health and management | Print material produced and distributed to PMN members Number of local farmer livestock knowledge being documented in pig and poultry. Increase farmers interest and adoption of local knowledge Number of new technologies being developed. | Post the livestock relevant basic information on KGA websites. Share farmers’ information on other farmers’ documentation. | Farmers adopt new skills and learn from local innovation. Farmers record all innovations and reports produced to KGA. Farmers increase their knowledge/skills |
|  | ACTIVITIES: |  |  |  |
| 3.4.1 | Write manuals and fact sheets and reprint existing out of print livestock information manuals and distribute widely | No of handbooks and factsheets being printed and distributed for farmers over 3 years. | Types of factsheets, manuals and books being reprinted. | Information for farmers to improve their knowledge. Additional funding may be needed for manual printing |
| 3.4.2 | Collect, document and share local knowledge or innovations in livestock | No of local innovation or knowledge and skills being collected. Documentation of livestock information and distribute to farmers. Promising innovations that are tested as trials in livestock farmer research centres | List of farmers done collection of local innovation of information. Innovation on KGA website Activity report. Photo of different breeds. | The knowledge being shared and in used. |
| 3.4.3 | Document local and different varieties of pig, chicken and ducks | Increase and document the number of different breeds of pig, chicken and ducks. Develop conservation and sharing plan | List of different varieties, colours of livestock breeds on KGA website and newsletter. Documentation report. Photo of different breeds. | The types of breeds being divided and documented for reference. |
| 3.4.4 | Documentation of local foods, medicine for livestock health and nutrition | No, of documentation of foods and medicine for livestock were documented. Farmers Access basic information’s. | List of local foods and medicines for livestock being produced and available on website and as handouts Activity reports. | Information documented for future farmers. |
| 3.4.5 | Research other livestock opportunities e.g., fish, bees, and goats if appropriate. Network with international organizations to develop livestock focussed projects in animal health and pig feeding and management. | Search for information on other livestock Probably on bees and goats. | Report on research produced. List of proposed new livestock species. | To improve and engaed on other livestock for future programs. |
| 3.4.6 | Distribution of livestock information to partners & farmers focussed on information for low care, medium care and high care livestock models | Number of factsheets’, handbooks and other livestock relevant information disseminated across PMN farmers Information available on KGA website | Distribution list of farmers and information shared. Distribution report. | Farmers access basic information on livestock |
| 3.4.7 | Lessons learned on livestock are shared across the network | Number of stories /articles / radio programs produced % of PMN members reached by these sharing activities | Documentation – KGA website and PMN newsletter and other Distribution records | Information shared amongst the farmers(linkage) |

|  | COMPONENT 4 | VERIFABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
| 4 | Marketing and Value Adding |  |  |  |
|  | COMPONENT OBJECTIVE |  |  |  |
|  | To increase capability of village enterprises to process and market agricultural commodities for local and export sales | Increased number of rural households making and marketing (reduced impediments in value chain) products for local and export sales in increasing amounts & value Increase in % of rural incomes of women and men derived from self-employment No. of men, women and SMEs receiving and acting on improved information to improve livelihood choices | Interrogation of KGA data base, -PMN survey/survey of farmers directly involve in the project | Infrastructure does not worsen, Enterprises able to understand & improve the complex Interactions between production & sustainable sales Local enterprises adopt advice & techniques Consumers buy the products, (possibly) willing to pay more to support local enterprises |
|  | OUTPUT: |  |  |  |
| 4.1 | Value Chain established for priority products | Methodology completed and used in field by year 3 Visit to partners to test methodology Training material produced | Value chain reports Value chain maps produced Workshops, and reports Evaluation of training | Sufficient data available (i.e.enterprises willing to supply info) to make recommendations |
|  | ACTIVITIES: |  |  |  |
| 4.1.1 | Develop a methodology for mapping various commodity chains for priority products | Methodology is developed | Studies lead to actions to improve market access |  |
| 4.1.2 | Test the methodology, and review value chain mapping activities to identify gaps | Methodology is tested in field. Year 3, working in partnership with relevant other components | Value chain maps produced Workshop reports Evaluation report |  |
| 4.1.3 | Develop training modules, course materials, information | Training Modules developed and used in field | Modules is posted on the website |  |
| 4.1.4 | Engage a technical person in value chain and making markets work for the poor to build internal capacity in M4P /value chain programs | Consultant/ technical person is hired | PSO and partners trained in value chain in year 3 Partners and PSO producing marketing reports and solving problems affecting rural livelihoods |  |
|  | OUTPUT: |  |  |  |
| 4.2 | Market Advisory Service developed | Advisory services being accessed by members, donors and government | Project reports Advisory service information posted on website | Farmers are willing to form market groups Involvement of information component to produce and disseminate information/ materials produced to partners/farmers |
|  | ACTIVITIES: |  |  |  |
| 4.2.1 | Undertake Market survey to identify opportunities in priority product areas | Market survey is conducted in 3 locations | Market survey reports posted on internet Studies lead to actions to improve market access |  |
| 4.2.2 | Develop Value chain advice and training information and materials | Training materials developed | Training materials used in field and posted on the internet Copy of training materials | Internal skills developed within KGA |
| 4.2.3 | Develop information on agricultural policies and standards relevant to local farmers | Standards /policy developed | Copy of standards Farmers accept and use standard |  |
| 4.2.4 | Mapping of communication and infrastructure and providing advice to KGA partners about planned and existing infrastructure | Map is produced (year3) | Map Access deal negotiated with mobile phone operators for PMN members Activity report | Information available from infrastructure providers |
| 4.2.5 | Mapping the development activities of related organizations to enhance cooperation | Map is produced (year3) | Map |  |
| 4.2.6 | Develop corporate partnership strategy | Partnership strategy is develop year 3 | Numbers of farmer organizations becoming middleman or cooperative |  |
| 4.2.7 | KGA marketing and branding strategy: (promoting the KGA Market Advisory Service) | Strategy is developed And implemented | Increase in X number of farmers accessing KGA services, X number of donors or other development agencies who access the KGA network. (NB. Actual numbers to be determined in plan) |  |
| 4.2.8 | Develop appropriate business models for building farm based businesses that market processed foods, livestock, VCO and other products at a local, regional or national level | Business plan is developed for 3 partners | Numbers of farmer organizations becoming middleman or cooperative Number of farmers participating or farmers groups saling produces in villages or urban centres |  |
| 4.2.9 | Help farmers access credit | Number of farmers accessing credit | List of farmers | Farmer credit management system in place to ensure repayment |
| 4.2.10 | Extend successful model across the network |  |  | That there are successes and they are documented |
|  | OUTPUT: |  |  |  |
| 4.3 | Capacity Building for partners | Training material produced Training completed PSOs and partners produce marketing reports for their local areas and components | Reports posted on KGA information system/website, Workshops and training reports, Number of farmers trained |  |
|  | ACTIVITIES: |  |  |  |
| 4.3.1 | Develop business/marketing skills training materials | Training materials produced | Training materials produced and posted on website |  |
| 4.3.2 | Develop materials and information on improved post harvest production relevant to priority product markets | Materials are produced | Materials are produced and posted on website Information is shared with farmers 4.3.3Number of farmers accessing information |  |
| 4.3.3 | ToT for partners in basic Marketing/Management skills( business skills, financial management/bookkeeping, cost- benefit) | Training completed for partners 10 partners year 4 | PSOs and partners produce marketing reports for their local areas and components |  |
| 4.3.4 | Develop policies and standard on good management practices | Policies and standards developed | Number of farmers accessing and using information |  |
| 4.3.5 | Post harvest management capacity building (packing/handling, transport, materials, trainings) | Training completed | Training report Number of farmers practicing/ or have increased sales of produce due to improved skills in post harvest handling |  |
|  | OUTPUT: |  |  |  |
| 4.4 | Farmer Fresh | FF meets its customer and revenue projections, generating x amount of produce sales on monthly basis FF is a successful market linkage program for Honiara linked farmers | Number of customers Gross margin (weekly/monthly) Number and $ value of PMN members supplying produce (fresh and processed) | High quality produced can be supplied to KGA |
|  | ACTIVITIES: |  |  |  |
| 4.4.1 | Develop Business plan for farmer fresh across Honiara | Plan is produced Plan is implemented | Plan produced, posted on website |  |
| 4.4.2 | Strategic marketing of Farmer Fresh | FF meets its customer and revenue projections, generating x amount of produce sales on monthly basis | Number of customers Gross margin (weekly/monthly) | Demand for farmer fresh increases |
| 4.4.3 | Established network of Honiara PMN members connected to Farmer Fresh | FF is a successful market linkage program for Honiara linked farmers | Number and $ value of PMN members supplying produce (fresh and processed) |  |
|  | OUTPUT: |  |  |  |
| 4.5 | KGA Business Development Strategy including development of commercial activities | Plan produced and implemented Realistic income generating opportunities for organisation are identified with 5% of organisations funds coming from these sources by Year 5. | Plan adopted by board | Board member involvement in the business development strategy |
|  | ACTIVITIES: |  |  |  |
| 4.5.1 | Develop a business plan for KGA | Plan is produced year 3 | Plan adopted by board |  |
| 4.5.2 | Investment in business development activities, with involvement from the Board | Plan is implemented | Progress reports / new income sources for KGA as a % of total income |  |

|  | COMPONENT | VERIFABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
| 5 | Women and Nutritional Health |  |  |  |
|  | COMPONENT OBJECTIVE |  |  |  |
|  | To improve family health and nutrition among rural households through dissemination of information and skills by KGA partners, hospitals and clinics | A x % decrease in child malnutrition in bush villages over the project period | Site visits to clinics and Hospitals o Surveys of Child Health Records in selected villages o KGA M&E database o Visits to farmer schools & other selected CBOs | Appropriate government & NGO policies in place recognizing that bush villages are in need of special assistance |
|  | OUTPUT: |  |  |  |
| 5.1 | Sup -Sup Gardens established in hospitals and clinics | Sup Sup gardens established |  | Partner hospitals/clinics involved in the partnership |
|  | ACTIVITIES: |  |  |  |
| 5.1.1 | Establish 2 model gardens | 2 sup -sup gardens established at Atoifi / Sasamuqa hospital | Garden established and used Photos to the gardens. Hospital agreements. | Hospital use the garden to feed sick peoples |
| 5.1.2 | Out reach to clinics to do the same as hospitals. And to bush & isolated communities | Sup – sup gardens in clinic | Clinic records Garden established and used Photos to the gardens. Hospital agreements. | Increase in no of women adopted the sup-sup garden |
| 5.1.3 | Training of women trainers | ToT and follow training conducted by those trainers with 10 partners. -15 women trainers trained as trainers | Participants lists Training reports Hospital & clinic Records | More women have sup –sup gardens |
| 5.1.4 | Establish institutional arrangements with partner hospitals/clinics | Signed agreements | Signed agreements | Partner hospitals/clinics interested in partnership |
|  | OUTPUT: |  |  |  |
| 5.2 | Nutrition and health programs | Improved health and nutrition of women and children | Health statistics |  |
|  | ACTIVITIES: |  |  |  |
| 5.2.1 | Health & nutrition training (focussed on home food production) developed and delivered to KGA partners | 20 training in bushed communities | Training reports Participants lists | More women gain knowledge and aware of the nutrition problems. Villages grow more vegetables & Change their Child feeding Practices, especially those used for weaning |
| 5.2.2 | Develop linkages with other NGO 's & MOH, Church for activities through workshops and meetings and Joint plans to scale up growth monitoring | 2 hospital & 3 clinics establish nutrition & health training focused on home production. Promotion of green leafy & fruits for nutrition linked to PMN newsletters | Reports of health Programs & Workshops Newsletters and Distribution Website and other Media posts | More clinic adopted the program |
| 5.2.3 | 2 hospital & 3 clinics establish nutrition & health training focused on home production. |  |  |  |
| 5.2.4 | Training of partners and Promotional of orange fleshed sweet potato | Similar training conducted at all KGA partners farmer school workshop; (promotion of orange fleshed sweet potatoes and banana. | Training reports Participant’s lists. Newsletters and Distribution Website and other Media posts | More people aware and eat orange flesh crops. |
|  | OUTPUT: |  |  |  |
| 5.3 | IPDM training of trainers for women trainers | Women trainers providing IPDM training | Training reports Program reports | Women available and interested to become trainers |
|  | ACTIVITIES: |  |  |  |
| 5.3.1 | TOT training delivered to 15 women trainers | Training completed of core Group of 15 women IPDM for Food crops trainers | Training reports Participants list | Women able to identify insects & pest and share knowledge with other women’s |
| 5.3.2 | Follow up training and Evaluate changes in home food production | Follow up training conducted Changes in home food | Reports of training Participants list PMN surveys | More follow up training for women’s in isolated areas. |
|  | OUTPUT: |  |  |  |
| 5.4 | Gender capacity building and annual gender audits of KGA program | Gender disaggregated data collected | Gender audit reports | Gender disaggregated data collected in MIS |
|  | ACTIVITIES: |  |  |  |
| 5.4.1 | Gender monitoring and KGA gender policy | Implemented Develop gender M&E indicators, working with information team and develop gender policies for KGA | Copy of the policy | The policy was in place and used |
| 5.4.2 | Training in gender policy | Training in gender issues for Staff and partners Gender based M&E indicators | Gender policy Adopted by board Changes in gender Participation in the programs | More integration among both sex (M/F) Equal responsibility share |
| 5.4.3 | Undertake annual gender audit | Gender audit completed | Gender audit report |  |
|  | OUTPUT: |  |  |  |
| 5.5 | Model kitches and fuel efficient/reduced smoke stoves for rural households | Model kitchens established and kiko stoves adopted in the community Improved health statistics | Program reports Health records |  |
|  | ACTIVITIES: |  |  |  |
| 5.5.1 | Awareness rising on smoke pollution and kiko stove making | A number of farmer schools & CBOs testing and Demonstrating at least 3 Smokeless/reduced smoke and fuel efficient stoves | Farmers who adopt Smokeless stoves Internet, media and Radio stories and Posts about fuel efficient and Smokeless stoves | Increased awareness in Solomon Islands on the health Risks of indoor smoke pollution And the burden on women’s time for firewood collection |
| 5.5.2 | Models improved kitchen hygiene | Models of improved kitchen Hygiene (raised fires, raised And clean food preparation Areas) Develop model kitchens and trial improved smokeless stoves at farmer Schools & selected CBOs. | Households with Improved kitchen hygiene. | More women adopt the system. |
| 5.5.3 | Develop Model kitchens in isolated areas & bush villages. | Number of model kitchen established and working. | Model kitchen establishment Pictures of the model kitchens. | Increase in numbers of women adopt the system |
| 5.5.4 | Provide training on improved cooking techniques, sanitation and recipes. | Trial and distribute recipes for nutritious and tasty foods, and add lessons/demonstrations to all KGA food production/processing workshops. | Nutrition, health and cooking information and practical’s introduced to all farmer school and attachment programs. | Different receipts introduce to women and increase in balance diets. |
|  | OUTPUT: |  |  |  |
| 5.6 | Improved market access for women (see component 4 also) | Women’s incomes improved through improved marketing activities | Program reports | Small grants scheme funds utilised for increased market access |
|  | ACTIVITIES: |  |  |  |
| 5.6.1 | TOT for women farmers' organizations on marketing and roles of FO in improving value chains. | Training to 10 partners and farmers from isolated areas | Training report Participants list | Women gain knowledge in making skills and understand more in value chin |
| 5.6.2 | Small grants to women's groups for market linking activities and capacity building. | Number of small grants to women’s groups especially from isolated areas. | List of women involved Activity reports. | Build capacity of women groups to market. |

|  | COMPONENT | VERIFABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
|  | Youth in Agriculture and Urban Agriculture |  |  |  |
|  | COMPONENT OBJECTIVE |  |  |  |
|  | To strengthen the capacity of youth to improve family livelihoods | Incremental increase in the number of village projects implemented by youth, either alone or in collaboration with other members of the household | Visits to KGA partners KGA M&E database 6-monthly & annual plans Reports & surveys | Consumers with the cash available to buy increased production Infrastructure – roads, ships, communication ns sufficient to market produce to urban areas |
|  | OUTPUT: |  |  |  |
| 6.1 | Networking with other organization to implement youth in agriculture programs | Liking with MWYC, Save the children, SIARTC etc. | 6-monthly & annual plans List of organizations Minutes meetings | Strong link with other organizations. Link activities |
|  | ACTIVITIES: |  |  |  |
| 6.1.1 | One Youth group established as KGA partner | 1 youth group becomes a partner for KGA. | MOU for the partner Activity list | More youths involved in carry out the activities. |
| 6.1.2 | Farmer attachments programs - 100 youths attached to farmer programs per year | 300 youths attach 100 a year. | List of attachment students. Activity report. | Youths involved more in agriculture activities. |
| 6.1.3 | Develop youth trainer Network | A network start with 5 trainers | List of trainers | Youth trainers were used by KGA to facilitate trainings. |
| 6.1.4 | Youth trainers included in all TOT training courses | At least 5 top lead youths trainers. | Training report Participants list. | Youths gain skills and knowledge and train more youths. |
| 6.1.5 | Youth become PMN members (20 per year) | 20 youth join PMN per year | List of PMN member youths. | More youths join the PMN |
| 6.1.6 | Train young people from other organisations | At lest 5 youth train per year | List of organizations List of youths Training report | Youths will train other youths in their organization. |
|  | OUTPUT: |  |  |  |
| 6.2 | Organic farming courses for youth | 4 component courses’ outline | 6-monthly & annual plans Courses outline | More youth farmers learn practical skills and knowledge’s and put in practices. |
|  | ACTIVITIES: |  |  |  |
| 6.2.1 | Develop organic training Curriculum in partnership with Zai Na Tina Organic Farm | An organic training curriculum developed. | Copy of the curriculum | Used the curriculum for attachment students. |
| 6.2.2 | Training delivery | 4 trainings a years a total of 12 trainings. | Training report Participants list | More youths gain skills and knowledge’s. |
| 6.2.3 | Certification for the graduates. | 300 youths received completed their attachment and graduated with certificate. | Copies of certificates List of graduates. | Youth received certificated as based for continuation |
| 6.2.4 | Evaluation of the program. | 2 times Evaluation of the program 1 in year 3 and 1 in year 5. | Evaluation report | Improve the attachment program |
|  | OUTPUT: |  |  |  |
| 6.3 | Youth involvement in urban agriculture green waste & fresh produce | Youth Groups involved urban agriculture. | List of youths groups Activity report 6-monthly & annual plans | More youths involved and leading the development of this outcome |
|  | ACTIVITIES: |  |  |  |
| 6.3.1 | Develop on green waste recycling models (2) | 2 model s | No of tones of solid waste from market. Other records. | More youths involved in making compost and green waste. |
| 6.3.2 | Develop Youth waste recycling enterprise (2) | 2 enter prices youth groups as models. | Record of income & sales and other records. | Youths sustain their enterprise (youth-led) |
|  | OUTPUT: |  |  |  |
| 6.4 | Urban agriculture network | An agriculture network was developed. | List of farmers 6-monthly & annual plans | More farmers join the network |
|  | ACTIVITIES: |  |  |  |
| 6.4.1 | Establish Vegetable gardens in schools (3 per year) | At least 3 schools per year | List children’s involved in the vegetable garden. | More schools involved in vegetable production |
| 6.4.2 | Awareness raising on organic standards (at least 2 per year) | At least 2 per years | Activity report Participants list. | More youth farmers gain knowledge. |
| 6.4.3 | Plan urban agriculture activities using youth led initiatives | 3 youth led groups | Copy of plans | Increase in youth led |
| 6.4.4 | Build youth capacity to plan & manage Urban organic vegetable production | 3 youth groups | Copy of plans List of youths | Youths take led on urban agriculture. |
| 6.4.5 | Village training of youth in pig, poultry and vegetable and organic farming. Farming. | 20 training in all provinces. | Training reports Participant lists. | Increase Youths participants in farming activities. |

|  | COMPONENT 7 | VERIFABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
|  | Information Service Component |  |  |  |
|  | COMPONENT OBJECTIVE |  |  |  |
|  | To improve the quality of information collected and used by KGA & partners in the implementation of programs & components | An M&E database used to monitor and make adjustments to KGA’s program Suitable agricultural information services operating in selected areas & used to the satisfaction of farmers | Visits to KGA partners Interrogation of KGA M&E database 6-monthly & annual plans Reports & surveys | That the new information leads to gains in yields, quality, etc, & reduced labour input |
|  | OUTPUT: |  |  |  |
|  | Program information & learning system | M&E system established for project monitoring | M&E system | - That KGA use the M&E system Methods to make information available are robust & far reaching |
|  | ACTIVITIES: |  |  |  |
|  | KGA information system – Agriculture information services | Farmer information is accessible | Rural communities take advantage of the information provided |  |
|  | M & E system (8) | Monitoring & Evaluation framework/ systems established | Acceptable M& E system is implemented |  |
|  | Activity Management system | Activity management system | Regular updates made to system by all relevant staff Activity Tracking and monitoring mechanism followed usage of information from the system |  |
|  | Impact Assessment | Impact assessment systems (Year 3 - 5) | KGA impact assessment report | MSC- Good stories analysed |
|  | PMN household surveys | PMN household surveys (Year 2 onwards) reach 20% of members per year by Year 5. | Number of PMN members surveyed & analysed # Baseline survey report |  |
|  | Mid Team Review | Mid term review Year 3 | Mid-term review report |  |
|  | Annual report | Annual Report produced each year, 2011 – 2013 and beyond | Annual Report |  |
|  | OUTPUT: |  |  |  |
|  | Existing KGA information resources widely available | A number of libraries, training videos, WorldSpace systems, radio messages & newsletters with trained information brokers responding to information requests to clients’ satisfaction |  | Methods to make information available are robust & far reaching |
|  | ACTIVITIES: |  |  |  |
|  | Document partners 2 x years | Partner experiences are well documented | KGA reports | Profile updated and partners recognised |
|  | KGA materials available –library in Honiara and partners & schools | All previous KGA training manuals, technical studies and assessments, old newsletter fact sheets, are available: at partners, for members and for sale at KGA | Number of partner mini libraries of KGA publications | Good practices are adopted and practiced |
|  | Emails and internet access Websites – link to SPC websites program | All previous KGA training manuals, technical studies and assessments, old newsletter fact sheets, are available: at partners, for members and for sale at KGA, and for download on web KGA staff and partners have access to email and internet and understand how to use it effectively | Web site posts made reqularly Increasing % of Partners and staff with email and internet access | Website posts and usage statistics |
|  | Publications (year 3) (Video) | Develop plans and proposals for new publications including video (year 3). Implement (Year 3 onwards) | Distribution and sales of publications | Innovative & best practices recorded in a documentary film |
|  | Radio program | Develop and disseminate appropriate programs through the national broadcaster (SIBC) | Positive feed back and increased interaction between farmers & KGA staff/ programs | KGA media releases and stories |
|  | OUTPUT: |  |  |  |
|  | Research and develop materials to support advocacy programs | Develop plans and materials appropriate for carrying out advocacy in specific issues, to garner government, donor & other organisation support | KGA has a good reputation New policy & best practices adopted | Website posts and usage statistics KGA media releases and stories published Conferences and events where KGA makes presentations and papers |
|  | ACTIVITIES: |  |  |  |
|  | Attending meetings | KGA is well represented by the relevant people within organisation and partners at different types of meetings | Recognition of KGA’s role An effective partner in development issues | Conferences and events where KGA makes presentations and papers |
|  | Raise awareness of the Needs of farmers, government, and community tec. | The needs of rural farmers for food security are increasingly recognised by public, govt, donors and other organisations | Influence policy changes and increased collaboration with Government & stakeholders |  |

|  | COMPONENT 8 | VERIFABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- | --- |
|  | Project Management |  |  |  |
|  | COMPONENT OBJECTIVE |  |  |  |
|  | To effectively and efficiently implement program components on schedule & according to budget through support to management, monitoring and reporting of component project | A number of well implemented components as judged by independent program reviews There are signs that non target households are taking up recommendations | Visits to KGA partners Interrogation of KGA M&E Database 6-monthly & annual plans Minutes of KGA Board Reviews | That the outputs from the individual project remain relevant to the needs of rural households & integrate in an interconnected way |
|  | OUTPUT: |  |  |  |
|  | Organizational management system operational and delivering program objectives | Staff, partners and consultants hired and mobilised to produce quality outputs and utilise project resources effectively Outputs achieved | Project reports Annual review M&E reports | Systems are implemented consistently across the program/organisation |
|  | ACTIVITIES: |  |  |  |
|  | Establish and implement effective and appropriate management systems in the following areas: - Governance - Finance - Project - Annual work plan - Management system - Reporting - Regular meeting (monthly) - HR and performance management - Administration - Risk management | Systems established and providing adequate data and information for reporting and monitoring and evaluation Convene regular meetings (monthly, annual planning meetings, quarterly management meetings, staff reflection and staff retreat meetings) Development of annual plans and activities monitored against annual plans | Organisational audit reports Program reports and annual plans Performance management system information M&E information Board reports | Management ensures consistent application of systems |
|  | Review KGA Management and Operations Procedures | Operation manual reviewed and approved by the Board | Revised MOP Board meeting minutes |  |
|  | Establish consistent report templates across the organisation and with partners | Report templates developed and in use | Program reports | Staff use report templates and train partners on their use |
|  | Develop KGA disability policy | Disability ratified by the Board | Board meeting minutes | KGA disability policy is consistent with AusAID Disability policy |
|  | Develop revised organisational structure, roles and responsibilities and review terms of reference for all positions in light of revised program design | Organisation structure agreed and ratified by Board | Organisation chart Position descriptions |  |
|  | Hold Annual General Meetings | Meetings held and attended by quorum of members (September) | Meeting reports |  |
|  | OUTPUT: |  |  |  |
|  | Organisational Development | Staff capacity built to ensure quality implementation of components | Training reports M&E information Program reports and reviews | Management and Board fully support capacity building of staff and all staff make time and resources available |
|  | ACTIVITIES: |  |  |  |
|  | Undertake internal training needs analysis and develop strategic training plan. Training should include - Advocacy - Proposal writing - Budget development - Fundraising - Project management - Financial Management - Research capacity development - Market development | Staff are fully able to perform their functions to a high quality | Training reports Performance monitoring reports Program reports Board reports | Organisation and staff prioritise internal staff capacity development |
|  | OUTPUT: |  |  |  |
|  | Monitoring and evaluation system implemented and producing outcome and impact information | An M&E database designed, data collected on activities, outcomes and impacts and used, providing feedback on program outcomes against the logframe, allowing adjustments as necessary and organisational learning | M&E database Project reports Reviews | Indicators are manageable and based on information that can be gathered |
|  | ACTIVITIES: |  |  |  |
|  | Develop current activity monitoring database to include outcome and impact indicators | M&E database developed and in use | M&E database Project reports Reviews |  |
|  | Develop outcome and impact information to provide to Board, donors, government, members and the public, eg. Through website, proposals, marketing information, public information pieces | Information widely disseminated through a range of media to key stakeholders | Board reports Project reports Reviews Website Stakeholder engagement |  |
|  | Train staff and partners on M& E system | Training completed | Training reports Program reports |  |
|  | Collect stories / Most Significant Change information | Stories collected and disseminated | Board reports Project reports Reviews Website |  |
|  | Annual review (June 2013) | Annual review completed and recommendations acted upon | Annual review report Annual plans |  |
|  | Mid Term review (May/June 2012) | Mid term review completed and recommendations acted upon | Mid term review report Annual plans | External evaluator, AusAID and SIG involved in the review |
|  | Final Evaluation (May/June 2014) | Evaluation completed | Evaluation report | External evaluator, AusAID and SIG involved in the review |
|  | Regular analysis of households surveys to compare against baseline and to rank PMN members according to the numbers who have reached KGA targets. | PMN households surveys conducted on a regular basis, data analysis done and report available | Annual Survey report with recommendations | Survey information and methodology is comparable to baseline data survey |
|  | OUTPUT: |  |  |  |
|  | Advocacy strategy implemented | Changes in government and policy and donor support towards food security and sustainable agriculture | Government policies Donor reports Media pieces |  |
|  | ACTIVITIES: |  |  |  |
|  | Identify key advocacy priorities and develop research pieces to advocate using evidence grounded in the KGA program to key stakeholders | Advocacy reports and papers | Reports submitted to government |  |
|  | KGA representation at relevant meetings and forums | KGA represented at relevant meetings and forums | Meeting minutes Program reports |  |
|  | OUTPUT: |  |  |  |
|  | Organisational growth and improved diversification of funding | Increased funding for KGA from increasing numbers of donors Ongoing funds are sourced for core organisational support beyond 2015 KGA has adequate funds to carry out its work | Donor funding agreements KGA financial reports | Program development officer hired and active in the role Board involved in development and implementation of strategy |
|  | ACTIVITIES: |  |  |  |
|  | Develop diversification strategy in consultation with the Board. Areas to consider include: - Increase PMN members (and hence fees) - Provide training and advisory services (to farmers, partners, donors, NGOs, government) - Increase support from other donors (increase number of quality submissions) - Corporate partnerships (eg. Provide advice on sourcing produce from farmers) - Commercial activities (eg. Sale of seeds, chickens etc) - Research partnerships (with regional research institutes, donors, NGOs) - Further develop the partnership with Ministry of Agriculture to provide increased services. | Diversification priorities identified and plan of action implemented Financial return on investment analysis completed | Diversification strategy and justification Program development reports | Diversification strategy supported and implemented as high priority by Board and management |
|  | Submit increasing number of high quality proposals with donors | Increased funding for KGA from increasing numbers of donors Ongoing funds are sourced for core organisational support beyond 2015 | Donor funding agreements |  |
|  | Develop commercial activities as appropriate | Increased income from commercial activities | Financial reports | Board involvement in commercial activities |
|  | Increase PMN membership | Increased number of members Increased % who pay their annual subscription fees. | Program reports Financial reports | KGA remains relevant to members |