LANGOCA

Laos – Australia NGO Cooperation Agreement Program

Final

Program Design Document

Volume 1

13 December 2006

Table of Contents

Executive Summary	iii

Location Map	vi

Acronyms	vii

1.  Program Preparation Steps	1

1.1  Program Origin	1

1.2  Study Team and Method	1

2.  Situation Analysis	2

2.1  Policy and Program Context	3

2.2  Analysis of the Development Situation	3

2.3  Lessons Learned	4

2.4  Options Considered and Proposed Strategy	5

2.5  Rationale for the Program	7

3.  Program Description	8

3.1  Program Goal	8

3.2  Objectives and Component Description	9

4.  Management and Financing Arrangements	18

4.1  Planning and Management Mechanisms	18

4.2  Resources	20

4.3  Program and Activity Level Agreements	21

4.4  Contracting and Financing Arrangements	22

4.5  Role and Responsibility of Key Stakeholders	22

4.6  Program Performance and Monitoring and Evaluation	24

5.  Risk, Sustainability and Feasibility	27

5.1  Risk Management	27

5.2  Sustainability	28

5.3  Feasibility	28

Design Process TOR	30

Persons Consulted during Design	33

Timeline for LANGOCA Design Process and Start Up	34

Logical Framework Matrix	36

LANGOCA Activity Design, Appraisal Criteria and Reporting Proformas	40

A.  Activity Design Document Proforma	40

B.  ADD Appraisal Criteria	42

C.  Six Monthly Progress Report Proforma	43

D.  Annual Plan Proforma	44

E.  Activity Completion Report Proforma	45

Draft TOR for PCC, PIC, Secretariat, Technical Advisors and the Annual Program Assessment	46

A.  Draft TOR: Program Coordination Committee	46

B.  Draft TOR: Program Implementation Committee	47

C.  Draft TOR: LANGOCA Secretariat	48

D.  Generic TOR: Technical Advisors	49

E.  Draft TOR: Annual Program Assessment	50

Implementation Schedule	51

Risk Matrix	53

## Executive Summary

The LANGOCA Program addresses the Laos-Australia Development Cooperation Strategy’s (LADCS) Objective 3: to reduce the vulnerability of the poor; 3.1: to reduce the impact of natural disasters, and 3.2: to reduce the impact of UXO.  The LANGOCA Program is based on Cooperation Agreements with four Australian NGOs: Oxfam, CARE, World Vision and Save the Children Australia (SCA). It builds on the lessons learned from previous Cooperation Agreements by adopting a strategic approach which aims to maximise and promote the lessons learned more broadly, and thereby enhance the quality and impact of the individual activities across the disaster management and UXO sectors.

The rationale for the Program is based on the recommendations of the LANGOCA Analytical Mission (undertaken in May 2006). The Analytical Mission found that the vulnerability of the poor in Laos is most effectively reduced by integrating poverty reduction and crosscutting issues with disaster management and UXO approaches. Furthermore, an effective approach must address coordination, capacity building, implementation and policy dialogue across both the disaster management and UXO sectors. The LANGOCA Program capitalises on the experience of LANGOCA NGOs and includes strategies for assisting the Program to maximise coordination, capacity building, best practice from community based activities, and policy dialogue, across all levels: national, provincial, district and community. The strategies include a close working relationship with key GoL partners, in particular, the National Disaster Management Office (NDMO) and National Regulatory Authority (NRA).

The LANGOCA goal, components and component objectives are summarised in Figure 1.

Program Goal

To reduce the vulnerability of the poor by integrating poverty reduction and crosscutting issues with disaster management and UXO approaches in Laos

Component 1

Disaster Management

Objective: To reduce the impact of natural and man-made disasters.

Component 2

Unexploded Ordnance

Objective: To reduce the impact of unexploded ordnance.

Component 3

Program Development

Objective: To build and promote Program capacity.

Component 4

Program Management

Objective: To manage the Program effectively.

Figure 1: LANGOCA Goal, Components and Component Objectives

A Summary Program Logframe is presented as Figure 2, indicating the outputs within each Component and the initial activities included in each of Components 1, 2 and 3. The initial portfolio of activities is to be implemented in poor districts of the following provinces: Saravan, Sekong, Vientiane, Sayaboury, Khammouane and Luang Prabang.

The LANGOCA Program adopts an innovative approach to enhance the quality and impact of the individual activities so that the benefits of the Program exceed the benefits of the individual activities. The Program incorporates an ongoing learning process and builds sustainability. It does this by enhancing the disaster management and UXO approaches utilised by Program partners by integrating crosscutting issues through research, capacity building, coordination, promoting lessons learned and policy dialogue. The inclusion of both long and short term activities enables LANGOCA to build on lessons learned, improve the quality and effectiveness of implementation, build sustainability, as well as respond flexibly to emerging priorities in the disaster management and UXO sectors, throughout the life of the Program.

The approved LANGOCA budget is A$14 million over a five year period, including $6.1 million for initial disaster management activities, $5.1 million for initial UXO activities, and $200,000 for the development of best practice models for the integration of crosscutting issues in disaster management and UXO activities. A detailed description of the initial activities is included in Volume 2 of the PDD. In addition to these initial activities, the Program includes A$2 million which has been retained for new activities to be implemented throughout the life of the Program, as further priorities are identified.

Program Goal

To reduce the vulnerability of the poor by integrating poverty reduction and crosscutting issues with disaster management and UXO approaches in Laos

Component 1

Disaster Management

Objective: To reduce the impact of natural and man-made disasters.

Outputs

To reduce the impact of natural and man-made disasters

Initial long term activities:

Oxfam: Drought in Upland Communities: An integrated Program Response (Saravan, Sekong and Vientiane Provinces)

SCA: Sayaboury Integrated Hazard Mitigation Project (Sayaboury Province)

WV: Community Based Disaster Risk Reduction (Khammouane Province)

Initial short term activities:

SCA: Tools for District Risk Assessment (Sayaboury Province)

SCA: Disaster Risk Education for Children (Sayaboury Province)

Component 2

Unexploded Ordnance

Objective: To reduce the impact of unexploded ordnance.

Outputs

To reduce the impact of unexploded ordnance

Initial long term activities:

CARE: Reducing UXO Risk and Improving Livelihoods of Ethnic Communities in Sekong Province

WV: Integrated UXO Action Project (Khammouane Province)

Component 3

Program Development

Objective: To build and promote Program capacity.

Outputs

Best practice models developed for the integration of crosscutting issues in disaster management and UXO activities

Initial short term activity:

CARE: Effective Programming Models Working with Vulnerable Ethnic Groups in Laos (Sekong, Luang Prabang and Sayaboury Provinces)

Best practice applied within LANGOCA on the integration of crosscutting issues in disaster management and UXO activities

Effective coordination between LANGOCA NGOs and key stakeholders in the disaster management and UXO sectors

Best practice, strategic planning and policy options for the disaster management and UXO sectors highlighted and promoted

Component 4

Program Management

Objective: To manage the Program effectively.

Outputs

Effective leadership provided by the PCC

Activities effectively coordinated between LANGOCA NGOs and other key stakeholders

Effective and efficient administrative program support provided by the Secretariat

Activity performance monitored:

M&E of individual activities

Contract monitoring

Program performance evaluated on a periodic basis

Figure 2:  Summary Program Logframe

## Location Map

SCA:

risk assessment

SCA:

disaster management

SCA:

risk education

CARE:

Ethnic group programming research

Oxfam:

Disaster management

World Vision: UXO

World Vision:

Disaster management

CARE: UXO

Oxfam:

Disaster management

CARE:

Ethnic group programming research

## Acronyms

| ACR | Activity Completion Report |
| --- | --- |
| ADD | Activity Design Document |
| ADPC | Asian Disaster Preparedness Centre |
| AM | Analytical Mission |
| ANGO | Australian Non Government Organisation |
| APAR | Annual Program Assessment Report |
| AusAID | Australian Agency for International Development |
| CAs | Cooperation Agreements |
| CBDRM | Community Based Disaster Risk Management |
| CN | Concept Notes |
| DDMC | District Disaster Management Committee |
| DM | Disaster Management |
| DRR | Disaster Risk Reduction |
| FSD | Fondation Suisse de Deminage |
| GoA | Government of Australia |
| GoL | Government of Lao PDR |
| INGO | International Non Government Organisation |
| LADCS | Laos - Australia Development Co-operation Strategy |
| LANGOCA | Laos–Australia NGO Cooperation Agreement |
| Lao PDR | Lao People’s Democratic Republic |
| LDC | Least Developed Country |
| LT | Long Term |
| M&E | Monitoring and Evaluation |
| MA | Mine Action |
| MAG | Mines Advisory Group |
| MFA | Ministry of Foreign Affairs |
| MOU | Memorandum of Understanding |
| MRE | Mine Risk Education |
| NDMO | National Disaster Management Office |
| NGOs | Non Government Organisations |
| NGPES | National Growth and Poverty Eradication Strategy |
| NRA | National Regulatory Authority |
| PCC | Program Coordination Committee |
| PCR | Program Completion Report |
| PDD | Program Design Document |
| PDMC | Provincial Disaster Management Committee |
| PIC | Program Implementation Committee |
| SCA | Save the Children Australia |
| ST | Short Term |
| SWP | Sector Working Paper |
| TA | Technical Assistance |
| TOR | Terms of Reference |
| TWG | Technical Working Group |
| UXO | Unexploded Ordnance |
| WV | World Vision |

### Currency

Aust $ 1.00 = US $ 0.78 = Laos Kip 7500

(December 2006)

# 1.  Program Preparation Steps

## 1.1  Program Origin

AusAID’s strategic direction and recent policy statements in the White Paper on Australian Aid (2006) place an increased emphasis on the importance of partnerships and quality in the design and delivery of the aid program.  A vehicle for this change process has been the introduction of ‘cooperation agreements’ with NGO partners.  Cooperation Agreements (CAs) aim to build on and maximise the unique strengths of NGOs; particularly in relation to their long-term experience, capacity and linkages with partner organisations and communities in specific countries. The Laos-Australia NGO Cooperation Agreement (LANGOCA) Program is an integral part of this strategic approach.

The LANGOCA Program closely links NGO programs and expertise to the existing Laos-Australia Development Cooperation Strategy 2004-2010 (LADCS), in order to ensure that support to NGOs in Laos is effectively targeted to strategic development priorities.  The Program will include a range of activities that aim to directly address LADCS Strategic Objective 3, to reduce the vulnerability of the poor, with a specific focus on Objective 3.1 to reduce the impact of natural disasters, and Objective 3.2 to reduce the impact of unexploded ordnance (UXOs).

Under this new approach to engagement with NGOs, AusAID requested capability statements from members of the Australian NGO community interested in delivering support in these two areas and subsequently entered into four CAs with four Australian NGOs: Oxfam, CARE, World Vision (2 sectors), and Save the Children.  These CAs enable AusAID to draw upon the expertise of these NGOs to undertake strategic policy development as well as program implementation.

Following agreement to the broad direction of the LANGOCA Program and the signing of the NGO cooperation agreements AusAID undertook an Analytical Mission (AM) from 2-15 May 2006 to examine the linkages between vulnerability reduction, disaster mitigation/ risk reduction, UXOs and crosscutting issues such as gender, ethnicity, HIV/AIDS and environment.  The AM was undertaken in conjunction with the LANGOCA NGOs and the Government of Laos (GoL), and provides a rationale for developing an integrated framework and presents a range of options for future joint AusAID and NGO interventions to reduce vulnerability to UXO and disasters. A summary of the options is presented in Section 2 of the PDD.  The AM has been technically appraised and validated in an in-country Stakeholder Workshop (28 June 2006), attended by key stakeholders from both sectors.

The findings of the AM have been incorporated into the design of the LANGOCA Program.

## 1.2  Study Team and Method

The program design process took place between July and December 2006. The Design team consists of two core members: a Program Design Consultant and a Program Management Consultant, working in partnership with AusAID post and desk, and LANGOCA NGOs. Terms of Reference (TOR) for the design are presented as Attachment 1.

The objectives of the LANGOCA Program design process are:

- To integrate the findings of the Analytical Mission (AM) and ideas from GoL, LANGOCA NGOs and AusAID into a draft Program Design Document (PDD) in accordance with AusGUIDE, with particular attention given to the most appropriate governance, management and Monitoring and Evaluation (M&E) arrangements; and

- To appraise and prioritise specific disaster management and UXO activities proposed by NGOs for inclusion in the LANGOCA Program.

The design process builds on the situational analysis and Options Matrix developed as part of the AM and has included the following steps:

- Review and integration of all relevant background documentation.

- Consultation with LANGOCA stakeholders throughout the design process including: AusAID (Laos desk and post, Community Programs Section, Asia Contracts Section); GoL; LANGOCA partner NGOs; and other international donors and NGOs as appropriate.

- Preparation of an options paper for an AusAID-NGO workshop in Melbourne, which focused on: 1) Management approaches, including proposed elements of the LANGOCA management framework; 2) Program priorities, including an outline of a high level program performance framework; 3) Proforma for preparation of NGO Activity Concept Notes (CN); and 4) Criteria for appraisal of CNs.

- Appraisal of initial disaster management and UXO CNs.

- Preparation of a preliminary Draft PDD prior to a workshop in Vientiane.

- Appraisal of revised CNs.

- Facilitation of a workshop in Vientiane with AusAID and LANGOCA NGOs, and a meeting with the GoL, to discuss: 1) appraisal comments on revised CNs; and 2) the preliminary Draft PDD.

- Revision of the Draft PDD with a follow up workshop in Vientiane with AusAID, GoL and LANGOCA NGOs.

- Finalisation of the Draft PDD prior to Peer Review.

- AusAID Peer Review.

- Finalisation of the LANGOCA PDD.

Attachment 2 provides a list of persons consulted during the design phase, and a summary of the design process and timeline is provided at Attachment 3.

# 2.  Situation Analysis

The situational analysis presented in this Section reflects the key findings of the AM.  The objective of the AM process was to develop a detailed analytical framework which would inform the development of the LANGOCA Program.  The key outputs of the AM include: the overarching LANGOCA Analytical Mission Paper; Disaster Management and UXO Sector Working Paper (Annex 6); Bibliography (Annex 8); Disaster Management and UXO Stakeholder Matrix (Annex 9); Disaster Management and UXO Lessons Learned (Annex 11); and Options for Activities (Annex 13).

The Analytical Mission has made an important contribution to the disaster management and UXO sectors in Laos by supporting and strengthening coordination between stakeholders at all levels: including GoL, donors, international NGOs (INGOs), private sector and communities, through the various stakeholder and verification workshops, and field visits.

A summary of the development context and lessons learned is presented below.

## 2.1  Policy and Program Context

The Governments of Laos (GoL) and Australia (GoA) agreed on the Laos - Australia Development Co-operation Strategy 2004-2010 (LADCS) in April 2004.   The goal of LADCS is to ‘advance Australia’s national interest by assisting Laos to improve the pre-conditions for poverty reduction and sustainable development’. The LADCS directly reflects and supports the aims of the GoL’s National Growth and Poverty Eradication Strategy (NGPES) and aims to support pre-conditions for poverty reduction and reform by improving Laos’ capacity to create and implement sound policy, as well as encouraging growth of civil society.

The Strategic Objectives of the LADCS are:

Strategic Objective 1: To build Laos human capital

- Improve access to education; and support the application of new skills and knowledge by developing Laos public policy and management skills and Laos entrepreneurial skills for small and micro enterprise.

Strategic Objective 2: To promote the growth of the market economy

- Strengthen the enabling environment by expanding access to private land titles and strengthening property rights; and contribute to Laos’ further integration into the region through regional programs.

Strategic Objective 3: To reduce the vulnerability of the poor

- Reduce the impact of natural disasters; and reduce the impact of UXO.

LANGOCA will directly address LADCS Strategic Objective 3, to reduce the vulnerability of the poor.  LANGOCA focuses on Specific Objective 3.1 to reduce the impact of natural disasters, and Specific Objective 3.2 to reduce the impact of UXOs.  LANGOCA is therefore underpinned by the LADCS, the GoL NGPES, the National Socio-Economic Development Plan, and related sub-sector policy documents.  As recommended in the AM, LANGOCA also takes an integrated approach to crosscutting issues including HIV/AIDS, gender, capacity building, ethnicity, and environment, and is underpinned by AusAID policies, including the new Mine Action, HIV/AIDS and Humanitarian strategies, as well as current best practice on quality in program design and delivery.

## 2.2  Analysis of the Development Situation

The analysis presented in this Section summarises the key issues identified in the AM.  In Laos vulnerability is the key factor impacting on a community’s ability to cope with disasters or the impacts of UXO contamination.  Poverty is a main determinant of vulnerability in the Laos context, as are increasing pressures on the environment and population.  This is exacerbated by Laos’ status as a Least Developed Country (LDC) and the high percentage of rural poor, in particular ethnic communities inhabiting remote, mountainous areas stretching the full length of the country.  Focusing on coping mechanisms (both existing and new) and building community resilience are effective strategies to reduce vulnerability.

Disasters are serious disruptions to society which exceed peoples’ ability to cope.  In Laos the disaster management sector reflects the local experience of the effects of natural and man-made disaster events such as floods and drought. However, of greater impact in Laos is the high vulnerability of remote, rural communities to ‘everyday disasters’: that is slow-onset, ongoing and compounded impediments to livelihood and community coping mechanisms, such as crop pests; animal disease; human disease; lack of access to safe water and sanitation, UXO and the general weakening of community coping mechanisms due to rapid socio-economic change, relocation and environmental degradation.  The high level of poverty related vulnerability of remote, rural communities in Laos means that even small-scale hazards can exceed the local ability to cope, resulting in disaster.  There is broad agreement that reducing vulnerability to hazards through building capacity to cope, or community resilience, effectively reduces the risk and experience of disasters.  By adopting approaches which are integrated, multisectoral and link disaster risk reduction to long term development strategies, disaster management can also add value to poverty reduction measures.

Severe UXO contamination still impacts over 37% of all agricultural land in Laos, creating a serious obstacle to sustainable development; limiting the utilisation of potentially productive land; killing and maiming people (particularly farmers and children) and animals; inhibiting fuel and water collection, communications and transport; and generally undermining social and economic development activities at the community level, as well as the national economy at macro-level.  For example, the scrap metal trade continues to grow, with people seeking UXO for scrap metal, despite the risks.  Poverty, rather than lack of knowledge about dangers, has been found to be the key factor in determining who collects scrap metal. Vulnerable, rural communities can benefit significantly from the reduced impact of UXO contamination through an integrated approach which incorporates UXO/ mine risk education; livelihood support; enhanced survey and clearance; improved survivor assistance services; and the improvement of linkages between impact reduction and post clearance land use within communities.

## 2.3  Lessons Learned

The overarching element for both sectors is the relationship between poverty, vulnerability and hazard.  In understanding the Laos context and the constraints which shape sector activities, three major issues emerge:

- Remoteness and isolation and poor access to communications;

- Weak coordination across stakeholders at all levels; and

- The need for capacity building across all levels.

While the lessons learned also reflect the specific sector experiences, there are several broad lessons which demonstrate the importance of integration. These include:

- The relevance of working within a broader poverty reduction framework for sustainability;

- The importance of utilising a community based approach;

- Building effective linkages between policy, activation of existing systems and practice at all levels;

- Understanding and practicing implementation of crosscutting issues: gender, ethnicity, HIV/AIDS, and environment; and

- A long term commitment for sustainable outcomes.

The major assessment of the sectoral analysis is that policy, strategy and action needs to take closer account of the critical linkages between UXO, disaster management, vulnerability and poverty reduction in the Laos context.  Many critical lessons have been learned across the two sectors. However, the communication and integration of these lessons and experiences is ad hoc and opportunistic, and would benefit from some concerted efforts at coordination, to increase the effectiveness and the sustainability of sectoral activities.

In the last 10 years significant changes have emerged in Laos.  They impact not only the disaster management and UXO sectors but broader issues of poverty and development.  These issues include: the growing gap between rich and poor; degradation of natural resources and the decline of forest areas; increasing population; increasing resettlement and relocation; and expansion of roads and infrastructure into neighbouring countries as part of economic growth strategies, which brings with it the potential risk of increasing HIV/AIDS, increased mobility, and unsustainable natural resource development.  The potential for future impacts of these changing patterns of development is significant, not only for the disaster management and UXO sectors, but for poverty reduction and economic growth overall.  This requires strategic consideration and incorporation into planning, policy and activity development.

## 2.4  Options Considered and Proposed Strategy

As part of the AM process a list of potential options for disaster management and UXO activities was developed and verified with key stakeholders (during the Stakeholder Validation Workshop, 28 June 2006).

Four categories have been identified as critical to assisting the development and sustainability of activities in the disaster management and UXO sectors:

- Coordination,

- Capacity building;

- Implementation of community based disaster management and UXO projects; and

- Policy dialogue.

Options have been developed to provide a balanced range of activities, with opportunity for strategic, policy, practical and hands on activities phased across the short and long term.  The options presented also identify opportunities for a range of stakeholder participation and cooperation across all levels: national, provincial, district and community.

Table 1 summarises the key options which have been utilised to inform the preparation of LANGOCA NGO Activity Concept Notes and underpin the rationale for the LANGOCA Program design.  These options reflect the unmet needs, gaps, constraints and lessons learned across the two sectors, and provide a critical assessment of rationale, constraints, timeframe and stakeholder participation appropriate for identified activities.  An underlying principle reflected throughout the options is that crosscutting issues will be integrated across all disaster management and UXO activities as they are designed and implemented.  While the structure of Table 1 does not infer prioritisation, key stakeholders endorsed the sectoral analysis and suggested that prioritisation be given to capacity building and coordination (including policy) in disaster management; and coordination and policy (including planning) in the UXO sector.

Table 1:  Summary of Options for Disaster Management and UXO Sector Activities

| DISASTER MANAGEMENT | UXO |
| --- | --- |
| 1. COORDINATION | 1. COORDINATION |
| Support NDMO, PDMC, DDMC and Village DMC to develop plans: Strategic and Action Plans which incorporate disaster risk reduction activities in addition to response activities | Strengthen Research - Investigation of research gaps - Conducting research where gaps have been identified - Responding to recommendations from research i.e. research action - Contribute to policy development - Establishment of NRA resource centre - Support to NRA in developing monitoring and effectiveness indicators for integrated UXO action |
| Improve information systems Collection and dissemination of data Risk assessments (incorporating information on both hazards and vulnerability) Historical patterns and current occurrence of disasters | Support to NRA in promoting fora to share technical lessons learned; best practice for technicians, practitioners and government |
| Support forum for sharing partnerships/ dialogue between NGOs and GoL at all levels | Media Campaign - Advocacy - Awareness raising |
| Sharing training materials, training, lessons learnt |  |
| 2. CAPACITY BUILDING | 2. CAPACITY BUILDING |
| Training materials, knowledge skills, management, planning, M&E: identify and /or develop appropriate materials | Support to UXO Lao and NRA to provide support for Survivor Assistance: a. Support to policy development b. health services c. socio-economic |
| Activate existing structures as related to above 2 activities | Support for a National Database (NRA) - Collection of data and management of data |
| Resources for sector coordination (e.g. Financial, technical) | Support to UXO Lao and NRA in terms of technical and managerial support |
|  | UXO Lao to provide nationally accredited training to UXO clearance operators |
| 3. IMPLEMENT DISASTER MANAGEMENT / POVERTY REDUCTION PROJECTS | 3. IMPLEMENT UXO/ POVERTY REDUCTION PROJECTS |
| Undertake situational analysis on needs, vulnerability, community resources and capacity, coping mechanism, cultural and traditional practices Implement Poverty Reduction Projects - Reduce vulnerability through interventions on food security, income generation, human/animal health improvement, water and sanitation, literacy and numeracy - Disaster risk reduction through infrastructure projects, natural resource management (e.g.. reforestation, soil conservation), early warning systems - Building community resilience through strengthening existing coping strategies, developing and supporting new effective coping mechanism, raising community awareness, supporting local mechanisms to plan and implement disaster risk reduction and response activities | Implement poverty reduction activities involving UXO/ mine action elements - adopting best practice - trial new practices - applying research - supporting national structures such as the NRA and meeting information requirements - needs based rural development - participation - geographic focus and community based - may include: agricultural extension, small-medium enterprise development, small scale infrastructure, water and sanitation, market access, literacy, clearance etc |
| Review existing research on ethnic groups and government policies that may have implication on disaster management | UXO/ Mine Risk Education (MRE) |
| 4. POLICY DIALOGUE | 4. POLICY DIALOGUE |
| Support the inclusion of program and community lessons in policy development/ improvement | Support fora for dialogue among GoL, donors, NGOs and the private sector, including in regional dialogues |
| Support NDMO’s engagement in national and regional policy dialogues | Support inclusion of technical lessons learned, community based approaches and best practice for technicians, practitioners and government |
| Support fora for dialogue among GoL, donors, NGOs and the private sector |  |

The National Disaster Management Office (NDMO) and National Regulatory Authority for the UXO/ Mine Action Sector in Lao PDR (NRA) have been identified as the key disaster management and UXO GoL partners, respectively, for the LANGOCA Program:

- NDMO is the secretariat for the National Disaster Management Committee in Laos and its main function is to be a coordination point between the various central ministries and provincial government structures, to promote disaster risk reduction, and to effect disaster response.

- The NRA was established by Prime Ministerial Decree in March 2004 and its main goal is to ensure a cohesive and holistic approach to UXO Mine Action in Laos in cooperation with all stakeholders.

## 2.5  Rationale for the Program

The Analytical Mission provided a clear technical recommendation, aiming to enhance the effectiveness in reducing vulnerability of the poor, by integrating poverty reduction and crosscutting issues with disaster management and UXO approaches, in the poorest areas in Laos.  As discussed in Section 2.4, the Analytical Mission also recommended an approach – at the Program level – which encompasses coordination, capacity building, community based activities, and contributions to policy dialogue.  LANGOCA NGOs bring extensive community based and local capacity building experience.  The LANGOCA Program approach capitalises on this experience and identifies a strategy for assisting the Program to provide a contribution to maximise coordination, capacity building, best practice from community based activities, and policy dialogue, across all levels: national, provincial, district and community.

Earlier AusAID NGO CAs have typically been managed as a series of discrete activities, combined under one umbrella primarily for administrative efficiency. The LANGOCA Program builds on the lessons learned from previous CAs by adopting an approach which aims to enhance the quality and impact of the individual activities so that the benefits of the overall Program exceed the benefits of the individual activities. The LANGOCA Program will do this by:

- Promoting effective coordination and communication across the Program, between the LANGOCA NGOs, and between the NGOs, GoA, GoL and other key stakeholders across all levels;

- Incorporating research activities and providing technical support for the benefit of all Program partners;

- Providing funding consistency for the NGOs, by funding long term activities (which extend for the full five year duration of the Program);

- Including short term activities (typically of a duration of one year or less) to enable targeting of research, coordination, policy and capacity building activities to be undertaken;

- Retaining $2 million for further activities to be funded after the initial activities have been identified (these “unallocated funds” will enable new short term activities and/ or modifications/ new directions for existing long term activities to be implemented throughout the life of the Program) and thereby provide added flexibility and responsiveness; and

- Ensuring that long term activities have the flexibility to be modified over time through an annual planning process that builds on lessons learned and accommodates necessary changes.

The Program will therefore include a portfolio of long term (5 years) and short term (one year or less) activities. As part of the PDD design process LANGOCA NGOs developed Concept Notes (CNs) for proposed activities, based on the options identified as part of the AM (refer Table 1). The CNs were technically appraised. Based on the appraisals and financial considerations, AusAID has approved in principle the initial portfolio of short and long term activities (subject to Peer Review). The Draft PDD is presented as Volume 1. The CNs which describe the initial portfolio of short and long term activities are presented in Volume 2 (along with the CN proforma and appraisal criteria).

The program design process itself has already contributed to improved coordination within the disaster management and UXO sectors in Laos. The AM had broad participation – GoL, AusAID, NGOs and other sector stakeholders.  The design process has enabled linkages between these key stakeholders to be strengthened over time. It has also provided the opportunity for considerable analysis of the initial CNs, including assessment of the degree to which the CNs contributed to sectoral priorities.

# 3.  Program Description

## 3.1  Program Goal

The Program goal and component objectives are based on those outlined in the Laos-Australia Development Cooperation Strategy (2004-2010), which includes the following:

Strategic Objective 3: to reduce the vulnerability of the poor

Specific Objective 3.1 to reduce the impact of natural disasters

Specific Objective 3.2 to reduce the impact of UXO

The goal of the LANGOCA Program is to reduce the vulnerability of the poor by integrating poverty reduction and crosscutting issues with disaster management and UXO approaches in Laos. This reflects the strategic objectives in the Cooperation Strategy and builds on the Analytical Mission, which recommends that poverty reduction, community based livelihoods approaches and crosscutting issues are integrated within disaster management and UXO activities by focusing LANGOCA in poor districts in Laos.

The achievements of the Program will be assessed in terms of:

- Number of poor people benefiting, and the extent of these benefits (particularly in terms of improved livelihoods), as a direct result of LANGOCA activities;

- Assessment of the level of disaster management and UXO support provided to poor districts;

- Assessment of the effectiveness of the integrated disaster management and UXO approaches included in the LANGOCA program;

- Assessment of the effectiveness of integrating crosscutting issues into disaster management and UXO approaches included in the LANGOCA program; and

- Evidence of activities being replicated, lessons learned being applied more broadly, or specific policy recommendations being accepted as a result of LANGOCA activities.

The LANGOCA goal, components and component objectives are summarised in Figure 3.

Program Goal

To reduce the vulnerability of the poor by integrating poverty reduction and cross cutting issues with disaster management and UXO approaches in Laos

Component 1

Disaster Management

Objective: To reduce the impact of natural and man-made disasters.

Component 2

Unexploded Ordnance

Objective: To reduce the impact of unexploded ordnance.

Component 3

Program Development

Objective: To build and promote Program capacity.

Component 4

Program Management

Objective: To manage the Program effectively.

Figure 3: LANGOCA Goal, Components and Component Objectives

The subsequent description of the Program components is based on the Program’s Logical Framework Matrix, which is presented as Attachment 4. A Summary Program Logframe is also presented as Figure 2 (refer Executive Summary).

As discussed further in Section 4.6, the Logframe itself will be reviewed and revised periodically to ensure it remains an appropriate tool to guide implementation, monitor progress and evaluate achievements and impact.

## 3.2  Objectives and Component Description

### Component 1: Disaster Management

The objective of Component 1 is to reduce the impact of natural and man-made disasters.  The objective has been broadened from only a natural disaster focus (as per Objective 3.1 of the LADCS), as recommended by the AM.

A number of long and short term disaster management activities will be implemented which, as discussed in Section 2.4, will focus on activities that:

- Contribute to more effective coordination within the sector, across all levels;

- Build the capacity of key stakeholders such as NDMO;

- Utilise a combined disaster management community based poverty reduction/ livelihoods approach and integrate crosscutting issues across all aspects of the sector; and

- Highlight best practice and provide opportunities for strategic planning and policy dialogue.

As reflected in the Logframe (Attachment 4), the component achievements will be assessed in terms of the following indicators:

- Increased capacity of national, provincial, district and village disaster management agencies to provide assistance and respond to disasters (eg. national policies and action plans, improved communications, coordination, technical knowledge and skills);

- Enhanced capacity of NDMO;

- Increased capacity of communities to plan for and respond to disasters (eg. improved knowledge, plans, infrastructure); and

- Increased livelihood opportunities for communities, arising from disaster management activities.

In addition, the disaster management component will also be assessed in terms of the number of poor people benefiting, and the extent of these benefits (particularly in terms of improved livelihoods), as a direct result of LANGOCA disaster management activities (although the relevant indicator is at the goal level). This is discussed further in Section 4.6.

Component 1 includes the following output.

Output 1.1:  Long and short term activities implemented effectively

In the initial portfolio of activities for Output 1.1, OXFAM, SCA and World Vision have proposed the following long term disaster management activities (refer to Concept Notes 1, 2 and 3 in Volume 2):

- Oxfam: Drought In Upland Communities: An Integrated Program Response (Saravan, Sekong and Vientiane Provinces)

The activity will take an integrated approach to addressing disaster risk reduction and work with vulnerable ethnic communities in remote upland areas who experience slow onset drought and are at risk from UXOs. This activity will be implemented in Ta Oy District (Saravan), Kalum District (Sekong) and Xaisomboun District (Vientiane). The objectives include: building household, community and village leadership knowledge and skills and resources to mitigate, prepare for and respond to disasters; supporting district, provincial and national (NDMO) agencies to respond more effectively to disasters in targeted areas; as well as improving food security, and reducing the impact of animal/ human disease and UXOs.

- SCA: Sayaboury Integrated Hazard Mitigation Project (Sayaboury Province)

The activity aims to reduce vulnerability in target communities in Sayaboury Province by developing community resilience and supporting provincial, district and village level capacity to plan for and mitigate the impact of chronic hazards. SCA will work in partnership with ADPC for both long and short term disaster management activities and builds on the work of the two short term disaster risk reduction (DRR) activities identified below.

- WV: Community Based Disaster Risk Reduction (Khammouane Province)

The activity will focus on increasing communities’ resilience and capacity to manage and mitigate future natural disasters and livelihood related disasters; including working directly with communities, village disaster preparedness units, disaster management committees at both provincial and district levels, and NDMO. WV will partner with ADPC. This activity will be implemented in Nhommalath District, Khammouane Province and build on the relationships and linkages developed for the UXO long term activity.

SCA has proposed the following short term activities (refer to Concept Notes 4 and 5 in Volume 2). These activities contribute to SCA’s long term activities to maximise potential impact.

- SCA: Tools for District Risk Assessment (Sayaboury Province)

The activity will support the development of risk assessment tools and a district database to assist Sayaboury authorities to identify, analyse and support the foundation of disaster risk plans for the most vulnerable communities, and increase planning and management capacity within village, district and provincial disaster management committees.  This activity will support SCA’s long term disaster management activity in Sayaboury.

- SCA: Disaster Risk Education for Children (Sayaboury Province)

This pilot activity in Sayaboury aims to equip children in schools and teachers with knowledge and skills in disaster risk management, to reduce vulnerability to diasters through hazard awareness, resilience building and preparedness planning. This activity will support SCA’s long term disaster management activity in Sayaboury.

The estimated cost of the initial disaster management activities is $6.14 million ($5.93 million for long term and $0.21 million for short term). In addition, it is expected that other short term activities (or modifications to existing long term activities) will be identified during implementation and funded from the unallocated funds. These may include, for example, discrete institutional strengthening activities with NDMO; capacity building activities with provinces, districts and village agencies; or identification and/or development of appropriate training materials.

Initial disaster management activity focus: The initial portfolio of activities for Output 1.1 focuses on:

- Building the capacities and coordination of key stakeholders and partners at the national, provincial, district, village and community levels;

- Developing best practice approaches to a combined disaster management community based poverty reduction/ livelihoods approach by integrating crosscutting issues across all levels of the sector;

- Enhancing capacity building by supporting the development of risk assessment tools, DRR education modules; community based disaster preparedness, and organisational DRR capacity;

- Promoting strategic planning, implementation of action plans and policy dialogue at national, provincial and regional levels; and

- Implementation of activities across all levels, including poor districts of Sayaboury, Saravan, Sekong, Vientiane and Khammouane Provinces (see Location Map on page vi).

Activity management and coordination: The specific management and coordination arrangements for each activity are discussed in each Concept Note (Volume 2) and will be finalised during the activity design process. (See Attachment 5 for Activity Design Document Proforma and Appraisal Criteria.)  Each activity will include:

- Coordination and management arrangements at provincial (eg. Provincial Steering Committee), district (eg. District Steering Committee) and community level as appropriate, and a provincial representative will participate in LANGOCA Program level management (refer Output 4.2);

- Linkages between activities and existing coordination mechanisms at national, provincial, district and village levels, wherever relevant, to avoid duplication;

- Capacity building at national, provincial, district and community levels, as appropriate; and

- A monitoring and evaluation framework that includes baseline data and specific activity indicators which (as discussed further in Section 4.6) contribute directly to the measurement of performance at the component and Program levels.

### Component 2: Unexploded Ordnance

The objective of Component 2 is to reduce the impact of unexploded ordnance. A number of long and short term activities will be implemented which, as discussed in Section 2.4, will focus on activities that:

- Contribute to more effective coordination within the sector, across all levels;

- Build the capacity of key stakeholders such as NRA;

- Utilise a combined UXO action/ community based poverty reduction/ livelihoods approach and integrate crosscutting issues, across all aspects of the sector; and

- Highlight best practice and provide opportunities for strategic planning and policy dialogue.

As reflected in the Logframe (Attachment 4), the component achievements will be assessed in terms of the following indicators:

- Increased area of land released for development;

- Increased livelihood opportunities arising from land clearance, UXO risk education and survivor assistance activities;

- Improved knowledge and awareness on UXO risk;

- Improved support for UXO survivors (economic, psycho-social, trauma counselling, vocational training, employment);

- Enhanced capacity of NRA (and the contribution attributed to LANGOCA); and

- Increased capacity of national, provincial, district and village UXO agencies to address the impact of UXOs (eg. national policies and action plans, improved communications, coordination, technical knowledge and skills).

In addition, the UXO component will also be assessed in terms of the number of poor people benefiting, and the extent of these benefits (particularly in terms of improved livelihoods), as a direct result of LANGOCA UXO activities (although the relevant indicator is at the goal level). This is discussed further in Section 4.6.

Component 2 includes the following output.

Output 2.1:  Long and short term activities implemented effectively

CARE and World Vision have proposed the following long term UXO activities (refer to Concept Notes 6 and 7 in Volume 2):

- CARE: Reducing UXO Risk and Improving Livelihoods of Ethnic Communities in Sekong Province

The activity addresses the multi-faceted vulnerability of poor ethnic communities affected by UXO contamination in 2 districts of Sekong Province. It incorporates best practice UXO contamination clearance, community based planning and land use allocation, mine risk education, and small scale rural development initiatives to enhance livelihood security. CARE will work in partnership with Swiss Foundation for Mine Action (FSD). This activity builds on the short term activity for effective programming models for working with vulnerable ethnic groups identified under Output 3.1.

- World Vision: Integrated UXO Action Project (Khammouane Province)

The activity will adopt an integrated approach to UXO action, combining risk education and clearance with community development and survivor support. WV will work in partnership with Mines Advisory Group (MAG). This activity will be implemented in Mahaxay District, Khammouane Province and build on the relationships and linkages developed for the disaster management long term activity.

The estimated cost of the initial UXO activities is $5.07 million. In addition, it is expected that a number of short term activities, or modifications to existing long term activities, will be identified during implementation and funded from the unallocated funds. These may include, for example, discrete institutional strengthening activities with NRA; capacity building activities with provinces, districts and village agencies; identification and/or development of appropriate training materials related to UXO mine risk education; or promotion of livelihood strategies for UXO survivors.

Initial UXO activity focus: The initial portfolio of activities in Output 2.1 focuses on:

- Building the capacities and coordination of key stakeholders and partners at the national, provincial, district, village and community levels;

- Developing best practice approaches to a combined UXO community based poverty reduction/ livelihoods approach by integrating crosscutting issues across all levels; sector;

- Enhancing capacity building by supporting community based UXO approaches, and building capacity of district and village organisations;

- Promoting strategic planning, implementation of action plans and policy dialogue, at national, provincial and regional levels; and

- Implementation of activities across all levels, including poor districts of Sekong and Khammouane Provinces (see Location Map on page vi).

Activity management and coordination: The specific management and coordination arrangements for each activity are discussed in each Concept Note (Volume 2) and will be finalised during the activity design process. (See Attachment 5 for Activity Design Document Proforma and Appraisal Criteria.)  Each activity will include:

- Coordination and management arrangements at provincial (eg. Provincial Steering Committee), district (eg. District Steering Committee) and community level as appropriate, and a provincial representative will participate in LANGOCA Program level management (refer Output 4.2);

- Linkages between activities and existing coordination mechanisms at national, provincial, district and village levels, wherever relevant, to avoid duplication;

- Capacity building at national, provincial, district and community levels, as appropriate; and

- A monitoring and evaluation framework that includes baseline data and specific activity indicators which (as discussed further in Section 4.6) contribute directly to the measurement of performance at the component and Program levels.

### Component 3: Program Development

The objective of Component 3 is to build and promote Program capacity. This component includes a number of outputs which aim to enhance the quality, effectiveness, sustainability and impact of the individual activities included in Components 1 and 2, so that the benefits of the Program exceed the benefits of the individual activities.

Component 3 includes the following outputs.

Output 3.1:  Best practice models developed for the integration of crosscutting issues in disaster management and UXO activities

Participating NGOs will be supported to undertake research to provide information to develop best practice models for the integration of crosscutting issues within disaster management and UXO activities, which will improve the design and implementation of specific activities at the provincial, district and community levels. CARE has proposed an initial activity (refer Concept Note 8 in Volume 2):

- CARE: Effective Programming Models Working with Vulnerable Ethnic Groups in Laos (Sekong, Sayaboury and Luang Prabang Provinces)

The activity will explore the factors that contribute to effective programming with vulnerable ethnic groups in Laos including: linkages between contributing factors to poverty and vulnerability; strategies to address constraints; identification of lessons and best practice to inform policy and program response across the sectors; with a view to integrating findings into LANGOCA long term activity design and implementation.

Additional activities may be identified during the implementation of the Program and funded from the unallocated funds.  These could include, for example, the development of additional programming models related to gender, HIV/AIDS, or the environment.

Output 3.2:	Best practice applied within LANGOCA on the integration of crosscutting issues in disaster management and UXO activities

NGOs will be able to source advice or training to integrate crosscutting issues in disaster management and UXO activities, which will improve the design, implementation and sustainability of specific activities at the provincial, district and community levels. Assistance may be requested throughout the Program and funded from the unallocated funds. Advice or training may be provided, for example, on crosscutting issues related to gender, environment, as well as ethnicity, thereby building on Output 3.1. The members of the Program Implementation Committee (which includes NDMO, NRA, AusAID and the LANGOCA NGOs as core members) will have prime responsibility for identifying and requesting (from the Program Coordination Committee) any such assistance.

Output 3.3:	Effective coordination between LANGOCA NGOs and key stakeholders in the disaster management and UXO sectors

Annual workshops (or meetings) will be held to strengthen linkages between Program partners, improve coordination, share ideas and information, and provide input to Program strategies and planning. These workshops will also provide an important opportunity to showcase the progress and achievements of LANGOCA across the two sectors.  It is expected that these workshops will be incorporated within (or simply contribute to) existing sectoral workshops/ meetings. Appropriate fora could be the Sector Working Group for UXO and the nascent Disaster Management Sector Working Group. By bringing resources and experiences to bear, LANGOCA can contribute to invigorating the Sector Working Groups.

The inclusion of LANGOCA in an existing Sector Working Group meeting, as proposed, will require the support of NRA and NDMO. Therefore, it is recommended that NRA and NDMO discuss the annual workshops with other core members of the Program Implementation Committee (PIC) and present recommendations for the annual workshop/ meeting to the Program Coordination Committee (PCC) each year. This is discussed further under Component 4 and in Section 4.1. Such an approach will not only encourage synergies between LANGOCA and other key sector stakeholders, but also enable the flexibility, if required, to conduct a workshop (possibly in Year 5) that is focused specifically on LANGOCA achievements and lessons learned.

It is envisaged that the annual workshops (or meetings) will include LANGOCA NGOs and partner organisations, NDMO, NRA, various donor representatives, provincial and other Program stakeholders and others working in the sectors. During the workshops, it is expected that LANGOCA NGOs will provide a summary of key lessons learned and identify and discuss opportunities and priorities for subsequent years. In addition, one or more independent technical advisors will provide assessment of LANGOCA progress to date and will contribute to discussions on Program strategies and priorities. The Annual Program Assessment is discussed further in Section 4.6.

The Program will have the resources to appoint a workshop facilitator, if required, to help ensure a productive exchange of information and ideas, as well as to assist in compiling specific recommendations arising from the workshop in relation to the lessons learned, best practice models, Program and sector priorities, and policy-related recommendations.

In addition to annual workshops, the Program may support a range of other activities to enhance coordination. Some individual LANGOCA NGOs already participate in various sectoral and technical working groups (TWGs). The Program could also support the participation in some additional meetings (including international and regional fora) to enhance coordination and Program strategic impact.

Output 3.4:	Best practice, strategic planning and policy options for the disaster management and UXO sectors highlighted and promoted

The documentation of lessons learned, best practice, priorities and policy options will be a key output of the annual workshops. The aim of this Output is to contribute to raising technical standards and promoting best practice and sector priorities. The Program could also publish a series of papers, which could for example, commence with the publication of the Sector Working Paper from the Analytical Mission.  Best practice findings (Output 3.1) should also be published and disseminated to key stakeholders. In addition, best practice in both sectors, as well as strategic planing and policy dialogue could be actively promoted through participation in key stakeholder regional, national, provincial and district policy fora.

The members of the Program Implementation Committee will have prime responsibility for identifying opportunities to promote best practice, and will submit these suggestions to the Program Coordination Committee as part of the usual annual planning process (described further in Section 4.1).

### Component 4: Program Management

The objective of Component 4 is to manage the Program effectively. The Program structure is summarised in Figure 4, and the core management responsibilities are elaborated in the Output descriptions which follow.

| Program | PCC PIC Technical Advisors Secretariat Activity Level Management and Coordination Arrangements Provincial Steering Committee District Steering Committee |
| --- | --- |
| Activity |  |

Figure 4: LANGOCA Program Coordination and Management Structure

Component 4 includes the following outputs.

Output 4.1:  Effective leadership provided by the PCC

The Program Coordination Committee (PCC) will be the key decision making body for the Program and will have prime responsibility for (i) the approval of all short and long term activities and activity budgets, (ii) ensuring LANGOCA remains strategically focused, (iii) providing overcite of program outcomes and quality, including further specification of indicators to assess Program impact (refer Section 4.6) and any other changes to the Logframe, as required; and (iv) resolving (when possible) any significant problems. The PCC will consist of representatives from GoL (Ministry of Foreign Affairs, MFA) and GoA (AusAID), who will co-chair the PCC. The PCC will meet twice each year (March and November).

The chair of the Program Implementation Committee (PIC, see Output 4.2) will be invited to brief the PCC on discussions at the PIC, summarising discussions held on program progress and recommendations made in terms of strategic direction and priority activities.  This briefing will draw on an approved written record of the PIC meeting.  This arrangement will help ensure that the exchange of information between the PCC, LANGOCA NGOs and GoL partners is maximised.  After providing the PIC meeting briefing to the PCC the PIC chair will withdraw from the remainder of PCC discussions thus avoiding potential conflict of interest issues. The PCC will be provided with Secretariat support and will have access to independent technical advisers (refer Section 4.4). Draft TOR for the PCC is included in Attachment 6.

Output 4.2:	Activities effectively coordinated between LANGOCA NGOs and other key stakeholders.

A PIC will be established to strengthen linkages between Program partners; improve coordination; share ideas, information and experiences; and provide input to Program strategies and planning, including further specification of indicators to assess Program impact (refer Section 4.6) and any other recommended changes to the Logframe, as required.

The PIC shall comprise one representative from each of the participating LANGOCA NGOs, AusAID, NDMO and NRA as core members. NDMO and NRA will coordinate input on behalf of the GoL. Provincial representatives plus NGO partners and other line ministries/ agencies will attend in an advisory capacity, as required. The broad representation will assist activity implementation at provincial, district and community levels, and help ensure support for an integrated, multisectoral approach, including crosscutting issues.

The PIC will meet twice each year and will be chaired on a rotating basis by the NGO partners. Provincial representatives will attend one meeting each year. The chair of the PIC will be invited to brief the PCC on discussions at the PIC. The PIC will have access to Secretariat support. Draft TOR for the PIC is included in Attachment 6.

The specific management and coordination arrangements for each activity are discussed in each Concept Note (Volume 2) and will be finalised during the activity design process. Each activity will include coordination and management arrangements at provincial (eg. Provincial Steering Committee), district (eg. District Steering Committee) and community levels, as appropriate (refer Figure 4).

Output 4.3:	Effective and efficient administrative program support provided by the Secretariat.

The PCC and PIC will have Secretariat support to assist with a range of administrative, coordination, management and reporting functions. A Vientiane based organisation will be contracted to provide Secretariat support. This will be a cost effective option and enable close collaboration with LANGOCA NGOs and other partners.

The Secretariat will, under the direction of the PCC, undertake the following tasks: organisation and support of PCC and PIC meetings; record the Minutes of the meetings; organisation and support of Workshops and other meetings as required; preparation of Annual LANGOCA Program Summary (discussed in Section 4.1); assisting in contracting of locally sourced technical assistance; and other administrative and logistical support required for effective implementation of the Program. The Secretariat will not have a direct technical role in the Program, but require program administration expertise in dealing with a wide range of stakeholders. Secretariat services will be provided on a part-time basis during the life of the Program. Draft TOR for the Secretariat is included in Attachment 6.

Output 4.4:	Activity performance monitored.

M&E of individual activities

Each NGO will have prime responsibility for monitoring the progress of each activity they manage, based on the M&E Framework developed as part of activity design. The M&E Framework will include baseline data and specific activity indicators which (as discussed further in Section 4.6) contribute directly to the measurement of performance at the component and Program levels.

Progress will be reported by each NGO twice each year: once as a Six Monthly Progress Report presented in September, and once as an update included in the subsequent Annual Plan, presented in March.

The PCC may also identify activities which warrant periodic monitoring. As discussed further in Section 4.1, a pool of technical advisors will be available to undertake short term monitoring of selected activities and report back to the PCC. These advisors will liaise with and provide advice to the NGO concerned, and/ or the PIC, as appropriate. Details of reporting and monitoring of activities are discussed further in Section 4.6.

Each NGO will prepare an Activity Completion Report (ACR) for each activity. This will summarise the main objectives, methodology, achievements both in terms of outputs and outcomes, an assessment of likely impact, lessons learned and recommendations for further support. The ACR will also contain a cost summary.

Contract monitoring

AusAID will be responsible overall for monitoring the contracts of LANGOCA NGOs, the Secretariat and independent TA.  Contract monitoring with LANGOCA NGOs will be based on Service Orders between AusAID and each NGO, which will reflect the PDD and the intent of the CAs.

Output 4.5:	Program performance evaluated on a periodic basis.

Program Performance will be based on the following: (i) Annual Program Assessment Reports (APAR), prepared by independent TA as described in Output 3.3; (ii) Mid Term Review (MTR); and (iii) Program Completion Report (PCR).

The Analytical Mission helped identify a baseline for the Program. Additional indicators, relating specifically to the incidence and depth of poverty and livelihoods in Laos, will need to be clarified and information collected prior to activity implementation. This is discussed further in Section 4.6.

Independent technical advisors will be contracted to conduct a MTR (in year 3) and to prepare a PCR (in year 5).  APARs will provide the major link between Activity performance monitoring and Program performance monitoring. APARs will do this by assessing the likely contributions that individual activities will make to the component objectives, based on indicators which address the relevant sector (Component 1 or 2), and indicators for Components 3 and 4.

Details of reporting and the evaluation of Program performance is discussed further in Section 4.6.

# 4.  Management and Financing Arrangements

## 4.1  Planning and Management Mechanisms

### Finalisation of Activities and an Annual Plan for Year 1

Each NGO will submit Activity Design Documents (ADDs) for each of the long and short term activities described in the approved Concept Notes in either January or March 2007. Each ADD will include additional implementation and cost details for Year 1, avoiding the need for separate annual plans in the first year of the Program.

The ADDs will be submitted to AusAID Post and will be assessed by the PCC, based on the selection criteria presented in Attachment 5:

- Following submission of each ADD and in consultation with the PCC, AusAID Post will engage technical advisors to appraise each ADD (using the appraisal criteria presented in Attachment 5);

- AusAID Post will ensure that activity budgets have not been exceeded;

- The PCC will decide on the program for Year 1, based on an appraisal of the ADDs and advice from the PIC, and will then be able to confirm the allocation of funds for each approved activity. The PCC may at their discretion, request additional information or changes to any of the ADDs prior to implementation or as a requirement prior to final approval of an activity; and

- An Annual LANGOCA Program Summary will be prepared, which lists the activities to be undertaken in Year 1 and includes the approved cost for each activity.

It is anticipated that the Secretariat will be established in March 2007. The AusAID Post will therefore be expected to assume some additional administrative roles prior to this time. Once established, the Secretariat will assist AusAID Post and the PCC in the above tasks. The timeframe for these tasks is outlined in Attachment 3 and an Implementation Schedule is presented as Attachment 7.

### The Annual Planning Process for Year 2 Onwards

Each NGO shall produce a Six Monthly Progress Report in early September. This will provide an update on progress and identify any constraints or problems for each activity being implemented. Financial reports will also be included, broken down by quarter. The Six Monthly Progress Reports will be a key resource for the conduct of the annual LANGOCA review of progress for both the disaster management and UXO sectors, resulting in an Annual Program Assessment Report (APAR, refer Section 4.6). The PCC may choose to engage independent TA to undertake the review. This will be conducted in September or October.

As discussed under Outputs 3.3 and 3.4, annual workshops and other fora will produce summaries of lessons learned and recommendations relating to best practice models, Program and sector priorities, and policy-related recommendations.  Recommendations from the workshops and other fora will be utilised by the PIC when developing their Program related recommendations for the PCC. The PCC – when meeting in November – will be able to respond, both in terms of providing strategic guidance to the Program and ascertaining the level of funding available for the Program in the next financial year. This information will be utilised by the participating NGOs when developing annual plans for the following year and preparing designs for new short term activities.

The annual planning process for Years 2 to 5 is summarised in Table 2.

Table 2:  Annual Program Level Planning Process

| Month | Activity |
| --- | --- |
| Early September | NGOs submit brief Six Monthly Progress Reports (covering the period January to June) to AusAID for each activity. |
| Sept/Oct | AusAID engages independent TA to conduct a brief review of progress of the activities included in the disaster management and UXO sectors, resulting in the Annual Program Assessment Report. |
| October | Annual workshops held to share lessons learned and improve sector coordination. As discussed under Output 3.3, it is expected that these workshops will be incorporated within (or simply contribute to) existing sectoral workshops/ meetings. Independent TA will present a brief summary of the Annual Program Assessment Report during the annual workshops. |
| Early November | The PIC meets and builds on annual workshop outcomes to prepare its recommendations to the PCC in terms of Program strategies and specific opportunities for new activities. The PIC will agree on which Concept Notes will be prepared. |
| Late November | The PCC meets and provides advice on Program strategy, specific advice to NGOs on which Concept Notes are to be developed into full ADDs, and provides an indication of the level of funds available for the following financial year. |
| Early March | ADDs and Annual Plans (which incorporate the Six Monthly Progress Reports covering the period July to December) are submitted to the PIC and PCC. |
| Early March | The PIC meets to discuss annual plans and new ADDs, prepares recommendations for the PCC, and with Secretariat support, prepares a draft Annual LANGOCA Program Summary, which is submitted to the PCC. |
| Early March | The PCC organises for an appraisal of draft annual plans and new ADDs by independent TA, as required. |
| Late March | The PCC meets and decides on the funding allocation for the following financial year. As a result of this, the Secretariat finalises the Annual LANGOCA Program Summary. |

It is envisaged that the PCC could have the capacity to approve new short term activities at times outside the regular planning process (for example, approving ADDs during the November PCC meetings). This would provide additional flexibility and responsiveness within the Program, and would need to be coordinated with the PCC, PIC, relevant LANGOCA NGOs and GoL partners.

### Annual LANGOCA Program Summary

The Annual LANGOCA Program Summary will include:

- A brief description of each activity and the budget for each activity over the next financial year;

- Proposed technical assistance or training inputs (refer Output 3.2);

- Recommendations for the annual workshops (refer Output 3.3), including the proposed dates, linkages to existing sectoral workshops/ meetings, and inputs to be provided through LANGOCA;

- Proposed publications to highlight best practice (refer Output 3.4);

- A schedule of dates for key sectoral coordination meetings (in addition to the annual workshop) and PIC and PCC meetings;

- Suggestions for highlighting and promoting the Program; and

- Any other recommendations for consideration by the PCC.

This document will be prepared by the PIC in early March (with assistance from the Secretariat), submitted to the PCC, then revised by the Secretariat in late March once the PCC confirms the activities and budget allocations for the next financial year (see Table 2). The Annual LANGOCA Program Summary is expected to be a relatively short and succinct document that can be utilised by Program partners to summarise the key activities being undertaken in the next financial year.

## 4.2  Resources

The approved LANGOCA budget is A$14 million over a 5 year period. The Program will retain $2 million for unallocated activities. In addition, approximately $1 million will be required for program management, Workshops, and related technical assistance, leaving $11 million for the initial portfolio of long and short term activities. Because the cost of the initial Concept Notes exceeded the approved budget, and the Concept Notes were of a high quality, AusAID decided to augment the budget using non-bilateral funds. The resulting allocation of funds is summarised in the following table.

Table 3: LANGOCA Funding Summary

A$ million

| Funding category | Sub-total | Total |
| --- | --- | --- |
| Component 1: Disaster Management - Oxfam: Drought In Upland Communities: An Integrated Program Response - SCA: Sayaboury Integrated Hazard Mitigation Project - WV: Community Based Disaster Risk Reduction - SCA: Tools for District Risk Assessment - SCA: Disaster Risk Education for Children | 2.00 1.93 2.00 0.10 0.11 | 6.14 |
| Component 2: Unexploded Ordnance - CARE: Reducing UXO Risk and Improving Livelihoods of Ethnic Communities in Sekong Province - WV: Integrated UXO Action Project | 3.07 2.00 | 5.07 |
| Component 3: Program Development - CARE: Effective Programming Models Working with Vulnerable Ethnic Groups in Laos - LANGOCA workshops and/ or contributions to existing sectoral meetings | 0.20 0.28 | 0.48 |
| Component 4: Program Management Management and coordination |  | 0.80 |
| Unallocated funds |  | 2.00 |
| Total |  | 14.49 |

Although the majority of LANGOCA Program funds will be allocated in the first half of 2007, the unallocated funds and an annual planning process will ensure the Program retains considerable flexibility. It is also AusAID’s intention to consider further budget supplementation during implementation. This should be accommodated through the usual annual planning process.

Additional cost details – at the Program level – are presented as Attachment 8. The initial cost estimates for each of the initial activities (including design) are contained within the Concept Notes (Volume 2).

## 4.3  Program and Activity Level Agreements

The Australia-Laos Development Cooperation is governed by an umbrella MOU signed in 2002.  The GoL and GoA will enter into a Subsidiary Arrangement for the LANGOCA Program. This Arrangement will be confirmed once the PDD is finalised. Figure 5 illustrates the process for agreements at Program and activity levels.

GoL – GoA Umbrella MOU

GoL – GoA LANGOCA Subsidiary Arrangement

PIC review of ADD

PCC provisional approval of ADD

GoL approval of ADD & Activity Agreement

GoL – NGO Agreements / GoL Decrees on ODA & NGOs

Activity Agreement (based on ADD) signed at appropriate level

NGOs consult with line agencies, local government and communities

Activity design & Agreement

NDMO and NRA coordinate GoL review process

Technical appraisal and PIC recommendations considered

Figure 5: Process for Agreements at Program and Activity Levels

Each NGO has an agreement to operate in Laos. NGO activities in Laos are governed by Prime Ministerial Decree No. 71, and by Prime Ministerial Decree No. 168,  governing ODA. Subsidiary Agreements are then developed for each activity at the appropriate level (eg. national, provincial, district).

For LANGOCA, NGOs will begin their activity design process which will include consultations with key stakeholders (including line agencies and local government representatives) and develop an ADD and an outline of the Activity Agreement, in parallel. Once an ADD is prepared, it is submitted to the PCC and PIC. This enables the GoL (coordinated by NDMO and NRA) to review the ADD, which feeds into the discussion by core PIC members, including relevant line agencies or provincial representatives, if appropriate. It also enables AusAID to undertake an external technical appraisal of the ADD.

The PCC then reviews the ADD and the recommendations of the PIC and the independent appraisers. If approved, the PCC provides provisional support for the ADD. The ADD is then the basis for the Activity Agreement. With GoL approval, the Activity MOU will be signed by the appropriate level by the key line agency, then submitted to GoL (MFA) for final endorsement.

## 4.4  Contracting and Financing Arrangements

### LANGOCA NGOs

The contract requirements and financial limitation of each activity will be specified in the Service Order with each NGO. There will be one Service Order required for each NGO for activity design and one for the implementation of each activity. AusAID will make an annual payment to each NGO for each activity, based on the cost projection contained in the ADD and – for activities extending over more than one financial year – in subsequent annual plans. The NGOs will be required to acquit these funds on an annual basis. Subsequent payments will be dependent on the acquittal of prior payments and acceptance by AusAID of progress reports and annual plans.

The NGO will be wholly responsible for any sub-contracting or partnership arrangements, as well as any payments to other organisations, individuals, and for materials.

### Secretariat

A limited tender process will be initiated in January 2007. The contract for Secretariat services will be managed through the AusAID Post (with assistance from AusAID Contracts Section). AusAID Post will task the Secretariat on behalf of the PIC and PCC. It is anticipated that the Secretariat will be established in March 2007. The Post will monitor the performance of the Secretariat. The Secretariat will have funds for PCC and PIC meetings, Workshops, Program publications, locally sourced TA and any additional administrative tasks.

### Technical and Strategic Advisors

Independent TA will be required by the PCC for the appraisal of designs, review of selected progress reports, Annual Plans and other advice on a periodic basis throughout the life of the Program. In addition to specific technical advice for the disaster management and UXO sectors,  strategic advice may also be required to review sector achievements, or in identifying gaps/ opportunities at the Program level, as well as contributing to Workshops.

Technical and strategic advice will in general be provided to both the PCC and PIC, and these inputs will include close consultation with the LANGOCA NGOs. As the technical advisors will generally need to liaise closely with LANGOCA NGOs and GoL partners, and the advice will often involve only 1 or 2 days input, there will be distinct advantages in locating and contracting advisors who reside in the region, and preferably in Laos. However, it is recognised that some international TA from outside the region may also be used from time to time, for example, for Program review.

Independent TA will be contracted separately by AusAID Post or the Secretariat. A Tasking Note for each input will be prepared by AusAID Post or the Secretariat, outlining clearly the tasks to be performed, the time input available, and the reporting and presentation requirements. Generic TOR for the independent TA is included in Attachment 6.

## 4.5  Role and Responsibility of Key Stakeholders

### GoL:  Ministry of Foreign Affairs

MFA will:

- Co-chair the PCC;

- Provide input to the annual planning process and consult with AusAID during the finalisation of the Annual LANGOCA Program Summary (to ensure the Program contributes to GoL priorities and the development priorities agreed between the two countries);

- Provide links between the Program and GoL agencies;

- Assist in the effective coordination of the Program with other donors and GoL programs;

- Facilitate GoL approval of changes to the designs of existing activities and approval of new activities; and

- Maintain dialogue and build relationships with the GoL, NGO partners and other key stakeholders to support their inputs to the Program.

### GoL:  NDMO and NRA

NDMO and NRA will:

- Participate in the PIC and play a key coordination role on behalf of the GoL;

- Assist in ensuring effective coordination between LANGOCA activities and those of GoL, donors and other key stakeholders, including, for example:

- Coordinating GoL input to activity designs (and preparation of Activity Agreements) as discussed in Section 4.3 and illustrated in Figure 5);

- Suggesting links between the annual LANGOCA workshops and other sector or technical meetings;

- Assist and facilitate coordination across all levels of government: national, provincial, district and village;

- Assist in identification of priorities for the LANGOCA Program;

- Promote lessons learned, best practice models and strategic policy initiatives across the sector (including, for example, suggesting the preparation of particular LANGOCA publications); and

- Maintain dialogue and build relationships with the GoL, NGO partners and other key stakeholders to support their inputs to the Program.

### GoL:  Provincial Government

Provincial Government will:

- Support the establishment of Provincial Steering Committees (or equivalent) and appropriate coordination/management arrangements at district and community levels for individual activities;

- Support an integrated, multisectoral approach, including crosscutting issues, for the implementation of individual activities;

- Provide a representative (generally from the Provincial Steering Committee) to participate in one PIC meeting each year;

- Provide input to Workshops, as appropriate; and

- Assist in resolution of implementation constraints/ issues, as they arise.

### GoA:  AusAID

The AusAID Desk will:

- Provide input to the annual planning process, including provision of forward budget estimates;

- Contribute to strategic input into LANGOCA Program development;

- Promote linkages between LANGOCA and other Australian activities in Laos and the region, including for example, NGO programs in Cambodia and Vietnam and the regional HIV/AIDS project;

- Promote LANGOCA in Australia; and

- Maintain dialogue and build relationships with the GoL, NGO partners and other key stakeholders to support their inputs to the Program.

The AusAID Post will:

- Co-chair the PCC;

- Prepare a Service Order for each NGO for the activity design phase;

- Prepare a Service Order for the implementation of each activity;

- Supervise and manage contracted activities – including:

- Ensuring that funds are being appropriately used,  through report documentation review, monitoring visits, and if necessary commissioning independent financial audits;

- Ensuring that a system exists for confirming that the LANGOCA NGOs/ activities are delivering quality outputs (goods and services delivered) through the annual reviews by the technical advisers;

- Ensuring that the LANGOCA NGOs/ activities are achieving quality results;

- Requiring evidence of continuous improvement.

- Manage the contract with the Secretariat, which may include a periodic review of performance and/or periodic audit;

- Provide input to the PCC and PIC;

- Contribute to strategic input into LANGOCA Program development;

- Prepare and/or approve Tasking Notes for technical advisors, and contract and brief the advisors for each input;

- Organise and contract teams to undertake a MTR and prepare a PCR;

- Provide input to Aidworks;

- Promote LANGOCA in Laos;

- Participate in fora concerning disaster management, UXO and related fields, and contribute to Program development by sharing information with other LANGOCA partners;

- Promote linkages between LANGOCA and other Australian activities in Laos and the region, including for example, NGO programs in Cambodia and Vietnam and the regional HIV/AIDS project;

- Consult with MFA during the preparation and finalisation of Annual LANGOCA Program Summary; and

- Maintain dialogue and build relationships with the GoL, NGO partners and other key stakeholders to support their inputs to the Program.

TOR for the PCC, PIC, Secretariat and Independent Technical Advisors are presented as Attachment 6.

## 4.6  Program Performance and Monitoring and Evaluation

Each activity will be assessed using a number of process and impact indicators which are derived from the Program Logframe. As shown in the Logframe (Attachment 4), the process indicators have been clearly identified for the goal and component objective levels. However, the impact indicator presented in the Logframe (at the goal level) is the number of poor people benefiting, and the extent of these benefits (particularly in terms of improved livelihoods), as a direct result of LANGOCA activities. Before activity implementation commences, the impact indicator(s) need to be specified clearly. This is discussed below, and is followed by an outline of the M&E system for (i) each activity and (ii) the Program as a whole.

### Impact Indicators

The impact of the long term activities and the Program as a whole could be assessed using one or more livelihood indicators, such as improved nutrition, reduced mortality, increased food production, increased income levels, etc. These indicators relate directly to poverty measurements.

It will be important for all NGOs – and other stakeholders including AusAID, NDMO and NRA – to agree on the choice of a common group of baseline impact indicators and how each indicator is to be defined and measured. The PIC is an appropriate committee to discuss and finalise impact indicators, although the PIC may need external technical assistance or input by other GoL agencies to facilitate this discussion. The PIC will need to review available GoL poverty data. If the GoL collects poverty data at district and village levels on a regular basis that can be used to assess the impact of activities (and the Program as a whole), it will reduce the need to collect initial baseline data and minimise the cost of impact assessment for individual activities. In selecting livelihood indicators, care will need to be taken to ensure:

- Livelihood indicators can be measured effectively;

- Impacts can be demonstrated over a relatively short period of time; and

- Impacts can be attributed to LANGOCA activities.

It is recommended that the PIC meets prior to the completion of activity designs to finalise the impact indicators, define these carefully and outline how each will be measured (to ensure consistency across activities and the Program as a whole). The impact indicators should then be incorporated in the Logframe at the goal level. The number of poor people benefiting, and extent of these benefits – based on the final choice of indicators – will also be used to assess the impact of individual disaster management and UXO activities, and the Disaster Management and UXO components.

### Activity Performance M&E

Each NGO will have prime responsibility for monitoring the progress of each activity they implement, based on the M&E Framework developed as part of activity design (see Attachment 5).  Activity M&E Frameworks should include:

- Indicators to assess the impact of the activity (see above);

- Indicators which address the relevant sector (Component 1 or 2) and indicators for Components 3 and 4;

- Disaggregated data on crosscutting issues (eg. gender, ethnicity, environment, HIV/AIDS) as appropriate;

- GoL poverty data, as appropriate, and other baseline data; and

- Specification of the means of verification to be used to gather indicator data (i.e. how information will be collected, and the resources required).

### Reporting Requirements

Six Monthly Progress Reports and Annual Plans will report on progress, and the Activity Completion Report will provide an overview of actual achievements compared with objectives.

Details of reporting and monitoring of activities are presented in Table 4.

Table 4: Activity Reporting Requirements for LANGOCA NGOs

| Report | Brief description | Frequency | Responsibility |
| --- | --- | --- | --- |
| Activity Design Document | Describes the activity and provides budget details (with additional detail in the first year to avoid preparing an initial annual plan for the same activity). A draft proforma for long and short term ADDs is presented in Attachment 5. | One per activity | NGOs will submit ADDs to the PCC |
| Six Monthly Progress Report | A brief report on each activity, summarising actual progress and financial expenditure against objectives specified in the activity designs, and highlighting major achievements, significant constraints (if any) and strategies for overcoming constraints. The September Six Monthly Report shall cover the period January to June. A draft proforma is presented in Attachment 5. | One per activity per year, required in September | NGOs will submit reports to the PCC |
| Annual Plan | For each activity extending beyond the initial financial year, an annual plan will be required summarising progress, outlining the main activities, inputs and costs required for the next year. This includes a Six Monthly Progress Report (for the period July to December). The Annual Plan provides an opportunity to refine the activity from its original design. A draft proforma is presented in Attachment 5. | One per activity (for activities extending beyond the first financial year), required in March | NGOs will submit reports to the PCC |
| Activity Completion Report | A brief report comparing actual progress with objectives, methodology, achievements both in terms of outputs and outcomes, an assessment of likely impact, significant constraints, lessons learned and recommendations for further support. The ACR will also contain a cost summary. A draft proforma is presented in Attachment 5. | One per activity | NGOs will submit reports to the PCC |

Proformas for each of the above reports are presented in Attachment 5. All M&E and reporting costs, including the collection of baseline data and assessment of activity impact, should be included in the Activity Design costs.

### Program Performance

Program Performance will be based on the indicators at the goal and component objective levels, and will include the following: (i) Annual Program Assessment Report (APAR); (ii) Mid Term Review (MTR); and (iii) Program Completion Report (PCR).

APARs will provide the major link between Activity performance monitoring and Program performance monitoring. APARs will do this by assessing the likely contributions that individual activities will make to the component objectives, based on indicators which address the relevant sector (Component 1 or 2), and indicators for Components 3 and 4. Program performance assessment will utilise disaggregated data on crosscutting issues (eg. gender, ethnicity, environment, HIV/AIDS), as well as relevant GoL poverty data where available.

Independent technical advisors will be contracted to conduct the APARs, as well as a MTR in year 3, and prepare a PCR in year 5.  AusAID corporate processes and experience drawn from other CAs will inform the planning for the MTR and PCR.  Details of reporting and the evaluation of Program performance is summarised in Table 5.

Table 5: LANGOCA Program Performance Matrix

| Report | Brief description | Frequency | Responsibility |
| --- | --- | --- | --- |
| Annual Program Assessment Report | Brief review of ADDs, Six Monthly Progress Reports, Annual Plans, Activity Completion Reports, Annual LANGOCA Program Summary, field visits and consultations (as appropriate). Advice on implementation of individual activities and the effectiveness of integrating crosscutting issues. Strategic advice on Program direction and identification of new activities. Assessment of Program level performance, Logframe and management, and recommendations as appropriate. | September each year | AusAID will contract independent TA on behalf of the PCC |
| Mid Term Review Report | TOR will be prepared by the PCC for an independent review of the Program (referring to AusGuidelines and AusAID Community Programs Section as appropriate). It will examine program performance, continuing design relevance and identify opportunities for program improvements, options for changes in direction (including review/ refinement of the Logframe, as required). | Year 3 | AusAID will contract independent TA on behalf of the PCC |
| Program Completion Report | TOR will be prepared by the PCC to prepare the PCR (referring to AusGuidelines as appropriate). Activity completion reports will form a part of the PCR. It is envisaged that LANGOCA NGOs will play a key role in the preparation of the PCR. | Year 5 | AusAID will contract independent TA on behalf of the PCC |

Draft TOR for the Annual Program Assessment is presented in Attachment 6.

# 5.  Risk, Sustainability and Feasibility

## 5.1  Risk Management

NGOs will identify risks for each activity and describe how these risks will be managed or mitigated. This will be included in the ADDs (see Attachment 5) and reported on as part of the Six Monthly Progress Reports.

In addition to the risks that will impact on individual activities, there are a number of risks at a Program level that may impact on the achievement of the Component objectives and Program goal. The PCC – and to a lesser extent the PIC – will have the main responsibility for monitoring and managing Program risks. A Program level Risk Management Matrix is presented as Attachment 9.

As indicated in the Risk Management Matrix, there are a number of risks that may reduce the impact of the Program. Some of the main risks, and proposed mitigation measures, are summarised in the following table.

Table 6: Risk Summary

| Risk | Mitigation |
| --- | --- |
| NDMO and/ or NRA are unable to engage with LANGOCA due to resource constraints and/ or other commitments | Support NDMO and NRA to enhance their coordination capacity |
| Ineffective coordination across stakeholders in both sectors | Promote best practice and lessons learned through Workshops, sectoral TWGs, independent technical advice and maximise input from program partners, particularly NDMO and NRA |
| Practical difficulties of integrating crosscutting issues at activity and Program levels |  |
| Delays in GoA and GoL approval process | Support GoA and GoL priorities, improve coordination, and promote local ownership of activities and the LANGOCA Program |
| Increased cost of UXO clearance activities | Manage UXO clearance costs by coordinating with other stakeholders to explore opportunities for scaling up pilot activities and developing best practice |

There are also a number of Program design features that aim to reduce risk, including the promotion of partner ownership, providing flexibility in both long and short term activities, allowing for technical and strategic advice at relevant times, and maximising the opportunities to benefit from lessons learned.

## 5.2  Sustainability

The Program includes a number of strategies to promote sustainability:

- Developing best practice by promoting community based poverty reduction/ livelihoods approaches which integrate crosscutting issues across all levels of the disaster management and UXO sectors;

- Understanding and practicing implementation of crosscutting issues: gender, ethnicity, HIV/AIDS, and environment across the Program;

- Incorporating research activities and providing technical support for the benefit of all Program partners;

- Promoting effective coordination and communication across the Program, between the LANGOCA NGOs, and between the NGOs, GoA, GoL and other key stakeholders across all levels;

- Providing funding consistency for the NGOs, by funding long term activities (which extend for the full five year duration of the Program);

- Simultaneously maximising flexibility and responsiveness by funding new short term activities and/ or modifications/ new directions for ongoing long term activities, and retaining funds for this throughout the life of the Program;

- Through an ongoing learning process by promoting the exchange of information, lessons learned and best practice models, with the intention that it will benefit not only LANGOCA Program partners but other stakeholders in the disaster management and UXO sectors; and

- Building effective linkages between policy, activation of existing systems and practice at all levels.

In summary, the innovative approach adopted by LANGOCA to the Cooperation Agreement mechanism, aims to not only maximise the impact and sustainability of individual activities, but also to maximise the long term impact of the Program as a whole.

## 5.3  Feasibility

Reducing the vulnerability of the poor to disaster management and UXO impacts is a major development priority for both the GoL and GoA. This priority is reinforced by adopting an approach to disaster management and UXO sectors which is integrated, multisectoral and addresses crosscutting issues. The Program is consistent with the policy framework of both countries.

LANGOCA builds on the unique strengths of NGOs, and particularly their long term experience and relationships with local levels of government and the communities in which they work. The Program provides LANGOCA NGOs and key government stakeholders (NDMO and NRA) with a key role in the management of the Program. There will also be a concerted effort to coordinate and strengthen relationships between a wide range of stakeholders, while maximising the participation and ownership of the government agencies and communities directly involved in implementation.

The Program is well founded from a technical perspective. The Analytical Mission provided clear recommendations to integrate community based, poverty reduction / livelihoods and crosscutting issues with disaster management and UXO approaches. The mainstreaming of crosscutting issues across all aspects of the Program ensures issues relating to gender, ethnicity, HIV/AIDS and the environment are effectively integrated. Independent advice to the Program and appraisal of individual activities will contribute sound technical support to assist in the effective integration of crosscutting issues.

The Program incorporates an ongoing learning process and builds sustainability. It does this by enhancing the disaster management and UXO approaches utilised by Program partners by integrating crosscutting issues through research, capacity building, coordination, promoting lessons learned and policy dialogue. The inclusion of both long and short term activities enables LANGOCA to build on lessons learned, improve the quality and effectiveness of implementation, build sustainability, as well as respond flexibly to emerging priorities in the disaster management and UXO sectors, throughout the life of the Program.

In terms of the demonstrated local capacity for a locally recruited secretariat; there are a range of organisations present in Vientiane which it is assessed have the institutional capacity and can deliver the secretariat services.

Finally, there are a number of risks that could impact on the success of individual activities and the Program as a whole. However, there has been a concerted effort to identify these, and build into the Program design an appropriate methodology to mitigate these risks. The Program is therefore considered feasible.

Attachment 1

# Design Process TOR

### Background

These terms of reference have been prepared for the development of the design of the Laos-Australia NGO Cooperation Agreements (LANGOCA) program.

AusAID’s strategic direction and recent policy statements place an increased emphasis on the importance partnerships and quality in the design and delivery of the aid program.

A vehicle for this change process has been the introduction of ‘cooperation agreements’ with NGO partners.  Cooperation agreements aim to build on and maximise the unique strengths of NGOs; particularly in relation to their long-term experience, capacity and linkages with partner organisations and communities in specific countries.

The proposed LANGOCA program will link NGO programs and expertise closely to the existing Laos-Australia Development Cooperation Strategy 2004-2010 (LADCS), in order to ensure that support to NGOs in Laos is effectively targeted to strategy development priorities.  The program will include a range of interventions that aim to directly address LADCS Strategic Objective 3, to reduce the vulnerability of the poor, with a specific focus on Objective 3.1 to reduce the impact of natural disasters, and Objective 3.2 to reduce the impact of unexploded ordnance (UXO).

Under this new approach to engagement with NGOs, AusAID requested capability statements from members of the Australian NGO community interested in delivering support in these two areas and subsequently entered into five ‘in-principle’ cooperation agreements (CAs) with four Australian NGOs: Oxfam, CARE, World Vision (2), and Save the Children.  These agreements will enable AusAID to draw upon the expertise of these NGOs to undertake strategic policy development as well as program implementation.

Following agreement to the broad direction of the LANGOCA Program and the signing of the NGO cooperation agreements AusAID undertook an Analytical Mission (AM) to examine the linkages between vulnerability reduction, disaster mitigation/ risk reduction, UXOs and crosscutting issues such as gender, ethnic groups, HIV/AIDS and environment.  The AM was undertaken in conjunction with the NGOs and the Government of Laos, and it provides a rationale for developing an integrated framework for future joint AusAID and NGO interventions to reduce vulnerability to UXO and disaster mitigation (DM).  The AM has been subject to an in-country Validation Workshop attended by key local and international stakeholders; appraisal by a UXO Sector Specialist (Jo Durham, MAG) and AusAID’s rural development advisor (Alwyn Chivers).  It has also been positively received and reviewed during the Debrief Meeting in Canberra on 19 July 2006.

The AM provides four sets of options for activities assessed as critical to assisting the development and sustainability of the DM and UXO sectors: 1) coordination, 2) capacity building; 3) implementation of DM and UXO projects; and 4) policy dialogue.  It includes a range of options with opportunity for strategic, policy, practical activities phased across the short and long term.  The options presented also identify opportunities for a range of stakeholder participation and cooperation across national, provincial, district and village levels.

### Objectives of the Program Design

- To integrate the findings of the Analytical Mission, NGO and AusAID ideas and related documentation into a draft Program Design Document (PDD) in accordance with AusGUIDE, and with particular attention to the most appropriate governance and management as well as Monitoring and Evaluation arrangements.; and

- As part of this process and based upon NGO and AusAID ideas, prioritise specific interventions to reduce vulnerability to UXO and disaster risk reduction for this initial period and identify a process for ongoing prioritisation and programming under LANGOCA

### Scope

The Design team will commence on 20 July 2006 and will consist of two core members a Program Design Consultant and a Program Management Consultant (note this may change). The design team will:

- Review and then integrate all relevant background documentation into a draft PDD format (listed).

- Consult with LANGOCA stakeholders throughout the design process including:

  - AusAID (Laos desk and post, Community Programs Section, Asia Contracts Section);

  - The Government of Laos;

  - LANGOCA partner NGOs; and

  - Other international donors and NGOs;

- Prepare two options papers for incorporation into the PDD by 3 August in preparation for an NGO workshop (7 August):

  - Management approaches, including proposed elements of the LANGOCA management framework; and

  - Program priorities, including an outline of a high level program performance framework.

- Provide a summary report on the outcomes of the NGO workshop (10 August) and incorporate into draft PDD where relevant.

- Provide, circulate and discuss at in-country workshop(s) the draft program design document including the proposed interventions, key governance and management approach, roles and responsibilities of stakeholders, a program logframe, a performance management framework an indicative budget by year and intervention, and a risk assessment matrix.

- Taking into account feedback, finalise a draft program design document for peer review. The PDD should include but not limited to:

  - a description of LANGOCA objectives, partners, alignment with the country program/White Paper, GoL NGPES, and the design process undertaken;

  - a rationale for the program objectives, management approach and selected interventions;

  - responses to the issues identified in the LANGOCA design process concept note;

  - appropriate governance and management processes, including:

    - principles for cooperation and implementation;

    - proposed initial interventions and areas for further analysis that LANGOCA will support; and

    - processes for selection and agreement of future LANGOCA interventions.

  - program budget broken down by year and intervention;

  - program monitoring and evaluation performance framework (including Program Logframe); and

  - identification of likely risk areas and an assessment of their importance and controllability.

- Based upon PDD structure, draft an MOU incorporating key information, Roles and Responsibilities, expected inputs, and the governance framework as a basis for negotiation with GoL counterparts.

- Present each major iteration of the design and MoU to stakeholders and incorporate feedback, including up to three in country missions.

- Deliver the final Program Design Document within one week of receipt of final AusAID comments on the draft design document; submit a revised final design document.

- Prepare a final MoU(s), or similar, which will govern operations between AusAID, NGOs and the GoL.

- Provide an Aide Memoire to record the activities and outcomes following each in-country mission. And,

- Provide recommendations on how to progress the NGO concepts to implementation stage, including a generic process and suggested TORs for further design, if required.

### Design team composition

The design team will include two core members a Program Design Consultant and a Program Management Consultant.

### Reporting

The design team shall produce the following:

    - A program priorities options paper (no more than 5 pages) identifying key program priorities based on the findings of the analytical mission report to be provided to AusAID by 3 August 2006.

    - A program management options paper document (no more than 5 pages) identifying key proposed elements of the LANGOCA management and governance based on the findings of the analytical mission report and similar Program designs to be provided to AusAID by 3 August 2006.

    - A brief report summarising the outcomes of the Melbourne meeting with LANGOCA NGOs to be held on 7 August 2006.  This report will be provided to AusAID by 10 August 2006.

    - Draft program design document prepared.  This will include a summary of the proposed interventions to be included in the LANGOCA program design, key proposed elements of LANGOCA management, an outline of a program logframe and an outline of a performance management framework.  This report will be provided to AusAID by 18 September 2006 and then circulated to stakeholders.

    - In-country mission (27-28 September) and revision of draft program design document (and draft MoU). This report will be provided to AusAID by 6 October 2006.

    - Attend peer review on 25 October 2006.

    - A revised draft program design document incorporating the advice provided during the peer review process.   This report will be provided to AusAID by 1 November 2006.

    - In-country validation visit (16 and 17 Nov).

    - A finalised program design document incorporating feedback received during the in-country validation workshop for key stakeholders.  This report will be provided to AusAID by 23 December 2006.

All documentation will be provided to AusAID in both hard copy (one copy) and digital (Microsoft Office 2003) formats.

### Key Background Documents

The following documents were provided to the design team:

    - LANGOCA Analytical Mission Report

    - AusAID appraisal of draft LANGOCA Analytical Mission Report

    - LANGOCA detailed timeline (as at 24 July and subject to change)

    - A chronicle of main LANGOCA discussions

    - Report of the LANGOCA Analytical Mission debrief

    - The Laos Australia Development Cooperation Program Strategy 2004-2010

    - A short breakdown of the budgeting structure

    - Minutes from LANGOCA meeting of the NGOs in Laos on 11 July

    - Minutes from LANGOCA  meeting of the NGOs in Australia on 14 July

    - AusGUIDE Part 3B - Preparing activity designs and relevant AusGUIDElines (refer http://www.ausaid.gov.au/ausguide/)

Attachment 2

# Persons Consulted during Design

| Name | Position | Organisation |
| --- | --- | --- |
| Dr Bountheuang Mounlasy | Director General, Department of International Cooperation | Ministry of Foreign Affairs |
| Mr Phonesavanh Chanthavilay | Deputy Director General, Department of International Organizations | Ministry of Foreign Affairs |
| Madame Vansy Vilignaphone | Director of NGO Division, Department of International Organizations | Ministry of Foreign Affairs |
| Mr Phetsamone Keorongvichith | Official, Department of International Organizations | Ministry of Foreign Affairs |
| Mr Rob McGregor | Program Manager – Laos Mekong Section | AusAID, Canberra |
| Mr Michael Hassett | First Secretary | AusAID, Vientiane |
| Mr Paul Mitchell | Laos Program | AusAID, Canberra |
| Mr Warren Hoye | Program Manager | AusAID, Vientiane |
| Ms Rakounna Sisaleumsak | Program Officer | AusAID, Vientiane |
| Ms Sounisa Sundara | Program Assistant | AusAID, Vientiane |
| Mr Leigh Vickery | Country Program Director | SCA, Vientiane |
| Mr Loy Rego | Director and Team Leader, Disaster Management Systems | ADPC |
| Mr Khamlouang Keoka | Country Representative | OXFAM, Vientiane |
| Ms Nami Nelson | Program Coordinator | Care Laos |
| Mr Frank Reimann | Country Director | Care Laos |
| Mr Tony Fish | Program Manager | FSD |
| Mr Stephen Rozario | National Director | World Vision, Vientiane |
| Mr Prasanna De Silva | Director - Operation | World Vision, Vientiane |
| Mr Phearak Svay | Program Officer | World Vision, Melbourne |
| Ms Jo Durham | Country Program Manager | MAG, Laos |
| Mr Jamie Franklin | Program Officer | MAG, Laos |
| Ms Lee FitzRoy | Program Coordinator, East Asia | Oxfam, Melbourne |
| Ms Catherine Johnston | Asia Team Leader | World Vision, Melbourne |
| Ms Cathy Boyle | Senior Program Officer | CARE, Canberra |
| Mr Luc Delneuville | Independent UXO Consultant | Vientiane |
| Ms Kathryn Sweet | Independent Disaster Management Consultant | Vientiane |
| Ms Kate Bunbury |  | SCA, Melbourne |
| Ms Cecilia Valla |  | CARE, Canberra |
| Ms Sarah Morgan | Program Development Advisor | SCA, Vientiane |
| Ms Judith Ascroft | Asia Regional Manager | SCA, Phnom Penh |

Attachment 3

# Timeline for LANGOCA Design Process and Start Up

| Date | Activity | Comments |
| --- | --- | --- |
| December 2005 | Cooperation Agreements signed | Cooperation Agreements signed with CARE, SCA, World Vision (2) and Oxfam. |
| 2-15 May 2006 | Analytical Mission undertaken | The mission examined the linkages between vulnerability reduction, disaster mitigation/risk reduction, UXOs and crosscutting issues such as gender, ethnicity, HIV/AIDS, capacity building and environment. The final report provided the rationale for developing an integrated framework, including a Matrix of Options, for future joint AusAID and NGO interventions to reduce vulnerability to UXO and disaster management. |
| 28 Jun 2006 | AM Stakeholder Validation Workshop in Vientiane | Validation of AM findings and Options Matrix. |
| 19 Jul 2006 | AM Debrief Meeting in Canberra | Debrief prior to finalising the AM Report. |
| July 2006 | Design consultants appointed | Two design consultants were appointed on a part-time basis to undertake a consultative process to prepare a Program Design Document. |
| 4 Aug 2006 | Options Paper prepared on the Program management arrangements | The Options Paper was subsequently discussed in Melbourne on 7 August. |
| 7 Aug 2006 | Melbourne workshop | Meeting held with NGO partners to discuss Program management options. A report was prepared summarising the proposed management arrangements (8 August) and outlining the format required for Concept Notes (which described the individual activities that NGOs planned to undertake). |
| 28 Aug 2006 (LT) 4 Sep 2006 (ST) | Draft Concept Notes submitted to AusAID | An Appraisal Report was prepared based on an appraisal of the Concept Notes by independent technical advisors, AusAID and the design consultants. The report provided recommendations on how the Concept Notes could be improved, and was discussed in Vientiane on 27-28 September. |
| 18 Sep 2006 | Preliminary draft PDD prepared and circulated | A preliminary draft PDD was prepared for discussion in Vientiane on 27-28 September. It contained two main options for the Program management arrangements (reflecting comments received from NGOs and AusAID since the Melbourne meeting). |
| 27-28 Sep 2006 | Vientiane workshop | Meeting held with NGO partners to discuss the Program design and the initial appraisal of the draft Concept Notes. Extensive discussions were held on the allocation of the available budget. Key government personnel were not available to attend the workshop although a meeting was held with MFA to discuss the Program and design process. |
| 2 Oct 2006 | Workshop Report circulated | A report of the workshop was produced summarising the main points of agreement, outlining a revised design process timeframe, and outlining criteria to prioritise Concept Notes. |
| 13 Oct 2006 | NGOs submitted revised Concept Notes to AusAID (16 October for WV) |  |
| 20 Oct 2006 | Appraisal Report submitted to AusAID |  |
| 24 Oct 2006 | AusAID confirms Concept Notes to be included in the Program Design Document, and Appraisal Report circulated to NGOs | AusAID confirmed the Concept Notes and their budgets following discussions with CARE. |
| 30 Oct 2006 | Draft PDD prepared and submitted to AusAID |  |
| 2 Nov 2006 | Draft PDD submitted to GoL and circulated among NGOs |  |
| 14 Nov 2006 | Vientiane workshop: Draft PDD review | The workshop included GoL (NDMO and NRA), AusAID and NGO partners, and provided an opportunity to review the PDD. |
| 20 Nov 2006 | Revised Draft PDD submitted to AusAID | The revised draft PDD will be forwarded to GoL, NGOs, external appraisers and members of AusAID’s Peer Review. |
| 6 Dec 2006 | Peer Review of the Draft PDD |  |
| 13 Dec 2006 | Final PDD submitted to AusAID Draft Subsidiary Arrangement prepared | NGOs will also be required to submit a one page design summary (including costs) to AusAID by this date. |
| 20-Dec-2006 | AusAID finalises Service Orders with LANGOCA NGOs for activity designs | NGOs will be able to commence activity designs. |
| 17-Jan-2007 | First ADD submission date Subsidiary Arrangement signed by GoA and GoL AusAID prepares tender documents for the Secretariat | This is the first of two opportunities to submit ADDs for the first financial year. AusAID organises appraisals as required, in consultation with PCC. |
| 29-Jan-2007 | ADD appraisal commences |  |
| 2-Feb-2007 | ADD appraisal concludes |  |
| 9-Feb-2007 | First PCC held and first group of ADDs approved |  |
| 14-Feb-2007 | AusAID confirms contractual arrangements with NGOs and implementation of first group of activities commences |  |
| 9-Mar-2007 | Second ADD submission date AusAID appoints and establishes Secretariat | AusAID organises appraisals as required, in consultation with PCC. |
| 11-Mar-2007 | ADD appraisal commences |  |
| 15-Mar-2007 | ADD appraisal concludes |  |
| 22-Mar-2007 | First PIC meeting held | TOR for PIC reviewed, chair selected, recommendations made for first year of LANGOCA Program prepared for PCC (including summary of activity designs and activities relating to Component 3, including Workshops, publications, other inputs). |
| 29-Mar-2007 | Second PCC meeting held | 1st year of LANGOCA Program finalised, including the second group of ADDs. |
| 2-Apr-2007 | AusAID confirms contractual arrangements with NGOs | Implementation of second group of activities commences. |

Attachment 4

# Logical Framework Matrix

| Narrative | Indicators | Means of Verification | Responsibility | Assumptions |
| --- | --- | --- | --- | --- |
| Goal To reduce the vulnerability of the poor by integrating poverty reduction and crosscutting issues with disaster management and UXO approaches in Laos | - Evidence of activities being replicated, lessons learned being applied more broadly, or specific policy recommendations being accepted as a result of LANGOCA activities - Assessment of the effectiveness of integrating crosscutting issues into disaster management and UXO approaches included in the LANGOCA program - Assessment of the effectiveness of the integrated disaster management and UXO approaches included in the LANGOCA program - Assessment of the level of disaster management and UXO support provided to poor districts - Number of poor people benefiting, and extent of these benefits (in terms of livelihood impacts), as a direct result of LANGOCA activities | - MTR and PCR - Activity Completion Reports - Annual Program Assessment Report - GoL poverty data and/ or activity-specific baseline and impact assessment surveys | - PCC - NDMO, NRA - PIC - Individual NGOs | - Best practice models are adopted by other stakeholders - GoA and GoL approval processes do not unduly delay implementation - There will be effective coordination between key stakeholders - Livelihoods can be measured effectively; impacts can be demonstrated over a relatively short period of time; and impacts can be attributed to LANGOCA activities |
| Component 1 Disaster Management Objective: To reduce the impact of natural and man-made disasters | - Increased capacity of national, provincial, district and village disaster management agencies to provide assistance and respond to disasters (eg. national policies and action plans, improved communications, coordination, technical knowledge and skills) - Enhanced capacity of NDMO - Increased capacity of communities to plan for and respond to disasters (eg. improved knowledge, plans, infrastructure) - Increased livelihood opportunities for communities, arising from disaster management activities. | - Activity Completion Reports - MTR and PCR - Annual Program Assessment Reports | - NDMO - PCC - PIC - NGOs | - NDMO’s engagement in LANGOCA is not constrained by a lack of resources or other commitments - There will be effective coordination across the sector - Additional short term activities are identified and adequate designs developed - Refer to each Activity Design Document for assumptions linking the individual activity to the component level indicators |
| Output 1.1 Long and short term activities implemented effectively - Oxfam: Drought in Upland Communities: An integrated Program Response (Saravan, Sekong and Vientiane Provinces) - SCA: Sayaboury Integrated Hazard Mitigation Project (Sayaboury Province) - WV: Community Based Disaster Risk Reduction (Khammouane Province) - SCA: Tools for District Risk Assessment (Sayaboury Province) - SCA: Disaster Risk Education for Children (Sayaboury Province) | - Refer to each Activity Design Document for specific indicators | - Six Monthly Progress Reports - Activity Completion Reports - MTR and PCR - Annual Program Assessment Reports | - NDMO - PCC - PIC - NGOs | - Implementation effectiveness is not reduced as a result of GoL approval processes, GoL resources, natural or man-made disasters or management arrangements between NGOs and their partners |
| Component 2 Unexploded Ordnance Objective: To reduce the impact of unexploded ordnance | - Increased area of land released for development - Livelihood opportunities arising from land clearance, UXO risk education and survivor support activities - Improved knowledge and awareness on UXO risk - Improved support for UXO survivors (economic, psycho-social, trauma counselling, vocational training, employment) - Enhanced capacity of NRA - Increased capacity of national, provincial and village UXO agencies to address the impact of UXOs (eg. national policies and action plans, improved communications, coordination, technical knowledge and skills) | - Activity Completion Reports - MTR and PCR - Annual Program Assessment Reports | - NRA - PCC - PIC - NGOs | - NRA’s engagement in LANGOCA is not constrained by a lack of resources or other commitments - There will be effective coordination across the sector - Increased clearance costs do not adversely affect activity implementation - Additional short term activities and develop adequate designs for them - Refer to each Activity Design Document for assumptions linking the individual activity to the component level indicators |
| Output 2.1 Long and short term activities implemented effectively - CARE: Reducing UXO Risk and Improving Livelihoods of Ethnic Communities in Sekong Province - WV: Integrated UXO Action Project (Khammouane Province) | - Refer to each Activity Design Document for specific indicators | - Six Monthly Progress Reports - Activity Completion Reports - MTR and PCR - Annual Program Assessment Reports | - NRA - PCC - PIC - NGOs | - Implementation effectiveness is not reduced as a result of GoL approval processes, GoL resources, natural or man-made disasters or management arrangements between NGOs and their partners - Increased clearance costs do not adversely affect activity implementation |
| Component 3 Program Development Objective: To build and promote Program capacity | - Degree to which LANGOCA activities adequately address crosscutting issues and utilise an effective integrated approach | - MTR and PCR - Annual Program Assessment Reports - Six Monthly Progress Reports | - PCC - PIC - NGOs | - Best practice models are adopted by Program partners - Crosscutting issues are effectively integrated within LANGOCA activities - There will be effective coordination between key stakeholders |
| Output 3.1 Best practice models developed for the integration of crosscutting issues in disaster management and UXO activities - CARE: Effective Programming Models Working with Vulnerable Ethnic Groups in Laos (Sekong, Sayaboury and Luang Prabang Provinces) | - Appropriate research identified, completed and results disseminated | - Activity Completion Reports - MTR and PCR | - PIC - PCC | - PCC, NGOs, NDMO and NRA are able to identify and develop appropriate activities to enhance knowledge of crosscutting issues |
| Output 3.2 Best practice applied within LANGOCA on the integration of crosscutting issues in disaster management and UXO activities | - Degree to which crosscutting issues have been effectively integrated with disaster management and UXO activities | - Activity assessments by independent technical advisors - MTR and PCR | - PIC - PCC | - PCC, NGOs, NDMO and NRA are able to identify areas in which they require support for the integration of crosscutting issues |
| Output 3.3 Effective coordination between LANGOCA NGOs and key stakeholders in the disaster management and UXO sectors | - Evidence of effective coordination between LANGOCA NGOs and other key stakeholders | - Workshop Reports - Participation in sector and technical working groups - MTR and PCR | - PCC - PIC - Secretariat | - There will be effective coordination across the sector - Appropriate TA can be accessed - Sector stakeholders are able to participate and contribute effectively during Workshops |
| Output 3.4 Best practice, strategic planning and policy options for the disaster management and UXO sectors highlighted and promoted | - Evidence of best practice, strategic planning and policy options (including those relating to the integration of crosscutting issues) being (i) documented and (ii) promoted among technicians, practitioners, donors and government | - Workshop Reports - MTR and PCR - Participation in sector and technical working groups | - NDMO, NRA - PCC, PIC | - Sector stakeholders are able to participate and contribute effectively during strategic planning and policy dialogue |
| Component 4 Program Management Objective: To manage the Program effectively | - Program activities delivered on time and within budget. | - LANGOCA Annual Plans - MTR and PCR - Six Monthly Progress Reports | - PCC - NGOs | - The MOU between GoA and GoL provides a sufficient platform for activities to be undertaken - The Service Orders between AusAID and the NGOs provide a sufficient platform for activities to be undertaken |
| Output 4.1 Effective leadership provided by the PCC | - Evidence of strategic planning, activity approval, budget management, donor harmonisation and program promotion undertaken on a timely basis | - PCC Minutes - Annual LANGOCA Summary - MTR and PCR | - PCC | - GoA and GoL meet as and when required |
| Output 4.2 Activities effectively coordinated between LANGOCA NGOs and other key stakeholders | - Evidence of information sharing, activity coordination, discussion on program strategies and best practice undertaken on a regular basis | - PIC Minutes (including presentations to the PCC) - Workshop Reports | - PIC, Secretariat - NDMO, NRA (in addition to their role in the PIC) | - LANGOCA NGOs, NDMO and NRA agree to provide the level of resources required for the PIC to undertake the tasks required of it |
| Output 4.3 Effective and efficient administrative program support provided by the Secretariat | - Assessment of the quality of administration support provided | - PCC Minutes - MTR and PCR | - PCC | - A suitable organisation can be contracted within Laos to provide secretariat services |
| Output 4.4 Activity performance monitored: - M&E of individual activities - Contract monitoring | - Refer Outputs 1.1, 2.1 and 3.1 - Activity assessments completed as and when required | - Six Monthly Progress Reports - Additional Activity Monitoring Reports - Activity Completion Reports - MTR and PCR | - NGOs - PCC - AusAID | - AusAID Post has sufficient resources to manage the contracts with each NGO - Suitable TA can be contracted to undertake annual assessments, MTR and PCR |
| Output 4.5 Program performance evaluated on a periodic basis | - Program assessments completed | - Annual Program Assessment Reports - Activity Completion Reports - MTR and PCR | - PCC | - Suitable TA can be contracted to undertake annual assessments, MTR and PCR |

Attachment 5

# LANGOCA Activity Design, Appraisal Criteria and Reporting Proformas

## A.  Activity Design Document Proforma

The Activity Design Documents (ADDs) serve two primary purposes. The first is to provide a complete description of the activity, and the second is to provide additional implementation and cost details covering the initial financial year, to avoid the need for a separate annual plan during the first year. ADDs will be submitted to the PCC for approval.

The ADDs will be similar to the Concept Notes (prepared for the initial portfolio of activities and presented in Volume 2), but provide further clarification than was possible during the preparation of the Concept Notes, and outline in further detail the activities and costs for the initial financial year.

The same proforma shall be used for both long and short term activities. However, it would be expected that less information will be required for short term ADDs.

Indicative length: Short term ADDs 5-10 pages, Long term ADDs 10-20 pages

1. Conceptual Framework and Problem Analysis

- Activity Summary

- Problem Analysis

- Rationale

- How the activity fits with the Analytical Mission outcomes: including its situational analysis, options for activities (i.e. coordination, policy, capacity building, community based projects) and cross cutting issues

- Linkages with GoL and donor national, provincial and/or district programs and priorities

- Relevant expertise and experience to undertake the activity (this should include the expertise and experience of the NGO and partner organisation, and sub-contracted technical expertise, if required)

- Program structure

- How does the activity fit within the Program structure

- Key Assumptions and Risks

2. Partners and Coordination

- Partners

- Linkages to other LANGOCA activities

- Other Stakeholders

- Government, communities, others (including other INGOs, Multilaterals, Not for Profit Associations, etc)

- Management and coordination arrangements, including relationships with GoL at all levels and other partners (eg. other NGOs, UN, etc).

3. Activity Description

- Goal and Objectives

- Location(s)

- Target Groups and beneficiaries

- Duration and phasing (start and end dates, relationships to other LANGOCA activities)

- Outcomes and key outputs

- Implementation process

- How does the activity contribute to the areas of coordination, policy, capacity building and community-based support?

- How will crosscutting issues be integrated and mainstreamed?

- Sustainability strategies and risk factors

- M&E framework, including baseline data to be collected and means/ method of collection, and performance indicators (including indicators that link the activity to the component objectives)

It is recommended that a Risk Management Matrix and M&E Framework are included in the ADD (for guidance refer to AusGuidelines).

4. Feasibility

- Brief narrative on feasibility and validity of assumptions (e.g. in terms of the available budget, the human resource requirements, the timeframe and expected contributions from other partners and the GoL)

5. Time Frame

- Including design, implementation start and completion

6. Budget

- The budget should include, and specify separately, the activity design costs. Costs should be categorised as follows:

- Technical Assistance – international

- Technical Assistance – local

- Procurement

- Training

- Operational costs – UXO clearance

- Operational costs – infrastructure

- Operational costs – livelihood support (including UXO survivor assistance)

- Operational costs – UXO/ mine risk education

- Activity management and coordination

- In addition, the ADD should include an estimate of the total level of funding directly contributing to capacity building.

7. Description of Activities and Budget for the First Financial Year

- A summary of the main activities to be completed in the first year, a time frame for these, and a detailed cost summary will be required to avoid preparing a separate annual plan. Costs should be presented using the above cost categories.

## B.  ADD Appraisal Criteria

The ADDs will be appraised by the PCC (and independent TA) using the following criteria:

- How will the activity contribute to the Program goals/ and build on the analysis of the AM (eg. does it contribute to the areas of: coordination, policy, capacity building and community-based support, as outlined in the AM Report)?

- Does the activity have adequate links to national, provincial and/or district programs and priorities (eg. have the programs or activities of government and other agencies been acknowledged / built on)?

- Is the activity based on sound technical parameters/knowledge (or does the activity include appropriate research)?

- Has the NGO (and partners/sub-contractors) the relevant expertise and experience to design and implement the activity?

- Are crosscutting issues (gender, ethnicity, HIV/AIDS, environment and capacity building) adequately addressed in the planning and implementation of the activity?

- Has the activity location been clearly specified?

- Will the activity be effectively coordinated and managed and have appropriate links with GoL at all levels?

- Will the activity contribute effectively to donor harmonisation?

- Will the activity be sustainable?

- Does the activity propose an adequate M&E framework (including identification of baseline data and performance indicators which link the activity to the component objectives)?

- Is the activity feasible and are risks manageable in terms of the available budget, the human resource requirements, the timeframe and expected contributions from other partners and the GoL?

- Is the activity strategic at a program level?

- For short term activities, do they compliment long term activities?

## C.  Six Monthly Progress Report Proforma

Six Monthly Progress Reports will be prepared for each activity which continues beyond the period of reporting (as described below). A Six Monthly Progress Report due in September will cover the period January to June. A Six Monthly Progress Report due in March will cover the period July to December and will be incorporated within the Annual Plan. Cost information will be presented for the same six month periods.

The main focus of the Six Monthly Reports will be to briefly report on progress of the activity being implemented; that is, Component 1 or 2, as relevant. NGOs will also be asked to provide some commentary on the contribution which the activity makes to Component 3 and 4 objectives.

Indicative length: 5-6 pages

1. Main Achievements by Component and Output

- Component 1/ Component 2

- Component 3 (by output)

- Component 4 (by output)

2. Activity Management and Coordination

- A brief summary of management and coordination arrangements and their effectiveness

3. Issues and Problems

- Identification of key implementation issues, constraints and strategies for remedial action

- Component 1/ Component 2

- Component 3

- Component 4

4. Activity Monitoring and Evaluation

- A brief summary of monitoring and evaluation events (eg. baseline data collected)

- Reporting against performance indicators

5. Recommendations

- A brief description of any recommended changes for implementation of the activity during the next six months

6. Financial Summary

- Costs should be categorised as follows:

- Technical Assistance – international

- Technical Assistance – local

- Procurement

- Training

- Operational costs – UXO clearance

- Operational costs – infrastructure

- Operational costs – livelihood support (including UXO survivor assistance)

- Operational costs – UXO/ mine risk education

- Activity management and coordination

## D.  Annual Plan Proforma

For each activity extending beyond the initial financial year, an annual plan will be required summarising progress and outlining the main activities, inputs and costs required for the next financial year. The Annual Plan provides an opportunity to refine the activity from its original design. The Annual Plan incorporates a Six Monthly Progress Report (for the period July to December).

Indicative length: 10 pages

A. Report on Progress for the Previous Six Monthly Period

1. Main Achievements by Component and Output

- Component 1/ Component 2

- Component 3 (by output)

- Component 4 (by output)

2. Activity Management and Coordination

- A brief summary of management and coordination arrangements and their effectiveness

3. Issues and Problems

- Identification of key implementation issues, constraints and strategies for remedial action

- Component 1/ Component 2

- Component 3

- Component 4

4. Activity Monitoring and Evaluation

- A brief summary of monitoring and evaluation events (eg. baseline data collected)

- Reporting against performance indicators

5. Financial Summary for the Previous Six Monthly Period

- Costs should be categorised as described for the ADDs and Six Monthly Reports

B. Annual Plan

6. Recommendations

- A brief description of any recommended changes for implementation of the activity during the next financial year

7. Description of Activities and Budget for the Next Financial Year

- A summary of the main activities to be completed in the next financial year, a time frame for these, and a detailed cost summary (using the same cost categories as the ADDs and Six Monthly Progress Reports)

## E.  Activity Completion Report Proforma

The ACR includes a report on progress for the previous six months (to avoid a separate Six Monthly Report being prepared) and a report for the entire activity, which includes an assessment of the main achievements, the likely impact, significant constraints, lessons learned and opportunities for new activities or replication. The ACR will also contain a cost summary.

Indicative length: Short term activities 10-15 pages, Long term activities 15-20 pages

A. Report on Progress for the Previous Six Monthly Period

1. Main Achievements by Component and Output

- Component 1/ Component 2

- Component 3 (by output)

- Component 4 (by output)

2. Activity Management and Coordination

- A brief summary of management and coordination arrangements and their effectiveness

3. Issues and Problems

- Summary of key implementation issues, constraints and strategies for remedial action

- Component 1/ Component 2

- Component 3

- Component 4

4. Activity Monitoring and Evaluation

- A brief summary of monitoring and evaluation events (eg. baseline data collected)

- Reporting against performance indicators

5. Financial Summary for the Previous Six Monthly Period

- Costs should be categorised as described for the ADDs and Six Monthly Reports

B. Activity Completion

6. Main Achievements by Goal, Component and Output

- Contribution to Activity goal

- Contribution to Program goal

- Contribution to Component 1/ Component 2 objectives

- Contribution to Component 3 objectives

- Contribution to Component 4 objectives

7. Lessons Learned

- A brief description of any recommended changes for implementation of the activity during the next six months

8. Opportunities for New Activities or Replication

- A description of recommendations for possible opportunities for replication and/ or new short term activities

9. Financial Summary

- Costs should be categorised as described for the ADDs and Six Monthly Reports for the entire activity duration

- In addition, an estimate of the total level of funding directly contributing to capacity building should be included in the ACR.

Attachment 6

# Draft TOR for PCC, PIC, Secretariat, Technical Advisors and the Annual Program Assessment

## A.  Draft TOR: Program Coordination Committee

### Roles and Responsibilities

The PCC is the key decision making body for the Program and will consist of representatives from MFA and AusAID. The PCC will be co-chaired by MFA and AusAID. The PCC will have prime responsibility for (i) the approval of activities and activity budgets, (ii) ensuring LANGOCA remains strategically focused, iii) providing overcite of program outcomes and quality, including further specification of indicators to assess Program impact and any other changes to the Logframe, as required and (iv) resolving (when possible) any significant problems. More specifically, the PCC will:

- Assess ADDs (using the appraisal criteria presented in Attachment 5) and draft Annual LANGOCA Program Summaries and decide on the activities and activity budgets for the following financial year (thereby directing the focus of the Program);

- Review the implementation of approved activities and provide advice to the PIC in regard to GoA/ GoL priorities, emerging challenges and new opportunities (thereby influencing the strategies of both the Disaster Management and UXO components);

- Provide overcite for monitoring of program outcomes and quality, including further specification of indicators to assess Program impact and any other changes to the Logframe, as required;

- Identify the need for independent TA and prepare TOR or Tasking Notes for TA inputs;

- Provide recommendations to the PIC in terms of its roles and responsibilities;

- Provide direction to the Secretariat in terms of the support it provides to the PCC and PIC;

- Maintain dialogue and build relationships with the GoL, NGO partners and other key stakeholders to support their inputs to the Program;

- Take the lead in the resolution of any disputes that arise during the planning or implementation of activities;

- Prepare TOR for the MTR and PCR Report and provide input to these teams;

- Encourage a culture of coordination, collaboration, innovation and high performance within the Program; and

- Identify opportunities to promote the Program and its achievements, including the presentation – when appropriate – of results and recommendations that may influence disaster management or UXO policies in Laos.

### Operating Guidelines

The PCC will meet at least every six months (more frequently if required). One meeting will be held in November, at which time the PCC will provide strategic direction to the Program and an indication as to the level of funding available to the Program in the following financial year. The PCC will also meet in March to review new activity designs and annual work plans (for ongoing activities) and confirm the allocation of funds for the following financial year.

The Minutes of each meeting will be kept including a clear record of all decisions made.  The Minutes will be circulated to all members for comment within 5 working days, then revised as necessary.

The Chair of the PIC will be invited to brief the PCC on discussions at the PIC summarising discussions held on program progress and recommendations made in terms of strategic direction and priority activities.  This briefing will draw on an approved written record of the PIC meeting.  This will assist the PCC members to maintain regular contact with Program partners and keep abreast of activity implementation. After providing the PIC meeting briefing to the PCC the PIC chair will withdraw from the remainder of PCC discussions thus avoiding potential conflict of interest issues.  Other members of the PIC, implementation team members or independent TA may also, from time to time, be invited to attend PCC meetings. The PCC will also be provided with Secretariat support.

The PCC is expected to review and finalise these TOR in its inaugural meeting, and make subsequent changes as required, to ensure the PCC remains an effective decision making body.

## B.  Draft TOR: Program Implementation Committee

### Roles and Responsibilities

The PIC aims to strengthen linkages between Program partners, improve coordination, share ideas and information, and provide input to Program strategies and planning, including further specification of indicators to assess Program impact and any other recommended changes to the Logframe, as required. The PIC shall comprise one representative from each of the participating NGOs and one representative each from AusAID, NDMO and NRA as core members, plus NGO partners, provincial representatives and other line ministries/ agencies in an advisory capacity, as required.

The PIC will:

- Prepare a draft Annual LANGOCA Program Summary for submission to the PCC, which will include:

- A brief description of each activity and the budget for each activity over the next financial year;

- Proposed technical assistance or training inputs (refer Output 3.2);

- Recommendations for the annual workshops (refer Output 3.3), including the proposed dates, linkages to existing sectoral workshops/ meetings, and inputs to be provided through LANGOCA;

- Proposed publications to highlight best practice (refer Output 3.4);

- A schedule of dates for key sectoral coordination meetings (in addition to the annual workshop) and PIC and PCC meetings;

- Suggestions for highlighting and promoting the Program;

- Any other recommendations for consideration by the PCC;

- Finalise the indicators to assess the impact of individual activities and the Program as a whole, define carefully and outline how each indicator will be measured (to ensure a consistent approach);

- Identify issues that need to be addressed by the PCC;

- Work with the Secretariat in terms of overall Program administration;

- If required, provide recommendations to the PCC concerning the need for technical and strategic advice (which could include advice regarding the preparation of draft TOR for advisory inputs for consideration by the PCC);

- Maintain dialogue and build relationships with the GoL, NGO partners and other key stakeholders to support their inputs to the Program;

- Provide input to the MTR and the team preparing the PCR;

- Provide input, as appropriate, to other teams/agencies working in the disaster management, UXO or other related sectors; and

- Encourage a culture of coordination, collaboration, innovation and high performance.

Participation by NDMO and NRA in the PIC will ensure effective coordination on behalf of the GoL, and assist in facilitating coordination across all levels of government (national, provincial, district and village) and assist in identification of priorities for the LANGOCA Program.

Participation by Provincial Government representatives in the PIC (during one meeting each year) will strengthen linkages between the Program and the implementation of individual activities and provide support for an integrated, multisectoral approach, including crosscutting issues, across all levels of government.

### Operating Guidelines

It is anticipated that the PIC will meet at least every 6 months (and more frequently when required), generally a week or two prior to meetings of the PCC. This will enable reports and recommendations to be prepared for presentation to the PCC.

The chair of the PIC will be rotated between the 4 participating NGO representatives. The meeting agenda will be drafted by the chair, in consultation with the other members. The Minutes of each meeting will be kept including a clear record of all decisions made.  The Minutes will be circulated to all members for comment within 5 working days, then revised as necessary.

The PIC will be provided with Secretariat support. The Secretariat will maintain close contact with each of the PIC members throughout the life of the Program.

The PIC is expected to review and finalise these TOR in its inaugural meeting, and make subsequent changes as required, to ensure the PIC remains an effective coordination body.

## C.  Draft TOR: LANGOCA Secretariat

### Roles and Responsibilities

The Secretariat will be contracted by, and will be answerable to, AusAID Post. However, the Secretariat’s primary role is to support the PCC and PIC with a range of coordination, management, reporting and other administrative functions. To provide effective support to the PCC and PIC, and enable close collaboration with NGOs and other partners, the Secretariat will establish and maintain an office in Vientiane for the duration of the Program.

The key functions of the Secretariat will be to:

- Provide administrative and logistical support to the Program (although not to individual activities funded within the Program, which will be managed by the NGOs and their partners);

- Provide secretariat support to the PCC and PIC (including the recording and circulation of Minutes);

- Assist in the preparation and finalisation of Annual LANGOCA Program Summaries and circulate as appropriate;

- Assist in contracting TA and provide logistical and administrative support to TA, the MTR and PCR;

- Organise Workshops and other meetings as tasked by the PCC;

- Manage an activity account from which the cost of PCC and PIC meetings, workshops, selected transport costs for external advisors, etc., will be met;

- Organise translation services if required at a Program level (although translation requirements for individual activities will be organised and managed by the NGOs and their partners); and

- Organise publications and promotional materials as directed by the PCC.

### Operating Guidelines

The Secretariat is expected to maintain a permanent presence in Laos and maintain an office during regular business hours. The Secretariat’s work program will mostly be determined by the PCC, as well as responding to AusAID in between scheduled meetings, as directed through the LANGOCA Activity Manager. The Secretariat will need to establish a good working relationship with the members of the PCC and PIC. It is anticipated that the Secretariat will provide inputs on a part time basis.

### Skills Required

The Secretariat is expected to have expertise in the following areas:

- Information dissemination/ knowledge management (including information technology);

- Report writing;

- Logistics;

- Capacity to contract services and technical expertise;

- Finance and budgeting;

- Organisation and facilitation;

- Coordination and communications; and

- Liaison with AusAID, GoL and other key stakeholders.

## D.  Generic TOR: Technical Advisors

### Roles and Responsibilities

Technical and strategic advice will in general be provided to both the PCC and PIC, and will work closely with NDMO, NRA, LANGOCA NGOs and partners. The advisors may be required to:

- Review ADDs, activity progress and Annual Plans;

- Prepare the Annual Program Assessment Report and present a summary at Workshops;

- Provide advice in terms of either gaps or opportunities within either the disaster management or UXO sectors and the Program as a whole;

- Provide advice or comment to the PCC, PIC, MTR or PCR teams on general progress of the disaster management or UXO sectors, or on specific activities.

The technical and strategic advisors will preferably play a supportive role during Program implementation, by providing advice and working with the NGOs, to improve the activities being implemented, supporting LANGOCA priorities, and encouraging effective coordination.

### Skills Required

Technical advisors will be expected to have sound technical knowledge in their respective sectors and be familiar with disaster management or UXO programs and activities in Laos.

Strategic advisors will be expected to have detailed knowledge of program management, planning and performance assessment, and proven capacity to provide strategic advice at the Program level.

Technical and strategic advisors will be expected to have good interpersonal skills; proven report writing skills; and the ability to work with interpreters, if required.

## E.  Draft TOR: Annual Program Assessment

### Objectives

The Annual Program Assessment provides (i) an independent assessment of progress of individual activities and their contribution to the achievement of the goal of the Program, (ii) an analysis of the effectiveness of integrating poverty reduction and crosscutting issues in DM and UXO approaches across the Program, (iii) advice on program level performance, cohesion and management, and (iv) recommendations on strategic advice on Program directions and identification of new activities.

### Tasks

The Annual Program Assessment will include:

- A brief review of ADDs, Six Monthly Progress Reports, Annual Plans, Activity Completion Reports and Annual LANGOCA Program Summary, as relevant;

- Field visits to selected activities, including consultations with key stakeholders (eg. NDMO, NRA, Provincial Steering Committees, community representatives);

- Presentation of a brief assessment of progress at Workshop and participation in Workshop discussions and the subsequent PIC meeting, as required; and

- Preparation of an Annual Program Assessment Report (to be submitted to the PCC).

### Skills Required

Technical advisors participating in the Annual Program Assessment will be expected to have:

- Sound technical knowledge in DM or UXO sectors and familiarity with current programs and activities in Laos;

- An understanding of crosscutting issues and their integration in DM and UXO activities;

- Detailed knowledge of program management, planning and performance assessment; and

- Proven capacity to provide practical advice at the activity level, and strategic advice at the Program level.

Attachment 7

# Implementation Schedule

| Financial Year | 2006/7 | 2007/8 |  |  |  | 2008/9 |  |  |  | 2009/10 |  |  |  | 2010/11 |  |  |  | 2011/12 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Quarter | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Component 1: Disaster Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 Initial activities: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Oxfam: Drought in Upland Communities: An integrated Program Response |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |
| - SCA: Sayaboury Integrated Hazard Mitigation Project |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |
| - WV: Community Based Disaster Risk Reduction |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |
| - SCA: Tools for District Risk Assessment |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - SCA: Disaster Risk Education for Children |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2: Unexploded Ordnance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1 Initial activities: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - CARE: Reducing UXO Risk and Improving Livelihoods of Ethnic Communities in Sekong Province |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |
| - WV: Integrated UXO Action Project |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |
| Component 3: Program Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - CARE: Effective Programming Models Working with Vulnerable Ethnic Groups in Laos |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3 – Workshops |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |
| Component 4: Program Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.1 – PCC meetings | Xx |  | x | x |  |  | x | x |  |  | x | x |  |  | x | x |  |  | x | x |  |
| Output 4.2 – PIC meetings | X |  | x | x |  |  | x | x |  |  | x | x |  |  | x | x |  |  | x | x |  |
| Output 4.3 – Secretariat functioning | X | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |
| Output 4.5 – Annual Program Assessments |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |
| Output 4.5 – Mid Term Review |  |  |  |  |  |  |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |
| Output 4.5 – Program Completion Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |

NB: Several of the initial activities may commence in Q4 of 2006/7. The duration of long term activities will remain at 5 years irrespective of the commencement date.

Attachment 8

# Risk Matrix

| Risk Source | Risk Event | Impact on Program | L | C | R | Risk Mitigation | Responsibility | Timing |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Goal To reduce the vulnerability of the poor by integrating poverty reduction and crosscutting issues with disaster management and UXO approaches in Laos | Ineffective coordination across stakeholders in both sectors | Activities aren’t replicated, lessons learned aren’t applied more broadly, nor specific policy recommendations accepted | 2 | 4 | M | Promoting best practice and lessons learned through Workshops, Sectoral/ Technical Working Groups, independent technical advice; maximising input from program partners, particularly NDMO and NRA | PCC, PIC | Throughout Program |
|  | Existing policies limit the ability to implement new approaches | Lessons learned not applied more broadly, nor specific policy recommendations accepted | 3 | 3 | M | Promoting best practice and lessons learned through Workshops, Sectoral/ Technical Working Groups, independent technical advice; maximising input from program partners, particularly NDMO and NRA | PCC, PIC | Throughout Program |
|  | Unwillingness to change practice to incorporate an integrated approach including crosscutting issues | Activities will be less effective and have less impact | 3 | 4 | H | Promoting best practice and lessons, through capacity building with Program partners at all levels across sectors | PCC, PIC | Throughout Program |
|  | Vulnerabilities caused by external factors such as natural/ man-made disasters, economic downturn, increased degradation of natural resources, epidemics (bird flu, HIV/AIDS), increased population pressure, decreased livelihood opportunities. | Vulnerability increases as a result of external factors, and community less able to participate in LANGOCA activities | 3 | 4 | H | Improve coordination, communication and capacity building to address preparedness to external factors | PCC, PIC | Throughout Program |
|  | Reduced support in the longer term to the sectors from GoL and donors | Longer term impact (and benefit) of the Program will be reduced and impacts of the activities will not be sustained | 2 | 4 | H | Demonstrate best practice and lessons. Strengthen coordination and capacity at all levels. | PCC, PIC | Throughout Program |
| Component 1 Disaster Management Objective: To reduce the impact of natural and man-made disasters | NDMO unable to engage with LANGOCA due to resource constraints and/ or other commitments | Poorer coordination, limited potential for replication of lessons learned | 2 | 4 | H | Support NDMO to enhance their coordination capacity | NDMO | Throughout Program |
|  | Capacity of communities to participate effectively inhibited by external factors (as above) | Vulnerability increases as a result of external factors, and community less able to participate in LANGOCA activities | 3 | 4 | H | Improve coordination, communication and capacity building to address preparedness to external factors | NGOs, PIC NDMO | Throughout Program |
|  | Appropriate short term activities not identified | Failure to address key sector priorities and constraints | 2 | 3 | M | Coordinate with wide range of stakeholders to identify priorities ( Workshops, PIC meetings, sectoral/ technical Working Groups) | PCC, PIC NDMO NGOs | Throughout Program |
|  | Lack of coordination, capacity and resources within relevant disaster management agencies | Activities aren’t replicated, lessons learned aren’t applied more broadly, nor specific policy recommendations accepted | 2 | 4 | M | Ensure capacity building opportunities integrated appropriately into activities | PIC NDMO NGOs | Throughout Program |
|  | NGOs can not access appropriate expertise to design and/ or implement activities | Could limit the range of activities undertaken | 3 | 3 | M | NGOs are encouraged to develop partnerships to identify and access relevant expertise. The expertise and experience to design and implement activities has been included in the appraisal criteria for ADDs. | NGOs PCC | Throughout Program |
|  | Delays in GoA and GoL approval processes | Individual activities delayed and overall program impact reduced | 3 | 4 | H | Support GoA and GoL priorities, improve coordination (including NDMO capacity), and promote ownership of activities and LANGOCA Program | PCC PIC NDMO | Throughout Program |
| Component 2 Unexploded Ordnance Objective: To reduce the impact of unexploded ordnance | NRA unable to engage with LANGOCA due to resource constraints and/ or other commitments | Poorer coordination, limited potential for replication of lessons learned | 2 | 4 | H | Support NRA to enhance their coordination capacity | NRA | Throughout Program |
|  | Capacity of communities to participate effectively inhibited by external factors (as above) | Vulnerability increases as a result of external factors, and community less able to participate in LANGOCA activities | 3 | 4 | H | Improve coordination, communication and capacity building to address preparedness to external factors | NGOs, PIC NRA | Throughout Program |
|  | Appropriate short term activities not identified | Failure to address key sector priorities and constraints | 2 | 3 | M | Coordinate with wide range of stakeholders to identify priorities (Workshops, PIC meetings, sectoral/ technical Working Groups) | PCC, PIC NRA NGOs | Throughout Program |
|  | Lack of coordination, capacity and resources within relevant UXO agencies | Activities aren’t replicated, lessons learned aren’t applied more broadly, nor specific policy recommendations accepted | 2 | 4 | M | Ensure capacity building opportunities integrated appropriately into activities | PIC NRA NGOs | Throughout Program |
|  | Delays in GoA and GoL approval processes | Individual activities delayed and overall program impact reduced | 3 | 4 | H | Support GoA and GoL priorities, improve coordination (including NRA capacity), and promote ownership of activities and LANGOCA Program | PCC PIC NRA | Throughout Program |
|  | NGOs can not access appropriate expertise to design and/ or implement activities | Could limit the range of activities undertaken | 3 | 3 | M | NGOs are encouraged to develop partnerships to identify and access relevant expertise. The expertise and experience to design and implement activities has been included in the appraisal criteria for ADDs. | NGOs PCC | Throughout Program |
|  | Increased cost of clearance activities | Limits land cleared and support for additional UXO activities (eg livelihood opportunities, survivor support, mine risk education) | 4 | 3 | H | Focus on pilot activities to develop best practice. Coordinate with other stakeholders to explore opportunities to scale up activities. | NGOs PIC NRA | Throughout Program |
| Component 3 Program Development Objective: To build and promote Program capacity | Integrated approach (including poverty reduction and crosscutting issues) not implemented effectively across the Program | Activities will have less impact, models developed will be less effective in addressing vulnerability and less likely to be replicated. | 2 | 3 | L | Provide technical support, research, promote exchange of information, lessons learned and best practice through Workshops and PIC meetings. | NGOs PIC NDMO, NRA | Throughout Program |
|  | NGOs can not access appropriate expertise to design and/ or implement activities | Could limit the range of activities undertaken | 3 | 3 | M | NGOs are encouraged to develop partnerships to identify and access relevant expertise. The expertise and experience to design and implement activities has been included in the appraisal criteria for ADDs. | NGOs PCC | Throughout Program |
| Component 4 Program Management Objective: To manage the Program effectively | PIC not functioning effectively | Effective coordination across NGOs and GoL (NDMO/ NRA) will be difficult, and could limit overall Program impact Delays in activity implementation | 3 | 4 | H | Provide PIC with opportunity to contribute to Program strategy and priorities (and having a Program that is flexible and responsive). Provide adequate Secretariat and technical support. Provide support to NDMO and NRA to support their coordination capacity | PIC, PCC Secretariat NDMO/ NRA | Throughout Program |
|  | Unallocated funds spent quickly | Limits flexibility and responsiveness of Program impact | 3 | 3 | M | PCC manages funds appropriately (unallocated funds spread over the life of the Program). | PCC | Throughout Program |

The Risk Management Matrix contains an assessment of risk based on the following criteria:

L = Likelihood of occurrence (1=Rare, 2=Unlikely, 3=Possible, 4=Likely, 5=Almost certain)

C = Consequence of occurring (1=Negligible, 2=Minor, 3=Moderate, 4=Major, 5=Severe)

R = Risk level - a combination of the above two assessments (E=Extreme, H=High, M=Medium, L=Low)

Further details relating to the likelihood and consequence scores, and resulting assessment of risk level, are provided in AusGUIDElines (refer www.ausaid.gov.au/publications - Ausguide)

Australian Aid: Promoting Growth and Stability. A White Paper on the Australian Government’s Overseas Aid Program. (April 2006)

Key background documents are listed in the TOR, which is presented as Attachment 1.

Ludmilla Kwitko and Mike Finlayson were the Design Consultants engaged by AusAID to prepare the PDD.

Terminology and definitions utilised in the PDD follow the protocol established in the AM (based on the United Nations International Strategy for Disaster Reduction Secretariat Guidelines, and International Mine Action Standards Glossary of Mine Action Terms, Definitions and Abbreviations).

LACDS http://www.ausaid.gov.au/country/country.cfm?CountryID=35&Region=EastAsia.

For consistency the term Laos is used throughout the report, unless Lao or Lao PDR are officially used, or directly quoted.

A detailed Matrix of Options is presented in the AM Report (Annex 13).

Capacity building also forms a key element of long and short term activities identified in Components 1 and 2 (including capacity building at national, provincial, district and community levels).

The Program Implementation Committee (PIC) and Program Coordination Committee (PCC) are described under Component 4 Program Management. The process for identifying and requesting advice or training is outlined in further detail in Section 4.1.

Submission of ADDs in January aims to allow implementation of some activities to commence earlier (eg. some activities include infrastructure works that need to be undertaken prior to the wet season). However, it is expected that the majority of ADDs will be submitted in March.

Six Monthly Reports will not necessarily be prepared in September 2007 because the majority of activities will have only commenced implementation in July. As discussed in Section 4.6, the September Progress Report covers the period January to June. However, if some activities commence prior to July a Six Monthly Report (or Activity Completion Report for short term activities, if appropriate) will be prepared.

This and subsequent references to the financial year refers to the Australian financial year from July to June.

Australian aid program “Laos Devolved Humanitarian Program” funds will be used to augment the budget of this activity.

Government of Lao PDR. Prime Minister’s Office. No. 71/PM. Decree of the Prime Minister on the Administration of Non-Governmental Organisations (NGOs) in the Lao People’s Democratic Republic.

Government of Lao PDR. Prime Minister’s Office. No. 168/PM. Decree issued by the Prime Minister on the Management and Utilisation of Official Development Assistance ODA (Decree No. 168/PM, dated 22 November 2004).