TA 7780-LAO: National Integrated Water Resources Management Support Project

(Cofinanced by the Government of Australia and the Spanish

Cooperation Fund for Technical Assistance)

Memorandum of Understanding

Joint Mid Term Review Mission (15-20 February 2013)

# BACKGROUND

- The Asian Development Bank (ADB) and the Australian Agency for International Development (AusAID) Joint Mid Term Review (MTR) Mission (the Mission) was fielded to the Lao People’s Democratic Republic (Lao PDR) from 15 to 20 February 2013 to review the Technical Assistance (TA) 7780-LAO National Integrated Water Resources Management Support Project (the Project).

- The MTR mission reviewed overall TA implementation progress against the design and monitoring framework (DMF) targets; assessed the likelihood of achieving TA impact, outcome and outputs, and the need to restructure or reformulate the TA and, if so, the effects of this on the outcome and expected impact of the Project; revised and updated the TA DMF; reviewed and recommended adjustments to the TA implementation arrangements; and reviewed the draft annual work plan and budget for 2013.

- The Mission met the Director General of the Department of Water Resources, Ministry of Natural Resources and the Environment (DWR, MONRE), Director General of the Nam Ngum River Basin Committee Secretariat, Project Management Unit (PMU) Manager, component managers of the Project Implementation Units, TA international Integrated Water Resources Management (IWRM) advisor, and Project consultants from consulting firms Aecom, Idom and GHD. The Mission was received by Excellency Vice Minister Sisavath on 20 February 2013. The Director General, DWR chaired the wrap up meeting on 20 February 2013. The list of persons met by the Mission is provided in Appendix 1 and the Mission schedule is in Appendix 2.

- The key findings and recommendations of the Mission are summarized in this Memorandum of Understanding (MOU). The Mission requests comments from the Government by 27 February 2013. The agreements in this MOU are subject to the approval by higher authorities of the Government and ADB.

# Mission Findings

### Physical progress

- The four outputs of the Project are: Output 1 – National capacity built in IWRM; Output 2 –River basin management development; Output 3 – National groundwater management action plan prepared and Output 4 – IWRM education strengthened at the National University of Laos.

- The PMU prepared a progress report covering the period of August to December 2012, which is attached in Appendix 3.

### Output 1 National capacity built in IWRM

- Implementation progress towards DMF targets. Key progress is on the training plan which has been developed and which will be implemented in 2013. The rigorous training needs assessment (TNA) process took more time than initially envisaged, hence the DMF target that the staff would have already been participating in personal continuing professional development (CPD) programs by end 2012 is off track. However, the Mission feels that this delay is not a concern and there is adequate time to catch up by the end of TA duration. The DMF target will be revised to a more realistic target date.

- Key issues.  Original TA design and corresponding Package 1 TOR was set up to be overly process-heavy in the name of capacity building, but the main capacity that appears to be built is the improved, but still limited capacity to manage the TA itself which does not warrant the extensive and expensive resources dedicated. DWR, MONRE has requested the Mission to consider some proposed changes to the TOR of Package 1. The Mission will do so upon receipt of DWR’s request.

- The Mission learnt that the Package 1 consultants are working on a set of harmonized World Bank and ADB procurement guidelines. The Mission advised the consultants to check with ADB LRM the availability of Lao translations of ADB guidelines. The World Bank has mobilized an international expert on procurement and project administration to provide intermittent support to the PMU, and has offered that the same expert could assist on the ADB components.

- Capacity of the PMU and PIUs remains a challenge and is the source of many implementation delays.

- Priorities for 2013. The key activities to be carried out under Component 1 are related to the training plan.

- Way forward. The Mission agreed the following with DWR/MONRE and the consultant:

- Implementation of the training plan. The training plan needs to be updated to include the information ADB requires in the concept notes and the necessary budget breakdown. Once this is done, it will be the basis of approval of training activities.

- Gender action plan. DWR is such a nascent organizational unit that it is unlikely that work on the Gender Action Plan as originally designed will gain much traction. Mission however recognizes the importance of the gender aspect and will work with the ADB gender specialist staff to identify ways in which gender can be mainstreamed. Package 2 participation consultant (Idom) will also provide recommendations on how gender can be mainstreamed into river basin planning (RBP) processes and implementation.

- Asia Water Week. As part of capacity development, key PIU technical team members have indicated interest to attend Asia Water Week in Manila in March 2013. Their participation will be financed from the TA.

### Output 2 River basin management (RBM) development

- Implementation progress towards DMF targets. Idom consultants continue to support DWR and its branches in provinces (PONRE), districts (DONRE) and villages and the Nam Ngum River Basin Committee Secretariat (NNRBCS) to prepare the river basin plan. Activities held include (i) consultation with relevant MONRE departments on river basin planning processes, the state of the basin outline and stakeholder consultation guidelines; (ii) development of a workplan for December-January 2013 with five milestones to get the component back on track, including the organizing of the first meeting of the national river basin management taskforce and Nam Ngum Technical Working Group at provincial level, the organization of stakeholder workshops in the basin. DWR and its braches have been closely worked with related line agencies both in central and NNRB based on their mandates such as: data collection for NN profile development, NN IWRM Plan, RB and sub-basin modeling and WR inventory, water quality management and monitoring, water quantity monitoring, sub-basin planning and management, initiative for RB planning guidelines, various trainings and local public awareness raising, survey and prepare to establish national IWRM demonstration site in Vangvieng District, advise the proposed water management proposals from provinces and districts. In addition, the DWR’s branches have regularly reported both vertical and horizontal, especially their daily works, water related issues, etc.  The first draft of Guidelines for River Basin Plan presenting the recommended processes design and structure for the further development of the NNRB Plan was submitted to the PIU-2 in early October and discussed in specific meetings held in November and December 2012. An improved second draft was shared in January 2013. The mission requested that the TA should carefully study the role and linkage of relevant agencies in central, province, district and village as well as other stakeholders for  RB Planning and Implementation. Because this will be applied in other basins, the TA should work closely with DWR for this accomplishment. DWR has not been involved since beginning of the process while its mandate was clearly specified. Another important step towards achievement of the DMF targets concerns the Prime Minister’s Decision no.10/PM dated 29 January 2013 on the organization and activities of the Nam Ngum River Basin Committee (NNRBC). However, the new NNRBC and Secretariat mandates are unclear comparing to existing Local Administrative Law, No. 03/NA, dated 21 October 2003, MONRE Decree, PONRE and DONRE mandates. The presentation of Component 2 on implementation progress is attached as Appendix 4.

- Key issues. The component has been recently split into two subcomponents by MONRE. A Component 2.1 will cover national level policy and guidelines on river basin planning and management which coordinates with other basins in the country while Component 2.2 is the original TA design under Output 2 as well as C2.1 activities also originally support and link to the original Output 2, this is just split for clearer role between DWR (national) and basin level in order to accredit the Output 2 milestones in consistent with and effective approach for RBMP in NN and efficiently replicate the lessons from NN to others. This does not constitute any change to the original concept of Component 2 of the TA. DWR has the responsibility to lead and coordinate IWRM in Lao PDR in the basin and sub-basin scales, so the conceptual split of the Component is generally logical given the range of activities that have been included to collectively support IWRM. In practical terms, DWR is responsible for coordination with related agencies and stakeholders in the basin and nationally while NNRBCS has very general and unclear mandate to coordinate and play the legal role with local agencies in the NN basin. Because, NNRBCS has no branches in provinces and districts as well as staff in provinces and districts. NNRBC is an ad-hoc which is not in the line agencies and the Secretariat has very limited capacity with inadequate staffs to deal with the issues happened in NNRB. In addition, NNRBCS is not formally executed in the MONRE organizational structure (out of 17 departments which has no legal rights to get annual budget from MONRE based on its Mandate No. 435/PM, dated 28 November 2011. This is to make sure the continuity and sustainability once the project finished). This faced some difficulties for RBM and activity monitoring system by MONRE Department of Inspection in the past experience. Meanwhile, DWR has legal mandate which supported by its water resource section/unit in each PONRE and DONRE (vertical organization of DWR). They have very clear mandate in terms of reporting and coordinating within the respective provinces and districts agencies (horizontal line) and also with central level representing by DWR and related Departments of MONRE.  This supported the GoL policy and legislative framework, i.e. Local Administrative Law, No. 03/NA, dated 21 October 2003, PM Decree on MONRE, 3Built Policy of GoL (decentralization of responsibility to province, district and village), etc. Moreover, the DWR has very clear mandate to guide the local agencies for their IWRM planning in river basin and implementation by provinces and districts. This legal linkage is considered as an important element in administrative system of Lao PDR. Because all of the issues and solutions are direct responsibility of provinces and districts (governors is the highest position for making decision in their own areas). . The separation of Component 2 into C2.1 and C2.2 has also amplified the need for clarifications of roles. This directive appoints a new C2.1 Component Manager to provide overall DWR guidance and coordination of RBM in accordance with the DWR mandate. The PMU will advise the Mission formally of the setting up on the new PIU and its composition and TOR, and the establishment of its subaccount. Upon receipt of this advice, TA will make the financial provision for running costs for a PIU for C2.1. The Mission will then have to examine how the TA can accommodate a budget for the new activities proposed under C2.1.

- Team leader replacement. In October, DWR requested the replacement of the package 2 Team Leader (TL) for a number of reasons concerning his performance. The Idom Project Manager accompanied by a Senior Partner-Director travelled to Vientiane the following week to deal in person with the issue. Aware that under the current situation expressed by the EA representatives the continuity of the Team Leader would not help for a successful finalization of the TA, IDOM proposed an in-house expert with international background as the suitable replacement for the TL position that was accepted by DWR and ADB. The first input of the new TL commenced the 20 November 2012. The Mission appreciates the considerable effort that Idom has put into identifying an appropriate candidate for the TL position. The impact of the replacement in the overall performance and in strengthening the collaboration among the parties can be assessed as positive, given his different approach and working style compared to the previous TL. Given this positive change, and the fact that time was lost in part due to the transition between the two TL, the performance issues of the previous team leader, the Mission accepts to increase the input of the new TL. However, the new TL and consultants of Package 2 should be more active in supporting the C2 both C2.1 and C2.2 nationally and basin level respectively to fit the Component milestones. Because the activities split out by C2.1 is the same as planned in DMF and suite with TOR (the AWPB of C2 were jointly identified by DWR (C2.1), C2.2 and P2). The mission requested the P2 to carefully divide the TA time for both C2.1 and C2.2 based upon the existing TOR and work activities of each sub-component including concept notes, approach, report and RBM coordination mechanism support without separate advice between C2.1 and C2.2. The detailed TA support for both subcomponents will be advised by PMU based on C2 input. This is one of the harmonization of the C2 milestone achievements for the rest of the TA, except Sedone works.

- Sedone River Basin. DWR is contemplating initiating work on another river basin plan, with the assistance of the IWRM Advisor. Preliminary discussion indicates that Sedone river basin as a likely choice. In August 2012, the Mission had advised that DWR/MONRE needs to examine the projected use of the unallocated Project budget and determine the amount that is needed for the work on the second river basin (Aide memoire August 2012). The proposal for Sedone and its accompanying budget was only received on 19 February 2013 and therefore Mission will continue discussions with DWR. DWR intends to carry out the work through the C2.1 PIU.

- Priorities for 2013. The key activities to be carried out under this component will center around the guidelines for the RB plan process, state of the basin report, river basin management strategy, 5 year river basin management action plan and communication plan for Nam Ngum (and Sedone, to the extent the TA budget allows), top down/bottom up stakeholder involvement strategy and technical working group for NNRBMP. The Mission received on 19 February 2013 the proposed activities and budget for C2.1 (for example on the task force) and Sedone river basin planning and will review in due course.

- Way forward. The Mission agreed the following with DWR,MONRE , NNRBCS and the consultants:

- Priority. All agree that this component is critical to the success of the TA. Increased cooperation and collaboration is needed between DWR and NNRBCS for this component to succeed.

- Availability of funds. The fund request for C2.1 activities and Sedone will be reviewed by the Mission. For C2.2, which has already shared the concept notes  with the Mission, the concept notes need to be revised following Mission comments and resubmitted;

- Mobilisation of consultants. All consultant mobilization needs the prior clearance of ADB to ensure optimal use of resources and that consultant inputs coincide with key activities. Delay in the organization of key activities may imply holding off on mobilization of consultants;

### Output 3 – National groundwater management action plan prepared

- Implementation progress towards DMF targets. NREI has gathered and compiled data for groundwater sector assessment and groundwater resource assessment, with the technical support of consultants. In addition, groundwater team was established in central and provincial level to facilitate Component 3 activities. The component is on track to meeting its DMF targets.

- Key issues. NREI is addressing the two main issues (i) the scope of work in the package 3 consultant contract which does not full cover the scope of works stated in the Designing and Monitoring Framework (DMF) of the TA; (ii) links of component 3 activities to the ACIAR funded groundwater research program being implemented by a team led by the International Water Management Institute (IWMI). The DMF includes purchase of specialized groundwater monitoring equipment, a pilot study, and training. However, PIU3 requires assistance to carry out these activities, and there is no provision in the Package 3 contract. On the other hand, the purpose of the ACIAR project is to demonstrate viable technologies and identify strategies that would enhance agricultural use of economically accessible groundwater in Lao PDR for both dry season and supplementary wet season irrigation by smallholder farmers. The ACIAR project contains in field and modeling based studies, therefore, to make sure that there are appropriate links between the two projects, PIU3 participated in the inception meeting and stakeholder consultations of the ACIAR funded project. Details on the ACIAR work are attached as Appendix 5.

- The Mission had a meeting with PMU, PIU3, consultants, AusAID and IWMI team, and agreed with the IWMI team leader that Component 3 and the ACIAR funded project would have close coordination and cooperation on data inventory and capacity building and pilot activities. At the same time, the Mission confirmed the necessity for conducting a pilot assessment on Component 3 for capacity building and making the first national groundwater management action plan. PIU3 needs to clarify the pilot assessment activity and AWPB 2013 on Component 3 as well as the necessity of consultant contract variation as soon as possible. In addition, the Mission confirmed with PMU that groundwater management training would be conducted in Component 1 training with close cooperation with the capacity building activities in the ACIAR funded project.

- Priorities for 2013. The key activities to be carried out under Component 3 this year will lead up to management plan and the final workshop of the consultant in November 2013.

- Way forward. The Mission agreed the following with NREI:

- International consultant. The Mission will discuss with GHD the possibilities of increasing the inputs of the international consultant.

### Output 4 – IWRM education strengthened at the National University of Laos

- Implementation progress towards DMF targets. DMF target on NUOL graduates has in part been achieved, with 43 graduates from the first batch of students, with approximately 50% female graduates. However these students understandably did not benefit from the improved curriculum which is to be rolled out. Therefore while the quantitative target has been achieved, the implied qualitative aspect still has to be delivered. Package 4 consultants accomplished its activities based on the TOR which include; (i) review of the curricula; (ii) implement a study tour for senior WRED staff; (iv) prepare a strategic plan and detailed proposal for implementing the curriculum; (v) prepare a design and monitoring framework and detailed monitoring and evaluation (M&E) plan. The consultant was expected to facilitate twinning agreements with one of more universities and/or institutes. WRED signed the in-principal agreements for cooperation at the faculty level with two institutions, Kasetsart University and Asian Institute of Technology in Thailand, however WRED has entered into formal twinning arrangements which have to signed at the central university level  with any international university.

- Key issues. This Mission reminds NUOL as it did during the August 2012 review mission that this IWRM curriculum is made available to NUOL students studying agriculture, hydropower and mining. At the present time, NUOL is receiving support from a World Bank-AusAID Hydropower and Mining Technical Assistance Project.  In addition the Mission requested NUOL to consider how its IWRM students can be involved in other components of the NIWRMSP, including for field work and internships. The Mission visited NUOL and studied the university library that needs to be expanded for IWRM education.

- Priorities for 2013. Endorsement of the Strategic Plan by NUOL, and identification of key strategic priority areas that could be proposed for funding under the TA.

- Way forward. The Mission agreed the following with NUOL:

- NUOL needs to clarify, prioritize and make concept notes of the component 4 next step activities based on the strategies and action plan for further strengthening IWRM education at NUOL.

### Design and Monitoring Framework

- The Mission reviewed the DMF. The revised DMF is proposed in Appendix 6. There is a general update in the DMF to replace WREA with MONRE. The impact and outcome statements remain valid.

- As for the output statements, while they remain valid, the reference to the IWRM Support Program component has been removed. While the concept behind the TA remains to provide inputs to the Support Program which is directly linked to the National Water Resources Policy and Strategy, the Policy and Strategy has only been in draft form and in any case, the Mission is aware of the updating of the latter. The updating exercise has now introduced 12 or possibly 16 key areas and if possible the Mission would like to have an English translation of the summary of the updated key areas to ensure that the TA and the consultant input offered to the Government using TA funds are in line with the latest thinking on the Policy and Strategy.

- Some target years were adjusted to take into account delays in project implementation, stemming from the time needed to mobilize the four consulting packages as well as the slow implementation progress noted in 2012. Overall TA duration of 4 years is still deemed sufficient.

- The Mission suggests that the existing two gender related indicators be removed or revised. For example, the TA does not have control over the percentage of female RBC members. An updating will be proposed in line with the Mission’s view that the gender aspect of the TA be mainstreamed as far as possible into the technical components and be as realistic and meaningful as possible. For example, the Component 2 has been requested to look into ways of incorporating gender aspects into the river basin planning process. Similarly the Mission requested Component 1 to look into training on gender related issues.

- Assumptions and risks. The Mission carried out a thorough review of assumptions and risks, as in Appendix 7. The Mission feels that the TA remains relatively risky, mainly because of institutional issues and because the capacity of PMU is at present inadequate to manage a TA of this size and complexity.

### TA approach

- The Mission reviewed the original TA approach. The TA is designed primarily as a capacity building TA (CDTA). It was recognized that the capacity in the IWRM was limited within DWR, MONRE, but the work is of critical importance to Lao PDR, and especially the Nam Ngum River Basin (NNRB) which is taking the lead in RBP. Much is said about the need for the TA consultants to assist the government staff to implement the TA activities (rather than substituting their role), which in principle is correct. However, since IWRM is a relatively new discipline for most of the counterpart staff, in practical terms it is necessary for the consultants to take a strong lead in implementation of the TA activities. This involves initiating the activities, and from a position of action, progressively drawing in the counterpart resources and building capacity. It must also be recognized that robust capacity building is a long-term undertaking, and it would be unrealistic to expect that adequate capacity can be achieved within the life of this TA. The important issue it to make a start, and at the same time advance the work, which can be held up as examples of good practice, and hence a launching pad for future work. One implication of this reality check is that more international consultant inputs are needed, especially for Components 2 and 3, as discussed above.

- The original TA approach was that by building the Government’s capacity, the Government would be able to deliver the outputs in the DMF. For example, the TA inputs are supporting Nam Ngum river basin plan preparation, but the assumption was that a second river basin plan would be prepared by the Government using its own or other resources. This approach is ambitious given the current state of capacity.

- The original TA approach to use the PMU as a single entry point for management of funds and coordination across the components. However it is equally important in terms of efficient project management to ensure ways that promote ownership of the TA work and the corresponding availability of financial resources, paired with technical accountability and financial responsibility. This mismatch between resource availability and technical accountability has become obvious in Component 2 and if the problems of budget transfer between PMU and PIUs are not resolved, the Mission will make an exception to the general TA approach. See the discussion on the financial section for further details (ref para. 41)

### Financial progress

- Disbursement. The total approved TA amount is $3.9 million. The Government has agreed to contribute $0.31 in in-kind contribution. As of 18 February 2013, The TA has committed $2.74 million (and has disbursed $1.05 million. The decrease in the committed amount (from $3.08 million in August 2012) is due to the cancellation of the AusAID reserved amount, following receipt of the final tranche of AusAID funds in November 2012. An uncommitted amount of $1.16 million remains. The financial status of the Project, by category can be found in Appendix 8.

- Advance payment facility. The total amount advanced to DWR/MONRE is $215,392. This comprises of two advances ($89,638 in November 2011 and $125,754.15 in August 2012) using the advance payment facility. The original request for the second advance was $128,718 but only $125,754 was released due to an unliquidated amount of $2,964 from the first advance. The EA has been advised that this amount of $2,964 this can be used for activities included in the second advance. The current unliquidated amount is $99,122.38. A detailed status of the advance is attached in Appendix 9.

- The Mission reminded the PMU that the third request for advance can not be made until approximately 75% of the current advance has been liquidated. The Mission urged the PMU to liquidate on a timely basis. For the next advance request, ADB will review the breakdown of the advance request with the accompanying one-page concept notes (in line with AWPB, when PMU manages to prepare one of sufficient quality). Upon approval of the third advance, the PMU and PIUs can proceed with the activities without further approval from ADB, unless it is related to items that need such approval (studies, contracts with service providers, international travel, equipment) or to an activity which was not in the approved advance.

- Expenditure guidelines. The Package 1 consultant on administration and finance has prepared expenditure guidelines, which have been reviewed by the Project Management Specialist. The PMU informed the Mission that it will send the agreed version to ADB. The Mission reminded the PMU that unit rates indicated in the Ministry of Finance Decision No 0008/MOF must be used without exception. For items which do not figure in the said decision, the unit rates proposed by PMU appear to be reasonable.

- While clear expenditure guidelines are certainly useful, Mission notes however that most of the budget inaccuracies that are routinely identified during ADB review of the activity budget proposals refer to mistakes such as the overestimation of the number of eligible per diem days, choice of location of workshop that is not justifiable and so on. The Mission has advised PMU and PIUs that the accountability for a proper detailed activity budget preparation lies with them, and that any expenditure made mistakenly will not be liquidated.

- Fund flow. The Mission observed difficulty in fund flow from PMU to PIUs, especially in the case of Component 2.2. The Mission learnt that it only takes a day to transfer the funds to the PIU subaccounts. The Mission expects therefore that in the future, the preparation of fund transfer and actual transfer does not require more than five working days from the time of ADB approval. If by that time the transfer is not made, ADB will proceed with other means of ensuring that activities are not delayed For Component 2.2, two main options will be a direct transfer to the NNRBCS using its own advance payment facility or an increase in the Idom contract to cover critical activities without which mobilization of the international and national consultants would be futile. NNRBCS already has the experience of being an implementing agency (IA) under the Nam Ngum River Basin Development Sector Project, and also has specific NNRBCS strengthening support under the said project’s ongoing additional financing.

- Budget for 2013. The Mission discussed the annual work plan and budget of each component. The budgets are in different stages of preparedness, mostly received in an uncoordinated way during the Mission duration itself, and therefore need seriously further review by Component PIUs and ADB. There has been no exercise yet to rationalize the overall TA budget. The Mission notes that the rough estimates exceed the available uncommitted budget. In order to be properly review the budget, there needs be a more informative workplan (currently only annotated budgets are available) and failing which, the corresponding one-page concept summaries are essential to understand the rationale behind the activity and hence the appropriateness of the budget. Up to now, only the activities on Nam Ngum have corresponding concept notes (reviewed by Mission and IWRM advisor). Component 1 has a detailed training plan, that, when adjusted to incorporate the standard information requested in the one-page concept notes can be accepted in lieu of concept notes. If ADB does not receive a complete annual budget proposal, ADB will approve batches of concept notes as they are submitted, in accordance with the priorities explained below, so that the whole TA is not delayed. In the interest of transparency and saving time, henceforth PIUs are requested to copy ADB and AusAID at the same time they submit the concepts and budget estimates to PMU. The Mission advises that it will review the budget according to the following principles:

## High priority - implementation of the training plan;

## High priority - necessary increases in international consultant inputs;

## High priority - activities that were originally envisaged at TA design. New activities will be considered as second priority or the relevant PIU will be encouraged to mobilize other resources;

## Low priority – activities and equipment that could be covered by other projects;

## Low priority/exclusion – any activity which for which there is no evident need for capacity development, i.e. if the local institutions can already carry out the work using existing internal capacity, then they will be encouraged to mobilize other resources;

## Exclusion – procurement of vehicles (other than the vehicle currently being procured for Nam Ngum RBC activities and some motorcycles);

## Exclusion – any ordinary meeting that is budgeted as a workshop.

### Project management

- Guidance and oversight. In the last review mission (August 2012) the Project Director informed the Mission that DWR/MONRE would strengthen the TA guidance, coordination and leadership functions by assigning another DWR/MONRE staff to assist PMU and by assigning one of the two Deputy Director Generals as Deputy Project Director for the NIWRMSP (i.e. both ADB and World Bank supported components). The Mission welcomes the fact that the DDGs have been in post since January 2013 and request DWR, MONRE to explain further the direct role of the DDG in assisting the Project Director to fulfill the necessary TA guidance, coordination and leadership functions.

- Steering committee. The Mission requests that, in coordination with the World Bank supported components, the joint steering committee meeting be held to discuss the MTR recommendations and to actively look for areas of collaboration.

- National implementation support consultant. The Project Director requested the Mission to consider the recruitment of a national implementation support consultant. The Project Director stressed the importance of a Lao-speaking national consultant who would be able to work closely with the counterpart national consultant on the World Bank funded components to ensure NIWRM-SP wide coordination. The PMU will submit a TOR to ADB for this position for an initial 12 months. The PMU must also explain in its submission to ADB, how this proposed position does not overlap with the coordination functions of the Package 1 consultants.

- Reporting. Recommendations of the last review mission have not been followed. They have been updated by the PMS (see appendix 10) Reporting should also include a quick analysis of training evaluation by the participants.

- Consultant inputs. The summary of consultant inputs used as of February 2013 is shown in Appendix 11.

# GENERAL MTR RECOMMENDATIONS

- In general, the three main recommendations of the MTR are:

## Improved cooperation and collaboration between different parts of the Government and different projects are necessary to optimize the benefits to Lao PDR from this external assistance.

## The remaining inputs of international and national consultants must be used in an efficient and effective manner. This includes scheduling and funding activities like studies and workshops in a timely way.

## Fund flow problems must be fixed by improving the annual work plan and budget planning process and justification for budget requests, transfers and liquidation.

# FOLLOW UP ACTIONS

- The actions taken since the August 2012 review mission were summarized in Appendix 3 of the aide memoire of the Special TA Administration Mission of January 2013. PMU has accomplished most of the actions. Looking ahead, the following actions and timeframe have been agreed:

- Table 1: Key follow up actions

| - Para. Ref.; - Action; - By whom; - By when. - 2; Request changes to the TOR of Package 1; - PIU1, DWR; - 27 Feb 2013. - 12; Update and finalise training plan for approval; - PIU1, DWR; - 27 Feb 2013. - 12; - Identify gender mainstreaming linked to actual TA components; - Idom, ADB; - 27 Feb 2013. - 14; - Advise ADB of the setting up on the new PIU, its composition and TOR, and the establishment of its subaccount.; - PMU; - 27 Feb 2013. - 18; - Clarify synergy with Nam Ngum River Basin Development Sector Project (additional financing); - DWR, ADB; - 27 Feb 2013. - 23; - Discuss international consultant input; - PIU3, ADB; - 15 March 2013. - 27; - Clarify, prioritize and make concept notes of the component 4; - PIU4; - 27 Feb 2013. - 45; - Submit TOR for national implementation consultant; - PMU; - As soon as possible. - Gen; - Submit Annual Workplan and Budget 2013 and accompanying concept notes; - PMU and PIUs; - As soon as possible. |  |  |  |
| --- | --- | --- | --- |

- The next Joint Review Mission is proposed to be held in August 2013.

- The Mission expresses its gratitude to the Government, its staff and agencies met for the cooperation extended to the Mission.

- Signed:

| - Chanthanet Boulapha Director General Department of Water Resources MONRE | - (signatory to be provided) - AusAID | - Su Chin Teoh Natural Resources Specialist Mission Leader - ADB |
| --- | --- | --- |
| - Date: | - Date: | - Date: |

- List of Appendices

| 1. | List of persons met |
| --- | --- |
| 2. | Mission schedule |
| 3. 4. | Progress report prepared by PMU (August 2012 to December 2012) Presentation by PIU 2 |
| 5. | ACIAR project summary |
| 6. | Revised Design and Monitoring Framework |
| 7. | Review of assumptions and risks (in the Design and Monitoring Framework) |
| 8. | Financial status of the Project, by category |
| 9. | Status of Advance Payment Facility usage |
| 10. | Recommendations of Project Management Specialist (from final report 27 December 2012) |
| 11. | Summary of consultant inputs |

- Appendix 1

LIST OF PERSONS MET

(to insert meeting attendance lists)

| Name and Surname | Position | Organization | Tel | Email |
| --- | --- | --- | --- | --- |
| DWR |  |  |  |  |
| Mr Chanthanet BOULAPHA | DG | DWR |  | chanthanet@gmail.com |
| Mr Phonexay SIMMALAVONG | Administrative | DWR | 22485198 | mrjoybig@yahoo.com |
| Mr Phousavanh FONGKHAMDENG | Planning | DWR | 23665577 | Lan.jrp@gmail.com |
| Mr. Ounakone XAYVILIYA | PMU | DWR | 22239223 | ounakone@gmail.com |
| Ms Chindavanh |  | DWR | 22219930 | chindavanh.one@gmail.com |
| Mr Sakda PHIXAYAVONG | M&E | PMU, DWR | 99650000 | s_sakda@live.com |
| Mr Pinthong SALEUSAY | Finance | PMU, DWR | 22008400 | pin_sls@yahoo.com |
| Ms Vanseng KHAMMANIKHOT | Admint | PMU, DWR | 22235490 | k.vanseng@gmail.com |
| Mrs Phoukham KEOSEHOUN | Accountion | PMU | 22018786 | keosehoun@hotmail.com |
| Component 1 |  |  |  |  |
| Mr. Bounsanong FONGNALY | P1 Manager | P1 | 55478689 | Fongnaly79@yahoo.com |
| Ms Keodokmay | Finance | P1 | 55654200 | Keo.pk@hotmail.com |
| Antonio Dano | CTA | NIWRMSP |  | tonydano93@yahoo.com |
| Mr Simoune | P1 Consultant | P1 | 54872679 | Simoune_dara@hotmail.com |
| Mr Bounlap | M&E specialist | ESC | 55676726 | bounlap@hotmail.com |
| Mrs Sengmanichans | Training Specialist | P1 |  | Sengmanichanhsoncham@gmail.com |
| Maporn (Gaew) Lertsuridy | AECOM Project coordinator | AECOM ASIA | 58892407 | Maporn.lertsuridy@aecom.com |
| Mr Khamkeng CHANTHAVONGSA | Institutional Develop Specialist | AECOM, NIWRM-DWR | 55699473 | chhamkeng@yahoo.com |
| Component 2 |  |  |  |  |
| Mr Souphasay KORMANY | P2 coordinator | NNRBCS | 97985040 | Kormany_s@gmail.com |
| Mr Khounma VORLALATH | Finance | P2 | 55920861 | loyhenry_9@yahoo.com |
| Jorge Ocin | P2 | IDOM |  | jocon@idom.com |
| Rudi Kuiper | TL P2 | IDOM |  | rudikubb@gmail.com |
| Mr Boriboun | Dpty P2 | LCG/IDOM | 55555133 | bsanasisane@gmail.com |
| Component 3 |  |  |  |  |
| Mr Oulaphone ONGKEO | P3 Manager | P3, NREI | 22248529 | oulaphoneongkeo@gmail.com |
| Mr. Bounhieugs | National Consultant | P3 | 55833273 | bounhieugsvnhaneb@yahoo.com |
| Component 4 |  |  |  |  |
| Mr Bounyam THOUMMAVONG | PIU, P4 | WRED/NUOL | 22418423 | yomthoma@gmail.com |
| Mr Khamtan | M&E | PIU , P4, NUOL | 23071979 | khamtanh@yahoo.com |
| Dr. Torkil Jonch Clausen | IWRM Adviser | ADB | 22531570 | TJC@DHIGROUP.com |
| Paul Pavelic | RS | IWMI |  | ppavelic@cgiar.org |

- Appendix 2

Mission schedule

| - Date/Day | - Item | - Notes |
| --- | --- | --- |
| - 15 February 2013 (Friday) | - 9:00 – Courtesy call on CD, LRM - 9:30 - Mission meeting (ADB LRM Learning Center) - 10:30 – Kick off meeting (DWR Meeting Room) - Presentation of overall progress (Project Director) - Progress since last review mission (PMU) - Identification of issues to be discussed for current review (Mission) - Confirmation of review programme - 14:00 – Discussion on AWPB for Component 2 | - Mission - Mission - Present: EA, IAs, PMU, PIUs consultants and Mission NNRBCS, PMU, consultants, Mission |
| - 16 February 2013 (Saturday) | - 9:00 – visit to NNRBCS office; further discussion as necessary on Component 2 | NNRBCS, PMU, consultants, Mission |
| - 17 February 2013 (Sunday) | - 10:00 – meeting with IDOM - 16:00 – meeting with staff consultant (GMS flood and drought) | Mission |
| - 18 February 2013 (Monday) | - 9:00 – Discussion on AWPB for Component 3 14:00 – Discussion on AWPB for Component 4 (at NUOL Tadthong campus) 16:30 – Discussion on Component 2 (continued) | NREI, PMU, consultants, Mission NUOL, PMU, consultants, Mission |
| - 19 February 2013 (Tuesday) | - 7:30 – Meeting with staff consultants (GMS flood and drought) - 9:00 – Discussion on AWPB for Component 1 and training plan (at DWR); discussion on revised DMF - 14:00 – Discussion with PMU and C1 manager on financial and administration matters - 15:00 – Discussion with DG DWR | PMU, PIU, consultants, Mission |
| - 20 February 2013 (Wednesday) | - 9:00 – Draft MOU sent to Government for review - 10:00 – Meeting with DOI, MAF, MPWT and IAs on resettlement and social issues (GMS flood and drought) - 14:00 – Meeting with Vice Minister Sisavath, MONRE - 15:00 – Wrap up meeting and discussion of draft MOU | All Mission |

- Appendix 3

PROGRESS REPORT PREPARED BY PMU

- (To insert)

- Appendix 4

PRESENTATION ON COMPONENT 2 PROGRESS PREPARED BY piu2

- (To insert)

- Appendix 5

SUMMARY AND SCOPE OF ACIAR PROJECT

- (To insert)

- Appendix 6

revised dmf

| Design Summary | Performance Targets and Indicators | Data Sources and Reporting Mechanisms | Assumptions and Risks |
| --- | --- | --- | --- |
| Impact Water resources managed in Lao PDR river basins for sustainable economic, social, and environmental objectives | By 2020 in five basins: Investment decisions are consistent with IWRM river basin plans (baseline 2010 = 0). Water resources use agreements implemented (baseline 2010 = 0) | Project investment plans and proposals reported in the River Basin Committee and WREA annual reports MOUs with concession holders | Assumption All of the department in MONRE, MAF and MEM are cooperative to IWRM. Risk Critical decisions may be made before MONRE has significant influence. Hydropower, mining, and agricultural concessionaires resist implementation of basin management plans and regulations. |
| Outcome IWRM human resources and institutional capacity strengthened in MONRE, two RBC(S) and other key agencies | By the end of 2015: Effective river basin committees operating in at least two basins. (baseline 2010 = 0) At least two major river basins have IWRM plans fully integrated with province and national plans. (baseline 2010 = 0) 75% of MONRE staff successfully complete phase 1 CPD programs (baseline 2010 = 0) Water allocation and regulation mechanisms established and in use. | MONRE executive and management action plans and meeting minutes Provincial records of adoption of basin plans. RBC minutes and records. CPD assessment reports MONRE water allocation decisions widely disseminated | Risks Delay in finalization of new water laws constrains the role of MONRE in providing leadership in the sector Change of senior leadership and loss of trained staff weakens MONRE |
| Outputs 1. National capacity built in integrated water resources management 2. River basin management developed. | 80% of water resources management sector professional staff in MONRE are actively participating in tailored personal CPD programs by end of 2015 (baseline 2010 = 0). MONRE GAP prepared as a financing application by end 2014 (baseline 2010 – No specific WREA GAP). Two basin plans are published by MONRE in collaboration with basin management organizations. | MONRE executive and management action plans and individual training plans State-of-the-rivers publications National, provincial, and district socioeconomic plans River basin committee minutes and publications | Assumptions Parallel financing by development partners is provided within the IWRM support framework. Additional financing for GAP implementation secured MONRE employs water resources management staff continuously. Risks Sustainable financing for RBCs not obtained |
|  | NNRBC is established and operational (baseline 2010 draft NNRB plan prepared). NNRBC communication plans are implemented by 2013 (baseline 2010 – no plan established). | Provincial council record of adoption of plans State-of-the-rivers publications | Coordination with other ministries, projects and basin actors fails to generate expected synergy of action |
| 3. National groundwater management action plan prepared | Groundwater management plan is published for major aquifers by end 2014 (baseline - little awareness of groundwater issues). | WREAMONRE national groundwater management plan |  |
| 4. Integrated water resources management education strengthened at the National University of Laos | NUOL graduates a minimum of 10 IWRM bachelors of science per year (25% female) by 2015 (baseline 2010 =0). WREA employs about 50% of at least 5 NUOL IWRM graduates (baseline 2010 = 0). | University graduation records WREAMONRE employment records |  |

- Appendix 7

REVIEW OF ASSUMPTIONS AND RISKS

Impact level

Risk: Critical decisions may be made before WREA has significant influence.

MTR mission comments: WREA is no longer in existence.. On November 28th 2011, GOL established the Ministry of Natural Resources and Environment (MoNRE), under which the Department of Water Resources (DWR) absorbs the functions of the former WREA. As a new Department, it is building up its influence while still working out clear demarcation of roles and responsibilities. Therefore, this risk remains valid..

Risk: Hydropower, mining, and agricultural concessionaires resist implementation of basin management plans and regulations.

MTR mission comments: This risk remains valid.

MTR mission recommendations: There is an important assumption at impact level which needs to be included. The assumption is that “All the departments in MONRE, MAF and MEM cooperate according to IWRM principles”, because IWRM will not materialize without active cooperation among the water related government agencies.

Outcome level

Assumption: Natural resources remain key basis for economic development.

MTR mission comments: It is fairly obvious that natural resources will remain the key basis for economic development in the foreseeable future in Lao PDR. This assumption is not directly relevant to the TA and the MTR mission recommends that it be removed.

Risk: Delay in finalization of new water laws constrains the role of WREA in providing leadership in the sector

MTR mission comments: As noted above, WREA has been replaced by DWR, MONRE. This risk identified remains valid, although work on the updating of the water law has been ongoing in 2012. The TA needs to ensure sufficient coordinatation with IFC and the World Bank Water Law Component.

Risk: Change of senior leadership and loss of trained staff weakens WREA

MTR mission comments: This is a risk that has materialized. The project design was led by strong leadership of WREA which now has changed with the institutional reorganization in MONRE. Sufficient leadership and ownership in in the TA has not been demonstrated over the last 12 months. Similarly the lack of a critical mass of trained staff in DWR means that the baseline for capacity development is low.

Output 1

Assumption: Parallel financing by development partners is provided within the IWRM support framework.

MTR mission comments: The IWRM support framework has been updated and is being finalised but the Mission has not received a copy. In fact the IWRM support framework does not at present to be a widely used framework besides during the initial desing of the ADB and World Bank components. Mission suggests to remove the word “parallel” as it has a connotation of cofinancing which could be confusing.

Assumption: Additional financing for GAP implementation secured

MTR mission comments: MTR mission recommends that instead of a general gender action plan for gender aspect would be incorporated in RBP on Component 2. tbd

Output 2

Risk: Sustainable financing for RBCs not obtained

MTR mission comments: We need to watch the budget for RBCs carefully, and according to the RBCs budget situation, we need to finance RBCs activities for the development of river basin management.

Risk: Coordination with other ministries, projects and basin actors fails to generate expected synergy of action

MTR mission comments: The success of this output depends on a key assumption which is that the DWR and NNRBCS have a good cooperative relationship. However, this risk has materialized because of less coordination and cooperation between the two organizations. We need to watch the progress and activities on National Task Force for making NNRBP.

Output 3

No risk/assumption identified at design.

MTR mission comments: According to the situation of groundwater use, we need to manage the risk that major groundwater users resist implementation of groundwater management action plan.

Output 4

No risk/assumption identified at design and confirmed at MTR.

- Appendix 8

FINANCIAL STATUS OF THE PROJECT (USD)

- Appendix 9

STATUS of ADVANCE PAYMENT FACILITY 1 and 2

- Appendix 10

RECOMMENDATIONS FROM PROJECT MANAGEMENT SPECIALIST

(DECEMBER 2012 REPORT)

1	The TA is designed primarily as a capacity building TA (CDTA). It was recognized that the capacity in the IWRM was limited within MoNRE /DWR, but the work is of critical importance to Lao PDR, and especially the Nam Ngum River Basin (NNRB) which is taking the lead in RBP. Much is said about the need for the TA consultants to assist the government staff to implement the TA activities (rather than substituting their role), which in principle is correct. However, since IWRM is a relatively new discipline for most of the counterpart staff, in practical terms it is necessary for the consultants to take a strong lead in implementation of the TA activities. This involves initiating the activities, and from a position of action, progressively drawing in the counterpart resources and building capacity. It must also be recognized that robust capacity building is a long-term undertaking, and it would be unrealistic to expect that adequate capacity can be achieved within the life of this TA. The important issue it to make a start, and at the same time advance the work, which can be held up as examples of good practice, and hence a launching pad for future work.

2	The separation of Component 2 into C2.1 and C2.2 has also introduced the need for clarifications of roles. This directive appoints a new C2.1 Component Manager to provide overall DWR guidance and coordination of RBM in accordance with the DWR mandate. This does not constitute any change to the original concept of Component 2 of the TA, except it now becomes Component 2.2 under the same Component Manager and continues to have responsibility for the Nam Ngum RBP as before. However, it now falls under DWR guidance on overarching policy matters provided through C2.1. Although the precise role of each is currently a topic of ongoing discussions, there is clear logic to this is decision because:

- It facilitates the application of the guidelines and framework for river basin planning and management in line with national policy.

- It enables information exchange and a degree of harmonization between the planning and management in various basins.

Specific recommendations

Recommendation on coordination with World Bank funded components: DWR should consider convening a joint NIWRMSP meeting (possibly a retreat), preferably in Q1 2013 as the WB components are still in the early stages. It should involve key staff and consultants from all components so they can get to know each other, inform each other of their activities, and discuss specific linkages that should be established. Regular follow-up meetings should also be scheduled (monthly or quarterly). The PMU, assisted by P1, will arrange the meetings, and the meetings should be chaired by the NPD.

Recommendation on IWRM Advisor guidance:

- To anchor the advice and guidance provided by the IWRM Advisor, it should be presented in the reports on each of the IWRM’s visits so that the DWR (and particularly the NPD) are able to readily access it as required.

- To assist the IWRM Advisor to plan and schedule his inputs, the PMU /CTA/C2 should prepare a list of the reports, workshop /training concept notes, and other documents that they wish to have reviewed by him, and the likely timing.

Recommendation on monitoring and S curve: The P1 team will convene a consultation meeting with all the component staff to discuss and review the draft presented by the Project Management Specialist, and reach consensus on breakdown of activities and percentage weightings. This will then be the basis for the TA S-curve that will be finalized for inclusion in the Q4 2012 Quarterly Progress Report.

Recommendation on Expenditure Guidelines:  The FAS, with the assistance of the CTA for quality checks, should finalize the Expenditure Guidelines taking into consideration the comments that have been provided by the PMS in December 2012, and resubmit them to PMU.

Recommendation on Review and Approval of Technical Reports

These procedures are designed to have the reports cleared within 3 weeks if there are acceptable without comments, 8 weeks if 1-step revisions are needed, or a maximum of 10 weeks if a second round of revisions is needed.  The process in Table 2 has been discussed at a weekly meeting of the components, and so far no specific changes have been suggested. However, the time for the various steps may need further discussion and adjustment if considered necessary.

Table 1: Review Process for Technical Reports

| Activity | Respon-sibility | Due Date | Cumulative time (weeks) |
| --- | --- | --- | --- |
| - Submission of draft Report to PMU. (PIU to agree the report is ready for wider review before submission). Submitted informally to ADB /AusAID at this stage. | PIU/ Consultant | -- |  |
| - Discuss the report and the planned action | PMU & PIU | Not more than 1 week after submission (Step 1). | 1 week |
| - Submit draft report for review to ADB, AusAID, individuals (eg, CTA, & IWRM Advisor if applicable), & institution that need to review /comment | PMU | Max 1.5 weeks after submission | 1.5 weeks |
| - Hold a stakeholder’s workshop (or meeting) to review or clear the report | PMU | Max 3 weeks after submission of the report | 3 weeks |
| - Consolidate all comments, and send to the Consultant for the revision of the report | PMU | Not more than 1 week after the workshop | 4 weeks |
| - Revise the report and re-submit to PMU | Consultant | Max 2 weeks after receiving the comments (or as specified in the contract) | 6 weeks |
| - Review the revised report and recommend either approval (or additional provide further comments to consultant if necessary) | PMU & PIU | Max 1 week after resubmission of report | 7 weeks |
| - Final Approval of Report (if Step 7 accepts) Consultant to submit final to ADB /AusAID | PMU /NPD | Max 2 weeks after resubmission | 8 weeks |
| - If additional revisions are needed, discuss with consultants, agree on additonal revisions, and receive 2nd resubmission from Consultant | PMU, PIU, & Consultant | Max 2 weeks from Step 7 | 9 weeks |
| - Subject to acceptance, approval report. Consultant to submit final to ADB /AusAID | PMU /NPD | Max 1 weeks after 2nd resubmission | 10 weeks |

Recommendations on Reporting:

- MPRs of each component will be de-formalized and serve as information sharing, and prepared according to the standard template prepared by the CTA and issued by the PMU to the PIUs in May 2012. For each component, MPRs will be prepared by the consultants in close consultation with their respective PIUs. They will be a max 2-3 pages, shall be completed not later than 1 week after the end of the month, and not subject to formal approvals. Only electronic form of MPRs are required, and when complete will be emailed by the PIU Manager to the following cc list: DG (as the National Project Director), PMU, ADB, AusAID, the other 3 PIU Managers, and the consultant Team Leaders of each Package.

- QPRs – at the end of each quarter starting from Q3 2012 (covering the period July-September), the CTA will assist the PMU to prepare a QPR covering the overall TA. It will be completed and cleared for distribution not later than 2 weeks after the end of each quarter. It will be distributed electronically (cc: DG, ADB, AusAID, 4 x PIU Managers, 4 x consultant TLs). P1 will also prepare hard copies x 15 to be distributed by the PMU (distribution: DG x 1, PMU x 2, ADB x 2, AusAID x 2, each PIU x 1, each Package x 1).

- APRs –each component will continue to prepare an annual progress report with the assistance of the consultants. They will be completed and cleared by each PIU not later than 15 days from the end of the year, and submitted (electronically and hard copy if requested) to the PMU for clearance. The PMU will provide clearance (or comments) within 1 week. If cleared, the PMU will distribute them electronically (same cc list as for QPRs), and the concerned consultant will prepare 15 hard copies for the PMU to distribute (same distribution as QPRs).

- Appendix 11

- SUMMARY OF CONSULTANT INPUTS USED

| Name of consultant | Position | Total person-months | Person-months utilized as of Feb. 12, 2013 | Person-months remaining |
| --- | --- | --- | --- | --- |
| Package 1 |  |  |  |  |
| International |  |  |  |  |
| - Antonio M. Daño | CTA/Water Governance | 25 | 10.47 | 14.53 |
| 2. Mathew Ko | M & E specialist | 5 | 3.11 | 1.89 |
| National |  |  |  |  |
| 3. Khamkeng Chanthavongsa | Institution development specialist | 33 | 12.32 | 20.68 |
| 4. Sengmanichanh Somchanmavong | IWRM training specialist | 30 | 9.64 | 20.36 |
| 5. Simuone Darasmy | Administration & finance specialist | 39 | 13.23 | 25.77 |
| 6. Bounlap Pathilath | M & E specialist | 12 | 6.18 | 5.82 |
| Package 2 |  |  |  |  |
| International |  |  |  |  |
| 7. David Baringo | River basin management specialist | 15 | 9.0 | 6.0 |
| National |  |  |  |  |
| 8. Boriboun Sanasisane | River basin management specialist | 30 | 14.5 | 15.5 |
| 9. Ms. Duangchith Viravongsa | Participatory planning specialist | 18 | 9.7 | 8.3 |
| 10. Mr. Khamkeng Sixaya | Climate change adaptation specialist | 2 | 0.13 | 1.87 |
| Package 3 |  |  |  |  |
| International |  |  |  |  |
| 11. Nick Lombardi | Groundwater Resources Specialist | 4 | 1.96 | 2.04 |
| National |  |  |  |  |
| 12. Mr. Bounhieng Souvanhane | Groundwater Resources Specialist | 20 | 11.4 | 8.6 |
| Package 4 |  |  |  |  |
| International |  |  |  |  |
| 13. Paul Taylor | IWRM curriculum development specialist | 6 | 5.94 | 0.16 |
| National |  |  |  |  |
| - Sengmanichanh Somchanmavong | IWRM education specialist 1 | 6 | 5.5 | 0.5 |
| 15. Kanya | IWRM education specialist 2 | 6 | 6.0 | 0.0 |
| 16. Mone | Climate change adaptation specialist | 2 | 1.0 | 1.0 |
| Torkil Clausen | IWRM Adviser | 10 | 5.5 | 4.5 |

The Mission comprised Su Chin Teoh, Natural Resources Specialist (SEER), Mission leader; Hidefumi Murashita, Water Resources Specialist (SEER); Sisavanh Phanouvong, Senior Project Officer (LRM); John Dore, Senior Regional Water Resources Sector Specialist (AusAID); Somsanith Mounphoxay, Program Officer (AusAID). The Mission was assisted by the TA IWRM advisor (consultant). Country Director LRM participated in the meeting at the Nam Ngum River Basin Committee Secretariat Office on 16 February 2013.

PONRE is Provincial Department of Natural Resources and Environment

DONRE is District Office of Natural Resources and Environment

Village Water Resource Committee (comprises of deputy head of village as a chairman, village security staff, voluntary safeguard, youth, women, Worker Union, Lao Front Construction, voluntary public health).

Water quantity, quality, river/tributaries, wetlands and surface and groundwater.

Piloted in 3 sub-basins in NN namely Nam Lik, Nam Ting-Nam Chat and Nam Kho and WQM guideline development and built local capacity for WQ sampling collection, tool usage and maitenance, etc..This leaded by Division of Surface and Groundwater Quality Management of DWR.

This initiated by existing DWR capacity and team (leaded by Division of RB Management and Development in DWR), experience and this will be further discussed with C2 and national TWG.

Water day, wetland day, river clean up activity-Nam Xong, etc.

ADB’s Technical Assistance Special Fund (TASF) finances $0.3 million. The Government of Australia provides A$3.2 million equivalent and the Spanish Cooperation Fund for Technical Assistance provides $600,000, administered by ADB.