PACIFIC HORTICULTURAL & AGRICULTURAL MARKET ACCESS PROGRAM (THE PHAMA PROGRAM) PROGRAM DESIGN DOCUMENT (RFT) Volume 2 APPENDICES 6 July 2010

TABLE OF CONTENTS

| Appendix No. | Appendix Title | Page No. |
| --- | --- | --- |
| 1 | Summary trade data for selected PICTS | 3 |
| 2 | Summary of current market access and key opportunities for new/ improved access | 6 |
| 3 | Institutions involved in gaining and maintaining market access | 10 |
| 4 | Related donor-funded programs and projects | 19 |
| 5 | Management of market access issues and preliminary workshop outcomes | 30 |
| 6 | Role of SPC in program implementation: Component 4 specification | 75 |
| 8 | Program logical framework | 106 |
| 10 | Draft M&E framework | 114 |
| 11 | Risk management matrix | 121 |
| 12 | Terms of reference for key positions | 126 |

APPENDIX 1

SUMMARY TRADE DATA

APPENDIX 2

SUMMARY OF CURRENT MARKET ACCESS AND KEY OPPORTUNITIES FOR NEW/ IMPROVED ACCESS

|  | FIJI | SAMOA | TONGA | VANUATU | PNG |
| --- | --- | --- | --- | --- | --- |
| CURRENT ACCESS/ TRADE |  |  |  |  |  |
| (1) Fresh |  |  |  |  |  |
| Australia Note: Those in bold print are HTFA-treated. | Papaya, coconuts, taro, leaves of (amaranthus, bael, cassava, chickory, cordyline, taro), various cut flowers. | Coconuts, taro, leaves of (amaranthus, bael, chickory, cordyline), various cut flowers. | Coconuts, taro, leaves, leaves of (amaranthus, bael, cassava, chickory, cordyline, taro), various cut flowers. | Coconuts, taro, leaves of (amaranthus, bael, chickory, cordyline), various cut flowers. | Coconuts, taro, leaves of (amaranthus, bael, chickory, cordyline), various cut flowers. |
| NZ (MAF Biosecurity New Zealand Standard: 152.02 (5 November 2007)) Note: Those in bold print are HTFA-treated. | Papaya, mango, breadfruit, eggplant, chilli, pineapple, plantain, pigeon pea, snow pea, cow pea, guar beans, long beans, papdi, green beans, duruka, sugarcane, kava, coconuts, peanuts (fresh), yam, cassava, taro, taro bavia, tarua, ginger, okra, drumsticks, rocket, lettuce, chive, dill, coriander, oregano, basil, sage, thyme, turmeric, lemon grass, mint, betel nut, leaves (of amaranthus, bael, betel, curry, mango, papaya, roselle, taro, tarua). | Papaya, breadfruit, eggplant, banana, plantain, kape, kava, sugarcane, coconuts, yam, cassava, taro, tarua, ginger, leaves (of banana, beach bean, Indian mulberry, Indian pennywort, lillypilly, Malay apple, papaya, pepper, soap bush, taro, tarua, wart fern, wild coffee and six others for which no common name is listed). | Avocado, breadfruit, chilli, eggplant, mango, papaya, tomato, banana, plantain, squash, butternut, watermelon, kape, kava, sugarcane, coconuts, yam, cassava, taro, tarua, ginger, leaves (of beach bean, Indian mulberry, Indian pennywort, lillypilly, Malay apple, pepper, soap bush, taro, tarua, wart fern, wild coffee and six others for which no common name is listed). | Papaya, eggplant, lime, pomelo, lemon, grapefruit, mandarin/tangerine, tangelo, orange, pineapple, cucumber, squash, sweetcorn, green beans, coconuts, yam, cassava, taro, tarua, ginger, vanilla, leaves of (taro, tarua). | Ginger, coconuts, taro, yam, cassava, betel nut, tarua. |
| Other | Ginger (US) |  | Squash (Japan) |  |  |
| (2) Processed |  |  |  |  |  |
| Australia | Coconut meat, palusami (cooked taro leaves and coconut cream frozen), taro (frozen), taro leaves (frozen), vegetables/culinary herbs (blanched and frozen), spices, noni juice | Coconut meat, noni juice, palusami (cooked taro leaves and coconut cream frozen), taro (frozen), vegetables/culinary herbs (blanched and frozen) | Coconut meat, palusami (cooked taro leaves and coconut cream frozen), taro (frozen), taro leaves (fresh), vanilla, vegetables/culinary herbs (blanched and frozen) | Beef, coconut meat and meal, essential oils, palusami (cooked taro leaves and coconut cream frozen), taro leaves (frozen), vanilla, vegetables/culinary herbs (blanched and frozen) | Coconut meat and meal, taro (frozen), taro leaves (frozen), vanilla, vegetables/culinary herbs (blanched and frozen) |
| NZ | Mangoes (pickled) [Ranjan Farms; Fresco], coconut flesh (pieces or grated) [All] – MAFBNZ Standard 152.02 Approved processed commodities list Frozen fruit/vegetables (except frozen Citrus spp. Leaves) which have been commercially processed, packaged and labelled – MAFBNZ Standard 152.02 All cooked, pickled, pureed, dried fruit/vegetables in accordance with BNZ-NPP-HUMAN Importation into New Zealand of stored plant products intended for human consumption Most nuts in accordance with BNZ-NPP-HUMAN Importation into New Zealand of stored plant products intended for human consumption | Banana (peeled and chopped), mango (peeled and chopped), pineapple (peeled and chopped) [Malaefono Plantation], coconut flesh (pieces or grated) [All] – MAFBNZ Standard 152.02 Approved processed commodities list Frozen fruit/vegetables (except frozen Citrus spp. Leaves) which have been commercially processed, packaged and labelled – MAFBNZ Standard 152.02 All cooked, pickled, pureed, dried fruit/vegetables in accordance with BNZ-NPP-HUMAN Importation into New Zealand of stored plant products intended for human consumption Most nuts in accordance with BNZ-NPP-HUMAN Importation into New Zealand of stored plant products intended for human consumption Honey (with appropriate zoosanitary certificate regarding European foulbrood) | Coconut flesh (pieces or grated) [All] – MAFBNZ Standard 152.02 Approved processed commodities list Frozen fruit/vegetables (except frozen Citrus spp. Leaves) which have been commercially processed, packaged and labelled – MAFBNZ Standard 152.02 All cooked, pickled, pureed, dried fruit/vegetables in accordance with BNZ-NPP-HUMAN Importation into New Zealand of stored plant products intended for human consumption Most nuts in accordance with BNZ-NPP-HUMAN Importation into New Zealand of stored plant products intended for human consumption Honey (with appropriate zoosanitary certificate regarding European foulbrood) | Beef, coconut flesh (pieces or grated) [All] – MAFBNZ Standard 152.02 Approved processed commodities list Frozen fruit/vegetables (except frozen Citrus spp. Leaves) which have been commercially processed, packaged and labelled – MAFBNZ Standard 152.02 All cooked, pickled, pureed, dried fruit/vegetables in accordance with BNZ-NPP-HUMAN Importation into New Zealand of stored plant products intended for human consumption Most nuts in accordance with BNZ-NPP-HUMAN Importation into New Zealand of stored plant products intended for human consumption | Coconut flesh (pieces or grated) [All] – MAFBNZ Standard 152.02 Approved processed commodities list Frozen fruit/vegetables (except frozen Citrus spp. Leaves) which have been commercially processed, packaged and labelled – MAFBNZ Standard 152.02 All cooked, pickled, pureed, dried fruit/vegetables in accordance with BNZ-NPP-HUMAN Importation into New Zealand of stored plant products intended for human consumption Most nuts in accordance with BNZ-NPP-HUMAN Importation into New Zealand of stored plant products intended for human consumption Coffee beans (green) in accordance with BNZ-NPP-HUMAN Importation into New Zealand of stored plant products intended for human consumption |

| KEY OPPORTUNITIES |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| (1) New access for fresh |  |  |  |  |  |
| Australia | Ginger, breadfruit, chillies, jackfruit, eggplant, mango, vi | Breadfruit, papaya, avocado, vi | Breadfruit, papaya, mango | Ginger |  |
| NZ [Note: Those products marked * appeared on MAFBNZ’s “2007/2008 Prioritised List for Import Health Standards”. Also those in bold print regarded as a priority for industry in-country.] | Vi*, cucurbits* (including bitter gourd, luffa, pumpkin), jackfruit*, other chilli varieties Cut flowers* | Vi*, pineapple*, Tahitian chestnut*, limes*, rambutan*, Citrus spp.* | Pineapple*, beans*, okra*, peas*, pele leaves*, baby corn* | Vi*, banana*, breadfruit*, capsicum*, mango*, tomato* | Cooking banana*, pineapple*, asparagus*, sweet potato* |
| Other | Papaya (US), breadfruit (US), ginger (Japan). | Breadfruit (US) |  | Nuts (EU) | Nuts (EU) |
| (2) New access for processed |  |  |  |  |  |
| Australia | Processed root crops | Kava, noni juice |  | Various nuts (Canarium spp. etc), kava | Coffee, nuts |
| NZ |  |  |  | Canarium nuts |  |
| Other |  |  |  |  |  |
| (3) Improved access for fresh |  |  |  |  |  |
| Australia | Papaya, taro | Taro | Taro | Taro | Taro |
| NZ [Note: Those products marked * appeared on MAFBNZ’s “2007/2008 Work Programme” for review] | Taro* | Taro*, banana* | Taro* | Taro* | Taro* |

APPENDIX 3

INSTITUTIONS INVOLVED IN GAINING AND MAINTAINING MARKET ACCESS

The process of gaining, maintaining and improving MA involves technical, organisational and political input by key public and private sector institutions at both national and regional levels. The level of involvement of any institution is dependent on the specific MA issue being addressed, the mandated role of the institution and the capacity of the institution to deliver the required input/s.  The key institutions involved are outlined below.

- IMPORTING COUNTRY AGENCIES WITH MARKET ACCESS RESPONSIBILITIES

  - Biosecurity Services Group (BSG)

BSG, within the Department of Agriculture Fisheries and Forestry (DAFF), is responsible for consideration of international MA requests and determination of final import policy. BSG maintains Australia’s highly conservative approach to quarantine that ensures the level of risk from imported agricultural and horticultural commodities remains very low. A detailed and time-consuming import risk analysis (IRA) process and stringent risk management measures, should imports be approved, characterise this process. MA requests are now being prioritised under a newly regulated IRA process announced in 2007. The new process, which specifies that IRAs must be completed within 24-30 months, will not necessarily mean a reduction in the amount of time required from application through to final approval of a MA request, as BSG may delay the entry of requests into its work program until it has the resources available to process the request within the time required.

Inclusion and prioritisation of MA requests in the BSG work program is considered by an internal DAFF committee. Many criteria are taken into account when developing the annual IRA work program. DAFF has indicated that PICT MA requests will still be subject to the usual processes.

PICT fresh commodity MA requests completed within the last ten years include Solomon Islands pineapple (2002), Fijian papaya (2002) and New Caledonian limes (2006). Fijian ginger is currently on the BSG ‘A’ priority list but commencement of the IRA is yet to be announced. Vanuatu papaya is on the BA ‘B’ list but work is unlikely to commence in the near future. There are currently no other PICT MA requests in the published work program, although there are many on the waitlist.

AusAID funded a Market Access Coordinator position within BA during 2007, designed to facilitate consideration of PICT MA issues. While there were relatively few MA gains over the period, PICTs report that the position resulted in improved communication and coordination with BA on MA and maintenance issues. Funding for this position has now recently been re-established through PHAMA.

  - Australian Quarantine Inspection Service (AQIS)

Once a MA request is approved and import policy recommended by BSG, AQIS (also part of DAFF) is responsible for implementing operational aspects of the policy. PICTs have indicated some difficulty in communicating with AQIS to determine import requirements for existing MA and receiving feedback on non-compliance issues. These difficulties are due to ill-defined communication channels at the bilateral level; difficulty experienced by some PICTs in interrogating the AQIS Import Conditions Database (ICON); and a lack of formal feedback to the relevant PICT quarantine agency regarding non-compliance events.

  - MAF Biosecurity New Zealand (MAFBNZ)

The NZ Ministry of Agriculture and Forestry’s biosecurity arm, MAFBNZ, is responsible for the consideration of requests for the import of risk goods into New Zealand.  Under the Biosecurity Act 1993, an import health standard (IHS) is required for importation of all biosecurity risk goods.

Since July 2006 all applications for new or amended IHSs are managed by MAFBNZ under a defined funding and management system.  The development of IHSs follows a system very similar to BSG’s IRA process. Under this system, all identified IHS work is prioritised using criteria established in the biosecurity Integrated Risk Management Framework.  These criteria include: strategic (fit with the NZ government’s goals); net benefit (for NZ); technical (difficulty of the work); acceptability (of the result for New Zealanders); and practicality (the availability of required resources). The Ministry of Foreign Affairs and Trade (MFAT) represents NZ’s international trade objectives on the prioritisation panel.  Nevertheless MAFBNZ is very careful in its handling of apparent favouritism of one country/region over another. Available resources are subsequently matched to the highest priority work.  Once all Crown-funded resources have been allocated, applicants that have indicated they are willing to self-fund their application are offered the option, in order of priority; but initial trials of this new approach have not been well regarded. It is important to note that IHSs not included on the current two-year work programme must be reconfirmed before they will be reconsidered for the next two-year work programme.  This means it is essential to actively engage in the Prioritisation Rounds (and respond to the notified deadlines) as the opportunity to do so only comes once every two years.

Notable PICT MA successes into NZ were made under RMFFP (1990-2000), including access for: papaya, eggplant, breadfruit, mango, pineapple, plantain and two varieties of chilli from Fiji; papaya, breadfruit and eggplant from Samoa; avocado, breadfruit, chilli, eggplant, mango, papaya and tomato from Tonga; and papaya, eggplant, lime, pomelo, lemon, grapefruit, mandarin/tangerine, tangelo, orange, pineapple, cucumber and squash from Vanuatu.

Recently MAFBNZ has published its 2009-2011 IHS Development Programme, separating its Plant IHSs  into ‘non Pacific’ and ‘Pacific’.  Pacific IHSs expected to be progressed during 2009-2011 include six new commodities, namely: Tahitian lime from the Cook Islands; Polynesian plum or vi from Fiji, Vanuatu, Cook Islands and Samoa; Mexican lime from New Caledonia; Tahitian lime from Samoa; Island cabbage from Tonga, Vanuatu, Fiji and Samoa; and coconut from Tuvalu.  There were a further 10 Pacific requests for new IHSs that are ‘not expected to be progressed in the foreseeable future’.

Similar to the Pacific Coordinator position in BSG funded by AusAID during 2007, in the recent past NZAID has supported a position within MAFBNZ intended to facilitate communication on PICT MA issues. PICTs report enthusiastically on the benefits of this position. Responsibility for the position now rests with MAFBNZ, which has confirmed baseline funding for a Senior Adviser, Plant Imports (Pacific) within the Border Standards Directorate. The position has been filled since February 2008.

In June 2008 MAFBNZ established a working group, the MAFBNZ Pacific Forum, to prepare a ‘MAFBNZ Pacific Strategy’.  The working group coordinates the implementation of the strategy which has two stated thrusts: (i) decreasing the biosecurity risks to New Zealand associated with trade with PICTs by pushing that risk off-shore; and (ii) providing input into sustainable TA projects to improve the biosecurity, and trade opportunities of PICTs.  The strategy makes mention of the establishment in 2007 of the full time position within MAFBNZ dedicated to addressing Pacific Island IHS requests, and acknowledges the need to develop more sustainable engagement with countries to which NZ has special obligations.  Whether this translates into more favourable treatment of PICT MA requests remains to be seen.

  - MAFBNZ Clearance Service

Formerly known as the MAF Quarantine Service, the MAFBNZ Clearance Service is responsible for inspecting imported consignments to check compliance with IHSs.  The inspection regime required on arrival in New Zealand is specified in the relevant IHS.  PICTs face similar difficulties in dealing with the NZ Clearance Service as noted previously for AQIS.

  - Food safety responsibilities in Australia and New Zealand

In addition to the biosecurity/quarantine standards that may apply to imported products, FS-related standards also apply to imported food and beverage items of animal or plant origin.  These are particularly relevant in relation to processed product and MRLs on fresh product. International FS standards are set by the Codex Alimentarius Commission and commonly referred to as the Codex standards.  In general, Codex standards specify the requirements for food and beverage items imported into Australia and NZ.  In NZ, the NZ Food Safety Authority (NZFSA), formerly part of MAF, sets policies, criteria and procedures to monitor the safety of imported food for human consumption.  NZFSA now works closely with Food Standards Australia New Zealand (FSANZ) in the development of new food standards with particular attention given to food composition and labelling.  FSANZ (formerly the Australia New Zealand Food Standards Authority) develops food standards (primarily composition and labelling) for food sold in New Zealand and Australia. The 'product' from this arrangement is a joint Australia New Zealand Food Standards Code that has replaced the New Zealand Food Regulations made under the New Zealand Food Act 1981, and the Australian Food Standards Code.

  - Biosecurity, quarantine and food safety organisations in other importing countries

The institutional set-up governing MA for agricultural and horticultural products into countries other than Australia and NZ is broadly similar to that outlined above. There is a clear perception among PICTs of the relative ease of dealing with the regulatory agencies of various countries. Japan is considered the easiest country to deal with in a regulatory sense, followed by the US, NZ and then Australia respectively. The relative ease of dealing with agencies may be attributed, in part, to the quarantine status of the respective countries. However, in many instances an unwillingness or inability to engage or communicate to resolve MA issues is cited.

- PICT GOVERNMENT AGENCIES WITH MARKET ACCESS RESPONSIBILITIES

MA responsibilities within PICTs generally sit within the Quarantine Departments/National Plant Protection Organisations (NPPOs) of the Ministries of Agriculture. The names of these institutions vary between PICTs. They have a range of common roles including prioritisation of MA requests, development of MA submissions, bilateral negotiation of MA agreements, and implementation of stipulated export protocols. The Quarantine Departments and national R&D providers fill an important role in the development of pest lists and various other R&D activities required to gain, maintain or improve MA. The ability of the PICT Quarantine Departments to manage MA issues for high-value agricultural and horticultural products is generally low. In addition, their ability to manage biosecurity operations (monitoring and surveillance for exotic pests and diseases, and incursion responses), which is closely related to and often underpins MA, is also considered to be generally low.

- INDUSTRY ASSOCIATIONS AND COMMUNITY GROUPS

Formal representation of industry interests through industry associations and community groups is a critical element of industry development. An important function of these organisations is to provide an interface between producers and government in relation to driving the MA process, including identification of MA priorities; implementation of requirements to maintain MA in line with agreed access protocols; and development and implementation of industry/product standards. A range of representative organisations and community groups exists in target PICTs, but composition, function and effectiveness is highly variable. Most comprise a grouping of key agricultural growers and/or exporters; but many are poorly organised, have relatively limited capacity, and demonstrate a weak relationship with government.

The inability of PICT government agencies to progress MA issues that are considered important by industry has been a source of considerable frustration and a catalyst for the formation of industry representative associations and groups in many cases. In some instances associations – and even individual growers or exporters – have, out of frustration, attempted to bypass the relevant government agency responsible for MA issues and deal directly with importing country regulatory authorities. There is an increasing reluctance on the part of importing country agencies to deal in any way other than government-to-government, and in the long run the approach will prove counterproductive. This reinforces the need for industry to be formally organised and to develop an effective working relationship with relevant PICT government agencies. Establishing this relationship is a key objective of PHAMA.

Whilst there is frustration at the current state of MA there is also optimism (in some cases excessive optimism) within most industry groups that good potential for new markets exists. There is also a determination to ensure that industry becomes a key partner with government in the pursuit of improved MA arrangements. However, the time and resources required to co-ordinate activities and work with government, and due recognition by government that industry has a valid role to play, are key constraints on industry participation.

- SECRETARIAT OF THE PACIFIC COMMUNITY

Negotiating market access is a sovereign responsibility that lies with PICT governments. Other aspects related to obtaining, maintaining and improving market access (such as implementation of agreed market access protocols, R&D, training, development of pest lists and animal and plant health status-related databases, and extension) are provided in varying degrees by national government agencies and by SPC-LRD which has a mandate to help ‘increase trade by building trade capacity and strengthening PICT biosecurity services in the region’. In effect, the regional mandate of SPC recognises that technical capacity supplementation is a necessity for many PICTs. The smaller PICTs in particular will always lack the skills and capacity to address biosecurity issues and progress MA arrangements on their own, and are therefore likely to remain dependent on SPC’s assistance, or support from other ‘third party’ service providers, in the longer term.

  - Organisational Structure and Objectives

SPC, formerly known as the South Pacific Commission, was founded in 1947 with the aim of promoting and advancing the social and economic development and well-being of Pacific Island Peoples. Core functions include capacity building, resolution of cross-boundary issues and technical capacity supplementation. The organisation is currently divided into three divisions: Land Resources, Marine Resources and Social Resources. In early 2010, SPC will absorb the energy programme of the Secretariat of the Pacific Islands Applied Geoscience Commission (SOPAC) and merge with the South Pacific Board for Educational Assessment (SPBEA), at which time three additional divisions will be formed: Economic Development; Science and Technology; and Educational Assessment. SPC is headquartered in Noumea, has regional offices in Fiji and the Federated States of Micronesia, and 14 field offices located throughout the Pacific Region. It is funded by a broad range of donor organisations, with the bulk of funding being project-tied.

The Land Resources Division (LRD) has three main objectives: (i) improved food and nutritional security; (ii) integrated and sustainable agricultural and forestry resource management and development; and (iii) improved biosecurity and increased trade in agriculture and forestry products. It is organised into seven thematic and three support groups.

Regional biosecurity and trade facilitation services are delivered mainly through the Biosecurity and Trade Facilitation Group (BAT), which will be a key player in the implementation of PHAMA. BAT aims to: (i) facilitate trade and tourism while minimising the threat to biological diversity, agricultural production, food security and public health from exotic pests and diseases; (ii) serve as secretariat to the Pacific Plant Protection Organisation (PPPO); (iii) strengthen national capacity to undertake economic and financial analyses of opportunities for increased domestic and export trade; (iv) develop and promote sustainable and efficient post-harvest technologies; (v) improve administrative frameworks for effective delivery of biosecurity services; (vi) develop emergency response and contingency plans for pest incursions and outbreaks; and (vii) conduct surveillance and monitoring of quarantine pests including fruit flies.

Other more science-oriented thematic groups of LRD also play an important role in relation to delivery of SPC’s regional biosecurity and trade facilitation services. In particular, the specialist plant protection scientists and veterinarians of the Plant Health and Animal Health and Production Groups assist PICTs by undertaking regular surveys of plant pests and animal diseases; updating and managing pest and disease lists; maintaining information databases such as the Pacific Pest List Databse; sourcing or producing and distributing publications and other information resources on plant and animal health status; and supporting and building the surveillance and diagnostic capacity of national biosecurity (quarantine, plant and animal health) personnel.

Biosecurity and trade facilitation services related to coastal fisheries remain the responsibility of SPC’s Marine Resources Division; with responsibility for oceanic fisheries resting largely with the Pacific Islands Forum Fisheries Agency (FFA).

  - Staffing

BAT currently has five staff (a Biosecurity and Trade Facilitation Adviser, Biosecurity and Trade Facilitation Officer, a Biosecurity Technician, a Biosecurity Information Facility (BIF) Technician, and a Biosecurity Assistant as the helpdesk person) as well as access to about 20 relevant professional staff in the Plant Health (8) and Animal Health and Production (12) thematic groups. All of the BAT staff positions are project-funded, with funding for all positions due to finish by mid 2010. In contrast, the Adviser positions in the Plant Health and Animal Health and Production thematic groups are presently core-funded positions. BAT and the Plant Health thematic groups are also faced with recruiting professional staff to fill a number of key positions that have been recently vacated and/or will shortly be vacated.

  - Funding

Funding for the 2009 BAT workplan amounts to just over 800,000 AUD, from a range of donors. The funding is entirely project tied, with no core funding. Most funding allocations are one-off allocations or are due to phase out by mid-2010 – in effect, until PHAMA (and two other programs under preparation) are confirmed and commence, funding for BAT activities dries up from June 2010.

Major projects managed by LRD in which BAT (or equivalent) has played or is playing a role include the Project on the Regional Management of Fruit Flies in the Pacific (RMFFP, 1990 to 2000); Pacific Regional Economic Integration Project (PACREIP, 2004 to June 2010); the Regional Trade Facilitation Programme (RTFP, 2004 to 2009); the Plant Protection in the Pacific Project (2002 to 2008), and Facilitating Agricultural Commodity Trade (FACT, 2008 to 2012). It is also involved in a range of smaller activities.

There are two projects soon to be implemented in which BAT will or may be expected to play a significant role. One, to be implemented by SPC, builds on FACT (FACT II, 5 year program beginning 2010). The second, the Pacific Regional Aid-for-Trade Technical Assistance Program (PRAfTAP, 2010 to 2014) is the successor to PACREIP. From project proposal documentation available in late August 2009, it appears that both these projects are likely to support areas of activity allowing the continuation and expansion of some of BAT’s core biosecurity and trade facilitation work. Some ambiguity remains however, with the designs yet to be finalised and approved.

- OTHER REGIONAL ORGANISATIONS

  - Pacific Plant Protection Organisation (PPPO)

The PPPO was founded in October 1994 as one of the Regional Plant Protection Organisations under the International Plant Protection Convention. All Members of the Pacific Community (27 in total, including 22 PICTs and 5 founding members) are Members. PPPO exists to provide advice on phytosanitary measures in order to facilitate trade without jeopardizing the plant health status of the importing Members and countries. It is responsible for co-ordinating harmonization of phytosanitary measures in the Region; fostering co-operation in plant protection and other phytosanitary matters among and between Members and countries and organisations outside the Pacific region; and acting for Members in developing contacts with, and where appropriate providing input into, other global and regional organisations that have authority in such matters.

The LRD of SPC is designated to be the PPPO’s Secretariat and run the day-to-day affairs of the organisation. As such, LRD is required to pay particular attention to ensuring that the views and concerns of Pacific members are adequately taken into account in the development and implementation of global phytosanitary measures. The PPPO should be a key player in driving regional MA issues and promoting regional trade. However, the level of effectiveness in these areas is limited by resource and human capacity issues common to many other key PICT institutions. Ongoing funding for SPC to provide Secretariat services is also an issue.

  - Pacific Islands Forum

The Suva-based Pacific Islands Forum (PIF), formerly known as the South Pacific Forum, is now recognised as the premier regional policy-making body of the self-governing states in the Pacific. It comprises the heads of government who meet annually to develop collective responses to regional matters, including economic development and trade. The Forum’s administrative arm is known as the Forum Secretariat (PIFS). In contrast, SPC is a technical, non-political organisation that provides advisory and consultative services to its 27 members and facilitates co-operation with regional and international organisations.

  - Pacific Islands Trade and Investment Commission (PITIC)

PITIC is the international agency of the PIFS. It has four overseas offices (in Australia, NZ, China and Japan), funded by the respective countries in which they are located. It aims to contribute to sustainable economic advancement of PIF countries by supporting private sector development in the region. PITIC works closely with a network of government, peak industry bodies and non-government agencies to deliver a range of practical trade, export, tourism and investment support services to businesses in the Pacific region, similar in many ways to those that might be provided by a Trade Commission. The different PITIC offices have a slightly different focus depending on their individual strategic plans. These functions can include provision of market assessment and development services for ‘export ready’ companies; trade promotion activities; and identification of possible importers/import country development partners. In the future it is possible that the PITIC network will be expanded to include India, Taiwan, and Europe.

Utilisation of PITIC resources by agricultural and horticultural export industries is generally uncoordinated and lacks strategic focus. PHAMA could help to provide this additional focus based on the clear identification of priorities assessed to have greatest merit, linked with a formal program of activities to gain, improve and maintain access for these priorities. Depending on strategic direction and capacity, the PITIC offices could be valuable partners in carrying out export market assessments and feasibility studies, and in providing support to new exporters entering new markets.

  - Pacific Islands Private Sector Organisation (PIPSO)

PIPSO, established in 2006 under PIFS, aims to facilitate policy dialogue (including trade dialogue) within the private sector at a regional level. PIPSO members include peak National Private Sector Organisations (NPSOs) for each of the 14 forum island countries (usually the National Chambers of Commerce). To date agriculture and horticulture have been poorly represented within these higher-level fora. The efforts of PHAMA will directly improve the articulation of agricultural and horticultural MA issues, which should provide an important input to the ongoing trade dialogue efforts of the NPSOs and PIPSO.

APPENDIX 4

RELEVANT DONOR-FUNDED PROGRAMS AND PROJECTS

| Name of Program/ Project | Donor, Funding, Duration and Executing Agency | Geographic Focus | Brief Description | Possible Linkages with PHAMA |
| --- | --- | --- | --- | --- |
| Project on the Regional Management of Fruit Flies in the Pacific (RMFFP) | - FAO, AusAID, UNDP and SPC – Phase 1 (1990-1993); AusAID, UNDP, NZ Government – Phase 2 (1994-April 1997); AusAID, UNDP, NZ Government – Phase 3 (May 1997-December 2000). - Phase 1 US$0.86m; Phase 2 US$1.15m and Phase 3 US$1.77m - 1990 to 2000. - Executed by national government agencies. | - Phase 1: Fiji, Cook Islands, Western Samoa, Tonga - Phase 2: Four countries included in Phase 1 PLUS the Federated States of Micronesia, Solomon Islands and Vanuatu - Phase 3: 22 Pacific Island Countries and Territories (PICTs) | - Aimed to ameliorate the problem of fruit flies, initially to develop export markets for locally grown fresh produce by (i) upgrading technical knowledge about fruit flies and ensuring that plant protection, quarantine, and private sector personnel understood the impact of fruit flies on the production and export of fresh fruit and vegetables, (ii) reducing the extent of fruit fly damage in fresh fruit and fleshy vegetables caused by fruit flies, and strengthening the capacity of quarantine services and the private sector to overcome quarantine restrictions imposed by importing countries on Pacific island exports of fresh fruit and fleshy vegetables. | - Good example of the benefits of a more product focused approach rather than a generic capacity-building approach. - Maintaining and establishing new export markets of fresh fruit and fleshy vegetables through PHAMA requires maintenance of the fruit fly surveillance system(s) established as part of the RMFFP. |
| Pacific Agreement on Closer Economic Relations – Regional Trade Facilitation Programme (PACER-RTFP) | - Australia and New Zealand - New Zealand has committed to providing $1m over three years. - 2004 to 2009 - The quarantine component of the RTFP is executed by SPC’s Land Resources Division, Plant Health, Animal Health and Biosecurity and Trade Facilitation thematic teams. | - Forum Island Countries (FICs) | - The Pacific Agreement on Closer Economic Relations (PACER) FICs and Australia/New Zealand recognises that trade can play a crucial role in promoting economic growth. - RTFP includes several components designed to promote trade and address some of the constraints to increased trade in the region. - RTFP seeks to build national knowledge and capacity in quarantine, customs and product standards and conformance. - Note: Although not funded under RTFP, SPC in partnership with Fiji MoA has developed SPS export commodity pathway systems to facilitate the trade of fresh commodity exports. This has included the development of training materials, the training of farmers, exporters, extension and quarantine officers. | - With PACER-RTFP concluding at the end of 2009, any direct linkage to PHAMA is likely to be through PACER-Plus. - Possibility of unutilized NZAID budget allocations to RTFP that could rolled into PHAMA???? |
| PACER-Plus |  | - FICs, Australia and New Zealand | - PACER envisages the development of a trade and economic agreement between Australia,NZ and FICs. This new agreement called PACER-Plus, includes trade capacity building and trade development assistance to strengthen PICTs ability to trade. | - PACER-Plus is expected to include individual schedules of commitments and tailored trade development assistance taking into account the particular circumstances of each country. As such, PHAMA and PARDI could be considered such commitments. |
| Centre for Import-Export Technical Facility (IMPEXTEK) | - PPPO initiative funded under PACER-RTFP - More-or-less supported through PACER-RTFP and EU-PPP - 2005 to 2009 - Implemented by the Biosecurity and Trade Support (BATS) component of SPC’s Land Resources Division | - 22 PICTs of Melanesia, Micronesia and Polynesia | - Establishment of a helpdesk facility with the objective to assist PICTs with technical advice and support on (i) import risk analysis and development of national import conditions/protocols, (ii) export/market access facilitation, and (iii) general biosecurity and biosecurity related trade matters. | - PHAMA will pick up the funding of some of these on-going regional functions. |
| Pacific Regional Economic Integration Project (PACREIP) | - European Commission - €9.2m plus €2m top up funding was approved in March 2006 - 2004 to 2009, extended to June 2010 - Implementing agencies are the Pacific Islands Forum Secretariat (PIFS), the South Pacific Tourism Organisation (SPTO), SPC and the Secretariat of the Pacific Regional Environment Programme (SPREP). | - Pacific ACP countries | - The overall objective of PACREIP: the sustainable development of the Pacific ACP economies as an economically integrated region. Furthermore, Pacific ACP countries accept that an integrated regional approach is the most effective strategy for engagement in the global economy. As a first step towards a more comprehensive integration, the Pacific ACP countries have established the Pacific Island Countries Trade Agreement (PICTA), providing for free trade in goods. - PACREIP supports regional economic integration of the Pacific ACP economies in two important ways: (i) consolidation of the Pacific ACP economies as an integrated regional unit through the establishment of a free trade area covering the Pacific ACP countries, and (ii) engagement of the Pacific ACP countries as a regional unit in the wider regional and global processes, including the negotiation and subsequent operation of trade with developed country partners such as the EU, and also in multilateral negotiations at the WTO. | - PHAMA will promote increased regional trade in high value agricultural products under the PICTA framework. - Possible linkage in relation to negotiation of regional trade access mechanisms. |
| Pacific Regional Aid-for-Trade Technical Assistance Progamme (PRAfTAP) | - European Development Fund - US$18.6m - 4 years commencing in early 2010 - Pacific Island Forum Secretariat (PIFS) | - Pacific ACP States (PACPS), i.e. all 14 FICs plus Timor Leste | - PRAfTAP is a follow-up program to PACREIP - The overall objective of PRAfTAP is to contribute to the economic integration and sustainable development of the PACPS through AfT initiatives, and to improve the livelihoods of the people in the Pacific through the increased regional economic integration and expanded trade and investment opportunities. - Specifically, PRAfTAP is to strengthen the institutional and human resource capabilities of the PACPS to formulate and coordinate trade strategies, trade policy and regulations; to effectively participate in the multilateral, regional and bilateral negotiations; to promote the private sector participation in trade and investment and to benefit from AfT initiatives in the Pacific. | - PHAMA will promote increased regional trade in high value agricultural products under the PICTA framework. - Like PACREIP, possible linkage in relation to negotiation of regional trade access mechanisms. - PRAfTAP and “FACT II” (see below) relate to strengthening national capacity to comply with international standards and other technical and SPS requirements and/or improving market access for PICTs’ exports of farmed and natural resources. As such, both PRAfTAP and “FACT II” are likely to support areas of activity in SPC’s BAT that complement PHAMA’s Component 4 activities. Component 4 design will be reviewed once the PRAfTAP design is finalised to ensure that no duplication occurs. |
| Plant Protection in the Pacific Project (EU-PPP) and ADDPIC [funded by two different financing agreements but operated as one project] | - European Development Fund - EU-PPP – duration of 4 years with funding of €4.3m (ACP: €3.2m; OCT €1.1m) starting 2002; ADDPIC – duration of 4 years with funding of €1.5m starting March 2004 to be finished by 31 December 2007 but extended to 31 December 2008. - 2002 to 2008 collectively. - Implemented by the Secretariat of the Pacific Community (SPC) | - 8 Pacific ACP countries (Fiji, Kiribati, Papua New Guinea, Solomon Islands, Tonga, Tuvalu, Vanuatu and Western Samoa) and three Overseas Countries and Territories (OCT) in a special relationship to EU member states (French Polynesia, New Caledonia and Wallis and Futuna). ADDPIC project was to cover the 6 new ACP countries – Cook Islands, Federated States of Micronesia, Republic of the Marshall Islands, Nauru, Niue, Palau. | - The EU-PPP Project supports the plant protection and quarantine departments of eight Pacific ACP states and three OCT territories. It aims to facilitate quality food production and trade by minimizing pests. It provides technical advice, training, equipment, biocontrol, identification and information services. - The main objective of SPC’s “Biosecurity” component of the EU-PPP Project is to support the establishment of effective and sustainable quarantine services in the region. It involves working closely with the national quarantine services of the PICTs and focuses on the areas of compliance with international Phytosanitary standards, capacity building, strengthening and harmonisation of quarantine laws, emergency response planning for pest outbreaks, and increasing awareness of quarantine requirements amongst traders and the travelling public. | - PHAMA will directly build on the national-level capacity developed under the PPP Project, as well as regional capacity developed within SPC BAT. |
| Facilitating Agricultural Commodity Trade (FACT) Project | - EC, SPC and PICTs and Private Sector - €4.2m (EC €4m, SPC €150,000, PICTs and Private Sector €75,000) - Phase 1 – 2008 to 2012 (likely to be extended for an additional five years) - SPC Land Resources Division. | - 14 Pacific ACP states. | - The FACT Project will contribute to increased trade by Pacific ACP states (PACPs) by supporting enterprises within the existing commercial farming and forestry sector. - The aim of the FACT Project is to assist selected commercial ventures and producer groups to become export-oriented, market-driven enterprises that consistently supply overseas markets with competitive products. - FACT is involved with 14 enterprises (including cooperatives of farmers which cover small holders as well as processing facilities) selected for their export growth potential based on commercial criteria following a survey of the 14 PACPs. Remedial technical and financial support by the FACT Project of each enterprise will be based on deficiencies in the enterprise supply chain determined by detailed systems analysis conducted by independent agricultural production and marketing analysts.. | - PHAMA provides a potential mechanism for addressing technical market access issues that may arise in relation to the particular products/ enterprises being developed under FACT. |
| Enhanced Sustainable Livelihoods Through Facilitating Increased Trade and Product Diversification (referred to as “FACT II”) | - EC plus co-financing. - €13m (EC €9m, Co-financing €4m) - Five-year program beginning 2010 - SPC Land Resources Division, assisted by SPC’s Marine Resources Division. Implementing partners are PIFS, PIPSO, PITIC and FAO. | - Pacific ACP states and OCTs | - Builds on the FACT pilot project. - The objective is to facilitate an increase in consistency, quality, quantity and diversity of agricultural, forestry and aquaculture exports from Pacific ACP states and OCTs through improved production, processing and value adding practices, sanitary and phytosanitary (SPS) standards compliance, product and market diversification. - Among other matters, the project is expected to strengthen national capacities (through capacity building and capacity supplementation) of Pacific ACP states, OCTs and export enterprises to comply with international and other relevant SPS standards. | - PHAMA provides a potential mechanism for addressing technical market access issues that may arise in relation to the particular products/ enterprises being developed under FACT. - PRAfTAP and “FACT II” also relate to strengthening national capacity to comply with international standards and other technical and SPS requirements and/or improving market access for PICTs’ exports of farmed and natural resources. As such, both PRAfTAP and “FACT II” are likely to support areas of activity in SPC’s BAT that complement PHAMA’s Component 4 activities. Component 4 design will be reviewed once the “FACT II” design is finalised to ensure that no duplication occurs. |
| Pacific Agribusiness Research for Development Initiative (PARDI) | - Australia - Approximately A$12 million, including postgraduate training components - Initially 4 years - Funded and implemented by the Australian Centre for International Agricultural Research (ACIAR) | - Particular focus on Solomon Islands, Fiji, Samoa, Vanuatu, Tonga and Kiribati | - PARDI seeks to improve product competitiveness and market access to increase economic growth for the benefit of smallholder farmers and traders in the region. - Unlike PHAMA, PARDI is to focus on research designed to underpin the development of targeted high-value agriculture, fisheries and forestry value chains. - PARDI will foster resilient and sustainable supply chains through consistent production (quantities and timeliness) at affordable input costs and consistency of product quality, for a targeted number of products that have profitable or potentially profitable domestic and export markets. - PARDI will follow a highly targeted approach aimed at improving supply chain competitiveness for highest priority agricultural (including horticultural, fisheries and forestry) products into specific markets. | - PHAMA provides a potential mechanism for addressing technical market access issues that may arise in relation to the development of particular supply chains under PARDI. - PARDI and PHAMA are therefore highly complementary programs. |
| Samoa Quarantine Improvement Project (SQIP) | - AusAID - A$5.4m - 2001 to 2006 - Quarantine Division, Ministry of Agriculture, Forestry, Fisheries and Meteorology/AMC: URS Australia Pty Ltd | - Samoa | - SQIP was designed to address the need for technical institutional strengthening of the Quarantine Division within the Ministry of Agriculture, Forestry, Fisheries and Meteorology. - SQIP is reported to have successfully delivered a number of interventions, including those that have strengthened the management capacity of the organisation, encouraged and cemented the recruitment of young graduates with science based qualifications, enhanced the knowledge, abilities, skills and hence confidence of Quarantine Division staff, developed technical and procedural systems and manuals that will facilitate ongoing consistent operations, provided staff with the skills and expertise to effectively engage stakeholder and client consultations and facilitated significant public awareness activity. | - PHAMA will directly benefit from and build on the capacity developed through this project. |
| Private Sector Support Facility (PSSF) in Samoa | - NZAID, UNDP - NZ$0.6m year for 5 years allocated as Category A (SAT$20,000-50,000 for up to 2 years) or Category B (SAT$1,000-20,000) grants. - 2008 to 2012 - Small-medium sized private sector businesses. | - Samoa | - The ultimate objective of private sector development for Samoa is trade. Improving trade performance is expected to directly contribute to improving livelihoods and the quality of life of Samoan citizens. - The Private Sector Support Facility (PSSF) is to combine several previous funds supporting the private sector economy of Samoa, including the Tourism Support Fund (TSF), the Private Sector Support Allocation (PSSA) and the Structural Adjustment Facility (SAF). The PSSF aims to support proposals that are likely to have a strong economic impact for Samoa by way of grants as well as a series of Business Forums run by the private sector for the private sector. The dominant focus is on small to medium businesses employing and/or engaging the private sector economy. Target groups of the PSSF include (i) manufacturing and exporting, (ii) tourism, and (iii) producers groups. | - PHAMA provides a potential mechanism for addressing technical market access issues that may arise in relation to the development of particular products/enterprises under PSSF. |
| All ACP Agricultural Commodities Programme (AACP) | - EU-funded, working with five other international partner organisations namely, CFC, FAO, ITC, UNCTAD and the World Bank. - €45 million. - September 2007 to 2010. | - A February 2008 workshop in Apia, Samoa was the first of six sub-regional “kick-off” workshops that AAACP is to convene in the African, Caribbean and Pacific sub-regions. | - AACP aims to improve incomes and livelihoods of agricultural producers in Commodity Dependent Developing Countries within the ACP Group of Countries. It supports the participatory formulation of commodity chain strategies, sustainable commodity production and related policy development, access to regional and international markets, crop and market diversification, access to market-based commodity risk management instruments and, cooperation with donors to advance commodity strategies. | - PHAMA provides a potential mechanism for addressing technical market access issues that may arise in relation to the development of particular value chains targeted under AACP. |
| Fiji Papaya Project (part of the All ACP Agricultural Commodities Programme – Project GCP/INT/045/EC) | - EU-funded, with technical support from FAO. - Koko Siga (Fiji) Ltd. | - Fiji | - Activities making up this project are designed to integrate small farmers into the value chain for “Fiji Red” papaya and thus improve the industry’s competitiveness and increase the volume of produce sourced from small farmers. | - Papaya is a likely target product for PHAMA in Fiji. |
| Enterprise Challenge Fund (ECF) for the Pacific and South-East Asia | - AusAID - Grants of between A$100,000 to A$1.5m with the lead bidder contributing a minimum of 50% of the project costs; total AusAID funds A$10m. - 2007 to 2010. - For-profit private sector businesses (NGOs and other groups may be partners in a consortium led by a for-profit business). | - Phase 1 (beginning September 2007) calls for applications for grants from Fiji, Indonesia, Papua New Guinea and southern Philippines. - From March 2008 projects are being considered in Fiji, Papua New Guinea, southern Philippines, Vanuatu, Solomon Islands, Cambodia, Lao PDR, East Timor and selected provinces in Indonesia. - Projects can be led by for-profit businesses from any country, provided they have registered business entities in the target countries. | - The goal of ECF is to encourage private sector-led growth which will help reduce poverty. - Aimed at helping the private sector develop commercially successful ventures that otherwise will not get the chance to go to market. | - No direct linkages. PHAMA may provide improved market access for businesses applying for ECF development grants. |
| Regional Programme for Food Security (RPFS) in the Pacific | - Italian Government’s contribution to FAO’s Trust Fund for Food Security and Food Safety. - 2006-2010 for the expansion phase of the programme which began in 2002 with an estimated cost of US$11.47 million. | - FICs – Cook Islands, Federated States of Micronesia, Fiji, Kiribati, Nauru, Niue, Papua New Guinea, Palau, Republic of Marshall Islands, Samoa, Solomon Islands, Tonga, Tuvalu and Vanuatu. | - Designed to enable FICs to increase efficiency and sustainability of agriculture, improve food security and health, to facilitate trade in agricultural products and decrease impact of natural disasters. | - No direct linkages. Products/enterprises targeted under RPFS may be able to help inform the selection of target products under PHAMA. |
| Stable Exports Fund (STABEX – EU compensatory finance scheme) – Tonga | - European Development Fund (compensatory transfers of funds). - STABEX funds for vanilla, bananas, coconut and other products amount to almost €12 m. | - ACP countries. | - STABEX was set up in 1975 (at the time of the first Lome Convention) as one of the instruments of cooperation between the European Community and the ACP States and was likened to “insurance against a bad year”. - STABEX sought to limit, by means of compensatory transfers of funds, the damage resulting from a loss of earnings by ACP countries on exports to the EC of certain agricultural products – losses resulting from a fall in export prices and/or a fall in the quantities exported. - Compensatory transfers of funds not used as they were meant to be in Tonga, and although frozen, accumulated. Now to be used for projects associated with post harvest processing and husbandry of agricultural products. | - Unutilised STABEX funds in Tonga, already earmarked for export facilitation activities, could be utilized to address critical export infrastructure constraints (e.g. fumigation facilities, sanitary port handling facilities) that will also be central to successful implementation of PHAMA. |
| Vanuatu Agricultural Security (Quarantine) Project | - Ministry of Foreign Affairs and Trade (New Zealand) - NZ$2.8m - November 1994 to November 1999 (with a Continuing Links Phase January 2000 to June 2001). - Lincoln International was the management services contract. | - Vanuatu | - Aimed at upgrading plant and animal agricultural security and surveillance procedures in Vanuatu. - The objectives of the project were to assist Vanuatu export animal and plant products and to ensure that domestic agricultural production is protected from foreign pests and diseases. | - PHAMA will directly benefit from and build on the capacity developed under this Program. |
| FST/2004/055: Domestication and commercialization of Canarium indicum in Papua New Guinea | - ACIAR - A$0.6m - January 2006 to December 2009 - Agroforestry and Novel Crops Unit, James Cook University | - Papua New Guinea, Solomon Islands, Vanuatu | - The positive attributes of the canarium nut – a high value, nutritious, premium product with good processing attributes – led to the confirmation of Canarium indicum as a suitable candidate for domestication and commercialisation. - The project therefore aims to seek out, characterise, select and multiply Canarium trees in Papua New Guinea that have superior commercial traits for cultivar development and field tests. It also aims to improve market prospects for these products in Papua New Guinea, Solomon Islands and Vanuatu, deliver selected cultivars and training to the participating communities, and disseminate information to stimulate adoption. | - Canarium is a possible target product for PHAMA in Vanuatu and the Solomon Islands. |
| Development of a hot water dip treatment regime for Fijian taro exports to New Zealand Note: ACIAR is intending to support further research into hot water immersion treatment of root crops | - Pacific Cooperation Foundation (PCF, a charitable trust founded in 2002), Secretariat of the Pacific Community (SPC) - 2007 - SPC | - Fiji “and elsewhere” | - PCF is currently working with the SPC to trial a new hot water treatment for taro mite which will enable taro from Fiji and elsewhere in the region to enter New Zealand without the need for fumigation after arrival – which is costly and reduces both the quality of the taro and the return to the Pacific exporters. - SPC/CRGA 37 (07) (Committee of Representatives of Governments and Administrations Thirty-Seventh Meeting, Agenda Item 2.2.1 – Land Resources Division Overview Report for 2007 refers to “Market access and sources for new products were explored: … Research to identify a suitable hot-water dip treatment regime for Fiji taro exports to NZ continued, …” | - Insufficient information available at this stage to determine possible linkage. The activity provides a good example of how NOT to design and implement an R&D activity that is intended to address a particular market access issue. |
| Solomon Islands Rural Development Program (RDP) | - World Bank, as managing donor with European Union and Australia (through RAMSI) - US$20 million - 5-year program that began implementation in 2008. - Managed by the Ministry of Development Planning and Aid Coordination. | - Solomon Islands (initially piloted in four provinces – Choiseul, Temotu, Malaita and Western Province but expanding into all provinces in Year 3) | - The objective of the Solomon Islands RDP is to raise the living standards of rural households by establishing improved mechanisms for the delivery of priority economic ad social infrastructure and services by the public and private sectors. - Two specific components relate to improving agricultural services and rural business development. | - No direct linkages. PHAMA may provide improved market access for businesses applying for Supplemental Equity Facility grants under RDP. |
| Solomon Islands Rural Livelihoods Program (SIRLP), | - AusAID - Phase 1 A$40 million - Two-phase 10-year engagement with Phase 1 (5 years) beginning May 2010 - Component 1 of SIRLP is mainly delivered through local partners and involves four regional Focus Teams, while Component 2 is to be implemented in partnership with the Ministry of Rural Development and Indigenous Affairs (MRDIA) and involves a Rural Development Secretariat. | - Solomon Islands | - SIRLP builds off achievements and lessons of the Forest Management Program and the Agricultural Livelihoods component of the Community Sector Program. Essentially it is an expansion of current engagements – the Solomon Islands Forest Management Program II concluding in June 2009 and the Community Sector Program and its Agricultural Livelihoods component scheduled to finish in January 2010 – but with a strong M4P focus. - SIRLP is to integrate with those of the ongoing RDP. - SIRLP uses a strategic approach that integrates both livelihood and business analysis tools to identify innovative investments that sustainably improve livelihoods at the local level. | - No direct linkages. In time, PHAMA may provide improved market access for local SIRLP partners. |
| Productive Sector Growth Support Programme – Phase 1 Vanuatu (PSGSP-P1) Note: Information sourced mainly from Programme Description dated June 2009. | - EC plus other donors – AusAID and NZAID in the first instance. - €6.3m (EC €5.5m, AusAID €0.5m, NZAID €0.3m) - Initial 3-year phase (7-year programme in total). - Government of the Republic of Vanuatu (GoV), led by the Department of Strategic Policy, Planning and Aid Coordination (DSPPAC) but with other central and sector ministries, such as the Ministry of Agriculture, Quarantine, Forestry and Fisheries (MAQFF), closely involved. | - Vanuatu | - PSGSP-P1 is to increase the effectiveness of public, private and civil society institutions in supporting increased output and reduced inefficiencies in the productive sectors. - Initial interventions are likely to include direct investment in the improvement, expansion and operation of key public services including extension, biosecurity and export inspections and certification, and possibly inter-island shipping. | - No direct linkages identified at this stage. Detailed design work on individual components is to be undertaken under the initial phase of the Programme itself. |

APPENDIX 5

MANAGEMENT OF MARKET ACCESS ISSUES

AND PRELIMINARY WORKSHOP OUTCOMES

# INTRODUCTION

Market access prioritisation workshops were conducted in Fiji, Tonga and Vanuatu as a pre-start-up activity and as part of the design phase. A workshop was not conducted in the Solomon Islands as the Solomons visit was a pre-design visit (previously conducted in Fiji, Tonga, Samoa and Vanuatu as part of the 2008 pre-design program) to determine the suitability of the Solomons as part of the PHAMA program. The Samoan workshop was not conducted during the design phase of the program because of the earthquake and tsunami that devastated Samoa the week before the workshop was to be conducted. Rather than delay finalisation of the design it was determined that a Samoan workshop would be conducted at a later date (tentatively early 2010, prior to program start up) to ensure that design can be finalised and the program contracted without unnecessary delay.

The workshops provided government and industry stakeholders with an opportunity to:-

- discuss and provide comment on the proposed PHAMA design;

- provide an outline of the current in-country market access processes and issues;

- discuss and provide comment on the proposed PHAMA market access prioritisation process;

- identify and prioritise several key commodities following this prioritisation process;

- develop actions plans for progressing the top 1 or 2 identified market access commodities; and

- discuss and provide comment on the proposal to establish a Market Access Working Group (MAWG) (if not already established) as the national body to consider, prioritise and manage in-country PHAMA program delivery.

Workshop attendees were identified using interview records from the preliminary design phase, in-country information from Post, industry and government. The workshops sought to bring key government and industry market access stakeholders together to develop a partnership approach for the management of market access issues under the PHAMA program.

An outline of the PHAMA design, concepts and methods were provided as an introduction to the workshop and discussed by attendees. Workshop attendees confirmed that industry and government co-operation on market access issues in the past had been variable and ranged from non-existent to minimal; and that a structured and strategic approach to gaining and maintaining markets was generally lacking. There was strong support by all attendees for a focussed and prioritised approach to manage technical market access issues by an in-country co-ordinating body consisting of government and industry members. There was also acknowledgement that technical and secretariat support, provided by PHAMA, would be required to assist the co-ordinating body.

There was strong support for the establishment of combined industry and government market access MAWGs in all countries.  There was some concern raised regarding appropriate representation at the workshops and commodities considered as part of the prioritisation process. It was stressed to workshop participants that the initial workshops were merely the beginning of the PHAMA market access process. Further, that future MAWG membership and consideration of commodities were to be determined by the MAWG (with assistance from an in-country secretariat and PHAMA technical assistants (TA)) on an on-going basis. This approach was endorsed and there was agreement that the MAWG membership should be kept at about 10 participants to ensure MAWG functionality and effectiveness.

Attachment 2 provides a summary of workshop outcomes for each country.

# PROCESS FOR PRIORITISING MARKET ACCESS ISSUES

The prioritisation of market access issues according to a set of criteria based upon a very clear definition of the specific issue/s (new, improved or market maintenance), potential economic returns, capacity to supply, demand within a target country and research and development that may be required is essential to focus scarce market access resources in the exporting country and the regulatory authorities of the target market.

Without clear and relatively stable prioritisation of market access issues the regulatory authorities in the target market may devote resources on access requests where there is no eventual trade (due to lack of capacity to supply or inability of the exporting country to meet SPS requirements) or are unable to complete risk analysis for a specific commodity (this make take 1-5 years dependent upon the associated issues) due to continually changing priorities or insufficient information provided by the potential exporting country. This has often led to inefficient use of importing regulatory authorities resources and frustration by potential exporters due to the time taken to consider their access requests.

The prioritisation process discussed with workshop participants suggested consideration of following principles in deciding priorities (refer Attachment 1):-

- the need for a clear definition of the market access issue (new, improved or market maintenance);

- determination of demand for the commodity in the destination market;

- estimation of perceived benefits to the exporting country economy if markets are established, improved or maintained;

- determination of the current size of the industry and capacity to supply the target market;

- whether air or sea freight would be required and if available;

- determination of the pest and disease status of the commodity;

- identification of any commodity-specific infrastructure constraints to supply the market;

- identification of research and development requirements and costs; and

- estimation of possible timelines for gaining, maintaining or improving access.

The workshops discussed the principles outlined above and applied them to a range of current market access opportunities and issues suggested by participants. This exercise generated considerable discussion to clarify issues and determine priorities. There were many unanswered questions requiring further research. Importantly, some clear and commodity priorities emerged (high, medium and low), determined using the suggested prioritisation criteria and process. Further, there was strong agreement that a prioritisation approach for consideration of market access issues was a valuable tool to efficiently allocate scarce market access resources.

# PRELIMINARY PRIORITISATION OF MARKET ACCESS WORK

The workshops resulted in the preliminary identification of some clear potential priorities for future market access efforts, and in preliminary workplans detailing what needs to be done to address the particular market access issue/s identified for top priority areas. Worksheets detailing how the priorities were determined are presented in Attachment 3, and preliminary action plans in Attachment 4. Results are further summarised below.

## Fiji

### Products, Issues and Action plans

Fresh ginger, chillies and taro to Australia and canned beef (substituting Fiji beef for NZ beef) were the commodities and markets identified. Ginger and chillies are both new market access requests. A market access request for ginger has been lodged and prioritised by Biosecurity Australia as an ‘A’ priority. A market access submission is yet to be developed for chillies. Fiji currently has access for Taro and improvements to the market are sought. Canned beef, for regional trade is a market improvement issue.

Ginger

Key elements of the Action Plan include:

- confirmation of the status of work currently being done by BA;

- review the information package submitted to BA to determine any possible gaps and identify additional information that could be relevant;

- decide on a strategy to convince BA to formally commence the IRA;

- summarise the existing policy conditions for ginger exports to other countries to use in negotiations with BA; and

- conduct a scoping study on possible fall-back options for risk management.

The above package of actions was recommended as a pre-startup activity, subject to availability of funds and approval by AusAID.

Taro

Key elements of the Action Plan include:

- conduct a review of existing policy to determine why devitalisation is required by Australian quarantine authorities;

- prepare a formal request to AQIS to clarify why devitalisation is required;

- depending on the response:

  - determine if alternative devitalisation measures are available.

  - Review the literature on taro leaf blight and virus transmission pathways. Confirm the status and distribution of taro leaf blight and viruses in Fiji and Australia (literature review supplemented with survey work if necessary);

- prepare a formal request to AQIS and MAFBNZ seeking species specific information on  interception data for organisms found on taro (mite, weed seed, nematode contamination).

Chilli

Key elements of the Action Plan include:

- review the NZ non-host status standard and existing import policy for chilli, and the Asia Pacific Plant Protection Commission (APPPC)regional standard, to determine if additional R&D to prove non host status for fruit fly is required.

- review the APPPC regional standard and determine whether conduct of the additional R&D required is likely to be practical and cost effective;

- conduct market analysis to confirm market demand and financial viability of proposed export trade;

- depending on outcomes of above, develop a market access submission based on the NZ submission, including identification of preliminary risk management measures (acceptance of non-host status for fruit flies).

Beef (processed/canned using local beef as a substitute for imported NZ beef).

Key elements of the Action Plan include:

- conduct analysis to determine the economic benefits and financial viability of substituting NZ beef with local beef;

- determine the availability of suitable diagnostic service providers for BSE testing and the cost.

### Key R&D Issues

Ginger

No R&D issues were identified.

Taro

Surveys to determine the status of taro leaf blight and several viruses of possible quarantine concern to Australia may need to be conducted in Fiji. This will assist with discussions on the need for devitalisation of taro.

Alternative devitalisation methods may need to be investigated should Australian disease concerns be proven to be legitimate.

Chilli

Additional non host status trials may need to be conducted if the APPPC regional standard requires a larger sample size than the original NZ standard.

Beef

No R&D issues were identified.

## Tonga

### Products, Issues and Action Plans

Tomatoes to New Zealand using dimethoate dipping to manage fruit fly, watermelons to New Zealand under winter window arrangements and processed frozen root crops to Australia and Japan were the commodities and markets identified. It should be noted that Tonga currently has access for tomatoes and watermelons to New Zealand. It is the phytosanitary treatments of dimethoate dipping and export under winter window arrangements that Tonga is seeking approval from NZ for.

Tomatoes

Key elements of the Action Plan include:

- confirmation of the status of current review by Australian authorities on the use of dimethoate dip, the likely outcome and anticipated impact upon the use of dimethoate for commodities for human consumption;

- if the use of the chemical is likely to remain an acceptable treatment method, Tongan quarantine officials to confirm with NZ quarantine officials that this is a priority; and seek inclusion of the issue on the NZ workplan;

- determine current import policies for Australia and NZ using dimethoate dipping and the fruit fly species that are covered by this protocol;

- determine if additional R&D on other fruit fly species present in Tonga is required;

- implement the required R&D on additional fruit fly species;

- upgrade the existing airport facilities to provide for dipping;

- develop and provide dip operator training; and

- develop industry standards, manuals and training for production of suitable tomato varieties.

Watermelons

Key elements of the Action Plan include:

- clarify the research protocol required by NZ quarantine authorities for acceptance of winter window arrangements with respect to fruit fly species of quarantine concern from Tonga;

- review the relevant winter window research that has been previously completed from other countries seeking access into NZ using this risk management strategy;

- Tongan quarantine authorities to confirm that this issue is a market access priority; and seek inclusion of the issue on the NZ workplan;

- develop a market access submission using the Australian winter window submission as template (if appropriate);

- develop the in-field management strategies required to maintain access, including relevant documentation, training materials, training for producers, extension officers and inspectors;

- develop industry quality standards and manuals and provide training.

Frozen root crops

Key elements of the Action Plan include:

- finalisation of  market assessments and surveys (including market demand, product and packaging requirements, labelling requirements, product quality standards and financial viability of the proposed market).

- assess future processing facility requirements, including the ability and cost to increase processing and production capacity;

- clarify status of Australia and NZ food safety authorities current review of acceptable cyanide levels for cassava;

- determine a cost effective and efficient service provider for chemical residues and nutritional analysis (determine the feasibility of establishing adequately resourced laboratory facilities in Tonga); and

- develop HACCP based food processing standards and procedures for root crops with associated training in implementation requirements.

### Key R&D Issues

Tomatoes

Research into the efficacy of dimethoate dipping on tomatoes for Tongan fruit fly species may need to be conducted dependent upon fruit fly species that had been investigated previously and responses from NZ regulatory authorities regarding their data requirements.

Watermelons

R&D requirements were identified as follows:

- conduct in field trials to develop procedures to confirm that no infestation of watermelons occurs during the Tongan winter months and possibly conduct climatic trials on Tongan fruit fly species to confirm that they would not be able to survive NZ winter conditions;

- develop in field management systems for fruit flies to meet NZ phytosanitary requirements for ongoing market access and the relevant documentation and training manuals for producers, extension officers and inspectors.

Frozen root crops

R&D requirements were identified as follows:

- finalise market analysis work currently underway; and

- conduct cassava varietal trials to identify low cyanide cassava varieties, if required.

## Vanuatu

### Products, Issues and Action Plans

Kava to New Caledonia as dried product and processed canarium kernel into new Asian markets were the commodities and markets identified. Kava was confirmed to be an existing market access issue where improvements in the quality of the kava would help to ensure continued market access. The processed canarium kernel into Asian markets was a new market access request.

Kava

An action plan with timelines was not able to be developed for kava at this stage as it was identified that additional information was required. However, it was agreed that an initial scoping study to be conducted as the next step.

Canarium nuts

An action plan was not determined due to time constraints.

### Key R&D Issues

Kava

Conduct a scoping study to investigate the following to assist with project planning:

- possible price incentives/disincentives to promote the production of quality product;

- investigation of the legal/regulatory framework including the Kava Act;

- assess Vanuatu’s capacity for carrying out the necessary food quality assessment work;

- assess current industry compliance with the CODEX Kava Standard and any additional measures needed to comply;

R&D requirements were identified as follows:

- develop a system of grower accreditation, audit and verification to ensure production of preferred kava varieties,

- develop a method for processing product that maintains food quality and safety standards and ensures varietal separation;

- determine a cost effective and efficient laboratory service provider for food quality testing work and upgrade Vanuatu resources if viable;

- finalise development of the CODEX Kava Standard to assist determination of whether kava is a food or pharmaceutical product; and

- develop national product standards and associated extension materials for production of high quality kava varieties.

Canarium nuts

Work is currently underway in Australia to determine the composition of the nut and various other nutritional and food safety aspects, financed by AusAID.

Additional R&D requirements were identified as follows:

- develop information packages to assist producers and processors understand and comply with relevant food safety standards;

- develop national product standards and ‘Best Practice’ codes for harvesting and processing the nuts; and

- develop training and communicate relevant extension materials.

## Samoa

The workshop was cancelled in Samoa due to the tsunami that occurred the week before the workshop was to be conducted. Rather than delay finalisation of the design it is recommended that the Samoan workshop be rescheduled after the PDD has been finalised, but before program startup, possibly in January/ February 2010. This will ensure that design can be finalised and the program contracted in line with the original schedule.

## Solomon Islands

The workshop was not conducted in the Solomons Islands as the Solomons visit was a pre-design visit (previously conducted in Fiji, Tonga, Samoa and Vanuatu as part of the 2008 pre-design Mission). This visit was undertaken to determine the suitability of the Solomons for inclusion within the PHAMA program. It is recommended that a workshop be conducted after design finalisation but before program startup, possibly in January/ February 2010 in conjunction with the re-scheduled workshop in Samoa.

# PROPOSED INSTITUTIONAL ARRANGEMENTS FOR PROGRESSING MARKET ACCESS

The concept of a MAWG consisting of government officials and industry representatives to prioritise market access issues and act as the in-country PHAMA coordination body, was presented to the workshop. This concept is based on existing examples of similar structures within several successful exporting countries, including Australia, New Zealand and the United States.

It was agreed that MAWG membership will include representatives from relevant government departments with market access responsibilities (e.g. Departments of Trade, Agriculture and Quarantine,), as well as the private sector (e.g. producer organisations, exporters, relevant community groups, Chamber of Commerce). In order to ensure effective operation, the group will be limited to a maximum of 10 members. Members should have a direct responsibility and passion for progressing MA issues. Private sector representatives should be cross-sectoral as far as possible. Additional members with specific sub-sectoral interests or particular expertise will be seconded on an as-required basis.

Government’s responsibility to conduct bilateral market access negotiations and industries’ operational knowledge and determination to gain and maintain new markets necessitates a partnership approach within the MAWG to ensure successful market access outcomes. Further, it was stressed that PHAMA would seek to utilise existing structures if they are present and suitable for the purpose, rather than establish new working groups.

The concept of a MAWG was strongly endorsed by the workshop members. Non government participants consistently expressed concern at the lack of government and industry dialogue on market access issues.

## Existing Institutional Arrangements

Current institutional arrangements for identifying and progressing market access issues in target PICTs are as follows:

- Fiji has several strong private sector groups seeking to progress market access issues but there is no MAWG in operation;

- The Solomon Islands has several small enterprises seeking to establish export markets but there is no MAWG in operation;

- Tonga has several strong industry groups, the most prominent being GROFED claiming national representation of the horticultural industry. GROFED and the Ministry of Labour, Commerce and Industry have both recently initiated the development of MAWGs along similar lines to those proposed by PHAMA. Both MAWGs are to be chaired by the Minister for Labour, Commerce and Industry; have similar memberships and functions. It was agreed that having two MAWGs operating in parallel would not be appropriate and industry and government should resolve this issue to ensure one body was available for determination of market access issues;

- Samoan — assessment pending.

- Vanuatu has several small enterprises seeking to pursue market access opportunities and a higher level National Trade Facilitation Committee (NTFC) established under PACER-RTFP. However, there is no MAWG in operation. Workshop participants suggested that a MAWG could be established as a working group to the NTFC.

It was agreed by all workshop participants that a MAWG consisting of a small number of government and industry members who have direct market access involvement, provided with secretariat and technical support, would be a very strong mechanism for implementation of the PHAMA program in-country.

## Market Access Working Groups

### Role and function

A MAWG will be established in each country where Component 1-3 activities are being implemented. MAWGs are intended to provide a practical working partnership between government and the private sector to manage the resolution of MA issues that are to be addressed by PHAMA. Main responsibilities will include:

- Increasing coordination between government and industry in the management of MA issues.

- Prioritising MA issues to be addressed by the program.

- Developing strategies and action plans to address these priorities, as well as an associated communication strategy.

- Identifying specific MA research and development needs.

- Providing briefings to relevant government agencies and industry on MA issues.

- Identifying and promoting linkages between PHAMA and other government and donor programs.

- Facilitating the mobilisation of government and industry resources in line with identified MA priorities.

- Actively communicating the work of the MAWG to government and private sector partners.

- Promoting successes in advancing MA for priority agricultural or horticultural products and/or establishment of new trade or increasing exports of priority products.

### Membership

Membership will include representatives from relevant government departments with MA responsibilities (e.g. Departments of Trade, Agriculture and Quarantine), as well as the private sector (e.g. producer organisations, exporters, relevant community groups, Chamber of Commerce). In order to ensure effective operation, the group will be limited to a maximum of 10 members. Members should have a direct responsibility and passion for progressing MA issues. Private sector representatives should be cross-sectoral as far as possible. Additional members with specific sub-sectoral interests or particular expertise will be seconded on an as-required basis.

Membership should initially be drawn from participants in the pre-startup workshops (see Attachment 2 for details). Additional members should be included if additional skills and representation are required. Membership from specific government departments, industries or relevant community groups has not been specified. Rather, members should have a strong market access focus, drive and enthusiasm. Willingness to devote additional time to MAWG requirements is essential. Since market access tends to be a dynamic and on-going process, additional members with specific skills and expertise should be invited to provide input to the MAWG as required.

### Operational guidelines

The MAWGs should meet face to face a minimum of two and a maximum of four times per year. Meetings should be no longer than 1.5 days to allow travelling time for attendees, taking a total of 2 days per meeting out of members’ existing work programs. Two of these meetings should occur immediately prior to development of annual work plans and six monthly progress reports by the PHAMA PMO, to ensure co-ordination of planning and reporting processes from the MAWG level upwards.

A chairperson will be elected by the MAWG. This position may be rotated on an annual basis if suitable MAWG members are available and if annual rotation is desired by the MAWG.

The PHAMA National Market Access Coordinators (NMACs) (see below) will fill the role of Secretary.

Meeting dates will be determined by the Secretary in consultation with members, at least six weeks prior to a proposed meeting. The Secretary will develop a meeting agenda and the relevant meeting papers supporting each agenda item in consultation with the MAWG. The meeting papers and agenda will be distributed to the members two weeks prior to the meeting, where possible.

Each member will have a casting vote on market access issues under consideration. Observers to the meetings and the Secretary will not have voting rights. Recommendations from the MAWG are to be forwarded to the PHAMA PMO which will consider each recommendation (and associated resource requirements) and provide the final endorsement, or request additional information, as required.

The MAWG may consider new market access requests, requests for improvement to existing markets (sanitary or phytosanitary protocols, food quality or food safety issues), research and development issues related to market access, or any other issues thought to be related to technical market access. In instances where the issue is considered beyond the scope of PHAMA or where the MAWG is unable to determine its status, the issue will be referred to the PHAMA PMO for further consideration. Those issues considered to be outside of the PHAMA scope will be referred by the PMO to other programs for assistance, where possible.

## Secretariat support for the MAWGs

PHAMA will provide secretariat and technical support for the operation of the MAWGs through the PMO and the National Market Access Coordinators (NMACs – see section 4.3.1 below). Key areas of support will include general administrative and budget support for the operation of the MAWG; organisation of meetings and agendas; coordination of MA activities being implemented; promoting communication and coordination between members; and provision of technical support to progress identified high-priority MA issues. Ensuring effective communication between group members will be essential, and will form an integral part of a communication strategy to be developed in conjunction with each MAWG on establishment.

### National Market Access Coordinators

The NMACs form a critical link in the program management structure. A full-time in-country NMAC will be appointed for Fiji, Tonga and Samoa. One full-time position will be shared between the Solomon Islands and Vanuatu due to the anticipated reduced volume of market access activities in these two countries, at least in the early stages of PHAMA. This part time arrangement for shared secretariat services between the Solomon’s and Vanuatu will be revised if required later in the Program. The positions will be funded and co-ordinated by the PHAMA PMO.

Key responsibilities of the NMACs will include:

- Providing secretariat support to the MAWG, including convening and coordinating MAWG meetings.

- Facilitating communication and coordination between MAWG members.

- Providing an operational linkage between the MAWG, the PMO, and SPC.

- Assisting the MAWG with the development of annual workplans, in line with PMO requirements.

- Monitoring the implementation of activities being funded by the program, in line with PMO requirements.

- Coordinating with other MA and supply chain development activities, including other donor-sponsored initiatives.

- Working with emerging exporters of priority products to build capacity and confidence in the dynamics of export procedures.

The NMACs will be locally recruited by the PHAMA PMO under 2-year renewable contracts, and will report to the PMO. Candidates will require good communication skills at industry and government levels and an ability to organise and manage a small group of executive members. Importantly, the NMACs must also have a basic understanding of the technical issues under consideration. Detailed technical knowledge is not expected but the ability to understand and communicate issues to the MAWG, TA staff and the MC will be required.

### Secretariat location

The Secretariat will be housed within an appropriate institution in each country, to be finalised pre-startup. Preliminary suggestions regarding location are as follows:

- Fiji – secretariat office to be provided within Nature’s Way Co-operative;

- Samoa – unable to conduct workshop prior to design finalisation;

- Solomons Islands – part time secretariat office to be based in Port Villa;

- Tonga – GROFED have indicated a strong preference for the secretariat to be located within their Nukualofa office;

- Vanuatu – the Department of Trade and Industries, Industries Division expressed interest in and chairing the MAWG.

### Operational support

In addition to cover the salary costs of the NMAC positions, PHAMA will provide operational support in the following areas (needs further discussion and refinement):

- Motorcycle; basic office equipment (computer/ printer; modem; software; small photocopier) and basic set of office furniture for each office;

- local transport allowance for the NMACs;

- contribution to office overheads (rental, power, water supply);

- communication costs;

- printing and report preparation costs;

- meeting costs, including direct travel and accommodation allowances.

Operating budget will be held by the NMAC on behalf of the PMO. TA contracts and budget will be managed directly by the PMO, in line with priorities established by the MAWGs and endorsed by the PMO.

ATTACHMENT 1: MARKET ACCESS PRIORITISATION QUESTIONS AND EXPLANATORY TEXT PROVIDED AT WORKSHOPS

High, medium and low – may be used for preliminary prioritisation where data is not immediately available for questions requiring numerical values. Further detailed analysis and data may be required in cases where priorities cannot be determined using high, medium and low descriptors.

Brief explanation of prioritisation questions

Commodity – provide a clear description of the commodity. Species, variety (if applicable), physiological state (if applicable).

Commodity condition and market destination – fresh, semi processed, processed and the target market?

Is new or improved market access being sought?

If improved market access what is the market access issue that needs to be addressed? – provide a clear explanation of the issue (changed destination import conditions, negotiation of a new treatment protocol etc).

Present economic significance of exports of the commodity? – are there existing exports of this commodity, if so what is/are the value/s?

What are domestic production volumes? – are figures available?

Is there demand in the target market? – has market research been conducted?

Is the proposed trade financially viable? – will expected market returns provide sufficient profit for industry?

Is there sufficient production capacity to supply the export market? – is there sufficient production capacity or is production able to expand to meet new market demand?

Are there industry-specific infrastructural requirements/ constraints to supply the target market? – must be industry specific rather than broad infrastructure requirements.

What is the estimated cost to address infrastructure restraints (if required)? – provide cost estimates of required infrastructure.

Are quarantine measures likely to be required for pests and diseases associated with the commodity? – is there a pest and disease list, if so what are the likely management measures required by the target market?

Are there any accepted management measures available for these pests? – is there existing policy or treatments that can be used to manage the identified pest and disease issues?

Are there any food safety issues? – provide a clear description of any food safety issues including possible chemical residue issues.

Are there accepted ways to address these food safety issues? – is there existing policy or data to address the identified food safety issues?

Are there product quality standards that need to be addressed? – provide a clear description of any food quality issues.

Is R&D required to address quarantine, food safety and product quality issue(s). – provide a description of R&D required, cost and time estimates.

Is the R&D realistically doable? - R&D cost and time estimates must be realistic and achievable (are there service providers to do the R&D?)

Will there be beneficial impacts for vulnerable groups such as rural households and women? This may the basis of ensuring access to PHAMA activities to vulnerable groups for example, women may be concentrated in particular sectors in different countries.

Is the request supported by government? – government support for determined market access priorities is crucial to achieve and maintain market access goals.

Is there private sector interest in exporting? – industry determination to achieve and develop market access priorities is essential for successful market access outcomes.

What priority does the Working Group give this market access work? – the working group to determine a priority rating (high, medium of low) for each commodity given the available information. If additional information is required to reasonably determine a priority the working group should highlight the specific information required.

APPENDIX 5

ATTACHMENT 2

WORKSHOP SUMMARIES

APPENDIX 6

ROLE OF SPC IN PROGRAM IMPLEMENTATION

COMPONENT 4 SPECIFICATION

# SPC’S ROLE IN RELATION TO BIOSECURITY AND TRADE FACILITATION

## Organisational Structure and Objectives

The Secretariat of the Pacific Community (SPC), formerly known as the South Pacific Commission, was founded in 1947 with the aim of promoting and advancing the social and economic development and well-being of Pacific Island Peoples. Core functions include capacity building, resolution of cross-boundary issues and technical capacity supplementation. The organisation is currently divided into three divisions: Land Resources, Marine Resources and Social Resources. However, changes that will add significantly to SPC's size and scope take effect in January 2010. With these changes, SPC becomes the lead coordinating agency for the regional energy sector, absorbing the energy programme of the Secretariat of the Pacific Islands Applied Geoscience Commission (SOPAC) into a new Economic Development Division of SPC including transport, infrastructure and communication. Furthermore, SOPAC’s core work programme becomes the SOPAC Science and Technology Division of SPC while a sixth division comprises the South Pacific Board for Educational Assessment (SPBEA) which is also to be merged with SPC.

SPC is headquartered in Noumea, has regional offices in Fiji and the Federated States of Micronesia, and 14 field offices located in the Cook Islands, French Polynesia, Kiribati, Marshall Islands, Nauru, Niue, Palau, Papua New Guinea, Samoa, Solomon Islands, Tonga, Tuvalu, Vanuatu, and Wallis and Futuna. SPC is funded by a broad range of donor organisations.

The Land Resources Division (LRD) has three main objectives: (i) improved food and nutritional security; (ii) integrated and sustainable agricultural and forestry resource management and development; and (iii) improved biosecurity and increased trade in agriculture and forestry products. It is organised into seven thematic and three support groups. Regional biosecurity and trade facilitation services are delivered mainly through the Biosecurity and Trade Facilitation Group (BAT), which aims to: (i) facilitate trade and tourism while minimising the threat to biological diversity, agricultural production, food security and public health from exotic pests and diseases; (ii) serve as secretariat to the Pacific Plant Protection Organisation (PPPO); (iii) strengthen national capacity to undertake economic and financial analyses of opportunities for increased domestic and export trade; (iv) develop and promote sustainable and efficient post-harvest technologies; (v) improve administrative frameworks for effective delivery of biosecurity services; (vi) develop emergency response and contingency plans for pest incursions and outbreaks; and (vii) conduct surveillance and monitoring of quarantine pests including fruit flies. As such, BAT will be a key LRD in the implementation of PHAMA.

Other more science-oriented thematic groups of LRD (especially Plant Health, and Animal Health and Production) also play an important role in relation to delivery of SPC’s regional biosecurity and trade facilitation services.

Biosecurity and trade facilitation services related to coastal fisheries remain the responsibility of SPC’s Marine Resources Division. Notably, responsibility for the Pacific Region’s oceanic fisheries, especially the tuna fisheries of 17 countries, rests largely with the Pacific Islands Forum Fisheries Agency (FFA).

Negotiating market access is a sovereign responsibility that lies with PICT governments. Other aspects related to obtaining, maintaining and improving market access, such as implementation of agreed MA protocols, R&D, training, development of pest lists and animal and plant health status-related databases, and extension are provided in varying degrees by national government agencies and by SPC-LRD which has a mandate to help ‘increase trade by building trade capacity and strengthening PICT biosecurity services in the region’. The boundary between national and regional roles shifts according to the resources available within PICT government agencies. Larger and better-resourced PICTs are more able to develop stand-alone national capacity in these areas; smaller PICTs are likely to remain largely dependent on external support from SPC and potentially from other ‘third party’ service providers in the longer term.

## Current Core Activities

BAT currently contributes to the delivery of a number of SPC-LRD outputs, namely:

- Development of sustainable forestry, agriculture and land use plans, policies, and legislation supported.

- Invasive species, pests, and disease problems identified and addressed, and capacity to respond at national and regional levels supported.

- National capacity to comply with international and other relevant standards strengthened.

- National capacity to increase domestic and export trade developed and strengthened.

- Sustainable and viable post-harvest technologies developed and promoted.

- Improved information available on plant and animal health status.

Current activities supported by BAT in line with these outputs include:

- Providing in-country national consultation, training, and if requested, legal assistance to 14 PACP countries on ‘new’ biosecurity legislation.

- Providing pest incursion response and quarantine pest surveillance services.

- Performing audits of national fruit fly surveillance systems, GPS mapping of PICTs fruit fly trap sites, and input fruit fly trap capture data in the Pacific Pest List Database (PPLD).

- Completing Phytosanitary Capacity Evaluations for the Federated States of Micronesia, Marshall Islands, Nauru, Papua New Guinea, and Vanuatu.

- Installing, commissioning and maintaining the various components of the Biosecurity Information Facility (BIF) in 15 PACP countries.

- Developing the capacity of national quarantine and plant protection services in biosecurity operations through targeted training and/or refresher training activities.

- Representing PICTs in relevant international fora such as the CPM and the RPPO Technical Consultation.

- Fulfilling SPC’s designated role as the Secretariat of the Pacific Plant Protection Organisation (PPPO).

- Facilitating the export of fresh produce by assisting PICTs, as requested, in the development of market access submissions, training of quarantine officers on export commodity pathways, development of quality standards and other related activities.

- Supporting PICTs, as requested, to undertake import risk analyses.

- Assisting with the development of post-harvest technologies, e.g. hot water immersion treatment for taro and cut flowers.

- Managing the PPLD and the Biosecurity Helpdesk services.

As noted in section 1.1 above, other thematic groups of LRD also play an important role in the delivery of SPC’s regional biosecurity and trade facilitation services. The specialist plant protection scientists and veterinarians of the Plant Health and Animal Health and Production Groups respectively, assist PICTs by:

- Undertaking regular surveys of plant pests and animal diseases.

- Updating and managing pest and disease lists.

- Maintaining information databases such as the Pacific Animal Health Information System (PAHIS) and the PPLD.

- Sourcing or producing and distributing publications and other information resources on plant and animal health status.

- Supporting and building the surveillance and diagnostic capacity of national biosecurity (quarantine, plant and animal health) personnel.

Up-to-date and validated data on plant and animal pests and diseases are essential for the development of national animal health and plant protection programmes, and the preparation of import risk analyses for imported goods and market access submissions for exports.

## Staffing

BAT currently has five staff (a Biosecurity and Trade Facilitation Adviser, Biosecurity and Trade Facilitation Officer, a Biosecurity Technician, a Biosecurity Information Facility (BIF) Technician, and a Biosecurity Assistant as the helpdesk person) as well as access to about 20 relevant professional staff in the Plant Health (8) and Animal Health and Production (12) thematic groups.

All of the BAT staff positions are project-funded; salaries for the Adviser, Officer and Assistant positions are funded through the Pacific Agreement on Closer Economic Relations – Regional Trade Facilitation Programme (PACER-RTFP), while recruitment of the two Technicians was supported through the Pacific Regional Economic Integration Project (PACREIP). PACER-RTFP concludes at the end of this year (2009) while PACREIP now comes to an end in June 2010. In contrast, the Adviser positions in the Plant Health and Animal Health and Production thematic groups are presently deemed to be core-funded positions. However, other positions in these groups are not core-funded. For example, following the appointment of two additional veterinarians the total number of SPC veterinarians is five but the two new positions are supported only by project funding that comes to an end in June 2010.

Currently, BAT and the Plant Health thematic groups are faced with the prospect of recruiting professionally-trained staff to fill positions that have been vacated and/or will shortly be vacated. The positions affected include: the Biosecurity and Trade Facilitation Adviser, Biosecurity Information Facility Technician, Senior Entomologist and Plant Pathologist. This does not take account of additional staffing needs identified outside existing positions.

## Funding and Funding Sources

Funding for the 2009 BAT workplan amounts to just over 800,000 AUD. The funding is entirely project tied, with no core funding. Currently, some activities undertaken by BAT staff are not funded.

Sources of funding in 2009 are:

PACREIP				173,000 EUR

PACER-RTFP				600,000 FJD

WTO-STDF				  53,000 USD

IPPC Secretariat			  21,000 USD

French Pacific Fund			  18,000 EUR

Papua New Guinea Government		260,000 PGK

TOTAL (approx)			800,000 AUD

PACER-RTFP concludes in December 2009. PACREIP was to have concluded at the same time but has been extended through to June 2010.  Funding from WTO-STDF, IPPC Secretariat, French Pacific Fund and the Papua New Guinea Government are all one-off allocations for specific activities in 2009.

## Linkage with Other Organisations

Pacific Islands Forum (PIF). The Pacific Islands Forum (PIF), formerly known as the South Pacific Forum, is now recognised as the premier regional policy-making body of the self-governing states in the Pacific. It comprises the heads of government who meet annually to develop collective responses to regional matters, including economic development. The Forum’s administrative arm is known as the Forum Secretariat (PIFS). In contrast, SPC is a technical, non-political organisation that provides advisory and consultative services to its 27 members and facilitates co-operation with regional and international organisations. SPC is in the process of implementing major organisational changes (referred to in section 1.1) under a reform process for regional institutions directed by Pacific Forum Leaders (and set out in the Regional Institutional Framework (RIF)).

Pacific Plant Protection Organisation (PPPO). The PPPO was founded in October 1994 by the South Pacific Conference (now Pacific Community Conference). All members of the Pacific Community are members of the Pacific Plant Protection Organisation. The Pacific Community consists of 27 members including 22 PICTs and 5 founding members. PPPO is one of the Regional Plant Protection Organisations established under the International Plant Protection Convention and exists to provide advice on phytosanitary measures in order to facilitate trade without jeopardizing the plant health status of the importing Members and countries. The LRD of SPC is designated to be the PPPO’s Secretariat and run the day-to-day affairs of the organisation. As such, LRD is required to pay particular attention to ensuring that the views and concerns of Pacific members are adequately taken into account in the development and implementation of global phytosanitary measures.

## Linkage with Other Programs

Major projects managed by LRD in which BAT (or equivalent) has played or is playing a role include the Project on the Regional Management of Fruit Flies in the Pacific (RMFFP, 1990 to 2000); Pacific Regional Economic Integration Project (PACREIP, 2004 to June 2010); the Regional Trade Facilitation Programme (RTFP, 2004 to 2009); the Plant Protection in the Pacific Project (2002 to 2008), and Facilitating Agricultural Commodity Trade (FACT, 2008 to 2012). It is also involved in a range of smaller activities.

There are two projects soon to be implemented in which BAT will or may be expected to play a significant role. One, to be implemented by SPC, builds on FACT and is entitled ‘Enhanced sustainable livelihoods through facilitating increased trade and product diversification’ (five year programme beginning 2010, referred to as ‘FACT II’). The second, the successor to PACREIP, is the Pacific Regional Aid-for-Trade Technical Assistance Programme (PRAfTAP) (four year programme beginning 2010) which is to be implemented by the PIF Secretariat. Aspects of both projects relate to strengthening national capacity to comply with international standards and other technical and sanitary and phytosanitary requirements and/or improving market access for PICTs’ (PACPs and OCTs specifically) exports of farmed and natural resources. From project proposal documentation available in late August 2009, it appears these projects are likely to support areas of activity allowing the continuation and expansion of some of BAT’s core biosecurity and trade facilitation work. Some ambiguity remains however, with the designs yet to be finalised and approved.

## Evaluation of SPC Performance

As noted in section 1.1, LRD’s BAT thematic group has been responsible for the delivery of regional biosecurity and trade facilitation services. The scope of the activities BAT has been involved in (refer section 1.2) is expansive and requires considerable technical/scientific expertise as well as operational experience to deliver effectively. On current staffing levels, BAT is below critical mass to honour its 2009 commitments to the PACREIP, PACER-RTFP and WTO-STDF projects let alone deliver the full set of outputs required of SPC-LRD by PICTs as part of its regional mandate.

In effect, the regional mandate of SPC recognises that technical capacity supplementation is a necessity for many PICTs. The smaller PICTs in particular will always lack the skills and capacity to address biosecurity issues and progress MA arrangements on their own, and are therefore likely to remain dependent on SPC’s assistance in the longer term. In reality, SPC-LRD is not well resourced to assist and generally lacks the necessary practical experience to tackle major biosecurity issues in the region (e.g. threat of invasive ants) or work on a day-to-day basis with national agencies to gain new export markets or improve existing export conditions. Nevertheless, as expressed by one SPC staff member in an unguarded moment, the ‘PICTs are very grateful for whatever they can get’ so SPC’s struggle to maintain core capacity appears to have gone unnoticed. As a minimum, it was suggested that seven staff are required in BAT for effective delivery of regional biosecurity and trade facilitation services. This is considered to be a conservative estimate and does not include provision of specialist diagnostic/analytical services required from plant protection and animal health scientists on an ongoing basis.

# CONSTRAINTS

## Key Constraints/Issues

- With present staffing arrangements, BAT lacks practical market access expertise that will be critical for the successful implementation of the Program. BAT also relies heavily on the Plant Health and Animal Health and Production thematic groups for the delivery of core biosecurity and trade facilitation services. While this potentially offers some advantages in terms of local access to specialist diagnostic/analytical capacity, it also means that resource constraints external to BAT could adversely affect implementation.

- Present funding arrangements for SPC in general and BAT in particular mean that provision of core regional services is not sustainable. The provision of medium-term ‘core funding’ (e.g., through PHAMA) for relevant and clearly defined market access-related information services would potentially improve the sustainability of such services to all PICTs.

- Although LRD is designated to be the PPPO’s Secretariat, no funding has been made available to run the day-to-day affairs of the organisation and ensure that the views and concerns of the 27 Pacific Community members are adequately taken into account in the development and implementation of global phytosanitary measures. In the absence of funding for the PPPO Secretariat, engagement of PICTs in international standard setting processes and their ability to trade in accordance with international standards is compromised.

- SPC’s lack of funding and personnel to oversee the coordination of surveillance programmes across the region could ultimately undermine the ability of PICTs to pursue export markets. Maintaining the integrity of fruit fly surveillance systems established during the RFFMP and/or invasive ant surveillance established more recently as part of the Pacific Ant Prevention Programme should not be regarded as ‘new’ activities funded on an ad hoc basis – they should have secure, long-term funding.

# COMPONENT 4 DESCRIPTION

Component 4 has been designed as a discrete set of activities, implementation of which will be managed by LRD. It involves providing SPS-related information services; facilitating PICTs’ involvement in the international SPS standard setting processes; as well as supporting some core surveillance and reporting systems. Such activities are best provided from regional level. They underpin market access for traded commodities and align with the overall strategic direction of the Program. In line with SPC’s regional mandate, implementation of these activities will not be limited to the five PICTs directly targeted under Components 1-3, but will be extended to all PICTs. PHAMA will be used as a vehicle for providing increased certainty of funding for these core services, which should go some way towards improving the quality of services provided.

## Component Outcome

SPC providing regional MA support services in an effective and efficient manner.

## Key Result Areas

Key result areas include:

- Provision of MA information services to national-level stakeholders improved.

- PICTs effectively engaged in relevant international fora (e.g. CPM, OIE, PPPO).

- MA-related surveillance and reporting maintained in accordance with international standards.

- Technical MA capacity within SPC enhanced.

## Activities

A set of discrete activities has been identified under each of the four key outcomes as described below.

- Market Access Information Services

Support will be provided to help SPC develop and operate MA-related information services as follows:

- Maintenance and updating of PICTs’ animal health information utilising the World Animal Health Information System (WAHIS) and FAO’s Transboundary Animal Disease Information System (TADinfo), a software package that is entirely customisable to the animal disease quantification and management needs of each user.  Note: Use of WAHIS and TADinfo will be supported in preference to further developing the Pacific Animal Health Information System (PAHIS)).

- Maintenance and updating of the Pacific Pest List Database (PPLD) including: (i) PPLD maintenance and data entry; (ii) timely verification of records for public access; and (iii) ongoing software and equipment upgrades.

- Provision of a MA-related ‘Helpdesk’ facility, with primary focus on addressing enquiries related to relevant international standards and/or zoosanitary, phytosanitary and food safety requirements of trading partners.

- Compilation and provision of information to support: (i) the preparation of MA submissions and data packages by PICTs not covered by PHAMA’s Components 1-3; and (ii) import risk analyses for agricultural and horticultural products from other PICTs to facilitate timely consideration of MA submissions and hence regional market access.

- Continued development of the Pacific Islands Trade Statistics Database currently being developed by LRD.

- Renewal of SPC’s 5-year CABI subscription.

2.	International Engagement

Support will be provided to ensure SPC fulfils its role as the Secretariat for the PPPO as follows:

- Annual hosting of the PPPO Executive Committee.

- Annual participation (as in representation of PICTs) in the RPPO Technical Consultation.

- Convening a consultation workshop on draft International Standards for Phytosanitary Measures (ISPMs).

- Preparation of PPPO submissions on draft ISPMs and/or IPPC Secretariat requests for information.

- Annual attendance of the Commission on Phytosanitary Measures (CPM) in Rome (noting that RPPOs hold observer status only).

- Triennial hosting of the PPPO Technical Board meeting.

Other areas where PHAMA will support SPC to ensure appropriate engagement of PICTs in the international SPS regulatory environment include:

- Representation of PICTs at Regional OIE (World Organisation for Animal Health) meetings, through LRD’s Animal Health and Production Group.

- Establishment of a WTO Enquiry Point to ensure timely communications between the WTO SPS Committee (e.g. WTO SPS Emergency Notifications) and PICTs.

3.	Market Access-Related Surveillance and Reporting

Support will be provided to SPC to undertake MA-related surveillance and reporting, as follows:

- Reporting of PICTs’ animal health information to comply with international requirements and the SPC-OIE agreement for non-member (OIE) PICT countries.

- Fruit fly surveillance audit, verification and training (to ensure the trapping systems established under RMFFP are maintained appropriately).

- Fruit fly and invasive ant diagnostics and trapping supplies provided as a regional service for countries without national entomological expertise.

- Invasive ant surveillance audit, verification and training (to ensure the surveillance systems established as part of the Pacific Ant Prevention Programme (PAPP) are maintained appropriately).

.

4.	Technical Market Access-Related Capacity within SPC

Within SPC, the Program will fund a Market Access Specialist to be a focal point for developing practical MA skills within SPC long-term, working closely with the Principal Market Access Specialist in the PMO. The Program will also fund a Senior Entomologist and 5 Technicians working in specified areas. Remaining technical gaps (e.g. taxonomic experts) in current LRD staffing will be covered through short-term program-recruited TA.

In addition to being responsible for the management of Component 4 activities as detailed above, it is anticipated that SPC-LRD will also be involved in supporting the implementation of a range of other activities under Components 1-3. Examples include the training of quarantine officers, growers/producers, exporters and treatment facility operators on the operational procedures required to meet new export protocols developed under the Program. These additional activities will be contracted to SPC by the MC on a case-by-case basis.

## Technical Assistance

Technical Assistance includes 1 full-time Market Access Specialist; and 1 full-time Senior Entomologist. Both of these positions are internationally-engaged. Terms of Reference are provided in Attachment 2.

The Market Access Specialist is designed as a focal point for developing practical MA skills within SPC long-term, and will also provide a key link between the PMO and SPC. S/he will report to and be responsible to the BAT Coordinator. This position is also expected to develop and maintain a close working relationship with the PMO-based market access and quarantine/ biosecurity specialists.

The Senior Entomologist position will provide essential diagnostic capacity for MA-related surveillance and the updating of data on plant pests and diseases necessary for the preparation of MA submissions. S/he will report to and be responsible to either the Plant Health Coordinator or BAT Coordinator, as SPC sees fit.

Both TA positions will be recruited and managed by SPC.

## Support staff/ technicians

In additional to the 2 full-time TA positions, the Program will support 5 FTE support staff/ technicians working in the following areas:

FTEs

(a) Animal health information database			0.5

(b) Pacific pest list database				0.5

(c) Helpdesk facility					0.5

(d) Trade statistics database development		1.0

(e) WTP SPS enquiry point				1.0

(f) Reporting of PICTs’ animal health information	0.5

(g) Fruit fly surveillance work				1.0

All support staff/ technician positions will be recruited and managed by SPC.

# MANAGEMENT ARRANGEMENTS

## Management Structure

Key elements of the PHAMA management structure include:

- Management of the overall Program will be contracted to a Managing Contractor (MC).

- A Program Management Office (PMO) will be established by the MC in Suva, physically located within SPC. The MC will be directly responsible for implementation of Component 1-3 activities.

- Implementation of Component 4 activities will be delegated to SPC-LRD, with MC coordination. LRD will be fully responsible for implementation of Component 4 activities. The Market Access Specialist appointed by LRD will be the designated Activity Manager for Component 4 activities, under the direction of the SPC BAT Coordinator.

- A Market Access Working Group (MAWG) will be established in the five countries where Components 1-3 are implemented to help determine MA priorities and action plans, and coordinate the implementation of Program activities.

- National Market Access Coordinators (NMACs) will be employed in the five countries where Components 1-3 are implemented . They will be responsible for providing secretariat support to the MAWGs and for maintaining an operational linkage between the PMO, SPC and the MAWGs.

- A regional Program Coordinating Committee (PCC) will be responsible for providing high-level governance steerage of the Program. SPC will be represented on the PCC through the head of LRD or designate.

These structural arrangements are further detailed in the Main Report.

## Management Processes

### Planning

Component 4 planning and plan approval processes will be integrated with those to be adopted for Components 1-3, managed by the PMO. SPC will prepare an annual workplan in May of each year in line with the Program Design Document. This workplan will specify activities to be implemented by SPC over the following 12 months (July 1 to June 30) together with associated resource requirements. The PMO will consolidate the SPC workplan with Component 1-3 workplans to produce an integrated Annual Strategic Plan (ASP) for the overall Program, which will go to the PCC by mid June for endorsement.

### Procurement and financial management

SPC will be responsible for procurement of all goods and services required for implementation of Component 4 activities, following SPC’s standard procurement guidelines. Financial management (including audit) will follow SPC’s usual procedures for an activity of this nature.

All program funds will flow through an Imprest Account managed by the MC on behalf of AusAID. SPC will be funded 6-monthly in advance through this account, in line with projected expenditures in the corresponding ASP, subject to satisfactory acquittal of previous advances.

### Reporting

Key reporting requirements are detailed in the Main Report, summarised below:

- Annual Strategic Plans to be submitted by mid June each year, covering the following July-June Australian FY. The ASPs will be regarded as an enabling framework designed to guide implementation, rather than a constraining blueprint.

- Annual Progress Reports to be submitted by the end of July each year.

- Interim 6-month Progress Reports to be submitted by the end of January, following the same format as the Annual Progress Reports.

- Six-Monthly Financial Reports to be submitted by the end of January (covering July-December) and July (covering January-June expenditures). MC- and SPC-managed expenditures must be reported in the same format, to be determined by the MC.

- Monthly Exception Reports to be submitted at the end of each calendar month. These will be brief (maximum 3 pages) reports highlighting any significant issues that have arisen over the month, and how these issues are being addressed.

- Phase 1 Completion Report to be submitted by end-March 2013.

Where relevant, reports will be prepared as consolidated whole-of-program reports, incorporating both MC- and SPC-managed components. SPC will be required to prepare all contributions to these reports following formats and timelines as prescribed by the MC. The MC will be responsible for final consolidation.

### Coordination

There is a risk that the split management arrangements will diminish coordination of SPC-implemented Component 4 activities and MC-implemented Component 1-3 activities. Both SPC and the MC should recognise this risk and be proactive in promoting communication between staff and coordination of activities on a daily basis.

Specific coordination mechanisms built into the design to aid coordination and communication include:

- Physical location of the PMO within SPC in Suva.

- Integrated planning, plan approval and monitoring arrangements across both MC and SPC-managed components.

- Establishment of the MAWGs at national-level as a single gateway/focal point for all activities implemented in-country, both MC- and SPC- implemented.

- Conduct of annual workshops, rotated between countries, bringing together PMO staff, SPC staff, MAWG chairpersons and the NMACs to review progress and issues at whole-of-program level.

- Conduct of monthly internal planning and review meetings by key LT PMO and SPC staff.

- Development of a formal Communications Strategy, with clear specification of communication responsibilities and protocols.

- Establishment of high quality electronic communication capacity between the PMO, SPC and the in-country secretariat offices.

### Monitoring and evaluation

A preliminary M&E Framework is presented in Appendix 10, to be finalised prior to or during startup. SPC will be further consulted during this process. Once the M&E Framework has been finalised, SPC will be required to monitor and report outcomes in line with the agreed framework, with guidance from the PMO.

### Review

The MC will facilitate an independent Quality Review of the Program at the end of Years 2 and 4, on behalf of AusAID. These Quality Reviews will monitor the systems and processes of the MC and SPC in relation to Components 1-3 and Component 4 respectively; quality of management; quality of reporting; and effectiveness of governance arrangements. TORs will be drafted to reflect any particular concerns of the PCC or AusAID. The Quality Review Team will report directly to the PCC, and will include one member nominated by AusAID (from AusAID’s Rural Development Expert Panel), and one member jointly nominated by the MC and SPC.

### Communication strategy

A formal communication strategy is considered essential given the regional nature of the program (involving a regional PMO overseeing operations in 5 countries); the involvement of both the PMO as well as SPC in implementation management; and the imperative of establishing effective communication within the MAWGs and between the MAWGs and various other stakeholders and actors. A communication strategy will be developed prior to or during startup. This will be a practical guide outlining who needs to be communicating with whom, when, and how.

# KEY RISKS AND OUTSTANDING ISSUES

## Key Risks

Key risks and mitigation measures related to SPC implementation of Component 4 include:

- SPC’s structural funding issues lead to Component 4 resources becoming excessively diluted by non-programmed activities. Mitigation measures include quarantining SPC’s involvement to Component 4; tying funding to a clearly defined set of activities; providing medium-term funding for these activities as core activities, rather than viewing them as a project ‘add-ons’; providing medium-term funding for additional positions in LRD to improve the technical market access-related capacity within SPC; closely monitoring implementation performance; and adoption of 6-monthly financial disbursements.

- SPC-managed Component 4 activities are insufficiently coordinated with the MC-managed Component 1-3  activities. Mitigation measures include physical location of the PMO within SPC; preparation of consolidated planning and monitoring reports, led by the MC; adoption of a seamless planning and budget approval process; and use of the NMACs and MAWGs as a focal point for PMO and SPC MA-related activities in-country.

- Inability to attract and retain suitable TA for the SPC positions (qualifications, experience, approach and motivation). Mitigation measures include defining recruitment and selection criteria as part of design; and allocating sufficient time and resources to the selection process.

## Outstanding Issues

Outstanding issues include:

- Two upcoming projects (PRAfTAP and FACT II – refer section 1.6) are likely to support areas of activity in SPC allowing the continuation and expansion of some of BAT’s core biosecurity and trade facilitation work. The final set of activities supported under Component 4 of PHAMA should be further reviewed once the designs of PRAfTAP and FACT II are finalised, in order to ensure no duplication occurs.

APPENDIX 6

ATTACHMENT 2

TOR FOR KEY TECHNICAL ASSISTANCE  POSITIONS

- Market Access Specialist

- Senior Entomologist

POSITION: MARKET ACCESS SPECIALIST – SPC (INTERNATIONAL)

LOCATION AND DURATION:

This position will be based within the SPC-LRD in Suva, Fiji; and will initially be for a 3 year period through to the end of Phase 1 in mid 2013. Frequent travel between Suva and the countries where PHAMA Components 1-3 is being implemented, as well as other Pacific Community members will be required.

GENERAL DESCRIPTION:

The SPC Market Access Specialist will:

- have overall responsibility for management of  PHAMA Component 4 activities within BAT, in consultation with the BAT Coordinator and the PMO-based Principal Market Access Specialist, and in accordance with AusAID’s contract with SPC for implementation of Component 4 activities;

- act as a key liaison point for the PMO within SPC-BAT;

- ensure the overall coherence and quality of PHAMA-supported activities implemented by SPC-BAT;

- extend the provision of market access-related assistance to other PICTs not directly included under PHAMA; and

- represent SPC-BAT on market access and technical issues, as required.

S/he will report to and be responsible to the BAT Coordinator for all actions taken. This position is also expected to develop and maintain a close working relationship with the PMO-based technical assistance.

SPECIFIC TASKS AND RESPONSIBILITIES:

The SPC Market Access Specialist will:

- Assist PICTs not covered under Components 1-3 to identify high priority market access issues and develop action plans to address highest priority issues, in consultation with the PMO Principal Market Access Specialist and the BAT Coordinator.

- Provide technical market access support (e.g. for the preparation of market access submissions and data packages) to PICTs not covered under Components 1-3.

- Provide technical support to PICTs for the conduct of import risk analyses for agricultural and horticultural products from other PICTs (to facilitate timely consideration of market access submissions and hence regional market access).

- Oversight the identification, contracting and supervision of market access and R&D service providers mobilised to help address particular high priority market access issues ‘approved’ for support by SPC.

- Oversight the development and operation of the market access ‘Helpdesk’ facility to PICTs.

- Together with the PMO-based Principal Market Access Specialist develop mechanisms that ensure effective coordination between PMO-managed and SPC-managed components/activities.

- Monitor, report and provide technical input on regional/international biosecurity and quarantine related activities or developments that may impact (adversely or favourably) on technical market access for the PICTs not covered by PHAMA Components 1-3.

- Provide technical market access related assistance to the PPPO Secretariat as required.

- Provide inputs to the PHAMA annual planning and monitoring processes as required by the PHAMA Team Leader.

QUALIFICATIONS AND EXPERIENCE:

The successful candidate will have:

- A graduate degree from a recognised University in a relevant field – preferably agricultural/horticultural science, animal or plant sciences.

- At least 5 years experience working in technical market access related areas, preferably including experience in the Pacific.

- An understanding of the processes and issues involved in establishing and maintaining market access for agricultural products including:

  - Relevant international SPS issues underpinning technical market access;

  - Quarantine and biosecurity-related issues (e.g. surveillance, incursion response, reporting) that may impact upon technical market access, particularly in the Pacific region; and

  - Technical market access, quarantine and biosecurity mechanisms, structures and processes within governments of the PICTs and destination target markets including Australia and NZ.

- Proven technical market access skills, including:

  - Working with industry groups to resolve market access issues;

  - Working with industry groups to develop and establish appropriate surveillance and monitoring systems in support of market access;

  - Assisting in the development of technical market access submissions and strategies;

  - Experience in the conduct of risk analyses related to market access requests;

  - Experience in the evaluation of market access related research and development;

  - Experience in bilateral market access strategy development and negotiations, preferably at the senior government level; and

- Demonstrated ability to establish strong working relationships with national counterparts at a senior level.

- Well developed skills in: inter-personal communication; report writing; numeracy; analysis; and networking.

- Advanced computer literacy.

POSITION: SENIOR ENTOMOLOGIST – SPC (INTERNATIONAL)

LOCATION AND DURATION:

This position will be based within the SPC-LRD in Suva, Fiji; and will initially be for a 3 year period through to the end of Phase 1 in mid 2013. Frequent travel between Suva and the countries where PHAMA Components 1-3 is being implemented, as well as other Pacific Community members will be required.

GENERAL DESCRIPTION:

The Senior Entomologist will:

- have overall responsibility for the verification of all insect records from PICTs to ensure timely public access of PICTs’ records maintained in the Pacific Pest List Database (up-to-date and validated data on plant pests and diseases being essential for the preparation of market access submissions for exports);

- provide expert diagnostic support, including training of national staff,  for market access-related surveillance programs;

- liaise with SPC-Plant Healh Group entomologists and plant pathologists to coordinate the maintenance and update of the Pacific Pest List Database in response to pest and disease surveys supported by other programs (e.g. FACT II); and

- ensure the overall coherence and quality of PHAMA-supported diagnostic/identification services (e.g. short term TA) implemented by SPC.

S/he will report to and be responsible to either the Plant Health Coordinator or BAT Coordinator, as SPC sees fit, for all actions taken. This position is also expected to develop and maintain a close working relationship with the PMO-based technical assistance.

SPECIFIC TASKS AND RESPONSIBILITIES:

The Senior Entomologist will:

- Identify insects collected in the course of fruit fly surveillance undertaken in the 22 PICT members of the Pacific Community. Identifications may be required of the Senior Entomologist as part of fruit fly surveillance audit; verification of specimens with a preliminary identification by national staff ; as well as identifications undertaken directly for PICTs without the appropriate entomological capacity.

- Identify insects collected in the course of invasive ant surveillance undertaken in Pacific Community members. Identifications may be required of the Senior Entomologist as part of invasive ant surveillance audit; verification of specimens with a preliminary identification by national staff; as well as identifications undertaken directly for PICTs without the appropriate entomological capacity.

- Verify entomological records and/or specimen identifications from the 22 PICT members to facilitate timely public access to all entomological records in the Pacific Pest List Database.

- Advise the BAT Coordinator on appropriate changes to procedures for fruit fly surveillance and invasive ant surveillance, and communicate any approved changes to PICTs.

- Assist in BAT training programmes for national PICT representatives involved in fruit fly surveillance and invasive ant surveillance, where appropriate focusing on diagnostics and preservation/curation of specimens.

QUALIFICATIONS AND EXPERIENCE:

The successful candidate will have:

- A graduate degree in zoology/agricultural science from a recognised University, preferably including entomology papers AND a post-graduate degree on a relevant entomological topic(s).

- At least 5 years experience working in a plant protection diagnostic laboratory, preferably including experience with Pacific fauna such as tephritid fruit flies.

- An understanding of the phytosanitary-related processes involved in establishing and maintaining trade in agricultural/horticultural products including:

  - Familiarity with relevant international standards for phytosanitary measures (ISPMs) underpinning technical market access; and

  - Quarantine and biosecurity-related matters (e.g. pest survey design, surveillance, incursion response, reporting) that may impact upon technical market access, particularly in the Pacific region.

- Internationally-recognised diagnostic/taxonomic skills, as demonstrated by:

  - A strong publication record in relevant peer-reviewed entomological or taxonomic journals; and

  - Established collaborative research projects with other diagnostic scientists and/or taxonomists.

- Demonstrated ability to establish strong cooperative relationships with international counterparts involved in providing diagnostic services and/or related research (e.g. CABI).

- Well developed skills in: inter-personal communication; scientific report writing; analysis; and networking.

- Advanced computer literacy.

APPENDIX 8

SUMMARY LOGFRAME

|  | Intervention Logic | Performance Indicators (PIs) | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- |
|  | Goal: Increased exports of high value primary products, contributing to increased economic growth and improved rural livelihoods. Objective: PICT government and industry organisations working collaboratively to gain, maintain and improve access into key markets for selected high priority products. | Industry level Incremental export volumes for target products. Incremental export revenue for target products. Contribution of target products to total export value. Contribution of target products to total GDP. Contribution of target products to agricultural export value. Contribution of target products to agricultural GDP. # FTE jobs created. Producer level (case studies only) # hh’s involved in particular export production activities. % change in hh income due to export production. # FTE jobs created due to export activity. | Program assessments as follows: Baseline data established for all products targeted. Impact assessment against key indicators every 3 years, using: - available trade statistics; - export data from regulatory agencies; - export data from treatment facility operators; - industry surveys where required; - case studies of export producers. | High-value products which have comparative and competitive advantage for export can be identified and markets developed. Sufficient supply of export quality product is available or can be developed. Effective linkages exist or can be developed between producers and international markets. A significant number of rural smallholders are able to become involved in export production activities. Government fully engages with industry in the process of gaining, maintaining and improving MA. Increasing energy and transport costs do not kill economic viability. Political stability is maintained in target countries. Appropriately skilled TA can be mobilised to support implementation of the Program. |

|  | Intervention Logic | Performance Indicators (PIs) | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- |
|  | COMPONENT 1: PREPARATION AND PROCESSING OF MARKET ACCESS SUBMISSIONS |  |  |  |
|  | Intermediate Outcome: Market access priorities identified and high quality market access submissions prepared and accepted by importing government authorities. | # new products for which access has been gained, by type and market. # of products for which export protocols have been improved, by type and market. | Trade approval notifications and modifications. | Import country regulatory agencies are able and willing to process well-prepared MA requests in a timely and efficient manner. |
|  | Key Result Areas: |  |  |  |
| 1.1 | MAWGs involving government and industry representatives established and operating effectively. | # MAWGs that are established and functional. | MAWG membership lists. MAWG minutes. Results achieved. | Government agencies are willing to improve coordination with industry in pursuit of a common goal. MAWG members have sufficient time to devote to MAWG business. |
| 1.2 | MA issues prioritised and action plans prepared. | # and nature of MA requests prioritised and action plans prepared. | MAWG minutes. | MAWG can agree on a prioritisation process. Government and industry are able to agree on specific priorities. |
| 1.3 | MA submissions and data packages prepared. | # and nature of MA submissions and data packages prepared. | Submissions and data packages. | Pest and disease information is available for the commodity pest lists included in the submissions. |
| 1.4 | Preliminary risk management packages prepared. | # and nature of risk management packages prepared. | Risk management packages. | Acceptable and cost-effective risk management measures can be identified. Required R&D is completed in a timely manner. |
| 1.5 | Bilateral coordination and communication enhanced. | # Pacific Coordinators in place. # of bilateral meetings held. # of bilateral negotiations held. # of bilateral negotiations directly assisted by PHAMA TA. | BA and MAFBNZ records. NPPO records. Program records. | Role of PHAMA TA in supporting MA negotiations is accepted. |

|  | Intervention Logic | Performance Indicators (PIs) | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- |
|  | COMPONENT 2: IMPLEMENTATION OF MA REQUIREMENTS |  |  |  |
|  | Intermediate Outcome: SPS measures required to establish/maintain market access for specified high priority products being successfully implemented by government and industry. | # of consignments presented for export certification. # and % of consignments for which export certification is issued. # and % of consignments into target markets that are rejected, by reason. | Export certification records produced by export country regulatory authorities (e.g. NPPOs). Import country regulatory agency records and notifications. | Exporting country regulatory agencies are adequately resourced to competently implement required export protocols. |
|  | Key Result Areas: |  |  |  |
| 2.1 | Operational procedures required to meet SPS protocols developed. | # of products for which operational/ export system procedures are documented and being implemented. # of products for which ‘Best Practice’ codes are documented and being implemented. | Operational procedures/ system manuals. ‘Best Practice’ codes. | Industry is fully involved in the development of all procedures and codes. |
| 2.2 | Capacity of quarantine officers, exporters, producers and treatment facility operators to implement required procedures and meet target market quality standards improved. | # of people trained, by subject and by sex. % of participants receiving training reporting that skills/ knowledge learned is being applied. | Training plans and records. Training evaluations. | Suitable candidates for training can be identified and retained. |
| 2.4 | Sanitary and phytosanitary treatment, sanitary handling and diagnostic facilities established/ upgraded and operating effectively. | #, type and ownership of facility supported. Type of support being provided. Operational status and throughput. | Program records. Facility operational records. Audit reports from import country regulatory agencies or independent auditors. | Govt is prepared to expedite the development of essential facilities. Private sector has a prominent role in the operation of key facilities, and tariffs are market-determined to ensure financial sustainability. |

|  | Intervention Logic | Performance Indicators (PIs) | Means of Verification MoVs | Assumptions |
| --- | --- | --- | --- | --- |
|  | COMPONENT 3: RESEARCH & DEVELOPMENT |  |  |  |
|  | Intermediate Outcome: R&D activities required to gain, maintain and improve market access identified and implemented. | # and nature of R&D activities completed that have directly contributed to new or improved market access. Approx cost:benefit of R&D activities that have resulted in new or improved MA arrangements. # and nature of R&D activities identified. # and nature of R&D activities in process. # and nature of R&D activities completed. | Activity Design Documents and Completion Reports. Program evaluations. Program records. | Industry is fully involved in R&D priority setting and implementation so that solutions are market-relevant. R&D priorities can be agreed. Suitable R&D partner organisations are available and can be contracted. |
|  | Key Result Areas: |  |  |  |
| 3.1 | Export markets analysed and export feasibility studies prepared. | # of market assessments completed. # export feasibility studies completed. | Market assessment reports. Feasibility studies. |  |
| 3.2 | Commodity-specific pest surveys completed and pest lists prepared. | # of pest surveys completed. # of pest lists prepared. | Pest lists. SPC pest list database. Quarantine agency records. |  |
| 3.3 | Sanitary and phytosanitary treatment protocols developed. | # and nature of sanitary and phytosanitary treatment protocols defined or refined. | Treatment protocol documentation. | Treatment protocols that are financial viable can be developed. |
| 3.4 | Product standards developed. | # and nature of product standards developed and implemented. | Product standards. | Industry is fully engaged. Sufficient financial incentives/disincentives are available to underpin adoption of standards. |
| 3.5 | Application of international zoosanitary, phytosanitary and FS standards assessed. | # of export submissions that refer to ISPMs. # of export system procedures that include ISPM components. | ISPM assessments. Export submissions. Export system procedures. | TA has a sound understanding of WTO SPS principles and related ISPMs and the ability to apply this to export trade. |
| 3.6 | Capacity of exporters to enter new markets improved. | # of people trained, by subject and by sex. # outwards trade missions organised and participation. # inward buyer missions conducted and participation. # and value of market development grants made. | Program records. |  |

|  | Intervention Logic | Performance Indicators (PIs) | Means of Verification MoVs | Assumptions |
| --- | --- | --- | --- | --- |
|  | COMPONENT 4: REGIONAL SUPPORT SERVICES |  |  |  |
|  | Intermediate Outcome: SPC providing regional market access support services in an efficient and effective manner. | Assessment by client PICTs of SPC’s performance in providing core regional support services under PHAMA. Assessment by international standard setting bodies (e.g. CPM and PPPO) of SPC’s performance in representing PICTs’ interests. | Annual satisfaction surveys. | Resources provided to SPC by the PHAMA Program are dedicated to intended purposes. SPC maintains effective working relationships with national quarantine departments. |
|  | Key Result Areas: |  |  |  |
| 4.1 | Provision of MA information services to national-level stakeholders improved. | WAHIS and TADinfo developed and operational. PPLD being maintained. Trade Statistics Database developed and operational. # and type of information requests made to the ‘Helpdesk’. | WAHIS, TADinfo, PPLD and Trade Statistics Database status reports and records of use. SPC ‘Help Desk’ records. |  |
| 4.2 | PICTs effectively engaged with relevant international for a (e.g. PPPO). | # and nature of meetings/workshops convened/attended. # submissions made on behalf of member countries. # of submissions which result in a successful outcome. # consultations held with member countries on current issues. | SPC records. Submissions. Minutes/reports of relevant international fora. | PICTs actively participate in PPPO and other international fora (through SPC) to drive regional biosecurity and quarantine agendas. |
| 4.3 | MA-related surveillance and reporting maintained in accordance with international standards. | Animal health info being regularly reported in compliance with international requirements. Fruit fly surveillance systems maintained. Invasive ant surveillance systems maintained. | SPC records, OIE records. Fruit fly surveillance and audit reports. Invasive ant surveillance and audit reports. |  |
| 4.4 | Technical MA capacity within SPC enhanced. | # and nature of MA submissions and data packages facilitated by SPC for non-PHAMA countries. | Submissions and data packages. |  |

|  | Intervention Logic | Performance Indicators (PIs) | Means of Verification MoVs | Assumptions |
| --- | --- | --- | --- | --- |
|  | PROGRAM MANAGEMENT |  |  |  |
|  | Intermediate Outcome: To effectively and efficiently manage the Program in a manner that is responsive to stakeholder needs. |  |  |  |
|  | Outcomes: |  |  |  |
|  | Program governance arrangements established and operating effectively. | PCC and MAWGs established and meeting routinely. ASPs and M&E reports reviewed and endorsed by PCC. Adequate PS representation on PCC & MAWGs. | PCC and MAWG membership. PCC and MAWG minutes. | Govt is willing to include PS, and PS is willing to be involved. Effective working relationships with govt and relevant industry organisations are developed and maintained. |
|  | Program Management Office established and operating effectively. | PMO fully staffed. Staff performing to a satisfactory level. # and type of training conducted for PMO staff. Physical and financial management systems established. Operations Manual, Communication Strategy established and revised. ASPs prepared in timely manner and approved by AusAID. ASPs implemented in an efficient manner. Progress reports prepared in a timely manner. M&E Framework established and effectively implemented. MC and SPC-managed components effectively coordinated. Timely mobilisation of high quality ST TA. | Staffing records and duty statements. Annual staff performance evaluations. 6-mnth Progress and Financial Reports. Training reports. Operations Manual, Communication and ASPs. MEF design. 6-mnthly Progress Reports and Financial Reports External Quality Reviews. TA mobilisation records and contracts. | Competent TA can be recruited and retained, with clearly defined and accepted roles and responsibilities. Program can develop appropriate systems for effectively supporting implementation across several different PICTs from a centralised PMO. An effective working relationship is established and maintained between the MC and SPC. |
|  | Program effectively coordinated with other relevant donor programs. | # of other donor programs with which PHAMA is formally associated. Nature of cooperation. | 6-mnth Progress Reports. |  |
|  | Lessons learned systematically reviewed and shared with PICT governments and other donors. | # lessons learned/ sharing workshops conducted; # of participants. | 6-mnth Progress Reports. Lessons-learned reports. |  |

APPENDIX 10

DRAFT M&E FRAMEWORK

FINAL Framework forthcoming and will supersede this Draft.

|  | Intervention Logic | Performance Indicators (PIs) | Means of Verification | Responsibility for data collection | Frequency/deadline | Reporting mechanism |
| --- | --- | --- | --- | --- | --- | --- |
|  | Goal: Increased exports of high value primary products, contributing to increased economic growth and improved rural livelihoods. Objective: PICT government and industry organisations working collaboratively to gain, maintain and improve access into key markets for selected high priority products. | Industry level Incremental export volumes for target products. Incremental export revenue for target products. Contribution of target products to total export value. Contribution of target products to total GDP. Contribution of target products to agricultural export value. Contribution of target products to agricultural GDP. # FTE jobs created. Producer level (case studies only) # hh’s involved in particular export production activities. % change in hh income due to export production. # FTE jobs created due to export activity. | Program assessments as follows: Baseline data established for all products targeted. Impact assessment against key indicators every 3 years, using: - available trade statistics; - export data from regulatory agencies; - export data from treatment facility operators; - industry surveys where required; - case studies of export producers. | ST M&E Specialist, assisted by NMACs. | Baseline established for all products where MA has been gained or improved as a result of PHAMA support. Follow-up assessments at end of Phase 1 (mid 2013). | Impact assessment included in the Phase 1 Completion Repport. |

|  | Intervention Logic | Performance Indicators (PIs) | Means of Verification | Responsibility for data collection | Frequency/ deadline | Reporting mechanism |
| --- | --- | --- | --- | --- | --- | --- |
|  | COMPONENT 1: PREPARATION AND PROCESSING OF MARKET ACCESS SUBMISSIONS |  |  |  |  |  |
|  | Intermediate Outcome: Market access priorities identified and high quality market access submissions prepared and accepted by importing government authorities. | # new products for which access has been gained, by type and market. # of products for which export protocols have been improved, by type and market. | Trade approval notifications and modifications. | ST M&E Specialist, assisted by NMACs. | Annual. | Annual Progress Reports. |
|  | Key Result Areas: |  |  |  |  |  |
| 1.1 | MAWGs involving government and industry representatives established and operating effectively. | # MAWGs that are established and functional. | MAWG membership lists. MAWG minutes. Results achieved. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 1.2 | MA issues prioritised and action plans prepared. | # and nature of MA requests prioritised and action plans prepared. | MAWG minutes. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 1.3 | MA submissions and data packages prepared. | # and nature of MA submissions and data packages prepared. | Submissions and data packages. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 1.4 | Preliminary risk management packages prepared. | # and nature of risk management packages prepared. | Risk management packages. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 1.5 | Bilateral coordination and communication enhanced. | # Pacific Coordinators in place. # of bilateral meetings held. # of bilateral negotiations held. # of bilateral negotiations directly assisted by PHAMA TA. | BA and MAFBNZ records. NPPO records. Program records. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |

|  | Intervention Logic | Performance Indicators (PIs) | Means of Verification | Responsibility for data collection | Frequency/ deadline | Reporting mechanism |
| --- | --- | --- | --- | --- | --- | --- |
|  | COMPONENT 2: IMPLEMENTATION OF MA REQUIREMENTS |  |  |  |  |  |
|  | Intermediate Outcome: SPS measures required to establish/maintain market access for specified high priority products being successfully implemented by government and industry. | # of consignments presented for export certification. # and % of consignments for which export certification is issued. # and % of consignments into target markets that are rejected, by reason. | Export certification records produced by export country regulatory authorities (e.g. NPPOs). Import country regulatory agency records and notifications. | ST M&E Specialist, assisted by NMACs. | Annual. | Annual Progress Reports. |
|  | Key Result Areas: |  |  |  |  |  |
| 2.1 | Operational procedures required to meet SPS protocols developed. | # of products for which operational/ export system procedures are documented and being implemented. # of products for which ‘Best Practice’ codes are documented and being implemented. | Operational procedures/ system manuals. ‘Best Practice’ codes. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 2.2 | Capacity of quarantine officers, exporters, producers and treatment facility operators to implement required procedures and meet target market quality standards improved. | # of people trained, by subject and by sex. % of participants receiving training reporting that skills/ knowledge learned is being applied. | Training plans and records. Training evaluations. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 2.4 | Sanitary and phytosanitary treatment, sanitary handling and diagnostic facilities established/ upgraded and operating effectively. | #, type and ownership of facility supported. Type of support being provided. Operational status and throughput. | Program records. Facility operational records. Audit reports from import country regulatory agencies or independent auditors. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |

|  | Intervention Logic | Performance Indicators (PIs) | Means of Verification | Responsibility for data collection | Frequency/ deadline | Reporting mechanism |
| --- | --- | --- | --- | --- | --- | --- |
|  | COMPONENT 3: RESEARCH & DEVELOPMENT |  |  |  |  |  |
|  | Intermediate Outcome: R&D activities required to gain, maintain and improve market access identified and implemented. | # and nature of R&D activities completed that have directly contributed to new or improved market access. Approx cost:benefit of R&D activities that have resulted in new or improved MA arrangements. # and nature of R&D activities identified. # and nature of R&D activities in process. # and nature of R&D activities completed. | Activity Design Documents and Completion Reports. Program evaluations. Program records. | ST M&E Specialist. | Annual. | Annual Progress Reports. |
|  | Key Result Areas: |  |  |  |  |  |
| 3.1 | Export markets analysed and export feasibility studies prepared. | # of market assessments completed. # export feasibility studies completed. | Market assessment reports. Feasibility studies. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 3.2 | Commodity-specific pest surveys completed and pest lists prepared. | # of pest surveys completed. # of pest lists prepared. | Pest lists. SPC pest list database. Quarantine agency records. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 3.3 | Sanitary and phytosanitary treatment protocols developed. | # and nature of sanitary and phytosanitary treatment protocols defined or refined. | Treatment protocol documentation. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 3.4 | Product standards developed. | # and nature of product standards developed and implemented. | Product standards. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 3.5 | Application of international zoosanitary, phytosanitary and FS standards assessed. | # of export submissions that refer to ISPMs. # of export system procedures that include ISPM components. | ISPM assessments. Export submissions. Export system procedures. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 3.6 | Capacity of exporters to enter new markets improved. | # of people trained, by subject and by sex. # outwards trade missions organised and participation. # inward buyer missions conducted and participation. # and value of market development grants made. | Program records. | PMO, assisted by NMACs. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |

|  | Intervention Logic | Performance Indicators (PIs) | Means of Verification | Responsibility for data collection | Frequency/ deadline | Reporting mechanism |
| --- | --- | --- | --- | --- | --- | --- |
|  | COMPONENT 4: REGIONAL SUPPORT SERVICES |  |  |  |  |  |
|  | Intermediate Outcome: SPC providing regional market access support services in an efficient and effective manner. | Assessment by client PICTs of SPC’s performance in providing core regional support services under PHAMA. Assessment by international standard setting bodies (e.g. CPM and PPPO) of SPC’s performance in representing PICTs’ interests. | Annual satisfaction surveys. | ST M&E Specialist, assisted by SPC Activity Manager. | Annual. | Annual Progress Reports. |
|  | Key Result Areas: |  |  |  |  |  |
| 4.1 | Provision of MA information services to national-level stakeholders improved. | WAHIS and TADinfo developed and operational. PPLD being maintained. Trade Statistics Database developed and operational. # and type of information requests made to the ‘Helpdesk’. | WAHIS, TADinfo, PPLD and Trade Statistics Database status reports and records of use. SPC ‘Help Desk’ records. | SPC Activity Manager. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 4.2 | PICTs effectively engaged with relevant international for a (e.g. PPPO). | # and nature of meetings/workshops convened/attended. # submissions made on behalf of member countries. # of submissions which result in a successful outcome. # consultations held with member countries on current issues. | SPC records. Submissions. Minutes/reports of relevant international fora. | SPC Activity Manager. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 4.3 | MA-related surveillance and reporting maintained in accordance with international standards. | Animal health info being regularly reported in compliance with international requirements. Fruit fly surveillance systems maintained. Invasive ant surveillance systems maintained. | SPC records, OIE records. Fruit fly surveillance and audit reports. Invasive ant surveillance and audit reports. | SPC Activity Manager. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
| 4.4 | Technical MA capacity within SPC enhanced. | # and nature of MA submissions and data packages facilitated by SPC for non-PHAMA countries. | Submissions and data packages. | SPC Activity Manager. | 6-monthly | Interim 6-monthly Progress Reports. Monthly Exception Reports. |

|  | Intervention Logic | Performance Indicators (PIs) | Means of Verification | Responsibility for data collection | Frequency/ deadline | Reporting mechanism |
| --- | --- | --- | --- | --- | --- | --- |
|  | PROGRAM MANAGEMENT |  |  |  |  |  |
|  | Intermediate Outcome: To effectively and efficiently manage the Program in a manner that is responsive to stakeholder needs. |  | Independent Quality Review, scheduled for end of PY 2&4. | Quality Review Team. | Scheduled for end of PY 2 and PY 4. | Quality Review Report to PCC and AusAID. |
|  | Outcomes: |  |  |  |  |  |
|  | Program governance arrangements established and operating effectively. | PCC and MAWGs established and meeting routinely. ASPs and M&E reports reviewed and endorsed by PCC. Adequate PS representation on PCC & MAWGs. | PCC and MAWG membership. PCC and MAWG minutes. |  |  | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
|  | Program Management Office established and operating effectively. | PMO fully staffed. Staff performing to a satisfactory level. # and type of training conducted for PMO staff. Physical and financial management systems established. Operations Manual, Communication Strategy established and revised. ASPs prepared in timely manner and approved by AusAID. ASPs implemented in an efficient manner. Progress reports prepared in a timely manner. M&E Framework established and effectively implemented. MC and SPC-managed components effectively coordinated. Timely mobilisation of high quality ST TA. | Staffing records and duty statements. Annual staff performance evaluations. 6-mnth Progress and Financial Reports. Training reports. Operations Manual, Communication and ASPs. MEF design. 6-mnthly Progress Reports and Financial Reports External Quality Reviews. TA mobilisation records and contracts. | Program Director, Team Leader & SPC Activity Manager. | On-going. | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
|  | Program effectively coordinated with other relevant donor programs. | # of other donor programs with which PHAMA is formally associated. Nature of cooperation. | 6-mnth Progress Reports. | Program Director, Team Leader & SPC Activity Manager. | On-going. | Interim 6-monthly Progress Reports. Monthly Exception Reports. |
|  | Lessons learned systematically reviewed and shared with PICT governments and other donors. | # lessons learned/ sharing workshops conducted; # of participants. | 6-mnth Progress Reports. Lessons-learned reports. | Program Director, Team Leader & SPC Activity Manager. | On-going. | Interim 6-monthly Progress Reports. Monthly Exception Reports. |

APPENDIX 11

RISK MANAGEMENT MATRIX

| Risk Class | Risk | Like- lihood | Conse- quence | Rating (1-5) | Mitigation Measures |
| --- | --- | --- | --- | --- | --- |
| Management | Lack of Yr 2 budget adversely affects overall performance of Phase 1. | High | Med | 4 | Maximise pre-startup preparatory work. Have a range of subcontracts fully prepared in Yr 2, ready for implementation from late Yr 2 onwards. Push any infrastructural investments into Yrs 3 and 4. Seek other ‘top-up’ donor funding for Yr 2. |
|  | Under-expenditure in yrs 3 and 4 perceived as poor performance. | Med | Low | 2 | Forewarn AusAID of likely difficulties caused by limited Yr 2 budget. Define performance criteria that are not based on disbursement. Clarify mandate of oversight body in relation to performance criteria. |
|  | Inability to attract and retain suitable TA for the PMO and SPC (qualifications, experience, approach and motivation). | Med | High | 4 | Define recruitment and selection criteria as part of design. Allocate significant time and resources to the selection process. Require non-exclusivity for key personnel in tender. Ensure option for key long term technical advisors to provide scheduled on-going short term inputs, as an alternative to full-time placement. |
|  | Inability to attract and retain suitable NMACs (qualifications, experience, approach and motivation). | Low | High | 3 | Define recruitment and selection criteria as part of design. Allocate significant time and resources to the selection process. Ensure attractive salary and non-salary benefits. Provide on-going training. Allocate sufficient time and resources for appropriate liaison with PMO TAs. |
|  | Inability to identify and recruit suitable subcontractors (qualifications, experience, approach and motivation). | Low | High | 3 | Require tenderers to demonstrate knowledge of and access to suitable expertise. |
|  | Difficulty of managing and ensuring integrity of a geographically distributed team. | Low | Med | 2 | Ensure appropriate internal communication protocols; adequately resource communication equipment. |

| Risk Class | Risk | Like- lihood | Conse- quence | Rating (1-5) | Mitigation Measures |
| --- | --- | --- | --- | --- | --- |
|  | SPC-managed Component 4 activities insufficiently coordinated with the MC-managed Component 1-3 activities. | Low | Med | 2 | Physical location of PMO within SPC. Preparation of consolidated planning and monitoring reports, led by the MC. Adoption of a seamless planning and budget approval process. Use of the NMACs as a focal point for PMO and SPC MA-related activities in-country. |
|  | External risks (natural disasters, tensions, economic factors) | Low | Med | 2 | Security and evacuation procedures in place. Ensure a geographically and sectorally diversified portfolio of activities. |
| Intervention | Failure to develop a constructive working relationship between industry and government. | Med | High | 4 | Formation of the MAWG. On-going facilitation by NMACs, assisted by PMO where necessary. Only fund activities if it is clear that the MAWG is functional. |
|  | Inability to identify and attract appropriate members for the MAWG, especially industry representatives. | Med | Med | 3 | Focus on individuals that have active interest/ responsibility for MA. Focus on cross-sectoral industry representatives. Payment of direct expenses. |
|  | MAWG members do not have time or inclination to engage at the required level. | Med | Med | 3 | Limited face-to-face meetings. On-going facilitation by NMACs. Payment of direct expenses. Focus on quick wins to develop and retain interest. Keep group small and efficient. |
|  | Failure to follow agreed process for selecting high priority activities. | Low | Med | 2 | Adequate training in the process. Give some flexibility for MAWG to adjust to meet local needs and conditions. Don’t fund activities that are clearly not well prioritised. |
|  | Industry and government unable to agree on MA priorities. | Low | Med | 2 | Mediation by the NMAC/ PMO staff. Don’t fund activities until major differences have been resolved. |
|  | Industry representatives on the MAWG are excessively biased towards vested commercial interests. | Med | Med | 3 | Select representatives that have cross-sectoral responsibilities. Provide on-going training on MAWG roles and responsibilities. Be prepared to change MAWG members if necessary. |

| Risk Class | Risk | Like- lihood | Conse- quence | Rating (1-5) | Mitigation Measures |
| --- | --- | --- | --- | --- | --- |
|  | Integrity of the MAWGs is compromised by national government policies and agendas, or perceived ‘emergency’ situations, without regard to industry wishes. | Low | Med | 2 | Clearly defined criteria for determining priority product/s. Agreed mechanism to assess and prioritise ‘emergency’ situations. Don’t fund activities until major differences have been resolved. |
|  | Exporting country governments remain reluctant to adopt a more proactive approach to communications with importing country agencies. | Med | Med | 3 | Exposure to negotiation practices of other countries. Joint regional representations (strength in numbers). Direct use of international TA to support more active management of the process. |
|  | Improved MA arrangements fail to result in increased exports. | Low | High | 3 | Careful selection of priorities following defined criteria. Be prepared to spend time to get appropriate data before pursuing a particular opportunity/ issue. Focus on ‘export ready’ industries. Actively develop linkages and synergies with other supply chain projects. |
|  | Overall PHAMA work program is excessively focussed on MA into Australia and NZ, with highly limited capacity of Australia and NZ to process requests. | High | Med | 4 | Encourage MAWGs to spread efforts between different importing countries. Influence MAWGs to identify options relating to improving or maintaining access, in addition to seeking new access. If necessary fund the appointment and maintenance of Pacific Coordinators in DAFF and MAFBNZ. |
|  | Expectations for MA gains exceed capacity to deliver. | High | Med | 4 | Careful management of expectations by the PMO. Good resourcing to progress activities as speedily as possible. Go for ‘low hanging fruit’ where early wins are possible. |
|  | Insufficient resources are allocated by PICT governments to support national biosecurity and quarantine services, affecting the ability to competently implement negotiated MA protocols. | Med | Med | 3 | Use the MAWG as a key forum to get cross-party agreement on priorities and exert some influence on resource allocation. Provide Program funding for key government activities and services directly related to priority products during early years, if necessary. Promote successes to government through effective PR. |
|  | SPC’s structural funding issues result in Component 4 resources being excessively diluted, resulting in suboptimal performance. | Low | Med | 2 | Quarantine SPC’s involvement to Component 4. Tie funding to a clearly defined set of activities. Close monitoring of implementation performance. 6-monthly/annual financial disbursements. |

| Risk Class | Risk | Like- lihood | Conse- quence | Rating (1-5) | Mitigation Measures |
| --- | --- | --- | --- | --- | --- |
|  | The development needs of larger and more accessible target countries are excessively emphasised over those of smaller and more remote countries. | Med | Low | 2 | Establish a MAWG and locate a NMAC in each country to identify issues and opportunities. Establish max budget allocations for each country, with PCC authority required to exceed these. |
| Development | Importing government regulatory agencies are reluctant to more actively engage with PICTs, despite improved MA submissions and more active management of the submission process. | Med | High | 4 | Mobilise experienced international TA to help manage the process. Be prepared to ‘go political’ through appropriate fora (e.g. PIF). |
|  | Climate change adversely affects the future development and diversification of agricultural industries and trade in PICTs. | ?? | High | ?? | Actively monitor impact of climate change on agricultural production, existing exports and export potential. Emphasise PHAMA as a mechanism for actively managing change. |
|  | Increasing energy prices adversely affect PICTs ability to compete in key markets | Med | High | 4 | Actively monitor impact of energy prices on export feasibility in consultation with other supply chain focused projects. Go for low volume/ high value exports. Emphasise PHAMA as a mechanism for actively managing change. |
|  | Production activities associated with new/ improved MA arrangements result in negative environmental impacts. | Low | Low | 1 | Focus on high-value, niche products rather than commodities. Explicitly include possible environmental impact in the prioritisation matrix. |

APPENDIX 12

TERMS OF REFERENCE FOR LONG -TERM POSITIONS

- TEAM LEADER (INTERNATIONAL)

- PRINCIPAL MARKET ACCESS SPECIALIST (INTERNATIONAL)

- QUARANTINE & BIOSECURITY SPECIALIST (INTERNATIONAL)

- MARKET ACCESS SPECIALIST – SPC (INTERNATIONAL)

- SENIOR ENTOMOLOGIST – SPC (INTERNATIONAL)

- NATIONAL MARKET ACCESS COORDINATORS (X4) (NATIONAL)

- PROCUREMENT/ FINANCE OFFICER (NATIONAL)

- ADMINISTRATIVE ASSISTANT/SECRETARY (NATIONAL)

Notes:

A combined TOR is presented for the 2 key technical positions within the PMO – the Principal MA Specialist and the Quarantine/ Biosecurity Specialist –on the basis that there is likely to be considerable crossover in roles and responsibilities. Tenderers will be given flexibility to ‘mix and match’ the particular skill sets of candidates proposed to specific elements of the job description provided. As reflected in the position titles, it is likely that one of the candidates will have more experience in managing the process of gaining market access; the other in the implementation of biosecurity and quarantine measures required to maintain access once gained.

Also note that these 2 positions are costed as full-time positions. It may however prove difficult to attract candidates with the required skills and experience for long-term placement. The option of utilising periodic ST inputs totalling 4-6 months per year, per position, would be an acceptable alternative, provided on-going involvement of the same person could be assured.

All positions with the exception of the Market Access Specialist (SPC) will be recruited and managed by the MC. SPC will be responsible for recruitment and management of the Market Access Specialist located within SPC. The National Market Access Coordinators will be located in the various countries under PHAMA and will have a close working relationship with the Market Access Working Groups, but will report to the PMO.

POSITION: TEAM LEADER (INTERNATIONAL)

LOCATION AND DURATION:

This position will be based in the PMO in Suva, Fiji; and will initially be for a 3 year period through to the end of Phase 1 in mid 2013. A moderate amount of travel within the Pacific will be required.

GENERAL DESCRIPTION:

The Team Leader will:

- have overall responsibility for managing the implementation of PHAMA in accordance with the PDD, the contract and the approved Annual Strategic Plans;

- ensure the overall coherence and quality of program implementation, team management, personnel development, stakeholder relations, reporting and adherence to contract conditions; and

- represent the contractor in all dealings with AusAID and outside parties.

S/he will report to and be responsible to the Managing Contractor for all actions taken.

SPECIFIC TASKS AND RESPONSIBILITIES:

The Team Leader will:

- Recruit, guide and mentor Program staff.

- Establish robust financial and administrative systems.

- Establish systems for program planning, monitoring and performance evaluation.

- Together with the MA Specialist, oversight the contracting and supervision of service providers mobilized to help address particular issues as identified by the MAWGs.

- Monitor the use and acquittal of Program funds, ensuring funds are applied in line with the contract and approved Annual Strategic Plans.

- Establish mechanisms that ensure effective communication and coordination within the program. Particular attention should be paid to coordination of PMO-managed and SPC-managed components/activities.

- Liaise and coordinate with relevant government agencies, private sector organizations, and regional organizations.

- Liaise with donors and actively investigate opportunities for linking with relevant supply chain development initiatives.

- Maintain a responsive relationship with the PCC and AusAID by providing timely information, advice and recommendations on all PHAMA matters.

- Analyse and synthesise project experiences and actively contribute to the on-going development of the PHAMA design.

QUALIFICATIONS AND EXPERIENCE:

The successful candidate will have:

- A post-graduate degree from a recognized University in a relevant field – preferably agricultural economics, agribusiness or rural development.

- At least 10 years experience working in international development, preferably including experience in the Pacific.

- A general understanding of the process and issues involved in establishing market access for agricultural products.

- Proven managerial skills, particularly in:

  - Planning, administration and financial management of donor projects;

  - Working with and coordinating professional teams;

  - Coordinating geographically dispersed development activities;

  - Leading AusAID or other donor development activities;

  - Effectively liaising with government and non-government organizations.

- Demonstrated ability to establish strong working relationships with national counterparts at a senior level.

- Well developed skills in: inter-personal communication; report writing; numeracy; analysis; and networking.

- Advanced computer literacy.

POSITIONS:

PRINCIPAL MARKET ACCESS SPECIALIST (x1) (INTERNATIONAL)

QUARANTINE & BIOSECURITY SPECIALIST (x1) (INTERNATIONAL)

LOCATION AND DURATION:

These positions will be based in the PMO in Suva, Fiji; and will initially be for a 3 year period through to the end of Phase 1 in mid 2013. Frequent travel between Suva and the countries where PHAMA is being implemented will be required.

A combined TOR is presented for the 2 positions on the basis that there is likely to be considerable crossover in roles and responsibilities. Tenderers will be given flexibility to ‘mix and match’ the particular skill sets of candidates proposed to specific elements of the job description provided. As reflected in the position titles, it is likely that one of the candidates will have more experience in managing the process of gaining market access; the other in the implementation of biosecurity and quarantine measures required to maintain access once gained.

Also note that the 2 positions are costed as full-time positions. It may however prove difficult to attract candidates with the required skills and experience for long-term placement. The option of utilising periodic ST inputs totalling 4-6 months per year, per position, would be an acceptable alternative, provided on-going involvement of the same person could be assured.

GENERAL DESCRIPTION:

The Principal Market Access Specialist and the Quarantine and Biosecurity Specialist will:

- have overall responsibility for development and management of the market access strategies and action plans to be supported under PHAMA;

- ensure the overall coherence and quality of  market access strategies developed and implemented by the MAWGs in each country;

- ensure coherence between MC-implemented and SPC-implemented components of the Program;

- represent the Team Leader on market access and technical issues when dealing with AusAID and outside parties, as required.

Both positions will report to and be responsible to the Team Leader.

SPECIFIC TASKS AND RESPONSIBILITIES:

The Principal Market Access Specialist and the Quarantine and Biosecurity Specialist will:

- Assist with the establishment/recruitment, guidance and mentoring of the MAWGs, NMACs, and the SPC-based Market Access Specialist.

- Provide technical support to the MAWGs, NMACs, and the SPC Market Access Specialist.

- Oversight the activities of the MAWGs, assisted by the NMACs, related to identifying high priority market access issues and development of action plans to address these issues.

- Oversight the identification, contracting and supervision of service providers to be mobilised to help address particular market access issues as identified by the MAWGs.

- Directly assist PICT government NPPOs in market access negotiations, as requested.

- Oversight the activities of SPC-BAT, promoting maximum coherence between Component 4 activities and Component 1-3 activities.

- Ensure that market access strategies and activities are in line with relevant international SPS standards (e.g. pest free areas, post-harvest treatments).

- Liaise and coordinate with relevant government agencies, private sector organisations, and regional organisations (including SPC-BAT) on market access issues.

- Ensure that market access strategies and activities are appropriately aligned with other donor activities, where relevant.

- Monitor, report and provide technical input on regional/international biological and quarantine related activities or developments that may impact (adversely or favorably) on technical market access for the PICTs.

- Investigate and promote opportunities for developing regional market access agreements.

- Identify and promote the transfer of experiences and ‘lessons learned’ between participating countries.

- Provide technical assistance to the PPPO Secretariat as required.

- Assist the Team Leader to establish mechanisms that ensure effective communication and coordination within the program, especially between the PMO and the MAWGs/NMACs; and between the PMO and SPC-BAT.

- Assist the Team Leader to establish systems for program planning, monitoring and performance evaluation.

QUALIFICATIONS AND EXPERIENCE:

The successful candidates will have:

- A graduate degree from a recognised University in a relevant field – preferably agricultural science, animal or plant sciences. For one of the positions a post-graduate degree in animal health or plant protection would be desirable.

- At least 10 years experience working in relevant technical market access-related areas, preferably including experience in the Pacific.

- A thorough understanding of the processes and issues involved in establishing market access for agricultural products, and/or developing biosecurity systems enabling safe trade in agricultural products, including:

  - Relevant SPS issues underpinning technical market access;

  - Quarantine and biosecurity-related issues (e.g. surveillance, incursion response, reporting) that may impact upon technical market access, particularly in the Pacific region; and

  - Technical market access, quarantine and biosecurity mechanisms, structures and processes within governments of the PICTs and destination target markets including Australia and NZ.

- Proven technical market access skills, including:

  - Working with industry groups to identify, prioritise and resolve market access issues;

  - Working with industry groups to develop and establish appropriate surveillance and monitoring systems in support of market access;

  - Development and evaluation of technical market access submissions, data packages and strategies;

  - Experience in the conduct of risk analyses related to export market access requests;

  - Experience in the identification, commissioning and supervision of technical market access related R&D;

  - Experience in bilateral market access strategy development and negotiations, preferably at senior government level; and

  - Experience in developing the capacity of quarantine/ biosecurity agencies to protect trade.

- Demonstrated ability to establish strong working relationships with national counterparts at a senior level.

- Well developed skills in: inter-personal communication; report writing; numeracy; analysis; and networking.

- Advanced computer literacy.

POSITION: MARKET ACCESS SPECIALIST – SPC (INTERNATIONAL)

LOCATION AND DURATION:

This position will be based within the SPC-LRD in Suva, Fiji; and will initially be for a 3 year period through to the end of Phase 1 in mid 2013. Frequent travel between Suva and PICTs will be required.

GENERAL DESCRIPTION:

The SPC Market Access Specialist will:

- have overall responsibility for management of  PHAMA Component 4 activities within BAT, in consultation with the BAT Coordinator and the PMO-based Principal Market Access Specialist, and in accordance with AusAID’s contract with SPC for implementation of Component 4 activities;

- act as a key liaison point for the PMO within SPC-BAT;

- ensure the overall coherence and quality of PHAMA-supported activities implemented by SPC-BAT;

- extend the provision of market access-related assistance to other PICTs not directly included under PHAMA; and

- represent SPC-BAT on market access and technical issues, as required.

S/he will report to and be responsible to the BAT Coordinator for all actions taken. This position is also expected to develop and maintain a close working relationship with the PMO-based technical assistance.

SPECIFIC TASKS AND RESPONSIBILITIES:

The SPC Market Access Specialist will:

- Assist PICTs not covered under Components 1-3 to identify high priority market access issues and develop action plans to address highest priority issues, in consultation with the PMO Principal Market Access Specialist and the BAT Coordinator.

- Provide technical market access support (e.g. for the preparation of market access submissions and data packages) to PICTs not covered under Components 1-3.

- Provide technical support to PICTs for the conduct of import risk analyses for agricultural and horticultural products from other PICTs (to facilitate timely consideration of market access submissions and hence regional market access).

- Oversight the identification, contracting and supervision of market access and R&D service providers mobilised to help address particular high priority market access issues ‘approved’ for support by SPC.

- Oversight the development and operation of the market access ‘Helpdesk’ facility to PICTs.

- Together with the PMO-based Principal Market Access Specialist develop mechanisms that ensure effective coordination between PMO-managed and SPC-managed components/activities.

- Monitor, report and provide technical input on regional/international biosecurity and quarantine related activities or developments that may impact (adversely or favorably) on technical market access for the PICTs not covered by PHAMA Components 1-3.

- Provide technical market access related assistance to the PPPO Secretariat as required.

- Provide inputs to the PHAMA annual planning and monitoring processes as required by the PHAMA Team Leader.

QUALIFICATIONS AND EXPERIENCE:

The successful candidate will have:

- A graduate degree from a recognised University in a relevant field – preferably agricultural/horticultural science, animal or plant sciences.

- At least 5 years experience working in technical market access related areas, preferably including experience in the Pacific.

- An understanding of the processes and issues involved in establishing and maintaining market access for agricultural products including:

  - Relevant international SPS issues underpinning technical market access;

  - Quarantine and biosecurity-related issues (e.g. surveillance, incursion response, reporting) that may impact upon technical market access, particularly in the Pacific region; and

  - Technical market access, quarantine and biosecurity mechanisms, structures and processes within governments of the PICTs and destination target markets including Australia and NZ.

- Proven technical market access skills, including:

  - Working with industry groups to resolve market access issues;

  - Working with industry groups to develop and establish appropriate surveillance and monitoring systems in support of market access;

  - Assisting in the development of technical market access submissions and strategies;

  - Experience in the conduct of risk analyses related to market access requests;

  - Experience in the evaluation of market access related research and development;

  - Experience in bilateral market access strategy development and negotiations, preferably at the senior government level; and

- Demonstrated ability to establish strong working relationships with national counterparts at a senior level.

- Well developed skills in: inter-personal communication; report writing; numeracy; analysis; and networking.

- Advanced computer literacy.

POSITION: SENIOR ENTOMOLOGIST – SPC (INTERNATIONAL)

LOCATION AND DURATION:

This position will be based within the SPC-LRD in Suva, Fiji; and will initially be for a 3 year period through to the end of Phase 1 in mid 2013. Frequent travel between Suva and the countries where PHAMA Components 1-3 is being implemented, as well as other Pacific Community members will be required.

GENERAL DESCRIPTION:

The Senior Entomologist will:

- have overall responsibility for the verification of all insect records from PICTs to ensure timely public access of PICTs’ records maintained in the Pacific Pest List Database (up-to-date and validated data on plant pests and diseases being essential for the preparation of market access submissions for exports);

- provide expert diagnostic support, including training of national staff,  for market access-related surveillance programs;

- liaise with SPC-Plant Healh Group entomologists and plant pathologists to coordinate the maintenance and update of the Pacific Pest List Database in response to pest and disease surveys supported by other programs (e.g. FACT II); and

- ensure the overall coherence and quality of PHAMA-supported diagnostic/identification services (e.g. short term TA) implemented by SPC.

S/he will report to and be responsible to either the Plant Health Coordinator or BAT Coordinator, as SPC sees fit, for all actions taken. This position is also expected to develop and maintain a close working relationship with the PMO-based technical assistance.

SPECIFIC TASKS AND RESPONSIBILITIES:

The Senior Entomologist will:

- Identify insects collected in the course of fruit fly surveillance undertaken in the 22 PICT members of the Pacific Community. Identifications may be required of the Senior Entomologist as part of fruit fly surveillance audit; verification of specimens with a preliminary identification by national staff ; as well as identifications undertaken directly for PICTs without the appropriate entomological capacity.

- Identify insects collected in the course of invasive ant surveillance undertaken in Pacific Community members. Identifications may be required of the Senior Entomologist as part of invasive ant surveillance audit; verification of specimens with a preliminary identification by national staff; as well as identifications undertaken directly for PICTs without the appropriate entomological capacity.

- Verify entomological records and/or specimen identifications from the 22 PICT members to facilitate timely public access to all entomological records in the Pacific Pest List Database.

- Advise the BAT Coordinator on appropriate changes to procedures for fruit fly surveillance and invasive ant surveillance, and communicate any approved changes to PICTs.

- Assist in BAT training programmes for national PICT representatives involved in fruit fly surveillance and invasive ant surveillance, where appropriate focusing on diagnostics and preservation/curation of specimens.

QUALIFICATIONS AND EXPERIENCE:

The successful candidate will have:

- A graduate degree in zoology/agricultural science from a recognised University, preferably including entomology papers AND a post-graduate degree on a relevant entomological topic(s).

- At least 5 years experience working in a plant protection diagnostic laboratory, preferably including experience with Pacific fauna such as tephritid fruit flies.

- An understanding of the phytosanitary-related processes involved in establishing and maintaining trade in agricultural/horticultural products including:

  - Familiarity with relevant international standards for phytosanitary measures (ISPMs) underpinning technical market access; and

  - Quarantine and biosecurity-related matters (e.g. pest survey design, surveillance, incursion response, reporting) that may impact upon technical market access, particularly in the Pacific region.

- Internationally-recognised diagnostic/taxonomic skills, as demonstrated by:

  - A strong publication record in relevant peer-reviewed entomological or taxonomic journals; and

  - Established collaborative research projects with other diagnostic scientists and/or taxonomists.

- Demonstrated ability to establish strong cooperative relationships with international counterparts involved in providing diagnostic services and/or related research (e.g. CABI).

- Well developed skills in: inter-personal communication; scientific report writing; analysis; and networking.

- Advanced computer literacy.

POSITION: NATIONAL MARKET ACCESS COORDINATORS (X5) (NATIONALS)

LOCATION AND DURATION:

A full-time NMAC will be appointed for Fiji, Tonga, Samoa, Solomon Islands and Vanuatu.. The positions will be based in-country, co-located with a relevant industry or government organization.

NMACs will be locally recruited by the PHAMA PMO. The initial contracts will be for a 3 year period through to the end of Phase 1 in mid 2013. Occasional travel to the PMO in Suva, or to other PICTs, will be required.

GENERAL DESCRIPTION:

The NMACs form a critical link in the program management structure, providing an operational link between Market Access Working Group (MAWG) members, and between the MAWGs, the PMO and SPC. They will be the key in-country contact points for the overall Program, responsible for:

- providing secretariat support to the MAWGs in each country;

- assisting with the identification of priority market access issues and development of corresponding workplans;

- coordination of activities being supported by PHAMA to help address particular issues; and

- monitoring of in-country activities and results.

The NMACs will report to the PHAMA Team Leader through the Principal Market Access Specialist. They will also be expected to maintain a particularly close working relationship with the chairman of the MAWG.

SPECIFIC TASKS AND RESPONSIBILITIES:

The NMACs will:

- Provide administrative support to the MAWG, including convening and coordinating MAWG meetings.

- Facilitate communication and coordination between MAWG members.

- Provide an operational linkage between the MAWG, the PMO, and SPC.

- Assist with the development of annual workplans, in line with PMO requirements.

- Assist the MAWG and PMO to identify the need for external TA to address priority market access issues, where possible identifying suitable local TA resources.

- Assist the MAWG to coordinate the implementation of market access activities being funded by the Program.

- Monitor the implementation of PHAMA-funded activities, in line with PMO requirements.

- Coordinate with other market access and supply chain development activities, including other donor-supported initiatives.

- Work with emerging exporters of priority products to build capacity in the implementation of required quarantine procedures.

QUALIFICATIONS AND EXPERIENCE:

Successful candidates will have:

- A graduate degree in a relevant field – preferably agricultural economics, agribusiness, trade development, or agricultural science.

- At least 5 years experience working in a relevant field. Ideally this will include experience in establishing market access arrangements for agricultural/ horticultural export industries, either with government or industry.

- A basic understanding of the technical quarantine/ biosecurity issues involved in gaining and maintaining access for agricultural products. Detailed technical knowledge is not required but an ability to understand and communicate issues to the MAWG, PMO and SPC will be required.

- Demonstrated ability to work with both government and industry stakeholders.

- Demonstrated ability to actively network and coordinate activities across a team.

- Well developed inter-personal communication and writing skills.

- Computer literacy.

POSITION: PROCUREMENT/ FINANCE OFFICER (NATIONAL)

LOCATION AND DURATION:

This position will be based in the PMO in Suva, Fiji; and will initially be for a 3 year period through to the end of Phase 1 in mid 2013. Occasional travel to countries covered under the Program may be required.

GENERAL DESCRIPTION:

Under the direction of the Team leader, the Procurement/ Finance Officer will be responsible for establishing and managing the PMO’s procurement and financial control systems, including:

- preparation and management of annual operating budgets;

- coordination and submission of estimates on administration and program running costs;

- procurement, including contracting and oversighting the financial performance of subcontractors engaged by the Program; and

- monitoring of expenditure.

SPECIFIC TASKS AND RESPONSIBILITIES:

The Procurement/ Finance Officer will:

- Assist the Team Leader to prepare consolidated Annual Strategic Plans (ASPs) for the Program.

- Assist SPC and the MAWGs/ NMACs with preparation of annual workplans for Component 4 activities and in-country activities, respectively; for incorporation into the ASPs.

- Manage the procurement of all goods and services for the PMO, in line with AusAID procurement guidelines. This will involve a significant level of subcontracting to external service providers.

- Establish and manage electronic and paper-based systems to record PMO purchase orders, contracts, claims for payment, and expenditures.

- Ensure that PMO financial records and accounts, both paper and electronic, are efficiently managed and kept up-to-date.

- Routinely liaise with the MC through the Team Leader on funding allocations, charge codes and required financial management procedures and reporting formats.

- Establish and manage a petty cash system for the PMO and the NMACs, including advances, accountable expenditures and reimbursement of claims.

- Prepare consolidated 6-monthly financial reports covering PMO and SPC expenditures for submission to AusAID, ensuring that actual expenditures are approximately in line with ASP approvals.

- Prepare ad hoc financial reports for the Team Leaer and AusAID, as required.

- Assist AusAID to engage local auditors to undertake audit services in line with the procurement guidelines, including contract preparation and finalization; and ensure that appropriate preparations are completed by the PMO prior to the annual audit.

- Establish and manage a payroll system for locally-hired staff, covering salary rates, pay increases, overtime, bonuses, termination, and other salary and allowance payments; and overtime and pay variation advice forms.

- Assist the Team Leader with preparation of a simple financial procedures manual.

- Provide training to PMO staff in the operation of relevant financial procedures and systems, as required.

- Perform other financial management tasks as directed by the Team Leader.

QUALIFICATIONS AND EXPERIENCE:

The successful candidate will have:

- Relevant tertiary qualifications in accounting/financial management.

- A minimum of 5 years work experience in financial management, preferably including experience working for an international development agency.

- Demonstrated experience in the establishment and operation of financial control systems.

- Demonstrated experience in procurement and payment procedures.

- Demonstrated experience in managing subcontractors.

- Sound organisational skills, and a demonstrated ability to set priorities and meet deadlines and to work under minimal supervision.

- Adequate working knowledge of written and spoken English.

- Advanced computer literacy, including a sound knowledge of computerized accounting systems.

POSITION: ADMINISTRATIVE ASSISTANT/ SECRETARY (NATIONAL)

LOCATION AND DURATION:

This position will be based in the PMO in Suva, Fiji; and will initially be for a 3 year period through to the end of Phase 1 in mid 2013. Occasional travel to countries covered under the Program may be required.

GENERAL DESCRIPTION:

Under the direction of the Team Leader, the Administrative Assistant/ Secretary will be responsible for the day-to-day administrative management of the PMO. The position will also play a key role in facilitating liaison between the PMO, SPC, the MAWGs.

SPECIFIC TASKS AND RESPONSIBILITIES:

The Administrative Assistant/Secretary will:

- Manage the general operation of the PMO on a day-to-day basis, ensuring the office is run effectively and efficiently at all times.

- Facilitate routine liaison between the Team Leader, SPC and the MAWGs.

- Establish and manage electronic and paper filing systems for the PMO.

- Ensure email and internet security protocols are established, and that all electronic data relating to Program activities is securely managed under central control.

- Establish and manage registers for PMO assets; incoming and outgoing correspondence; and short term consultants and sub contractors used engaged by the PMO.

- Manage the recruitment, mobilisation and orientation of any new PMO staff and short-term advisers.

- Maintain relevant personnel records for all PMO staff, including a record of official PMO staff movements, staff leave, etc.

- Directly supervise any administrative support staff employed by the Program (e.g. drivers, security).

- Assist the Team Leader to implement a performance appraisal system for PMO staff.

- Coordinate travel arrangements for PMO staff.

- Assist with the organization of PCC meetings, including preparation of meeting agendas and minutes.

- Organise repairs and maintenance of PMO office facilities and equipment.

- Assist with the preparation of PMO manuals, reports and other documentation as required.

- Manage the distribution of relevant reports and documents to AusAID, SPC, MAWGs, partner governments etc as required.

- Assist the Team Leader with preparation of a simple administrative procedures manual.

- Perform other administrative tasks as directed by the Team Leader.

QUALIFICATIONS AND EXPERIENCE:

The successful candidate will have:

- A minimum of 3 years work experience in office administration, finance and human resources management, preferably including experience working for an international development agency.

- Sound organizational skills, a demonstrated ability to set priorities and meet deadlines.

- Demonstrated ability to work independently and exercise initiative.

- Ability to work sensitively and cooperatively with people in a multicultural environment.

- Fluency in written and spoken English including a demonstrated ability to prepare correspondence and reports in English.

- Excellent communication, interpersonal and teamwork abilities.

- A high level of computer literacy, including a sound knowledge of word processing and spreadsheet applications.

- Desirable but not essential: Relevant tertiary qualifications

There have also been several smaller cut flower additions to existing policy, outside of the IRA process.

The role and function of SPC in relation to providing regional biosecurity and quarantine services is further detailed in Appendix 6.

Specific SPC-LRD outputs relevant to PHAMA to which BAT currently contributes, and current activities in line with these outputs, are further outlined in Appendix 6.

Additional detail is provided on these activities in Appendix 4.

Variously labelled PITIC (Sydney and Auckland); Pacific Information Centre (Tokyo); and PIFTO (Beijing).

Hazard analysis and critical control points

This assessment of core activities was confirmed in late August 2009 by the then BAT Coordinator.

Additional detail is provided on these activities in Appendix 4.

Suggested by the then BAT Coordinator in late August 2009.

One technician for animal health information and reporting, 1 for PPLD and Helpdesk activities, 1 for trade statistics database development/maintenance work, 1 for the WTO SPS Enquiry Point, and 1 for fruit fly/ant surveillance work.

Similar to the arrangement established for implementation of the EU-funded FACT program

Note that Year 2 (2010/11) is the first full year of implementation; Year 1 (2009/10) being the initial design/startup year.