Sida/UNCDF

Mobile Money for the Poor (MM4P)

Programme Strategy and

Annual Work Plan 2012 (Mar- December)

Prepared for the MM4P Investment Committee

April 2012

Prepared by:

Mobile Money for the Poor Advisor and Project Manager

##### Acronyms

| API | Application Programme Interfaces |
| --- | --- |
| ARPU | Average Revenue per User |
| ATL | Above the Line (marketing) |
| ATM | Automated Teller Machine |
| AusAID | Australian Agency for International Development |
| B2P | Business-to-Person (payments) |
| BB | Branchless Banking |
| BMGF | Bill and Melinda Gates Foundation |
| BTL | Below the line (marketing) |
| CGAP | Consultative Group to Assist the Poor |
| CTA | Country Technical Advisor |
| EOI | Expression of Interest |
| G2P | Government-to-Person (payments) |
| GSMA | GSM Association |
| KM | Knowledge Manager |
| KYC | Know Your Customer |
| IC | Investment Committee |
| IFAD | International Fund for Agriculture and Development |
| LDC | Least Developed Country |
| MFI | Microfinance Institution |
| MFS | Mobile Financial Services |
| MM4P | Mobile Money for the Poor |
| MNO | Mobile Network Operator |
| P2P | Person-to-Person (transfer) |
| PA | Programme Assistant |
| PFIP | Pacific Financial Inclusion Programme |
| PM | Advisor and Project Manager |
| POS | Electronic Funds Transfer/Point of Sale Device |
| PSP | Payment Service Provider |
| UN | United Nations |
| RTA | Regional Technical Advisor |
| Sida | Swedish International Development Agency |
| TS | Technical Specialist |
| UNCDF | UN Capital Development Fund |
| UNDP | United Nations Development Programme |

Table of Contents

Executive Summary	1

Table 1:  MM4P Targets  (2012-2017)	1

Part I  Programme Strategy	3

1	Background	3

1.1	Global Context	3

Table 2: LDC Statistics	3

1.2	Internal Context	6

1.2.1	MM4P SWOT	8

Table 3:  MM4P SWOT	8

2	Mission and Outcomes	8

2.1	Mission, Purpose and Outcome	8

3	Strategy	9

3.1	Assumptions Based on Lessons Learned	9

3.1.1	Customers	9

3.1.2	Products	11

3.1.3	Delivery Channels	11

3.1.4	Service Providers	13

3.1.5	Regulators	14

3.2	Cashless Financial Services Ecosystem Evolution	16

Diagram 1:  Cashless Ecosystem Development	18

Table 4:   Mobile Financial Services Business Inputs	19

4	Strategies	20

4.1	Primary Strategies	20

4.1.1	Strategy 1. Ensure available, affordable, and safe financial services for low-income customers.	20

4.1.2	Strategy 2. Increase transaction flow through partnerships with high volume drivers	21

4.1.3	Strategy 3.  Build scalable, self-replicating delivery channels	21

4.2	Secondary Strategies	22

4.2.1	Strategy 4.  Move customers from awareness to engagement, and beyond	22

4.2.2	Strategy 5.  Assist regulators in providing proportional regulation and oversight	22

5	Approach	23

5.1	Role of Funders	23

Diagram 2:  Role of Funders (CGAP)	23

Diagram 3:  Risk Appetite	24

5.2	Method of Implementation	25

5.2.1	Preparation and Development Phase	25

Table 5  Focus Countries and Potential Outreach	26

5.2.2	Project Identification	26

5.2.3	Project Design, Appraisal and Approval	27

5.2.4	Policy and Advocacy Engagement	28

5.2.5	Customer research, education and protection	29

Diagram 4:  Financial Capability Progression	30

5.2.6	Knowledge generation and sharing	31

6	 Outputs and Measurements	32

6.1	Output 1:  Scalable, replicable solutions that reach the poor	32

6.2	Output 2  Informed, client-centered products, services and delivery mechanisms	32

6.3	Output 3 Educated and engaged policy makers, regulators and other key stakeholders	33

6.4	Output 4 Shared knowledge and experiences	34

6.5	Output 5  High performance, respected team	34

Part II	Annual Work Plan 2012	36

1	MM4P Status Update	36

Diagram 5:  Roll-Out of MM4P in Develoment Phase	37

1	2012 Priorities	38

2	Activities	38

2.1	Programme Activities	39

Table 6:  Programme Activities	39

Table 7:  Key Risks and Mitigants to Programme Activities	46

2.2	Management Activities	47

2.2.1	Update on Management Activities	47

Diagram 8:  MM4P Organizational Structure	47

Table 8: MM4P Staffing	48

Table 9: Management Activities	49

Table 10:  Key risks and mitigants to management activities	51

3	Budget  2012	52

Table 11:  MM4P 2012 Budget	52

Annex 1	Logical Framework	54

Annex 2 Programme Budget	56

# Executive Summary

Financial inclusion requires bringing the entire financial sector to low income and rural households. The most promising development in decades is the innovative use of mobile phones and other branchless banking technology as a means to do so. Mobile telephony has reached billions and the penetration rate of mobile phone use is growing by more than 20% annually. CGAP and GSMA project that 364 million low-income, unbanked people could use mobile financial services in 2012. The success of M-Pesa in Kenya and G-Cash in the Philippines and the promising deployments of MTN in Uganda and Tanzania are undeniable, reaching millions in just a few years and changing the way low income people move money. Also irrefutable is that the list of success stories is not growing as expected.

###### Table 1:  MM4P Targets  (2012-2017)

| Indicator | 5 Years | 10 Years |
| --- | --- | --- |
| New customers | 4,000,000 | 10,000,000 |
| New Active customers | 1,400,000 | 3,500,000 |
| Previously unbanked | 1,000,000 | 3,500,000 |
| Customers with a new 2nd generation product | 2,000,000 | 7,500,000 |
| Cost of Subsidy | 27,000,000 | 27,000,000 |
| MM4P Cost per client acquired | $7 | $3 |

Many operators in the past few years launched rather quickly into new countries mimicking M-Pesa’s service, failing to invest the time, money or effort to understand the client, in design the service around local needs or build the distribution network up front. The vast majority of nearly a hundred reported deployments remain shallow, limited primarily to P2P transfer and air time top up served by inadequate agent network. Mobile money operators are experiencing the “sub-scale trap”  where the distribution network is not sufficiently extensive or to reach customers and customers are therefore not experiencing the product or seeing the benefits. If these new services are going to help drive financial inclusion, the providers need assistance in building the volume of cashless transactions and places to transact that meet the needs of the local market.  This requires a range of appropriately designed and priced second generation products that can generate enough volume to be profitable to the provider. Such product development and distribution capability will have to come from a better understanding of the market and negotiating “win-win” partnerships, often between previously unrelated companies and industries. The role of funders such as UNCDF is to help MNOs, banks and others see these opportunities, incentivize the broadening of their service and deepening of the distribution to ensure that third “win” for low-income customers is also an outcome of these partnerships.

A look at global support for mobile money from funders shows a great focus on a handful of countries, few of which are least developed countries (LDCs). Mobile Money for the Poor (MM4P), a new programme proposed by UNCDF in partnership Sida and AusAID is designed to focus intently on some of the poorer countries where the commercial business case may be marginal, but the needs of the population are great. The goal is to work intently with partners to reach 4 million additional customers through mobile and branchless technology, of which at least 1.4 million active users and 1 million were previously unbanked. In additions, at least 2 million customers should gain access to at least one new appropriate and affordable “second generation” products designed for the low income user.

To achieve this UNCDF has designed a global programme that focuses on a small group of LDCs developed countries to help demonstrate how this can be achieved. Most of these countries are in the inception phase of BB and MFS development, with limited or stalled deployments and equally limited client uptake. While the programme’s primary focus will be on increasing the quantity and quality of services delivered and the delivery mechanisms, it will also take a broad view of the development of the cashless ecosystem and identify areas to help build customer and regulator confidence in the services.

This document consists of Part 1: Programme Strategy and Part 2: Annual Work Plan. The Programme Strategy includes a situational analysis as well as presentation on UNCDF’s belief on how BB and MFS can evolve in LDCs through the development of an cashless ecosystem.  From this, UNCDF has developed its strategies to foster this evolution, determined its approach and put forward MM4P’s mission, outcomes and key outputs for the five year programme. These are also included in the MM4P Logical Framework which appears in Annex 1.  The Annual Work Plan provides a list of priorities for the current year and a detailed list of activities to pursue.  It also includes the annual budget.

Each year, MM4P will conduct a strategic review, looking at external conditions as well as internal changes to determine if any changes are required to the current strategies or outcomes and to set the priorities for the new annual work plan.

# Part I  Programme Strategy

# Background

## Global Context

In the past ten years, mobile phones have been introduced as part of the delivery mechanism for financial services. The services range from basic money transfer to a variety of banking and insurance products that can be partially delivered via mobile phone. The most notable successes have occurred in the larger, emerging markets such as Kenya, the Philippines and India by non-bank providers, primarily MNOs. We know from M-Pesa in Kenya and a few other examples that mobile money has the potential to reach millions of users in the time it has taken traditional MFIs to reach thousands of customers and provides the “clear promise of massively increasing financial inclusion on a scale unseen to date despite 25 years of extensive investment in (largely credit-driven) microfinance.

| ###### Table 2: LDC Statistics | 2009 |
| --- | --- |
| Population (mean in '000) | 9,998 |
| Mobile Penetration (mean) | 32.6% |
| GDP Per Capita (mean) | $497 |
| Financial Services Access (average) | 14% |
| Ease of Doing Business (avg. out of 183) | 151 |

In most LDCs, the number of mobile phone subscribers is rapidly outstripping the current access to finance and offers a potential to reach millions with a safer, more secure way to send and store money. CGAP and GSMA project that 364 million low-income, unbanked people could use mobile financial services in 2012. These projections are based on relatively conservative assumptions about the number of mobile operators who will launch such services and the percent of customers who will use them. The explosive growth of mobile phones underpins the potential opportunity. By 2012, the number of people without a bank account but with a mobile phone is estimated to grow from 1 billion to 1.7 billion. Across 40 LDCs surveyed by UNCDF, mobile phone penetration was at 25% while access to finance was 14% on average. More striking are the growth rates – with mobile phone penetration growth reaching double digits, growing at a rate of 23% a year, while financial access growth is flat.

LDCs present particular challenges for financial inclusion initiatives and mobile money providers to reach scale, such as:

- Overall population, economic activity and disposable incomes are lower;

- Business and regulatory environments are less developed and less conducive to innovation;

- Physical, technological and financial infrastructure is underdeveloped and therefore lacking natural distribution networks;

- Local providers (financial and telecommunications) lack the expertise and multinational providers may lack the corporate management, technical and financial support for smaller markets.

On average only 14% of the adult population in LDC’s has access to financial services and growth is stagnant. Using the burgeoning mobile networks and building upon people’s comfort with using phones, there is an opportunity to increase people’s access to needed financial services.

Despite its success in Kenya, it is unlikely that “M-Pesa style” mobile money services—based person-to-person (P2P) transfers served through a large, dominant MNO propriety agent network—will achieve success in many LDC markets.  As noted by Mas and Radcliffe of the Bill and Melinda Gates Foundation (BMGF), few developing countries have the population base, economic activity, the urban-rural family connections or the reasonably extensive bank infrastructure as Kenya has. This is doubly true of LDCs.  Further, few MNOs have the penetration rates, market dominance or the millions to spend as did Safaricom, a virtual monopoly in its own market.  There is a growing concern that the pursuit of M-Pesa style mobile money deployments in other markets could result in more failed pilots that could scare regulators and mar the reputation of the banks, MNOs and the channel itself.

Box 1: Lowering the Million Mark

The CEO of Safaricom, Sir Michael Joseph, has commented that it takes a million active subscribers for mobile money to be sustainable. (Brookings Institute, May 2011).  This is worthy of note given the success of M-Pesa. The consequence of this statement is that most LDCs with an average population of less than ten million are unlikely to see sustainable mobile money services.  It is a challenge for funders of mobile money to lower the million mark. Regional initiatives, greater product offerings and different agency models may all be part of a “less than a million” strategy.

There have been a wave of recent mobile money deployments in many countries, including LDCs, but growth in use of mobile money services—particularly in the first year—has failed to live up to expectations. Mobile money operators frequently report experiencing the “sub-scale trap” where the agent network is not sufficiently extensive and the customers are not adequately informed or motivated to use the service. Many operators launched rather quickly, failing to invest the time, money or effort in the service or the distribution network up front. The vast majority of reported deployments remain shallow, limited primarily to P2P transfer and air time top up served by inadequate agent networks.  While “self top up” (customer direct purchase of air time from an mobile wallet) up can be quite lucrative for MNOs offering the service, domestic money transfer is a fairly high cost service to providers and clients  because it leads to intensive use of cash agents who must be compensated for their efforts. Incentivizing agents usually requires paying most, if not all, of the commission on cash transactions to the agents, leaving very little for the operator and making smaller transactions too costly for customers. This brings into question the “best practice” of focusing so heavily on P2P in small, less densely populated markets at the expense of offering other services.

As noted in recent CGAP and other studies, MNO deployments of mobile money generally take more than three—and most likely five or more—years to break even. In LDC markets with smaller numbers of active mobile users and lower average transaction sizes, it may take even longer.  Still, the rush to deploy continues as MNOs, and to a lesser degree banks and other payment service providers (PSPs), see mobile financial services as a critical service to remain competitive. There is some justification for this. The utility of mobile money in a MNO’s overall voice business—reducing cost of air time sold and perceived reductions in voice-user “churn” (loss of clients to competitors)—does motivate MNOs. Mobile network operators stand to earn $7.8 billion in direct and indirect revenues from serving the 364 million customers of 2012 as well as reduce churn—compelling market opportunity. According to CGAP, the indirect benefits, particularly the reduced cost of air time sales, can be close to half of all financial gains to the operator. For banks, the benefits of adding a branchless or mobile channel are a lower cost means to serve their existing customer base and lower the overall lower cost of funds. For now, the “must have” and “cost reduction” factors have outweighed lack of a clear business case. But this has not translated into sufficient investment in research, products or the delivery channel needed for success.  On the contrary, it has led some to believe that mobile financial services can lead to quick financial gains despite evidence that suggests otherwise.

Due to the lack of uptake on the P2P money transfer, some providers are becoming content with a modest service that is designed primarily to reduce costs to MNOs or provide banks with cheap funding or reduced traffic in branches. This will do little to reach the unbanked.  More challenging environments require a suitable product mix adapted for the environment that drives high customer usage—in other words, the service has to be better than cash for multiple uses. For the poor to benefit, the cashless ecosystem must be as broad and integrated as possible. Second generation services such as small purchases, public transportation, planned savings, insurance, international remittances, loan repayments, and even emergency relief are examples of services that could increase average revenue per customer (ARPU).

Savings is still an unexploited opportunity of mobile money deployments. Research in Kenya and the Philippines suggest that customers are increasingly trusting MNOs with their savings. While regulatory constraints and adequate customer protection are genuine concerns, the level of stored value permitted on many of these systems is consistent with the savings needs of users, enabling them to accumulate and use necessary sums. However the current pricing structures of MNO deployments are often prohibitive to provide affordable savings to the poor.

In the past year banks and MNOs have begun working more closely together, blurring the lines between branchless banking and non-bank mobile money. Several MNOs have partnered with banks to link mobile money accounts with individual bank accounts.  The entrance of payment service providers also highlights the interest of PSPs in entering this market, further eroding the distinction between banked and unbanked.  A partnership between EcoBank and MTN exists across Africa and Orange has developed integrated solutions with banks in several countries.

Technology offers tremendous opportunities for financial inclusion.  It will not happen through a “one-size fits all” approach and it may take more time and effort that providers and investors would like. For this reason, there is an opportunity for funders of inclusive finance to make sure this opportunity is not lost.

## Internal Context

UNCDF Inclusive Finance area has active projects of approximately $148 million in 23 countries. Traditionally, UNCDF has worked through joint UNCDF/UNDP “country programmes” which support financial service providers to reach the poor, including for-profit and non-profit organizations, banks and non-bank financial institutions. In keeping with best practices, UNCDF takes a financial sector development approach and concentrates its technical and financial resources in the areas of greatest need and opportunity at the macro (policy, legal, regulatory), meso (financial infrastructure and financial sector support services) or micro levels (retail financial services), after taking due account the work of other funders. Its primary focus has been building up retail services.

Box 2:  Mobile Money by Numbers top 25

- Rwanda

- Angola±

- Liberia

- Senegal*

- Bangladesh*±

- The Gambia±

- Maldives*±

- Zambia±

- Benin

- Nepal

- Bhutan

- Lesotho

- Vanuatu

- Togo

- Malawi

- Sudan

- Niger

- Yemen±

- Mozambique

- Cambodia

- Tanzania*

- Mali*

- Mauritania

- Madagascar

- Solomon Islands

*other donors have significant on-going work in these countries.

± Countries without UNCDF IF programmes

Since 2008 UNCDF, AusAID, the European Union Africa, Caribbean and Pacific Microfinance Framework Programme and UNDP Pacific Center have supported the development of branchless and mobile financial services in its regional, multi-donor Pacific Financial Inclusion Programme (PFIP). With few financial service providers in the region and only a handful of microfinance institutions (MFIs), PFIP opted to catalyze the development of mobile and branchless financial services in the Pacific.  It followed the financial sector development approach and applied it to the development of the services by providing market research, advocating and providing legal regulatory support, sharing global learning on branchless banking, and fostering strategic operating partnerships. At the same time it has provided performance-based grants to six partners, including banks, non-banks, MNOs, a non-bank agent and an IT firm and to build and use mobile money platforms. Five mobile money services and two branchless banking efforts were launched with PFIP support since June 2010. After meeting with initial success in registering customers, many of the deployments have experience a slow uptake in usage. The deployments with greater success were those who found high volume drivers early on and those that invested heavily in client outreach and agent network development.

In 2009, UNCDF launched the global MicroLead programme with the BMGF to invest in bringing strong deposit taking microfinance institutions to underserved LDCs.  MicroLead is a now US$50 million fund (with additional support from MasterCard Foundation), designed to bring leading microfinance institutions and other financial service providers from developing countries and enabling them to expand their operations regionally and globally. Similarly, YouthStart, funded with US$12 million in support from MasterCard Foundation, focuses on working with leading institutions in sub-Saharan Africa to test and roll out financial services and training for youth.  YouthStart is supporting 12 financial institutions to pilot and roll out sustainable financial services tailored to youth. UNCDF is having success with its global funding mechanisms (MicroLead and YouthStart) because they permit it to identify the best partners and projects globally, allocate (and re-allocate) funds flexibly and share lessons learned across regions.  It has also helped introduce strong UNCDF partners from one region to another.

In 2010, UNCDF developed a four-year corporate management plans with four strategic objectives, including one objective to “develop new products and services that support efforts to achieve the MDGs in the LDCs.” UNCDF chose to investigate mobile financial services as a new product line. In 2010, UNCDF conducted a global market (desk) survey on the potential for mobile money in the LDCs (Mobile Money by Numbers) and determined there was great potential in the LDCs given the fast growth rate of mobile phone services, as well as a great need given the slow growth rate in access to finance. In 2011, UNCDF developed a Project Concept and Draft Project Document and agreed to commit $1mm to develop a global programme dedicated to supporting the expansion and “downreach” of mobile financial services in the LDCs. The cost of the programme as designed was estimated to be $26 million. In late 2011, Sida committed SEK 40 Million ($4.6mm) to the programme to assist in its first few years.

UNCDF determined to commence the project development phase of the programme before approving its status as a global programme given the shortfall of funding. The proposed development phase outcomes are:

- Complete the scoping of the potential markets and identify projects to fund;

- Develop the policies, procedures, plans and budgets for the programme;

- Raise a total of $15 million of the $26 million total proposed budget for the programme;

The development phase will last 18-24 months, depending on how quickly it accomplishes these outcomes. If UNCDF is unsuccessful, it will need to determine how to adapt its effort to meet the funding available. The options will be discussed among the funders in the first half of 2013.

### MM4P SWOT

###### Table 3:  MM4P SWOT

| Strengths | Weaknesses |
| --- | --- |
| - High level commitment - Core funding ($5.4mm) for start-up - Experienced advisor - Strong field presence, country and regional technical advisors on-site - Commitment and track record of coordination - Flexible instruments without max or min, may utilize strategically or tactically - Able to take informed risks - May support commercial, non-profit of government entities - Utilize performance-based agreements - Minimal disbursement pressure | - Partially funded programme, unable to implement full plan - Slow hiring and procurement processes at start-up - Outdated quantitative research on LDCs - Relative weak corporate knowledge management systems, track record on knowledge generation - Partially funded, able to make only a few commitments |
| Opportunities | Threats |
| - Strong relations with central banks in most countries - Reputation of UN as impartial actor - Few other interested funders in target countries - Strong funder relations, interest of other funders in programme - Relationships with AFI, GSMA, CGAP - UN relations with host governments - Corporate linkages UN agencies, ILO, IFAD | - Challenging environment in host countries - Fast moving industry - Impatience of C-level of partners reduces investment - New technologies, methods pose high risks - Proposed level of funding to partners inadequate to achieve goals - Political, economic turmoil in host countries - Failure to win host government support |

# Mission and Outcomes

## Mission, Purpose and Outcome

Mobile Money for the Poor’s mission is to help low income and rural households in LDCs increase their financial security through appropriate, affordable and secure means to receive, manage and save money through branchless banking and mobile financial services.

This mission requires MM4P to not only look for the projects with the greatest chance of financial success, but also to work on projects that have the greatest potential to improve the lives of the poor. If done properly, MM4P can catalyze further investment by other public and private investors into mobile money services in LDCs.

The purpose of MM4P is to demonstrate how the correct mix of technical, financial, and policy support, as well as research, can assist in scaling up and/or replicating sustainable BB and MFS that reach the poor in very low-income countries.

The outcome of MM4P is for 4 million additional individuals and/or small and microenterprises in the LDCs have access to one or more appropriate branchless or mobile financial services by the end of 2017, including 1.4 million active customers, 1 million that were previously unbanked and 2 million with a second generation service.

# Strategy

## Assumptions Based on Lessons Learned

As more implementations achieve scale, some lessons have been identified globally. In addition, UNCDF’s prior experience in inclusive finance, its BB and MFS partners in the Pacific Region, as well as the history of product development in the financial services sector enables MM4P to make educated assumptions about the key elements required to successfully implement a BB and MFS business during start-up and in the early years of the expansion. These factors can be categorized according to the requirements along critical elements of the value chain, such as customers, products, delivery channels, service providers, or regulations, which is how they will be described in UNCDF’s strategy.

### Customers

UNCDF recognizes that the customer needs to be at the center of any successful product, service, or business. If customers’ needs and day-to-day realities are not taken into consideration at the onset, it is highly unlikely that the solution will provide a benefit at a price point that works for the customer.  This is particularly true for poor customers, who have very little expendable capital and who need to be extremely careful with their financial decisions.

In the case of mobile financial services, business success depends not only on customers using the product, but using it often.  A high number of transactions per customer each month are necessary to ensure the financial viability and scale of a branchless banking business model. High transaction volumes per active customer are even more important in countries with small populations or limited infrastructure, conditions that are likely to occur in the LDCs where UNCDF will be implementing its’ MM4P initiative.

Key assumptions related to the customer include:

- All financial services are a series of transactions and safekeeping. Electronic services are providing a more efficient, available and cost-effective means to facilitate any type of transaction or safekeeping and can be applied to almost any financial service if structured and priced correctly. As noted in a recent study, mobile money is going beyond a money transfer system and there is “evidence of extensive informal financial behavior, which has characteristics similar to those among informal financial groups.” Yet what that means in the day-to-day lives of individuals differs by socio-economic class. To deliver services that make a difference in their lives, it is vital to understand the transactional behaviors of those living on less than $2 a day.  Understanding that behavior and how it can be modified will be a key to customer uptake and service use.

- Time is money when it relates to client activation.  Customers are made aware of services through a combination of costly above-the-line (“ATL”) advertising and below-the-line (“BTL”) marketing and education. When a customer wants to sign-up for a mobile financial service, the process needs to be extremely easy—each hurdle risks losing an interested customer at huge opportunity cost to the provider. This means “Know Your Customer” (“KYC”) requirements and operational procedures must be simple and quick to implement, which may require a revision of KYC requirements so they are proportionate to the risk associated with a customer’s level of activity. Client information can be gathered progressively, as the frequency, and type, of use increases.

- Moving clients from awareness of a service to experiencing it is a significant challenge.  Customers’ financial practices are “sticky,” even when they are costly or inefficient. People’s psychological attachment to physical cash is not easily overcome. The trust that individuals have in the brands behind their mobile phones or banks does not simply translate to BB and MFS. Customers need to experience the service directly to appreciate its value. Those who have strong habits related to cash need to use that solution several times in relatively quick succession to change their behavior.

- Existing behaviors are more easily modified when an alternative addresses key customer “pain points”, which are urgent or unmet needs of that are difficult to solve. Pain points are frequently driven more by opportunity costs of related to existing solutions rather than transaction price.  An example is the requirement to travel long distances – at generally significant direct and indirect cost - or experiencing long delays to receive or send money.

- Ingrained behaviors can also be forced to change. Customer adoption can be driven when existing channels that are used for financial services, such as the delivery of salaries via cash, are replaced with an electronic solution. In such a scenario, customers who want to retrieve their salaries must use the new channel. Other examples that could “force” customer uptake include government subsidy payments, loan disbursements, international remittances, or even product rebates.

### Products

The first examples of mobile financial services were focused on domestic P2P payments.  While this product proved to be quite successful in a few markets, such as the Philippines and Kenya, it has not been as successful in other markets.  Research suggests that this is because money transfer is not a “pain point” in other markets where families may not be split between urban and rural locations (e.g Ghana) or where other affordable solutions exist (e.g. Tanzania).  As a result, mobile financial service providers are experimenting with, and introducing, other products the address customers’ needs such as bill payments, international remittances, micro-insurance, and purchasing. Product research and innovation is becoming a key element of all branchless banking initiatives.

- Products for the poor need to be based on their unique requirements.  A shortcoming of deployments to date has been taking a “one product and price” suits all approach to the market.  While this may assist with initial uptake, the strategy will not result in either the high transaction volumes required nor will it achieve the pro-poverty goals of MM4P. The poor will need financial products that help them save money, manage cash flow, and reduce their financial risks.  And they will need these products at prices they can afford.

- As the basic mobile financial infrastructures are implemented, innovative products will emerge.  With the high usage rates of M-PESA and other mobile financial services in Kenya, critical scale of customers and access points has been achieved. This is leading to an explosion of entrepreneurial innovation in the country.  Technology developers are emerging in the hundreds to create products and services in health care, education, consumer goods, and a range of products and services that are enabled through mobile financial commerce.  These types of innovations can be leveraged to increase customer usage and drive transaction volumes.  As such, Kenya should be watched as a living laboratory for the types of services that can emerge in other countries.

- As mobile financial services evolve, there will be a greater need to link mobile solutions to other financial channels.  Due to their simplicity of use and a high level of existing customer awareness, some MFS providers are adding debit cards and even internet portals to their mobile platform. This enables customers to transact more quickly and it provides linkages to existing access points, such as ATMs and POS terminals.  Thus, while mobile devices are critically important, other opportunities to build customer participation warrant some consideration.

### Delivery Channels

Delivery channels are probably the most critical component of mobile financial services and the least well-understood.  Building agents networks for cash-in and cash-out is difficult, time-consuming and expensive initially, but if the frameworks and incentives are correct, these channels can become self-replicating.

Mobile financial service quality can be measured on four mutually reinforcing “abilities”. While not all of these aspects need be perfect, the service will only be as strong as the weakest link in this chain.

- Availability – service should be on demand, with easy registration that has few restrictions. Ideally usage should commence immediately upon registration, which could be prior to completion of the full registration and due diligence processes.  Availability is determined by the service provider’s internal policies and procedures, as well as by regulations.  In some cases, internal restrictions can be even more onerous than regulatory constraints.

- Reliability – the underlying technology must be available 24/7 with very little downtime or disruptions; and the agent network must be available over extended periods of time and have enough liquidity to ensure that customers can retrieve cash upon request.

- Affordability – prices need to take into consideration the relatively small transaction sizes of poorer customers, as well as the frequency with which they are likely to transact.  This suggests that there may need to be different pricing strategies and approaches below certain transaction sizes.

- Accessibility - the “2 kilometer rule” suggests that customers must be able to reach a service within 30 minutes for daily (small) transactions, although they will travel further for large transactions, such as salary or loan disbursements.  At a minimum, the distribution network must be reasonably close to the customers from the beginning of the service.

Other considerations based on lessons learned from prior experience include:

- Trust is not easily transferred or gained, but can be lost fairly quickly. Strong brands in one service may not provide adequate comfort to customers to quickly adopt the company’s mobile financial services. First impressions are crucial, since it is harder to regain trust than gain it the first time.  Thus, the elements of the solution that customers will engage with must be top notch “out of the box”.  Agents need to be well trained, clearly branded, and have sufficient opportunities to manage their liquidity before the product launches. Dispute resolution approaches should also be in place prior to launch.

- Compelling incentives will push individuals to become agents, creating self-replicating networks. Branchless and mobile distribution works best when distribution channels are self-replicating, such that the incentives drive entrepreneurs to pursue the opportunity to become retail agents, master agents, or distribution partners. This is harder to do in countries where microenterprises and entrepreneurship are weak. These countries may require more initial investment and technical assistance as well as longer, on-going channel support.  They may also require credit lines, loans or a knowledgeable, strategic investor to help retail agents enter the business and manage their liquidity.

- Agents are more likely to put energy into expanding customer usage when they receive attractive compensation.  When distribution partners and retail agents receive a significant percentage of the commission for cash handling, they will work harder to expand the channel and increase transaction volumes. In such a scenario, the mobile financial service provider, and other members of the value chain, will obtain their financial remuneration from transaction flow, cost reduction, reduced churn, and/or float.

- Due to the high cost of building and maintaining agent networks, these structures will ultimately be shared. Although it is unlikely to happen immediately in most geographies, global experience in payment systems shows that interoperable and shared distribution channels almost always provide greater returns due to the joint effects of lower costs per provider, economies of scale, and increased customer usage. In many countries, individual players are likely view their distribution networks as a competitive advantage, and will seek to establish proprietary channels. While this may work at the master agent level, experience shows that retail agents will support multiple financial service providers.  This will lead to replication and high costs. Consolidation and sharing is likely to happen over time, but may be accelerated in those countries where regulators institute some level of interoperability.

### Service Providers

The types of companies that are emerging to provide mobile financial services are continuing to change.  MNOs still dominate the industry, but their dominance is gradually giving way to a variety of partnership models. The terms MNO-led and bank-led are becoming less meaningful as an increasing number of regulators and market leaders realize that “mobile transfer” is evolving into a range of financial services that more closely resemble banking. Interoperability is becoming more accepted, even among MNOs, which were the most resistant.  Third-party providers such as PSPs that offer multi-bank and/or multi-MNO solutions are also emerging in more and more countries. These changes are altering the business and financial models of all the players in the industry, and make the following assumptions even more relevant.

- Chief Executive (“C-Level”) commitment and realistic operational expectations are crucial to success. Unrealistic expectations lead to frustration and inadequate funding, which in turn causes rushed implementations, management turnover, and poor performance.  Without the appropriate level of financial and resource commitment, branchless banking initiatives will fail. Failures, even those based on limited commitment, can negatively impact and slow-down the progress of the entire industry.

- High transaction volumes are required to drive provider revenues.   Customer acquisition is not sufficient to build a mobile financial service business; active customers who use the service often are vital. Efforts need to focus on building customer usage as quickly and routinely as possible, with a goal of achieving high levels of regular transactions on a monthly basis.  To achieve this goal, new businesses are experimenting with new services so they can bring a broader range to the market as quickly as possible. Mobile financial service platforms also need to be flexible enough to enable new third-party products to be easily integrated through application program interfaces (APIs).

- Successful models need to include all segments of society, which are often linked. Wealthier urban customers may be the first adopters of a new financial solution, but to use it effectively they will introduce the service to family members, household staff, and colleagues.  Merchants, corporations, and micro and small enterprises will be interested in using the service, if it is convenient for them to do so.  These users can also help bring poorer, more rural customers to the product. To capture both ends of the market, offerings and rollout plans need to be developed strategically.

- Pricing models needs to take the poor into consideration.  Pricing in many markets has been inflexible, based on flat or stepped rates that make small size, large volume payments too costly for poor customers. Many providers forgo opportunities to reach more customers in favor of maintaining their commission margins for themselves or their agents. While understandable, this is hard to manage in lower income countries with lower volume P2P transfers such as LDCs.  The higher fees make it difficult for the low income or low margin business to  use the service.

- The total business case for mobile financial service providers is difficult to quantify. Anticipated revenue is only one part of the total business case for financial institutions and mobile operators that enter into the branchless or mobile financial services business. For financial institutions, cost savings, efficient customer acquisition, fee revenue, as well as increased funding for financial assets are some of the additional benefits; whereas customer retention, increased transaction volumes, reduced cost of air time sales, and the opportunity for add-on services provide additional benefits to MNOs. The perceived benefits of these services, and the scale they can reach, are providing the incentives service providers need to enter, and stay, in the MFS market.

### Regulators

Just as business models are changing, so too are the attitudes and approaches of regulators around the world.  Thanks to the efforts of CGAP, the World Bank, AFI, GSMA and UNCDF, regulators are developing a greater understanding of the issues and challenges within mobile financial services.  An interesting transition over the past year to two has been the shift of regulators - in all regions of the world - toward models that include regulated financial institutions. There seems to be a global move away from the MNO-led model that catapulted M-PESA to success.

What is most critical in terms of regulations is that all players in the market have a clear understanding of what is, and is not, acceptable to the regulator. In addition, to clarity and openness, successful regulations will include an element of proportionality to ensure that all customers have easy, unencumbered access to the solutions. For scale to be achieved, it is also important that all players have an opportunity to participate in the emerging industry.

The role of regulators is crucial to the overall success of mobile financial services. Significant difficulties can occur when there are multiple regulators involved that have not yet clarified their respective roles and responsibilities within the MFS space. Assisting all regulatory bodies in continuing to develop their expertise will be important not only to the regulators, but to all stakeholders.

- Regulator’s leadership can facilitate, or hinder, the development of the ecosystem. Regulators are often keenly interested in the success of mobile financial services. However, their fiduciary responsibility makes them cautious as they consider new payment or financial systems.  Thus a common approach is that many regulatory bodies take a “watch and learn” approach. They are more willing to do this, if they have adequate education and exposure to the issues related to mobile financially services globally.  It is even more important for regulators to understand the regulatory implications in their own countries.  These regulators want to watch how things unfold domestically before they make additional changes to existing regulations or frameworks. Supporting that intention with global examples can be a powerful input that leads to appropriate regulations.

- Regulators tend to be patient and deliberate. While this approach has benefits, it also means that negative opinions and attitudes can take a long time to change.  In general, changes in regulations can take one to several years, and changes in the country’s laws can take even longer. Funders can help by addressing regulator concerns and issues quickly, helping them take non-threatening steps that facilitate engagement with providers.  In addition, funders can support pilots or research that can be used to mitigate regulators’ fears or apprehensions.

- Regulatory frameworks can be developed in stages. Key risks, such as the integrity of MFS trust accounts, could be addressed during the start-up phase while a fuller set of regulations could be developed as the service matures.  In addition, new business models or services could be introduced in a “pilot” mode to test opportunities while more rigorous regulations are considered and developed. More complex concepts, such as interoperability, could be phased over time to maximize compliance.

- Regulations need to reflect the capacity of the regulator to enforce them.  Enforcement will be a combination of regulator will, resource capacity, and likelihood of negative consequences, or positive rewards.  Compliance will also depend on the relationship between the providers and the regulators

UNCDF has developed a strategy and approach for MM4P in its first year that attempts to address many of the assumptions described above.  At the same time, the strategy also takes into consideration the limited resources available to MM4P in the first year of its operation.  These competing requirements – addressing the assumptions and doing so within the constraints of the current program - will require difficult choices in each country in which the UNCDF engages. The approach that UNCDF will take to building a strategy from these assumptions will be similar to the financial sector approach used for inclusive finance.

## Cashless Financial Services Ecosystem Evolution

The development of BB and MFS is taking longer than was originally thought.  As with all industries linked to innovation, BB and MFS are part of an evolving system that is subject to disruptive changes and full of emergent and often uncoordinated actors. This is particularly true as businesses move from start-up stages to scale.  There is an inherent level of chaos and change as companies seek to discover business models and processes that can stabilize enough to allow rapid growth. This makes it difficult to predict how this emergent industry will unfold. The timing of different stages is difficult to predict and depends largely on quickly some order emerges from the chaos.

Ultimately, the goal of MM4P is to ensure that poor customers have a range of financial services available to them close to where they live and work at prices that they can afford. In order to achieve this goal in the LDCs where UNCDF will be working, customers need to be moved from cash as their primary transaction currency to mobile or electronic value, such that a high volume of their daily transactions are cashless. This will be a requirement in order to achieve the transaction volumes that will be necessary for financial sustainability of the BB and MFS providers and growth of the overall sector.

UNCDF’s conceptualization of this process looks at the combination of elements and actors involved in the provision, product development and delivery of BB and MFS services. It highlights three stages (presented in Diagram 1):

- Start-up.  The inception phase in which systems are created, products tested, clients sensitized and services piloted and launched. Ideally, one or more high volume users are recruited to use the system, or in some cases these users’ need may drive they system’s development.  The focus MM4P countries are primarily in this phase (Malawi, Nepal) or on struggling to enter the next phase (Liberia, Rwanda).

- Expansion. Is the period of rapid scaling in which the right product offering and pricing motivates clients, the distribution network incentives motivate agent replication, and new uses are drawn into the system by existing users.  This is often the period where providers establish multiple partnerships that help drive (and maintain) the expansion and begin to experiment with new uses.

- Consolidation.  Once the system has reached a critical mass and is widely accepted, an industry begins to mature that is based on the service. This industry depends on predictable and affordable access to the system around which a wide variety of services can be developed.

While moving through these phases change must also occur in the attitudes, capabilities and actions of clients and regulators.  The most critical among these are customers, which need to be led through a behavior change process that begins with unaware of the benefits of the new service, through awareness, to experience and regular use, and ultimately to reliance. Like customers, the regulators also need to make a journey from awareness of, and interest in, BB and MFS through an openness that allows them to analyze the space domestically and globally. The analysis will, hopefully, lead to the development of new, market appropriate regulations, and ultimately, to expertise.

The timing of the stages described below is less predictable. To some degree, it is based on the experience we have seen in Kenya. As an example, M-PESA spent 2-3 years in the start-up phase from 2004-2007, developing the concept, pilot testing, recognizing unforeseen challenges, performing market testing, recreating the business case, and launching their solution.  Since 2007, the MFS business in Kenya has been going through an expansion phase. Innovation (and the accompanying chaos) is on-going, so we cannot say that Kenya has moved into the consolidation phase; it may take a few more years for that to occur.

To achieve scale, a number of critical inputs need to be successfully implemented at different stages of the business development – and market – lifecycle.  Corresponding to start-up, expansion, and consolidation phases, these inputs include efforts related to regulations, corporate commitment, business planning, market analysis, market development, and operations.  The requirements in the start-up and expansion phases are better understood while those in the consolidation stage are based a few significant successes in mobile financial services as well as an overall understanding of how businesses mature.

Table 4 describes the types of inputs that will be required by a mobile financial service provider during the start-up years, which are defined as the first two years of the business; during the expansion phase, years 3 through 8, and during the consolidation phase starting in year 9 or 10 and beyond.  As mentioned earlier in this document, we feel fairly confident about the inputs during the start-up and expansion phases.  It is more difficult to accurately predict what will be required in the consolidation years, as no country has reached this point. However, these predictions are be based on what has been seen in other parts of the financial services sector as well as in other industries.

###### Diagram 1:  Cashless Ecosystem Development

###### Table 4:   Mobile Financial Services Business Inputs

# Strategies

All of MM4P’s LDC countries are currently in the start-up phase of market development; some are still building the basic service, while others are struggling to enter the expansion phase. UNCDF’ goal is to move all of its focus markets into the expansion phase, scaling the industry. UNCDF’s strategy is built upon a providing these core set of inputs that we believe are required to support the start-up phase and to hasten the entry into the expansion phase. Decisions will be made based on the state of the industry and an analysis of the interventions, should be the most likely to not only help MM4P achieve its outcomes and should ensure that the scaling of services includes sustainable, appropriate financial services for the poor.

MM4P will achieve its outcome through a set of primary and secondary strategies.  Primary strategies receive the bulk of MM4P’s energy and resources, particularly in the first few years when MM4P’s resources are limited. These interventions have been selected because we believe they can have a direct and more immediate impact on UNCDF’s key objectives of ecosystem development and customer adoption.  Secondary objectives will be achieved indirectly, initially, customized to support its primary strategies. However, these strategies will depend on the needs and the market and are likely to play a larger role once MM4P’s supported partners are implementing their projects.

## Primary Strategies

Primary strategies will focus on driving the accessibility, customer adoption and choice of products and services.  The three strategic objectives articulated below will be achieved through engagements with service providers, transaction volume drivers, and the delivery channel.

### Strategy 1.	Ensure available, affordable, and safe financial services for low-income customers.

- Work with BB and MFS partners that have the best proposals, capabilities, and potential to be scalable and/or replicable and are committed to reaching the mass market, including the poor.  MM4P will favor approaches that are transformative (i.e. bring in unbanked customers) and can have a significant demonstration effect.  Providers’ capabilities will be determined by the expression of interest submission, interviews, business plan analysis, and evaluation of the business against a set of partner criteria.

- Remain agnostic in regard to providers, whether they are banks, MNOs or payment service providers (PSPs).  However, MM4P but will favor meaningful partnerships between two or more of these types of providers.

- Support research to improve providers’ product and service mix by better understanding customer behaviors and “pain points”.  Initially, MM4P will favor applied or exploratory research that can help partners implement new or better services within a fairly short time period, over general or statistical research. Special attention will be paid to research that helps providers develop “second generation” financial products that allow customers to accumulate, or access, useful sums of money for life events, such as illness, natural disasters, funerals, school fees, and marriages. Once partners have achieved momentum, MM4P will look at investigative research that looks more closely at the factors that contribute to partners’ success.

- In most cases, grants will not be provided to purchase core technology or hardware, but may be used to improve or augment technology platforms, build APIs or other interfaces to provide linkages to other systems/partners, or secure technical support to implement new technology.

### Strategy 2.	Increase transaction flow through partnerships with high volume drivers

- Partner with bulk payment providers, billers, and/or distribution companies that can help capitalize the ecosystem and drive customer usage.  These interventions will be applied as early in the strategic and deployment states as possible. Partner decisions will be based on anticipated transaction volumes, frequency of delivery, ability/likelihood to reach low-income customers, and potential for replication. These may include G2P or P2B (i.e. bill pay).  MM4P will also pay special attention to payments linked with other funders and UN agencies.

- Develop a bulk payments service that could be delivered by multiple service providers in a country to avoid concentrating all of MM4P’s risk with one actor.

- Grants will be considered to augment or improve technology platforms, build back-end linkages, establish business processes, and/or provide technical assistance for the implementation.

### Strategy 3.  Build scalable, self-replicating delivery channels

- Support agent networks or models that can be quickly scaled and/or replicated. These networks may be built and managed outside of the provider, but developed in partnership with them.  Special attention will be given to developing incentives that enable agent networks to scale quickly and/or self-replicate.

- Support the development of methods, tools, or systems that enable agents to work in more difficult and remote regions, preferable drawing on existing tools and expertise.

- Grants may be for long or short-term technical assistance, training, capital funding for the establishment of agent network managers and/or guarantee mechanisms for credit lines to mitigate retail agent start-up and liquidity management capital requirements. In some cases, MM4P may consider bringing in an outside entity with experience to assist or start an operation.

## Secondary Strategies

Secondary strategies are also driven by customer adoption and scale. However, these objectives, which relate to furthering customer education and assisting regulators, will be undertaken to support the primary strategies on an “as appropriate” basis.  MM4P will attempt first to achieve secondary objectives through partnerships with its grantees, other funders or expert organizations. When these leveraged options are not available in a particular country, MM4P may engage directly with regulators or on issues related to customer uptake. Such engagements will be expected to accelerate the primary outcomes being pursued in that geography.

### Strategy 4.  Move customers from awareness to engagement, and beyond

During the first year of operations, UNCDF is choosing not to engage directly in customer education due to the high costs of bringing customers from “unaware” to “reliance”.  By working with high volume users, MM4P hopes to drive customers to utilize mobile financial services. This will bring them along the first steps of the customer journey.  MM4P will also provide additional support, as appropriate, to help customers move farther along the customer journey.

- Ensure that MMP4 partners understand the level of marketing investment required to successfully transition customers to regular users of the service. Provide assistance, as needed, to design and develop effective marketing, outreach and training campaigns.

- Provide funding to partners to test out new and innovative means to move customers from awareness to regular use.

- Partner with research organizations such as CGAP, GSMA, the BMGF, local funders and other multilaterals to provide additional inputs/support to MM4P customers and to ensure that UNCDF partners are included in relevant research studies.

- MM4P will not normally fund large scale marketing and outreach campaigns due to their high cost and difficulty in measuring results.  However, MM4P can work with partners to improve those campaigns, develop the capability to launch them effectively and to better measure their impact. MM4P may also consider subsidizing outreach campaigns in difficult areas (rural, poor, post-conflict).

### Strategy 5.  Assist regulators in providing proportional regulation and oversight

Regulators, which play a critically important part of the ecosystem, are being assisted in some countries through CGAP, the World Bank, AFI, and other funders.  These organizations have developed specific expertise related to payments regulations. Since driving these issues are not part of UNCDF’s core competency, MM4P’s preferred level of involvement will be through partnerships with the industry’s regulatory leaders. MM4P’s goal will be to ensure that the regulators in the focus countries have access to all the information they need to make educated decisions, as well as the expertise they require to craft appropriate laws, regulations, procedures and policies.

- Engage central banks from the onset to identify their goals, issues, and concerns.  This effort will also help MM4P understand the context in which it will need to achieve its goals, as well as the issues that potential customers, service providers, and delivery channels may face.

- Work with CGAP, AFI, and others to bring the regulators the information and exposure they require to progress along the regulatory journey from being interested in mobile financial services to establishing an appropriate regulatory regime.

- In those LDCs where other funders or institutions are not engaging regulators on these issues and if regulations are not conducive to enabling mobile financial services for the poor, MM4P may have to play a more comprehensive role.

# Approach

Like its strategy, MM4P’s approach is grounded in the lessons learned by UNCDF and the industry as a whole. The approach leverages UNCDF’s strengths, while also considering MM4P’s current technical and financial resource constraints.

## Role of Funders

As identified by CGAP, the key roles for funders are to (1) advise policy makers, (2) invest in public goods, particularly those that generate and share knowledge, (3) support branchless and mobile financial services with technical assistance, and (4) fund operations. The MM4P strategy includes work in all of these areas.

###### Diagram 2:  Role of Funders (CGAP)

MM4P’s funding approach also considers best practices for funder engagement, including the emerging lessons of funders that are supporting BB and MFS.  Those most relevant to UNCDF are as follows:

- Avoid distorting markets, but don’t avoid hard choices. Support private sector actors must be competitive and decisions must be transparent.  When the objective is to reach the poor, the opportunity to influence private sector partners to build inclusive services may outweigh the potential sensitivity them public funds.  MM4P will initially fund projects through a competitive process.

- Combine funding and technical assistance. Given the requirements of building an cashless ecosystem, funders should look for opportunities to leverage other programs and consider pooling or coordinating funding with others to share risk and augment their capabilities. MM4P will recruit retainer consultants to provide on-going advice to partners during implementation.

- Address the big “front-end” issues. Front-end issues include activities like ensuring consumer adoption, developing an effective, widespread agent network, developing products and services that are relevant for the low income unbanked segment, and proving the business case for serving that segment.  Many of these activities or goals fall under MM4P’s strategy.

- Favor technical support over providing core resources. Resources should focus more on the “front end” issues (products, delivery channels) rather than the back-end technology.

###### Diagram 3:  Risk Appetite

- Adjust to the context. Regulatory frameworks, customer needs, delivery channel infrastructure opportunities, number and size of high volume users, and capacity of service providers will be unique in each country.  As a result, funders inputs must be adjusted to suit the local conditions and address specific needs.  Although there will be some commonalities, support in each country will differ.  UNCDF engages with regulators daily through its country technical advisors who can assist MM4P in understanding and addressing their concerns.

- Accept informed risks -- and failures. While it is always desirable to invest in opportunities that lead to success, part of the purpose of grant or equity is to be “patient” funding to enable experiments, underwrite risk, and create the opportunity for implementations projects that are unproven. UNCDF’s risk appetite is medium to high. MM4P will seek to build a mix of projects that blend the high potential for success with those that can address the low level of access to finance. Most important, MM4P will document its complete experience as failures can be as instructive to the future development of the industry as successes.

- Tailor funding to project goals. The funding needs to be able to adjust to the objectives and business approaches of the recipients. In addition, there needs to be enough flexibility in the instrument to reward performance and permit adaptation. MM4P will primarily use performance-based grants which set a target and a minimum performance target to provide some room for variation.  Disbursements will be output-based rather than time-bound to facilitate either faster or slower achievement of results. In some cases, MM4P may choose to directly contract technical assistance on behalf of the partner, or even provide a loan or loan guarantee if they are the needed instruments.

- Give a consistent message. The fact that the funding is intended to increase the reach of services for the poor needs to be highlighted in communications with potential partners and be explicit in presentations, discussions and agreements.  Funders need to seek “win-win” situations for the funders, their partners, and, ultimately, and low-income customers. This voice is consistent with the “one UN” message that the UN is there to better the lives of the people in an honest and neutral manner.

- Build trust and a common vision. Funders can play a role of intermediary, particularly bridging the gap between traditional inclusive finance institutions, MNOs, and regulators. This is more likely to occur when they construct a road map for how to build those bridges.  MM4P will do this by bringing actors together, whenever possible, and attempting to resolve issues between these actors.

## Method of Implementation

### Preparation and Development Phase

In 2010, UNCDF conducted a desk study of 40 LDCs using statistics to develop a ranking based on objectively measurable indicators. In late 2011, UNCDF consulted its regional and country technical advisors to identify the countries on that list where UNCDF felt it had the best opportunity to help build or improve scalable BB and MFS.  In early 2012 UNCDF identified four countries in which it would begin its process, including:  Liberia, Malawi, Nepal, and Rwanda. In addition, MM4P has also agreed to assist UNCDF Laos which is working with AusAID to develop a comprehensive multi-year programme to support BB and MFS.

Beginning in late 2012, UNCDF will determine the next set of countries, if any, it will investigate. The decision will be based on a revision of the current data set on LDCs as well as consultations with UNCDF Regional Technical Advisors.

UNCDF has been in consultations with other funders active in supporting BB and MFS including CGAP, Gates Foundation, IFC, MasterCard Foundation, and GSMA Mobile Money for the Unbanked (MMU) to discuss how UNCDF can contribute meaningfully to the its development in LDCs. In each case it has discussed these focus countries with other funders and sought their information, input and advice.

###### Table 5  Focus Countries and Potential Outreach

| All figures in (‘000) |  | Current |  | Potential Customers |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Population | Mobile Penetration | Bank Penetration | Potential New | Potential New Unbanked | Potential New Active |
| Liberia | 3,477 | 68% | 11% | 352 | 106 | 123 |
| Malawi | 15,263 | 26% | 21% | 590 | 148 | 207 |
| Nepal | 29,331 | 37% | 20% | 1,612 | 403 | 564 |
| Rwanda | 9,998 | 57% | 23% | 854 | 213 | 299 |
| Laos | 6,320 | 48% | 40% | 603 | 151 | 211 |
| Total | 64,389 | 47% | 23% | 4,011 | 1,020 | 1,404 |
| MM4P Outcome |  |  |  | 4,000 | 1,000 | 1,400 |

### Project Identification

#### Scoping Missions

MM4P will conduct scoping missions in the markets identified that include an MM4P Advisor and an expert consultant. MM4P has developed a TOR template for the missions which can be adjusted to suit the context. The objectives of the scoping mission are:

- identifying and analyzing current, ongoing and planned BB and MFS related initiatives  and donors that are involved in these activities;

- conducting a review of existing legislation, regulations and guidelines, relevant institutions and their activities;

- identifying  and analyzing key players, stakeholders, partnerships;

- identifying current and potential challenges, constraints, gaps and opportunities in the use of BB/MFS in delivery of financial services;

- ascertaining government and industry concerns and willingness to increase financial access to the poor through use of BB/MFS as a delivery model

- engage the relevant regulator(s) to secure support for MM4P approach

The output of the mission is a report that includes:

- An analysis of all current, on-going and planned branchless and BB/MFS  initiatives;

- An analysis of industry wide plans and strategies for addressing existing bottlenecks and/or obstacles impeding development of BB/MFS;

- Gap analysis of current situation and identification of obstacles and opportunities;

- Recommendations and solutions for UNCDF to facilitate branchless/BB/MFS development as a means of significantly scaling up financial services to the unbanked poor;

- Proposition of at least three interventions, design and estimated cost;

- A roadmap for implementing a pilot BB/MFS initiative and its eventual scale up.

MM4P has committed to at least four scoping missions in 2012 and up to six during the development phase.

#### Expressions of Interest

In each focus country UNCDF must balance its desire to quickly select the most capable organizations with the best projects with ensuring that there is a process that is transparent and impartial to select partners. As noted in the strategy, UNCDF will seek to work with a combination of partners including the service provider, the distribution network and a high volume user. MM4P will work with local UNCDF and UNDP staff and other funders to issues requests for expression of interest (EOI) for grants and technical assistance. EOI submissions will be short, with a focus on the proposed project, outputs (and outreach), institutional capacity and financing needs. EOI submissions will be assessed on a set of key criteria that may be modified to address the specific contexts of the country. MM4P will review EOIs with local and regional UNCDF staff and develop a short-list of 2-4 projects in each focus country that represent a strong mix.

Prior to issuing EOIs, MM4P will share the EOI with other active funders in the host country. UNCDF is also required to secure approval or a “no objection” from the relevant government authority in each host country, usually the central bank. To hasten the process, MM4P will ask the central banks in host countries to review and comment on the EOI and to agree to a “fast-track” no objection procedure for shortlisted applicants prior to issuing the EOI.

### Project Design, Appraisal and Approval

UNCDF’s experience is that projects are more likely to succeed if technical assistance is given during the project design phase. This also gives UNCDF and opportunity to lead partners in a certain direction while also responding to their request for assistance. With the assistance of expert consultants, MM4P will work with shortlisted partners to develop the project design, targets, budget and implementation plan. The process may be short with a strong partner and require only offsite interaction if the partner has clear plan and the capacity to implement. In some cases it may require significant inputs from UNCDF including on-site and off-site assistance, and could include exposure or exchange visits and engagement with other experts.

#### Project Appraisal

Because the industry and markets are changing quickly, MM4P will not require an extensive business plan initially.  Unlike traditional MFIs, branchless and mobile financial service providers are not accustomed to developing business plans for external consumption and such plans are often developed for the funders’ use rather than for partners. MM4P will gather the critical inputs from partners in the most convenient and meaningful form, usually from their own internal documents. Through this process MM4P will gather the necessary information and documentation for to complete its due diligence.

Based on these inputs, the MM4P team will develop a project appraisal document that addresses the following:

- objectives and outputs;

- soundness of project design;

- management capacity and commitment;

- feasibility and sustainability;

- scalability and/or demonstration effect;

- analysis of key risks and mitigants;

- contribution to financial inclusion (low income, rural, vulnerable, women);

- value for money.

Projects that have completed the full assessment will be presented to the MM4P Investment Committee (IC) for consideration, including any recommended preconditions to funding.

#### Project Approval

The IC will consider all projects presented by the MM4P team. Projects will be judged on several criteria including:

- Overall appraisal

- Contribution to MM4P’s achievement of its mission, goal and outcome

- Value for money

Given the lack of resources, the MM4P team will submit only project that it feels have a strong chance of approval.

Once the IC approves the project, MM4P will negotiate performance-based agreements with the partner.  Agreements are output-based, such that funding is disbursed once key qualitative or quantitative targets have been met. MM4P will also consult with other active funders to advise them of the IC’s decision and seek to address any concerns that they may have.  Most important, MM4P will seek the “fast-track” approval of the host country central bank for the project immediately after IC approval.

### Policy and Advocacy Engagement

With assistance from UNCDF CTAs, MM4P will identify the key regulatory constraints and opportunities using a combination of diagnostic approaches from CGAP, Bankable Frontier Associates and AFI.  In most of the focus countries, other funders or stakeholders have begun to engage the regulator on BB and MFS and conducted a legal and regulatory inventory. With its UNCDF local staff, MM4P will determine its required level of engagement in policy and regulatory issues to achieve three goals: (1) secure a “no objection” for its partners’ proposed projects; (2) complement the existing support to the regulator from others; and (3) involve the regulator and other key government stakeholders in the global policy efforts on this issue. UNCDF has worked closely with CGAP, the World Bank, AFI and GSMA to bring the necessary learning, exposure and networking opportunities for regulators. Its approach will be to use its resources to deepen regulators’ engagement with these expert bodies and others which are well placed to provide long-term policy advice.  It will also use its resources to “fill the gap” in support by other funders. Examples of support are supporting attendance at learning events, providing targets technical advice, and facilitating exchanges, as needed.

### Customer research, education and protection

#### Customer Research

MM4P is keenly aware of the importance of customer research as well as the importance of educating and protecting customers. Quantitative research and large-scale surveys are valuable public goods and powerful tools that help providers, regulators, and funders alike. However, such research efforts require significant time, funding and expertise. MM4P lacks the resources to take on such efforts at present. At the same time, UNCDF’s observations in the Pacific is that timely, independent research is very valuable to providers within the first year of the service being offered and can help them direct their marketing and outreach efforts more effectively. Research to segment customers and identify important use cases is also valuable.

To address this issue efficiently, MM4P will verify that grant partners have conducted adequate market research. Otherwise, MM4P will seek to include customer and product research in the project design of partners. MM4P will also seek to reach out to other interested funders and the government to see if it can complement existing or proposed customer research efforts.

MM4P has budgeted for a Knowledge Manager beginning in 2013. Should MM4P succeed in raising additional funds, it will seek to expand its effort into public research, particularly as it relates to customer adoption, behaviors and benefit. In doing so, it will also work closely with regulators which have a keen interest in data gathering. In all cases, UNCDF will seek to link with existing financial service research efforts, such as FinScope, Financial Diaries and others.

#### Customer Education

Financial education efforts as a whole are still in the early stages of development and it is very difficult to measure impact of specific interventions. Providers are increasingly interested in securing assistance to offer or facilitate financial education for their customers. They recognize that the lack of financial competency impedes customers’ ability to understand the value of the service and use the service correctly. The theory of change behind financial competency is similar to the “customer journey” highlighted in the Diagram 4.

A challenge for branchless and mobile financial service providers is that have little (if any) direct personal contact with customers; rather the customers interact electronically and through third party agents.  As the noted by the Financial Education Fund, the cost of data collection increases as indicators shift from input through output, outcome and impact. Mass media and other non-direct channels provide creative alternatives, but the customer behavior prior to the skills and attitudes cannot be gauged unless through population wide surveys.

###### Diagram 4:  Financial Capability Progression

While behavior (e.g. use of the service) can be measured and tracked, it will be difficult to attribute the cause behind the change. As a result, most financial capacity efforts supported would have to be measured through a combination of activities and behaviors, rather than skills, attitudes or impact.

UNCDF’s own research shows that financial education improves not only consumer’s financial behaviors, but also improves and their use of financial services.  Financial education is more effective when paired with products or services that enable the customer to put that education to use.  Unfortunately, MM4P does not have adequate resources to fund large scale financial education efforts independently of its partners. In the development phase, it will help partners to develop plans to address this issue and consider subsidizing efforts of short-listed partners or assistance in the technical design of such efforts. Some key issues MM4P will consider are:

- Is the effort of value to the client or is it primarily to benefit the provider?

- Is there a means to measure the baseline and change in behavior?

- Is the effort sustainable or valuable enough for providers to continue it.

Of particular interest to MM4P is how providers can leverage their communications (SMS, call campaigns) to provide concise, useful information to customers on financial education.

Should MM4P continue with adequate funding, MM4P will work with the UNCDF country programmes in focus countries to identify innovative financial capacity building efforts that can be expanded to include a specific focus on BB and MFS.  It will also work with UNCDF staff what efforts related to financial literacy the host country central banks are conducting and how MM4P might support them.  Rather than create something new, it is important for MM4P and UNCDF to work within the existing delivery structures for providing financial education and seek ways to address the use and benefits of the cashless ecosystem.

#### Customer Protection

UNCDF is also committed to consumer education and protection and is a signatory of the Smart Campaign. Unfortunately, there are few consumer protection guidelines for BB and MFS at present. MM4P’s approach will be twofold:  it will request grantees become members of the Smart Campaign; and it will work with other interested parties globally to establish principle for client protection relevant for BB and MFS.

### Knowledge generation and sharing

UNCDF has found knowledge sharing to be critical to educate partners and regulators in the inception phase of mobile money, and build a culture of learning and sharing around this new industry. UNCDF recognizes its limitations in generating knowledge and it benefits from membership in CGAP as well as close association with other organizations that are active in industry research.

MM4P’s approach is to share existing knowledge regularly with partners, assist partners in attending learning events, facilitating exchanges and support local learning events.   UNCDF has found that supporting key stakeholders to participate in such events builds trust and goodwill that ultimately leads to positive actions.  It also helps build a sense of community between disparate stakeholders involved in BB and MFS—including regulators and providers—that is necessary for finding mutually beneficial solutions.

MM4P will not invest in large global studies in the first few year; rather it will contribute to the global learning agenda by requiring partners to report regularly and to participate in evaluations and others’ studies.  With the agreement of its partners, it will issues a series of shorter notes that highlight the lessons learned in the first few years.

MM4P has budgeted for a part-time Knowledge Manager to begin in 2013 to manage this area. Beginning in 2014, MM4P will commission studies to evaluate the outcomes of its works and capture the lessons learned.

# Outputs and Measurements

Mobile Money for the Poor will work on four key areas, all of which are needed for both the programme and its partners to succeed.  The outputs reflect the strategy and approach.

## Output 1:  Scalable, replicable solutions that reach the poor

Scalable and replicable BB and MFS providers deliver accessible, available, reliable and affordable financial services to low-income persons, small and microenterprises, including women and those in rural and remote areas.

Output 1 is the primary focus of MM4P and will receive the greatest resources and focus in the development phase of the programme.

The key support areas under Output 1 will include:

- introducing, extending or improving financial services;

- building or improving distribution channels;

- adding high volume drivers to the services;

- introducing new products and services appropriate for the poor;

- building new partnerships between providers, distributer and users.

The indicators used to measure progress will be as follows:

- The number of additional clients that gain access to a BB or MFS;

- The number of active clients that are accessing BB or MFS;

- The number of “transformational” clients, those who were previously unbanked, disaggregated by gender and urban/rural;

- Number of points of full service and partial service (e.g. ATMS, POS) disaggregated by urban/rural;

- Frequency of services interruptions or closures (track in %).

## Output 2  Informed, client-centered products, services and delivery mechanisms

Market and customer research is created and shared to enable policymakers, providers, distributors and others to develop products, services and new approaches to move clients from awareness to reliance on branchless and mobile delivery channels.

Initially, Output 2 will be imbedded in the project design of partners.  However, MM4P will work to develop independent research as a “public good” once it has the resources to do so.

Potential assistance will focus on:

- Assisting partners to conduct initial market and client surveys, drawing on the existing tools developed by others, to identify the gaps in the market and the opportunities;

- Assisting partners in product development and piloting;

- Assisting partners in developing better capacity to conduct in-house research, as well as capture and analyze and analyze to understand and measure client activities;

- Commissioning, co-funding or helping to shape quantitative and qualitative demand research into low-income customers’ behaviors, needs, competence and attitudes in regard to BB and MFS;

- Assist partners in developing meaningful financial capacity building of customers;

All research will be conducted to include gender disaggregated data to maintain an emphasis on reaching rural and female customers.

The indicators used to measure progress will be as follows:

- Number of clients gaining access to a new pro-poor product or service (e.g. low cost deposit, microinsurance, cash transfer, etc.), disaggregated by gender and urban/rural;

- Number of products designed based on quantitative and qualitative market research;

- Cost of service;

- Number of projects which include a financial education  or consumer awareness component;

- Number of partners that formally commit to the Smart Campaign or similar principles;

- Number of clients reached by financial education or consumer awareness.

## Output 3 Educated and engaged policy makers, regulators and other key stakeholders

Relevant policy makers, funders and other stakeholders supported and empowered to make decisions and take coordinated action and allocate resources to enable partners to achieve their targets.

This output includes both the policy and advocacy work at the country level, but also MM4P’s contribution to coordination and cooperation at the global level.

Activities will include:

- Work with AFI, CGAP, the World Bank and other relevant funders to help policy makers and regulators in focus countries build an enabling environment for a thriving cashless ecosystem;

- In partnership with AFI, link policy makers and regulators in focus countries with a global network to share experiences and commitments, through on-site visits, workshops, and  participation in AFI and others’ learning events;

- Lobby governments to implement government to person (G2P) payments through branchless or mobile channels.

- Assist UNCDF country programmes in addressing their needs in regard to BB and MFS;

- Represent UNCDF at global events related to BB and MFS and participate in corporate activities on the topic;

- Train relevant UNCDF and UNDP in-country staff on programme initiative and projects to prepare them to conduct regular monitoring;

- Coordinate donor efforts, particularly in host countries, to ensure maximum cooperation and coordination;

The indicators used to measure progress will be as follows:

- Number of permissions granted for a BB or MFS service to MM4P partners;

- number of policy or regulatory impediments or constraints to partners’ projects reduced or removed (i.e. KYC or other regulatory or policy restrictions) or enabling regulations or policies implemented;

- Number of focus country governments that encourage or engage in consumer awareness and protection for BB and MFS clients (with MM4P’s assistance).

- Number of joint-funder efforts, including research, co-funding or co-sponsoring.

## Output 4 Shared knowledge and experiences

Partner and other key stakeholders have access to global information, learning events on global best practices and lessons are learned, documented and shared.

Activities will include:

- Support learning for partners and other key stakeholders that will promote the success of its projects or otherwise contribute to meeting its objectives;

- Develop strategy and procedure for knowledge generation and knowledge sharing that includes CGAP, MasterCard Foundation, Bill and Melinda Gates Foundation, GSMA and other relevant knowledge builders in the industry;

- Contribute to the global learning agenda by requiring partners to report regularly, participate in evaluations and others’ studies;

- Establish a regular communication initiative with partners, policymakers and other stakeholders in focus countries;

- Develop a notes series on lessons learned and opportunities;

- Develop and implement a meaningful and appropriate monitoring and evaluation plan, building on the required UNCDF policies and procedures.

The indicators used to measure progress will be as follows:

- Number of research products produced or contributions made to research by MM4P;

- Number of partners supported to attend learning events or participate in exchanges;

- Number of learning events sponsored or co-sponsored by MM4P;

## Output 5  High performance, respected team

Develop a nimble, efficient, transparent and well-respected global programme that is a model for UNCDF.  The key activities are:

- Build a small team of qualified, energetic experts that is respected globally and by UNCDF’s partners;

- Establish a well-functioning programme and office, with clear procedures that are followed;

- Assist UNCDF in fulfilling the its corporate management plan and contribute to the follow-on plan;

- Develop and maintain a strong, informed and effective investment committee.

- Manage and use funds wisely to maximize programme goals.

The indicators used to measure progress will be as follows:

- Quality of UNCDF contracted technical support, as measured by partners;

- Timeliness of semi-annual reports to IC;

- Amount of funds raised to directly support MM4P;

- Amount of funds raised for UNCDF with MM4P assistance or inputs;

During the development phase, the project will not focus on all outputs to the same extent. The ambition level for the full programme is shown in the Logical Framework in Annex 1.

# Part II	Annual Work Plan 2012

The Annual Work Plan sets out the annual priorities, activities and budget for the year.  This document will guide the MM4P team throughout the year.  The annual work plan for 2012 includes March – December, the first nine months of the development phase. The key goals of the development phase in the Project Development Document are clearly stated as:

- Complete the scoping of the potential markets and identify projects to fund;

- Develop the policies, procedures, plans and budgets for the programme;

- Raise a total of $15 million of the $26 million total proposed budget for the programme;

The 2012 AWP closely follows these priorities.

# MM4P Status Update

The project development document was approved in December 2011.  UNCDF had secured a total of $5.6 million to begin the programme, approximately 20% of the total proposed funding. Therefore UNCDF chose to approve MM4P for up to a two year “development phase” rather than a five year project.  This was also in keeping with other interested funders’ who preferred to see MM4P fully established programme with a clearly identified pipeline of projects before committing resources.  While fundraising efforts are proceeding, a supplemental plan was included in the project development document to highlight the staged approach.

Diagram 5 below highlights the plan for a staged approach as UNCDF seeks additional funding partners. The different work packages (W) each need to work together, however some can be initiated after others. The development phase includes work packages A, B and C, which are heavily focused on Outputs 1 and 2, Scalable Projects and Market Research. However, the trigger for work package D is to attract a main funder to the programme that enables it to expand. At this stage, Outputs 1 and 2 will expand dramatically and effort will be made to develop Outputs 3 and 4. Policy, Advocacy and Coordination as well as Knowledge Sharing.

A key decision point will be in Q1 or Q2 of 2013.  At this point, MM4P will have a clearer idea of the progress of its efforts as well as the likelihood of securing additional financial support. At this point, the IC will have the opportunity to decide if MM4P should consider additional countries or additional efforts in the focus countries.

###### Diagram 5:  Roll-Out of MM4P in Develoment Phase

# 2012 Priorities

It is important that the programme maintains focus on the steps need to achieve its outcomes. This is particularly true in the programme development during which a clear focus is needed to ensure MM4P is established position and role in the global development of BB and MFS and is able to attract additional financial support.  Each year, the AWP will recommend priorities that will help determine which activities will be pursued.

The proposed priorities in order of importance for 2012 are as follows:

- Scoping exercise in at least four countries to establish the basis for MM4P activities and a pipeline of projects;

- Identifying, appraising and approving funding in at least two countries with a mixture of partners with a high chance of success and the possibility of reaching the poor with two years;

- Consulting, coordinating and collaborating with other funders and key global stakeholders to establish MM4P’s relevance;

- Raising additional funds to secure MM4P’s longer-term future;

- Establishment of MM4P’s as a well-run programme, including staffing, policies and procedures and office set up.

# Activities

Planned activities are those identified by MM4P as definite pursuits, are scheduled and budgeted, and are pending IC approval.

MM4P has planned the following activities and projects for the coming year, organized by output in Table 6.  This list will adapt and grow during the year as new initiatives are explored. For instance, not all focus countries may result in the an expressions of interest in 2012 if the scoping mission results indicate it is too early to solicit them. The priorities are proposed by the MM4P Advisor and Programme Manager and may be subject to revision based on the input of the IC and developments in the focus countries.

The positions of Technical Specialist (TS) and Programme Associate (PA) are being recruited.  Unfortunately, these are unlikely to result in hires until Q3, 2012.  In the interim the Advisor and Programme Manager has responsibility for all activities and is being supported by expert consultants.

## Programme Activities

###### Table 6:  Programme Activities

(PM = Advisor/Programme Manager. TS = Technical Specialist, KM = Knowledge Manager, RTA = UNCDF Regional Technical Advisor, CTA = UNCDF Country Technical Advisor)

| 2012 |  |  |  | Output | Activity | Description | Tasks | Assigned | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |  |  |  |  |  |  |
|  | x | x | x | 1 | Investment Committee | Establish an informed and interested investment committee to oversee programme activities and grants | - Establish IC policies and procedures (May) - Organize initial meeting, approve policies (June) - Identify and recruit expert non-funder participants (Jun) - Identify meeting venue/regularity (Jun) - Conduct one meeting quarterly or as needed | PM | H |
|  | x | x | x | 1 | Create MM4P Fund | Develop a flexible, nimble performance-based fund facility that can respond to or promote opportunities to develop mobile money solutions for the poor | - Develop policies and procedures (Jun) - Develop appraisal document (May) - Set criteria for funding per country (Mar) - Develop Expression of Interest for each country/RFA docs (Mar-Dec) - Get IC approval (Jun) - Finalize reporting formats (Aug) | PM | H |
|  |  | x | x | 1 | Grantee oversight | Oversee and monitor progress grantees | - Conduct training of UNCDF country staff to conduct regular monitoring (Sep/Oct) - Contract retainer consultants to provide remote and (as needed) on-site TA during the project cycle (Sep – on-going) - Maintain regular contact to discuss progress (On-going) - Assist in resolving issues and identifying opportunities (on demand) - Collect quarterly reports, analyze and provide feedback (On-going) | TS | M |
|  | x | x |  | 1, 2, 5 | Expert Assistance | Build roster of experts and identify at least one expert per region to retain on contract to assist with identification, development and oversight of projects | - Add consultants to roster of experts from UNCDF/UNDP and other databases (Mar) - Identify consultants for scoping missions, project development through retainers or experts roster (Jun) - Develop retainer contract procurement process for TA (Jul) - Advertise, receive and vet applicants (Aug) - Conclude retainer contracts for on-going TA (Sep) | PM, TS | H |
|  |  | x | x | 1,2,3 | G2P, B2P | Identify G2P or B2P opportunities in host countries | - Raise awareness on G2P or B2P during scoping missions (Mar – ongoing) - Identify at least one mass payment opportunities in host countries (Mar-Dec) - Advocate on G2P with partners, design one project (Mar-Dec) - Approve assistance for one G2P project (Dec) | TS, CTA, Experts | M |
| x | x | x | x | 1 | Country mobile money scoping missions | Diagnostics of short-listed countries | - Develop TOR for retainer consultants (Mar), vet with stakeholders - Conduct inventory, collect BB and MFS research on focus countries (Feb-Sep) - Scoping mission in Malawi (Mar) - Scoping Mission in Nepal (May) - Scoping Mission in Liberia (May) - Scoping Mission in Rwanda (TBD) - Visit countries, conduct scoping mission and regulatory diagnostic - Vet scoping studies with stakeholders | PM, TS, Experts | H |
|  | x | x | x | 1 | Malawi Project Development | Identify, appraise and approve projects | - Issue request for EOI in Malawi (May) - Vet responses, create shortlist (Jun) - Assist at least 2partners in finalizing projects (Sep) - Approve at least 2 projects (Oct) and negotiate PBAs | PM, TS, Experts, CTA, IC | H |
|  | x | x | x | 1 | Nepal Project Development | Identify, appraise and approve projects | - Issue request for EOI (Jun) - Vet responses, create shortlist (Jul) - Assist at least 2 partners in finalizing projects (Oct) - Approve at least 1 projects (Nov) and negotiate PBAs | PM, TS, Experts, CTA, IC | H |
|  | x | x | x | 1 | Liberia Project Development | Identify, appraise and approve projects | - Issue request for EOI (Jul) - Vet responses, create shortlist (Aug) - Assist at least 2 partners in finalizing projects (Dec) - Approve at least 1 projects (Dec) and negotiate PBAs | PM, TS, Experts, CTA, IC | H |
|  |  | x | x | 1 | Rwanda Project Development | Determine MM4P’s role | - Work with IFC, MC and CTA to determine MM4P role in Rwanda - If chosen, issue request for EOI (Oct) | PM, TS, Experts, CTA | H |
|  |  |  | x | 1,2,3 | Remittances | With IFAD and other UN programnmes, develop remittance links | - Present project to IFAD, identify best means to partner (Oct) | PM, RTAs | L |
|  | x | x |  | 1,3 | MicroLead | Assist in vetting BB and MFS proposals | - Review MicroLead proposals with BB and MFS content (Apr-May) - Assist Microlead PM in creating PBAs (Jun – Aug) - Determine MM4P’s role in collaborating, oversight, if any | PM, MicroLead PM, TS, RTAs | M |
|  | x | x | x | 1,2,3 | Country Programme Assistance | Assist UNCDF country programmes with BB and MFS | - Assist UNCDF Laos in developing and implementation plan for a BB and MFS project for AusAID (Jul) - Assist INFUSE Timor-Leste in project identification and appraisal (Jul – Dec) - Respond to requests for assistance from RTAs and CTAs - Follow up on leads from UNCDF RTAs, CTAs and country offices, prioritize funding opportunities for UNCDF country programmes | PM, TS, RTAs, CTAs | M |
|  |  | x | x | 2 | Market demand Research | Commission quantitative and qualitative research on the nature of demand for financial services | - Inventory market research on customer demand in focus countries during scoping missions (Mar - ?) - Work with partners to identify information gaps (Mar – Dec) - Seek opportunities to assist other leaders in public market research - Work with at least one approved partner to include market research in the project design (Jul - Dec) | PM, TS, KM | L |
|  |  |  | x | 2 | Product Research | Assist partners in conducting quantitative and qualitative research on existing or proposed products | - With at least two selected partners, identify best product opportunities in focus countries (Dec) - Assist partners in developing TORs for assistance to conduct strong product research. (Dec) - Agree on protocol for sharing results of proprietary research | TS, Experts | M |
|  | x |  | x | 2 | Financial Capacity | Identify and incorporate financial capacity into programme | - Identify strategy and approach for MM4P to address financial capacity building (Apr) - Add indicators related to output related to inputs and outcomes (Apr) - Identify fin. Capacity efforts in EOIs (Jun – Dec) - Contract assistance to work with partners to address fin. Capacity efforts (Oct) | PM, TS, Experts | M |
|  |  |  | x | 2 | Impact Research | Determine approach to measure impact | - Discuss timing and scope of impact research with IC (Aug) - Develop strategy for impact research (Dec) - Initiate in 2013/14 | KM, Experts | L |
| x | x | x |  | 3 | Regulatory Inventory in focus countries | Maintain clear record of current regulation regarding mobile financial services | - Review existing regulatory data (Mar – Dec) - Identify gaps in knowledge in focus countries (Mar – Dec) - Complete inventory for two countries (Dec) | PM, CTAs, Experts | M |
|  | x | x | x | 3, 5 | No objection procedures | Secure “no objection” for approved projects | - Develop “no objection” procedures (Mar) - Present to regulators during scoping missions (Mar – Sep) - Secure “no-objection” agreements for approved projects (Sep) | PM, TS, CTAs | H |
| x | x | x | x | 3 | Advocacy on regulation | Work with AFI, CGAP and the World Bank in a partnership to work with regulators in project countries to ensure the enabling environment for the mobile money deployments | - Work with CTAs and AFI to identify key regulators in focus countries (May-Dec) - With UNCDF regional/country staff, visit/inform regulators of programme (Mar – on-going) - identify opportunities and gaps in coordination with others working in regulatory space during scoping missions (Mar – Dec) - Support at least two regulators to educate themselves, through exchanges and scholarships or workshops (Jun – Dec) | PM, CTAs, Experts | H |
|  | x | x |  | 3 | AFI partnership | Establish partnership between AFI and UNCDF | - Identify best means for MM4P to collaborate closely with AFI - Negotiate partnership agreement with UNCDF and AFI to support regulatory change | PM, UNCDF | M |
|  | x | x | x | 3 | Better than Cash | Assist UNCDF in establishing BTC, as needed | - Participate in BTC selection of secretariat (Mar) - Assist UNCDF in determining response to BTC (Apr-May) and developing proposal - Assist in workplan development for BTC (June – Aug) - Provide input in to Management Committee (Aug – Dec) | PM | M |
|  |  |  | x | 3 | UN Agencies | Advocate within UN system | - Identify key UN agencies for MM4P and BTC (Sep) - Liaise with agencies to identify best opportunities in focus countries (Sep – Dec) | PM, TS, UNCDF | L |
| x | x | x | x | 3 | Donor Coordination | Ensure that donors in focus countries are adequately coordinating efforts | - Identify existing coordination mechanisms, both local and international during scoping missions - Inform local donors of efforts, seek input - Conduct one joint scoping mission (Dec) - Participate in at least two global donor coordination meetings (Apr, ?) - Co-host donor training with CGAP on BB and MFS (Jun) - Assist coordinating bodies in maintaining dialogue on current and planned projects in inclusive finance/mobile money (on-going) - Share information on projects under consideration with coordination mechanisms (on-going) | PM RTAs CTAs | H |
|  | x | x | x | 3, 5 | Fundraising | Secure leads for at least $10 million in funds | - Secure a commitment from AusAID of $500,000 - Continue dialogue with MC Foundation, move project to next stage of approval (Sep) - Meet with Gates Foundation to discuss MM4P and the new strategy (Mar) - Initiate discussion with EU on possible 2014 funding (Mar – Dec) | PM, TS, UNCDF | H |
|  |  | x | x | 4 | Knowledge Mgmt. Policy | Develop Knowledge management policy including coordination role with others | - Recruit and hire KM Associate (see output 5) - Discuss with major creators of knowledge how best to share information (Mar – Dec) - Develop draft KM strategy for IC - Identify means to require partners to participate in global studies of others | PM, KM, UNCDF | L |
|  | x |  | x | 4 | UNCDF Capacity Building | Develop UNCDF ability to oversee and develop mobile money | - Provide workshop at regional FIPA meeting (Sep-Oct) - Provide tools to understand and identify opportunities (Oct) - Identify key staff in host countries (Mar-Dec) - Identify training opportunities, both international and in-country for key staff (May – Dec) - Conduct information session for UN agencies in Brussels (May) - Educate other UN agencies on MM possibilities | PM, TS | M |
|  | x | x | x | 4 | Learning events | Sponsor key partners and stakeholders for learning events | - Identify learning needs of shortlisted partners - Support learning for partners and other key stakeholders that will promote the success of its projects or otherwise contribute to meeting its objectives. - Contribute to at least one global learning event | PM, TS | M |
|  |  |  | x | 4 | Monitoring | Monitoring and Evaluation of Programme | - Develop a regular regime of reporting on activities and results to stakeholders and other interested parties (Sep) - Develop and implement a meaningful and appropriate monitoring and evaluation plan, building on the required UNCDF policies and procedures (Nov) - Set quarterly reporting with partners (Sep) - Set semi-annual reporting with IC (Jun) | PM, TS | M |
|  |  | x | x | 4 | Standards Setting | Be part of development of standard creation in mobile money | - Work with funders and others to develop initiative to standardize definitions and standards for reporting (e.g. Mix Market or GSMA) - Require partners to report according to global standards, to global benchmarking groups (when possible) | PM | L |
|  |  | x | x | 4 | Information Exchanges | Information exchanges in focus countries | - Hold at least two local information exchanges | TS, CTAs | L |
|  | x | x | x | 4 | International Fora | Participate directly or through partners in relevant international events | - GSMA MMU (Feb, Oct) - AFI Global Policy Forum (Mar, Sep) - MMT (one per year) - MFWA (2x per year, call) | PM | M |
| x | x |  |  | 4 | Visibility | Develop visibility of the programme and its funders | - Finalize name and identify of programme (Aug) - Develop market/branding guidelines for programme (Sep) - Develop and maintain a website for the project for promotion and information sharing (2013) - Develop basic materials to promote programme (Aug) - Draft TOR for website development (Dec) | PM, KM | M |

###### Table 7:  Key Risks and Mitigants to Programme Activities

| Output | Risks | Likeli- hood | Impact | Possible Mitigation |
| --- | --- | --- | --- | --- |
| 1 | Scoping missions cannot identify quality projects | L | H | - Identify technical assistance needs of high potential partners and develop plan to raise capacity - Identify alternative focus country |
| 1 | EOIs are of poor quality | M | M | - Select high potential partners - Agree on technical assistance with experts and education to determine merits of possible project - Forgo first round of EOIs, reissue at later date - Identify external third party interested in entering country |
| 1 | Failure to identify G2P initiative, receive EOI | M | L | - Identify other private/non-profit alternative - With CTAs and UNDP, lobby government on G2P - Expose key decision makers to key learning events - Link with BTC initiative to raise profile of G2P - Work with other funders to identify alternative possibilities |
| 1 | Political or economic upheaval | M | M | - With CTAs, determine impact on timing and outcome - Adjust MM4P time frame accordingly - Be flexible in negotiating changes with partners |
| 3 | Failure to get central bank “no objection” | L | H | - With CTAs and UNDP, lobby central bank for support - Identify key issues with CB and address - Seek AFI assistance to address concerns - Expose key decision makers to key learning events - Raise profile of central bank efforts internationally (AFI) |
| 3 | Prohibitive regulatory environment | M | H | - With CTAs and UNDP and key regulatory funders, lobby central bank for support - Work with key regulatory donors to develop strategy for change - Seek AFI assistance to address concerns - Expose key decision makers to key learning events - Raise profile of central bank efforts internationally (AFI) |
| 3 | Funder disagreement | L | L | - Meet with host country funders to identify concerns - Engage CGAP to discuss difference - Find means to complement host country funders |
| 3 | Lack of fundraising | M | H | - Continue dialogue with current UNCDF funders - Visit funders to highlight programme work - Cooperate with country programme to attract local funder support for BB and MFs |
| 3, 4 | Bad publicity related to mobile money (locally, regionally, globally) | M | M | - Proactively engage with regulators on mobile money developments - Encourage partners to develop regular communication with regulator - Work with global stakeholders to address issue through case studies |

## Management Activities

### Update on Management Activities

UNCDF assigned the Pacific Regional Advisor as the MM4P Advisor and Project Manager.  
As project development with partners will be a highly interactive process, UNCDF will recruit a full time Technical Specialist to work exclusively on building the pipeline and overseeing partners’ performance.  The recruitment process began in March and will hopeful result in hiring by Q3.   UNCDF is considering hiring a shared Knowledge Management Associate that can work with MM4P and other UNCDF global programmes. MM4P is currently in the process of recruiting a Programme Assistant, hoping to identify a current staff member in either UNCDF or UNDP with the requisite experience who is willing to take on the role.  In the interim, UNCDF is benefiting from part-time support from a Programme Assistant from a UNDP programme based in Brussels.

UNCDF opted to place MM4P in the UN House in Brussels, Belgium. The location is intended to 1) limit travel time to Africa and Asia and minimize the time difference, 2) situate MM4P near the headquarters of the largest mobile network operators, and 3) place MM4P in the proximity of potential funding partners.

###### Diagram 8:  MM4P Organizational Structure

The key roles of staff in 2012 are as follows.

###### Table 8: MM4P Staffing

| Title | Role | Focus Areas |
| --- | --- | --- |
| Advisor /Project Manager | - Recruit, hire, train and manage team - Develop Strategy, Policies, Procedures - Draft AWP and Budget - Plan scoping missions - Draft technical TOR, recruit consultants - Draft EOIs, evaluate submissions - IC Secretariat - Coordinate relations with donors - Lead fundraising efforts - Provide technical support to UNCDF | - Output 1 – co-lead - Output 2 – support - Output 3 – lead - Output 4 - support - Output 5 - lead |
| Technical Specialist | - Conduct scoping missions - Draft EOIs, evaluate submissions - Develop technical projects with partners - Oversee expert consultants - Draft project appraisals - Negotiate and draft performance based agreements - Identify research opportunities - Draft technical TORs for research - Oversee partner reporting, monitor, provide feedback - Conduct technical trainings - Provide technical support to UNCDF | - Output 1 – co-lead - Output 2 – lead - Output 3 – support - Output 4 – support - Output 5 – assist |
| Programme Associate | - Manage office - Prepare requisitions - Dispatch POs, request payment - Manage travel, claims, visas - implement daily administrative and finance operations - Prepare office budget - Input budget, budget revisions, track budget - Assist in procurement, preparation of documents - Logistics for meetings, workshop and trainings | - Output 1 – assist - Output 2 – assist - Output 3 - assist - Output 4 – support - Output 5 – lead |
| Knowledge Management Associate | - Identify, facilitate Knowledge sharing - Manage partner scholarships - Plan events, workshops - Manage publications, PR UN and Funder Reporting, M&E - Support TORs for research | - Output 1 - assist - Output 2 – support - Output 3 – support - Output 4 – lead - Output 5 - assist |

###### Table 9: Management Activities

(PM = Advisor/Project Manager, TS = Technical Specialist, KM = Knowledge Manager, PA = Programme Associate, FIN = UNCDF Finance, HR = UNCDF Human Resources, IF = Inclusive Finance Directors)

| 2012 |  |  |  | Output | Activity | Description | Tasks | Assigned | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |  |  |  |  |  |  |
| x |  |  |  | 5 | Project Manager | Recruit, hire and move PM | - Completed via internal transfer | IF, HR | H |
|  | x | x | x | 5 | Technical Specialist | Recruit, hire, move TS | - Completed job description (Mar) - UN approval (Apr) - Advertise (Apr) - Shortlist (May) - Interview (June) - Offer (Jul) - Relocate and train (Aug) | PM, IF, HR | H |
| x | x | x |  | 5 | Programme Associate | Recruit, hire local PA | - Develop short-term TOR for UNDP BRU support (Feb) - Establish short-term support arrangements (Mar) - Completed job description (Feb) - UN approval (Apr) - Advertise (Apr) - Shortlist (May) - Interview (May) - Offer (Jun) - Commence and train (Jul) | PM, HR | H |
|  |  |  | x | 5 | Knowledge Manager | Recruit, hire KM | - Determine sharing arrangements with MicroLead, Youthstart (Jul) - Completed job description (Aug) - UN approval (Sep) - Advertise (Sep) - Shortlist (Oct) - Interview (Oct) - Offer (Nov) - Relocate (Jan 2013) | PM, MicroLead PM, Youthstart PM, IF, HR | M |
|  | x |  |  | 5 | Annual Work Plan | 2012 Strategic Review and AWP approved | - Update situational analysis (Feb-Mar) - Develop strategy document (Mar-Apr) - Draft work plan (Apr) - Approve work plan (May – Jun) - Draft strategic review 2013 (Dec) | PM, IC | H |
| x |  | x |  | 5 | Budget | 2012 budget approved | - Draft budget (Jan) - Approve budget (Feb) - Modify semi-annually (Jun) - Quarterly monitoring (Jul, Oct) - Draft 2013 budget (Dec) | PM, IF, PA, FIN | H |
| x | x | x | X | 5 | Office | Establish office | - Finalize arrangements with UNDP BR, sign lease (Feb) - Establish communications (Feb) - Purchase equipment (Mar – Jun) - Purchase furnishing (Mar – Jun) | PM, PA, IF, FIN | M |
| x |  | x |  | 5 | ICF | Finalize internal control framework | - Draft ICF for start-up (Jan) - Monitor ICF issues (Feb-Jun) - Modify, finalize and document ICF (Jul) | PM, IF, FIN | M |
|  |  | x |  | 5 | Reporting | Funder Reporting | - Establish semi-annual IC reporting format (Jul) | PM, PA | M |
|  | x | x |  | 5 | RCAs | Complete individual workplans and assessments | - PM workplan (Mar) - TS, PA workplan (Sep) | PM, TS, PA, IF | L |
| x | x |  |  | 5 | PFIP transition | Provide advice during transition | - Provide advice in interim period, resolving problems (Feb-May) - Conduct handover, training with new PFIP Advisor (May) | PM | H |
|  |  | x |  |  | Annual Retreat | IF Annual Retreat | - Participate in retreat (Sep-Oct) - Assist in developing sessions on MM4P | PM, TS | M |
|  |  |  |  |  | Corporate Fundraising | Raise regional and core funds | - Contribute to global fundraising efforts - Represent programmes to European donors, as requested - Assist with securing AusAID core funding | PM | M |
| x | x | x | x |  | Corporate Support | Support overall Corporate Strategy | - Assist in liaising with the EC - Assist IF in finalizing Mix Market reporting | PM | M |
|  |  |  |  |  | UN Coordination | Work with UNDP BR to support overall presence and coordination | - Participate in HOA meetings - Participate in key policy group meetings - Contribute to UNDP BR annual report for EU - Seek synergies with |  |  |

###### Table 10:  Key risks and mitigants to management activities

| Output | Risks | Likeli- hood | Impact | Possible Mitigation |
| --- | --- | --- | --- | --- |
| 5 | Delays in recruitment of PA | H | M | - Secure short-term assistance from UNDP BR - Request secondment from field |
| 5 | Delays in recruitment of TS, inability to identify candidate | H | M | - Contract retainer consultant through competitive process - Refocus retainer consultants to provide more general support - Seek secondment from field |
| 5 | Delays, complications in expert consultant recruitment | M | L | - Utlize Asia and Africa regional retainer consultants for short term - Seek UNCDF HQ assistance to hasten the process - Work with UNDP BR to expedite the process |
| 5 | Key staff becomes unavailable | L | H | - Identify possible UNCDF staff to provide oversight in interim - Seek waiver for non-competitive process to quickly fill position - Reschedule AWP activities to reflect loss of staffing |
| 5 | Delays in funders disbursement | M | H | - Borrow against received funding, track expenditures for reversal - Rebudget UNCDF contribution to increase 2012 contribution |

# Budget  2012

The budget is linked to the progress of the programme.  It assumes that 2012 will focus on pipeline development.  Beginning in 2013, it is assumed a large partner joins the project to expand the funding and technical assistance.

Sida will be the primary funder in the first two years.  Funding from AusAID was included in keeping with the verbal commitment to provide $500,000 for 2012. This agreement has not yet been finalized. The expenses assigned to AusAID are temporarily being funded by Sida, but will be reversed and attributed to AusAID upon receipt of funds.

A complete budget for the Programme can be found in Annex 2.

###### Table 11:  MM4P 2012 Budget

|  |  | 2012 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Description | Total | UNCDF | Sida | AusAID | Other |
| Output 1 | Scalable Projects |  |  |  |  |  |
| 61300 | Technical Specialist | 85,749 |  | 85,749 |  | - |
| 62300 | Recurring benefits | 40,216 |  | 40,216 |  | - |
| 63300 | Non-recurring benefits | 17,244 |  | 17,244 |  | - |
| 71600 | Relocation | 43,000 |  | 43,000 |  | - |
| 71200 | Consultants | 140,000 |  | 140,000 |  | - |
| 71600 | Travel - Team and Consultants | 80,000 |  |  | 80,000 | - |
| 72600 | Grants | 500,000 |  | 500,000 |  | - |
| 74500 | Misc. | 20,000 |  |  | 20,000 | - |
|  | Subtotal | 926,210 | - | 826,210 | 100,000 | - |
| Output 2 | Sector and Market Research |  |  |  |  |  |
| 71200 | Consultants | 320,000 |  | 150,000 |  | 170,000 |
| 71600 | Travel - Consultants | 60,000 |  |  | 37,000 | 23,000 |
| 74500 | Misc. | 20,000 |  |  | 20,000 | - |
|  | Subtotal | 400,000 | - | 150,000 | 57,000 | 193,000 |
| Output 3 | Policy, Advocacy and Coordination |  |  |  |  |  |
| 61300 | Senior Advisor | 133,843 |  | 133,843 |  | - |
| 62300 | Recurring benefits | 61,981 |  | 61,981 |  | - |
| 63300 | Non-recurring benefits | 24,815 |  | 24,815 |  | - |
| 71600 | Relocation | 43,000 |  | 43,000 |  | - |
| 61300 | UNCDF Field Staff | 70,000 |  | 70,000 |  | - |
| 74500 | Misc. | 20,000 |  |  | 20,000 | - |
|  | Subtotal | 353,639 | - | 333,639 | 20,000 | - |
| Output 4 | Learning, Monitoring and Evaluation |  |  |  |  |  |
| 61300 | Knowledge Manager | 97,500 |  |  |  | 97,500 |
| 71200 | Consultants - M&E | 25,000 |  | 25,000 |  | - |
| 71600 | Partner Travel | 50,000 |  |  | 50,000 | - |
| 72400 | Web/Printing/Publications | 125,000 |  |  | 25,000 | 100,000 |
| 74500 | Conferences. Misc | 60,000 |  |  | 60,000 | - |
|  | Subtotal | 357,500 | - | 25,000 | 135,000 | 197,500 |
| Output 5 | Programme Support |  |  |  |  |  |
| 61200 | Programme Assistant | 80,000 |  | 80,000 |  | - |
| 73100 | Rent, Taxes, Utilities | 19,000 | 19,000 |  |  | - |
| BA005 | Furniture | 7,000 | 7,000 |  |  | - |
| BA007 | IT Equipment | 10,000 | 10,000 |  |  | - |
| 72200 | IT & Communications | 16,000 | 16,000 |  |  | - |
| 74500 | Misc. | 28,000 | 8,000 |  | 20,000 | - |
| 75100 | FACADM | 366,269 |  | 303,863 | 35,070 | 27,335 |
|  | Subtotal | 526,269 | 60,000 | 383,863 | 55,070 | 27,335 |
|  | Total | 2,563,618 | 60,000 | 1,718,712 | 367,070 | 417,835 |

## Annex 1	Logical Framework

|  | Narrative | Indicators | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- |
| Development Objective | The financial security and opportunities of low-income households are improved through the use of BB and MFS |  |  | - UNCDF secures necessary funding - Access to appropriate financial services improves financial security, ceteris parabis - Improvement in HH situation can be verified through surveys |
| Immediate Objective | To increase the number low-income households, micro and small enterprises in LDCs that have on-going access to appropriate BB and MFS | - 4 million additional individuals and/or small and microenterprises in the LDCs gain access to BB or MFS - 2 million clients gain access to a “second generation” BB or MFS product or service - 1 million unbanked individuals gain access to financial services through BB and MFS By the end of 2017 | Partners report the increase in accounts, track unbanked new subscribers and new products adapted by existing customers from the inception of partner selection. | - Partners are able to track customer numbers and numbers are reliable, including the previously unbanked - Partners agree to report through 2017 - Increase is reasonably attributable to the MM4P’s activities |
| Output 1 | Scalable and replicable BB and MFS projects deliver appropriate financial services to low-income persons, small and microenterprises, including women and those in rural and remote areas | - 4 million additional new customers gain access to BB and MFS - 1.4 million BB and MFS customers become active; - 1 million unbanked individuals gain access to a financial services through BB and MFS - 2 bulk payments projects implemented Includes information disaggregated by sex and rural/urban. | - Partner quarterly and annual reports - Partner studies or evaluations - UNCDF and other’s research | - Fund is able to secure permission to fund partners in LDCs from central banks - MM4P is able to secure adequate funding for a pipeline of promising projects - MM4P is able to attract strong partners with requisite interest in inclusive finance - Partners implement proposed projects in good faith and reasonable on time - Needed regulatory changes for new products are adapted to suit project requirements - Partners are able to disaggregate reporting by rural areas and female customers |
| Output 2 | Market and customer research is created and shared to enable policymakers, providers and others to develop products, services and new approaches that move clients from awareness to regular use of BB and MFS | - 2 million customers gain access to “second generation” BB or MFS service - At least 4 client research studies conducted that benefit partners and stakeholders - At least 4 financial education/consumer awareness efforts included in projects - 75% of service providers commit to Smart Campaign or similar principles | - Quarterly reports - Copies of research reports and surveys - Reports on financial education/consumer awareness efforts - Copies of financial education/ consumer awareness materials | - Partner negotiations result in agreement for new product or service as well client awareness efforts - Regulators approve introduction of new products or services - Clients have or gain the ability to use new products or services - Consumer awareness or financial education results |
| Output 3 | Relevant policy makers, donors and other stakeholders are supported and empowered to make decisions and take coordinated action and allocate resources to enable partners to achieve their targets | - 100% of approved partners receive permission to implement MM4P project; - 2 policy or regulatory impediments or constraints to partners’ projects are reduced or removed removed or enabling regulations or policies are implemented; - 2 host country government’s or advocates supported to engage in consumer awareness and protection efforts; - At least 6 coordinated efforts with other funders, including research | - Secured “no objections” for partners’ projects. - Documented policy or regulatory changes - Tracking of “in-kind” contributions from other funders - Agendas or jointly sponsored events or research | - Policy makers and regulators are willing to make changes and/or take initiative - Political environment is stable to enable growing relationship with policy makers and regulators - Policy maker actions are reasonable attributed (partially or in full) to MM4P actions - CGAP, AFI and others are willing to expand partnership to new fund |
| Output 4 | Knowledge created and shared so that partners and other key stakeholders have access to global information, learning and learning events related to BB and MFS and MM4P lessons are document and learned | - 8 research products produced or include MM4P contributions - 8 partners supported to attend learning events or exchanges; - 6 workshops or learning events sponsored or co-sponsored by MM4P - 75% of UNCDF consultancies or sponsored events are rated as “good” or “very good” by partners | - Copies of knowledge products - Invitation and attendance lists of events - Presentations from events - Evaluation forms for events | - MM4P secures adequate funding to pursue Output 4 - UNCDF CTAs and UNDP support worskhops and learning events - Learning events sponsored or selected are relevant to stakeholders |
| Output 5 | The programme is nimble, efficient, transparent and well-respected that contributes to the corporate goals of UNCDF | - MM4P receives a “good” or better rating at mid-term evaluation - Funding increased by US$10 million; - UNCDF increased funding of US$10 million with MM4P support; | - Copies of knowledge products - Copies of funding agreements | - MM4P secures adequate funding - MM4P is able to identify and hire a strong team - MM4P is able to manage procurement in a timely manner to be responsive. - MM4P maintains support of UNCDF HQ and UNDP Brussels |

## Annex 2 Programme Budget

Mobile Banking from Concept to Reality.  http://www.cgap.org/p/site/c/template.rc/1.26.10806/

Those reported on the GSMA Mobile Money for the Unbaked Deployment Tracker  http://www.wirelessintelligence.com/mobile-money/

Mas and Radcliffe.  Scaling Mobile Money. Bill & Melinda Gates Foundation.  September 2010.

MM4P defines active as clients who have transacted in the past 90 days.

MicroSave. “Beyond Just Payments:  Technical Assistance, Investment, Knowledge and Training to Take M-banking to the next level. January 2012.

Mobile Banking from Concept to Reality.  http://www.cgap.org/p/site/c/template.rc/1.26.10806/

GSM Association.  Wireless Intelligence Data Base as of September 2010

Subsidiaries of banks and MNOs in smaller countries fail to get the investment resources or management buy-in for mobile financial services given the relatively high start-up costs.  This was evidenced in the Pacific where Vodafone was unable to make technical resources available for Vodafone Fiji.

Honohan, Patrick. “Cross Country Variation in Access to Financial Services.” Journal of Banking & Finance
Volume 32, Issue 11, November 2008, Pages 2493-2500.

M-Pesa is the product name of a mobile-phone based money transfer service for Vodafone in Kenya

MicroSave.

Mckay, Claudia and Mark Pickens.  Branchless Banking 2010: Who’s Served? At What Price? What’s Next? Focus Note No. 66. CGAP.  2010.

Mas and Radcliffe.  Scaling Mobile Money. Bill & Melinda Gates Foundation.  September 2010.

Those reported on the GSMA Mobile Money for the Unbaked Deployment Tracker  http://www.wirelessintelligence.com/mobile-money/

Five business case insights on mobile money. Presentation. CGAP. April 2011.

Mobile Banking from Concept to Reality.  http://www.cgap.org/p/site/c/template.rc/1.26.10806/.  Churn is the loss of customers who move to other providers, often for short-term incentives.

In February 2012 the CEO of Tigo Tanzania noted at an AFI Conference that “mobile money” has become the third core service of MNOs alongside voice and data when questioned by a relative small operator in a market should offer mobile money.

Vodafone Fiji; Digicel Fiji, Samoa, Tonga, Vanuatu; Nationwide Microbank; Post PNG SMK; Westpac InStore Banking.

A service other than person-to-person transfer, cash in and cash out.

Johnson, Susan.  What does the rapid uptake of mobile money in Kenya really mean for financial inclusion?  April, 2012.

Promotional activities carried out through mass media, such as television, radio, out-of-home, magazines, cinema and newspaper, are classed as "above the line" promotion. "Below the line" promotion refers to forms of non-media communication or advertising.

As noted in Portfolios of the Poor: How the World’s Poor Live on $2 a Day, it notes that clients often remain with money lenders despite cheaper options because it is convenient to do so. The “pain” of the high cost is not great enough to forgo the convenience.

In Fiji, few Social Welfare recipients opted to receive monthly payments via bank accounts despite the greater convenience. When forced to do so and trained on the use of electronic challenges, the response from beneficiaries was overwhelmingly positive.

With credit to Bankable Frontier Associates.

A GSMA survey showed that operators who have not properly trained agents experience lower returns initially and erosion of customer confidence.  (Driving Customer Usage for the Unbanked)

Banks will benefit from a relatively low cost of funds, whereas MNOs can benefit (if permitted by law) from the interest earned on the collective balances of clients)

The recent CGAP survey announces some interesting statistics on customer user rates with regards to branchless banking. Less than 30 per cent of registered users are active and if the activity rate per user drops to 10 per cent, the acquisition cost per customer rises to $50, and to $500 if the activity drops to one per cent. Most service providers count on a user being 50 per cent active, so the acquisition cost per customer is $10 and the bank remains profitable. It’s also believed there are six reasons for a customer to stop using the service – product features and pricing, marketing, the agent network, customer service, the user experience and the system/ network.

An API is specification (code or language) intended to be used as an interface by software components to communicate with each other.

For example, salary or loan disbursements may require lower pricing and alternative procedures to be cost effective and efficient.

As an example, Westpac Fiji’s need to fulfill the Fijian’s government tender to provide cashless distribution of social welfare benefits led to it building a branchless POS distribution network managed by agents.  M-Pesa Kenya was initially designed as a tool for MFI loan repayment.

As a new field, funders’ early experience is documented in “Emerging Lessons of Public Funders in Branchless Banking,” CGAP Focus Note 72.  July 2011.  UNCDF was a contributor to this focus note.

Estimated at 15% of total current voice customers.

Estimated at 25-30% of new customers.

Estimated at 35% of new customers.

Chart taken from “Guidelines and Tips, Monitoring and Evaluation Toolkit for Financial Education Initiatives.  December 2012.

This indicator may be difficult to track and verify, but will be negotiated with partners.

These market surveys will be coordinated with, or integrated into the sector diagnostic surveys that UNCDF will carry out with other stakeholders in preparing its next generation of sector development programmes.  As noted, this diagnostic tool is developed with Finmark Trust and CENFRI.

A service other than person to person money transfer.