FINAL EVALUATION REPORT - DFAT

Nabilan Phase III Mid-Term Review

December, 2024

This report has been prepared by Anna Trembath, Elsa Pinto, and Catherine Renshaw.

strategicdevelopment.com.au

EXECUTIVE SUMMARY

## Introduction

The Nabilan program is Australia’s flagship initiative addressing violence against women and children (VAWC) in Timor-Leste, delivered in partnership with implementing agency, The Asia Foundation (TAF). Commencing in 2014, Nabilan seeks to take a comprehensive and evidence-based approach to addressing VAWC. Representing a bilateral commitment to resource and implement core components of the ten-year Timor-Leste National Action Plan for Gender-Based Violence (NAP-GBV) 2022-2032, Nabilan’s official government partners are the Ministry of Social Solidarity and Inclusion (MSSI) and the Secretary of State for Equality and Inclusion (SEI).

Implementing partner TAF provides grants funding and technical support to 10 civil society organisation (CSO) partners, while working directly with MSSI and SEI. The program combines support for essential service delivery for women and children experiencing violence, community-based prevention initiatives aimed at transforming harmful gender norms, and systems change through policy influence and implementation, social work sector professionalisation, and feminist movement-building. Nabilan also regularly generates and disseminates evidence, supporting national research as well as undertaking programmatic evaluation.

Currently midway through Phase III (July 2022–June 2026), the program seeks to build on the successes of its previous phases. Phase III has seen a focus on maturing, testing and expanding the portfolio of prevention interventions while improving the quality of essential services to improve appropriateness, efficacy and safety for women and child clients. During Phase III, Nabilan has also increased its focus on violence against children (VAC) and has laid the groundwork for deepening its responsiveness to women with disabilities. The program is anticipated to be extended to a Phase IV (July 2026—June 2030).

Nabilan’s current End of Program Outcomes (EOPOs) are:

- EOPO1 (Services): Women and children experiencing violence are supported with consistently high-quality services

- EOPO2 (Prevention): Individuals, communities, and institutions act to prevent violence against women and children

Purpose, Scope and Approach of the Mid-Term Review

The purpose of this Mid-Term Review (MTR) is to assess the progress of Nabilan Phase III against its objectives and identify opportunities to enhance its impact, effectiveness, and sustainability. The review provides an evidence base to inform decisions on program adjustments for the remainder of Phase III and the design of Phase IV (2026–2030). The MTR also ensures accountability to DFAT, government stakeholders, program partners, and communities who stand to benefit from Nabilan.

A strategic investment-level evaluation, the MTR’s scope includes:

- Evaluating the relevance, coherence, effectiveness, efficiency, impact, and sustainability of the program.

- Assessing progress against the program’s Mid-Term and End-of-Program Outcomes and identifying key enablers and barriers.

- Offering actionable recommendations to strengthen the program in the short- and medium-term.

The MTR was undertaken from October to December 2024. The MTR team adopted a mixed-methods approach, and combined document analysis with 38 interviews, seven organisational roundtables, three workshops, and four site visits. Ethical considerations specific to VAWC research – in particular, do no harm – informed the evaluation design.

## Key findings

Overall

In Phase III, ten years into the life of the program, this Mid-Term Review (MTR) finds that Nabilan continues to represent an exceptional quality, high-value, critically relevant investment in ending violence against women and children (EVAWC) in Timor-Leste. ​The program is very significant to the EVAWC policy, programming and the funding ecosystem in Timor-Leste. In the current context, with Australian Aid funding comprising approximately 70 per cent of all funding to essential violence against women and girls (VAWC) services, Nabilan is in effect indispensable to sustaining national effort to address VAWC.

The holistic, comprehensive, integrated, ethical nature of the program is reflective of global best practice in the EVAWC field, including the careful introduction and adaptation of evidence-based prevention models to the local context. The prevention and services pillars of the program each comprise multiple interventions and strategies that are interconnected and effect change at levels from the individual to the societal. The program’s values-driven, ethical approach is consistent with good practice and has worked to propel program outcomes. Moreover, the momentum, optimism and joy reflected through the prevention pillar provide a useful balance to the difficult work of providing essential services to victim-survivors. In providing support to people presently experiencing violence as well as working on the root causes of gender-based violence, Nabilan represents a critical investment in women’s and children’s safety and in a future Timor-Leste with reduced VAWC and more equitable gender relations.

Evidence collected through the MTR process showed that in Phase III the Nabilan program has made significant achievements, including:

- Services pillar: Strengthened quality and accessibility of essential services, with more integrated and effective referral networks, adoption of standardised case management practices, and targeted professional skills development for social workers and counsellors.

- Prevention pillar: Community-level shifts in attitudes and norms have been documented and further evidenced through the MTR’s consultations, with initiatives like KOKOSA! and Ne’on Nain Mudansa (NeNaMu) (adaptations of globally-evidenced SASA! and Stepping Stones prevention models) driving community momentum for transformed gender relations.

The Nabilan program demonstrates strong alignment with Gender Equality, Disability and Social Inclusion (GEDSI) principles:

- Prevention and feminist leadership interventions target harmful gender norms and promote the rights, leadership and collective organising of women, including those experiencing intersectional forms of disadvantage and exclusion.

- The program has made good progress in disability inclusion through the success of the third phase of Bin Alin Hakbi’it Malu (BAHM), which included a cohort of women with disabilities. During the past two years, Nabilan has also undertaken disability inclusion reviews and consultations to improve access to appropriate service provision for women with disabilities in the second half of Phase III. Nevertheless, disability inclusion requires a concerted effort in the remainder of Phase III and into Phase IV.

- Efforts to engage groups experiencing other intersectional forms of social exclusion and disadvantage, including LGBTIQ+ individuals, are evident through the program’s partnership and intersectional feminist leadership models.

Relevance

In Phase III, Nabilan continues to respond effectively to the vast contextual need to sustain service infrastructure and support effective, quality responses to gender-based violence. Moreover, the program continues to diversify and strengthen pathways out of cycles of violence through its multifaceted prevention strategies, with this prevention work highly valued by both partners and communities. Extensive consultations during the Phase III design ensured that Nabilan’s core interventions reflect the priorities of beneficiaries, CSOs, and government stakeholders, and Nabilan’s priorities and partnership ways of working were found through the MTR to be deeply valued.

[The Nabilan team] see the whole situation in supporting victims, including staff self-care and stress management. This is very risky work, and we have trauma and stress but the system that Nabilan uses really helps us with this. Counselling training, Certificate III, routine training – it’s all really helped us; it’s excellent. I personally am really grateful because there are lots of things I didn’t understand and I’ve learned a great deal … They are like family. – Shelter senior leadership

The program also demonstrates responsiveness to changing needs, emerging evidence, openness to new ideas, and an interest in horizon-scanning to respond to contextual change. The key tenets of the Phase III program largely continue to have enduring relevance in the current context. Moving forward, the program will need to be attendant to the forthcoming introduction of high-speed internet from 2025 and its likely significant impact on the VAWC context.

Coherence

The Nabilan program has clear alignment to – and influence upon – Timor-Leste and Australian Government policy, plans and priorities, and effectively utilises key systems leverage points to amplify and accelerate change. By bridging the prevention and services pillars, and investing in initiatives that act as systems connectors, the program fosters a comprehensive approach to addressing VAWC. Learning forums, collaborative workshops, and regular partner engagements enhance internal program coherence and build local capability, with some room to improve a sense of shared purpose across Nabilan partners.

Effectiveness

Phase III implementation has occurred largely as planned, with a large body of work achieved. The program is achieving strong results, with evidence of progress against all six Mid-Term Outcomes. Notable successes include significant improvements in providers’ service and documentation quality and increased maturity of prevention efforts. Another key strength of the Phase III program has been a focus on program quality, evidence and learning, which in turn has supported partner ownership of key interventions and assisted the program to remain responsive to emerging learning and risks.

The investment modality with TAF as an NGO implementing agency funded through a DFAT grants mechanism is found to be highly effective, efficient and appropriate. TAF is a high-performing, ethical and well-regarded implementing partner. TAF’s partnership approach has supported systematic improvements in service outcomes, the effectiveness of prevention approaches, and contributed markedly to the development of local leadership to address VAWC. While the evidence collected through the MTR process attested to the strength of Nabilan’s partnership approach, opportunities to enhance Nabilan’s in-country profile and to increase coordination and collaboration in the EVAWC sector were identified.

Efficiency

Resources are being effectively utilised, with investments in core funding, technical assistance and accompaniment, and monitoring, evaluation and learning (MEL) yielding high returns in terms of transformative change. Program management practices are strong and effective, including between the Australian Embassy and TAF.

Impact

The program’s impact is evident at multiple levels, from individual beneficiaries to national systems. Prevention models like KOKOSA! are demonstrating promising results in terms of encouraging gender-transformative norms change in communities; notably in Phase III, supporting hard-to-achieve change regarding sexual decision-making and consent norms in intimate relationships.

This isn’t an easy change in mindset for men – in our patriarchal culture, women belong to them. [In KOKOSA!} we focus on the benefits and consequences and this moves them to change over time. For men, sexual consent is good because if they decide together, then there is good sexual connection and enjoyment together … It’s better to respect [women] and value them not just as sexual objects. For women, if there is sexual consent and they decide together, it gives them a sense of value and respect from men, and they can also feel love and romance together in their relationships. For us all, it shows us that we care about each other, including health and family planning – it creates harmonious relationships. – KOKOSA! partner staff

Strengthened service quality is improving outcomes for victim-survivors at points of crisis and into recovery while allowing service partners a sense of transparency and pride about their improved service response:

In the past, we just attended to the work, but we were not having the space to analyse our work, so this has really helped us. Nabilan saw the areas where our work wasn’t that good or could be improved, and then they helped us work together to improve. And they … walked with us constantly together and gave us lots of ideas. This gave us the spirit to work; previously, we just thought work, work, work, and we couldn’t necessarily see the results, but now we have a strong system. When we saw our improved results and progress, we were really surprised and happy. – Shelter senior leadership

In addition to intended impacts regarding prevention and services outcomes, the MTR determines that there is good evidence that the program is contributing to a positive impact at a systems level. Nabilan works with 10 diverse civil society organisational (CSO) partners and two government partners, with the program’s approach highly effective in nurturing local prevention and service response leadership, capabilities and sectoral integration. Further, the MTR process found strong evidence that Nabilan is a critical investor in sustaining the VAWC workforce through Phase III’s people-centred, trauma-responsive wellbeing and peer support initiatives.

Sustainability

Long-term investments in partner and community engagement, a trauma-responsive, person-centred model of support and care for the VAWC workforce, evidence generation, and policy alignment are strongly positioning Nabilan for sustained impact. Investments in professionalising social work and fostering feminist leadership also provide important foundations for enduring change at sectoral and civil society movement levels, while the Nabilan program’s approach to supporting government priorities enables influence of national policy. However, challenges related to financial sustainability and reliance on Australian Aid funding for essential VAWC services remain. Continued engagement by all actors will be needed to fully fund the NAP-GBV.

Conclusion

Midway through Phase III, the Nabilan Program continues to deliver excellent value, addressing urgent service needs while driving systemic and transformative change in Timor-Leste. It balances innovative prevention strategies with robust service delivery, ensuring both immediate and long-term impacts. The program has shown significant progress in shifting harmful gender norms that underpin VAWC, strengthening survivor support systems, and fostering collaborative partnerships with government, CSOs and local communities.

Looking forward, retaining and scaling the program in Phase IV, including increasing Australian investment, will be essential to consolidate these gains. Additional investments in strategies to address violence against children, disability and social inclusion, a systems orientation to the program design, and impact evaluation will enhance the program’s sustainability and effectiveness. Moreover, the program faces an opportunity to leverage its sound investment in prevention interventions and expertise by positioning as a prevention leader in Timor-Leste and the broader region, expanding its potential for influence and impact.

## Recommendations

Detailed recommendations are presented in the main body of the report; key recommendations domains are summarised here.

| # | Recommendation area |
| --- | --- |
| 1. | Retain the program and its core components for Phase IV: Given the program’s systemic impact and continued relevance, Nabilan should be retained and further strengthened in Phase IV (2026–2030). Maintaining the program’s focus on VAWC prevention and response will ensure ongoing alignment with Timor-Leste’s national priorities and Australia’s commitment to gender equality. |
| 2. | Increase the quantum of investment for Phase IV: To deepen and scale the program’s impact, additional resources will be required. The program has demonstrated the capacity to systematically build over time and use resources efficiently to successfully implement an ambitious agenda. Priority areas for increased investment include: - Expanding VAC-specific initiatives and strategies. - Supporting further service specialisation, including in terms of supporting child clients, women with disabilities, and clinical oversight and support - Positioning Nabilan as a national and regional prevention leader, through establishment of an independent prevention organisation that can incubate, scale up, quality assure, train, advise and evaluate, and facilitating Nabilan’s connection to key regional platforms. - Enhancing monitoring and evaluation frameworks and resources to track systemic impacts, undertake robust impact evaluation, and adapt to emerging challenges. - Supporting approaches to address new forms and patterns of violence and backlash to primary prevention gains that may emerge from a changing online environment. |
| 3. | Prioritise disability inclusion in service provision: Nabilan should determine a services disability inclusion strategy for 2025 to 2030, based on the analyses undertaken in early Phase III. Consideration of utilising BAHM alumni as lived experience advisors and a co-design approach to generating this strategy would be a useful way of leveraging the program’s existing disability inclusion strength. |
| 4. | Strengthen systems approaches: Develop an integrated Theory of Change which elucidates how Nabilan works as an integrated system of interventions and interconnections, identify broader systems change leverage points for future program focus, and anticipate challenges such as the impact of forthcoming high-speed internet. |
| 5. | Expand focus on VAC: Develop and implement a VAC-specific strategy. This should leverage insights from prevention initiatives to determine an appropriate prevention approach to VAC moving forward and the Phase III play therapy testing learning. Gaps in service provider capabilities and confidence to provide appropriate services to children should be prioritised. |
| 6. | Enhance collaboration and learning: Foster enhanced shared purpose amongst Nabilan partners, sustained GoTL engagement and increased external development partner awareness of Nabilan through structured approaches to coordination and engagement and cross-learning opportunities. |
| 7. | Amplify evidence and influence: Invest in impact evaluations, elevate program evidence and learning visibility through national, regional and global forums, and use a systems analysis to determine where best to utilise evidence to influence policies and practices. As a mature flagship initiative yielding high value, Nabilan would be well-placed to be linked to, and provide regional advice through, DFAT’s Southeast Asia Gender-Based Prevention Platform. |

ACRONYMS LIST

| Acronym | Full name |
| --- | --- |
| ALFeLa | Asisténsia Legál ba Feto no Labarik (Women and Children’s Legal Aid) |
| AFP | Australian Federal Police |
| BAHM | Bin Alin Hakbi’it Malu (Sisters Empowering Each Other) |
| CEF-UMS | Centro Esperansa Feto-Uma Mahon Salele (Centre for Women’s Hope-Safe Shelter) |
| CMAT | Case Management Assessment Tool |
| CODIVA | Coalition for Diversity and Action |
| CSO | Civil Society Organisation |
| DFAT | Australian Department of Foreign Affairs and Trade |
| DP | Development Partner |
| DRR | Disaster Risk Reduction |
| EQ | Evaluation Question |
| EOPO | End of Program Outcome |
| EQI | The Equality Institute |
| EVAWC | Ending Violence Against Women and Children |
| FGD | Focus Group Discussion |
| FOKUPERS | Forum Komunikasaun ba Feto Timor Loro Sa’e (Communication Forum for East Timorese Women) |
| FDMC | Fundasaun Media Development Centre (Media Foundations Development Centre) |
| GBV | Gender-Based Violence |
| GEDSI | Gender Equality, Disability and Social Inclusion |
| GoA | Government of Australia |
| GoTL | Government of Timor-Leste |
| HAMNASA | Hamutuk Nasaun Saudavél (Together for a Healthy Nation) |
| HDS | Haktanek Direitu Sidadaun |
| IDD | Investment Design Document |
| INGO | International Non-Governmental Organisation |
| JSMP | Judicial System Monitoring Program |
| KEQ | Key Evaluation Question |
| KII | Key Informant Interview |
| KOKOSA! | Komesa, Konxiénsia, Suporta, Asaun (Start, Awareness, Support, Action) |
| LGBTIQ+ | Lesbian, Gay, Bisexual, Transgender, Intersex, Questioning and other expanding and new parts of gender and sexual identities |
| M&E | Monitoring and Evaluation |
| MC | Managing Contractor |
| MEL | Monitoring, Evaluation and Learning |
| MSC | Most Significant Change |
| MSSI | Ministry of Social Solidarity and Inclusion (GoTL) |
| MTO | Mid-Term Outcome |
| MTR | Mid-Term Review |
| NeNaMu | Ne’on Nain ba Mudansa |
| NGO | Non-Governmental Organisation |
| ODA | Official Development Assistance |
| OECD-DAC | Organisation for Economic Co-operation and Development – Development Assistance Committee |
| OPD | Organisation for People with Disabilities |
| PHD | Partnership for Human Development (DFAT) |
| PMT | Program Management Team |
| PNTL | Polísia Nasionál Timór Lorosa’e/National Police of Timor-Leste |
| PRADET | Psychosocial Recovery and Development East Timor |
| SASA! | Start, Awareness, Support and Action |
| SVRI | Sexual Violence Research Initiative |
| SOGIESC | Sexual Orientation, Gender Identity and Expression, and Sex Characteristics |
| SOP | Standard Operating Procedures |
| SRHR | Sexual and Reproductive Health and Rights |
| SEI | Secretária de Estado da Igualdade (Secretary of State for Equality) |
| TAF | The Asia Foundation |
| TL | Team Leader |
| TOC | Theory of Change |
| TOR | Terms of Reference |
| VAC | Violence Against Children |
| VAW | Violence Against Women |
| VAWC | Violence Against Women and Children |
| WHO | World Health Organization |

CONTENTS

EXECUTIVE SUMMARY	i

Introduction	i

Key findings	ii

Conclusion	iv

Recommendations	v

ACRONYMS LIST	vi

CONTENTS	viii

1.	INTRODUCTION	1

1.1.	Purpose and Scope	1

1.2.	Methodology	2

1.3.	Limitations	2

2.	FINDINGS	3

2.1.	Relevance	3

2.2.	Coherence	8

2.3.	Effectiveness	12

2.4.	Efficiency	21

2.5.	Impact	22

2.6.	Sustainability and maximising value	29

3.	RECOMMENDATIONS	35

4.	PHASE IV OPTIONS	38

Annex 1 – Nabilan’s key program components and interventions	40

Annex 2 – Evaluation Plan	43

Annex 3 – Stakeholder Consultations	50

Annex 4 – Alignment of Nabilan’s Phase III design with global good practice principles	53

Annex 5 – Opportunities to strengthen Nabilan’s Theory of Change	54

Annex 6 – Achievement against intended implementation plan, Phase III	56

Annex 7 – Examples of Nabilan’s systems impact	60

# INTRODUCTION

Nabilan is DFAT’s flagship ending violence against women and children (EVAWC) program in Timor-Leste, implemented by The Asia Foundation (TAF). The program’s goal is that “women and children in Timor-Leste enjoy gender quality and live free from violence”. It represents a bilateral partnership to support the delivery of Timor-Leste's National Action Plan-Gender-Based Violence (NAP-GBV) 2022-2032. The value of DFAT’s investment in Phase III is AUD 20.5 million over four years.

Nabilan began in 2014 and is currently in its third phase (1 July 2022 to 30 June 2026). A fourth four-year phase is expected (July 2026 to July 2030). The Nabilan Phase III program has two pillars. First, it supports essential services for women and children experiencing violence. These services include legal aid, shelters, medical-forensic care, psychosocial support, and reintegration. Second, it seeks to prevent violence against women and children (VAWC) through various local programs and national strategies.

Nabilan’s current End of Program Outcomes (EOPOs) are:

- EOPO1 (Services): Women and children experiencing violence are supported with consistently high-quality services

- EOPO2 (Prevention): Individuals, communities, and institutions act to prevent violence against women and children

In Phase III, the Nabilan team administers grants to 10 national civil society organisation (CSO) partners:

Service and access to justice partners:

- Asisténsia Legál ba Feto no Labarik (ALFeLa)

- Centro Esperansa Feto-Uma Mahon Salele (CEF-UMS)

- Forum Komunikasaun ba Feto Timor Loro Sa’e (FOKUPERS)

- Psychosocial Recovery and Development Centre East Timor Fatin Hakmatek (PRADET Fatin Hakmatek)

Prevention partners:

- Coalition for Diversity and Action (CODIVA)

- Estrela+

- Fundasaun Media Development Centre (FMDC)

- Haktanek Direitu Sidadaun (HDS)

- Hamutuk Nasaun Saudavél (HAMNASA)

- Judicial System Monitoring Program (JSMP)

- PRADET

Nabilan also provides technical assistance and accompaniment to these partners, activists, and the Government of Timor-Leste (especially the Ministry for Social Solidarity and Inclusion-MSSI and Secretary of State for Equality-SEI).

Additionally, the program uses various other strategies and activities. These include research, generating and sharing evidence, policy influence, social worker professionalisation, and developing feminist leadership capacities and networks. See Annex 1: Nabilan program components and interventions for further information.

While Phase III of Nabilan largely continues and seeks to mature and extend the Phase II program, it increases its focus on violence against children (VAC) through positive parenting programs and trialling play-based therapy in services. This phase also focuses on disability inclusion, the transition of the program to national leadership, program quality, and amplifying program learning.

## Purpose and Scope

The purpose and focus of this MTR are based on the original Terms of References (TORs) and the result of several initial briefing conversations with the DFAT Gender Equality, Disability and Social Inclusion team at the Australian Embassy in Timor-Leste and the Nabilan team at TAF. The MTR of Nabilan Phase III seeks to understand the program’s performance and inform planning.

The purpose of the evaluation is summative in that it looks back to examine program relevance, coherence, effectiveness, impact and sustainability for the first half of the Phase III program (1 July 2022 to 30 June 2024). It is also formative, looking ahead and seeking to make timely, useful and feasible recommendations for improvements, adjustments and innovations for the remainder of Phase III and the expected Phase IV (July 2026 to July 2030).

This MTR is an investment-level evaluation. As such, the scope and focus are strategic and overarching rather than providing a comprehensive review of any of Nabilan’s components. Given ethical risks, the direct participation of service clients and children was out of the scope.

## Methodology

The MTR adopted a mixed-methods approach and was designed to be attentive to ethical considerations specific to VAWC research. The Key Evaluation Questions (KEQs) presented in Annex 2 were refined with feedback from DFAT and the Nabilan team during the evaluation planning process in October 2024. KEQs are organised by OECD-DAC evaluation criteria. An adjustment was made to the Sustainability criteria to centre future-oriented considerations more explicitly, consistent with the purpose of the MTR to support program adjustments and design planning.

As set out in the Evaluation Plan, the team led a primarily qualitative approach, with some limited quantitative analysis. The MTR team based its analysis on document review (provided with over 50 documents), 38 key informant interviews (KIIs), seven roundtable discussions with the Nabilan team and partners, a partner workshop, two workshops with community participants of prevention programming, site visits to four program locations, and an online survey disseminated to Timorese CSO partners (with 14 responses representing eight of 10 partners). Data collection was mainly in Tetum language, with some limited translation. Data was analysed according to the MTR Evidence Table (coded and triangulated), which brought together the evidence and their sources.

The TOR specified short case studies to illustrate and evidence findings. Based on a template provided by the MTR team, the Nabilan team identified two case studies for further validation and investigation. These case studies – focused on improved essential VAWC service quality, and community-level attitudinal, norms and practice change with regard to sexual decision-making and consent – may be found in Section 2.5: Impact.

An Aide Memoire slide deck summarised emerging findings and recommendations. This was presented in two sessions, followed by discussion and feedback for validation: to DFAT Dili and Canberra members, and to the TAF executive and the Nabilan leadership team.

See Annex 2: Evaluation Plan for further details.

## Limitations

No major limitations were experienced in terms of delivery against the ToR and evaluation plan. All prioritised stakeholders were engaged, the MTR team were provided with comprehensive access to existing program documentation, and communication was open and supportive from all stakeholders. The primary limitation to note is that Nabilan is a complex program comprising several interventions, and this is a relatively rapid investment-level evaluation. As such, this evaluation focuses on strategic insights rather than deeper assessments of individual interventions.

# FINDINGS

In this section, the MTR team discusses the review findings according to the evaluation criteria and KEQs. Related recommendations may be found at Section 3: Recommendations.

## Relevance

This set of KEQs seeks to answer the question: Is the intervention doing the right things?

### KEQ1. To what extent does the design of Nabilan Phase III respond to what is needed and valued by its beneficiaries and partners in the current context?

# Findings at a glance:

- In Phase III, Nabilan meets the urgent need to support essential VAWC service infrastructure while diversifying and strengthening prevention pathways.

- Partners deeply value the program’s focus areas and partnership approaches.

- The program is responsive to changing needs, new ideas and emerging evidence.

- Nabilan is better known and valued by its direct stakeholders than by external stakeholders working in the Timor-Leste EVAWC sector.

- The Phase III program’s key tenets still matter today. The program should consolidate its approach to VAC, especially in essential services, and prepare to respond to the likely impacts of high-speed internet.

Strength of evidence: Excellent.

The Phase II context was marked by the significant disruptions of COVID-19 and floods affecting Dili from April 2021. Nonetheless, Nabilan achieved significant progress against its expected outcomes and demonstrated an impressive responsiveness to this unanticipated context. With the external context settling, Phase III represented a welcome opportunity to “get back to core business” for TAF and DFAT. The Phase III design is responsive to the Phase II MTR, other intervention-specific evaluation and learning, and focused reviews of the program's legal service and justice sector support. Thorough consultation with approximately 40 organisations and programs also informed the design. These consultations confirmed a continuation of the core service support and prevention work, with some expansion in prevention initiatives and an increased focus on addressing VAC and program quality. Additionally, Nabilan undertook targeted consultations with a few organisations for people with disabilities (OPDs). These resulted in an identified need to focus on specific forms and impacts of violence experienced by women with disabilities and the barriers to their service access.

The MTR team finds that the Nabilan program and Australia’s long-term funding are vital to sustaining and improving the quality of and access to essential service provision for victim-survivors. Nabilan’s essential services support occurs in a context where current prevalence rates are unknown but unlikely to have significantly reduced since the findings of Nabilan’s baseline National Prevalence Survey in 2015, wherein three in five ever-partnered women between 15 and 49 had experienced intimate partner violence in their lifetimes. Hopes that the Government of Timor-Leste (GoTL) would increase its budget allocation to service providers, even modestly, had not materialised during Phase II. In a country where the EVAWC service infrastructure is mostly CSO-run (except two state-managed shelters), TAF modelling suggests that Australian Aid funding via Nabilan currently supports up to 70 per cent of violence-responsive essential services in-country. Moreover, Nabilan support occurs in a context where there are limited other donor funding options; no other donor has provided core funding, and these alternative funding sources have been reduced with the closure of two major UN-led shorter-term initiatives in 2023-24. Further, the MTR did not find any indication of a confirmed GoTL commitment to increased budget allocation for essential services in the short- to medium-term. The GoTL’s overall budget may also soon reach a ‘fiscal cliff’ as oil revenue reduces.

While other programs (particularly UN-led) have undertaken initiatives under the umbrella of primary prevention, the MTR team finds that Nabilan occupies an important and unique position as a primary prevention thought leader. Nabilan has brought exciting global models to Timor-Leste for the first time and worked carefully with local partners to adapt these to be contextually relevant to the context, with the guidance of global experts. Prevention partners and community members engaged through the MTR process expressed high commitment to and enthusiasm for these intervention models.

Phase III has seen Nabilan expand the EVAWC ecosystem through clever cross-sectoral partnerships with organisations that saw the potential and relevance of expanding their skills to support VAWC prevention. During the design process, the program team mapped potential new collaboration opportunities with organisations outside the EVAWC sector, particularly in preventing VAC through positive parenting and a transition in the Ne’on Nain ba Mudansa (NeNaMu) partnership. This mapping paved the way for the Phase III grants process, inviting potential new partners to proffer and articulate their ideas about adding value to Nabilan. As an organisation that had historically worked with incarcerated people, an HDS staff member expressed this process of establishing a mutually valuable collaboration that resulted in a new iteration of the positive parenting intervention:

Nabilan opened proposals and we applied; before that, we were talking with them about whether we could work together. We went to them because … we saw their work in communities and saw there was a need to bring this prevention of violence against women and children to prisons. – HDS senior staff member

In another example, Estrela+, a national membership association of people living with HIV, was supported to become the new partner for the NeNaMu initiative (an adaptation of Stepping Stones and Stepping Stones Plus):

We saw the link – the relevance and importance – between prevention of violence against women and children and strengthening community and youth knowledge and capacity about reproductive health and transmissible diseases. We saw that Stepping Stones had a real potential in supporting and strengthening our approach … In terms of Nabilan, we saw that there was really good training and communication which would support a strong partnership, and realised there was a lot of usefulness in supporting our self-development, self-care and networks. – Estrela+ senior staff member

The universally strong reception of grantee partners to the Nabilan grants program during Phase III is good evidence that the program’s design priorities, as well as its partnership approach, is highly responsive to what is needed and valued by partners and their beneficiaries. DFAT’s long-term funding, the provision of core organisational funding and capacity support, the TAF program team’s partnership model, and the approach to adapting global prevention models, are deeply valued and recognised unique program ingredients. Partnership is further explored in Section 2.3: Effectiveness.

79% of MTR Partner Survey respondents reported that the Nabilan program responds to most of their organisational needs. The remaining 21% said that the Nabilan program is responsive to all their needs.

In several instances, service partners identified additional needs that they recommended the program respond to moving forward, particularly regarding VAC. They welcomed more capacity-building in developmentally appropriate, trauma-responsive engagement of children.

With the children who come here, we do our best. We have needed to adapt our behaviour to young children to support them to feel more comfortable – we need to attend training to support us. We need to give children a lot of time and allow time for play and other things … I just do it with my prior knowledge but I don’t know many things so it will be good to attend training. – Counsellor, PRADET in Suai

As explored further in Section 2.3: Effectiveness, in Phase III, Nabilan has sought to respond to this known need for client-appropriate service engagement by testing a Play-Based Therapy approach, which is currently being recalibrated. FOKUPERS expressed an interest in protecting the rented Dili children's shelter premises from being sold (through acquisition), and other partners indicated a desire for separate child-friendly areas and the availability of toys and art supplies. Certain partners were very concerned about children experiencing incest returning to high-risk circumstances and wished for more strategic guidance as to how to make appropriate decisions and work with others to support those children while the perpetrator is not incarcerated. Some service partners were also interested in longer-term support for victim-survivors, especially once they return to communities, to help them escape the trap of dependency on abusive partners.

Government partners and stakeholders also endorsed the Nabilan program, the approach of TAF and the funding and support of the GoA for its relevance to context. Immediate government stakeholders – SEI and MSSI – spoke of:

- the influence upon and alignment with the National Action Plan-Gender-Based Violence (NAP-GBV) 2022-2032,

- the support for formulating, training and implementation of the Standard Operating Procedures (SOP) for case management of GBV and child protection presentations (case management expectations of service providers and members of the referral networks), and

- the importance of Nabilan’s evidence generation (such as through the National Prevalence Survey) in informing and supporting the justification of government priorities.

UN development partners (DPs), stakeholders who are external to the Nabilan program and engaged in their own EVAWC initiatives, held mixed opinions of Nabilan’s relevance to the Timor-Leste context. Responses by these partners suggested some gaps in their knowledge of the program, particularly in terms of prevention. While they expressed positive sentiments, some DPs criticised Nabilan’s prevention work as too small-scale and lacking in government institutional integration, as well as a sense that collaborative mechanisms could be improved to ensure consultation and reduce duplication or conflict on specific initiatives. Various examples of improved collaboration and coordination with Nabilan during Phase III were given, including work on a possible new referral hotline. All saw the potential for stronger cooperation and working relationships with Nabilan and DFAT as the donor.

The MTR team found strong evidence of effective mechanisms for regularly reviewing and adjusting program priorities. Nabilan Phase III is not a ‘set and forget’ design but responsive with room for emergent strategy. Partners attested to these mechanisms and to the Nabilan team’s responsiveness, which include: very regular planned and ad hoc communication with partners and with DFAT, partners assigned a key contact at TAF that they feel comfortable contacting, annual collaborative work planning processes with government and grantee partners, reporting formats with partners which allow partners to express new ideas or needs, communities of practice, learning and reflection workshops, annual partner retreats, and monitoring, evaluation and learning practices which Nabilan uses as genuine opportunities to consider, reflect, revise and iterate. Moreover, partners emphasised the TAF team's partnership approach's flexible, open, collaborative and respectful nature, allowing partners a sense of closeness and safety to raise any issues, needs or new ideas.

The MTR team finds that the Nabilan Phase III program has enduring relevance for the current context. Core tenets of the program should be maintained across Phase III and into Phase IV. The program team itself has already identified the need to deepen, extend or consolidate certain areas that also surfaced through the MTR process – including disability inclusion, strengthening service partner capacity on VAC, supporting partners to undertake their own risk plans, carefully planning to exit certain communities and enter others as prevention interventions reach a natural conclusion – have already been identified in 2025-26 Phase III plans. The most significant contextual shift on the horizon, other than a reduced budget capacity of the GoTL, is the introduction of high-speed internet, likely in 2025. The likely impacts on VAWC prevalence and patterns were raised as a real concern, particularly by the program team itself and Australian Aid partners, including the Australian Federal Police (AFP). DFAT and the Nabilan team are attendant to these forthcoming challenges. These needs and opportunities are further explored in Section 2.6: Sustainability and maximising future value.

### KEQ2. To what extent does the design of Nabilan Phase III incorporate a well-defined program theory and align with international best practice and evidence for preventing and responding to violence against women and children?

Findings at a glance:

- The Phase III Nabilan program demonstrates strong evidence alignment.

- The program is globally connected to evidence and practice expertise networks, allowing for ethical, informed contextualising of global evidence of ‘what works’ to prevent VAW.

- Phase III has a credible theory of change, with room to strengthen systems change analysis, identification of change mechanisms, and VAC change strategies.

- While gains have been made in sharing program evidence, further opportunities exist.

- While the program is strongly evidence-generating, important opportunities to extend the programmatic evidence base are apparent and require more resources.

Strength of evidence: Excellent.

In Phase III, the key strengths of the Nabilan program are its evidence alignment and generation. The Nabilan Phase III design is well-aligned with key tenets of the global evidence base about what works to respond to and prevent violence against women and children. This includes incorporating a range of interventions pitched at different levels of the socioecological framework, holistic in incorporating and connecting response and prevention efforts, addressing various forms and intersectional experiences of violence, prioritising feminist ethics and a 'do not harm' principle, being trauma-responsive in how it works with beneficiaries and VAWC workforce, and supporting an intersectional feminist and decolonising leadership model. More detail on how the Phase III program aligns with global good practice may be found at Annex 4.

The Nabilan program actively seeks out and is connected with global evidence about what works and what is promising to respond to and prevent VAWC and has made conscious, strategic decisions to introduce and carefully adapt interventions with proven effectiveness. For example, KOKOSA! is an adaptation of SASA! and SASA Together! (Uganda); NeNaMu adapts Stepping Stones and Stepping Stones Plus (Uganda); and the positive parenting programs adapt Bandebereho (Rwanda). In the cases of KOKOSA! and NeNaMu, the Nabilan team and partners have been trained and accompanied by Uganda-based experts in these models as they adapt and test to ensure fidelity, quality and support with strategic practice advice. These global technical advisors spoke very highly of the considered, ethical, strategic approach of the Nabilan program to introducing, adapting and sustaining these interventions in the Timor-Leste context.

Nabilan is one of the partners that bring me peace and make me enjoy my work as a Technical Advisor. They interact with the tools and ask technical questions … We are proud of Nabilan program and the work that they do with KOKOSA!. They have the heart for the program and communities and are really grounded in feminist principles; they observe ethical priorities for community engagement and prevention of violence against women; they do no harm … Nabilan has really tried to observe and implement SASA! and focused on fidelity. – Raising Voices SASA! and SASA! Together Technical Advisor

Nabilan’s grantee partners who implement these initiatives in communities and with community beneficiaries also held the evidence-based approach to adaptation and progression through these interventions in very high regard. HDS spoke of adapting, testing and learning from the prison-based positive parenting model drawn from Bandebereho:

Nabilan’s learning approach was different and great. First, we did a year of research with ex-prisoners, and then we made a manual for prisoners that was really relevant to their needs. What did we learn? Even though we had a long history of working with prisoners, we realised that there were a lot of things they hadn’t said to us, a lot of needs we hadn’t heard… With Nabilan, we then adapted a curriculum to the prison context and Timor context. Then we did the pilot program... and then an evaluation and the participants said they wanted to go deeper on certain sessions, so we have extended the pilot. – HDS senior manager

Beyond individual evidence-based and evidence-generating interventions, a strong, detailed design document underpins the whole Phase III program. A thoughtful Monitoring, Evaluation and Learning (MEL) plan accompanies the design and includes a credible theory of change (ToC) organised against the Prevention and Services pillars (and their EOPOs and Mid-Term Outcomes -MTOs). Specific key interventions such as KOKOSA!, NeNaMu, BAHM and Aman ba Mudansa (positive parenting) also have their own nested ToCs, which reflects good practice in relation to considering Nabilan as essentially a systems-level program comprising a cluster of interventions.

However, the MTR team finds room to strengthen the program’s overarching ToC. The ToC could:

- include a stronger systems orientation that demonstrates the connections between initiatives and interventions, places Nabilan within a broader ecosystem responding to and perpetuating VAWC, and supports identifying leverage points Nabilan could target to propel systems-level change;

- more explicitly articulate the program theories and evidence and the specific mechanisms of change underpinning Nabilan’s design;

- more clearly articulate how and in which ways the program prevents and responds to VAW and especially to VAC;

- be presented in a more visually engaging, narrative form that would, for example, be more accessible and compelling for partners;

- demonstrate how individual interventions and their ToCs 'nest' into the broader program's ToC.

These opportunities to strengthen Nabilan’s ToC are further detailed at Annex 5.

During Phase III, a significant amount of well-considered, high-quality, well-coordinated and collaborative MEL activity has occurred. This includes:

- Ongoing routine data collection and regular analysis associated with training and program intervention activities (including observations of training and program facilitation carried out by partners)

- Partner learning and reflection workshops

- The Case Management Assessment Tool (CMAT) process conducted in 2022 and 2023 (further elaborated in Section 2.5: Impact)

- BAHM Phases 2 (2023) and 3 (2024) evaluations

- KOKOSA!, NeNaMu and positive parenting process evaluations and end-of-phase assessments, including surveys, interviews, and focus group discussion data collection often drawn from global guidelines.

These activities – and the evident comfort with and use of MEL evidence by the Nabilan team and its partners to learn, improve and remain curious – are noteworthy achievements. The Nabilan’s dedicated MEL resources are lean, and the program takes an approach of MEL being everyone's responsibility. TAF staff and partners alike spoke to this shared learning and evidence-generation culture.

Moreover, in alignment with the Phase III design, TAF has supported a focus on ‘evidence amplification’ during Phase III; that is, the development of products to share and engagement in dissemination and influence opportunities. This has included:

- Development of Learning Briefs: ‘Gender-Transformative Positive Parenting in Timor-Leste’, ‘Strengthening Feminist Movements through Investments in Leadership, Solidarity, and Self-Care’, and ‘NeNaMu: Addressing Intimate Partner Violence through Community Engagement in Timor-Leste’

- Engagement in the Sexual Violence Research Initiative (SVRI) Forums of 2022 and 2024 to showcase NeNaMu and BAHM

The MTR team found that leveraging these products, particularly within the Timor-Leste context, to raise awareness of Nabilan and share evidence-based lessons has been somewhat inhibited by resourcing.

With further resourcing, there are opportunities for further strengthening, sharing and generating influence from Nabilan’s program evidence. These opportunities are further discussed in Section 2.6: Sustainability and maximising future value.

## Coherence

These KEQs seek to answer the question: How well does the intervention fit?

### KEQ3. How well do the various components, projects and actors in Phase III complement and support each other to achieve the end of program outcomes? (internal coherence)

Findings at a glance:

- Strong cross-partner collaboration, communication, coordination and learning practices are evident in the current program and are valued by immediate program stakeholders.

- These practices and the Certificate III and BAHM programs, including participation from different organisations, connect partners across the Services and Prevention pillars. However, further opportunity exists to support partners’ sense of shared program mission.

- Within the Services pillar, the program has made important contributions to strengthen the GBV referral network, including through relationship-building and role clarity.

- Nabilan invests in important ‘nodes of interaction’ (such as the Certificate III, BAHM, and training) that connect different program initiatives and extend into the broader EVAWC, social services and progressive civil society ecosystems.

Strength of evidence: Good.

Nabilan’s Phase III program directly supports 10 grantee partners and two primary government partners and engages with multiple other stakeholders, including other Australian Aid programs, other international donors and DPs, and state institutions such as PNTL. Grantee partners are based in six locations across Timor-Leste. The program also comprised a number of key interventions – support for essential services, legal and justice sector support, media support, the Certificate III in Social Work, KOKOSA!, NeNaMu, BAHM, two positive parenting projects, and LGBTIQ+ rights, SOGIESC awareness and violence prevention – each of which are significant investments requiring focus and expertise in their own right. In this sense, Nabilan can be considered a cluster of programs or a systems change investment rather than a traditional program.

Given the multi-component, multi-partner nature of the Nabilan Phase III program, the question becomes: to what extent do these investments coalesce as an internally coherent program driven by a shared vision and a connected network of partners and professionals, rather than separate streams of activity? The MTR team finds that there is strong internal program coherence. Three key strategies were identified as successfully supporting internal program coherence, each of which should be leveraged as strengths moving forward.

To the question, ‘has working with Nabilan helped your organisation’s professional connections with other organisations (for example, the referral network)?’, 100% of Nabilan MTR partner survey respondents answered, ‘yes, very much’.

First, the Nabilan team deliberately creates fora and regular opportunities for cross-partner collaboration and shared learning. These include peer support networks, retreats, and learning forums. Second, the Nabilan program is making a significant contribution to supporting the formal GBV case management referral system. In occupying a space of directly working with essential services CSO partners, legal support and justice system monitoring CSO partners, and the relevant government institution responsible for standards and formal oversight of the referral network, Nabilan is well-placed to support a more integrated referral system. The effectiveness of this strategic positioning (unique in-country) has been reinforced through the program's ways of working with the referral network, particularly supporting relational connections with one other and role clarity in understanding and operationalising the SOP.

Upon municipal visits to Suai and Baucau service sites, the MTR team heard from partners that friendly, mutually supportive collaboration, referral and information-sharing ease and victim-survivor-centred support between partners and with other referral systems members had improved markedly due to Nabilan’s support.

The Nabilan team also have routine meetings with all the partners, bringing us together and supporting each other to share experiences and get to know each other and our different work and experiences. With the referral network, now we understand each other much better and work together more closely. We have good, open, active, honest communication. They [Nabilan] encourage us to share our feelings and our concerns together. – CEF-UMS Senior Leadership

Third, and less obviously in the program’s design, Nabilan has invested in critical ‘nodes of interaction’ that create flows and connections between the parts of the internal Nabilan program system (as well as into the broader EVAWC and social services ecosystem). BAHM and the Certificate III of Social Work, as well as regular training and fora, act as these nodes of interaction that drive a shared sense of the program that is greater than the sums of its parts and support network-building, organic relationships and self-organising, all of which is also critical for long-term sustainability of the program’s outcomes. A common theme of interviews with key partner stakeholders was how their or their colleague’s engagement with these initiatives – even prior to becoming a formal Nabilan partner – had drawn them into connection with the program, piqued their interest in furthering their learning and skills development with regard to feminist leadership, social services and/or working in the field of EVAWC, and importantly created networks and communities of practices (some of which continued to live through for example WhatsApp channels) outside of formal Nabilan management.

Importantly too, these program connector initiatives support continuous reinforcement of a coherent and understood Nabilan approach to EVAWC: ethical, victim-survivor-centred practice; self-care, stress management, awareness of trauma and professional boundaries to support professionals’ sustained engagement in this sector; empathetic connection to one another as individuals and organisations working with a shared mission in a complex field; and a sense of agency, empowerment and leadership. That is, Nabilan is changing the collective mindset or norms shared by those working in the ecosystem through reinforcing strategies.

They see the whole situation in supporting victims, including staff self-care and stress management. This is very risky work and we have trauma and stress but the system that Nabilan uses really helps us with this. Counselling training, Certificate III, the routine training – it’s all really helped us; it’s excellent. I personally am really grateful because there are lots of things I didn’t understand and I’ve learned a great deal. – CEF-UMS Suai senior leadership

While the MTR team found that there is strong internal program coherence, some gaps and opportunities to further strengthen this integration were evident. While partners working in the prevention and services pillars are regularly connected and have an understanding of each other's work (and in one instance – PRADET – do both), it was apparent too that some level of siloing and tension exists between these pillars and between organisations. Noting that the MTR team's engagements with partners were confined to the MTR process and were therefore limited, these subtle tensions surfaced in several instances across the data collection process. For example, in a partner workshop, organisational representatives struggled to place their work against the separate pillars and the respective EOPOs. One participant challenged prevention partners to evidence their claims to community-level change (to which those partners were able to respond well based on MEL evidence collected with the Nabilan team). Moreover, a sense of ‘newcomers and the old guard’ was evident, with some prevention partners painstakingly recognising that they are less experienced players in the EVAWC and Nabilan space. In two interviews, long-term partners expressed a sense of disappointment or disgruntlement that they were not included as formal partners within the community prevention stream of work, conveying the implicit message that they had been working in the space for longer than some of the newer prevention partners. Finally, a dynamic that was less obvious but worth being attendant to is a possible tension between the hard, long-term graft of organisations supporting victim-survivors and advocating for change in state response, with the sense of joy, optimism, creativity and generativity that is apparent in the newer prevention space. This is notwithstanding the labour and challenging aspects of the prevention work, including vicarious trauma.

These small gaps and tensions suggest some need and opportunity to revisit instilling a sense of shared purpose in the second half of Phase III and into Phase IV. In some senses, the program framing of separate pillars may be detrimental to instilling a greater sense of shared purpose across prevention and services partners. The MTR team recommends that a systems mapping and framing of the program – including identifying current and potential interactions between partners and interventions – may be helpful for further cohering the Nabilan program and network. Practising sharing change or impact stories, as well as histories of work in the EVAWC space (even predating Nabilan), may also be helpful. Finally, it is recommended that the Nabilan team consider whether and how to involve certain services and advocacy partners in the prevention stream. The MTR team understands that Nabilan is actively considering this in the instance of one partner.

Further, the two positive parenting partners expressed that they had not yet had the opportunity to directly share with and learn from each other’s work in a forum focused on positive parenting. Both partners expressed a desire to do so while citing the barrier of HAMNASA not being authorised to observe HDS’s work in prison. The lack of shared learning is likely to more accurately reflect these initiatives' relative nascency, given that direct program observation is not the only available peer learning strategy. This gap can be easily remedied and should be given reasonably immediate attention.

The MTR team also noted that two geographic factors are mediating internal program coherence – the extent of direct Nabilan contact with municipality-based partner staff and the extent to which those partner staff are engaged by their Dili-based headquarter offices in the Nabilan program and supported by their own organisations. The MTR team noted inconsistency as to the extent to which municipal partner offices are involved in Nabilan and feel supported by their own headquarter organisations. In one notable organisational instance, municipality-based staff (in two sites) had minimal knowledge of the Nabilan program outside of isolated training opportunities, saying that their Dili superiors would engage with Nabilan.

### KEQ4. To what extent is Nabilan Phase III designed to effectively contribute to systems change for ending violence against women and children in Timor-Leste? (external coherence)

Findings at a glance:

- The Phase III program effectively utilises key systems leverage points to amplify and accelerate change – policies, official procedures, network support, initiatives which bring people together and shift mindsets.

- Phases III and IV would benefit from stronger systems analysis in order to further surface and strategically plan for systems effects and be prepared to respond to emergent shifts in the system.

Strength of evidence: Excellent.

In this report, a 'system' refers to a set of interdependent components or parts, with each component affecting the whole. A system is more than the sum of the parts – the interaction between the parts reinforces, disrupts, grows, accelerates, slows, or transforms. In relation to VAWC in Timor-Leste, systems may be considered in terms of what drives and perpetuates VAWC (including underlying norms and social conditions; factors within Timor-Leste and also global influences), and also the multiple actors, factors and interventions that work to disrupt, respond to and prevent VAWC. Importantly, in this conceptualisation, systems change is not synonymous with government/state institutional change (though, at points, systems change may incur shifts in formal institutions).

Systems thinkers have created various models for conceptualising types and likely impacts of certain systems leverage points. Muir posits a simple model of systems levers consisting of:

- Technical work: changes to policies, programs, practices, legislation, regulation, etc., including research to understand what works and what does not and for who and to test alternative models

- Where the resources go: changes to where funding flows, who makes the decisions, how resources get used (time, talent and treasure) and how the work gets done (individually, in coordination with others, or through genuine collaboration)

- Hearts and minds: understanding, galvanising and changing attitudes, beliefs, values and fears, who has something to gain, who has something to fear and who has something to lose.

Upon evaluative examination, the MTR team concludes that the Nabilan network of direct partners and stakeholders may be considered a sub-system within a broader EVAWC ecosystem of actors, programs, policies, activism and advocacy.

The Nabilan design includes numerous systems change levers, including:

| Design element | Systems change leverage point |
| --- | --- |
| Alignment with GoTL policies, strategies and action plan – in particular, the NAP-GBV 2022-2032 and the SOP for the GBV case management referral network | Technical work, with potential for where the resources go Changing the goals of the system |
| Certificate III Social Work; BAHM | Hearts and minds Self-organising systems structures |
| KOKOSA!, NeNaMu, positive parenting, play therapy, BAHM | Technical work Hearts and minds Self-organising systems structures |
| Sustaining essential service provision | Where resources go |

Figure 1: Nabilan’s systems leverage points

The question under examination here is, however, a consideration of the extent to which the design enables Nabilan to have a systems change effect. The MTR team finds that while key elements of systems change enablers are present in both the design and the Phase III implementation, suggestive of careful, clever strategising, systems change analysis and strategising are not made particularly explicit in the program design. This should be considered and addressed in the next phase’s design.

## Effectiveness

This set of KEQs seeks to answer the question: Is the intervention achieving its objectives?

### KEQ5. Two years into Phase III, to what extent is the program being implemented as planned, with the expected quality, and is it meeting its objectives?

Findings at a glance:

- Phase III implementation has occurred largely as planned.

- A small number of unexpected implementation challenges have occurred, some outside of direct program control. However, the program has proactively adjusted and strategised pathways through any issues.

- The intended focus on new strategies to address VAC has had mixed results.

- MTOs are mainly on track, across services and prevention pillars.

- Strong MEL practices and systems support the program's progress.

- A focus on quality programming is a key strength of Phase III.

Strength of evidence: Excellent.

Through reviewing the program design, implementation plans, program reports to DFAT, and interviewing key stakeholders, the MTR team concludes that implementation of the first half of Phase III has mainly occurred as planned, with most intended activities in the 1 July 2022—30 June 2024 period having taken place. The MTR has rated the level of achievement against each MTO-aligned activity area; in each area, Nabilan’s progress was assessed as either ‘good’ or ‘excellent’ (see Annex 6 for further detail). This represents the fulfilment of an ambitious Phase III agenda and an impressive volume of activity achieved.

Outputs such as training conducted and participant reach, planned growth to prevention reach, and increases in new clients accessing VAWG services have also largely met projected targets. In the first half of 2024, 1023 new clients were supported, compared to 940 clients in the same period of 2023. This represents the program being on track to achieve a 5% increase in new clients during the 2024 calendar year compared with 2023. In the first half of 2024, prevention partners reached 4,404 people, compared with 4,842 people during the 2023 calendar year.

Minor implementation challenges have primarily reflected operational context factors outside the Nabilan program team’s control. Primarily, these challenges have coalesced around the change in government following the May 2023 election and the shift in relationship – from the bilateral level down to the technical level – with MSSI. TAF has managed to carefully navigate this relationship and shore up relationships at the technical level, primarily through building on Timorese leadership within the Nabilan program. The relationship with SEI continues to be strong, largely due to the consistency of a key senior official with strong DFAT and TAF relationships. Government partnership and bilateral governance are further explored in Section 2.3.2 below.

Where other challenges have been experienced, such as stocktaking the play therapy approach and some partner issues, Nabilan has been aware, transparent, proactive, and collaborative in finding solutions. Play-based therapy is an example of proactive learning and recalibration following challenges during Phase III. In responding to a need to support service providers with child client engagement and support (a need reinforced in the MTR process), the TAF team sought to introduce and test the evidence-based play-based therapy approach. Adapting and testing this with Timorese partners during Phase III has yielded learning insights that the model may be too ambitious for the capacity and systems support currently available to service providers, including a lack of clinical supervision options in-country. Nevertheless, the Nabilan team has found that service providers respond well to knowledge and capacity development as to developmental theory and developmentally appropriate, trauma-responsive engagement of child clients. Accordingly, the team is recalibrating this intervention to more foundational basics rather than seeking to meet formal play-based therapy standards. The team has been open about the challenges experienced with this intervention and has shown responsiveness to learning and revising strategy.

Phase 3 Mid-Term Outcomes (MTOs) are determined to be mainly on track across each EOPO. Key strengths of the period (further explored in Section 2.5: Impact) are:

- Concerted improvements to service quality and referral and case management systems integration

- Supporting workforces with trauma-responsive wellbeing, self-care and peer support knowledge, capabilities and structures

- Communities shifting social norms, including norms associated with sexual violence, unequal intimate relationship power dynamics, and gendered burdens of unpaid care and domestic labour.

The following table summarises evidence of progress against the MTOs.

| Mid-term outcomes | Evidence of progress |
| --- | --- |
| - Women and children have access to support services (medical, psychosocial, legal, shelter) | Nabilan directly funds and supports four partners with 13 offices across five municipalities (Dili, Oecusse, Maliana, Suai, and Baucau). In January-June 2024, Nabilan partners accounted for 75% of all new VAWC services clients supported across Timor-Leste. Nabilan partners provide a range of complementary services, including temporary accommodation and longer-term shelter, psychosocial counselling support, legal support, forensic medical examinations enabling hospital care and evidence generation for legal cases, as well as referrals to other services, access to training and education, familial and community reintegration support, and follow up visits. New clients and the quantum of services provided have seen an upswing from 2023 to 2024. Notably, during 2023 the Nabilan team focused considerably on supporting partners to improve the quality of their service provision, to good effect, with six of nine service offices demonstrating improvement in their case management quality results between the CMAT audit periods in 2022 and 2023 (see Section 2.5: Impact). In 2023, 88% of cases handled by PRADET, FOKUPERS, and CEF-UMS met minimum standards or above, and 81% high standards. Where standards were not met as expected, Nabilan discussed with partners and undertook focused capacity development activities. Further, during Phase III, the Nabilan team and partners explored developmentally appropriate techniques to engage with child clients. While this may not continue in its original form, service partners clearly expressed support for child client engagement as a need and a request. Partner staff expressed a sense of not knowing the best ways in which to engage with traumatised children and a recognition that talk-based psychosocial support is typically not effective and appropriate. Phase III has also seen a concerted effort to conduct disability access reviews and consultations, which are still in the process of finalisation. Nabilan intends these to provide direction on improving access to and quality and appropriateness of service provision to women with disabilities. |
| - Social workers are professionalised and have increased capacity to support clients | The MTR team consistently heard from social workers (within services and prevention partners) that, where they had undertaken Nabilan’s Certificate III in Social Work and refresher training, this had a transformative effect on their practice and sense of themselves as professionals. A common theme in interviews was ‘previously, I did what I knew to do from my own heart and commitment; then I learned the right ways to do things’ (PRADET Suai KII). Knowledge and capacity development in professional social work was clearly a source of pride for an already-committed workforce, and many also spoke of the revelatory newness of the ideas of professional boundaries and not overburdening traumatised clients. Nabilan’s introduction of counselling training as a focused complementary stream of professional capacity development is particularly useful and timely during the period when the sixth round of the Certificate III is on pause. In 2023, in Nabilan’s follow-up surveys with counselling and Certificate III refresher training, 86% of participants reported applying skills or knowledge to their work (exceeding the 80% target). |
| - GoTL uses evidence to develop policies, plans and budgets to respond to violence against women and children | Indications of government responsiveness to Nabilan technical support and Nabilan-supported advocacy efforts are apparent. While it is challenging to ascertain direct Nabilan contribution, in 2023, MSSI's funding for shelters increased by 20% over 2022 levels. In the MTR team’s engagement with MSSI, they articulated that a key strength of the Nabilan program is generating and tabling evidence that provides a call to action and justification of government prioritisation, citing particularly the National Prevalence Survey. The MTR team cautions, though, that we did not receive an indication that budget allocation to essential VAWC services will increase again in the early 2025 budget. MSSI acknowledged the importance of Nabilan's engagement in supporting them in understanding the shelter funding environment and welcomed these discussions to extend beyond budget allocation for client food in 2025. PNTL requested Nabilan's support for training on competencies to incorporate into their training curriculum. The MTR team heard from a senior PNTL representative that this training was greatly appreciated, including the focus on stress management, and he requested Nabilan support to harmonise training materials with those provided by other UN actors. Nabilan supported SEI in revising the Law Against Domestic Violence and the Penal Code in preparation for presenting to Parliament, and the MTR team heard from SEI that this support was very well-received. Further, SEI emphasised Nabilan’s immense contribution to supporting them and broader GoTL to understand prevention evidence and frameworks, including longer timeframes required and the need to work across the socioecological levels. This was cited as directly informing the time period and strategic direction of the NAP-GBV 2022-2032, which includes a prevention pillar. Nabilan brings a new approach especially on prevention – a multisectoral approach, primary, secondary, and tertiary levels, the socioecological model. And this is very good; it gives a different dimension to prevention. – SEI senior official |
| - Participant parents/caregivers practice positive parenting | This stream of work is in a fairly nascent period, with the community-based project Aman ba Mudansa in its third round of implementation and the prison-based Aman Di’ak ba Futuru currently being piloted. Longer-term outcomes and impacts have yet to be determined, including because MEL tools encountered some challenges during initial piloting. Indications and community feedback suggest changes in attitudes and norms and a positive reception by beneficiaries. HAMNASA expressed that before Aman ba Mudansa, they had not achieved success in engaging fathers, only mothers. The MTR team heard from partners their deep interest in and commitment to the parenting models, to the extent that one of the partners sought Nabilan’s support to integrate the gender-transformative approach in another project funded by a different donor. A staff member from HAMNASA also expressed how profoundly impactful the work was in terms of them reflecting on their own lives, values and childhood experiences: We all think it’s very different experience from other funding. For example there are some really heavy areas of discussions and [during the adaptation and training process] we needed time to pause and reflect; they [Nabilan team] gave us that. For example on identifying violence and on power, I reflected on my past experiences and it brought up a lot of things. This was the case for others too. People cried. For example too on the parenting impact – we reflected on this including educating through force only; we realised this is abuse. We think about our past and sometimes feel sick, sad inside, angry. What did we learn from this? We learned about self-care; give space to yourself to feel these things, take time. In the community we support them to release their heavy energy including writing out everything they feel unhappy or angry on a leaf then release to the ocean; shout and shake it off. – HAMNASA senior staff member This was conveyed as a deeply healing, transformative experience. |
| - Target communities have reduced accepted of violence against women and children and have increased skills to address these issues | KOKOSA!: The MTR team undertook workshops with KOKOSA! participants from Dili communities and from Same. During these workshops, we heard communities' stories of change, with the key themes of change to sexual decision-making and consent practices, sharing of unpaid care and household labour, support for women who experience violence and encouragement and accountability for change by men who use violence, improved capacity of intimate partners to communicate and resolve differences, and a shift in parenting practices away from violent discipline, anger and impatience to gentler, more positive parenting (enabled by more sharing of care load between women and men). See Section 2.5: Impact for more detail. The MTR team’s own evidence collection accords with the Nabilan team’s own monitoring and evaluation assessment. In late 2023, in the Same end of support phase assessment, 77% of female respondents agreed that KOKOSA! has made the community safer for women, and that women feel safe to report cases of VAW. Men’s positive change across behavioural questions increased by 29%. SASA! technical advisors providing support to KOKOSA! regard the program’s results as very strong. NeNaMu: Nabilan's assessment of the shifts in knowledge and skills for Estrela+’s first cohort, the healthcare graduates, demonstrate reasonably equal positive shifts in female and male participants. In an MTR interview with one of the healthcare graduates, the alumna explained how NeNaMu was instrumental in supporting her to recognise and respond appropriately to VAWC, and realise her own positive duty and capacity, in her patient interactions: I learned a lot about identifying my own power and understanding about positive and negative power; how we can influence others. This really helped me to attend well to patients … Before I didn’t yet know about VAWC. I really benefitted from learning about this topic, and how to create relationships with others to address this, and also how to identify this and help patients. – NeNaMu healthcare alumna The Ulmera-based community intervention concludes in August 2024, so results are not yet known. However, engagement has shown promise to date. |
| - The prevention of VAWC sector (in Timor-Leste and the region) has increased capacity to implement effective interventions | BAHM: BAHM supports strengthening a form of intersectional feminist civil society leadership and movement building at a time when it has been noted that civil society spaces are closing down for collective action and advocacy. Phase 3 of BAHM supported deep engagement with women with disabilities, who mainly represented OPDs and VAW prevention sector representatives. The two groups ended up having unexpectedly positive and meaningful interaction with one another, disrupting forms of discriminatory beliefs held: We had what was meant to be two separate cohorts – people working in prevention and people from OPDs … But what ended up happening, quite unexpectedly and wonderfully, was the groups merged of their own volition. Even though initially there was a lot of tension because of the deeply ingrained discrimination of the prevention people against the people with disability and people with disability against LGBTIQ people and sex workers, in fact they really built up trust and understanding and broke down discrimination they had between the groups. There was also the unexpected benefit of building cross-sectoral exchanges that they started doing themselves, so a disability organisation inviting an LGBTIQ organisation to come and do a training and vice versa. That wasn’t Nabilan making them do that; that was them just doing that. That was a really amazing outcome. – The Equality Institute Research and Partnerships Manager A BAHM Phase 3 alumna – a woman with disability who is a senior leader of an OPD – spoke of the transformative effect of BAHM creating an inclusive, feminist space: Patriarchal culture says, ‘you’re a woman and you can’t do certain things’ … Society says that to women, and I’m a woman with disability. So this really made me lose confidence. [In BAHM], we discover our value and our power, to recognise that we, women with disability, have value like all women, like all humanity. In BAHM we had differences, but we learned how we can come together and put our power together, take care of one another and take care of ourselves … During the three months, we had a different kind of environment, a space where everyone could come as themselves with their own characters and get to know each other and see each other deeply, and work together well. – BAHM alumna and OPD senior leader CSO prevention partners: as well as institutional capacity building, partners have received various forms of Nabilan training and bespoke technical accompaniment, including stress management, introduction to KOKOSA! methodologies, child protection and sexual exploitation and harassment prevention. SEI has also received Training of Trainers from Nabilan to support their NAP-GBV engagement with other line ministries. In 2024, 74% of all training participants reported applying the new skills or knowledge in their work, and 99% reported that the training they received is relevant. These themes resounded through the MTR process. In the MTR process, partners to KOKOSA! and NeNaMu confirmed that they continued to learn and develop their skills to understand prevention, facilitate the interventions, and undertake associated MEL processes, with a deep appreciation for Nabilan’s accompaniment and support. CODIVA expressed particular gratitude for Nabilan in helping them extend and improve their SOGIESC training model as well as their training and facilitation skills, which in turn has assisted the small, grassroots organisation in accessing other funding sources and expanding their staffing profile. 13 of 14 respondents to the Nabilan MTR partner survey said that the program was ‘very good’ in improving their knowledge, abilities and capacity. The MTR team understands that DFAT and Nabilan have been considering improving monitoring indicators to track the development of prevention capacity and increasing independence to lead prevention initiatives; this would be a valuable addition to the training surveys and structured observations. Sharing learning nationally and regionally: During this phase, Nabilan has undertaken sharing of lessons learned and program evidence particularly through TAF’s networks, and presented at the biannual Timor-Leste Studies Association conference and at the SVRI Forums in both Mexico and South Africa in 2022 and 2024. Several evidence briefs have been produced in this period, and Nabilan has a refreshed website containing useful program information, including program evidence. |

Figure 2: Progress against Mid-Term Outcomes

A key feature of the Phase III program is the strong focus on program quality. As described in the CMAT case study in Section 2.5: Impact, service partners were encouraged to focus on the quality of case management and service provision over the quantity of services provided or the number of clients seen. At the outset of the phase, the program identified that growth in access to services without a commensurate focus on program quality could pose a substantial risk that women and children experiencing violence would receive not only unhelpful but possibly harmful service provision. For some partners (particularly ALFeLa), focusing on quality over quantity was quite a recalibration. It required significant support to think through new intake and case management processes without feeling that they were letting women down. Nabilan undertakes a rigorous annual audit process with a number of service partners, with strong improvement results demonstrated in this period.

The team has also undertaken or commissioned a number of assessments and evaluations. In the instances of KOKOSA! and NeNaMu, the team draws upon and adapts the global tools and approaches for KOKOSA! uses the SASA! database. Moreover, the careful and ethical approach to adapting, learning and improving introduced interventions attests to the focus on fidelity, quality, and ensuring that risks are managed. Local and global prevention partners spoke glowingly of Nabilan’s approach to program quality, including developing their capacity as facilitators and implementers. The MTR team noted the extent to which partners could describe the evidence they had generated throughout these processes and explain the rationale for and significance of a careful adaptation and learning approach. These are key indications that the Nabilan approach to instilling a shared sense of ownership over program quality is yielding positive results.

### KEQ6. How effective and appropriate are Nabilan’s modality and partnership approaches in delivering the program’s intended value?

Findings at a glance:

- TAF, as the NGO implementing agency funded through a grant, represents a highly effective program modality.

- The DFAT-TAF relationship is supportive of driving substantial program value.

- The partnership with the GoTL (specifically MSSI) has experienced some recent post-election challenges outside of the program’s control, and bilateral governance has suffered.

- The partnership approach with Timorese CSO grantees is valued and effective. Municipal engagement requires some strengthening.

- DFAT is recognised by stakeholders for its long-term, significant investment and Nabilan program branding is appropriate.

Strength of evidence: Excellent.

Program modality: The Nabilan investment takes the form of an annual direct grant to TAF, an international NGO (INGO), which has been the program's implementing partner for the full decade. TAF is responsible for dispensing sub-grants to the 10 Timorese CSO partners. At Post, Nabilan is managed by the First Secretary for Gender Equality and Disability Equity. The TAF leadership team, the First Secretary and the Senior Coordinator, Gender Equality, Disability and Social Inclusion hold planned monthly management meetings and are otherwise in contact on a very regular basis. Nabilan undertakes six-monthly and annual reporting to DFAT.

The Nabilan program team at TAF consists of 12 staff, including two positions – Team Leader and Prevention Manager – currently occupied by expat staff with long-term bases in Timor-Leste. The leadership team includes two Timorese Deputy Team Leaders. During Phase III, several Timorese staff members were promoted to technical coordinator roles, with responsibility for key interventions and the primary contact point for one or two partners each.

The MTR team finds that the program modality is very strong overall and enables an effective, innovative, long-term, values-driven and gender-transformative approach to EVAWC programming. Nabilan is unique in Timor-Leste in terms of having an INGO implementing agency rather than being implemented by a private managing contractor. As an INGO with a track record of work in this field and organisational infrastructure and connections to draw upon, not only in Timor-Leste but regionally, TAF provides a distinct value to this long-term investment. TAF has attracted, retained and nurtured a highly committed and dedicated program team. TAF staff articulated that they felt that the values-driven nature of the program sits comfortably within a for-purpose NGO environment.

The MTR team finds that the Nabilan team is well-cohered and high-performing. This has been supported by a program management approach that is highly collaborative and connected, with regular weekly, fortnightly and monthly meetings, including more informal learning fora and semi-regular reflections and retreats. Team members also have clear lines of responsibility and leadership positions. Timorese Nabilan staff spoke highly of the working environment as being respectful, supportive, and engaging. They expressed a high level of job satisfaction, underscoring job retention.

It's a good working environment; we have shared values and, therefore, feel happy to work. It's a difficult topic with the possibility for vicarious trauma but because of the good environment, support for each other and emphasis on wellbeing, we are happy. – Nabilan team member, TAF

We respect each other. It’s a good team, collaborative. It makes you feel strong and brave. – Nabilan team member, TAF

In addition to the working environment, Timorese staff members articulated that they were committed to staying with Nabilan because of the unique opportunity it afforded them to learn about long-term, evidence-based, quality EVAWC interventions, including primary prevention approaches. A number of the staff commented that Nabilan was unique in the country in undertaking 'true' primary prevention rather than awareness raising and that this work had impacted them personally on a deep level.

Nabilan is best practice prevention programming; I’ve learned a lot. I worked at other organisations doing prevention but not really good practice. You’d go home and feel nothing, it’s just a job. Not here; we go home and reflect on our own lives. It feels really motivating to work on good, evidence-based programming and in a program which learns from M&E. Nabilan is really strong on M&E and learning from results and impacts. – Nabilan team member, TAF

This finding that TAF is an exceptional implementing partner for Nabilan is reinforced by the universally highly positive feedback from partners about the TAF team and the partnership approach, explored further below. DFAT is also highly satisfied with TAF as an implementing partner, as evidenced in DFAT’s Annual Partner Performance Assessments and expressed to the MTR team.

DFAT-TAF relationships are strong, supportive of good program management and governance, and mutually reinforcing for an ambitious program agenda. The Post team has subject matter and contextual expertise, and this has facilitated Nabilan's positioning in the Australian Aid portfolio, including retaining long-term investment. Moreover, the MTR team heard from multiple stakeholders – including representatives from other aid programs – that Nabilan EVAWC and gender equality, disability and social inclusion (GEDSI) expertise is regularly drawn upon to enable collaboration, including on NAP-GBV ministerial support and in the provision of advice and training to support these programs, including through DFAT's Kalibur network of GEDSI advisor.

Further, in Phase III, there is evidence that TAF as an organisation has made a concerted effort to provide strategic value to the Nabilan team, including through executive leadership liaison with other INGOs, development partners and DFAT, and through providing resourcing to support the evidence and learning amplification strategy.

Financial arrangements are explored further in Efficiency, but it is noted here that the annual grants mechanism and TAF’s financial utilisation and management are also aspects of the effective program modality.

Nabilan’s current branding – which does not centre on Australian Aid visibility, but rather the programmatic mission – is appropriate. The MTR team found that organisational stakeholders are very aware and appreciative of Australian Aid funding supporting Nabilan. Further, the program's neutral branding protects against bilateral political challenges.

The MTR conclusions about the strength of the current program modality are tempered only by the current bilateral governance gap. Nabilan formerly represents a bilateral partnership between GoA and GoTL in actioning the NAP-GBV 2022-2032. Before the 2023 change in government, the Nabilan program was governed bilaterally - by DFAT/Post, MSSI, and SEI - which would monitor and endorse program direction, progress, risks and issues. As explored further below, this governance structure is currently inactive. This reflects a rupture in bilateral relationships and agreements between MSSI and GoA with the change in government; that is, it is not a reflection on Nabilan and has existed outside of the program’s control. Nevertheless, the current lack of overarching bilateral agreement with MSSI and SEI and the change in ministerial and staffing positions in GoTL have meant, in essence, the DFAT-MSSI-SEI Nabilan governance mechanisms ended in 2023. This has not been reinstated in part due to a concern that there may be a risk to the Nabilan program in doing so.

TAF has managed, including through Timorese leadership, to navigate and maintain reasonably strong technical and senior relationships with MSSI. Without a bilateral agreement, TAF plans to enter into a technical-level agreement with MSSI, providing some formality and joint decision-making regarding the program relationship. During this period, the SEI-TAF-DFAT tripartite relationship has remained consistently strong. While pragmatic workarounds have enabled the work with GoTL to continue, and the program has not suffered in part due to the trusted nature of TAF as the implementing partner, this lack of formal governance is not desirable in the longer term.

SEI, for example, is concerned that a lack of transparent program governance muddies the waters somewhat between technical program management and implementation and formal bilateral governance (including the appointed implementing agency and its workplan). Even while there are no current issues with the program’s implementation agency, SEI is keen to re-establish the governance processes which centre on the GoTL:

The general agreement between Australia and Timor-Leste has ended and they need to have a new one; since the new one is not in place yet they cannot sign any specific subsidiary agreement, so this is an issue. Now we discuss Nabilan and agree directly with TAF to avoid the risk. My thinking is that the GoTL and GoA hire TAF Nabilan – so when SEI signs directly with TAF Nabilan, we've effectively changed the positions. Previously, we were overview; they [TAF] were implementation. Now it's a bit difficult because we are signing on the same level. Previously TAF Nabilan would present their report and workplan to GoTL to approve the report and workplan so now if we sign directly with TAF Nabilan, who will overview and approve? – SEI senior official

Program partnership approach: The MTR finds that the program partnership approach is deeply valued by, and highly effective and appropriate for, Timorese CSO partners, as explored in Section 2.1: Relevance.

100% of Nabilan MTR partner survey respondents responded that they 'really value' the partnership between their organisations and the Nabilan program.

In Phase III, every grantee partner is assigned a key contact within the TAF team, and this responsibility is disbursed across the technical and senior leadership teams. This has worked well from partners' perspectives, with partners consistently relaying that the TAF is responsive, proactive, encouraging, supportive, and open to them communicating and raising issues at any time.

The strength of this partnership approach is evident in enabling some gains made in the program that could have been difficult to achieve in the context of a less trusting, more hierarchical donor relationship. For example, a process like the CMAT auditing could be quite intimidating or confronting if undertaken wherein partners felt they may be criticised or that there was a punitive donor intent. One partner (at the Dili headquarters level) did express some sense of reservation about the process, arguing that the Nabilan team did not have sufficient expertise or independence to undertake such a process. However, overall, the MTR team was struck by how positively received the process was, with most partners explaining how the Nabilan team had delivered feedback sensitively and with a view to encouraging improvements and deciding on a capacity development plan together.

In the prevention space, partners are overwhelmingly positive about Nabilan's 'walking together' approach to adapting, testing, learning, and refining international methodologies. This extends to how the Nabilan team offers them trust and hands-on support in increasingly independent implementation and facilitation roles.

Partners also noted Nabilan's ability to be an effective 'bridge' between their work and government policy and investment.

Nabilan’s partnerships extend globally, particularly in drawing upon expert technical assistance in adapting and applying proven prevention program methodologies such as SASA! and SASA! Together and Stepping Stones and Stepping Stones Plus. The technical advisors with whom the MTR team engaged had high praise for Nabilan's ways of engaging Timorese organisations and undertaking very careful, rigorous adaptation and testing processes. They emphasised that the quality of Nabilan’s work with KOKOSA! and NeNaMu is globally significant and should be shared widely.

## Efficiency

This domain seeks to answer the question: How well are resources being used?

### KEQ7. How well are program resources being used to govern, manage and deliver Phase III?

Findings at a glance:

- Nabilan represents an efficient use of GoA resources to support transformative change.

- Program management practices are strong and effective, including between Post and TAF.

Strength of evidence: Adequate (noting that a detailed value-for-money assessment is out of scope).

The Nabilan program represents an efficient use of GoA resources. A strong level of activity and achievement of outcomes is leveraged from the existing resource envelope, and the program is valued highly by community and partner beneficiaries. DFAT feedback and TAF reporting evidences a high utilisation rate of the annual grant, and the program has made good use of additional end-of-year funds where DFAT has made them available. DFAT oversees financial use every month, and six-monthly reporting includes detailed financial transparency and auditing. The long-term nature of the investment has meant that program expertise and experience have built continuously over time, supportive of maximising value generated from investment. Additionally, program efficiency benefits from TAF infrastructure, including financial reporting and management mechanisms. Program partners spoke highly of TAF’s support for financial management and fraud prevention oversight, and TAF has been proactive in spotting financial management issues and providing timely responses to partners.

Program efficiency is also greatly enabled by good program management and a high-performing, dedicated team (see Section 2.3: Effectiveness). As per Section 2.3, while pragmatic governance and decision-making arrangements are in place to support the GoTL partnership, there is currently no formal bilateral governance arrangement.

The MTR team finds that the Nabilan program is at a maximum stretch based on its current resource envelope; this is reinforced by financial utilisation rates, assessment of the volume of activity, and the difficulty for the program team in finding time for future-oriented strategic endeavours such as consultations on their idea for the establishment of an independent Prevention Organisation in-country. It would be difficult to imagine the team being able to manage more within current resources without a drop in the quality of partner engagement and program implementation; this was confirmed through discussions with the TAF team and executive leadership.

TAF notes that DFAT accountability and management requirements and invitations for broader engagement (such as advisory support to other DFAT programs or contributions to communities of practice) are resource-intensive, even if essential and generative. Nabilan has supported the growth of Timorese program leadership in meaningful ways. However, the extent of these DFAT interactions and the complex technical language required are considered barriers to appointing a Timorese person to the Team Leader role who can meet these system needs and requirements at the current time and likely in the near future. This was communicated clearly by Timorese staff members as well as international staff.

While there is a clear commitment to strong program oversight and collaboration by DFAT, TAF, and SEI, as noted in previous sections, formal bilateral governance is a recognised gap in the current program.

## Impact

This KEQ seeks to answer the question: What difference does the intervention make?

### KEQ8. What changes has Nabilan Phase III produced in the context of violence against women and children in Timor-Leste?

Findings at a glance:

- In addition to the achievement against the program’s MTOs, the MTR team finds that there is good evidence of achievement against Phase III EOPOs: 1. Women and children experiencing violence are supported with consistently high-quality services, and 2. Individuals, communities, and institutions act to prevent violence against women and children.

- In addition to these intended impacts, there is good evidence that the program has contributed to positive impact at a systems level, including supporting a people-centred systems approach, which is deeply transformational for beneficiaries.

Strength of evidence: Good.

EOPO1: Women and children experiencing violence are supported with consistently high-quality services

As explored in Section 2.4: Effectiveness, a key focus of the Phase III program has been on improving the quality of VAWC service provision. The MTR team finds that significant gains have been made in improving service quality during Phase III. While direct client feedback is currently limited (and outside of the MTR scope), it is expected that increased service quality enables an improved experience of safety, support and options for justice and rehabilitation. Service quality improvement outcomes are further explored in the case study below.

Case study 1 – the CMAT auditing process and service quality improvement

About the CMAT: The Case Management Assessment Tool (CMAT) process audits the quality of service providers’ case management practices, and their alignment with MSSI’s Standard Operating Procedure (SOP), with regard to client assessment, admission, counselling, reintegration, and follow up.

In undertaking this audit, Nabilan assesses a random selection of 20% of cases per provider and examines a small number of cases in detail.

In identifying that quality service improvement was to be a key focus of early Phase III, in late 2022 and 2023 Nabilan undertook their CMAT audit process across the five municipalities where PRADET safe houses and FOKUPERS and CEF-UMS shelters operate. On the basis of the 2022 results, Nabilan used results and requests from partners to determine required trainings, technical assistance and mentoring.

The resulting change: Between 2022 and 2023 CMAT audits, six of nine organisational offices demonstrated improvements in the percentage of cases meetings high standards – in one instance, a dramatic shift from 0% to 100%. Overall, across all partners, the proportion of cases not meeting minimum standards reduced from 29% in 2022 to 12% in 2023, and the proportion meeting high standards improved by 22%, from 59% to 81%.

In practice, the kinds of changes that were achieved in this quality improvement process included:

- confidential archiving of case files

- more regular and properly documented counselling, including documentation of what was discussed, counselling techniques and the client’s response

- using ethical, strengths-based counselling

- supporting counselling staff to use techniques such as breathing and grounding exercises and use of stress balls to reduce stress and tension

- applying consent procedures correctly and consistently, including gaining consent for a child client from a parent or Child Protection Officer

- improved coordination with MSSI for reintegration of clients

- conducting risk assessments consistently, including explaining risks to the clients to facilitate their decision-making

- more regular case conferences between referral partners to better facilitate a safer reintegration process and other forms of active coordination between partners through referrals and case conference meetings on complex cases

- ensuring follow up of clients at risk within a short period of time after reintegration.

For the Nabilan team, service quality improvement of this nature helps to ensure that women and child clients of VAWC services receive more appropriate, effective, and connected support (including referrals between organisations) and that their information remains confidential. In a context where there is limited access to information and capacity development regarding good service provision practice, a structured process like the CMAT, and the documentation and filing processes accompanying it, provide a structured learning opportunity for service providers to improve their practice.

Service providers’ experiences of the CMAT and resulting change: Overall, service providers engaged in the MTR process reported positive experiences of the process, describing Nabilan’s considerate feedback and useful follow up support. With one exception, they did not feel criticised on the basis of the baseline results; rather they reported feeling supported by the Nabilan team to systematise and improve their practices.

CMAT is like a way, a road, to really helping us, because when we work with victims, sometimes we’re really busy just attending to them, so our attention isn’t on documentation. So the documents are like a safeguard for staff who attend to people, they remind us what we need to do from initial contact to the end, from assessment to referral to visiting [reintegrated] clients. CMAT helps us all to move as a big group to using the same format, meeting the same standards … We didn’t feel scared to improve. – PRADET Baucau staff member

Partners voluntarily showed the MTR team their filing systems and the documentation which supports them to both structure their support provision, and to carefully and simply document case management.

Certain organisations expressed a great deal of pride in their improved results, feeling empowered by the specific data feedback and knowing that improved results means that they are better serving their clients, to whom they are deeply committed.

This is an excellent process because in the past we just attended to the work but we did not have the space to analyse our work so this has really helped us. Nabilan saw the areas where our work wasn’t that good or could be improved and then they helped us work together to improve. And they also worked with us to create a format and walked with us constantly and gave us lots of ideas. This gave us the spirit to improve; previously we just thought work, work, work and we couldn’t necessarily see the results but now we have a strong system. When we saw our improved results and progress we were really surprised and happy. We didn’t find this a heavy additional process; it really helped us with our work. And the format is really simple and they brought us and partners together to create. – CEF-UMS Suai senior leader

Others relayed that good documentation practices are supporting better internal sharing of workload and information, with clients transitioning more easily between staff depending on staff availability.

This has helped us in general with sharing with each other, like if one staff member is not available, the information is there and the client can be supported by another staff member. – FOKUPERS staff member, Suai

The CMAT and case management documentation process has enabled the referral network to understand their relative roles and responsibilities, and also share certain forms of client information upon referral and intake. This lessens the retraumatising burden on victim-survivors to tell their stories multiple times and supports an integrated, multiservice response:

Nabilan gives us lots of thoughts about how to improve the referral system for example if we are referred a client we don’t have to repeat asking certain information from clients so they don’t have to repeat their stories. In the past for example police would just bring the victim with no information but now between the referral network we have shared documents for referral and intake so we don’t have to ask the same information and we can see the chronology of victims’ story. We even ask the police to fill in their referral template or the police can verbally deliver the information and we can fill it out. We also do case conferences together (with other partners) when we see there is serious issues and need to share information and give ideas to each other. Victims are very happy with the referral network – we all accept them and work it out between ourselves; we don’t leave anyone behind. This reduces the burden upon victims; they are not overburdened by finding their way through the system. – CEF-UMS Suai senior leader

Some service providers were able to articulate other positive impacts for VAWC service clients:

We better and more carefully explain processes and options to victims, including legal options, for their decisions. Clients feel happy because we are supporting their referral needs for example to ALFeLa – we refer according to client’s needs and wishes. They also feel like we’re not turning them away if they have accessed another referral partner already.  – CEF-UMS Suai senior leader

In addition to the structured CMAT and related improvement processes, during Phase III, the Nabilan program has recognised the need and taken proactive steps to improve service quality response to women with disabilities and to children. These should be key areas of focus for the forthcoming program period, with the program team documenting how they intend to support an improved response to VAC and to violence experienced by women with disabilities through service provision for the remainder of Phase III and into Phase IV. This is further explored in Sustainability and maximising future value. Notably too, Nabilan fully funds the only shelter for children, run by FOKUPERS – an important investment in the VAWC service infrastructure.

EOPO2: Individuals, communities, and institutions act to prevent violence against women and children

Organisational capacity development, particularly of CSO prevention partners and SEI, was explored in Section 2.4: Effectiveness. This section considers the extent of evidence to suggest that Nabilan’s community-based prevention interventions – particularly KOKOSA! as the most mature intervention – is having community-level impact. In relation to assessing progress toward this EOPO, the MTR team was interested in understanding whether and how this prevention programming has catalysed individuals and communities to take action aligned with the prevention of VAWC.

Community-based primary prevention models seek to transform the harmful and rigid gender and power norms that underpin VAWC behaviours, including, but not limited to, the social acceptance of VAWC. Norms are different to individual attitudes; norms are shared unwritten rules or accepted ways of thinking that govern behaviours. For norms change to occur, there must be enough of a critical mass of mindset change. Community-based prevention models work on the theory that a long-range timeframe, population-based saturation of effort, as well as diffusion of change through community actors taking the change out to the broader community population are all important ingredients of norms and behaviour change. The SASA! and SASA! Together models upon which KOKOSA! is based have a ‘benefits-based’ approach to norms transformation; that is, they focus on positive reimagining of power relations and the benefits to all, rather than a shaming or blaming approach.

KOKOSA! communities are carefully facilitated through multiple stages, and at the point of the MTR, were in the third phase of Support (which is skills building and encouragement to come together with one another). This stage prepares communities to take action. Given this stage of programming, it is important that an assessment of impact is undertaken in and following the final Action phase of this programming. It is important, too, to recognise the limitations of this MTR process. This was not a full-scale impact evaluation, and it would be very useful to invest in robust, resourced impact evaluations of Nabilan’s key prevention interventions.

Nonetheless, within our limited engagement with KOKOSA! community members in Dili and Manufahi, the MTR team found good indications that individuals and communities are shifting from attitudinal and norm change to the application of skills to shift relational behaviours within intimate relationships, families, and communities. In the MTR workshops, KOKOSA! community participants were asked to work in small groups to canvas stories of significant change that had occurred in the last two years, determine one impact story to tell, and explain back to us and the group what happened, how KOKOSA! contributed, and why they considered that change story as significant. The MTR team then asked questions to support the elaboration of the stories told.

A number of key themes appeared in the stories told by KOKOSA! community members:

- Couples reflecting on the partner ‘deep discussions’ supported through KOKOSA! and applying their reflections to bring more emotional awareness, conflict resolution and collaboration skills to their interactions with one another and shifting away from gendered and uneven divisions of labour (particularly, men taking up more care and household labour, and in some instances, women seeking employment with the support of their husbands).

- Parents (including mothers) reconsidering their ways of relating to and disciplining children and moving away from lashing out at children to more gentle, positive parenting. This was said to be supported by the shifts above in couples experiencing more harmonious relationships and more equally sharing the load of care and household duties.

- The resultant impacts of children feeling safer and more loved at home and better thriving at school.

- Women feeling empowered as KOKOSA! activists to lead change and represent KOKOSA! in their communities, including through the facilitation of poster discussions at the household level.

- Men holding other men to account for their use of violence and encouraging change – including some men in the groups discussing their journeys of change away from the use of violence, said to have taken some time.

- Sexual consent practices between couples and men (particularly younger men) reflecting the attitudes and norms that previously underpinned their expectation of sex without consideration of their female partners (explored further in the case study below).

In addition to the stories themselves, the MTR team observed during the workshops that community participants were comfortable working together across age and gender differences and were articulate, confident and reflective narrators of stories of change. Moreover, the MTR team was struck by the spirit in which stories were shared and received – with honesty, personal accountability, vulnerability, passion, enthusiasm, emotional range, and support from other community members. Particularly in Dili, the group energy of optimism, passion, and collective support was palpable. Moreover, the MTR team was struck by the language and concepts, which appeared to have been integrated as an ease of vernacular – language that is particular to KOKOSA! (explored further in the case study below). KOKOSA! communities now share a new language around sex and intimacy – consent, decision-making, partnerships, pleasure and agency. The reflective, collaborative and narrational skills of community members are also suggestive of a contribution of KOKOSA! to building the personal and relational foundations necessary for community action.

Case study 2 – KOKOSA! and its impact on norms related to sexual violence, relations and decision-making

About KOKOSA!’s Support phase: In the KOKOSA! Support phase, community members and couples are supported to reflect on power within their relationships and how they may support positive use of power to prevent violence against women. By the end of the phase, activists, community leaders and other community members should know how to build healthy relationships and support others to change. They should also feel it’s everyone’s responsibility to prevent violence and have the confidence in themselves to do so. Lastly, they should be making positive changes in their own relationships; supporting women who experience violence; and holding men to account when they use violence, including supporting them to change

KOKOSA!’s Support phase draws upon SASA! Together, the revised version of SASA!. SASA! Together was designed to include a stronger component on prevention of intimate partner sexual violence and supporting couples to have the language and skills to approach sensitive conversations regarding sexual consent and mutual decision-making. Concepts of sexual consent and consent conversations are introduced. KOKOSA! strategies supporting this change include ‘deep discussions’ attended by couples, use of posters to generate conversations within households, and dramas and radio shows which explore these ideas, training and mentoring of community activists, and monthly activities and meetings with community members.

The Nabilan team supports each phase by training PRADET as implementers and accompanying PRADET’s facilitation, as well as supporting with MEL activities.

Prior to the Support phase: The Nabilan team relayed how taboo and difficult conversations and topics about sex were:

It wasn’t straightforward getting here. In the first KOKOSA! phase (Start) and part of the second phase (Awareness – Phase III Nabilan), community activists and leaders were not very comfortable talking about topics related to sex as it was considered taboo. They preferred to have discussions on ‘safe’ topics like sharing power in terms of sharing household responsibilities. This was noted in the Start and Awareness Phase Rapid Assessment Survey and in discussions with community members at that time. With the help of trainings, individual mentoring, lots of activity practice, and regular community meetings, activists, leaders and community members began to feel more comfortable talking about the consequences of men’s power over women, and the benefits of sharing power, including in sexual decision-making. The recent Rapid Assessment Survey as well as discussions with community members (including but not only Activists) demonstrates a greater willingness to discuss these topics previously considered taboo. – Nabilan team

The resulting change: Through multiple forms of M&E evidence – focus groups discussions, a Rapid Assessment Survey, PRADET partner reports and verbal updates – the Nabilan team identified sexual norms and consent practices were changing in KOKOSA! communities across 2023-24. PRADET shared with Nabilan one story of a young man from a Dili community, ‘Tomás’, who has been particularly vocal about the important of sexual consent and equal power in relationships and has been chosen to be Xefe Joventude (Youth Leader) with the village council on the basis of this advocacy and leadership.

When the MTR team ran a KOKOSA! community workshop in Dili, without prompting, Tomás told his own story:

Before KOKOSA!, I was in with my girlfriend for 4 years. When I wanted to have sex and she didn’t, I assaulted or forced her. I always did this. I used to threaten her or accuse her of having another man. Then KOKOSA! came and I understand better how to have sexual relations with consent. I watched the drama and it showed that when a man has sex with a woman without consent, it is assault. I saw that this is what I am doing. The drama showed the woman feeling not comfortable and crying, and I thought of my girlfriend. There was a positive too because the drama showed the man taking responsibility and changing.

I started to attend training and understand much more, including that what I had been doing was bad. I understood that to have better sexual relations, you need to ask and see if both the man and the woman want to, and then, only if both want to, you have sex. KOKOSA! has made a big difference to me. For three months, I tried to make change but nothing much changed; even after six months. I also worked with the PRADET staff member for counselling and encouragement. Sometimes in KOKOSA! they also teach tools or ways to calm himself which helps him with anger, for example deep breathing. Before, I couldn’t control my emotions.

My partner is very happy with the change. Before, she wanted to end the relationship, but she says now, ‘if you continue this way, we should be able to stay together a long time’. I see she is happy and our relationship is better; these are the benefits.

KOKOSA! helped me to see that these are not secret subjects. You don’t have to be scared. Before KOKOSA! we didn’t have the courage to share because people don’t keep secrets, but when PRADET came they explained that this is a safe space, it’s confidential. I asked my partner if I can share our story today. I think this is an important story to share because other men need to hear that sex without consent isn’t good and it’s criminal. If I don’t share, it will stop with me but other men need to be influenced to change.

Beyond Tomás’s individual story, in both Dili and Manufahi, this theme of sexual consent and equal sexual decision-making between female and male partners was prominent and volunteered by participants. After the workshop, PRADET staff in Manufahi joined the MTR team for a discussion, and the conversation on this theme continued. They talked about the process of supporting this change:

First it was really hard for the communities to accept talking about this. But with the posters and other strategies, they encourage people to begin talking about this. Often, people would say that men can oblige women to have sex and then they started realising that it is important for the man and women to decide together. This is like taboo, to talk about sex like this; like lulik (sacred). So we have deep discussions – women talk to the women and men talk to the men. It is important to grant confidentiality and make sure they trust us. We also share our experiences. They really feel this. Sometimes the men’s egos get in the way, but they slowly start to listen and realise this is good for a good relationship and good health. Sometimes the community feels ashamed or shy, so we encourage them to focus on the positives and the benefits for the relationship. It’s important to help create imagination and trust so they know we are people to share experiences with.

This isn’t an easy change in mindset for men – in our patriarchal culture, women belong to them. We focus on the benefits and consequences, and this moves them to change over time. For men, sexual consent is good because if they decide together, then there is good sexual connection and enjoyment together. They can also see that sex doesn’t have to just happen when they want to; if women are sick or tired, it’s better to respect them and value them not just as sexual objects. For women, if there is sexual consent and they decide together, it gives them a sense of value and respect from men, and they can also feel love and romance together in their relationships. For us all, it shows us that we care about each other including health, family planning – it creates harmonious relationships.

For the staff themselves, this work has been impactful and transformative in terms of their own views regarding sex, relationships, men’s sense of entitlement to women’s bodies and sexual objectification of women, and women’s sense of autonomy and right to not only sexual decision-making but also desire and pleasure:

I also used my negative power to dominate my partner a lot; I can see now that I didn’t regard her feelings, and I objectified her. Now, in terms of sexual consent, I listen to her. If she’s tired and wants to pause, I respect her decision. This is a big change. – PRADET male staff member 1

Before I started with KOKOSA! I was one of these people who considered my partner as second class and then I learned a lot and changed my ways, and our relationship is much happier and so is my partner. – PRADET male staff member 2

I myself make my decisions – if I’m not ready, then we don’t have sex. If I’m ready, if I feel like it, then I may approach my husband and ask him and I need to respect his decision. This is good not just for me but for the family. Sometimes women say they are not brave to talk like that to their husbands, but we say you have power and rights. – PRADET female staff member

Discussions with the SASA! global Technical Advisors from Raising Voices reaffirmed the significance of this impact in this hard-to-achieve area of social norms change.

When we did the SASA! revision, I was part of the team that led to SASA! Together. In there we thought about new activities that really focused on deepening discussions around sexual decisions which we didn’t have in the original SASA!. After the SASA! study we found out that some of the things that didn’t shift were the really intimate stuff like finances and sex. So the deeper discussions give a space for couples to talk about some sex and intimate things. Hearing that this has changed with KOKOSA!, it is amazing, and I think we need to document this to show that even in communities with strong cultural norms, people can shift. What is violence prevention if people can’t talk about such complex deep issues? I’m happy that this is happening in Timor and I’m really positive about the Nabilan program. – Raising Voices SASA! Technical Advisor

In addition to EOPO-aligned impact, the MTR team also suggests that there are good indications that Nabilan is having an important effect at a systems impact level. Nabilan is a critical sustainer of the EVAWC system in Timor-Leste, particularly CSO essential services, in the context of underfunded essential services, and in connecting government and civil society for a more integrated system. In other key ways, Nabilan has demonstrated effective use of strategic leverage points to support systems change. Some examples of these are documented at Annex 7. Here, we wish to focus on one key theme that was dominant across the MTR interview – a people-centred approach to systems change fostered by the Nabilan program.

The Nabilan approach recognises that systems of action and transformation are comprised of people, and that the work to respond to and prevent VAWC is difficult, traumatising, and also personally implicating. Many people will have experienced and/or witnessed, and possibly perpetrated, VAWC in their own lives. Discussions with the Nabilan team during the MTR process also surfaced a recognition there is a deep and recent history of multiple forms of trauma affecting the Timorese population following long periods of colonisation and war. In this context, sustaining a systems workforce as well as supporting the workforce to address traumas that may affect their professional efficacy is critical. The Phase III Nabilan design also recognises a real lack of professional counselling and psychological support services in-country, including clinical supervision for counsellors and social workers.

Across the MTR process, a key theme was partner staff, government officials and even Nabilan team members speaking of the Nabilan approach being deeply transformational, healing and sustaining of them as individuals. Involvement in prevention programming supported professionals to reflect on their own lives, including childhood upbringing and current intimate partnerships. Undertaking the Certificate III was spoken of by service providers who do counselling as the first time they had themselves experienced personal counselling.

The MTR team heard from services staff, in particular, how committed they are to the work they do and the traumatic toll it takes on them. We observed the toll directly as well during these conversations. Most critically, the investment by Nabilan during Phase III in supporting self-care and stress management strategies was spoken of time and again as being revelatory and deeply important to how people approach their work and sustain themselves:

Nabilan gave all of ALFeLa staff training on stress management. I cried. This program really helped in an emergency situation with me managing stress. I practice these techniques. I feel stressed when I have to attend cases; for example, I attended a sexual abuse case where a neighbour was abusing a boy, and it really affected me, and I stopped my kids playing with neighbours because of this trauma. I told management about the trauma, and they said we’d receive this stress management program which we did. When we did the stress management training, I spoke about this, and this really helped a lot, and I practice the technique with other cases. I feel that I can better manage myself. And sometimes I’m asked by other colleagues to attend interviewing with them. We have put in place peer support particularly with new cases when victims are telling their full story, as a stress management technique. – ALFeLa lawyer

While Nabilan has supported sustaining the EVAWC systems through a people-centred approach and filled a critical gap with stress management training, the need for more support, particularly to services staff – but also to prevention staff who come into contact with VAWC cases – was still evident to the MTR team. While there remains a lack of clinical supervision and counselling in-country, the traumatic toll of VAWC response will continue.

## Sustainability and maximising value

This set of KEQs seeks to answer the questions: Will the benefits last? What should be done differently/next to improve the program?

Findings at a glance:

- Nabilan’s funding, programming, partnership and people-centred approaches are supportive of longer-term sustainability.

- Some factors somewhat inhibiting sustainability are present and should be accounted for in designing Phase IV. These are reflective of both resource limitations and of contextual constraints and shifts.

Strength of evidence: Good.

### KEQ9. At this mid-point, to what extent are the foundations being laid for the sustainability of Nabilan’s outcomes and value, during and beyond Phase III? What factors are influencing this potential sustainability?

The MTR team finds that overall, Nabilan has a strong and explicit approach to supporting the sustainability of the investment and its outcomes. The Phase III design was accompanied by a sustainability plan, currently being reviewed, which supports a programming approach with a view to sustaining effects beyond the life of the program.

The MTR process surfaced the following factors supportive of sustaining Nabilan’s outcomes and value into the longer term:

Long-term, core and consistent funding: the funding model has been critical to foundationally supporting EVAWC efforts in-country, both in terms of essential services and providing the ability to thoughtfully trial prevention initiatives in a way that supports an ethical start to those initiatives and allows them to run their full course, with proper accompaniment and support

Considered approach to scale and expansion: Nabilan has demonstrated an ability to carefully build and implement a progressively ambitious program agenda over time, including expanding its prevention interventions and extending them to new communities and partners. Nabilan’s adoption of a ‘feminist scale’ approach to growing its prevention interventions has protected the quality, positive impact and ethical approach to these programming approaches – reinforced through the feedback of global technical advisors the MTR team spoke to. Additionally, the approach to introducing prevention interventions which take different time periods – with NeNaMu being a short, approximately three-month program, and KOKOSA! taking a number of years in a community – is also strategic, providing options including for scale-up and potentially for consideration of institutionalising NeNaMu as an offering of government. With current KOKOSA! communities heading into their final phase in 2025, Nabilan is at the point of considering exit and further expansion to new communities.

Partnership approach: As described in Effectiveness, Nabilan’s partnership approach is effective in building organisational capacity and quality of work, empowering and equipping organisations to progressively lead in interventions, and linking up actors and institutions to create effective flows of information and shared action across the EVAWC ecosystem.

Investment in people and workforce: the Nabilan program describes this as ‘professionalisation of the workforce’ through, for example, the Certificate III. The MTR team finds that Nabilan’s effects extend beyond skills and knowledge development to a personal-transformational, trauma-responsive effect that allows individuals a space to heal, transform mindsets, care for themselves and each other, and connect empathetically and inclusively with one another as humans and professionals. As described in Section 2.5: Impact, this people-centred systems approach is essential for sustaining the EVAWC ecosystem into the future, shoring up commitment to this field, creating self-organising systems of support, and protecting against burnout and harm from vicarious and direct trauma.

Working at multiple social levels – community, civil society, government and policy – and linking these levels: Nabilan’s deep and saturated approach to community engagement on EVAWC, as well as its commitment to supporting a vibrant, inclusive, feminist civil society, marks it as a distinct in-country investment, contrasting with other programs which are more focused on government support and briefer community interactions focused on awareness-raising. Nabilan invests in media capacity development through the FMDC partnership and through journalist training with SEI and JSMP’s judicial monitoring program, which are also critical civil society functions in a healthy democracy. Nabilan’s support for CODIVA, who promote LGBTIQ+ rights, community connections and work to protect LGBTIQ+ people experiencing violence, is a further example of Nabilan’s investment in an inclusive civil society. While working closely with civil society, Nabilan also has strong connections with government and is well-positioned to link its work at multiple levels and connect actors and institutions across these levels. This is aligned with a strong socioecological approach, evidenced to be critical in supporting sustained EVAWC change.

Investment in localised and feminist leadership: In addition to supporting partners to lead work and accompanying them long term, and supporting professionalisation of EVAWC and social services workforces, Nabilan has made another important contribution to building inclusive, feminist leadership in-country – the BAHM initiative. Evaluations demonstrate the important early stages of change associated with this work in terms of creating space for more individuals of diverse professional and personal backgrounds to step into a space of gender-transformative, inclusive leadership and to feel empowered. This has included women with disabilities, LGBTIQ+ people, and sex workers – cohorts who have been typically marginalised from being recognised and supported as leaders. Nabilan is currently supporting latest-round alumni to continue to connect with one another and self-organise to take action in their communities based on what they learned through BAHM. The MTR team heard from BAHM alumni and their colleagues, who are now Nabilan partners and applying BAHM learning to their organisations. While the intervention is small scale, it is a unique investment in regenerating and supporting an inclusive feminist civil society at a period in Timor-Leste’s history where civil society has faced pressure upon its freedom of expression and ability to organise.

Internally, Nabilan has progressively turned its attention to supporting local program leadership. While Nabilan’s plan to recruit a Timorese person to the Team Leader position during Phase III was not successful, the MTR team found that localisation of program leadership is being deliberately supported in other key ways. There appears to be a sharing of power, responsibilities and leadership within the Nabilan team that has been deliberately supported during Phase III. This includes:

  - through the promotion of key staff to Deputy Team Leader positions (of which there are two, who are part of the leadership team, with the other two positions held by international staff) and technical coordinator positions,

  - a program management approach which is feminist in its ethics, reinforces sharing of power and responsibility and non-hierarchical collaboration, and supports staff members to feel confident in their capacity to lead

  - government liaison being led by one of the Deputy Team Leaders, which has been critical to continued TAF relationships with MSSI following the change of government and flux in bilateral relations and to an ongoing positive relationship with SEI.

Timorese staff members attested to the genuine nature of this leadership sharing and expressed confidence in their professional capabilities: “We are experts in this work; we know the work. We can lead it.”

While the overall program approach to sustainability is found to be effective, some inhibiting factors and constraints are present and should be considered particularly for Phase IV design. Factors somewhat inhibiting sustainability are identified as:​

Factors internal to the program, most of which are reflective of resourcing constraints:

- A need for stronger services expertise that is commensurate with the program’s prevention expertise: In order to further deepen the program’s services approach to VAC, to supporting women with disabilities, and to strategise to further support the national gap in clinical supervision and counselling options, it would be useful for the program to have additional, ongoing access to specialist services expertise.

- Services staffing, particularly in municipal offices, wherein counsellors and lawyers may be the sole operators: Some services offices experience staffing level constraints for key frontline positions, limiting the level of service provision as well as exacting a toll on those staff members.

- In-person and partner access to global prevention technical advisors: Nabilan has drawn upon global technical advisor support, particularly in terms of KOKOSA! and NeNaMu, which is appropriate and advised in terms of adapting and applying these interventions in new contexts. This has been a successful model of collaboration, and global technical advisors emphasise that Nabilan is a key model of good practice in their engagement with global technical advice. However, two small gaps were noted in the context of KOKOSA! – the ability of Nabilan to resource regular visits by global advisors and the opportunities for PRADET to directly engage with the technical advisors. Both could be addressed through the resourcing of a visit by the two Ugandan-based technical advisors during 2025, which could be timed to support the Nabilan and PRADET teams in considering exit, expansion and impact evaluation strategies.

- The need for partner-owned risk management plans: During the MTR process, the team heard one instance of partner programming behaviour that, while meeting a need to protect LGBTIQ+ from experiencing violence, seemed high-risk for the staff involved. In another instance, we heard from the Nabilan team about a prevention partner managing an instance of known violence by a community activist. The Nabilan team has identified that it would be useful for partners to lead or actively collaborate on their own risk management planning so that they are prepared for and can strategise to manage difficult situations and avoid doing harm.

- Access to the MEL and communications resources which could strengthen the program’s impact evidence and its ability to amplify this evidence: While Nabilan has done a great deal with limited MEL, communications and amplification resourcing. However, its ability to generate robust impact and systems evidence, which would be supportive of sustaining prevention approaches and articulating a holistic systems-oriented program approach, and to leverage this evidence in-country and regionally in order to influence the work of other actors, is limited by resourcing.

- DFAT accountability requirements, servicing the donor relationship and supporting other aid investments with EVAWC advice: While there is a strong and mutually reinforcing relationship between the TAF Nabilan team and DFAT, the needs of this relationship in terms of ongoing management communications, program reporting, presentations and provision of advice to other Australian Aid program are experienced by TAF as resource-intensive and requiring a certain donor liaison expertise and level of technical development English that can be disempowering to Timorese leadership. In some ways, these may be currently unavoidable tensions of high Australian Aid investment in and commitment to an ambitious program, and it is understood by the MTR team that both DFAT and TAF have discussed engagements, workloads and where invitations to engage are optional for Nabilan. Even still, at this mid-term point, there is an opportunity to pause and reflect on whether this balance of this resource demand is supportive of Nabilan’s long-term sustainability and whether there are other options available. This could include, for example, being clear on where and why Nabilan should provide advice and training to other aid investments and where that expertise can be sourced elsewhere within DFAT or within other implementing agencies. A further option for Phase IV, should it be determined that, in fact, the level of engagement with Australian Aid programs is necessary and important for catalysing further systems impact, is that an additional senior position is funded within the Nabilan team that could support donor and DP liaison, as well as evidence amplification. Another option could be co-Team Leader roles with somewhat different responsibilities and the ability to have shadowing and mentoring.

- GoTL engagement approach: The current bilateral governance gap presents a risk for the program. This is an external constraint; however, it would appear that TAF’s ability to successfully navigate the MSSI engagement challenge during Phase III has somewhat relied on the skills and relationships of one Timorese staff member. This poses a potential risk to the program should, for example, that individual exit TAF. Moreover, the team structure does not emphasise government relations. It may be useful to consider and resource a revised team structure, which includes a government lead position. An additional option to consider would be to resource a position based at MSSI to further cement the relationship on supporting quality VAWC services, including internal advocacy for budget allocation.

External constraints and impending context shifts:

- GoTL budget allocation to essential VAWC services: While hearteningly, the GoTL’s budget allocation to VAWC services improved between 2022 and 2023, Australian Aid investment comprises the majority of funding available to essential services in-country, and there is little to suggest that this will shift in the short- to medium-term. While it is important to continue to support advocacy for essential services, through the Nabilan program’s support for data provision and CSO advocacy and through bilateral relations, this should be recognised as a major ongoing constraint in the context. This is not unique to the Timor-Leste context; this is common across the Pacific. That is to say, Australian Aid funding of essential services is likely to be required beyond Phases III and IV.

- In-country access to clinical supervision and counselling: The Nabilan program recognises this gap and has made an important and valued contribution to addressing this in Phase III through its training and support on trauma-responsive professional wellbeing, including self-care and stress management training, developing opportunities for peer supports, and supporting access to the Nabilan team directly to discuss complex cases. The value of this investment was a primary theme in MTR interviews with services staff and also other actors, including PNTL. However, the need for further professional wellbeing support, particularly for services (including legal services) – but also to prevention partner staff who articulated having experienced realising the full extent of VAWC for the first time through their work on Nabilan – was apparent to the MTR team. Services staff, in particular, carry a heavy burden, which takes a toll, and this toll can be compounded by isolation or lack of staffing alternatives in municipal offices.

- The forthcoming high-speed internet cable and likely impacts on VAWC patterns and prevalence: A key concern for a number of stakeholders was what is likely to occur with the introduction of high-speed internet to Timor-Leste in 2025. Australian Federal Police articulated that, based on experience elsewhere, this is likely to quickly propel child exploitation cases and other forms of violence, such as technology-facilitated abuse and image-based sexual abuse. The MTR team also notes that greater access to the internet is likely to facilitate a backlash effect in other ways that work against prevention efforts; for example, potential recruitment of younger men into movements and ideologies that are anti-feminist and anti-progressive and reinforcement of sexual norms associated with pornography, including male sexual entitlement and objectification, lack of consent, lack of protections against STIs, and child exploitation.

### KEQ10. What additional improvements, changes, or additions would help maximise the program’s value for the remainder of this phase and in the next phase? What other considerations should inform future design?

Remainder Phase III changes and additions

Overall, the MTR team finds that the Nabilan team and DFAT have established a strong plan and undertaken key foundational work that will support the remainder of the Phase III investment. This is a relatively ambitious agenda that includes a focus in 2025 on the Prevalence and Perpetration Study and related qualitative research pieces. Otherwise, we suggest that the emphasis of Phase III should be on consolidation, coordination and amplification, and deepening inclusion strategies, as well as designing Phase IV. Following are recommendations for operationalising this focus.

Phase III sustainability and value gaps, opportunities and improvement recommendations

| Gap | Within current resourcing envelope | With additional resourcing (where applicable) |
| --- | --- | --- |
| 1. Bilateral governance and government relations | - TAF to enter technical-level agreement with MSSI - DFAT and Nabilan to map the possibilities for reestablishment of a bilateral governance mechanism, including in discussions with SEI - Document current government engagement strategy and undertake risk assessment of this to inform Phase IV design | n/a |
| 2. Local partnerships | - Support collaborative risk planning with partners to ensure a do no harm and professional safety approach is shared by partners - Identify opportunities to give partner staff a sense of recognition and thanks for their efforts | - Strategise to promote more shared purpose and openness across the Prevention and Services streams, including supporting primary prevention learning and engagement opportunities for services and justice system organisations - Identify opportunities for greater municipality engagement |
| 3. DP coordination | - Continue and strengthen regular meetings and mechanisms for information sharing and coordination – 1:1 interagency and ‘UN family’ approach (the latter led by DFAT); DFAT to continue exploring reinstating the GBV and Gender Equality Donors network | - Consider possibilities for strategic engagement with UN agencies in informing and supporting the proposed Prevention Organisation (for example, an evidence stream to the prevention organisation could enable this) |
| 4. Services VAC response | - Document revised play therapy/child client engagement model moving forward and support services staff, particularly in municipalities, to gain access to skills to this | - Seek external expertise to assist with a services improvement strategy to inform Phase IV design - Work with GoTL and other relevant actors (for example UNICEF) in mapping the intersections between GBV case management and child protection SOPs and supporting partners to understand these - Support partners with reintegration and follow up risk management strategies particularly in cases of incest and other forms child abuse (as requested by partners) |
| 5. Services disability inclusion | - Finalise reviews and consultations and determine action plan for pragmatic first steps within Phase III - Determine resource model required for Phase IV for a more fulsome response | - Consider facilitating BAHM alumni to support co-design of/lived experience advisory engagement with action plan to respond to the disability reviews and engage with service providers to support their awareness of key needs and issues |
| 6. Prevention and feminist leadership | - Develop NeNaMu and KOKOSA! exit and modest scale-up plans - Undertake outcomes evaluations for NeNaMu and Positive Parenting - Undertake consultations to inform whether there is demand for the establishment of a national Prevention Organisation | - Support global technical advisors (particularly SASA!-aligned) to visit, which could support exit and scale-up strategising, consider the changing internet environment, enable stronger South-South relationship development with PRADET |
| 7. Evidence generation and amplification | - Continue to develop evidence briefs, including from the forthcoming National Prevalence Survey - Establish national mechanisms and fora (for example, a Prevention Showcase; regular DP meetings) to share this evidence in-country, as well as on LinkedIn and other social media platforms - DFAT to explore possibilities for Nabilan to be aligned with the Southeast Asia GBV Prevention Platform to support maximising value from other regional EVAWC investment, in an advisory capacity (to feed into Phase IV design) - Seek global fora (such as SVRI blogs or podcast, or promotion by global Technical Advisor organisations) to disseminate learning | - Undertake community research particularly for KOKOSA!, including community observations, in-community development of change stories, and for example measuring unpaid care work division through use of household surveys - Prepare for impact evaluations of KOKOSA! and NeNaMu, including seeking out relationships with highly-skilled evaluators to provide impact evaluation design advice - Undertake webinars, the recordings for which can be retained on the Nabilan website |
| 8. Preparing for the impact of high-speed internet | - Leverage the AFP’s forthcoming commissioned analysis of the potential impacts of high-speed internet - Identify Phase IV opportunities such as a social media campaign and community engagement focused on parents and young people in terms of online safety (in conjunction with other relevant actors) - Undertake discussions and planning with GoTL | - Seek regional/global expertise in preparing a strategy to address and prevent VAWC impacts of greater internet access, in preparation for Phase IV design. This could provide a gendered analysis to complement the AFP’s commissioned analysis. This could also be supported by the DFAT Southeast Asia GBV Prevention Platform. - Explore working with the AFP and other partners to determine a strategic response to VAWC impacts of high-speed internet - Identify key opportunities to integrate considerations in current design – for example, working with FMDC to develop radio programming, revisiting KOKOSA!, NeNaMu and positive parenting curriculum/ materials including on consent and parenting to examine ongoing relevance in a changed environment, educating service providers on different manifestations of violence such as technology-facilitated coercive control and how to support clients with this (including for example safe mobile phone use) |

Phase IV key considerations

The MTR team suggests that the key principles guiding Phase IV should be:

- The value of the Nabilan program and the need for increased investment in order to do more.

- Retain and sustain the core components of the program while focusing on strengthening the services specialisation (including response to children, access and response to women with disabilities, and strengthening clinical oversight and support).

- A rebalancing of the program toward addressing violence against children in more equal measure to violence against women – through service response capability and parenting programs in the first instance.

- Seeking to build on the great success of the stress management training and other forms of wellbeing support, to explore models of trauma-responsive workforce support that are progressively akin to clinical supervision and counselling.

- Leveraging the strength of BAHM Phase Three in engaging with women with disabilities, to considering structured opportunities for BAHM alumni to support the Nabilan program through, for example, lived experience advisory services or co-design engagement. This could be particularly helpful in supporting services to be more disability-inclusive and referral pathways more accessible.

- Careful scale-up of KOKOSA! and NeNaMu – including to new communities and perhaps with an additional KOKOSA! partner.

- Investing in robust, multi-year impact evaluations of Nabilan’s key prevention interventions

- An explicit systems orientation of the program, with a focus on identifying and maximising systems leverage points.

- Amplification of evidence and evidence-based influence through the establishment of a national Prevention Organisation and connections with regional programming, particularly where there is Australian Aid funding.

- Responsiveness to the changed context of greater internet access, including learning from regional research and programming initiatives working on similar issues.

# RECOMMENDATIONS

This section provides recommendations for the remainder of the Phase III Nabilan investment and for the probable Phase IV (2026-30) extension.

| Criteria | # | Recommendation | Phase III, IV, or both? |
| --- | --- | --- | --- |
| Overall findings | 1 | It is recommended that the Nabilan program be extended into Phase IV. | Phase IV |
| Overall findings | 2 | It is recommended that the level of investment be increased for Phase IV. Two options for investment increase are included below, with the MTR supportive of Option B. | Phase IV |
| Relevance | 3 | It is recommended that all key interventions and components of the Nabilan Phase III design retain relevance for the current environment, though as the Nabilan team recognises and is actioning, VAC service response capacity needs to be strengthened. Key interventions should be continued across Phases III and IV. | Both phases |
| Relevance | 4 | It is recommended that to support program responsiveness to forthcoming contextual changes (such as high-speed internet) and to maximise systems impact, the program invests in improving its Theory of Change for Phase IV, including systems analysis and future forecasting. A strengthened ToC should also be clearer about which forms of violence experienced by whom are addressed through which program strategies, and specifically how the program responds to VAC. | Phase IV |
| Relevance | 5 | It is recommended that DP coordination and liaison continue to be improved within the Phase III period, particularly with UN agencies. This could take the shape of more regular Nabilan-DFAT-UN agencies meetings, as well as direct meetings with particular agencies such as UNFPA. This increased engagement should also focus on supporting DPs to better understand the Nabilan program approach and evidence, especially in the prevention space. | Both phases |
| Coherence | 6 | It is recommended that, within Phases III and IV, the Nabilan team address the sense of siloing between program pillars and their partners, and the tension felt between older, more established partners and newer partners. Renewing of a shared program purpose could be supported through learning visits to each other’s work, practicing sharing stories of change including collaborations, and, in Phase IV, providing older partners with more opportunities to engage in the community-based prevention work. This could look like the careful incorporation of the most prevention-ready service partner into KOKOSA! scale up in the coming years, and opportunities for occasional training and accompaniment of community engagement for other partners. | Both phases |
| Coherence | 7 | It is recommended that, within Phase III, Nabilan creates structured opportunities for HDS and HAMNASA to learn from one another’s positive parenting interventions | Phase III |
| Coherence | 8 | It is recommended that the Nabilan team consider more municipal visits and opportunities for municipal staff to engage in Dili-based reflective learning processes. The MTR team acknowledges, though, that this must be approached sensitively, given that each grantee partner has their own, independent organisational systems. | Both phases |
| Coherence | 9 | It is recommended that the program undertake systems analysis, potentially with some limited external expertise, to support its systems-level strategising and to inform Phase IV design and MEL. | Phase IV |
| Effectiveness | 10 | It is recommended that as interventions mature and cohorts exit, outcomes evaluations are undertaken of NeNaMu and the positive parenting initiatives to fully understand their potential, including six-month post-exit follow up. This should include the partners of incarcerated men in the context of HDS’s ways of working with men. | Both phases |
| Effectiveness | 11 | It is recommended that as soon as possible, the formal bilateral governance gap should be addressed – acknowledging that this may not be feasible in the short term. Current pragmatic solutions are appropriate, in the absence of alternatives, and TAF is taking steps within its control to give some formality and GoTL oversight to Nabilan’s GoTL partnership by establishing a technical-level agreement with MSSI. However, a longer-term solution whereby DFAT, MSSI and SEI can come together is necessary for good governance. One suggestion – that there is a Nabilan Working Group comprising MSSI, SEI and DFAT attached to the Interministerial Steering Committee for the NAP-GBV – could be further explored with SEI. | When possible |
| Efficiency | 12 | It is recommended that the program should not be expected to do a significant amount of additional activity on the basis of the current resourcing envelope. | Both phases |
| Efficiency | 13 | It is recommended that the extent and servicing of DFAT requests for Nabilan engagement across the broader aid program be considered strategically in terms of their relative cost-benefit, including Nabilan resource usage and unintended impacts upon inhibiting localisation of leadership. | Both phases |
| Impact | 14 | It is recommended that in Phase IV investment be made in carefully designed, robust impact evaluations of KOKOSA! and NeNaMu as Nabilan’s leading community-based primary prevention initiatives. | Phase IV |
| Impact | 15 | It is recommended that in Phase IV investment be made in systems impact evaluation to further explore and document how Nabilan is effecting change at that level. | Phase IV |
| Impact | 16 | It is recommended that Nabilan maintain and seek to expand stress management training and other trauma-responsive strategies that support the VAWC workforce to sustain. | Phase IV |
| Sustainability | 17 | It is recommended that consideration is given to resourcing two Raising Voices Technical Advisors to visit Timor-Leste, engage with the Nabilan team and PRADET including in community exit planning, and undertake community observations. | Phase III |
| Sustainability | 18 | It is recommended that Nabilan support partners to undertake their own risk management plans. | Phase III |
| Sustainability | 19 | It is recommended that DFAT and TAF undertake a reflection on the current level and requirements of DFAT engagement and determine a strategy to strategically prioritise and/or manage. | Phase III |
| Sustainability | 20 | It is recommended that a co-Team Leader arrangement is considered to support national leadership of the program. | Phase IV |

See also: Phase III Options in Section 2.6: Sustainability and maximising future value.

# PHASE IV OPTIONS

The MTR team recommends an increase to Nabilan investment in Phase IV, commensurate with the principles articulated in Section 2.6: Sustainability and maximising future value. Two levels of increased investment are articulated below to provide options for consideration. It is the view of the MTR team that maximum value would be generated from Option 2 and that, if resourced, the Nabilan program is at the point of maturity to be able to manage a program agenda of this level of ambition.

Option 1 – focused on increasing program team/personnel resources to support consolidation and maturation:

Expected quantum of resource increase: approximately 20-25% per annum on Phase III resourcing

| Position/area of expertise | Would enable |
| --- | --- |
| Co-Team Lead role | - Further developing national program leadership - Sharing of critical strategic relationships – GoTL, DFAT, DPs - Greater strategic focus on assessing the desirability of a national Prevention Organisation, and exploring options for regional influence on good EVAWC programming practice (such as connecting with DFAT’s South-East Asia GBV Prevention Platform) |
| Specialist services expertise (ongoing consultant or dedicated position) | - Ongoing strengthening of quality of services - Support to service partners to appropriately undertake therapeutic engagement of child clients - Actioning Nabilan’s forthcoming service provision disability inclusion strategy, including supporting women’s access to services and the referral network in the first instance, and then providing women with disabilities appropriate, tailored support - Clinical oversight, particularly in terms of counselling - Development of options for trauma-informed workforce support |
| Shorter-term engagement with systems analysis expertise | - Support the program and partners to undertake systems analysis to inform a refreshed MEL framework and planning for Phase IV |
| Evidence and amplification role | - Development of learning briefs, papers, presentations, webinars, stories of change, MEL tools and focused reviews - Development of national opportunities to share prevention evidence - Support to the Prevention Organisation consultations - Engagement with DPs with relation to sharing evidence - Supporting strategising for regional influence |

Option 2 – focused on impact and amplification of systems impact (within and beyond Timor-Leste):

Expected quantum of resource increase: approximately 50% per annum on Phase III resourcing (inclusive of Option 1)

This option presumes actioning Option 1 in addition to the below.

| Focus area | Would enable |
| --- | --- |
| Investment in robust, multi-year/longitudinal evaluation of KOKOSA! and NeNaMu (including a period of careful mapping of expertise and design options) | - Testing and evidencing the effectiveness of these interventions in reducing VAWC and sustaining other forms of change over the longer-term - Amplifying Nabilan’s program model nationally, regionally and globally |
| Prevention scaling and leadership | - Greater level of community-based scaling of key prevention interventions (while still working to feminist scale principles) – to consider prevention partners on mature interventions and scaling up to twice the level of communities as in Phase III. Likely to require at least one additional prevention staff member at TAF, as well as an increased quantum of funds - Development of a Prevention Organisation in country (which also includes a prevention of technology-facilitated abuse component) - Establishing Nabilan’s regional influence (especially to other Australian Aid investments) in terms of prevention programming, including through DFAT’s SEA GBV Prevention Platform |
| Response to technology-facilitated abuse and exploitation | - Investment in research to inform programmatic and policy response to the significantly changed environment - New programming areas that respond to the changed internet environment. This could include an increased investment in media strategies that can reach population at scale, working with the GoTL on child exploitation response and online safety community education, and consideration of whether and how existing prevention interventions should be adapted to be responsive/attendant to technology-facilitated abuse and backlash to gender equality |

Annex 1 – Nabilan’s key program components and interventions

Nabilan’s key domains of activity

| Domain | Description |
| --- | --- |
| Essential service delivery and systems capacity: | Strengthening essential services for women and children experiencing violence, including social work professionalisation, enhanced counselling capabilities, enhanced case management systems, and improved referral pathways. With core funding and technical and organisational support, Nabilan supports four essential VAWC service providers working across 13 offices in five municipalities. These civil society organisation (CSO) service providers support clients with: - legal advice and accompaniment through criminal prosecutions, - temporary crisis accommodation and longer-term shelter, - medical-forensic examinations to support treatment and criminal case evidence, and - other forms of recovery support including assistance with access to informal and formal education, accompaniment for reintegration into communities and families, and follow-up visits once a client is reintegrated. Australian Aid is the major funder of essential VAWC services in country, with program funding modelling estimating that Nabilan comprises approximately 70 per cent of national VAWC service provision funding. Additionally, in the first half of 2024, three-quarters of new VAWC clients were supported by Nabilan-funded service providers. In addition supporting individual service providers, the program supports essential services systems capacity through: - development and implementation of a Certificate III in Social Work, with a focus on VAWC, of which graduates are both Nabilan partner staff and representatives of other social and community services, and - working with the Ministry of Social Solidarity and Inclusion (MSSI) to develop standardised case management expectations, quality standards and guidance for the gender-based violence case management referral network of government and non-government actors (including service providers, the police and MSSI itself). |
| Prevention efforts: | Across Phases II and III, the Nabilan program has proactively scoured the global landscape to identify primary prevention interventions which have been rigorously tested, have a strong evidence base and have global technical advice support available. Primary prevention interventions target the root causes of gender-based violence through transforming harmful gender norms and equipping individuals, families and communities to build norms and practices grounded in equality, respect and more flexible, collaborative gender roles. With the support of global prevention advice, the program implements three community-based primary prevention interventions with four CSO partners: - KOKOSA! (an adaptation of SASA! and SASA! Together, originating in Uganda with Raising Voices), - Ne’on Nain ba Mudansa (NeNaMu, an adaptation of Stepping Stones and Stepping Stones Plus, originating in Uganda with The Salamander Trust), and - two gender-transformative fatherhood and positive parenting initiatives (community- and prison-based adaptations of Bandebereho, originating in Rwanda with the Rwanda Men’s Resource Centre and Promundo as part of MenCare+). Additionally, the program works with: - a media CSO to undertake radio programming enhancing and more broadly disseminating KOKOSA and NeNaMu!-related messages, and - an LGBTIQ+ rights CSO which supports university students, communities and families with LGBTIQ+ and sexual orientation, gender identity and expression, and sex characteristics (SOGIESC) education and rights awareness |
| Feminist leadership and local partnerships for nationally-owned transformation to VAWC: | Through the Bin-Alin Hakbiit Malu (BAHM) feminist leadership development initiative, Nabilan seeks to expand access to and provide support for intersectional feminist movement building among CSO representatives and activists from diverse backgrounds, including women with disabilities and LGBTIQ+ people. Nabilan also takes an intentional, long-term approach to sustaining and developing Timorese leadership for the elimination of VAWC through its partnerships with government and CSOs. |
| Evidence generation and policy influence: | Nabilan includes a strong focus on supporting research (such as the VAWC Prevalence and Perpetration nationally-representative surveys) and undertaking programmatic monitoring and evaluation that support building the evidence base on what is needed and what works to prevent and respond to VAWC in Timor-Leste. Nabilan aims to use this evidence, and support others to do so, to advocate for and systematise policy reforms and programmatic approaches that are effective in addressing VAWC. |

Nabilan’s key initiatives with timeline

| Program pillar | Initiative | Description |
| --- | --- | --- |
| Services (EOPO1) | Certificate III Social Services with Ministry of Social Solidarity and Inclusion (MSSI) Introduced Phase I | Supports professionalisation and growth of the social worker workforce. |
| Services (EOPO1) | Play Therapy Introduced Phase III | Training and support for VAWC services in relating to and engaging child clients (2.5 – 11 years) through play techniques. |
| Services (EOPO1) | Counselling training Introduced Phase II | Development and implementation of a multi-day counselling training course, directed toward social worker/counselling roles based at Nabilan partners. |
| Prevention (EOPO2) | Komesa, Konxiénsia, Suporta, Asaun! (KOKOSA!) (in suku Letefoho, Manufahi, and 3 suku in Dili) with PRADET Introduced Phase II | An adaptation of the community-based GBV prevention model SASA! (originally implemented in Uganda), KOKOSA! sees local communities supported to surface and address gendered power inequalities between women and men and transform norms associated with gender inequality, power imbalances and violence. Communities are guided through four stages. |
| Prevention (EOPO2) | Ne’on Nain ba Mudansa (NeNaMu) (Dili) with Estrela Plus Introduced Phase II | A curriculum-based program in which four peer groups (younger women, younger men, older women, older men) work through modules to identify and share their own experiences regarding gender, relationships, sexuality and violence. On this basis of raised consciousness, they then learn about healthy, loving, respectful, non-violent intimate relationships and sexual and reproductive health and rights (SRHR). Participants also learn about how to access SRHR and VAWG services and support others to do so. Participants are encouraged to be peer supports and changemakers in their communities. |
| Prevention (EOPO2) | Bin Alin Hakbi’it Malu (BAHM) (Dili) with The Equality Institute (EQI) Introduced Phase II | Leadership program for emerging feminist leaders, based on an intersectional feminist leadership model and with a view to both movement-building as well as individual development. Incorporating self-reflection and self-care. LGBTIQ+ inclusive focus. |
| Prevention (EOPO2) | Aman Di’ak ba Futuru & Aman ba Mudansa (Dili) with HDS and HAMNASA Introduced Phase III | Gender-transformative positive parenting programs for parents and fathers, including a current pilot working with prisoners. |

Annex 2 – Evaluation Plan

Our approach to the evaluation was characterised by the following principles:

- Utilisation-focused: The evaluation focused on being useful to decision-making for the primary audiences (Embassy Senior Management, DFAT Activity Manager, The Asia Foundation (TAF) executive in Timor-Leste, TAF Nabilan program team, and DFAT gender equality and GBV stakeholders) as to the remainder of Phase III and looking to Phase IV.

- Constructive: This evaluation had a strong forward-looking focus on maximising the value and effectiveness of those investments into the future. Findings and recommendations are intended to be evidence-based and actionable.

- Mixed methods and evidence-building: This approach triangulates information from a variety of sources, such as the review of key program documents and reports and consultation with stakeholders both in-person and remotely. The evaluation validates, updates and strategically builds on the existing Nabilan evidence base, recognising that this is a mature program with prior and ongoing investment in research, monitoring and evaluation.

- Contextual and strengths-based: The evaluation approach recognises that Nabilan is a mature program with 10 years of history, and itself builds upon a rich history of feminist organising and community-based and CSO VAWC service delivery in Timor-Leste, as well as global good practice.

- Culturally appropriate: The evaluation approach sought to create an environment of sharing experiences and feedback without restraint. We worked as a closely collaborative multicultural evaluation team and looked to build rapport and spend time with local stakeholders. We saw work firsthand and used a variety of methods (including participatory) to engage stakeholders in candid conversation. We also worked primarily in Tetum, with some limited translation.

- Aligned with DFAT and global standards and best practice: Our approach to GEDSI aligns with DFAT’s good practice note,1 and our evaluation approach is aligned with DFAT’s Design and Monitoring Evaluation and Learning Standards, Ethical Considerations for Research and Evaluation on Violence Against Women and Girls Guidance, and Child Protection Guidance Note: Child Protection in Violence Against Women Programs.2 We also looked to broader accepted sectoral approaches to undertaking research and evaluation in the context of interventions focused on gender-based violence, particularly the World Health Organization’s (WHO)’s3 Ethical and Safety Considerations for Intervention Research on Violence Against Women (including the paramount principles of safety of evaluation participants and do no harm). Moreover, we recognised and sought to meet DFAT’s requirements for this mid-term review reporting to be high-impact, accessible, clear and succinct, as outlined in the TOR.

Further, Strategic recognised that the Nabilan Phase III program is guided by a set of principles. We translated those principles to further elaborate our evaluation approach. This was contained in the full Evaluation Plan.

### Data collection methods

The MTR team used a range of data collection methods, each suited for different purposes and respondents. The data collection method for each KEQ was selected primarily for the depth of information likely to be required, the respondents’ familiarity and closeness to the program, and to ensure a balance of tools and sources given the resources we set aside for this component of the review.

#### Primary Data Collection

Primary data collection used key informant interviews, workshops, and site visits.

| Method | Response time | Number |
| --- | --- | --- |
| Key Informant Interview (KII) | 1 hour | 38 in total |
| Case study workshop with Nabilan team | 1 hours | 1 |
| Site visit (structured observations, KIIs, partner workshops) | 2 hours – 2 days (depending upon site and number of partners) | 4 sites (Dili, Suai, Manufahi, Baucau) |
| KOKOSA! community change workshops | 3 hours | 2 sites (Dili, Manufahi) |
| Professional roundtables | 40 minutes to 1 hour | 7 in total (with TAF and with PRADET) |
| Partner participatory analysis workshop | 3.5-4 hours | 1 (Dili) |
| Partner online survey (Tetum) | 10-15 minutes | 14 responses representing 8 of 10 grantee partners |

#### Secondary Data Collection

The MTR team reviewed documents (over 50) supplied by the Nabilan team and Post, including regarding design, MEL and implementation of the program, reporting at program and activity level, evaluations, program research, and other program collateral including communications products. Program data was examined for relevance to responding to the KEQs, particularly in terms of the Effectiveness questions.

### Data analysis methods

#### Qualitative analysis

Qualitative coding

Qualitative data (including secondary sources) was topically and analytically coded in terms of themes, outcomes and criteria aligned with the KEQs. The MTR team used a combination of pre-determined codes and emergent coding, allowing for unexpected results to be surfaced in the process of data analysis.

Triangulation of data

We used a tried and tested method of organising our data from all sources into an MS Excel Evidence Table, which tags lines of data (evidence) against KEQs. All data arising from primary and secondary data sources/methods was entered into the Evidence table and tagged. This allowed the team to sort through the evidence repository from all data sources, triangulate findings and assess the strength of the evidence as a result. This method of data management and analysis reduces subjectivity in developing findings and produces an evidence trail to justify findings and recommendations.

Case studies

Two case studies were selected for deeper investigation and analysis based on their relevance in answering the KEQs and included in Section 2.6: Impact. The sampling approach here is purposive.

Expert Insights

The MTR team also draws upon their skills and knowledge to make insights and recommendations as a result of their experience with relevant programs, sectors and processes in the Asia-Pacific region and wider global context.

Evaluation Questions and Lines of Inquiry

| Evaluation criteria (OECD-DAC +) | Key evaluation questions | Lines of inquiry |
| --- | --- | --- |
| Relevance Is the intervention doing the right things? | - To what extent does the design of Nabilan Phase III respond to what is needed and valued by its beneficiaries and partners (East Timorese women, children and communities; civil society partners; GoTL) in the current context? | - To what extent does the Phase III design respond to a careful analysis of beneficiary needs and priorities? (including an intersectional gender and power analysis; an understanding of the forms and patterns of VAWC in country) - To what extent does the Phase III design provide opportunities for responsiveness and adaptation to changing needs, priorities and contextual factors? How may this support moving into the second half of Phase III and looking to Phase IV? (including building on the Phase II evaluation and feedback from partners and beneficiaries; changes in the environment; any backlash factors) - At this mid-term point, to what extent does the design have enduring relevance to stakeholders in the current context? |
| Relevance Is the intervention doing the right things? | - To what extent does the design of Nabilan Phase III incorporate a well-defined program theory and align with international best practice and evidence for preventing and responding to violence against women and children? | - How does the program use evidence (internal and external) to support design, planning and adaptation? - How does the program theory describe the intended changes/outcomes and the mechanisms and pathways to achieve this? - To what extent does the Phase III design align and compare with key tenets of international best practice in the field? - What are the opportunities for strengthening the design into Phase IV? |
| Coherence How well does the intervention fit? (internal and external systems change) | - How well do the various components, projects and actors in Phase III complement and support each other to achieve the end of program outcomes | - Are there established mechanisms for regular collaboration, sharing, communication, learning and coordination between project, partners and stakeholders (including the GoTL, other programs at Post and UN agencies)? How else has collaboration occurred and to what effect? - Is there an appropriate coverage, balance and resourcing of different program components and projects to support realisation of the two EOPOs? - How well do partners understand their roles in contributing to the overall program? - To what extent can Nabilan partners be considered a network or connected ecosystem? - To what extent does Nabilan encourage stakeholders to work in a coordinated way to improve safety for women and children experiencing violence? - How do interactions within the program—such as between projects or partners—create opportunities to drive progress and enhance impact? - What are the opportunities for further consolidating program coherence? |
| Coherence How well does the intervention fit? (internal and external systems change) | - To what extent is Nabilan Phase III designed to effectively contribute to broader systems change for ending violence against women and children in Timor-Leste? | - How does the design of Nabilan Phase III align with and support national policies, strategies, and action plans for ending violence against women and children? - What are the specific pathways, mechanisms or strategies through which the program aims to influence broader systemic factors, such as laws, policies, resourcing, institutional capacities, strengthening referral networks, the work of other international actors, or social norms? (This may include engagement with stakeholders across sectors, fostering feminist leadership, activities to enable advocacy, fostering partnerships and collaboration with other actors, sharing learning or coordinated action within the broader EVAWC sector and supporting integration with other sectors) - Is Nabilan’s technical support to and engagement with GoTL enabling systems influence? - What are the opportunities for further leveraging systems change? |
| Effectiveness Is the intervention achieving its objectives? | - Two years into Phase III, to what extent is the program being implemented as planned, with the expected quality, and is it meeting its objectives? | - To what extent have the expected Phase III mid-term outputs been delivered and milestones and targets met? Does this reflect implementation plans? - What are the barriers and enablers to effective implementation in Phase III? - Where are the strengths, gaps and areas for improvement in Phase III implementation that can be considered for the final period and into Phase IV? - How are newer programming elements (such as the primary prevention activities and incorporation of a focus on VAC) tracking? - Is the program MEL framework and approach appropriate and supportive of an effective program? - To what extent does Phase III exemplify a high-quality EVAWC program in Timor-Leste, and what specific factors contribute to or detract from its quality within this context? - To what extent have the Phase III mid-term outcomes been realised? (including to what extent are there indications of GoTL making decisions influenced by Nabilan?) |
| Effectiveness Is the intervention achieving its objectives? | - How effective and appropriate are Nabilan’s modality and partnership approaches in delivering the program’s intended value? | - How may Nabilan’s current modality and partnership approaches be described? - How effective and appropriate is it that the program continues to be embedded in TAF? What does the program gain by this? How effective are the arrangements and ways of working between DFAT and TAF? - To what extent does the modality enable engagement with GoTL, and how? - To what extent does the modality support the GoA’s priorities and bilateral relationship with GoTL? - How is Nabilan’s partnership approach received, by partners themselves and other stakeholders including GoTL? - What are the opportunities for improving and maturing the program modality and partnership approaches? |
| Efficiency How well are resources being used? | - How well are program resources being used to govern, manage and deliver Phase III? | - To what extent are available resources being used to best effect? - Does the program modality represent value for money? - To what degree is there good governance and management of the program? - To what extent is program research, monitoring and evaluation used well to support program management and improvement? |
| Impact What difference does the intervention make? | - What changes has Nabilan Phase III produced in the context of violence against women and girls in Timor-Leste? | - To what extent is the program on track to contribute to its End of Program Outcomes (EOPOs)? - What has been the effect of Nabilan’s Phase III support on partner organisations and communities? - Are there key achievements or examples of systems change or strategic influence that Nabilan III has enabled? If so, how have these occurred and what can be learned? - In which other ways, if any, has Phase III contributed to ending violence against women and children and promoting gender equality, how, and for whom? Including increasing women’s and children’s safety. - What changes are most valued by beneficiaries, partners and stakeholders, and why? - Are there any unintended consequences (positive or negative) of Phase III? |
| Sustainability and maximising future value Will the benefits last? What should we do differently/ next to improve the program? | - At this mid-point, to what extent are the foundations being laid for the sustainability of Nabilan’s outcomes and value during and beyond Phase III? What factors are influencing this potential sustainability? | - What lessons can be learned from Phase III about scaling and expansion to inform future phases of the program? Has the scaling and expansion of the program's scope in Phase III introduced any risks or negative impacts on sustaining the outcomes achieved in earlier phases? - Are resources sufficient to realise and sustain a high-value program? - To what extent may sustainability be affected by the GoTL’s tightening fiscal environment and how could the program respond? - How is the Nabilan program enabling long-term sustainability through fostering East Timorese leadership and power-sharing? |
| Sustainability and maximising future value Will the benefits last? What should we do differently/ next to improve the program? | - What improvements, changes, or additions would help maximise the program’s value for the remainder of this phase and in the next phase? What other considerations should inform future design? | - What Phase III strengths or leverage points can be built upon? What gaps, weaknesses or sustainability considerations should be addressed and how? - To what extent are intended Phase IV priorities relevant and feasible? How may they be prioritised? - To what extent is Phase III responsive to different forms and impacts of VAWC (including violence against women with disability, technology-facilitated abuse, violence against children), and what are the opportunities here for Phase IV? - Are there any other innovations or emerging evidence in the EVAWC space that could be leveraged for the next phase? - Are there any emergent changes in the broader system or sector (such as the proposed Prevention Organisation; the planned high speed internet cable to Timor-Leste) that the program should be attendant to? - What are the associated resource implications of any suggested changes? |

Annex 3 – Stakeholder Consultations

In addition to two community participant workshops with KOKOSA! participants from Dili and Manufahi (15 participants per workshop), the MTR team engaged the following stakeholders in 38 Key Informant Interviews and seven professional roundtables:

Government of Timor-Leste

| No. | Organisation | Name | Position |
| --- | --- | --- | --- |
| 1 | Ministry of Social Solidarity and Inclusion (MSSI) | Manuela Oliveira | National Director (Diretora Direção Nacional de Reincerção Comunitária) |
| 2 | MSSI | Joana Almeida | Chief of Department of Child Protection |
| 3 | MSSI | Hermina Felix Gusmao | Chief of Department of Social Protection for women |
| 4 | SEI | Armando da Costa | Director General |
| 5 | VPU – PNTL | Ricardo da Costa | Commander VPU Nacional |

Service Partners

| No. | Organisation | Name | Position |
| --- | --- | --- | --- |
| 6 | Sentru Esperansa Uma-Mahon Salele | Me. Santina Imaculada de Oliveira | Director |
| 7 | PRADET in Dili | Manuel dos Santos | Director |
| 8 | PRADET in Dili | Luisa Marcal | Coordinator |
| 9 | PRADET in Dili | Cristina Ximenes | Volunteer doctor |
| 10 | PRADET in Dili | Cristina Alves | Counsellor and examiner |
| 11 | PRADET in Dili | Natercia Soares Goveia | Counsellor |
| 12 | PRADET in Dili | Maria Zulmira | Economic empowerment officer |
| 13 | PRADET in Dili | Hortensia de Fatima Marcal | Counsellor and examiner |
| 14 | PRADET in Baucau | Joana da Costa | Coordinator |
| 15 | PRADET in Manufahi | Vicente dos Reis | Senior Program Officer (Dili & Manufahi) |
| 16 | PRADET in Manufahi | Maria de Jesus | Program Staff |
| 17 | PRADET in Manufahi | Celestina de Deus Martins | Responsible for KOKOSA! in Same |
| 18 | PRADET in Manufahi | Francisco Neves | Program staff/Community facilitator |
| 19 | PRADET in Suai | Cariana Elsa B. Amaral | Counselor and Coordinator |
| 20 | PRADET in Suai | Marcelina da Conceicao | Finance |
| 21 | ALFeLa in Dili | Marcelina Amaral | Director |
| 22 | ALFeLa in Dili | Olandina Cardoso | Program Manager |
| 23 | ALFeLa in Baucau | Alexandrinha de S. Soares | Lawyer |
| 24 | ALFeLa in Baucau | Maria Secundina Moreira | Legal Official |
| 25 | ALFeLa in Baucau | Francisco Salvador | Legal Assistant |
| 26 | ALFela in Suai | Escolastico C.N. Maia | Lawyer |
| 27 | FOKUPERS Dili | Domingas Afonso Amaral | Director |
| 28 | FOKUPERS Dili | Mercia Lopes | Director |
| 39 | FOKUPERS Suai | Maria Madalena | Coordinator/Counsellor |
| 30 | FOKUPERS Suai | Antonia de Jesus | Counsellor |
| 31 | JSMP | Casimiro dos Santos | Acting Director |

Prevention Partners

| No. | Organisation | Name | Position |
| --- | --- | --- | --- |
| 33 | FMDC | Francisco Gari | Director |
| 34 | FMDC | Dhesy Reis | Program Manager |
| 35 | Estrela+ | Ines Sarmento Lopes | Director |
| 36 | HAMNASA | Agostinha Cardoso | Program Manager |
| 37 | HAMASA | Lourenco | Program Performance Manager |
| 38 | CODIVA | Romiyati Barreto | Director |
| 39 | CODIVA | Julio do Carmo Amaral | Program Officer |
| 40 | HDS | Leo Dos Santos | Director |
| 41 | HDS | Dircia Costa | Program Manager |

BAHM Alumni

| No. | Organisation | Name | Position |
| --- | --- | --- | --- |
| 42 | CBRNTL | Norberta Soares | Director |
| 43 | Key Population | Zizi Belo | Counsellor |

NeNaMu Alumni

| No. | Organisation | Name | Position |
| --- | --- | --- | --- |
| 44 | Alumni (volunteer at TAF) | Fracisca Jesuina | Volunteer |

The Asia Foundation (TAF)

| No. | Organisation | Name | Position |
| --- | --- | --- | --- |
| 45 | TAF | Country Representative | Hector Salazar Salame |
| 46 | TAF | Xylia Ingham | Nabilan Team Leader |
| 47 | TAF | Lizzie Adams | Prevention Manager |
| 48 | TAF | Johana P. Shinta Dewi | Deputy Team Leader, Services |
| 49 | TAF | Maria Veronika | Deputy Team Leader, Prevention |
| 50 | TAF | Faustina da Costa | Program Officer, Services |
| 51 | TAF | Nivea Saldanha | Technical Coordinator Prevention |
| 52 | TAF | Helio Afranio S. Xavier | Technical Coordinator Prevention |
| 53 | TAF | Maria F. S. dos Reis Afonso | Associate Technical Coordinator |
| 54 | TAF | Elisabeth dos Reis | M&E Officer |

DFAT/Australian Aid

| No. | Organisation | Name | Position |
| --- | --- | --- | --- |
| 55 | DFAT-Post | Rebecca Dodd | Counsellor for Human Development |
| 56 | DFAT-Post | Felicity Errington | First Secretary, Gender Equality and Disability Equity |
| 57 | DFAT-Post | Gizela Carvalho | Senior Coordinator, GEDSI |
| 58 | DFAT-PHD | Melinda Mousaco | Director |
| 59 | DFAT-Partisipa | Annie Sloman | GEDSI and Performance Director |
| 60 | Timor-Leste Police Development Program | Detective Superintendent Darren Boyd-Skinner | Senior Responsible Officer |
| 61 | Timor-Leste Police Development Program | Detective Sergeant Julie Horgan | GEDSI Advisor |

Development Partners

| No. | Organisation | Name | Position |
| --- | --- | --- | --- |
| 62 | UN Women | Nuntana Tangwinit | Programme Specialist, EVAWG and WEE |
| 63 | UNICEF | Gizela Moniza da Silva | Child Protection Officer |
| 64 | UNFPA | Dra. Domingas Bernado | Assistant Representative/Head of Programmes |
| 65 | UNFPA | Dircio Francisco Xavier Fatima | Programme Analyst for Gender and Youth |

Global Prevention Partners and others

| No. | Organisation | Name | Position |
| --- | --- | --- | --- |
| 66 | Independent consultant | Veronica Tilman | Consultant, disability inclusion |
| 67 | The Equality Institute | Xian Warner | Research and Partnerships Manager |
| 68 | Raising Voices | Olive Nabisubi | Technical Advisor, SASA! |
| 69 | Raising Voices | Grace Ikirimat Odeke | Technical Advisor, SASA! |
| 70 | The Salamander Trust | Ellen Bajenja | Technical Advisor/Trainer, Stepping Stones |

Annex 4 – Alignment of Nabilan’s Phase III design with global good practice principles

| Key dimensions of strong EVAWC program design | Aligned Nabilan Phase III design elements |
| --- | --- |
| Works at different levels of the socioecological framework – from individual, interpersonal, family, community, organisational, institutional and system, and societal – across structures, norms and practices | - Incorporates a range of interventions pitched at different levels, such as NeNaMu, KOKOSA! and BAHM (individual, relational, family, community; attitudes, norms and behaviours) and working with CSOs (organisational) and government actors, policies and systems (system and institutional) - Works to support diverse forms of social institutions and organisations – including local communities, civil society and state actors – and the interlinkages between them |
| Holistic; working across and connecting response and prevention (or the prevention spectrum) | - KOKOSA! and NeNaMu can be considered primary prevention interventions, working at a whole-of-community level to address the drivers of male intimate partner violence against women in particular - The Positive Parenting programs may be considered to align with an early intervention model, supporting the change to the trajectories of people at higher risk of perpetrating and/or experiencing violence (for example, ex-prisoners returning to a family context upon release) - Response and recovery – the program supports victim-survivors in their acute needs period and, in more limited ways (for example through the longer-term shelters), to support victim-survivors to heal and thrive over the longer-term |
| Addressing different forms of violence | - The program design is clear that it is intended to focus on both partner and non-partner violence against women, and on different forms of violence against children - Support for addressing family and partner violence against LGBTIQ+ people is enabled through the partnership with CODIVA - There is a stated intention to continue to improve the program’s focus on violence against women with disabilities, including specific forms and impacts of violence - There is room to be more specific about which forms of violence experienced by whom are addressed through different interventions |
| Prioritises feminist ethics and ‘do no harm’ | - Program principles |
| Support for an intersectional feminist and decolonising leadership model | - This is apparent through the inclusion of the BAHM intervention (and its most recent phase which included significant participation of people with disabilities), the partnership and sustainability model, and the stated intention to continue to elevate Timorese program leadership |
| Intersectional in its conceptualisation of who is experiencing what kinds of violence and the differential impacts and drivers | - As above, there are indications (including through ongoing disability inclusion consultations and considerations, and through the partnership with CODIVA) of program design interest in considering violence against LGBTIQ+ people and women with disabilities |

Annex 5 – Opportunities to strengthen Nabilan’s Theory of Change

| Gap | Opportunity |
| --- | --- |
| Limited systems theory: - The ToC separates prevention from services and does not adequately show the nodes of interaction between program components or strategic systems leverage points it supports, i.e. it is not sufficiently conceptualised and represented as a systems-level intervention - The ToC does not sufficiently place Nabilan’s systems-level intervention within a broader systems analysis – including the bigger EVAWC ecosystem of organisations and civil society actors (in Timor-Leste and globally), and within the context in Timor-Leste (with global influence) that drives VAWC | - A systems overlay to the ToC which conceptualises and demonstrates how the program both creates nodes of interaction between the program interventions and pillars, and how it leverages key systems opportunities (or leverage points) - Visually demonstrate and describe how Nabilan both nests within and contributes to the Timor-Leste and global EVAWC ecosystem, and responds to a Timor-Leste current context. This could be accompanied by future-mapping ToC that articulates key forecast changes to the context (including the high-speed internet) and how that may affect VAWC patterns and change pathways |
| Articulation of the change theory/theories (such as GBV program theory including socioecological model and timescales, social norms theory, feminist leadership theory) and the program evidence bases (such as for SASA! and Stepping Stones) that underpin why Nabilan has been designed the way it has to achieve change. That is, the theory and global evidence behind why Nabilan has decided to focus on what it has and why it is likely to create change. | More direct reference to the global literature and to key tenets of feminist, GBV and social norms theory to support articulation of why Nabilan is likely to create meaningful change. |
| Relatedly, a clear explication of the theory behind responding to/preventing VAW and responding to/preventing VAC, where the overlaps and differences may lie, and what the evidence says is useful to respond to and prevent different forms of VAC. | It would be useful for the ToC to explain common drivers and risk factors driving both VAW and VAC, where there are intersections and potentials for polyvictimisation, and any specific considerations, including for certain forms of, and life course risk periods for, VAC. For example, currently the VAC aspect of the program is focused on preventing child maltreatment by parents, and responding to sexual, physical, emotional and psychological violence experienced by children (including incest), as well as children witnessing violence particularly toward mothers. It would be useful for this to be made clearer in the program theory. This would further enable the program to be clearer as to how and in which ways it is addressing VAC, and where there are opportunities to expand/deepen this focus. At present the design does not give a clear strategic focus to articulating the addressing of VAC; rather it discusses certain interventions and activities. |
| A strong visual/s and an accompanying narrative. Currently the program ToC is a simple outcomes hierarchy and while there are detailed descriptions of program components, there is not a succinct narrative description of why the program is likely to create change. | The existing ToC visual representation could be supplemented by more creative visuals (including potentially using the services of an illustrator) that demonstrate the nodes of interaction within the Nabilan program and into the broader EVAWC ecosystem. There is also an opportunity to represent the broader Timor-Leste context in which VAWC occurs and describe the roots of the problem. The program could seek to ‘storify’ the illustration of the program theory. The theory of change should be accompanied by a coherent, succinct story that articulates how Nabilan creates change. |
| Bringing together activities/strategies/key interventions and outcomes with the middle link – mechanisms of change. The current ToC does not demonstrate a connection between the interventions and other strategies used to create outcomes, and the mechanisms of change that produce the outcomes from the program strategies. | For example, the ToC could identify that mechanisms of change such as: if the Nabilan program works intensively and in staged ways over a period of time in certain communities, using a robust, tested methodology and benefits-based approach, in time community members will move to recognition of VAWC as a problem and their own power to shift that, and will positively transform harmful social norms and unequal power relations to prevent VAWC (for example, from male sexual entitlement to, and objectification of, women’s bodies and control of women, to right to agency and consent and women as possessing equal rights to men). |
| Being clear on how intervention-level ToCs nest within the whole-of-program. | Linking up ToCs at multiple levels and visually demonstrating how they nest/cascade. |

Annex 6 – Achievement against intended implementation plan, Phase III

| EOPO/Pillar | MTO | Intended activities (high-level summary) | Achievement | Evidence informing rating rationale |
| --- | --- | --- | --- | --- |
| EOPO1: Services | 1.1 Women and children have access to support services (medical, psychosocial, legal, shelter) | - Ensuring continuity of essential VAWC services, including direct funding of VAWC services and working with MSSI on standard-setting and monitoring for service quality - Providing training for first responders (health workers, community leaders, police) on how to identify and refer victims | Excellent | All major activity areas achieved: - Core funding and technical support (including case documentation, quality standards improvement and training) as intended to 4 services partners (ALFeLa – legal aid, PRADET – crisis shelter, medical forensic examination, medical treatment and counselling, FOKUPERS – shelters for women and children and CEF-UMS – shelter for women and children), across 13 offices in 5 municipalities - Trainings delivered to police, healthcare workers and university students - Medical forensic examiner accreditations undertaken |
| EOPO1: Services | 1.2 Social workers are professionalised and have increased capacity to support clients | - Building the capacity of all social workers to ensure delivery of high-quality, holistic, trauma-informed care, including delivering Certificate III in Social Services, training in counselling skills - Building the capacity of social workers to support vulnerable children and families, including delivering play therapy training for service providers, piloting play therapy, and providing training on child development and child protection - Supporting professionalisation of the social work sector and wellbeing of workers - Engaging MSSI on standard setting and quality assurance for the sector | Good | While there has been good achievement in most of these areas, this stream of activity has experienced some challenges, including: - The change of government and a shift in MSSI wanting their own, similar Certificate III (community services) and for the Certificate III to be delivered through an accredited delivery organisation impeded progress on delivery of the next round of the Certificate III Social Work - While play therapy has been introduced and tested, the Nabilan team and partners surfaced shared concerns that it may be too demanding and sophisticated, and lacking in appropriate clinical supervision supports in country, to be applied as a whole model. The Nabilan team has therefore adjusted to an approach of shoring up the fundamentals of age-appropriate child engagement and protection and including play therapy techniques as part of supporting child clients. |
| EOPO1: Services | 1.3 GoTL uses evidence to develop policies, plans and budgets to respond to violence against women and children | - Providing technical support and advocacy to the GoTL, particularly on the NAP-GBV strategies and accompanying annual implementation plans - Updating the detailed services costing study to ensure future investments from GoTL and other donors meet emerging needs and are sustainable - Conducting joint advocacy on gender and disability issues with PHD through existing mechanisms | Good | - While some challenges have been experienced in government engagement (particularly in terms of MSSI) with the change of government during this phase, key activities under this stream of work have largely progressed. - Nabilan is responsive to MSSI’s annual workplans and other requests for support, and has supported revision and finalising of the GBV case management SOP. - Costings analysis has been undertaken and updated, and in 2022 Nabilan supported SEI to revise the Law against Domestic Violence and the Penal Code to include new provisions, including on incest. - Nabilan has also conducted and commissioned thorough reviews of the access of women with disabilities to essential VAWC services – these will inform next steps including advocacy. - The program has also been responsive to PNTL training requests. |
| EOPO2: Prevention | 2.1 Participant parents/caregivers practice positive parenting | - Provision of technical support to VAC prevention partners to implement parent and caregiver interventions to reduce violence in family settings | Excellent | - During Phase III, two partners were secured for the positive parenting initiatives – HAMNASA and HDS. - Two rounds of community-based implementation of positive parenting have taken place with HAMNASA, following adaptation and testing, and a process evaluation has taken place. - A pilot of a positive parenting course with eligible incarcerated men is currently underway with HDS. |
| EOPO2: Prevention | 2.2 Target communities have reduced accepted of violence against women and children and have increased skills to address these issues | - Provision of direct funding and institutional strengthening support to prevention partners - Provision of technical accompaniment to partners for implementation of evidence-based prevention interventions, KOKOSA! and NeNaMu | Excellent | - Funding, training and technical accompaniment provided to 7 partners: PRADET (KOKOSA! in Dili and Manufahi, CODIVA (promoting LGBTIQ+ rights), FMDC (KOKOSA! radio programming), JSMP (court monitoring and advocacy), HAMNASA (couples-based positive parenting), HDS (prison-based positive parenting with men only) - KOKOSA! communities successfully transitioned from Awareness to Support phases, following end of phase evaluations testing readiness to transition. Communities are on track to enter Action phases in 2024. Over 400 activities undertaken, including poster discussions, community conversations, deeper discussions with couples, leader quick chats and communities meetings - NeNaMu was adapted to respond to learning following a process evaluation in 2022, which pointed to the need for careful attention to factors such as facilitator training, curriculum fidelity, participant retention and session modality. With new partner Estrela+, non-Dili-based locations were chosen for the second and third implementations (Sabuli in Metinaro and Ulmera), in part to avoid conflict with people’s other work and activities which tends to be a barrier to participation and retention in the busy urban environment of Dili. - Some partner challenges have been experienced in Phase II resulting in a change of Dili KOKOSA! implementation partner from CODIVA to PRADET at the start of Phase III, and support for PRADET in Manufahi. The previous NeNaMu partner, Marie Stopes Timor-Leste (MSTL), chose to exit the partnership due to a shift in country strategy, and Estrela+ has been successfully brought on board as the new NeNaMu partner. Prior to implementation in Sabuli, Nabilan supported Estrela+ to co-facilitate and test the approach with three cohorts from Estrela+’s HIV peer support volunteers and youth networks. |
| EOPO2: Prevention | 2.3 The prevention of VAWC sector (in Timor-Leste and the region) has increased capacity to implement effective interventions | - Supporting the VAWC sector and feminist movement, feminist leadership initiatives, funding and training for feminist groups and activists, including through BAHM - Supporting the establishment of a peak Timorese VAWC prevention body - Providing training to SEI on effective prevention approaches and integration into other sectors - Conducting and disseminating high-quality research and evaluations on what works to prevent and respond to violence against women and children | Good | - During this phase, BAHM rounds 2 and 3 have been undertaken and evaluated, including considerable positive lessons-learning on intersectionality and inclusion. Nabilan is providing ongoing support to BAHM round 3 participants as they implement strategies and undertake activism. - While strong support has been achieved for supporting the VAWC sector and feminist movement, SEI training has been provided, and the Nabilan team has had a good track record of undertaking formative research and evaluation during this Phase, progress has not been as strong in terms of progressing the proposed Prevention Organisation. |

Annex 7 – Examples of Nabilan’s systems impact

| Program element | Systems change leverage point | Evidence indicating impact |
| --- | --- | --- |
| Alignment with GoTL policies, strategies and action plan – in particular, the NAP-GBV 2022-2032 and the case management SOP | - The goals of the system - Technical work, with potential for where the resources go (Muir) | - Government officials confirmed that Nabilan was a direct contributor to the NAP-GBV 2022-32 having a prevention focus, a timeframe of 10 years to support the long-term nature of prevention work, and enabling government to fully understand what is meant by and required for primary prevention. - Nabilan’s support for SOP revision, and then roll-out to CSO partners, is a practical example of policy influence in action. Service providers relayed that Nabilan’s support for this process has supported them to feel clearer about the expectations of them, apply those through clear procedures, and also to practically understand the roles and responsibilities of different players in the referral network. In Suai the MTR team heard from multiple service providers that their victim-centred ways of working with one another, with clear referral mechanisms, were more harmonious and effective thanks to Nabilan’s support. This shift has, importantly, also been underpinned by Nabilan’s investment in supporting actors to come together and build empathetic, supportive relationships with one another. That is, the focus is not only procedural and transactional but collaborative and peer-supportive. |
| Certificate III Social Work; BAHM Both in terms of the knowledge and capacity building, and the connections and network building | - Hearts and minds (Muir) - Self-organising systems structures - Mindset/paradigm | - BAHM evaluations and the MTR team’s engagement with BAHM alumni demonstrate the personal-transformative, connective and inclusive impact of the BAHM intervention in itself. - Importantly in terms of systems impact, the MTR team heard a recurring theme of individuals having accessed one of these initiatives, which reinforced what else they may have gained through Nabilan support in terms of application to their working practices. Moreover, it expanded their connections – both into the EVAWC ecosystem for the first time for some people, or into wider networks, such as social worker alumni. The relationship building is important for self-organising and sustainability beyond the direct control of Nabilan, as is the impact of a growing system of connected individuals with professional influence who have approached EVAWC work with a mindset reflective of key principles of Nabilan’s work. This includes victim-survivor-centredness, trauma-responsive self-care and stress management, acceptance of difference and an interest in inclusion, and a feminist interest in recognising transformative gendered and other power hierarchies. |
| KOKOSA!, NeNaMu, positive parenting, play therapy, BAHM | - Technical work (Muir) - Hearts and minds (Muir) - Self-organising structure - Mindset /paradigm | - Nabilan is investing in adapting, testing and supporting others to become skilled in robust, evidence-based interventions that have brought whole new ways of addressing VAWC to Timor-Leste. This expands the system possibilities with regard to EVAWC in Timor-Leste and builds a workforce of organisations and individuals with the skills to carry on this work into the future |
| Sustaining essential service provision | - Where resources go (Muir) | - Program analysis of national data from January to June 2024 demonstrates that 70% of VAWC cases attended to by essential service providers were managed by Nabilan-funded service providers |

https://www.oecd.org/en/topics/sub-issues/development-co-operation-evaluation-and-effectiveness/evaluation-criteria.html

https://www.dfat.gov.au/publications/development/timor-leste-nabilan-phase-2-independent-evaluation

Nabilan leadership team member, TAF roundtable.

TAF and DFAT, Nabilan – Phase Three Design, p. 9 and Annex A: Stakeholder Consultation List.

TAF and DFAT, Nabilan – Phase Three Design, p. 9.

The Equality Institute (2016), Understanding Violence against Women and Children in Timor-Leste: Findings from the Nabilan Baseline Study: Summary Report (English), TAF, p. 19.

https://www.lowyinstitute.org/publications/timor-leste-s-uncertain-future

https://steppingstonestorights.net/

Dart, J. and Tolmer, Z. ‘Agile Theory of Change for system change endeavours: A think piece’, Clear Horizon Community of Learning, https://learn.clearhorizon.com.au/, accessed 15 December 2024.

See for example Donella Meadows, https://donellameadows.org/archives/leverage-points-places-to-intervene-in-a-system/.

https://www.paulramsayfoundation.org.au/news-resources/is-systems-change-possible-how-do-we-put-it-into-action

Introducing routine collection of client experience and satisfaction data is something that could be considered in or beyond Phase IV. However, ethical risks and service providers’ capacity to facilitate safe data collection should be priority considerations. Shoring up service quality fundamentals is paramount in Phases III and IV.

https://www.civicus.org/index.php/media-resources/news/united-nations/geneva/5885-civil-society-has-played-a-critical-role-in-strengthening-democracy-but-civic-space-shortfalls-remain

https://www.betterevaluation.org/blog/illustrating-models-theories-change