# ANNEX 07 – NTT District Selection

This annex describes the process and criteria in selecting the districts in NTT. Considering that AIPMNH, AIPD and AIPHSS have all been working in a number of districts in NTT, district selection has taken into consideration the history of commitment and capacity of each district.

AIPMNH has been working in NTT from 2008 starting with three districts and covering a total of 14 districts since 2010. AIPD started in 2011 in four districts. AIPHSS started implementation in the same four districts as AIPD in 2013.

PERMATA district selection criteria are:

- Working where AIPD and AIPHSS are already working. This is in recognition that to achieve the outcomes that PERMATA is designed to achieve will require inputs from a governance program and that PERMATA will continue the sub-national activities currently under AIPHSS.

- Capacity and commitment of elected representatives (Bupati, DPRD)

- Capacity of potential government partners

- Population size

- Health status (particularly of mothers and newborns)

- Poverty levels

- Financial resources available through APBD, APBN, or other special funds.

Based on the above and particularly the consideration around government commitment and availability of other financial resources through APBD, APBN or other special funds, DFAT has graduated 4 of the 14 districts of AIPMNH and therefore from July 2014 there are only 10 districts of AIPMNH. While the 4 districts have graduated this does not mean that their MNH services are now optimal or that there is equality of access.  It is judged that these districts are most able to continue to improve their services without the assistance of AIPMNH. Some districts have also been discontinued due to ongoing lack of commitment and engagement.  Need for improved MNH services remains in such districts and they should be assessed again in the future as conditions may change.

The list of the districts in NTT and Australia’s supported programs is in table below.

|  | Districts | AIPMNH | AIPD | AIPHSS | PNPM GSC/MCC | Population | % of poor people |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Sumba Timur | 2008 |  |  | 2013 | 238,241 | 30.35 |
| 2 | Ende | 2008 |  |  |  | 267,262 | 20.71 |
| 3 | Sikka | 2008 |  |  |  | 309,074 | 12.83 |
| 4 | Sumba Barat | 2009 |  |  |  | 116,621 | 29.61 |
| 5 | Manggarai | 2009 |  |  | 2013 | 307,140 | 21.52 |
| 6 | Manggarai Barat | 2009 |  |  |  | 236,604 | 18.9 |
| 7 | Ngada | 2009 | 2011 | 2013 |  | 148,969 | 11.35 |
| 8 | Kota Kupang | 2009 |  |  |  | 362,104 | 9.41 |
| 9 | Lembata | 2009 |  |  | 2013 | 124,912 | 24.78 |
| 10 | Kab Kupang | 2010 |  |  | 2013 | 321,384 | 20.13 |
| 11 | TTS | 2010 |  |  |  | 453,386 | 27.53 |
| 12 | TTU | 2010 | 2011 | 2013 | 2013 | 238,426 | 21.56 |
| 13 | Belu | 2010 |  |  | 2013 | 370,770 | 14.54 |
| 14 | Flores Timur | 2010 | 2011 | 2013 | 2013 | 241,053 | 9.14 |
| 15 | Sumba Barat Daya |  | 2011 | 2013 |  | 302,241 | 27.71 |
| 16 | Manggarai Timur |  |  |  | 2013 | 263,786 | 24.59 |
| 17 | Rote Ndao |  |  |  | 2013 | 125,035 | 29.11 |

Based on the above considerations, the following table lists the Districts that are graduated from AIPMNH, the rationale and the ongoing needs of the Sister Hospital program.

| District | Rationale for graduation | Sister Hospital Program |
| --- | --- | --- |
| Kota Kupang | Good performance and the most able to continue to improve MNH services independently. | N/A |
| Kabupaten Kupang | Poor commitment and engagement and the population has access to Kota Kupang MNH facilities. | N/A |
| Sikka | Reasonable performance and the second most able to improve MNH services independently. | Continue support for billing system |
| Belu | Despite low AIPMNH input and engagement with the project, Belu has performed well and receives special funding as it is a national border area. | Discontinue |

Based on the process of assessing the context, achievements, and commitments of each district, it is proposed that PERMATA should work in the following districts:

| No | Districts | AIPMNH | AIPD | AIPHSS | PNPM GSC/MCC | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Sumba Timur | 2008 |  |  | 2013 |  |
| 2 | Ende | 2008 |  |  |  | Ende can be considered for graduation in 2015 although there are good practices that can be shared with other districts |
| 3 | Sumba Barat | 2009 |  |  |  | Sumba Barat hospital is also serving Sumba Barat Daya; therefore we need to keep this district if we work in SBD |
| 4 | Manggarai | 2009 |  |  | 2013 |  |
| 5 | Manggarai Barat | 2009 |  |  |  |  |
| 6 | Ngada | 2009 | 2011 | 2013 |  |  |
| 7 | Lembata | 2009 |  |  | 2013 |  |
| 8 | TTS | 2010 |  |  |  |  |
| 9 | TTU | 2010 | 2011 | 2013 | 2013 | While this district has been supported by many DFAT programs, there has been no engagement by the political leadership for a number of years. PERMATA MC will need to coordinate with DFAT, AIPD, and PNPM during inception whether to continue in this district |
| 10 | Flores Timur | 2010 | 2011 | 2013 | 2013 |  |
| 11 | Sumba Barat Daya |  | 2011 | 2013 |  |  |

BPS NTT: http://ntt.bps.go.id/index.php/en/poverty2/40-data/kemiskinan/428-poverty-line-number-and-percentage-of-poor-people-by-regency-municipality-july-2012.html accessed in October 2014