## Sheet1
ANNEX 6: ANNUAL WORK PLAN
L/F Ref | Detailed Activities | Month
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Project Start Up
6.1 | Recruitment of Project team | bar: Month 1 to Month 3
6.2 | Advocacy with the government on the project and MSI Programme
6.1 | Inception/ Induction training | bar: Month 1 to Month 3
6.3 | Site specific project plans | bar: Month 1 to Month 3
OUTPUT 1: Capacity of service delivery Teams to effectively deliver quality, client friendly SRH services
1.1 | Core technical training team (CTTT) established and trained | bar: Month 1 to Month 3
1.2 | Develop a set of integrated SRH guidelines (clinical + non-clinical) based on existing good practice | bar: Month 4 to Month 6
1.3 | Training of clinical service providers and outreach workers (SRH promoters and CBDs) to all service providers on integrated SRH guidelines including counselling | bar: Month 7 to Month 9
1.4 | CTTT create annual training plan and conduct annual competency assessments of clinical and outreach programme team. | bar: Month 7 to Month 9
1.5 | Ongoing coaching, mentoring and capacity building by CTTT through field based monitoring. | bar: Month 7 to Month 12
1.7 | Establish and implement client centred service quality and service marketing framework that is adapted to “local service standards” | bar: Month 8 to Month 9
1.8 | Train CIC staff in cost control and budget management. | bar: Month 4 to Month 6
OUTPUT 2: Men and women of reproductive age, youth and Sex Workers are making informed choices about seeking SRH information and service, including contraceptive choices.
2.1 | Baseline survey (preparation, conduct, analysis and report) | bar: Month 4 to Month 6
2.2 | Conduct gender analysis | bar: Month 1 to Month 3
2.4 | Identify and select SRH promoters | bar: Month 7 to Month 12
2.6 | Train SRH promoters | bar: Month 7 to Month 12
2.5 | Develop and modify IEC materials | bar: Month 7 to Month 12
2.6 | Training for youth peer educators in accessing youth populations and BCC methods. | bar: Month 7 to Month 12
2.8 | SRH Promoters conduct small group sessions with all target populations to promote safer SRH practices | bar: Month 10 to Month 12
2.13 | Community and MSIM identify and select CBDs | bar: Month 7 to Month 12
2.14 | MSIM train CBDs | bar: Month 7 to Month 12
2.15 | Ongoing CBD support and monitoring provided by CTTT | bar: Month 7 to Month 12
OUTPUT 3: Delivery of comprehensive SRH services (FP/birth spacing, STI, VCCT, ANC, PAC, ARH) through 4 integrated service delivery centres and community based service provision (monthly mobile clinics, community based distribution of contraceptives).
3.1 | Establish and equip 2 new fixed clinic facilities | bar: Month 1 to Month 6
3.2 | Upgrade equipment in the 2 existing clinics | bar: Month 1 to Month 6
3.3 | Establish 2 new mobile clinic facilities | bar: Month 1 to Month 6
3.4 | Fee service affordability survey for 2 new centres | bar: Month 1 to Month 3
3.5 | MIS data collected for all client presentations in all sites and updated monthly
3.6 | MSIM centres participate MoH/DoH National External Quality Assurance Scheme for HIV testing laboratory services | bar: Month 5; Month 11
3.7 | Yangon support office oversees procurement and supply management of all centres ensuring no pipeline rupture
OUTPUT 4: Building a more supportive operating environment through advocacy with the public sector and collaboration with PFHAB partners.
4.1 | Quarterly coordination meetings between PFHAB partners in Myanmar to share implementation progress and lessons learned. | bar: Month 3; Month 6; Month 9; Month 12
4.2 | Semi-annual coordination meetings between PFHAB partners in Australia to share implementation progress and lessons learned. | bar: Month 6; Month 12
4.4 | Participate in township level coordination mechanisms to share information and advocate for more collaboration on SRH issues | bar: Month 2; Month 5; Month 8; Month 11
OUTPUT 5: Public and private sector providers have improved their capacity for providing quality, more integrated, client friendly SRH services.
5.2 | Contribute to semi-annual technical updates through the Myanmar Medical Association’s Continuing Medical Education Programme of SRH issues to public hospitals, GPs and partner INGOs. | bar: Month 5; Month 11
OUTPUT 6: Project Managed efficiently and effectively
Risk Management
6.4 | Risk Assessment + Update of Risk Register | bar: Month 4 to Month 6; Month 12
Supervision, Monitoring and Evaluation
6.5 | Finalise Project M&E framework | bar: Month 1 to Month 3
6.7 | Quarterly monitoring visits to Project sites - Yangon Management Team | bar: Month 3; Month 6; Month 9; Month 12
6.8 | Technical assistance / monitoring visit by MSIA Programme Support Manager | bar: Month 6
Reports
6.9 | Monthly narrative and financial progress report (MSI internal)
6.1 | Quarterly narrative and financial report to AusAID (dependent on donor requirements) | bar: Month 3; Month 6; Month 9; Month 12
6.11 | Annual report preparation | bar: Month 12