Annex 9: Monitoring and evaluation Matrix

| Monitoring Activity | Measuring: (Logframe Reference) | Timing | Responsibility |
| --- | --- | --- | --- |
| Detailed M&E Plan | Overall Framework for Project M&E | Q1 | PFHAB Project Manager Support of International M&E Adviser |
| Baseline and Endline Survey | Changes in Target Population Knowledge (Output 2), Public and Private Sector Knowledge (Output 5) and behaviours (Purpose Statement) | Q2, Year 1 Q3, Year 5 | PFHAB Project Manager Support of the International M&E Adviser, Project Officer, local baseline and endline research team |
| Customer Satisfaction Exit Questionnaires | Client perception of the quality of MSI services (Output 1) | Ongoing with Quarterly review | Field teams responsible for collecting the questionnaires. Project Management Team review on Quarterly Basis. |
| Mystery Client Assessments | Project Management tool to verify the quality (technical and client friendliness) of MSI services (Output 1) | Every 6 months in all sites | Project Management Team responsible for organising Mystery Clients. CTTT and Project Management Team responsible for briefing mystery clients. Feedback from Mystery Clients assessed every 6 months by Project Management Team |
| On-site Staff Competency Assessments | Quality of MSI services - clinical and counselling staff capacity. (Output 1) | Annual for all staff. Q4 Years 1-5. | Clinical Trainer Supported by other members of the CTTT |
| Participation in MoH/DoH National External Quality Assurance Scheme Laboratory tests | Quality of MSI laboratory services (Output 3) | Q2 & Q4 Years 1-5 | MSIM Country Program Director (all MSI centres) in coordination with PFHAB Project Manager for PFHAB sites. |
| MSIM Core Monitoring Information System | Uptake rates of MSI services by target populations (Output 3) | Monthly provision of data from township to centre. | Centre in Charge of each clinic provides data to the PFHAB Project Manager monthly. PFHAB Project Manager summarise monthly for internal review and for inclusion in monthly report to MSIA Program Support Manager. Data provided to donor in quarterly progress reports. |
| Quarterly Narrative and Financial Project Reports | Summary of progress against workplan (all outputs) including progress on Output 4- building a more supportive operating environment. | Quarterly | PFHAB Project Manager Signed off by MSIM Country Program Director and MSIA Program Support Manager |
| Annual Project Reports | Summary of progress against annual workplan, resourced workplan for following year, updated risk matrix, annual audit results and updated family planning checklist | Q4 Years 1-5 | PFHAB Project Manager Signed off by MSIM Country Program Director and MSIA Program Support Manager |