	Policy Priority


	Strategy
	Implementing agency
	Performance Indicators
	Timeframe



Planning Long, Acting Short
The Government’s Policy Priorities for 2009-12 
	Governance

	Responsible macroeconomic and fiscal management
	Finalise and institutionalise new development budget process to better align resources to priorities.

Maintain prudent budget management practices at all levels of government.

Maintain sound and stable monetary Policy.

Pursue a higher real economic growth rate  


	MFEM/MPM
	· New Development Budget process implemented 

· Any deficit should not exceed 3% of the overall budget 

· Sustainable debt level in relation to GDP maintained

· Stable financial system maintained

· Maintain at least 5% average real GDP growth over the four-year period


	2010

ongoing

ongoing

ongoing

2009-2012

	
	Strengthen the legal regime governing the appropriation and use of public funds.
	MFEM
	· Revised PFEM Act presented to Parliament

· Finance Regulation 2.2 report submitted

· Compliance with PFEM Act and regulations enhanced

· Review of the whole taxation system completed
	2009

2009 

ongoing

2009

	
	Payroll Cost maintained at the manageable level

Adequate resources made available for operational expenditure.
	MFEM
	· Link between the PSC, Department of Finance and line Ministries strengthened 

· Financial Service Bureaus established

· Stronger control of payroll

· An increased proportion of government budget allocated for operational expenditure
	2009

2009 

2010

	
	Strengthen government procurement and disposal of assets


	MFEM
	· Contracts and Tenders Act and supporting procedures and practices Reviewed

· Development partners have more confidence in and use government processes to finance project related activities
	2009

2010



	Strengthen accountability and transparency in public offices and institutions.
	Revive the public accounts committee.
	MPM
	· Public accounts committee convened on a regular basis


	2009

	
	Implement recommendations of the Ombudsman Review Report

Develop or amend relevant laws to hold Political Leaders and bureaucrats accountable to their decision.
	MPM

MPM
	· Ombudsman Act amended to ensure Ombudsman reports can be used as evidence

· Capacity building program in place

· Leadership Tribunal established

· Laws enacted or amended
	2009

2010

2011

	
	Revisit government ability to pursue legal recourse for financial loss
	MJSW/MPM/MFEM
	· Government recovered at least 30% of outstanding financial losses
	ongoing

	
	Strengthen the capacity of the Auditor General’s Office.
	MPM/MFEM
	· Auditor General appointed

· Technical support program in place

· Active audit work program developed and implemented
	2009

	
	Review the performance of state owned entities (SOEs) and where necessary abolish or institute reforms as required

Abolish or Privatise non-performing SOEs


	MFEM/MPM

MFEM/MPM


	· Targeted SOEs reviewed and reformed 

· Government’s financial exposure to SOEs reduced

· SOEs Act Passed by Parliament

· Government shares in SOEs sold
	2009-2011

2009

2010

	Decentralisation through more effective utilisation of human resources
	Review Governance Structure and status of the six Provinces

Develop Urbanisation Policy to improve urban management


	MOIA/MPM
	· Role of the Secretary General strengthened 

· Coordination and Planning improved

· Decentralisation Act improved

· Minister declaration made on potential urban areas subject to physical planning Act

· Key positions in Province/Municipal be made permanent


	2010

2012

2009/10

	Stability of government
	Promote political stability 

Review Government Ministerial structure.


	MPM
	· Relevant Constitutional Review committee recommendations implemented.

· Political parties legislation passed by parliament

· Government Act Amended

· People’s Representation Acts Reviewed

· Government’s Ministry structure reviewed and rationalised
	2009 

2010

2012

	Strengthening of a Professional and Robust Foreign Services


	Institutional Strengthening of Foreign Services in line with Foreign Service Act

Explore opportunities to expand bilateral relations

Review Vanuatu’s membership to regional and international organisations

Facilitate appointment of Ni Vanuatu to foreign Missions 
	MOFA/MPM
	· Appointment of heads of missions made in accordance with the foreign service Act

· Technical cooperation agreement with non-traditional donors established

· Contribution to regional/international organisation rationalised in line with ESCAP review recommendations

· Legislations to accommodate career diplomatic services amended


	2010

2009

2010


	Land

	Equitable and sustainable development of land while ensuring the heritage of future generations
	Implement key recommendations of the national land summit especially sustainable utilisation of land by Ni Vanuatu.


Strengthen Land laws Act to increase transparency in land lease decisions. 

Strengthen the capacity of the MLNR to formulate and implement land policies and laws.

Promote sustainable environment
	MLNR

MLNR

MLNR

MLNR/MOIA
	· Land reform program implemented to ensure:

· Better-informed collective customary decision-making. 

· Participatory land governance. 

· More effective and efficient enabling services.

· More efficient utilisation of land resources 

· Law amended to increase transparency and reduce opportunities for corruption in the use of ministerial powers in land disputes.

· Government capacity to acquire land for public interest enhanced

· MLNR restructured to better cope with workload; increase resource allocation to MLNR

· EIA carried out in all development

· National Disaster management Plan implemented
	2012

2009-2010

2012

2009

Ongoing

	Infrastructure

	Reliable and accessible infrastructure services
	Strengthening the institutional capacity of MIPU 

Rehabilitate and maintain the national road network to facilitate economic growth and service delivery.


	MIPU
	· Capacity building program in place.

· Better infrastructure policies and implementation plans

· Resources committed to road maintenance expanded.

· Use of private sector and local communities for road works and employment creation in rural areas increased.
	2009

Ongoing

2009-2012



	
	Ensure vigorous telecommunications competition continues to drive lower prices and greater access
	MIPU/Telecoms Regulator
	· Permanent independent regulator established

· UAP Fund used to extend subsidised telecoms services to remote areas

· New telecommunications legislation presented to Parliament

· SPIN and E-Government programs successfully completed

· Competition in the telecommunications industry sustained.
	2009

2009

2010

Ongoing

	
	Ensure that power is more widely available at a fair price.

Explore/expand and invest on potential renewable energy sources. 
	MLNR/URA/MIPU

MLNR/URA


	· Utilities Regulatory Authority (URA) maintains effective regulatory oversight. 

· Power tariff reviewed. 

· Luganville concession re-tendered

· Access and rural electrification programs increased. 
	ongoing

2009

2009

2009 

	
	Improve shipping, wharf and storage facilities
	MIPU
	· Policy, legal, institutional and governance of the domestic shipping industry strengthened.

· Management and oversight of current stevedoring concession agreements improved.

· Strategy for long-term wharf and stevedoring services developed and embarked on.

· Feasibility study on the need to establish an inland ports completed
	2011

2011

2010

2010



	
	Expansion/Construction of new international airport

Upgrading of Domestic Airstrips

Review the Air services/upper air space agreement
	MIPU/MTBD

MIPU

MIPU/MTBD


	· Feasibility study completed.

· Airstrip identified and funding secured

· New agreements signed.
	2010

2010

2010

	Productive Sector

	Support the productive sectors as an engine for investment, economic growth and employment
	Improved Productive sector institutional capacities

Improve farmers’ access to markets and information 

Improve access to credit facilities through existing commercial and micro credit schemes

Institutional Strengthening of DARD, Fisheries, and Forestry Extension Services. 

Restructure and strengthen Quarantine Services to facilitate export growth

Provide institutional strengthening for livestock services

Implement recommendation of the review of Copra industry

Encourage Tourism as an important source of Foreign Exchange Earner


	MTBD/MPM

MTBD/MNBD

MTBD/MNBD

MAQFF

MAQFF

MAQFF/MLNR

MAQFF/MLNR

MTDB/MAQFF
	· Fully-fledged Department of Trade and Industry established.

· Information, market access and facilities, especially between and within Provinces improved

· Support to microfinance programs enhanced

· Capacity building program in place for DARD, Forestry and Fisheries extension services

· Capacity building program in place to ensure compliance with sanitary and phytosanitary requirements

· Organic certification program enhanced

· Cattle industry strategy and investment program developed

· Coconut industry rehabilitation program established

· Increased arrival of tourists and trickling effects to all communities
	2009

2010

2011

2010

2010

2011

2009

Ongoing

	Human Resource Development

	Ensure quality of education for all.
	Improve the quality of education.

Phase out compulsory primary school contributions and replace with increased grants direct to schools
	MoE


	·  Vanuatu education sector strategy implemented through SWAP

· Review completed with the view to established an education assessment and quality authority 

· System of approved school bank accounts established; supporting audit, training and public awareness programs are in place. 

· Compulsory school contributions replaced by increased grants direct to schools
	2009 

2009/10

2010 

2010

	
	Increase human resource capacity in critical areas for Vanuatu’s development
	MOE/MPM
	· National Human Resource Development Plan developed

· Scholarship priorities and selection management reviewed

· Government and donors contributions to scholarship increased 
	2010

2009 

2009-2012

	Create better environment for employment opportunities 


	Expand trade skills development

Expand seasonal worker and other overseas employment opportunities


	MOE and MYDT

MOIA


	· Number of certified technical and tertiary training institutions increased

· Range of credible technical and vocational training programs increased.

· New study facilities for Year 14 Francophone completed

· Continued growth and success of the RSE scheme with New Zealand

· Arrangements for seasonal labour scheme with Australia established

· Opportunities for skilled migration expanded

· Localisation policy enforced
	2011

2012

2009 

ongoing

2010



	Support and Strengthen holistic development of youth and the conduct and development of quality sports for all.  
	Improve access, quality, relevance, management and delivery of skills development for effective participation in national, regional and global markets

	MYDST


	· The authority over the Technical and Vocational education and training subsector is clarified and defined.

· Technical and Vocational Education and Training Act  developed and finalized. 

· National Policy and Strategic Action plan on Technical and Vocational Education and Training   developed and implemented.

· Youth Employment Opportunities plan developed and implemented

	2009

2010

2010/2011

2010

	
	Strengthen the capacity of the Ministry of Youth, Sport and Training
	MYDST
	· Management restructuring to a fully established and fledged  Ministry of Youth, Sports and Training 

· New Office facilities at National and Provincial HQs completed

· National Youth Strategic Plan 2009 – 2019 developed and implemented

· National Sports and Recreation Strategic Plan 2009 – 2019 developed and implemented

· National Youth Act developed and finalized

· National Sports and Recreation Act developed
	2009

2010/2011

2009

2009/2010

2010

	Health

	Investing in a Healthy Vanuatu
	Strengthen the capacity of the Ministry of Health

Strengthen the delivery of basic health services to all, in remote, rural and urban areas.

Vigorously control and progressively eliminate malaria from Vanuatu

Invest in training and supporting the health workforce, particularly nurses to staff rural facilities


	MOH
	· New National Health Policy and structure finalised and implemented.

· Achieved the following Millennium Development Goals:

· Reduced Child Mortality

· Improved Maternal Health

· Combat HIV/AIDS and Malaria

· Resource allocation to favour community health (away from central hospitals and administration) rebalanced

· Health Infrastructure improved

· Reach of essential health services to remote areas increased

· Immunisation levels increased, supply of essential medications to health facilities maintained

· By 2014, eliminate malaria from TAFEA, stop all deaths and decrease nation-wide incidence to 7/1000 from 23.3/1000 in 2007

· Numbers of nurses trained and engaged increased– staffing shortfalls at rural facilities reduced 


	2009 

2009-2012

2009-2012

2009-2012

2009-2010

2009-2011

2011

	Security

	Strengthen security and the rule of law.
	Strengthen the capacity of law enforcement agencies.

Institutional strengthening of the Ministry of Justice for effective oversight of judicial services


	MOIA/MJSW

MJSW/MPM


	· Public confidence in law enforcement agencies restored

· Law and order maintained

· National Strategy Action Plan for Justice Sector developed

· Backlog of outstanding criminal and civil cases reduced

· Construction of new correctional facilities completed

· Construction of new court house embarked on

· Review of security


	2009-2010

2009 

2009 

2010-2011
2009


Abbreviation
MLNR
Ministry of Land and Natural resources

MPM
Ministry of Prime Minister

MFEM
Ministry of Finance and Economic Management
MOE
Ministry of Education

MYDST
Ministry of Youth Development, Sports and Training
MOIA
Ministry of Internal Affairs

MJSW
Ministry of Justice and Social Welfare

MTDB
Ministry of Trade, Tourism and Business Development

MIPU
 Ministry of Infrastructure and public Utilities

MOFA 
Ministry of Foreign Affairs

MOH
Ministry of Health

MNBD
Ministry of Ni-Vanuatu, Cooperative and Business Development

MAQFF
Ministry of Agriculture, Quarantine, Fisheries and Forestry

URA
Utility Regulatory Authority

NBV
National Bank of Vanuatu 

� Although this is a governance issue, for monitoring purpose it is preferred to be under land section.





PAGE  
1

