DFAT Management Response to the Independent Progress Review (Mid-Term Review) of the Partnerships for Improving Education (PIE) program.

| Recommendation | Management Response |
| --- | --- |
| - Program resourcing - Bring forward the Phase 2 budget allocation to the current phase, so that AUD75m is available for the remaining years of Phase 1. [Ref. discussion in Context, KRQ 1, KRQ 2, KRQ 3, KRQ 4 and KRQ 5] | Agree. |
| - Strategic oversight and governance - Introduce a regular external strategic monitoring and advisory function. [Ref. discussion in Context, KRQ 1, KRQ 2, KRQ 3, KRQ 4 and KRQ 5] | Agree. This gives effect to PIE’s design which envisages a technical advisory group function to provide external oversight and direction. |
| - Program activity stock-take (and adjustment) - Undertake a program activity stock-take to decide on appropriate adjustments to program activities to improve effectiveness, efficiency, and sustainability. [Ref. discussion in Context, KRQ 2, KRQ 3 and KRQ 4] | Agree. PIE will undertake a program activity stock-take to inform changes to activity planning for the purposes of effectiveness, efficiency and sustainability. |
| - Refine the MERLA framework - Draw on the PIE MES Review and experience to date to refine the MERLA strategy and framework. [Ref. discussion in KRQ 2, KRQ 3, KRQ 4 and KRQ 5] | Agree. PIE’s MERLA framework will be strengthened to enhance relevance and meaningfulness, thereby accurately reflecting progress made to date. The framework will also be streamlined for the purposes of simplification and efficiency. |
| - Strengthen strategic communication - Increase the Program’s collateral and capacity for public diplomacy and policy influence. [Ref. discussion in KRQ 1, KRQ 4 and KRQ 5] | Agree. PIE will review and update its current communication strategy to strengthen Learning and Adaptation functions that build on existing MEL products. |
| - Adjust current provincial engagement - Review progress to date and prioritise next steps in each of the four provinces to account for local context and priorities, and progress and learning to date. [Ref. discussion in Context, KRQ 2, KRQ 3 and KRQ 4] | Agree. PIE’s Annual Work Plan should reflect variations in programming in each of the sub-national locations in which it operates, and prioritise strategies in approach depending on the sub-national context. |
| - Geographic expansion – PIE should not proceed to a 5th province in the short term. Rather expansion to other provinces should be driven by GoPNG, with PIE support, informed by a longer-term plan for expansion and consultation with other partners, including the World Bank. [Ref. discussion in KRQ 1, KRQ 4 and KRQ 5] | Agree. |