Loans 2368/8232 and Grants 0087/0101-SAM: Power Sector Expansion Project

ADTA 4494-SAM: Implementing the National Energy Policy

AIDE MEMOIRE

REVIEW MISSION

# INTRODUCTION

1	A review mission (the Mission) from the Asian Development Bank (ADB) visited Samoa from 13 to 19 February 2011 to review progress on (i) Loans 2368/8232 and Grants 0087/0101-SAM: Power Sector Expansion Project (Project), and (ii) ADTA 4494-SAM: Implementing the National Energy Policy. A list of persons met is included in Appendix 1. A wrap-up meeting was held on 17 February 2011 at Ministry of Finance (MOF). This Memorandum of Understanding (MOU) records the understandings reached between the Government and ADB.

# Mission findings

Loans 2368/8232 and Grants 0087/0101-SAM: Power Sector Expansion Project (PSEP)

2	The Project was approved by the Board on 21 November 2007, signed on 11 December 2007, and became effective on 19 June 2008. Loan closing is on 31 December 2016. The Project is being co-financed by Japan International Cooperation Agency (JICA) and the Government of Australia.

3	Contract Awards and Disbursements. The cumulative commitments and disbursements as of 16 February 2011 are detailed below:

| Fund Source | Loan/Grant Amount – Current Value ($ million) | Contract Awards ($ million) | % | Disbursements ($ million) | % |
| --- | --- | --- | --- | --- | --- |
| 2368-SAM (ADB Loan) | 26.548 | 16.001 | 60% | 5.288 | 20% |
| 8323-SAM (JICA Loan) | 38.000 | 22.185 | 74% | 7.880 | 21% |
| 0087-SAM (ADB Grant) | 15.390 | 6.282 | 41% | 2.620 | 17% |
| 0101-SAM (AusAID Grant) | 8.000 | 7.603 | 95% | 2.507 | 33% |
|  | 87.974 | 52.071 | 59% | 18.295 | 21% |

4	Between February 2010 and February 2011, contract awards rose from 10% to 59% and disbursements rose from 5% to 21%. Both contract awards and disbursements are projected to reduce in 2011, as presented in Appendix 2 and 3.

5	Loan Buy Down Mechanism. The Project includes a loan buy down mechanism of $4 million for conversion of loan to grant, funded by AusAID. A summary of progress towards the performance targets is presented below.

Table 1: Progress on the Loan Buy Down Mechanism Triggers

| Triggers | Progress |
| --- | --- |
| 1. Appointment of an independent technical and price regulator for the power sector | The Electricity Act was passed in December 2010. TA 4994-SAM: Implementing the Samoa National Reform Energy Policy (grant financed by AusAID) supported drafting of the Electricity Act and Regulations. MoF intends to hire a power regulator by June 2011. TA 4994 has been extended to June 2011 to provide assistance with establishing the power regulator. MOF has indicated that allocation for the power regulator will be allocated in the 2011/12 budget. |
| 2. Improvement of Electric Power Corporation (EPC) debt collection performance such that accounts receivable shall not have exceeded 2 months of electricity sales for a minimum of two years | Receivables are 37.3 days as of January 2011. Receivables have remained below 2 months since 30 September 2007 (3.3 years). Current data for receivables is presented in Appendix 4. Compliance with this loan buy down trigger has been achieved. |
| 3. Usage of prepaid meters by 75% of all EPC’s electricity customers by 31 December 2012 | Currently an estimated 61% of EPC’s customers are using prepaid meters. The installation of prepaid meters is on-going. Installation projections for prepaid meters are included in Appendix 5. Installation targets are currently being met. |

6	Conversion of Loan to Grant. The Project Report and Recommendation to the President (RRP) para. 47 and para. 8 (c) of the Subsidiary Financing Agreement allows for up to 7% of Project costs or a ceiling of $10 million to be converted from loan to grant by MOF to EPC. Section 6.01 (b) of the Financing Agreement requires a conversion mechanism to be established. EPC and MOF have discussed options for triggers under the loan buy down mechanism would be suitable for conversion of the loan to grant. MOF agreed to finalize the mechanism for approval by the next Project Steering Committee.

7	PMU Staffing. Implementation of civil works on a number of large projects has commenced. The EGIS-BCEOM consultant supervision contract will expire in second quarter 2011. The Mission discussed construction supervision capacity with the PMU and expressed concern that current staffing levels were insufficient to adequately manage construction supervision. It was agreed that additional experienced staff are required to manage construction supervision and EPC confirmed that they will hire 3 additional fulltime construction supervision consultants for the duration of relevant subproject implementation.

8	Fiaga Powerplant. Contract SAM-PSEP-12/03A was signed with Bluebird AhLal in association with Mitsubishi Heavy Industries and Wood Pacific (BBA) on 10 November 2010 for USD26,681,042 for Design, Manufacture, Supply, Construct, Install and Commission of Fiaga Power Station. ADB received a letter from the Minister of Finance on 20 December 2010 proposing to partially change the currency of payment from USD to NZD and Yen. ADB responded advising that payment for Contract SAM-PSEP-12/03A should be made according to the currency schedule included in the accepted bid of BBA, in accordance with ADB Procurement Guidelines para 2.32 which states "Payment of the contract price shall be made in the currency or currencies in which the bid price is expressed in the bid of the successful bidder." In response to statements made by BBA to the Project Steering Committee in January 2011 regarding reluctance to continue with implementation of Contract SAM-PSEP-12/03A, the Executing Agency (MoF) agreed to continue discussions with BBA to bring the matter to a conclusion as soon as possible.

9	Imprest Account. The letter to ADB from the Minister of Finance on 20 December 2010 also requested establishment of an imprest account for the Project. The Mission discussed the option of establishment of an imprest account with the PMU and was advised that it was no longer required.

10	Office of Anti-corruption and Integrity (OAI) Project Review. The Mission advised the Government and EPC that OAI had randomly selected the project for review. Initial site visits by OAI are anticipated by March 2011.

11	Subproject Prioritization. The Mission discussed prioritization of remaining subprojects with the PMU. The PMU advised that the remaining budget may be insufficient to finance all remaining subprojects, including the proposed small hydropower subprojects. It was discussed that the small hydropower projects may be suitable for external grant financing by other development partners.

TA 4494-SAM: Implementing the National Energy Policy

12	TA 4994-SAM consists of the following components (i) Component 1: Establishment of the Clean Energy Fund (CEF), (ii) Component 2: Establishment of the Designated National Authority (DNA), (iii) Component 3: Regulatory and Policy Reform in the Power Sector, and (iv) Component 4: Resident Financial Management Advisors to EPC. Activities under Component 1, 2 and 4 have been completed. The closure of TA 4994-SAM has been extended to June 2011 to allow final activities to support establishment of the power regulator under Component 3. ADB agreed to assess the remaining budget to support (i) a final mission by one financial management advisor to EPC in March 2011, and (ii) office equipment to the power regulator.

III. 	CONCLUSION

13	The Mission would like to express its appreciation for the cooperation and the hospitality extended by the GoS and EPC. It is understood that the points of agreement and recommendations as reflected in the Aide Memoire are subject to the approval of higher authorities in GoS and ADB.

Signed in Apia, Samoa 18 February 2011

…………………………… Anthony Maxwell Team Leader Asian Development Bank

List of Persons Met

Ministry of Finance

Mr. Iulai Lavea			Chief Executive Officer

Ms. Noumea Simi			Assistant CEO, Debt Management

Ms. Justina Sau	Assistant CEO, State Enterprise Monitoring Division

Ms. Silia Kilepoa Ualesi	Energy Coordinator, Economic Policy and Planning Division

Electric Power Corporation

Mr. Mua’ausa Fiu Joseph Walter	Chief Executive Officer

Mr. Vui Lance Lameko		Manager, Corporate Services

Mr. Galumalemana Tologata Tile

Lei’a Tuimalealiifano		Project Manager, PMU

Mr. Tupai Fui Mau Simanu		Generation Engineer, PMU

Mr. Taulealeausumai Tiotio		Transmission & Distribution Engineer, PMU

Ms. Faalepo Solofa-Lemisio		Project Accountant, PMU

Mr. Alfred Matatia			Civil Engineer, PMU

Ms. Raema Schuster			Electrical Engineer, PMU

Ms. Nuulopa Pereira			Power System Planner, PMU

Mr. Mathew Lemisio			Environment and Legal Advisor, PMU

Ms. Moetuasivi S Asiono		PR and Community Specialist

Mr. Seukeva Asi Tiatia		Land Acquisition and Resettlement Specialist

Mr. Wairarapa Young			Renewable Energy Officer

Attorney General’s Office

Mr. Peter Bednell			Lawyer

Australian Agency for International Development (AusAID)

Ms. Frances Schuster 		Senior Program Manager

Other

Ms. Maeva Betham-Vaai 		ADB/World Bank Group Focal Officer

Mr. Fonoti Perelini Perelini		Team Leader EGIS-BCEOM

Mr. Brendan Heggarty		Generation/Transmission Specialist EGIS-BCEOM

Mr. Kazuyoshi Mori			JICA Technical Advisor

Mr. Shimpei Tomita			JICA Technical Advisor

Mr. Yosuke Suezawa			JICA Technical Advisor

Contract Awards and Disbursements

Actual (2008-2010) and Projected (2011-2016)

Contract Award and Disbursement Projections

Electricity Receivables

Prepayment Meter Installation Projections

The Mission comprised Anthony Maxwell: Team Leader, Chika Kondo: Project Manager, Japan International Cooperation Agency, Rebecca Salvo: Operations Officer, ADB, Ralph Karhammar: AusAID Consultant

Loan Buydown Agreement between the Government of Australia and Asian Development Bank with respect to the Power Sector Expansion Project Loan in the Independent State of Samoa, 19 February 2008

Subsidiary Financing Agreement (Power Sector Expansion Project) between Independent State of Samoa and Electric Power Corporation, 16 June 2008

Financing Agreement between Independent State of Samoa and Asian Development Bank for the Power Sector Expansion Project, 11 December 2007

One international generation engineer, one international transmission engineer, and one international civil engineer, all with extensive project construction supervision experience.