FACILITY DESIGN DOCUMENT

SAMOA PUBLIC SECTOR IMPROVEMENT FACILITY

September 2004

TABLE OF CONTENTS

Annexures	ii

LIST OF ACRONYMS	iii

EXECUTIVE SUMMARY	iv

1	BACKGROUND AND DESIGN PREPARATION	1

1.1	Program Origin	1

1.2	Development Assistance Context	1

1.3	Design Mission and Method	2

2	ANALYSIS	4

2.1	The Reform Agenda in Samoa	4

2.2	Policy and Program Context	7

2.3	Issues	9

3	PROPOSED RESPONSE	12

3.1	Program Strategy	12

3.2	Governance Facilities – Lessons Learned	12

3.3	Selection of the Response Strategy	15

4	DESCRIPTION OF THE PUBLIC SECTOR IMPROVEMENT FACILITY	17

4.1	Overview	17

4.2	Goal and Purpose	19

4.3	Component Structure and Objectives	20

4.4	Facility Location, Duration and Allocation	26

4.5	Eligible Assistance	26

5	Management Structure and Roles and Responsibilities	28

5.1	Overview	28

5.2	The Facility Coordinating Committee	28

5.3	The Facility Steering Committee	30

5.4	The Facility Management Unit	30

5.5	Review Group	32

5.6	The Public Service Improvement Fund	33

5.7	Integration with GoS structures and processes – Facility Management	34

6	Risk and Risk Management	35

7	Monitoring, Evaluation and Performance Assessment	37

7.1 	Overview	37

7.2 	Facility-level Monitoring	37

7.3 	Activity-level Monitoring	38

7.4 	Monitoring of Contractor Performance	38

7.5	Monitoring of FMU Performance	38

7.6	Reviews	39

7.7	Evaluation	40

8	Outcome of design issues	41

8.1	Feasibility	41

8.2	Impact on Poverty	47

8.3 	Social and Cultural Impact	47

8.4	Gender Impact	47

8.5	Impact on Environment	48

Annexures

Annex 1 – Terms of Reference

Annex 2 – People Consulted

Annex 3 – Aide Memoire

Annex 4 – GoS Planning Systems

Annex 5 – Summary Logframe

Annex 6 – Program Processes

Annex 7 – RFP

Annex 8 - Position Statements

Annex 9 – Risk Matrix

Annex 10 – References

Annex 11 – PSIF Relationship to Other Funding Mechanisms

LIST OF ACRONYMS

ADB	Asia Development Bank

AusAID	Australian Agency for International Development

ACC	Aid Coordinating Committee

ACR	Activity Completion Reports

CDC	Cabinet Development Committee

CEOs	Chief Executive Officers

CMS	Contracted Management Support

CPR	Contractor Performance Report

CST	Contracted Support Team

EPPD	Economic Planning and Policy Division, Ministry of Finance

FCC	Facility Coordinating Committee

FMU	Facility Management Unit

FSC	Facility Steering Committee

GoA	Government of Australia

Gof NZ	Government of New Zealand

GoS	Government of Samoa

HLDs	High Level Discussions

IEP   	Immediate and Emerging Priorities

ISIC	International Standard Industrial Classification of all Economic Activities

ISPs	Institutional Strengthening Projects

MCIL	Ministry of Commerce, Industry and Labour

MoF	Ministry of Finance

MPM	Ministry of the Prime Minister

MWCSD	Ministry of Women, Community and Social Development

MWTI	Ministry of Works, Transport and Infrastructure

NZAID	New Zealand Agency for International Development

PACTAF	Pacific Technical Assistance Fund

PSC	Public Service Commission

PSI	Public Sector Improvement ( in relation to the Facility ie. PSI Fund; PSI Framework)

PSIF	Public Sector Improvement Facility

PSIP	Public Sector Improvement Plan

RFP	Review and Forward Program

RG  	Review Group

SDS	Strategy for the Development of Samoa

SUNGO	Samoa Umbrella for Non-Governmental Organisations

TA	Technical Assistance

TOR	Terms of Reference

EXECUTIVE SUMMARY

Background

Samoa's political environment is stable and its democratic institutions are robust. Over the last decade Samoa has consolidated its place as a regional leader in the Pacific, particularly in relation to economic and public sector reform.  The Government's Strategy for the Development of Samoa (SDS) places priority on achieving a competitive economy with sustained economic growth, improved education, enhanced health standards and strengthened cultural and traditional values.  Within the “Strategy for Development of Samoa 2002-2004”, public sector reform has a high priority as a key strategic outcome.

Australia and New Zealand are major providers of development assistance to Samoa and have supported a number of significant public sector reform and institutional strengthening projects in the country.  AusAID in particular has significant experience with institutional strengthening projects (ISPs) in Samoa.  AusAID and NZAID have also, over recent years, been exploring opportunities to harmonise their development assistance programs in order to improve the effectiveness and impact of their programs in Samoa.  The first AusAID, NZAID and Government of Samoa (GoS) joint High Level Discussions (HLDs) on development cooperation were held in July 2002 and are scheduled to continue biannually.

Given the substantial investment by AusAID in supporting the GoS public sector reform agenda, a joint AusAID/GoS review of the impact of ISPs was undertaken in 2003.  The Review’s assessment of the contribution by ISPs to the GoS reform program was favourable, and noted that these projects have “provided a solid foundation on which to build continuing improvements in public sector efficiency and effectiveness”.  It further noted that these interventions have been closely aligned with national and sectoral priorities by enhancing public sector efficiencies and that they have therefore made a valuable contribution to progressing the GoS reform agenda. However the Review findings indicated the need to develop support, at a stage removed from ISPs, for effective public sector reform and capacity building.

The GoS agreed, in their response to the Review, to the establishment of a mechanism to provide this support.  Since that time, the concept of a Facility aimed at public sector improvement has been further appraised and endorsed by stakeholders.  The three governments (Australia, New Zealand and Samoa) have all expressed a clear and fundamental desire that such a Facility be aligned as closely as possible with existing GoS procedures and structures, and that its management be the responsibility of the GoS from the start, with short to medium term support provided if necessary.

As set out in the Design Mission’s TORs, the intention of AusAID/NZAID is to “design a Facility appropriate to Samoa’s social and cultural context, environment and economy that will support the Government of Samoa to build the capacity of its public service to implement its national development priorities.  The proposed Governance Facility is intended to provide a mechanism that can address priority small-scale needs in support of economic and public sector reform within key GoS public sector agencies”.

Issues and Selection of Design Strategy

In initial meetings between the Design Team and donors, several aspects of the TORs were reinforced.  In particular:

- The desire for an innovative and flexible design, and one which is as far as possible driven by priorities and conforms with the structures and processes of the GoS to promote ownership and sustainability; and

- That the design should allow for the Facility to be both proactive, assisting the GoS build on the achievements of socio/economic reform to date by supporting the development of a suite of core activities; and reactive, so as not to preclude responses to emerging or immediate issues within its overall strategic direction.

The Design Team consulted widely amongst Samoan stakeholders.  It is clear that there is widespread support for a Public Sector Improvement Facility (PSIF).  Several key messages were repeated throughout these consultations, and these provided a framework for the proposed design.

- There was an unambiguous desire on the part of the GoS to resource (in terms of management staff) and manage the PSIF in the long term but a recognition that the GoS team would need support and capacity building in the short to medium term.

- There is a need for transparency, accountability and equity in the management and decision making processes of the Facility.

- The Facility should strive to reduce the gaps in capacity between public sector agencies, rather than (inadvertently) increase this gap.

- The Public Service does not have the capacity or resources, from a whole-of-government perspective, to analyse the achievements of the socio/economic reform to date, and only by doing this can it focus future reform efforts (which are to include greater attention to social aspects of the reform) and identify critical constraints within and between agencies to pursue the reform agenda, and move forward cohesive and coherently to the next level of development.

- The activities funded by the Facility should reflect the key priorities of the GoS, as outlined in the Strategy for the Development of Samoa, and it is therefore important that:

  - these priorities be clearly articulated in the criteria against which proposals will be assessed

  - all activities ultimately supported by the Facility must be able to be justified in terms of how they contribute to improved service delivery to the community.

The GoS reform program has achieved a great deal.  Nevertheless, there are a number of critical issues identified by the stakeholders consulted which it is recommend be addressed in the design of assistance to enhance the ability of the GoS to progress the reform program.

There is a need to consolidate and sustain achievements, and to continue to pursue selected reforms not yet achieved.  Importantly, progress still needs to be made in establishing a whole-of-government approach to reform which integrates cross cutting issues and adequately involves both civil society and the private sector.  Support for planning, at a whole of government, sectoral and Ministry level; and improved collaboration between Ministries/Agencies, are areas in which the PSIF may effectively assist the GoS to pursue its public sector reform agenda.  Improvements in these areas are the desired end point of Facility assistance.

An overarching strategy of the design is therefore to strengthen cooperation and collaboration between public sector agencies, and between these agencies, civil society and the private sector, in identifying and addressing critical constraints to public sector reform as it impacts on service delivery.  The design proposes a core suite of activities which address strategic issues in reform, including the ability to identify constraints to public sector improvement and sector planning.  The ability to respond to immediate and emerging priorities is also addressed.  In particular, features of the Public Sector Improvement Facility (PSIF) design include:

- A flexible design which is as far as possible driven by the priorities and processes of the GoS, to promote ownership and sustainability;

- A two-component programming structure which affords the PSIF an ability to be both proactive and reactive.  The proposed design supports the development of a suite of core activities, but does not preclude responses to emerging or immediate priorities within the overall strategic direction of the Facility;

- Support for promotion of a whole-of-government approach to implementation of the reform agenda; and

- A focus on the structured transfer of the necessary skills to a GoS team that will, over time, take on full management control of the Facility.

Adoption of this design strategy will help ensure an integrated, whole-of-government approach to the issues which underpin and constrain public sector reform at both the strategic (planning and policy) and operational (service delivery) levels.  The design also ensures that the Facility is driven by GoS reform agenda priorities, that it conforms to the expressed desire of the three Governments that it will be ultimately managed by the GoS and, through a two component programming structure, provides a framework that allows the stakeholders to avoid diffusion of effort while providing some capacity to respond flexibly to emerging needs.  Separating the program delivery elements of the design over two components not only ensures that stakeholders focus on the different aims and expectations that arise in core programs as well as those associated with immediate and emerging needs, but also provides a tool to ensure that a tight focus can be maintained.

Public Sector Improvement Facility Design

The PSIF is designed to provide a flexible and responsive mechanism for supporting a program of public sector reform-oriented governance activities which have been identified as contributing to improved efficiency and effectiveness across the Samoan public sector and which build upon the benefits achieved to date under the range of ISPs which have been funded by Australia and New Zealand; or which respond to immediate / emerging needs within the public sector.   The PSIF therefore addresses the requirements of the Government of Australia (AusAID), Government of New Zealand (NZAID) and the Government of Samoa (GoS) for a Facility to channel donor funding to address the public sector reform needs of the GoS.  The PSIF is to be implemented within GoS structures through a core Facility Management Unit located at the Ministry of the Prime Minister and supported by a Contracted Support Team.

Goal and Purpose

The goal of the Public Sector Improvement Facility is to improve the efficiency and effectiveness of Samoa’s Public Service to support Samoa’s national development priorities.

The purpose of the Public Sector Improvement Facility is to strengthen cooperation and collaboration between public service agencies (and between them, the private sector and civil society), in identifying and addressing critical constraints within the GoS public sector to effective service delivery through a range of institutional strengthening initiatives.

The design of the PSIF has four components:

Component 1:  Core Program Activities.  The objective of this component is to support the design and implementation of strategically identified core activities which promote continued reform across the Samoan public sector and which improve the ability of the public sector to deliver quality services.

Component 2:  Immediate and Emerging Priorities (IEP).  The objective of this component is to support the ability of the GoS to identify and respond to smaller scale, immediate and emerging priorities in public sector reform.

Component 3:  Capacity Building of Facility Management Unit.  The objective of this component is to develop and support the capacity of a GoS Facility Management Unit (FMU) to implement and manage the PSIF.

Component 4:  Facility Mobilisation and Management.  The objective of this component is the effective management of the Public Sector Improvement Facility.

Critical to the success of the Facility will be the development of a sound, efficient activity planning and management cycle that can not only manage a number of core program activities but can also respond quickly to requests for a wide range of short term assistance.  The management structures developed:

- Must be designed to deliver a cost-effective program of assistance and also fulfill the wish of the three governments that the PSIF is, over time, managed solely by the Government of Samoa;

- Must not create unnecessary levels of administrative bureaucracy and wherever possible be harmonised with standard administrative procedures of the GoS; and

- Should wherever possible utilise existing systems and structures within the GoS.

With these fundamental requirements in mind, the design proposes a number of administrative structures that provide the necessary management oversight for the programs supported by the PSIF.  These are:

- a Facility Coordinating Committee (FCC) representing the Government of Samoa and the two donor governments – Australia and New Zealand

- A Facility Steering Committee (FSC) representing key Samoan public sector agencies and representation from civil society and the private sector

- a Facility Management Unit (FMU) staffed by GoS, which incorporates a contracted support team in the short to medium term

- a Review Group (RG) also staffed by the GoS and again incorporating a contracted transitional review adviser in the short to medium term

- a Public Service Improvement Fund (the Fund)

Facility Location, Duration and Allocation

It is recommended that the management of the PSIF reside with a GoS-appointed Facility Management Unit (FMU) within the Ministry of the Prime Minister (MPM).  It will be a requirement that the GoS contract/employ the staff of the FMU and provide office accommodation for the FMU.  The staff of the FMU will be counterparted by a donor-funded Contracted Support Team (CST) over the medium-term.

The Facility duration is five years, with an annual initial contribution by AusAID of AUD2 million and NZAID of NZ1 million.

Risks

The PSIF is a moderate to high risk activity that will require the establishment of effective liaison processes between AusAID, NZAID, GoS and the Contractor.  The GoS-run FMU, supported by the CST, will be required to develop strategies that address these risks and minimise their impact should they manifest. The most significant risk mitigation strategies proposed in this design are:

- A requirement that AusAID/NZAID operational issues are addressed and responsibilities in relation to the PSIF are clearly set out before the PSIF is implemented;

- The proposal of a foundation activity to allow stakeholders to determine and clearly articulate the strategic public sector reform focus of the PSIF ensures that the PSIF has a manageable program of activities that will contribute positively to the GoS reform priorities;

- A Stop/Go Review be held after end Year 1 to assess the level and effectiveness of support to the facility by the Ministry of Prime Minister (MPM) with a view to confirming that the site for the FMU should remain with the MPM or should be moved to the Ministry of Finance;

- That a Review of Transitional support be undertaken at the commencement of Year 3 to assess the capacity of the GoS FMU and Review Group staff to undertake their roles with a view to ensuring that the transition timetable remains on track; and

- The adoption of a process of progressive engagement to ensure that continued PSIF support is provided on the basis of a counterpart agency demonstrating appropriate levels of competency and commitment to provide a reasonable level of confidence that the resource investment will deliver a useful and relevant outcome.

1	BACKGROUND AND DESIGN PREPARATION

## Program Origin

Australia and New Zealand are major providers of development assistance to Samoa and have supported a number of significant public sector reform and institutional strengthening projects in the country.  AusAID in particular has significant experience with institutional strengthening projects in Samoa. AusAID and NZAID have also, over recent years, been exploring opportunities to harmonise their development assistance programs in order to improve the effectiveness and impact of their programs in Samoa, including harmonization of procedures and approaches providing for partnership and flexibility.  The first AusAID, NZAID and Government of Samoa (GoS) joint High Level Discussions (HLDs) on development cooperation were held in July 2002 and are scheduled to continue biannually.

In support of public sector reform in Samoa, AusAID has funded ten Institutional Strengthening Projects (ISPs) aimed at improving the capacity of GoS agencies to efficiently and effectively plan and manage their functions.  With funding averaging A$8 million a year and representing around 60 per cent of the bilateral aid program to Samoa, this program of ISPs has been a fundamental element of Australia’s aid commitment.  Similarly, NZAID has used the ISP model to support reform in the Justice Department, including the establishment of a Law Commission.  Building on this, NZAID intends to support a further ISP in the courts sector in 2004-05.  While there has been substantial assistance provided in implementing the GoS public sector reform agenda, a 2003 review of AusAID-funded ISPs noted the need to begin planning to consolidate the gains achieved in public sector reform, and to extend these gains across all government departments.  The Review further noted the need to develop support at a stage removed from ISPs for effective public sector reform and capacity building.

In response to the findings of the ISP Review, it was agreed at tripartite HLDs that high priority be accorded to the design of a Facility designed to meet Samoa’s unique social and cultural context, environment and economy in order to support the Government of Samoa (GoS) to further strengthen the capacity of its public service to implement its national development priorities.  It was agreed that this would be a mechanism managed by the GoS though, if required, with capacity building support employing principles of transparency, accountability and equity.

## Development Assistance Context

Given the substantial investment by AusAID in supporting the GoS public sector reform agenda, a joint AusAID/GoS review of the impact of ISPs was undertaken in 2003.  The Review’s assessment of the contribution by ISPs to the GoS reform program was favourable, and noted that these projects have “provided a solid foundation on which to build continuing improvements in public sector efficiency and effectiveness”.  It further noted that these interventions have been closely aligned with national and sectoral priorities by enhancing public sector efficiencies and that they have therefore made a valuable contribution to progressing the GoS reform agenda.

The Review outlined four clear messages for future assistance:

- The current ISPs have provided a solid foundation for enhanced public sector efficiency but there is a need to move forward to more flexible forms of support for improvements in the future, with substantially reduced emphasis on the ISP ‘model’ employed to date;

- More needs to be done on a whole-of-government basis to continue strengthening the public service;

- The GoS should have prime responsibility for both the identification of future strengthening needs and priorities and for the design, management, performance monitoring and evaluation of specific interventions to address these; and

- This needs to occur within a framework that relates institutional strengthening and public sector reform more explicitly to Samoa’s overall development strategy.

The ISP Review noted the need to consolidate the gains already achieved in public sector reform and to extend these across all government departments.  The Review recommended that AusAID should develop a programming strategy that would provide a basis for supporting continuing improvement in the capacity of Samoa’s public service to implement national development priorities.  In the absence of a sector level plan for Public Administration, or an agency tasked with implementing a whole-of-government approach to improved public administration, the Review recommended that future Australian support for capacity building be delivered within the framework of a Public Sector Improvement Plan (PSIP), to be developed by a Public Sector Improvement Committee reporting directly to the Prime Minister.

The Review also recommended the establishment of a Facility as the most appropriate means of delivering further support for public sector improvement, within the framework of a PSIP, on the basis that it could:

- Provide timely, responsive, targeted and flexible assistance to meet current and emerging needs of participating agencies;

- Develop partnership approaches between governments;

- Ensure scope for progressive engagement – commencing on a small scale and leading to a larger level of support if required and as counterpart agencies demonstrate commitment and capacity to participate; and

- Offer scope for scaling the program up or down annually on the basis of demand and on the availability of funds within a country program.

The GoS agreed, in their response to the Review, to the establishment of such a facility.  Since that time, the concept of a governance facility - since refined as a Public Sector Improvement Facility - has been further appraised and endorsed by stakeholders.  The three governments (Australia, New Zealand and Samoa) have all expressed a clear and fundamental desire that any such facility be aligned as closely as possible with existing GoS procedures and structures, and that its management be the responsibility of the GoS from the outset, but with short term medium term support provided if appropriate.

## 1.3	Design Mission and Method

A team of four members prepared the draft design of the Public Sector Improvement Facility (PSIF). The Design Team was made up of an AusAID-contracted Design Consultant, an AusAID Design Specialist, a NZAID contracted Consultant and a senior public servant from the GoS. The majority of the work was completed in Apia during the period 12 – 26 February 2004. The objectives of the mission were to:

- Consult with the Government of Samoa and other relevant organisations to determine the feasibility and implementation arrangements for the Facility; and

- Subject to feasibility, prepare an appropriate Design and related documentation for the Facility.

The Design Team’s Terms of Reference (TOR) are attached at Annex 1.

Before arrival in Samoa the Australian and New Zealand, Design Team members reviewed background documentation in relation to the proposed Public Sector Improvement Facility.

On arrival in Apia the Design Team attended an introductory meeting with officials and representatives of NZAID, AusAID, and the GoS.   At the invitation of AusAID/NZAID and the MoF, the Design Team subsequently held initial consultation meetings firstly with the Chief Executive Officers (CEOs) of nine GoS Ministries and secondly with the team leaders from current ISPs.  During these meetings the objectives of the mission were presented and the initial views of attendees sought.  This was followed by individual consultations with a number of key stakeholders (see Annex 2).

An Aide Memoire (Annex 3) outlining the Design Team’s initial findings and recommendations, and a preliminary design structure for the Public Sector Improvement Facility was presented to the GoS and other interested stakeholders in a debriefing on 25 February and formed the basis of a mission debrief provided to NZAID and AusAID by Design Team members on 2 and 5 March respectively.  This was followed by a Design Appraisal Workshop in Canberra coordinated by AusAID on 23 April.

# ANALYSIS

## The Reform Agenda in Samoa

Samoa's political environment is stable and its democratic institutions are robust. Over the last decade Samoa has consolidated its place as a regional leader in the Pacific, particularly in relation to economic and public sector reform.  The Government's Strategy for the Development of Samoa (SDS) places priority on achieving a competitive economy with sustained economic growth, improved education, enhanced health standards and strengthened cultural and traditional values.

Within the “Strategy for Development of Samoa 2002-2004”, public sector reform has a high priority as a key strategic outcome. The strategy document states “The public sector reform program will concentrate on improving and enhancing:

- The efficiency and effectiveness of Government services delivery;

- Financial management;

- Transparency and accountability;

- The corporatisation and privatisation program;

- The development of statistics for policy purposes; and that

- It will aim to minimise the social cost of reforms and provide a safety net for those disadvantaged”.

### Political and Socio-Economic Context

In 1994 the GoS initiated reforms which resulted in the introduction of bold policy measures and the creation of new government structures, systems and processes and associated legislation that have required strong government commitment.  Since 1994 the GoS has pursued an economic and public sector reform program aimed at providing an enabling environment conducive to economic growth and investment.  As part of the reform program, the GoS reviewed processes for the planning of Samoa’s economic and social development and introduced a more strategic approach to national development.  This approach resulted in the preparation and publication of the Government’s first Statement of Economic Strategy in 1995.

Since that time, Samoa has made major gains in establishing a sound and stable macroeconomic framework as the foundation for stronger economic growth led by private sector development.  Over the past three years, Samoa has maintained a high level of economic stability through appropriate fiscal restraint and sound monetary policy.  GDP growth has been achieved primarily through growth in the transport, communication, infrastructure, manufacturing, finance and business services sectors and agriculture, which recently expanded strongly after years of decline.

GDP	$1 billion (estimated 2002)

GDP per capita	$5,600 (2002)

1995-2002 Growth rate	4.5%

Annual inflation 	0.8% (at Nov 2003)

National Budget 	$128.1 million (2003/2004)

Life Expectancy	Male: 67.35 years, Female 73 years

Age Distribution 	0-14 years: 29.4%, 15-64 years: 64.6%, 65+ years: 6.1% (2003 est.)

Population Growth Rate	-0.27% (2003 est.)

Source: Pacific Magazine January 2004; Samoa- Australia- New Zealand High Level Discussion on Development Cooperation Record of outcomes; GoS Minister of Finance 2004/2005 Budget Speech

Key economic challenges include managing vulnerability of key sectors, particularly agriculture, fishing and manufacturing, to climatic and external shocks (as yet it is not clear what the full economic impact of cyclone Heta, which struck Samoa in January 2004 will be but by mid-year the strong surge in global oil prices was having an impact); small business and private sector investment; and ensuring all members of the community benefit as markets and village economies develop.

Despite ten years of macroeconomic stability and good growth, Samoa has not attracted significant foreign direct investment, and doing so remains a strategic challenge.  In addition, the 2002 ADB participatory poverty assessment indicated that there are still considerable pockets of need in Samoa. Unemployment rates and school drop out rates are on the rise.  Drug use, domestic violence, teenage pregnancies, and youth suicide are also said to be increasing. Urban slums are emerging in Apia and while there is data showing that the gap between rural and urban areas is increasing, hardship can be seen in both rural and urban areas. There are also significant gaps in the standard of living between the two main islands.

There have been a number of strategies and plans to drive the country’s development and the reform program. Additional thrust has come from restructuring the Public Service, a selected devolution process, reform of the financial system, and greater transparency and accountability of programs implemented by government agencies.

The major achievements of reforms to date have been concentrated in the financial and economic arena and in the way in which the business of government is managed. Samoa has attained a stable macroeconomic environment characterised by stable growth and low inflation assisting in improving the business environment; greater transparency of management (with moves toward performance management); the timely publishing of accounts; subscription to the general data system of IMF; and a review of legislation to promote financial transparency.

### Institutional Context

#### Formal Government

As part of the reform agenda, in mid-2003 Samoa realigned Government Ministries with an overall reduction in Ministries from 23 to 13, in addition to three Constitutional Authorities. CEOs were appointed to lead the new Ministries for a three–year period.

The key central agencies responsible for Public Administration are:

- Ministry of Finance (MoF), which has responsibility for Treasury, the Department of Statistics, the Registration of Births, Deaths and Marriages, and Economic Aid and Coordination. The MoF’s function is to provide expert economic and financial advice to Government and deliver quality services to all stakeholders.

- Public Service Commission (PSC) is tasked with the provision of Human Resource Management policy advice to Government and assisting line departments/agencies to ensure efficient and effective service delivery for the people of Samoa.

- Ministry of the Prime Minister (MPM) has responsibility for the Prime Minister’s Department, the Cabinet Secretariat and the Immigration Division - Visa and Policies (excluding Border inspection). The function of the MPM is to ensure the effective and efficient operations of the Cabinet by providing advisory and secretarial services, and to provide advisory and support services to Government Departments, organisations, designated agencies and the public at large through the dissemination of Cabinet decisions for their information and implementation as necessary.

- The Samoa Audit Office is a constitutional authority which is tasked with ensuring the financial integrity of the Parliamentary system of Government.  It has legal independence from the executive branch of Government in the fulfillment of its statutory responsibilities. Its mandate is to provide independent and professional audit services to all public sector entities in Samoa, and report on these findings.

- The Office of the Attorney General provides policy advice to the Head of State, Ministers, Ministries and government agencies and corporations covering all spheres of activity and across the full range of legislation. The Office is required to undertake or supervise the drafting of all Government Bills and Regulations. The office also undertakes criminal prosecutions, largely for the Police in the Supreme Court, but can also prosecute under other legislation. It also represents the government in civil claims before the Courts and tribunals.

More detailed information about the central agencies, along with information on all Samoan government Ministries and Authorities can be found on the Government of Samoa website www.govt.ws.

As well as the central agencies responsible for Public Administration, there are a number of important inter-ministerial committees responsible for decision making in regard to core government functions.

- The Cabinet Development Committee (CDC) is chaired by the Prime Minister and meets every two months to review policy issues affecting the implementation of the SDS. As such the Cabinet and CDC represent the highest level of authority for policy making and approval. The CDC comprises all Cabinet Ministers, Ministry CEOs and Heads of Departments and corporations (as appropriate) who direct and approve policies in support of the SDS. A representative of the Chamber of Commerce and SUNGO attend as observers. The CDC Secretariat is housed within the Economic Policy and Planning Division (EPPD) of the MoF.

- The Aid Coordinating Committee (ACC)  is responsible for the allocation of both foreign and, in conjunction with the Ministry of Finance (Treasury Department), the domestic financial requirements for project implementation.  The mandate of the ACC is to liaise with the donor community, consider, negotiate and allocate funding requirements for project implementation, prepare strategies for aid programming, and endorse the annual project pipeline.

#### Traditional and Informal Governance

During colonial times the Pulenu’u was created as an institution to carry out government directives in villages. The tradition continues today with each fono a Alii and Faipule (the traditional governing council of the village) selecting a matai (chief) to be their Pulenu’u with the government. The Office of the Pulenu’u, which provides administrative support for the work of the Pulenu’u, is based within the Ministry of Women, Community and Social Development (MWCSD). The Pulenu’u, which is made up of 240 matai, meets with the Ministry up to three times each month to learn about government initiatives (including receiving information regarding the introduction of new programs or polices) and to raise with the Ministry concerns and issues affecting villages.  Pulenu’u members are paid an allowance by the government for this work. There is an expectation that the information provided by the MWCSD will be conveyed to villages, and in return that the views of the villages will be conveyed to the government. Thus the Pulenu’u represents a critical link between government and the villages of Samoa and their governing structures. The importance of the Pulenu’u was recognised in the 2004/2005 budget with an allocation of additional finance to further strengthen the institution through a new initiative to also appoint women. This initiative will also ensure there is a better gender balance in the interface between the government and village community.

Over the past few years the non-government sector in Samoa has grown and diversified with a number of NGOs now functioning with ongoing programs to assist the community. The Samoa Umbrella for Non-Governmental Organisations (SUNGO) was established formally in 1997 to support and strengthen the network of non-governmental organisations in Samoa and also to serve as a focal point for information sharing and communication both nationally and internationally. It now has over 50 active financial members.  The importance of this section of civil society as a partner in development is recognised by the GoS, and SUNGO is frequently requested to provide a non-government perspective on issues in a number of national decision-making bodies, including as an observer on the Cabinet Development Committee.  Recently the Prime Minister offered the opportunity to SUNGO to meet with him on a regular basis, given that NGOs form part of the Prime Minister’s portfolio responsibilities.

## Policy and Program Context

### 2.2.1	Samoa’s planning and budgetary systems

Samoa’s planning and budgetary system consists of four major components drawn together under a Performance Management System (the GoS PSC Performance Management System Flow chart is attached at Annex 4).

- The vision of the medium-term (three-year) Strategy for the Development of Samoa (SDS) is “For every Samoan to enjoy an improved quality of life”.  The SDS articulates nine key Strategic Outcomes to help achieve this vision: maintaining a stable macroeconomic framework, the development of health, education, private sector, socio-cultural values and agriculture; as well as infrastructural services; tourism development; and improved service delivery by the public sector.

The SDS also contains a summary of the economic and social policies and strategies or actions that will produce these strategic outcomes. This summary includes key sectoral development objectives and priorities.  The SDS 2002 – 04 broadened Samoa’s development strategies and priorities to encompass wider facets of development, including social and cultural values.  The strategy emphasises enhanced public sector efficiency as a key pillar for future development in Samoa.

The MoF is responsible for preparation of the SDS in consultation with other government agencies, churches, the private sector, non-government organisations, and the public. Cabinet approves the SDS, and the MoF reviews its implementation.

- Sector Plans, which can cover a period of up to ten years, provide a detailed outline of sectoral performance, issues and opportunities, and the sector-specific objectives, policies and strategies that support the SDS. Sector Plans provide the framework for the identification of public policy initiatives and projects in the private and public sectors, including the role of the lead agency in developing the sector in partnership with other government agencies, churches, the private sector, and other non-government stakeholders.

Designated government agencies are responsible for the preparation of Sector Plans through a process of stakeholder consultation and participation.  Sector Plans also provide a strong link between the budget and the national plan.  The Cabinet Development Committee (CDC) approves Sector Plans and the MoF is responsible for ensuring consistency between the Sector Plans and the SDS.  In its role as planning secretariat to the CDC, the Economic Planning and Policy Division of the MoF is responsible for monitoring and reporting on the implementation of Sector Plans; but designated government agencies are also expected to monitor and report on progress.

The United Nations 1990 International Standard Industrial Classification of all Economic Activities (ISIC) is used by Samoa as a reference for defining 14 sectors, grouped under three broad headings, for the purposes of sectoral planning.

Economic Sectors:

- Agriculture (agriculture, fisheries and forestry)

- Manufacturing (food & beverages manufacturing and other manufacturing)

- Tourism (hotels and restaurants, wholesale and retail trade, and transport)

- Commerce (wholesale and retail trade)

- Finance (financial and business services)

Social Sectors:

- Education

- Health

- Public Administration

- Welfare and Social Services

Infrastructure Sectors:

- Construction

- Electricity

- Water

- Transport

- Communications

- Project Planning procedures are detailed in the GoS Manual on Project Planning and Programming, developed with TA support from the ADB.  Projects are identified, formulated and implemented by line ministries, and should contribute to the achievement of sectoral and SDS objectives. They are appraised, monitored and evaluated by the MoF.  Public sector projects above SAT$100,000 are approved by the CDC and included in the Public Sector Investment Program (prepared by the MoF) which outlines ongoing and pipeline development projects for a three-year period.

In this regard, the PSIF will require CDC approval as a whole, while it is not anticipated that it’s constituent parts (activities) will require this approval.

- Performance Budgeting requires line ministries and other government agencies to focus on outputs, and to justify these in terms of clearly specified medium-term sector policies and strategies.  These outputs, the activities that will produce them, and the measures of performance in producing outputs, are presented in three-year Corporate Plans.  Annual Management Plans focus on Corporate Plan outputs to be produced in the forthcoming financial year. CEOs in each Ministry also develop and resource a Capability Plan that identifies the skills needed by employees to deliver the Corporate Plan.  In addition, agencies are required to produce a Service Charter, which sets out how the agency will deal with its clients and monitor its performance.

The MoF is responsible for preparing the annual performance budget, based on line ministries’ budget estimates. These estimates are based on output structures that include approved public sector projects, but also include recurrent activities. Cabinet approves the annual budget, which is then submitted to Parliament to be enacted into law. The MoF is responsible for monitoring budget implementation.

### 2.2.2	Current Planning Situation

Sectoral planning processes are currently underway to form the basis of the 2005 – 2007 SDS and provide the policy and strategic framework for the identification of new development projects that could be included as outputs in Government Ministries and Corporations corporate plans.

A review of the 2002 - 2004 SDS will take place between February and May 2004, with the results being incorporated into the next SDS which is scheduled for completion in December 2005.  It is not expected that there will be major changes in the focus and direction of the next SDS.  Key sectors will continue to be education, health and agriculture along with increasing emphasis on supporting and strengthening the private sector.  Measurements of performance against targeted outcomes will be included in the new SDS.

2.2.3 Other Key GoS Systems

In addition to government planning and budgetary systems, a number of other GoS systems are important to the proposed operation of the PSIF.

The GoS procurement systems are regulated by the GoS Tenders Board Guidelines for Government Procurement by Public Tender. These guidelines were developed with TA support from the ADB and appear to cover the core requirements of the GoA Commonwealth Procurement Guidelines and the requirements of the GoNZ. The Guidelines apply to procurement under government-financed projects funded through the GoS budget, via donor aid and multilateral loans. They contain the provision to observe donor-financier guidelines where necessary.

## Issues

The GoS reform program has achieved a great deal.  Nevertheless, there are a number of critical problems identified by the stakeholders consulted which the Design Team used as the boundaries within which the PSIF was designed in order to enhance the ability of the GoS to progress the reform program. The nexus of these issues is the problem the PSIF seeks to address.

The crux of this problem is that is there is currently no existing mechanism or system which allows the GoS to consolidate and sustain achievements made under the reform program to date, and to continue to pursue selected reforms not yet achieved.  Further, and more importantly from a broader governance point of view, there is as yet no explicit whole-of-government approach to reform which integrates cross cutting issues.  This in turn impacts directly on service delivery.  Key elements currently hindering the pursuit of a whole-of-government perspective to the reform process include:

- A disjuncture between administrative and financial devolution, resulting in anachronistic legislation, plans, systems and processes in some areas;

- The need to strengthen linkages between line departments and sectoral analysis;

- The need for further devolution of financial management with in-built checks and balances, ongoing refinements to the budget process, and the introduction of a performance management and reporting system;

- Improvements in the integrity of audit processes;

- A lack of capacity in the public sector to provide independent analysis and policy advice to Government (via Cabinet) on a whole-of-government basis;

- A lack of capacity in the public sector (in terms of resources, processes and ability) to “reflect” on the achievements of the reform process, in order to accurately focus future reform efforts and to identify critical constraints within and between agencies to pursue the agreed reform agenda;

- The need to establish systems at a whole-of-government level that provide the capacity to follow up on the implementation of Cabinet decisions, and to ensure Cabinet and other Members of Parliament understand and support the overall reform agenda;  and

- Whilst there has been significant institutional restructuring and the development of government agency corporate plans, the impact of these developments has not been transmitted throughout public sector staff fast enough to improve services to the public.

### 2.3.1	Planning

The burden of planning within the reform agenda has been great - and it is here that reform fatigue is somewhat apparent.  In addition to AusAID and NZAID-funded ISP activities, there have been a range of related reform initiatives funded by other donors as well as core GoS programs and activities within the public sector.  In order to achieve the objectives of these initiatives, it is unsurprising that a tendency to focus on “ticking off” against milestones at the activity level, at the expense of an outcomes and impact-based approaches, may develop in the context of limited human resource capacities.  There is a need for a both a system-wide approach to link the different levels of planning and for a feedback mechanism to ensure monitoring and evaluation of outcomes and impact at the community level, which is the end point of the reform. This will require the time, human and financial resources and skills to ensure that the recognised intention to consult within and between government agencies, and with the citizens of Samoa, occurs during the planning process.  There is also a need for a mechanism for continuous improvement within and between GoS agencies.

Although a sound planning framework exists, the planning process is underdeveloped.  The introduction of the PSC-led Corporate Planning exercise raised concerns about the absorptive capacity of line ministries to formulate both Sector and Corporate Plans while simultaneously delivering their core functions. This led to delays in sector planning. However with the completion of the first round of corporate planning across government and the recent realignment of departments into Ministries, there has been renewed effort to focus on sector plans. One of the key issues regarding the development of multi-agency sector plans is the need to identify available funds for sector planning. The availability of these funds will be a major determining factor in their completion. Nevertheless, the plans are essential to feed into the SDS.

The table below summarises the situation regarding Lead Agencies and the Sector planning situation as of October 2003.

| Sectors | Lead Agencies | Sector Planning Situation |
| --- | --- | --- |
| ###### 1. Agriculture | Ministry of Agriculture | - Last sector plan covered 1997-2000. - Preparation for the sub-sector plan for Forestry is underway. |
| 2. Manufacturing | Ministry of Commerce, Industry and Labour (MCIL) | - No sector plan. - Resources required to develop the plan. |
| 3. Tourism | Samoa Tourism Authority | - Current sector plan covers 2002-2006. |
| 4. Commerce | MCIL/Foreign Affairs and Trade | - No sector plan. - Resources required to develop the plan. |
| 5. Finance | Central Bank of Samoa | - No sector plan. - Significant part of the Financial Reforms has taken place. |
| 6. Public Administration | Public Service Commission (PSC) | - No Sector plan as yet. Planning has not yet begun and is not expected to be complete until late 2005. - Significant part of the Public sector reform has taken place. - PSC are working on their sector plan through consultations with the Ministry of Finance. |
| 7. Education | Ministry of Education, Sports and Culture | - Current sector plan for 2001-2005. - There is capacity within the Ministry to formulate the next sector plan. |
| 8. Health | Ministry of Health | - Current sector plan for 2001-2005. - There is capacity within the Ministry to formulate the next sector plan. |
| 9. Welfare and Social Services | Ministry of Women, Community and Social Development | - No sector plan. - Resources required to develop plan. |
| 10. Construction | Ministry of Works, Transport and Infrastructure (MWTI) | - No sector plan. - Resources required to develop plan. |
| 11. Electricity | Electric Power Corporation | - No sector plan. - Resources required to develop plan. |
| 12. Water | Samoa Water Authority | - No sector plan. - There is a need of a local consultant to work together with SWA to formulate the sector plan. - The EU is most likely to fund the costs of formulating this sector plan. |
| 13. Transport | Ministry of Works, Transport and Infrastructure | - No sector plan. - Resources required to develop plan. |
| 14. Communications | Ministry of Communications and Information Technology | - No sector plan. - Resources required to develop plan. |

Source: Report on the Sector Planning Workshop held on 16 October 2003, GoS.

That few sector plans have been developed raises questions regarding the nature of the current planning processes.  It may be the case that the processes are too complex, or that Ministries lack the skills and resources to undertake these processes, which in turn raises questions as to whether resources will be available to realise and monitor the implementation of the plans.  This is critical in that the development of plans raises expectations of achievement, which if left unmet can be damaging to the reform agenda.

Where plans exist there is a reported lack of capacity in some Ministries to scope activities and programs that put these into effect, adopt innovative approaches or alternatives to known methods, or deliver mandated services.  In terms of management, more needs to be done to ensure responsibilities are delegated appropriately and that the intentions, processes and benefits of the reforms reach all levels of the public service.

### 2.3.2	Collaboration between Ministries/Agencies

For a range of reasons, collaboration and joint action among Ministries is often given low priority or overlooked in any country and the Samoan experience is no different.  Ministry CEOs are extremely busy with the day-to-day operation of their own Ministries and have little time for reflection on broader, whole-of-government issues.  They are often under pressure from their individual Ministers on portfolio priorities while being unaware of issues in other portfolios. This makes it difficult for CEOs to build on the synergy of their combined competencies and think from a whole-of-government perspective which must necessarily focus on the mix of broad priorities which make up the Government’s overall reform agenda.

The reform efforts to date have resulted in a capacity and resource gap between, and in some cases within, agencies. There is a need to address these disparities in order to lift the progress of reform to the next level and to ensure that deficits in some agencies do not become a critical mass, thereby reversing gains made in the reform to date.

# 3	PROPOSED RESPONSE

## Program Strategy

As the GoS is yet to develop its Public Administration Sector Plan, the design has not benefited from GoS preparation of a strategic framework that might guide the Public Sector Improvement Facility. The design therefore provides the required conceptual framework for the Facility, with its overarching strategy to strengthen cooperation and collaboration between public sector agencies in identifying and addressing critical constraints to public sector reform at both the strategic and operational levels defining the desired end point for the reform program.  The design proposes a core suite of activities that address strategic issues in reform, including the ability to identify constraints to public sector improvement and sector planning.  The ability to respond to immediate and emerging priorities is also addressed – and it is recognised that these issues may, in time, emerge as central issues to the reform program.

In particular, features of the Public Sector Improvement Facility (PSIF) design include:

- A flexible design which is as far as possible driven by the priorities and processes of the GoS, to promote ownership and sustainability;

- A two-component programming structure which affords the PSIF an ability to be both proactive and reactive.  The proposed design supports the development of a suite of core activities, but does not preclude responses to emerging or immediate issues within the overall strategic direction of the Facility;

- Recognising the need for a well-founded and agreed strategic focus for the Facility, the design proposes a Public Sector Strategic Review and Planning Activity to assist the GoS develop the Public Administration Sector Plan.  An important element of the plan will be the articulation of a Public Sector Improvement Framework that will outline critical areas of reform focus that are required to establish the foundations for sustainable public sector improvement.  This Framework will provide the basis upon which future Facility funding decisions will be made;

- Support for promotion of a whole-of-government approach to implementation of the reform agenda; and

- A focus on the structured transfer of the necessary management skills to a GoS team that will hold full management control of the Facility.

Adoption of this design strategy will help ensure an integrated, whole-of-government approach to the issues which underpin and constrain public sector reform at both the strategic (planning and policy) and operational (service delivery) levels.  The design also ensures that the Facility is driven by GoS reform agenda priorities, that it conforms to the expressed desire of the three governments that it will be managed by the GoS from the start and, through the two component programming structure, provides a framework that allows the stakeholders to avoid diffusion of effort while providing some capacity to respond flexibly to emerging needs.

## 3.2	Governance Facilities – Lessons Learned

### 3.2.1	Lessons for Design

Since the mid-1990s AusAID has made increasing use of Facilities (with a range of different foci) in its programs – Samoa already has access to the Pacific Technical Assistance Fund (PACTAF).  A number of significant lessons for the design of the proposed PSIF have emerged from the implementation of these Facilities:

- Form of Assistance:  It is imperative that the design of a Facility is tailored to the particular needs and circumstances of the partner country and that there is a clear rationale for a Facility as the delivery mechanism in preference to other forms of development assistance.

- Rationale:  Donors and the partner government must have a rationale for the assistance. Where the partner government is not clear of the direction of the overall reform process and does not maintain a commitment to continuous change, or where it wants to improve its functions but assistance mechanisms are unable to respond appropriately and in timely fashion, then experience shows assistance via a Facility will not be effective.

- Focus:  Facilities must manage the range of assistance provided to ensure that activities are not so diverse that the overall impact of the Facility is dissipated. Too many small activities decrease the overall ability of the Facility to contribute to the reform process.  Donors and the partner government must have a clear view of a Facility’s boundaries that is, what governance priorities can be supported, what should be referred to other assistance mechanisms, and what should be declined.

- Equity of Access:  A Facility must ensure that assistance is not captured by stronger agencies at the expense of those that require strengthening – agencies with weak governance often find it difficult to attract assistance but unless supported this can mean they will remain weak and thereby impede the overall reform process.

- Facility Management:  A Facility needs to have flexibility to meet changing demands whilst still maintaining a clear focus that meets core identified objectives.  Clear specification of the roles and responsibilities of the partner governments (and their agencies) and any contracted management or technical support agencies involved are needed in regard to: identification, approval, implementation and monitoring of the program in order to avoid confusion, overlap and neglect of responsibilities.

- Contracting issues: Contracting can be complex and therefore the issues associated with the way in which a managing contract is drafted needs careful consideration because of the potential impact on the effective implementation of the assistance and in particular the primary focus of contractor effort.

- Risk:  There is a need to identify and manage Facility risk in an appropriate way.  In particular, checks are required to ensure contracted management or technical support complies and performs effectively in relation to devolved functions. This is also essential to ensure sustainability of the assistance.

- Subcontractors should be recruited with adequate regard to sourcing appropriate levels of skill given the focus of the Facility.  Skilled personnel are often best sourced from the Public sector or consultant firms engaged by the public sector and, given the focus of much public sector reform, have relevant experience in change management.  There are patterns of behaviour in public sector organisations which are at least as important as the cultural differences between countries, and these influence the way in which organisations respond to change.  A lack of sensitivity to both social and organisational cultures can adversely affect sustainability, usually because the approach to implementation is culturally inappropriate (in both an organisational and social sense) or that the focus and output of work is not related to properly identified public sector needs.

- Output oriented approaches to managing and monitoring Facility management have proven more effective than administering inputs.  Such a focus is likely to minimise the potential for there to be overly intensive management of what can often be quite small-scale activities.

- Resourcing:  Facilities can be resource intensive.  It must therefore be recognised that facilities can be expensive in terms of the management costs involved in implementing and monitoring a range of small-scale activities. Care needs to be taken to ensure that the scope of assistance developed, management structures and administrative processes and mechanisms are justified in terms of overall benefit.

- Monitoring and Evaluation:  The performance of the Facility needs to be measured at both the overall program and sub-activity level to ensure appropriate impact. This requires a mechanism that minimises the resource cost of measurement at a complex number of levels.

### 3.2.2 Operational Lessons

The implementation of AusAID-funded facilities has also revealed a number of operational lessons relevant to the function of the proposed PSIF.

- Donor Expectations: Patient, careful and sometimes lengthy preparation processes and flexibility are required for effective governance interventions. Donors therefore need to be prepared to undertake or support frequent reviews and redirections of governance strategies - and be able to learn from them. Changes in the operational context require flexibility in responses.   Similarly, Donors should not expect quick, tangible outcomes from the PSIF.  Governance programs do not always fit well with results or outcomes based approaches to aid management. Some estimate a 10-year time frame should be used to judge the effectiveness of some governance activities.

- Need for shared understanding of concepts: Similarly, a shared understanding of key design and operational features of the PSIF at the outset will be essential.  In particular, the concepts of ‘flexibility’, 'demand driven responsiveness’ and ‘progressive engagement’ have caused confusion elsewhere.

- Establishment of Trust: Providing successful advice on governance issues requires trust and sound personal relationships between contracted management and technical support, donors and the GoS. This means governance activities need to provide opportunities for building relationships and the selection of contractors should emphasise country experience and cultural awareness.

- Technical Support: Both contracted and GoS technical support needs to be established at the outset of the program. Technical support personnel need to ensure managing/recipient agencies are conversant with the implications of proposals which they have developed (with or without the support of the FMU). Managing/recipient agencies need to have a clear understanding of all implementation issues such as the determination of realistic, robust program goals/objectives and delivery mechanisms, the identification of associated risks and the development of appropriate management strategies, and the specification of required counterpart commitments and inputs in order to achieve positive outcomes.

- Management: The PSIF will need to ensure management develops a practical method of synchronising sub-project needs for local contributions with the GoS budgetary process and for obtaining approvals for funding those needs. Expenditure across the PSIF is not likely to be even. As the Facility is established and a pipeline develops, expenditure on activities tends to build up slowly.  The three Governments will need to be prepared for a sustained and possibly increasing demand for funds over time, as the Facility processes bed down and activities progress.  The Design will need to take this into account and the PSIF/donor and GoS management will need to ensure processes are in place to manage this.

- Activities: For activities that are relatively simple in nature, a simpler design proforma or exercise is adequate and can reduce the time taken to develop operational specifications.   A range of methodologies and activities are needed to provide the support required to build individual and organisational capacity.  Experience has shown that sustainability, particularly of larger projects, is maximized if proposals include a review of completed activities and even the identification and design of next steps.

### 3.2.3 Maximising Facility Effectiveness and Efficiency

To maximise effectiveness and efficiency a Facility should be:

- Both reactive and pro-active: Facilities must be able to assist partner agencies achieve their long-term goals and objectives both at the agency level and across the whole of Government.  In this, they must be pro-active – engaging with senior government officials and working with them to develop solutions to known problems.  This requires well-articulated requests for assistance, good planning and design, and can often result in long-term engagement. However Facilities must also be able to respond quickly to immediate and emerging priorities and provide the appropriate assistance in the shortest possible timeframe. Balancing the tensions between the two approaches can be difficult.

- Strategically focused: To avoid diffusion of effort applications for assistance must be assessed against criteria which stress a focus on the Facility objectives.  Stakeholders must be very clear on what can and cannot be supported given the inevitable tension that arises when requests for assistance outstrip available resources.

- Responsive:  proposals must be actioned quickly to ensure they remain appropriate to the operating environment.

- Transparent: the selection of activities needs to be objective and consistent with Facility criteria, objectives and strategic direction, and be based on priority and merit.  Selection of sub-contractors needs to be in accordance with agreed Procurement Guidelines to ensure value for money.

- Issue oriented: proposals need to be expressed in terms of outputs or outcomes to be achieved, with defined and realistic quality and performance indicators.

- Monitored and evaluated: in terms of performance and sustainability at the levels of individual activity implementation; overall Facility performance (including management procurement processes and overall administration) and against the agreed strategic focus.

### 3.2.4	Potential Benefits from Facilities

Facilities have a number of potential advantages over other forms of development assistance:

- The potential to achieve substantial impact from relatively small investments that provide targeted and strategic interventions;

- The potential to build partnerships between government agencies (in this case Samoan and Australian and/or New Zealand government agencies);

- Scope for progressive engagement – commencing on a small scale and leading to larger levels of support as counterpart agencies demonstrate commitment and capacity to participate;

- Flexibility to respond to issues as they arise; and

- Scope for scaling the ‘program’ up or down annually on the basis of demand, changes in the delivery environment and in response to the availability of funds within the donor country program.

AusAID’s experience with facilities similar to the PSIF, in a range of countries, has seen them used effectively in three main ways:

- To provide institutions with injections of specific expertise to address clearly identified technical problems;

- To provide a rapid response mechanism in times of crisis, where traditional project modalities are too slow and cumbersome; and

- To act as a search mechanism to identify where support can be most effectively utilised.

## Selection of the Response Strategy

The Design Team consulted widely amongst Samoan stakeholders including the CEOs of ministries and representatives of civil society and the private sector; and with staff, both expatriate and Samoan, working on current ISPs.  It is clear that there is widespread support for a Public Sector Improvement Facility.  Several key messages were repeated throughout these consultations, and these provided a framework for the proposed design:

- There was an unambiguous desire on the part of the GoS to resource (in terms of management staff) and manage the PSIF in the long term but unanimous self-recognition that the GoS team would need support and capacity building in the short to medium term;

- There is a need for transparency, accountability and equity in the management and decision making processes of the Facility;

- The Facility should strive to reduce the gaps in capacity between public sector agencies, rather than (inadvertently) increase this gap;

- The Public Service does not have the capacity or resources, from a whole-of-government perspective, to analyse the achievements of socio/economic reform to date, and only by doing this can it focus future reform efforts and identify critical constraints within and between agencies to pursue the reform agenda, and move forward cohesive and coherently to the next level of development; and

- The activities funded by the Facility should reflect the key priorities of the GoS, as outlined in the Strategy for the Development of Samoa, and it is therefore important that:

  - these priorities be clearly articulated in the criteria against which proposals will be assessed,

  - all activities ultimately supported by the Facility must be able to be justified in terms of how they contribute to improved service delivery to the community.

# 4	DESCRIPTION OF THE PUBLIC SECTOR IMPROVEMENT FACILITY

## Overview

The PSIF is designed to provide a flexible and responsive mechanism for supporting a program of public sector reform-oriented governance activities which have been identified as contributing to improved efficiency and effectiveness across the Samoan public sector and which build upon the benefits achieved to date under the range of ISPs which have been funded by Australia and New Zealand; or which respond to immediate / emerging needs within the public sector and which may, over time, themselves become part of the core PSIF program.

There is a need to consolidate and sustain achievements, and to continue to pursue selected reforms not yet achieved.  Importantly, progress still needs to be made in establishing a whole-of-government approach to reform which integrates cross cutting issues and adequately involves both civil society and the private sector.  Support for planning, at a whole of government, sectoral and Ministry level; and improved collaboration between Ministries/Agencies, are areas in which the PSIF may effectively assist the GoS to pursue its public sector reform agenda.  Improvements in these areas are the desired end point of Facility assistance.

All activities carried out under the PSIF will take account of GoS policies and the direction of the GoS reform agenda.  The Government of Australia (GoA) has articulated a desire to ensure that its strategies “…. increasingly engage with and be driven by partner countries’ own frameworks for development”.  NZAID similarly requires “…that development should be a country-led, participatory and inclusive process based on partnership and local empowerment… The needs, aspirations and priorities of each partner country and its peoples should ideally be articulated and expressed in country-led national development strategies…”

The PSIF is designed to maximise the potential for GoS ownership and management, as stressed in the Design TORs and reinforced during the Design Mission, by incorporating a clear strategy for the building of management skills in a GoS team and, where appropriate, utilising and building upon existing processes and structures in Samoa.

Following the Design Team’s in-country consultations, several options were considered prior to finalising the design alternative proposed in the FDD.  The structure, operational features and management of the design decided on reflect the views expressed during these consultations, particularly in terms of where the Facility management should be sited, and the management of it.  The design also reflects the consultation between the three governments that preceded the design mission, clearly expressed in the TORs as a desire for a Facility managed, as far as possible, by the GoS.

In reaching its conclusions the Design Team gave consideration to various options for both management of the Facility and its structure.  An entirely GoS-managed Facility (with no external support provided) was considered, and discussed with stakeholders.  However this was not recommended for a number of reasons:

(a) 	a strongly expressed desire of GoS agencies, including MoF, for external assistance in the short to medium term, to develop GoS capacity to manage the Facility, regardless of where within government this management unit is located;

(b) 	the need to develop the capacity within the GoS to identify and maintain ongoing linkages with appropriate external (e.g. Australian or New Zealand) organisations from which technical expertise could be drawn to assist with Facility activities; and

(c) 	as a risk minimisation strategy given the views expressed in (a) above.

The option of tendering out all operational aspects of the PSIF was also considered, however this was rejected given the strongly stated desire of the GoS to manage and own the Facility right from the start. The lack of sufficient depth of local capacity to undertake the recommended contracted support roles rendered inappropriate the option, which was explored, of contracting these roles out within Samoa only.

It will be important that activities supported by the PSIF are strategically selected to ensure that the PSIF is the most appropriate funding mechanism for the particular activity.  The PSIF will, therefore, need to remain cognisant of the availability and scope of other governance projects and parallel sources of funding, including joint NZAID/AusAID supported in-Country training programs, donor-funded ISPs, regional technical assistance facilities, NZAID funding mechanisms, and other donor programs particularly ADB support.  Annex 11 provides a summary of the most relevant of these parallel projects and funding mechanisms.

For Ministries receiving assistance under ongoing ISPs, it is recommended that their primary source of additional similar assistance should be the ISP itself.  Maintaining the integrity of assistance within the ISP minimises the chance that assistance is diverted from the key strategic priorities of the agency being assisted.  However this does not preclude these agencies from participating in PSIF-funded activities led by other agencies or where the assistance sought is totally outside the goal and purpose of the ISP.  Similarly, the PSIF is well placed to provide any follow on support required at the completion of an ISP, or the provision of assistance for inter-agency activities which meet the strategic aims and objectives of the PSIF. Provision of assistance from an ISP to one part of a Ministry will not exclude other parts of the Ministry accessing support from the PSIF through these inter-agency activities provided that it can be demonstrated that the proposed activities will complement that being provided by the ISP.

The FMU and RG will need to foster a close relationship with the Aid Coordinating Division of the Ministry of Finance and  develop practical management processes to ensure projects proposed under the PSIF are not eligible for assistance under other funding windows or from other donors and have not been declined funding under the GoS regular budget bids for reasons that would preclude PSIF support. This co-ordination will be enhanced by the placement of the Review Group in the MoF, as discussed below.

It is also anticipated that the PSIF may, over time, attract funding from other sources, such as other donor programs and possibly the GoS itself, thereby allowing the benefits of the PSIF to be leveraged and contributing to improved policy dialogue, greater coherency with GoS development objectives and improved donor coordination.

Nevertheless, there is a possibility that too much will be expected of the PSIF, especially in the short to medium term. As noted, it can take several years before the impacts of governance activities become apparent. The PSIF cannot therefore be expected to be the sole way in which AusAID/NZAID provides support for GoS reform efforts.  While it can provide the backbone of and sustain that support, as noted elsewhere, ISPs are being sought in a number of key areas and there will continue to be a need for high level technical assistance outside the parameters of the PSIF, such as that provided under PACTAF, to some sections of government.

In addition to consistency with the stated intention of the GoA to “…better support partner government programs and systems” and the stated aims of AusAID/NZAID support for the PSIF as articulated in the Design Team Terms of Reference, the PSIF has been structured in a manner that will ensure that it becomes a key tool for reinforcing and progressing the public sector reform achieved to date.  The ability to undertake longer-term (albeit of a small-scale nature) initiatives that, amongst other things, support reforms previously introduced under ISPs, will promote sustainability.  In this regard, issues such as Facility and individual activity contracting, management and reporting procedures reflect, to the extent possible, the procedures already in place within the Samoan public sector and ensure transparency, accountability and cost effectiveness.  In addition, the recommended management structure and arrangements are designed to build the capacity of a GoS-funded Facility Management Unit (FMU), sited in the Policy Coordination Unit of the MPM. (Component 3).

A core program of activities developed and supported by the PSIF under Component 1 will address key GoS strategic goals and priorities.  Activities within this component will be carefully designed and focused to ensure their objectives and outcomes are relevant across the public sector and are sustainable.

By supporting small scale activities which respond to immediate and emerging priorities, within the overall framework of improved public sector efficiency and effectiveness, Component 2 of the PSIF is intended to provide a mechanism for addressing adjustments needed to address unmet or changing sectoral or planning priorities, allowing the PSIF to remain relevant and responsive to its operating environment.

Separating the program delivery elements of the design into two components not only ensures that the stakeholders focus on the different aims and expectations that arise in core programs as well as those associated with immediate and emerging needs, but also provides a tool to ensure that a tight focus can be maintained.  As mentioned in terms of lessons learned (Section 3.2), facilities are often presented with many more proposals than can be funded with the limited resources available.  This dilemma, together with demand to be flexible in responding to emerging needs and priorities, can lead to programming tensions.  The provision of a core program component allows the key stakeholders to commit a defined level of activity funding to a more tightly focused set of objectives leaving the balance of funds to be applied to a wider range of small scale activities under the second component.

Complementary to the need to articulate a clear focus (particularly for core programs) there is a need to specify a split in the funds allocated to approved activities to ensure that support for core program activity is not undermined by the less strategic (in a long term planning sense) support likely to be delivered under Component 2.  Any eventual split must be determined/agreed by the three governments; however the Design Team would recommend that as a minimum at least 60% of available program funds should be directed to Component 1 activities.

The design also recommends that a GoS-funded Review Group (RG) be established within an appropriate GoS agency to provide independent technical oversight to ensure that the proposed projects being funded and managed by the Facility have technical and developmental integrity.  It is also proposed that the RG undertake reviews of a sample of projects (nominated by the Facility Steering Committee in consultation with the donors) to provide an independent evaluation of performance against the approved designs. It is recommended that this occur at least annually.  In this, the design is not seeking to create a new structure but is building the capacity of existing GoS staff who are currently responsible for reviewing development projects funded by the GoS.  With the addition of donor representatives on the annual review of sample activities, this review could also assume the duties of previously used review mechanisms such as TAGs – thereby further simplifying Facility management and reducing overheads.

## Goal and Purpose

The goal of the Public Sector Improvement Facility is to improve the efficiency and effectiveness of Samoa’s Public Service to support Samoa’s national development priorities.

The purpose of the Public Sector Improvement Facility is to strengthen cooperation and collaboration between public service agencies (and between them, the private sector and civil society), in identifying and addressing critical constraints within the GoS public sector to effective service delivery through a range of institutional strengthening initiatives.

## Component Structure and Objectives

The design of the PSIF has four components (this section should be read in conjunction with Annexes 6 and 7 for more detailed explanation of procedural processes, and the roles and responsibilities of FMU, CST and implementing agencies):

Component 1:  Core Program Activities

Objective:  	To support (from identification to completion) strategically identified core activities which promote continued reform across the Samoan public sector and which improve the ability of the public sector to effectively deliver quality services.

The emphasis of this component is to identify, design and implement a set of core activities that are focused on addressing key issues impacting on continued public sector reform.  It is critical, in order to ensure the relevance and impact of the PSIF, that core program activities are strategically selected.  This component will, through promoting improved collaboration within the public sector, and between it and civil society/private sector agents, reinforce the gains made to date by Samoa’s reform program, including through previous and current AusAID/NZAID assistance, and ensure that the PSIF is engaged in key priority areas of public sector reform and service delivery.

It is intended that these activities, while they may be directed at/located within a specific department or ministry, will be focused on improving cooperation between agencies and will, therefore, potentially impact across the entire public sector.  In most instances, assistance to agencies will be based on activities drawn from their respective strategic or sector plans and will be directed at technical assistance, training, capacity building, institutional strengthening and other needs.   These activities may be of varying size and duration – ranging, for example, from ongoing provision of high level technical or policy advice; targeted technical assistance and training; the development of twinning arrangements between agencies in Samoa and other countries; to the development of sector planning frameworks/processes in one or a number of departments.

Output 1.1:	Public Sector Strategic Review and Planning Activity.

This foundational activity will assist in defining the focus of the PSIF on public sector reform.  The Public Sector Strategic Review and Planning activity will support the key central agencies (Public Service Commission, Ministry of Finance and the Ministry of the Prime Minister) to develop the GoS Public Administration Sector Plan (see Annex 6).  A key element of the Sector Plan will be the articulation of a Public Sector Improvement Framework (to be developed during the first six months of the PSIF’s operation) that will outline the critical areas of reform focus required to establish the foundations for sustainable public sector improvement.  Key elements of that Framework will be the development of a series of public sector improvement principles, strategic priorities and a set of funding principles/criteria (including contestability) that will guide how funds available under the PSIF will be directed.

Output 1.2:	Core program activities approved by the Facility Steering Committee (FSC) and endorsed by the Facility Coordinating Committee (FCC).

The FMU, with the assistance of a Contracted Support Team (CST) where required, and in consultation with GoS ministries, will formulate core program activities and submit them to the FSC for consideration and approval and the FCC for endorsement.

The exact specification of the initial set of core program activities and budget will be developed by the FMU in the initial Review and Forward Program (RFP).  See Output 4.5 and Annex 7.  The GoS propose that an existing PSC Appraisal Committee is best placed to prioritise key activities while the PSIP is developed under the Facility.  The FMU will, in consultation with the GoS, develop a consolidated list of activities that meet the criteria developed. The GoS acknowledge that all proposals, including those developed in advance of the PSIP, would need to meet agreed guidelines and criteria.

Output 1.3:	Approved core program activities delivered in accordance with approved procedures.

Subject to the management requirements of each program activity, once approved, the FMU will either undertake directly, or assist the managing agency tender, core program activities and appoint sub-contractors (where relevant) to manage and implement the activity in accordance with approved procedures. The sub-contractor will be required to submit progress reports, via the managing agency, in accordance with the activity design specifications.

Output 1.4:	Core program activities monitored and evaluated.

Each activity design will include a monitoring and evaluation plan to ensure the quality of milestones and that the objectives of the activity are met.  The requirements of activity level monitoring are detailed at Section 7.3, and specific criteria and processes will be outlined in a PSIF Operational Handbook.

Component 2:  Immediate and Emerging Priorities (IEP)

Objective:  	To facilitate GoS response to their immediate and emerging priorities in public sector reform.

The intention of this component is to provide the Facility with a mechanism which is more flexible and responsive than Component 1, allowing the PSIF to deliver short-term, smaller scale targeted activities of less than 12 months duration to a range of partner agencies.  While not narrowly defining the criteria governing the selection of activities to be supported under this component, activities must conform with the overall Facility goal and purpose and be consistant with the Public Sector Improvement Framework.  It is anticipated that the value of these activities will be below an amount to be agreed during the inception phase of the Facility.  Given the nature of the activities which it is envisaged this Component will support, the nature of the activity approval process may also differ and be less complex from that of Component 1 activities.  Annex 6 details the approval process.

It is not anticipated that the PSIF will invite proposals under this component, although the communication strategy will ensure that all CEOs, Departments and authorities are aware of its availability and its parameters (see Output 4.3). Rather the FMU will identify or be approached by a potential partner agency for activity funding.  In determining which proposals are to be recommended to the FSC for support, the FMU may take the following issues into account:

- that the proposal’s goal(s) and objective(s) conform with the goals and purpose of the PSIF and the Public Sector Improvement Framework;

- that the estimated cost of the proposal can be accommodated within available funding (taking into account competing requests for support);

- that appropriate technical assistance can be located either internationally or in Samoa; and

- that the estimated resource costs associated with the proposed activity can be justified in terms of the value of the anticipated outcome to the partner agency(ies).

In some cases, proposed core program activities for reasons of technical or developmental complexity, may require the contracting of specialised technical or design expertise to assist in design preparation.  In such instances, consideration may be given to approving an activity under this IEP component to allow such design assistance to be purchased.

It is anticipated that in some instances, activities assisted under Component 2 may, over time, become core programs if their direction is confirmed by the FMU as warranting consideration as a core program and this recommendation endorsed by the FSC and FCC.  The activity would need to conform to the defined and articulated focus for the core program.  As there is a tendency for activities to be rolled over it is recommended that an automatic requirement in rolling over an activity is that the proposal to continue must go to the FSC for approval as a core activity before it can be considered for further support.  Given that such activities are likely to be sizeable it is also recommended that they form part of the sample of activities to be reviewed in an annual review exercise (see Section 5.5).

Output 2.1:	IEP guidelines and approval processes confirmed and documented.

The approval process for the flexible response mechanism will largely reflect the process for core program activities (see Annex 6). The FMU will be encouraged to develop systems that are transparent, accountable, functional and, most importantly, ensure the delivery of quality aid interventions in an efficient and effective manner.

Output 2.2:	IEP program activities delivered in accordance with approved procedures.

The FMU will either undertake directly or assist the managing agency tender activities and appoint sub-contractors (where relevant) to manage and implement the activity in accordance with approved procedures. The FMU will require the managing agency to submit progress reports in accordance with the activity design specifications.

Output 2.3:	IEP program activities monitored and evaluated.

Each activity design will include an appropriate monitoring and evaluation plan to ensure the quality of milestones and that the objectives of the activity are met.

Should further funding be required, the FMU will consider whether these activities should be transferred to the core program component (i.e. the activities are necessary for meeting the approved core program goals and objectives).  The FMU will also report on IEP activities through the six-monthly RFP report (refer Annex 7).

Component 3 – Initial Capacity Building of Facility Management Unit

Objective:  	To develop and implement a program of support for building the capacity of the GoS Facility Management Unit (FMU) to effectively implement and manage the PSIF.

The design recommends that appropriate weight be given, in the initial stages of PSIF implementation, to both the delivery of activities which address constraints to public sector service delivery, as articulated in the Facility purpose; and to capacity building of the FMU as one means of enhancing the overall capacity of the MPM.  This balance will progressively shift towards an activity focus as capacity within the FMU is developed, such that by the time of withdrawal of the Contracted Support Team (CST), delivery of activities will be the primary focus of the PSIF.

This recommendation reinforces the directions of the Design TORs that “An innovative and progressive design particularly with respect to management arrangements is encouraged.  The design should investigate options and implications for accountability outside of the standard AMC management model including full management by GoS and partial management by GoS with transitional AMC support possibly contracted directly to GoS.  To the extent possible, it is recommended that the role of an AMC, if any, should be minimised”.  The TORs go on to state that “The GoS are considering appropriate management arrangements and have advised that there are cost effective management capabilities available in Samoa.  The GoS also see value in capacity building and strengthening ownership if managed within Government.  The GoS have also proposed that it is timely to consider operationalisation of the Facility through budgetary support.  If requested by the GoS, the Facility should provide interim/transitional support to build GoS capacity to manage the Facility” .

The management of the PSIF, in and of itself, is therefore a mechanism for promoting good governance and capacity building at the highest level of the public service.  That is, in addition to providing support for program activities which support reform and build public sector capacity to deliver quality services, the implementation/management of the PSIF itself is an activity which responds directly to the GoS reform agenda and one that can be achieved within the management cost of the facility rather than absorb program funding.

The role of the CST under Component 3 is to provide support to the FMU in the initial management of the PSIF through both ongoing skills transfer and more formal training processes where required, with the intention that CST’s role in building FMU (and therefore MPM) capacity will decrease over time and that the focus of the PSIF progressively shift towards activity delivery.

This component is the sole responsibility of the Contracted Support Team (CST) and will form an important part of the CST contract, to ensure that adequate attention is given by the Contractor to capacity building of the FMU.  The responsibilities of the CST are detailed in Section 5.  It is the intention of the design that this component be phased out over time, as FMU staff develop the range of competencies required to effectively manage the PSIF without external assistance.  In this regard, a Review of Transitional Support (see Section 7.5) will be undertaken at the commencement of Year 3 to assess the progress made by the CST in transferring the necessary management skills to their GoS counterparts, with a view to confirming the timeframe for ending transitional management support.

Output 3.1	Pre-mobilisation Support

To minimise the hiatus that may occur in program delivery due to the need to establish key management structures, a pre-mobilisation activity may be undertaken by selected CST members one to two months prior to PSIF mobilisation and to revisit and confirm the design as necessary.  The pre-mobilisation visit could, if required, also assist with finalisation of FMU and RG staffing and establishment of the PSIF office, preparatory discussions on the Public Sector Strategic Review and Planning Activity and an initial program of assistance..

Output 3.2	FMU capacity/competency analysis undertaken by CST.

The CST (HRD Short Term Adviser) will undertake a capacity/competency analysis of GoS staff members appointed/contracted to the FMU/RG and complete a systems capacity assessment of the MPM to support the FMU.  This will assist in the development of an HRD Plan (Output 3.3) and form the baseline against which testing and reporting of the progressive achievements of the necessary competencies is undertaken in Output 3.3.

Output 3.3	Development of an HRD plan for FMU/RG staff and provision of ongoing skills transfer to FMU staff throughout period of transitional support.

Based on the findings of the analysis undertaken under Output 3.2, the CST HRD Adviser will develop an appropriate HRD training and skills development plan that will provide the necessary training/mentoring to the FMU and RG staff to ensure that they have the necessary competencies to effectively manage the PSIF over the medium term.  The HRD Adviser will initiate the program developed.  The longer-term implementation of the HRD plan will be the responsibility of the CST.

Output 3.4	Regular assessment of skills and systems development against the approved HRD plan.

The CST will undertake assessments every 3 months to gauge the progressive development of skills/competencies of FMU/RG staff and MPM systems against the initial baseline analysis undertaken in Output 3.2.  These assessments, together with an outline of any changes implemented to the HRD plan as a consequence of the assessment findings, will be made available to the FMU/RG staff, the MPM, and to NZAID and AusAID.

Output 3.5	Develop, and assist the FMU to implement a program of workshops/materials designed to develop partner agency capacity, if required, in activity management, monitoring, evaluation and reporting.

The CST will assist the FMU to assess the capacity of partner agencies to effectively undertake activity management functions, in order to develop a suite of training workshops/materials which can be tailored for delivery to those agencies where assistance is required; and will subsequently assist the FMU to deliver this program of workshops as activities are identified and developed by agencies.  It is the intention that, over time, the FMU will develop sufficient skills in the development and delivery of these programs that they are able to undertake these functions independently of the CST (Output 4.8).

Output 3.6	Prepare PSIF Establishment Report.

The CST will prepare a report, to be submitted to the three governments at the end of month 6, on the establishment of the PSIF.  While the responsibility for management of the PSIF lies primarily with the GoS FMU, the role of the CST is to build the capacity of the FMU to effectively do so.  It is therefore anticipated that the CST will also be involved in the development of Outputs 4.1 – 4.7.    These outputs are of critical importance to effective implementation and, while it is anticipated that the FMU will have the capacity to review and update these subsequent to their creation, they will not have the capacity in at mobilization to develop these outputs without substantial CST assistance.

While the Establishment Report will include commentary on the achievement of these outputs, it is recommended that the initial documentation associated with outputs 4.2, 4.3 and 4.5 be submitted to the partner and donor governments for approval as they are developed.

Output 3.7	Establish a web-based management information system to support effective Facility management and information dissemination.  The system should be able to manage, document and track the following:

- receipt of expressions of interest and full proposals;

- assessment and approval/rejection;

- contracting/procurement;

- project implementation, progress and completion reports;

- project budgets;

- financial and physical reporting;

- progress reporting and monitoring;

- cumulative expenditure and forward commitments;

- project finances and invoices; and

- lessons learned.

The web-based management system should provide guidelines for applying for Facility Funds as well as on-line application forms.

Component 4 – Facility Management and ongoing FMU Capacity Building

Objective:  	The effective management of the Public Sector Improvement Facility by the FMU.  This will involve continued skills transfer by the CST to FMU Counterparts over the period of CST support.

The effective establishment of management functions and a consultative development approach to activity planning and management cycle procedures and protocols will be critical to the success of the Facility.   The design also allows for the FMU to assist partner agencies in building their capacity to effectively manage and monitor activities.

The ongoing management of the PSIF is primarily the responsibility of the GoS FMU.  This component describes the outputs that must be delivered by the FMU, with CST support in the medium-term, to ensure that the PSIF becomes and remains an effective mechanism for supporting public sector improvement.  The role of the CST will be to support the FMU to produce the following outputs:

Output 4.1	Establishment of Facility Steering Committee and appointment of FSC members, and provision of ongoing secretariat support to the FSC.

The FMU, with the assistance of the CST, and in consultation with GoS, will be required to develop a brief charter for the operations of the FSC and a position statement outlining the roles/responsibilities of FSC members, including the required skills and experience of FSC members, and to liaise with GoS in the appointment of these members.

The FSC will convene at least every six months to consider the RFP, the FMU will provide ongoing secretariat support to the FSC.

Output 4.2	Establishment and operationalisation of processes and procedures documented in an PSIF Operational Handbook.

The FMU, with CST assistance, will be expected to establish sound activity and financial management and accounting procedures and systems which ensure effective Facility management including regular reporting on financial commitments and expenditure.  The FMU will also need to develop financial management and accounting system for use by partner agencies, in managing the funds provided to them by the PSIF.  This system should be aligned as closely as possible with the systems in use by GoS (such as the GoS Planning Manual) and address the financial management requirements of AusAID and NZAID.

The FMU will also assess the activity planning and management needs of the PSIF (Components 1 and 2); and regularly review and make recommendations on the scope for improving these procedures as part of the Facility Review and Forward Planning process (RFP).  (Refer Output 4.7).

An Operational Handbook will be the key tool for PSIF operations and, based on its approved processes and procedures, future audits and reviews of facility operations will be undertaken.  A clear, concise handbook will also minimize the operational difficulties that may occur if and when there is staff turnover within the FMU.

The Operational Handbook should include financial, activity cycle, and specification of agreed strategic foci, funding parameters and approval criteria for Components 1 and 2 that will have been determined as a consequence of undertaking the Public Sector Strategic Review and Planning Activity (Output 1.1).  The Operational Handbook should be updated regularly as necessary.

Output 4.3	Development of Communications Strategy.

With the assistance of the CST the FMU will be required to develop a Communication Strategy for the facility for distribution to GoS agencies in order to raise awareness of the mechanism.  It will be necessary to create clearly defined parameters in the strategy for access to the mechanism in order not to create expectations that funding will be forthcoming for all.  This should include information on eligibility criteria, selection criteria, contracting procedures, monitoring and evaluation requirements and proposal formats.   It should also include information on the Public Sector Improvement Framework.

In the case of IEP activities, this will include advice on when the truncated approval process may apply (based on real time imperatives that make the normal approval cycle inappropriate).

It is important that organisations can easily and quickly obtain relevant information on the likelihood of receiving support under this mechanism. The communication strategy should effectively discourage those proposals that are clearly unlikely to be funded, although the FMU should have information to redirect such proposals to other donors or schemes, if appropriate.

Output 4.4	Establishment of the Public Service Improvement Fund, and provision of regular financial and annual audit reports to the three governments on Fund activity.

The FMU will, in consultation with GoA, GoNZ and GoS, establish a trust account in a financial institution acceptable to the three Governments to hold donor and possibly GoS funds to be support approved activities.

The FMU will, with CST support where required, will establish guidelines for the operation of the Public Service Improvement Fund that include: the specification of the type of activities that can be funded, the signatories to the account and delegations, the appointment of an independent auditor that will conduct an annual audit of the account, and the specification of financial reports to the Governments showing both expenditure to date, estimated monthly expenditure over the balance of the financial year and indicative commitments in out-years.  These guidelines will be incorporated into the Operational Handbook (Output 4.2)

Output 4.5	Assist the FMU to develop a Monitoring and Evaluation (M&E) Framework.

The Transitional Review Adviser will assist the FMU to develop an appropriate M&E Framework and M&E Tools for the PSIF.  The M&E Framework should be prepared prior to the first Facility Steering Committee meeting.  (The M&E Framework will be annually reviewed and updated by the FMU in light of the activities funded by the PSIF to ensure that it remains relevant to the direction of the Facility).

Output 4.6	Assist the RG to develop and implement appropriate activity appraisal and review guidelines.

The Transitional Review Adviser (TRA) will assist the GoS Review Group to develop an appropriate set of guidelines for the appraisal and review of activities funded by the PSIF.  This will include the development of Activity Completion Reporting proformas which are to be completed by partner agencies.  The TRA will mentor the RG staff in developing their capacity to undertake this appraisal and review process.

Output 4.7	Preparation of the first Facility Review and Forward Plan (RFP).  Regular preparation of subsequent RFPs.

The Review and Forward Planning process is a key tool in the activity management and planning cycle.  The RFP process performs two primary functions: a review function that reports on activities recently completed and underway, and a planning function outlining the proposals for new activities being presented for the FSC’s consideration and approval.  The exact specification of the initial set of core program activities and budget will be developed by the FMU in the initial Review and Forward Program (RFP) See Annex 7, Facility Review and Forward Planning Process, for detailed explanation of RFP processes.  The CST will provide support as required in the development of the RFP.

Once approved by the FSC this document will be submitted to the FCC for endorsement by the participating Governments.

RFP’s will be prepared by the FMU for all subsequent meetings of the FSC.

Output 4.8	Ongoing delivery of the workshops developed under Output 3.5.

As agencies identify and develop specific proposals for PSIF funding, the FMU will assist in the modification of proposals as required and deliver to these agencies the training modules developed under Output 3.5.

## Facility Location, Duration and Allocation

It is recommended that the management of the PSIF reside with a GoS-appointed Facility Management Unit (FMU) within the Ministry of the Prime Minister (MPM).  It will be a requirement that the GoS contract/employ the staff of the FMU and a MoF-based Facility Review Group (RG), and provide office accommodation for the FMU.  The staff of the FMU will be counterparted by a donor-funded Contracted Support Team (CST) over the medium-term.

The Facility duration is five years, with an annual initial contribution by AusAID of AUD2 million and NZAID of NZD1 million.

## Eligible Assistance

The principles of progressive engagement should underpin the development of activity proposals. It is thus anticipated that assistance, particularly under Component 2, is likely to commence with smaller scale interventions and scoping studies.  This will allow for progression to further stages of assistance depending upon the degree to which earlier assistance has effectively met the needs of the recipient agency and an assessment of the commitment, performance and capability of the managing agency.  Where activities are complex, approval may also be sought for short-term technical assistance or other support for the feasibility and design of activities to be supported.

There are a number of broad parameters that can be established for the funding of proposals under the PSIF.  However it is important that more specific guidelines reflect a process of consultation between GoS public sector agencies and Facility partners (GoS/AusAID/NZAID and the CST) in determining how to allocate funding.   The development of more detailed criteria, and proposal proforma, will be an important initial activity in Facility implementation.  While noting that a specific set of focal criteria will apply to Component 1 activities to ensure that the critical core program remains tightly focused, the overarching criteria in determining funding support to both Components 1 and 2 are:

- That proposals clearly articulate the link between the project and its intended outcome;

- That proposals clearly demonstrate how the activities to be undertaken within the project will result in the achievement of the identified outcome; and

- That the outcome is demonstrably consistent with the objectives of the PSIF and the Public Sector Improvement Framework  in terms of addressing critical constraints to service delivery.

- The proposal presents an opportunity for engagement with a key agency in terms of ongoing contribution to overall reform process;

- The PSIF is the most appropriate mechanism for providing the assistance requested;

- Value for money – that the cost of the proposal and the type of activity proposed represent the best and most cost effective way of achieving the desired outcome;

- Appropriate counterpart agency contribution – proposals should clearly identify what contribution will be made by the applicant agency(ies); and

- The project proposed includes a strategy for promoting sustainability of the outcomes achieved.

The specific intention of Component 2 is to provide flexibility and responsiveness in responding to emerging issues or priority areas.  Selection criteria for projects funded under this component must therefore reflect this intention.  In addition to the criteria outlined above, possible criteria for activities under this component include:

- A current and strategic issue is being addressed;

- The project has an opportunity to have a quick impact; and

- The project provides a potential for longer-term engagement between the agency and the ongoing reform program.

There are certain types of activities that are not considered appropriate be to funded by the PSIF.  These include:

- Major capital equipment.

- Funding of agency core and recurrent costs.

- Costs associated with regular attendance at, or hosting of, recurring conferences (that form part of the core function of the agency attending/hosting).

- Sitting or attendance fees associated with participation in project activities.

# 5	Management Structure and Roles and Responsibilities

## Overview

The PSIF will be required to manage a wide range of activities which will range in technical and developmental complexity, resource cost and size.

Critical to the success of the Facility will be the development of a sound, efficient activity planning and management cycle that can not only manage a pipeline containing a number of core program activities but can also respond quickly to requests for a wide range of short term assistance.

The management structures developed must:

- be designed to deliver a cost-effective program of assistance and also fulfill the wish of the three governments that the PSIF is, managed by the Government of Samoa from the outset, but with short to medium term support from a contracted support team;

- must not create unnecessary levels of administrative bureaucracy and wherever possible be harmonised with standard administrative procedures of the GoS;

- wherever possible utilise existing systems and structures (particularly within the GoS)

With these fundamental requirements in mind, this design proposes the establishment of a number of administrative structures that provide the necessary management oversight for the programs supported by the PSIF.  These are:

- a Facility Coordinating Committee (FCC)

- A Facility Steering Committee (FSC)

- a Facility Management Unit (incorporating a contracted support team in the short to medium term)

- a Review Group (incorporating a contracted transitional review adviser in the short to medium term)

- a Public Service Improvement Fund

## The Facility Coordinating Committee

The Facility Coordinating Committee (FCC) is the body that provides the three Governments (Samoa, Australia and New Zealand) with the opportunity to review Facility progress and performance and allows the three government stakeholders to ensure that funding is being committed and spent in an effective and efficient way.  As the PSIF peak governance body, the FCC will provide transparency and high-level accountability.

The FCC will include one representative from each Government.  Australia and New Zealand will be represented by nominated officers from their respective aid agencies.  The GoS will be represented by a nominated official from the Economic and Aid Division of the Ministry of Finance.

The FCC will meet twice a year immediately following the meeting of the FSC and will consider the program approved by the Steering Committee (it is recommended that the report provided to the FSC be also submitted to the FCC together with a copy of the minutes of the Steering Committee Meeting).  The FMU will provide the Secretariat for the FCC.

The FCC will approve the strategic focus of the PSIF as developed through the Public Sector Strategic Review and Planning activity, Public Sector Improvement Framework (and any subsequent revisions to the Public Administration Sector Plan).  Provided all three parties are satisfied that the performance of the Facility is acceptable and that the forward program conforms with the goal and purpose of the PSIF, the FCC will endorse the program of activities and communicate this to the FSC and FMU.  If this is not the case, there will need to be high-level negotiations to resolve the issues of concern to the satisfaction of all parties.

Should other donors wish to contribute to the Public Service Improvement Fund at a later time, consideration will need to be given to expanding this group to include all contributing donors.

Proposed Structure for Public Sector Improvement Facility

The diagram below outlines the management structure for the Facility.

Facility Management

Program

Funds

Proposed

Program

Endorsed

Program

GoS

Review Group

Ministry of the

Prime Minister

Facility Management

Unit

Donors

GoA/GoNZ

Contracted Support Team

Transitional Review Adviser

Facility Steering

Committee

Core Program

Immediate and Emerging Priorities Program

Activity 1

Activity 2

Activity 1

Activity 2

Facility Coordinating Committee

GoS/GoA/GoNZ

Approved

Program

Public Sector Improvement Facility

Project Activities

Public Sector Improvement Fund

Management funds

## 5.3	The Facility Steering Committee

### The FSC is the peak body charted with overseeing the work of the PSIF.  The FSC will meet regularly to review and approve the program ensuring that it meets the requirements of the GoS and the objectives of the Facility.  The functions of the FSC will include:

- program review and approval, which will include considering proposals for assistance against agreed selection criteria;

- program performance review;

- provision of high level advice on the strategic direction of the program.

The FSC will

- meet formally every six months at which time they will consider a Review and Forward Plan (RFP) prepared and presented by the Facility Management Unit;

- deliberate on the GoS priorities to be accorded to particular proposals.   While the FSC may have, in some instances, views on the technical content of proposals, the technical assessment of proposals is not within the mandate of this body.

In the case of proposals for which a time imperative means that formal consideration of the proposal cannot fit within the formal six monthly planning cycle, Committee representatives may be asked to consider proposals out-of-rounds.  In such cases the Chairperson may determine that a formal meeting of representatives is not necessary and that committee members can consider urgent proposals and communicate their views in writing either in hardcopy or by email.

The core members of the FSC will be appointed representatives from the:

- Ministry of the Prime Minister

- Ministry of Finance

- Public Service Commission

- A representative nominated by the Private Sector (possibly from the Samoa Chamber of Commerce and Industry)

- A representative nominated by the community sector.

It is recommended that the selection of Committee representatives be appointed not solely on the basis of the institution/constituency they represent, but that their skills, experience and capacity to undertake their role is taken into account.

To ensure continuity of representation, it is recommended that particular individuals from these bodies be appointed for two-year terms.  Representation should only change during that time where an appointee resigns or is transferred to another Ministry.

Representatives of other ministries may supplement this core membership at times should their input be considered useful when considering requests for assistance.

As with the FCC, the FMU will provide the Secretariat for the FSC.

## 5.4	The Facility Management Unit

The FMU is the body charged with the day-to-day management of the PSIF and the program of assistance that it supports.  The FMU, which will be appointed by the GoS, will:

- assist with the identification of projects and assist managing agencies develop activity proposals for FSC consideration;

- prepare program documentation for FSC consideration;

- monitor program implementation and prepare progress reports for the FSC;

- administer the Public Sector Improvement Fund;

- monitor and evaluate the performance of projects against the approved activity designs;

- monitor risk and prepare risk management strategies;

- support the operations of the Review Team (including the sourcing of specialist appraisal assistance);

- report on its operations to the FSC;

- prepare the Review and Forward Plan;

- provide the secretariat for the FSC and FCC as required;

- manage information generated by the PSIF including proposals, reports and activity completion reports;

- and

- release funds to the recipient agencies for approved activities following GoS procedures. .

Depending on the capacity of the  partner line agency, the FMU may also provide varying levels of support across the range of activities associated with the project management cycle.  If required, these could include:

- assistance with sourcing and contracting the necessary assistance in accordance with approved procurement procedures;

- management of the contracts associated with approved activities; and

- assisting agencies undertake their own monitoring and evaluation of sub-contractor activity.

The Design proposes that the Unit is established as a discrete unit with the Ministry of the Prime Minister, possibly under the area responsible for supporting the Cabinet (see Section 8.1.2 for detailed discussion of this recommendation).  Such a position will ensure that its staff are not diverted from their management responsibilities and will ensure that PSIF activity is aligned with the strategic development directions determined by Cabinet.

The Facility Management Unit will be staffed by three officers selected and funded by the GoS and will comprise:

- a Facility Manager;

- a Program Officer; and

- an Administration and Finance officer.

These positions will be either contracted by or be full-time appointed officers of the Ministry of the Prime Minister.

5.4.1	Contracted Support Team

It is anticipated that the GoS FMU will require support in undertaking their tasks in the short to medium term.  To provide the necessary program of skills development, this design proposes that AusAID/NZAID and the GoS contract, through a Contracted Management Support (CMS) provider, three people skilled in project management and public sector reform, with relevant experience in counterpart capacity building and skills transfer and relevant government systems, for varying periods over the first three years of operation.

The roles and responsibilities of the CST will be:

- to assist the FMU with mobilisation of the facility including the development of operational guidelines;

- to provide a program of structured training and support to FMU staff to provide them with the necessary skills to undertake the full range of management responsibilities over a period of two years followed by a period of advisory assistance, review and reinforcement by the transitional manager in Year 3; and

- to provide ongoing and intensive mentoring of the staff of the FMU and to assist the staff to maintain and improve the operating systems developed.

The goal of the CST is to ensure that by the end of Year 3, the FMU and RG have the skills to completely manage and operate the PSIF.  The need for any CST inputs beyond those specified will be considered in the review to be undertaken at the commencement of Year 3.

The CST will comprise:

- a transitional manager (24 months, plus 6 months in Year 3) ;

- a transitional program officer (18 months over Years 1 – 2, plus 3 months in Year 3); and

- a transitional administration and finance officer (4 months in Year 1, 2 months in Year 2).

An important activity in the early stages of mobilisation will be the creation of a Human Resource Development Plan and associated training program.  To ensure that this is done promptly and that the main transitional team can concentrate on the necessary work associated with supporting Facility establishment and the progressing of the initial program of assistance, the Design Team recommends the contracting of a capacity building and training adviser for the first two months following mobilisation, with a return visit in Year 2 to evaluate progress of skills and systems development and to provide refresher skill development to staff as required.

Refer Annex 8 for detailed position statements.

The CST will be supported by the parent CMS provider to assist with the sourcing and contracting of any external advisory assistance deemed appropriate and to facilitate any organisation to organisation linkages and ensure access to innovative practices and twinning arrangements.

## Review Group

The FMU is tasked with oversighting the development, in conjunction with the proposing organization, of activity proposals and, once FSC approval has been received, of detailed activity designs.  To provide support to and accountability of this group, the Design recommends that a technical support and Review Group be established by the GoS.  The RG would provide independent technical oversight , monitoring and appraisal of proposals to ensure that the activities being funded and managed by the PSIF have technical and developmental integrity.  The RG will help to ensure that activities and administration of the Facility are integrated into the coordination mechanisms of the GoS.

The RG would also undertake, at least annually, reviews of a sample of projects (nominated by the FSC in consultation with the donors) to provide an independent evaluation of performance against the approved designs.

The RG would:

- appraise initial proposals and detailed activity designs, prepare appraisal reports and certify that the implementation strategy proposed is likely to provide the assistance necessary to achieve the identified goals and objectives; and

- conduct a performance assessment and review of a sample of activities implemented over the previous six months immediately prior to the meeting of the FSC and advise the FSC and FMU of its findings and recommendations.

The Review Group will have access to a pool of funds (managed by the FMU) from which experts with specific technical backgrounds can be contracted where there is a need for specialised technical assessment.

The RG would comprise a Principal Review Officer and an Assistant Review Officer based in the Planning Division of the Ministry of Finance.  It should be noted that the MoF have indicated that they have staff in this Division who are already responsible for reviewing approved development projects funded by the GoS.  The MoF has indicated that this work would be an extension of these existing responsibilities.  As such, the PSIF review responsibilities are unlikely to require a full time commitment but would form a major element of the nominated officers’ work.  The Assistant Review Officer position is important to minimise the possible loss of expertise should the PRO move from his/her position.  These positions will be either contracted by, or be full-time appointed officers of, the Ministry of Finance.  Refer Annex 8 for detailed position statements.

5.5.1 Transitional Review Adviser

The MoF have indicated that the officers nominated to undertake the review role will require transitional support to enhance their capacities.   It is anticipated that the GoS’ Review Group will require this support in the short to medium term.  To provide the necessary program of skills development, this design proposes that the CST include an adviser with high level skills and extensive practical experience in the areas of project design and appraisal, public sector reform and change management, to provide intermittent support over a period of three years.

The roles and responsibilities of the Transitional Review Adviser (TRA) will be to:

- assist the RG develop activity appraisal and review guidelines;

- provide a program of structured support to the RG staff to provide them with the necessary skills to undertake the full range of appraisal and review responsibilities over a period of two years followed by a period of advisory assistance, review and reinforcement in Year 3; and

- provide ongoing and intensive mentoring of the staff of the RG.

The goal of the TRA is to ensure that by the end of Year 3, the appraisal and review process is being totally and effectively undertaken by the GoS Review Group.  The need for any CST inputs beyond those specified will be considered in the review to be undertaken at the commencement of Year 3.

The Transitional Review Adviser will be contracted to provide 9 months of advisory inputs over the first three years of the PSIF.  The need for any TRA inputs beyond those specified will be considered in the review to be undertaken at the commencement of Year 3.  Refer Annex 8 for a detailed position statement.

## The Public Sector Improvement Fund

The Public Sector Improvement Fund (the Fund) will be established as a Trust account in an agreed bank in Samoa by the Governments of Samoa, Australia and New Zealand at the commencement of PSIF.

The Fund will be used to fund the projects approved by the FSC for support under the PSIF and for the contracting of any specialist advisory support deemed necessary by the Review Group.  The Fund will not be used to support the costs of managing the PSIF.  The cost of the FMU staff will be met by the GoS with NZAID and AusAID funding the cost of the CST and the TA provided to the RG including the cost of the TRA.  The balance of NZAID’s and AusAID’s financial commitment will be allocated to the Fund.

The Governments of New Zealand and Australia will deposit their development funds in annual tranches.  The first tranche of funds will be deposited into the account on its establishment to cover their financial commitment to 30 June 2005 and then will make a principal annual allocation by 30 July each year.  The donors may provide additional funds at other times subject to the level of demand for funds by the Facility and in consideration of their other budgetary commitments.

In the month following Facility commencement, the GoS with the assistance of the CST, will:

- establish a trust account in a financial institution acceptable to the three Governments; and

- establish guidelines for its operation that include: the specification of the type of activities that can be funded, the signatories to the account, the appointment of an independent auditor that will conduct an annual audit of the account, and the specification of financial reports to the Governments showing both expenditure to date, estimated monthly expenditure over the balance of the financial year and indicative commitments in out-years.

The Public Service Improvement Fund will be managed by the FMU with assistance of the CST.   Any interest accrued as part of the Fund account will be maintained and accounted for as part of the PSIF Fund.

## Integration with GoS structures and processes – Facility Management

It is the stated desire of the GoS, AusAID and NZAID that the PSIF management structures utilise existing mechanisms wherever possible.  In determining the elements that contribute to the management of the PSIF, the Design considered a range of existing structures.  The final recommendations are based on the current roles and responsibilities of existing bodies and the clearly articulated views of key GoS stakeholders about how they wished to see the PSIF operate.

It is noted that the GoS already has in place committees which approve all projects undertaken by the government (the Cabinet Development Committee) and those funded by donors (the Aid Coordinating Committee).  The proposed membership of the Facility Steering Committee is, in effect, a sub-set of these committees, which comprise all ministries.

The use of the Cabinet Development Committee (CDC) or Aid Coordinating Committee (ACC) as a Facility approval mechanism was considered by the Team and discussed with both government and civil society representatives.  Notwithstanding the mandates of these committees, it is considered that the focus of the Facility on constraints within the public sector to effective service delivery :

- renders membership of these committees too broad and, in the case of the CDC, to be at too high a level, to be appropriate or practical for this purpose; and

- that civil society and the private sector should be full members of the Facility Steering Committee in recognition of their role in sector planning and service delivery, and given the desire for transparency and accountability of decision making processes.

5.7.1	Civil Society Representation on FSC

The TOR asked that the Design Team address a number of strategic considerations in designing the Facility. They requested the Design Team to “note the relationship in Samoa between government and local communities and therefore be designed to facilitate, support and strengthen the partnerships role between government and local communities in the provision of effective service delivery systems”.  The design “should ensure that it is inclusive of initiatives to appropriately ‘harmonize’ with local indigenous systems established for these purposes, increase support for community based planning and capacity building for the purpose of increasing community ownership and improved coordination with government.”  In relation to these considerations, two options for civil society representation on the Facility Steering Committee are apparent.

A FSC Representative, with appropriate skills and ability, could be nominated by SUNGO and/or by the Pulenu’u.  The roles of these two bodies are detailed in Section 2.1.2.2.  The work of NGOs is valued by the government as shown in the level of interest shown by the Prime Minister, government and other donors. SUNGO has many skilled and able members. However the Design Team considers it would be more appropriate for a nominee from the Pulenu’u be appointed because of the institution’s longstanding relationship with the government, scope and reach throughout the whole country.  This would also support the important socio-cultural linkage between the traditional and formal instruments of governance in Samoa, an issue recognised by donors and emphasised in the Design TORs.

# 6	Risk and Risk Management

The design identifies a number of risks that are likely to impact on the performance of the PSIF. These include:

- Coordination of development assistance programs, at a policy, process and operational level, between AusAID and NZAID;

- The capacity of the GoS-funded FMU to support the PSIF;

- The capacity of the GoS-funded RG to support the PSIF;

- That GoS support for reforms falters (at both/either a government-wide or individual Ministry level) – thereby undermining the rationale for supporting the PSIF;

- That a lack of strategic focus or inconsistency in its application when determining what proposals to support results in too wide a range of activities being supported with a subsequent loss of impact on addressing reform priorities;

- That the FSC and/or the FCC does not function effectively – thereby reducing the credibility and effectiveness of the PSIF and potentially leading to misunderstanding between the FMU and contracted management support;

- That activity partners do not actively participate in the design, implementation, monitoring and evaluation of activities – thereby reducing the legitimacy and sustainability of PSIF initiatives;

- That institutional capacity building and training needs are inadequately considered in PSIF activity designs to facilitate the transfer of knowledge and skills to project partners – thereby limiting the transfer of administrative and technical skills and the scope for sustaining activity initiatives once technical assistance has ceased;

- That appropriate qualitative and quantitative performance indicators are inadequately identified – thereby undermining the ability to measure activity progress and impact and thus be unable to justify the resource investment; and

- Expectations – of donors, GoS and partner agencies – are unreasonable given the resources available to the PSIF.

- That GoS staff-turnover within the FMU and RG may undermine the effectiveness of Facility management.

The Risk Matrix presented in Annex 9 provides a summary of the risks that are assessed as being significant in the implementation of the PSIF and attributes accountability and mitigation strategies for each risk identified.  In addition to these strategies, the three government stakeholders could consider negotiating a partnership charter between themselves and the Managing Contractor which  (amongst other issues) specifically addresses risk management. The PSIF can be rated as a moderate to high risk activity that will require the establishment of effective liaison processes between AusAID, NZAID, GoS and the CST.  The FMU, supported by the CST, will be required to develop strategies to address these risks and minimise their impact should they manifest. The FMU (with CST assistance) must continually monitor risks as part of implementation. A number of strategies are proposed to address and minimise the impact of risks on the implementation and operation of the PSIF. The most significant strategies adopted in this design are:

- A requirement that AusAID/NZAID policy and operational issues are addressed and responsibilities in relation to the PSIF are clearly set out before the PSIF is implemented;

- That a foundation activity has been proposed to allow stakeholders to determine and clearly articulate the strategic public sector reform focus of the PSIF that ensures that the PSIF has a manageable program of activities that will contribute positively to the GoS’ reform priorities;

- A Stop/Go Review be held after Year 1 to assess the level and effectiveness of support to the facility by the Ministry of Prime Minister (MPM) with a view to confirming that the site for the FMU should remain with the MPM or should be moved to the Ministry of Finance;

- That a review of transitional support be undertaken at the commencement of Year 3 to assess the capacity of the GoS FMU and Review Group staff to undertake their roles with a view to ensuring that the transition timetable remains on track;

- That consultative structures are designed to maintain a high standard of communication, including in terms of policy dialogue on continued assistance, between all stakeholders;

- The adoption of a process of progressive engagement to ensure that ongoing and potentially ‘deeper’ levels of engagement only occurs after a counterpart agency has demonstrated the necessary level of competency and commitment to provide a reasonable level of confidence that the resource investment will deliver a useful and relevant product;

- That there is a requirement for the FSC to be well briefed on its roles and responsibilities including the provision of a position statement for members  prior to the first meeting of the Committee to ensure that it can play a constructive role in shaping and guiding the work of the PSIF;

- That activity partners are actively engaged in the design and management process throughout the PSIF activity planning and management cycle.  This includes the expectation that a commitment to a defined counterpart contribution will be required for each proposal put forward for funding;

- That in the appraisal of activities, the need and scope for institutional capacity building and training is adequately assessed and resources allocated accordingly;

- The establishment of a PSIF Operational Handbook to define appropriate and agreed processes and that these be clearly and concisely presented so that replacement FMU and RG staff are able to become effective members of the management teams as quickly as possible;

- The establishment of a Monitoring and Evaluation Framework to monitor progress, risks, and impact at the Facility and activity levels, and the provision of feedback through this process to the FSC so that future programming decisions are made in the light of lessons learned;  and

- The development of a communications strategy to ensure all stakeholders and potential partner agencies are aware of what can be addressed by the PSIF, and of its relevance to continuing and sustaining improvements in public sector reform agenda.

# 7	Monitoring, Evaluation and Performance Assessment

## 7.1 	Overview

The PSIF will be monitored at the overall Facility level; individual activity level; and in terms of the performance of the Managing Contractor including the CST and TRA.  To facilitate effective monitoring the Contractor will be responsible, via the CST Transitional Review Adviser, for assisting the FMU to develop a Monitoring and Evaluation Framework for the Facility.  The M&E Framework developed should minimise the resource cost of measurement at a complex number of levels. This Framework should be developed in collaboration with the FSC and both AusAID and NZAID.

The Contractor will also be responsible for assisting the FMU and RG in the development of

its own monitoring and evaluation tools. The process of developing the Public Sector Improvement Framework should assist the FMU and RG in determining appropriate tools and mechanisms for monitoring and evaluation.  In turn, the M&E Framework should be aimed at collecting and analysing information of relevance to the FMU and RG monitoring and evaluation roles. The M&E Framework will include both qualitative and quantitative indicators and enable the collection of data to assess outcomes and impact. The M&E Framework will cover both the program and the activity level, and will need to ensure coherence between the different levels of monitoring and evaluation.

However, it must also be acknowledged that monitoring and evaluation according to the traditional logframe approach is not easily aligned with the PSIF design.  In a project, for example, the logframe approach dictates that the successful achievement of individual activities and outputs results in the achievement of the project’s purpose.  However in the case of the PSIF, it is anticipated that the overall impact of the Facility can be greater than the “sum of its parts”, because of the capacity building role of the CST within the MPM, and because activities funded by the PSIF will be strategically selected to have significant impact on public service reform at an organisational and/or sectoral level and WoG level.  It is therefore important that the M&E Framework adequately address this tension between traditional M&E indicators and ensuring that impact at an overall Facility level, outcome, and activity level is adequately attributed.

## 7.2 	Facility-level Monitoring

The success of the Facility is dependent on maintaining an appropriate strategic focus (including adjustment and refinement of objectives and focus if necessary), the success of individual activities, and on the capacity development of the FMU staff to ensure sustainable GoS ownership and effective management of the Facility.  The FMU will be responsible for managing a number of individual and independent activities and through its monitoring responsibilities and those of the RG, will provide advice to the FSC and FCC in terms of priority-setting and progress towards the Facility goal.

RFP reports prepared by the FMU for consideration at FSC and FCC meetings will include monitoring information collated at the Facility level and assess progress against strategic objectives.  The FMU will also need to identify relevant quality indicators at the program (component) level, which will enable the FMU to monitor progress against strategic objectives and to assess impact and outcomes.  It is anticipated that performance indicators will be more readily identifiable for the core program (Component 1) given the emphasis placed on longer-term (although not necessarily more expensive/complex) interventions. While performance measurement should be straightforward for IEP activities (Component 2), the development of program performance indicators for the IEP program as a whole will, however, pose a significant challenge given the potential for activities to be quite disparate in their objectives and duration.

In developing an M&E Framework care will need to be taken to ensure that its complexity and resource requirements are consistent with overall size of the PSIF and will take account of the capacity of the GoS staff who will ultimately be responsible for its application.

This monitoring will assist the donors, GoS and the FMU to assess the effectiveness of the Facility in meeting its objectives, purpose and goal.

## 7.3 	Activity-level Monitoring

Activity monitoring will be incorporated into activity development and implementation, and will be a key role of the FMU.  It will be a requirement for approval that all activity proposals and associated scopes of services (where needed) have clearly identified outputs and milestones (including skills transfer and training requirements) and a set of verifiable indicators linked to these.  The PSIF Operational Handbook to be prepared during the inception phase will fully detail requirements for proposals and scope of services, ensuring they contribute to effective monitoring and evaluation.

All activities should have Activity Completion Reports (ACR), to be completed by the contracted personnel or the managing sub-contractor and approved by the agency CEO, these will detail activity outcomes and outputs. ACRs will be the main source of information about the quality and relevance of outputs, contribution to development objectives and the likely sustainability of benefits on completion of the activity.  ACRs will also require a brief Contractor Performance Report (CPR) from the partner department or agency, where contracted support has been utilised.  This will report against performance criteria specified in the activity agreement and as outlined in the activity scope of services. Activity level monitoring will therefore include assessment of subcontractor performance, and prior performance of subcontractors will be taken into account by the FMU when assessing ongoing tenders.

Activity Completion Reports will provide a key source of information of progress with Public Service improvement through the Facility as well as lessons learned.  The FMU  will be responsible for collating Activity Completion Reports and disseminating relevant information through the PSIF website.   High level outputs as reported in the Activity Completion Reports should be collated by the FMU to report on activity as well as Facility level outputs and outcomes.

## 7.4 	Monitoring of Managing Contractor Performance

Contractor Performance monitoring and management will be undertaken via:

| Management Performance Assessed | Contract Tool | Monitoring Responsibility |
| --- | --- | --- |
| Delivery of Facility specifications under the contract Scope of Service | Contractor Milestones | Donors/GoS |
| Quality of services provided by Contractor at Facility level | Donor/GoS monitoring mechanisms Stop/Go Review Transitional Support Review | Donors/GoS |
| Skills transfer by CST to GoS FMU and RG staff | Contractor Milestones Stop/Go Review Transitional Support Review | Donors/GoS |

As it is anticipated that the Contractor-supplied Support Team in the FMU will progressively withdraw from supporting Facility management, it will be necessary that these arrangements be reviewed (and amended if required) in order to ensure their appropriateness to the Facility management environment.

## 7.5	Monitoring of FMU Performance including the RG

| Management Performance Assessed | Monitoring Tool | Monitoring Responsibility |
| --- | --- | --- |
| Quality of services provided by MPM FMU and MOF RG | Donor/GoS monitoring mechanisms Stop/Go Review Transitional Support Review Review of Facility Effectiveness | Donors/GoS |
| Responsiveness, efficient resource use and compliance with agreed procurement guidelines. | Regular Facility reporting Stop/Go Review Transitional Support Review Review of Facility Effectiveness | Donors/GoS |
| Financial management and accountability. | Activity financial statements/acquittals by partner agencies Fund statements and reporting to FSC/FCC (six- monthly and annual audited statement) Stop/Go Review Transitional Support Review Review of Facility Effectiveness | FMU/CST/partner agency GoS via independent auditor/Donors |
| Quality of services provided by sub-contractors at activity level | Activity Completion Report Performance Reports provided by partner agencies | FMU/CST (RG)/partner agency |

## 7.6	Reviews

There are a number of advantages of facilities, however in order to ensure that these are maximised, as noted in Section 3.2.2  above, donors must be prepared to support more frequent reviews and redirections of governance strategies and programs than would be the case in the implementation of more narrowly focussed projects.  All reviews will consider the use of the IEP Component against the parameters of the Facility.

The PSIF Design recommends the initiation of three specific reviews during the life of the PSIF.

Stop/Go Review – this review is to occur at 12 months and will review/assess:

- the level and effectiveness of support to the Facility by the Ministry of Prime Minister with a view to confirming that the site for the FMU should remain with the MPM or should be moved to the Ministry of Finance;

- Progress made in establishing the strategic framework for the PSIF though the Public Sector Improvement Framework;

- the performance of the Facility and its adherence to approved processes and procedures including an audit of the Fund; and

- progress made in transferring the necessary management skills from the Contracted Support Team to their GoS counterparts.

Review of Transitional Support – this review will be held at the commencement of Year 3 and will review and assess:

- progress made in transferring the necessary management skills from the CST to their GoS counterparts with a view to confirming the timeframe for ending transitional support;

- the performance of the Facility and its adherence to approved processes and procedures including an audit of the Fund;

- how well the selection of projects and their performance are contributing to the goal and purpose of the PSIF; and

- strategies for the GoS to maintain access to Australian and New Zealand TA.

Review of Facility Effectiveness – this review will occur towards the end of Year 4 and will review and assess:

- the performance of the Facility and its adherence to approved processes and procedures including an audit of the Fund; and

- how well the selection of projects and their performance are contributing to the goals and purpose of the PSIF with a view to recommending its continuation for a further 5 years.

Other Periodic Reviews

Other Periodic Reviews may be commissioned by the GoS and/or donor agencies in conjunction with the GoS.  These reviews would normally involve GoS and donor participation, consideration of the review findings, and then the initiation of agreed follow-up action.

## 7.7	Evaluation

The elements outlined above, ie Stop/Go Review, Review of Transitional Support, Review of Facility Effectiveness and other periodic reviews provide for effective performance monitoring, in addition to providing the sources of data to generate sufficient information for an evaluation process at several points – in reviewing transitional support, in reviewing Facility effectiveness, and in order to undertake an overall post-Facility evaluation.  It is proposed that AusAID/NZAID/GoS commission these evaluations independently, through a Facility Monitoring Group or ex-post evaluation team as appropriate.

# 8	Outcome of design issues

## Feasibility

    - Technical and Management Feasibility

In line with the expressed desire of the three Governments that the management of the PSIF be undertaken, as far as possible, within GoS structures and by the GoS itself, the actual management of the PSIF is the responsibility of the FMU, with support to be provided by the CST in the medium term.  This is unlike many donor-supported programs, where an external contractor is employed to undertake all project managerial functions.  This difference must be reflected both in the agreement between the three governments to support the PSIF, and in the contracting arrangements for the contracted management support recommended in the design.

Each of the activities proposed under Components 1 and 2 will be appraised in terms of their technical feasibility and developmental integrity.

The technical skills required for the preparation of the Review and Forward Plan (RFP) document, the capacity building of FMU staff (Component 3) and management of the Facility (Component 4) are anticipated in the identification of the skills required for the contracted management support staff.

##### Strategic Focus

Various commentators have proposed a wide range of potential projects for which the Facility could usefully provide support.

A key lesson learned from other governance facilities is that if the areas or institutions eligible for support are not tightly defined, too wide a range of activities/institutions can be supported, resulting in a subsequent loss of real impact.   Further, managing the tension between available funding and the wide-ranging demands for assistance can create disaffection with the facility amongst applicants.

To assist the PSIF determine an appropriate strategic focus and to then maintain the necessary management discipline to uphold this focus, the design proposes two programming components.  It is anticipated that the Core Program will have a tight strategic focus enabling substantial reform initiatives to be resourced (Output 1.1 provides for this focus to be developed) while the more flexible Immediate and Emerging Priorities component provides the capacity to respond to a wider ranging set of priorities.

It is critical that key stakeholders reach agreement before and during the inception phase on a concise strategic focus (particularly for the Core Program component) to ensure that the FMU and FSC and their institutional partners have clear parameters within which to operate.

##### A Public Sector Improvement Plan

Related to the above discussion on the need for a strategic focus, the 2003 ISP Review recommended that Australia’s future support for institutional strengthening/capacity building should be delivered within a Public Sector Improvement Plan (PSIP) which focused on:  how public services should be better planned, managed and delivered in 5-10 years time; what changes need to occur on a whole-of-government basis to achieve this; how these changes will be encouraged, implemented and/or funded; and how the outcomes and impacts of these changes will be measured and reported.  The ISP Review perceived the PSIP could meet six possible objectives:

- To provide a strategic framework for ongoing improvements in the efficiency and effectiveness of Samoa's public administration sector.

- To ensure that significant crosscutting issues impacting on the public sector's efficiency and effectiveness are adequately identified and, within available resources, addressed.

- To provide a reference point for the prioritisation of subsequent proposals for future institutional strengthening initiatives to be funded through the Public Sector Improvement Facility.

- To provide a framework within which the achievements of individual activities undertaken in support of improved public sector efficiency/effectiveness can be evaluated.

- To encourage, through their meaningful inclusion in the preparation of the PSIP and its subsequent implementation, strengthened collegiality and 'ownership' amongst GoS agency heads and non-government stakeholder in relation to public sector improvement initiatives.

- To meet the requirements of the GoS sector planning guidelines.

This PSIP could contribute to the determination of the necessary strategic framework to guide Facility operations.

However the Design Team’s discussions with key, central GoS agencies strongly indicated that while there was general recognition of the value of such a plan, it was not an immediate or short-term priority for them given the heavy demands that other essential current planning activities place on Sectors, Ministries and agencies.

After discussion with AusAID and NZAID staff (both Post and Desk), the Team decided they were not in a position to pursue the development of the PSIP further with the GoS.  Nonetheless, the Team concluded that the suggested objectives of the PSIP may be able to be fulfilled by giving priority to some key, inter-related activities that could be funded by the PSIF in its first year.  Subsequent to the mission, the GoS has indicated its desire to develop a Public Sector Improvement Framework.  In recognition of this, the Design proposes that a Public Administration Strategic Review and Planning Activity be undertaken in the first six months of Facility operation to assist with the development of the Public Administration Sector Plan and, as part of that, articulate a Public Sector Improvement Framework that will form the basis for guiding the future commitment of facility resources.   However this exercise does not exclude the development of a wider PSIP at a later time, if it is considered a priority for the GoS, once the current SDS, Sector, Ministry and Corporate Plans and charters are completed.  Therefore, the Design includes specific features which would support this possibility but the outcomes of which also stand alone in contributing to the objectives of the PSIF, including that:

- the core suite of activities has been designed to address significant issues impacting on the public sector's efficiency and effectiveness identified during the ISP Review and confirmed during the PSIF design process;

- the inclusion of a Public Sector Strategic Review and Planning activity (Output 1.1) to help inform the decisions surrounding the determination of a realistic strategic focus for the core program;

- both streams of activities (core program and emerging/immediate issues) envisage activities incorporating more than one agency, thereby providing opportunities for collegiality and team work on issues of common concern at a senior level of government; and

- the proposed placement of the Facility Management Unit within the Ministry of the Prime Minister, which has an overarching role in progressing the GoS whole-of-government agenda, has the potential to further foster cooperation among Ministries.

A number of commentators including the ISP Review Team and Alan Morris, an adviser to the GoS, have recommended a number of broad cross-agency activities that are important to ensuring the framework exists for effective public sector reform.  The Design recommends that a number of these could form potential activities under Component 1 of the PSIF:

- Strategic Review and Planning Process – to assist Facility stakeholders determine the strategic parameters that will guide the identification of activities supported under the Core Program component.

- Strengthening Cabinet Processes – an activity designed to work with the Cabinet Secretariat to strengthen its capacity to provide and coordinate the submission of high quality advice to Cabinet and improve operational procedures.

- Ministry of Prime Minister whole of government policy capacity building – to improve coordination and cooperation between Ministries to ensure the development of quality sectoral policies.

- Sector Planning – an activity that can provide assistance to Ministries as they work to complete the Sector Plans for which they are responsible.

- Support in development and implementation of Ministry Capability Plans – an activity that can provide assistance to Ministries as they work to complete their Capability Plans and to develop associated implementation plans.

- Support for legislative needs assessment – an activity designed to assist in the undertaking a legislative needs stocktake together with a prioritisation of the identified legislative program.

It should be noted that, given finite resources, it may not be possible for the PSIF to support all these activities while meeting agency-specific demands for assistance.  The potential activities outlined above may not necessarily be long-term activities.  However it is recommended that the Strategic Review and Planning activity (Output 1.1) be undertaken immediately upon commencement of the PSIF in order to provide the means by which other activities could be tested to see whether they fit within the parameters of the PSIF, and their priority, given limited funding available and in relation to other activities which have not at this point been identified.

    - Institutional Feasibility

Institutional feasibility, in terms of governance, is central to the integrity of the PSIF.  Both the management of the Facility, and the institutions supported by it, must be able to demonstrate adherence to the basic good governance principles of transparency and accountability.

The GoS has articulated its support at both a whole-of-government level, and at an individual ministry level, to the management and recommended location of the PSIF.  Further, the Design proposes a strategy for addressing the risk associated with Facility location (Stop/Go Review) and capacity building (Review of Transitional Support).

##### Partnership

The PSIF has the potential to achieve partnership at a number of levels - between the three government stakeholders (possibly through a Charter) and therefore within the FCC, the FSC, and the contracting arrangements for the CST. Within activities also there is the ability for the PSIF to foster partnerships:

- within and between Ministries;

- between Samoan government agencies and similar Australian or New Zealand agencies;

and to

- encourage both formal and informal mechanisms for cooperation.

##### Location of Facility Management

Taking into account the Design Mission TORs and the messages received during the consultations undertaken, two clear alternatives for where the PSIF could be situated emerged.  While not affecting the structure of the Facility, its day to day operation, nor the roles of the overseeing bodies, each alternative presents specific advantages, and specific risks.

Placement within the Ministry of Finance

The reasons for placing the Facility Management Unit in the Ministry of Finance (MoF) would be the:

- Role and authority of MoF in planning and budgeting.  The MoF has either direct responsibility or strong links to planning processes and systems.  This includes that SOEs, which are critical in some aspects of the sector planning process, report to MoF under the appropriate GoS legislation.

- Role in aid programming, planning and policy.

- Role in tasking and planning SDS and Sectoral Reviews.

- Capacity of the agency to support the FMU. Despite its undoubted strengths, there is still a need for policy formulation, advisory and analysis skills to be consolidated, broadened and deepened within the MoF to ensure long term sustainability.

Potential risks associated with this option:

- MoF is, given its mandate, a powerful agency.  This is intensified in Samoa because, vis a vis other agencies, the capacity of MoF is very high.  This may inadvertently result in a widening of the gap between the relative capacities of Finance and other agencies.

- There is the potential for this to increase aid program focus on economic, at the expense of social, issues, particularly in terms of funding for service delivery issues.

- The perception, particularly outside of government, in relation to these two points.

- The MoF does not have the mandate to coordinate the whole of government response to governance issues of service delivery.

The following strategies to reduce these risks could be adopted:

- That FSC membership includes high-level representation from other Ministries, and from the private sector and civil society.

- Transparency of funding criteria, and decision-making processes.

- Establishment of a specific unit to manage the Facility, rather than having the FMU subsumed into the normal business of an existing MoF division.

- To provide a counterbalance and check, the establishment of the Review Group within the Office of the Auditor General to ensure independent review and appraisal.

###### Placement within the Ministry of the Prime Minister

The FMU could be located in the Ministry of the Prime Minister (MPM) based on:

- Its role as the overarching government agency, it will promote increased cooperation and collaboration among agencies.  An effective way of promoting interagency cooperation is to link it to the development of issues – in this case the public service governance issues underlying the SDS agenda – that are to be put to Cabinet.  This will ensure that Cabinet is provided with a whole-of-government approach to these issues.

- Its role in providing the supporting structure for the ministries of government - the MPM has the mandate for pursuing the whole-of-government agenda and for providing high level and integrated policy advice to Cabinet and the Prime Minister.

- The Prime Minister has been a key proponent of reform and placement of this important resource within MPM will aid co-ordination with GoS reform agenda and coherence with whole-of-government policy development.

- That the Prime Minister has responsibility for monitoring government project activities via the Cabinet Development Committee.

- The status of MPM in terms of perception – stakeholders clearly expressed the view that placement within the MPM will help avoid the potential for narrowly-focused, Ministry-specific priorities to take precedence over the mix of broader socio-economic priorities that make up the Government’s development agenda.

- The need to build capacity in this critical part of government in order for it to assume its key role in policy coordination.  This will, in turn, allow the management of the GF itself to be a capacity building exercise, and a catalyst for change.

During the two week design mission there was not sufficient time for the Design Team to undertake a full capacity assessment of potential locations for the PSIF (MPM and/or MOF). However weaknesses in departmental capacity were recognised by the CEOs of both MPM and Finance, and by other agency CEOs, which indicate the MPM (as the recommended location of the PSIF) will need considerable assistance, at least initially, in managing the PSIF effectively. It appears that:

- The MPM currently is lacking capacity to effectively provide independent analysis and policy advice to Government (via Cabinet) on a whole-of-government basis.

- While new graduates have been recruited to MPM, they lack appropriate policy analysis skills/experience. The Ministry as a whole lacks a Senior Policy analyst capable of mentoring these new staff. The longest serving staff member within the Policy Coordination Unit has only been in their position for around 15 months.

- Capacity is currently lacking to follow up on the implementation of Cabinet decisions, and to ensure Cabinet and other Members of Parliament understand and support the overall reform agenda.

- There have been previous discussions and early planning in regard to a project to strengthen the Policy Coordination Unit, however a decision was taken that it was not timely for such an intervention.

- The CEO of the MPM has indicated that over time it is hoped to develop a Cabinet approved whole-of-government approach to reforms consisting of a Committee of Officials, chaired by the CEO of the MPM, to provide advice to Cabinet. Currently the capacity does not exist within the MPM to support this.  The MPM CEO sees potential in the FMU as being a precursor to the development of this capacity.

- There is a widespread feeling across senior members of the Public Service that there needs to be high level focused catalyst to promote wider change within the MPM. The PSIF has the potential to provide this.

The CEO of Finance also indicated that the program review capabilities of the MoF would require strengthening in order to carry out the rigorous and defensible appraisals and reviews of proposed activities as envisaged in the PSIF Design.  The CEO also indicated that the strengthening of this capacity would complement well a desire to have the MoF monitor the GoS-funded development programs undertaken by Public Sector Agencies.

An early task of the CST will be to complete a human resource and systems capacity assessment of the MPM, and of the PSIF Review Group located within the MoF.

To address the current lack of capacity in the MPM to effectively support Facility operations, and to ensure that other ministries place due importance on the pivotal role that will be played by the FMU, the Design Team proposes the following risk reduction strategies could be adopted:

- That the FMU be established as a self-contained unit staffed specifically for this task.  This reduces the likelihood that staff will be diverted by other business, while improving the overall capacity of the MPM to undertake its core business in ensuring that there is a whole-of-government approach to implementing the GoS public sector reform agenda.

- That a Stop/Go Review be held after Year 1 that assesses the effectiveness of support to the Facility by the MPM, to confirm that its placement within the Ministry is appropriate.

- That FCC membership includes high level representation from other Ministries, and from the private sector and civil society.

- That the skills set of the advisory team complement the capacity needs of the MPM.  In addition to a three-person Contracted Support Team, the Design Team also proposes short term support to assist with the development of an HRD and training plan for FMU staff and a systems development plan.

- To provide a counterbalance and check, the Design Team proposes the establishment of a small Review Group within the Ministry of Finance to ensure independent review and appraisal.

As indicated, this alternative comes with some risks.  However, it is the recommendation of the Design Team that the FMU be located within MPM, on the clear understanding that its role and function will eventually be integrated into the core functions of the MPM Policy Unit. This not only best reflects the aim of the Facility, but also reflects the articulated views of the majority of stakeholders consulted, including key ministries, when asked where the FMU should be located.  It should be noted that the strategies proposed to reduce potential risks do not involve significant additional management cost.

Institutional Feasibility for Activity Implementation

Activity selection criteria and appraisal guidelines should give appropriate emphasis to the Managing Agency’s capacity to implement the proposed activity.  It is envisaged that a successfully appraised activity will contain a commitment to the proposed activity from the Managing (partner) Agency, adequate personnel resources and an organisational structure that can successfully implement the activity.  Alternatively, managing agencies may sub-contract elements of the proposed activity to gain specific expertise. Such arrangements are seen as an effective and efficient way to increase the institutional capacity to the required level.

The Design provides for various levels of management support to be provided by the FMU to a recipient/managing agency depending on the assessed level of capacity of that agency.

The Design also recognises that CST support to supplement FMU capacity will be most intense as the pipeline of activities builds up and peaks.  The CST will be available to provide backstopping to the FMU when its workload is likely to be greatest.  This capacity supplementation will reduce as GoS capacity to manage activities becomes stronger and as the pipeline reduces as funds become increasingly committed.

By ensuring the PSIF is managed by the GoS and that the Facility management remains cognisant of the availability and scope of other sources of funding any linkages to an external contractor after the transition period may only be necessary for the sourcing of non-public sector expatriate expertise.

    - Financial Feasibility

It is important to recognise that Facilities can be resource intensive, and can therefore be expensive in terms of the management costs involved in implementing and monitoring a range of small-scale activities.  The stated allocation by AusAID and NZAID is considered to be sufficient to implement a program of assistance as envisaged.

However, as the ratio of management to program costs is not a fixed proportion, the three Governments should, over time, review their contributions to the Fund.  As management capacity of the FMU and of the public sector agencies accessing facility funds improves, it is expected that greater levels of funds could be put through the Facility without adding significantly to the associated administrative overheads.

As noted, expenditure across the life of the PSIF is not likely to be even. The FMU will need to ensure management processes are in place to accommodate this.

## Impact on Poverty

The Facility goal is to support economic and social reforms in line with the national development priorities set out in the Samoa Development Strategy.  Economic and social reforms aimed at improving quality of life can only be achieved in stable environments and growing economies.  A stable environment is a clear pre-requisite for sustainable development, which in turn has a direct impact on the alleviation of poverty.

The purpose of the Facility, to promote a whole-of-government approach to identifying and addressing critical constraints within the GoS public sector to service delivery, further reflects the GoS desire to create an enabling environment which will translate into improved quality of life for its citizens.

Specification of the intended direct/indirect contribution of each activity to improved service delivery is a key requirement of the activity planning and management cycle (refer Output 4.5).  The extent to which service delivery outcomes have been met, assessed and evaluated will be the subject of:

- Regular RFP Reports.

- Review of Transitional Support.

- Review of Facility Effectiveness.

## 8.3 	Social and Cultural Impact

The social and cultural implications of each PSIF activity will be tracked through the activity planning and management cycle (refer Output 4.5).   The consultative process undertaken during the development of the activity planning and management cycle will ensure the specification of processes that entrench consideration of social and cultural implications associated with each activity. It is expected that the PSIF Operational Handbook will provide guidance to ensure that opportunities to identify and address social and cultural issues are maximised at all points in the cycle and that an understanding of the importance of these issues is fostered.  The extent to which social and cultural issues have been addressed by PSIF activities will be the subject of:

- Regular RFP Reports.

- Review of Transitional Support.

- Review of Facility Effectiveness.

## Gender Impact

Gender impact will be an important aspect in activity proposals from partner agencies. As with social and cultural impact, the consultative process undertaken during the development of the activity planning and management cycle will ensure the specification of processes that entrench consideration of gender issues associated with each activity. It is expected that the PSIF Operational Handbook will provide guidance to ensure that opportunities to identify and address gender issues are maximised at all points in the cycle and that an understanding of the importance of these issues is fostered.  The extent to which gender issues have been addressed by PSIF activities and structures will be the subject of:

- Regular RFP Reports.

- Review of Transitional Support.

- Review of Facility Effectiveness.

Gender is also important at the level of PSIF structures. As far as possible, there should be equitable representation of both men and women on all PSIF committees and within personnel - both GoS and contracted support employed in the management and administration of the PSIF.

## Impact on Environment

The environment is not directly implicated in the management of the Facility however the processes for considering, approving, monitoring and evaluating activities must include steps that ensure that any environmental implications are identified and managed appropriately.

As for sections 8.2 and 8.3, the procedures for assessing environmental needs and appraising the environmental impact of activities and the Facility as a whole will be detailed in the PSIF Operational Handbook (refer Output 4.2). The extent to which environmental issues have been addressed will be the subject of:

- Regular RFP Reports.

- Review of Transitional Support.

- Review of Facility Effectiveness.

Annex 1

Design TORs

SAMOA GOVERNANCE FACILITY

# Terms of Reference – Design

# 1)	Purpose

The purpose of this assignment is to design a Facility appropriate to the country's unique social and cultural context, environment and economy that would support the Government of Samoa (GoS) to build the capacity of its public service to implement its national development priorities.

The proposed Governance Facility is intended to provide a mechanism that can address priority small-scale needs in support of economic and public sector reform within key GoS public sector agencies.  The ultimate goal of strengthening public sector reform is to maintain a stable macro economic framework and build economic growth through private sector development.

# 2)	Background

Samoa's political environment is stable and its democratic institutions are robust. Over the last decade Samoa has consolidated its place as a regional leader in the Pacific, particularly in relation to economic and public sector reform.  The Government's development strategy places priority on achieving a competitive economy with sustained economic growth, improved education, enhanced health standards and strengthened cultural and traditional values.

Since 1994, the GoS has pursued an economic and public sector reform program to create an ‘enabling environment’ conducive to growth and investment.  As part of this, the GoS reviewed processes for the planning of Samoa’s economic and social development and introduced a more strategic approach.  This resulted in the preparation and publication of its first Statement of Economic Strategy in 1995.

Since that time, Samoa has made major strides in establishing a sound and stable macroeconomic framework as the foundation for stronger economic growth led by private sector development.  The 2002-2004 Strategy for the Development of Samoa (SDS) has broadened Samoa’s development strategies and priorities to encompass wider facets of development, including social and cultural values.  The strategy emphasises enhanced public sector efficiency as a key pillar for future development in Samoa.

### Assistance from Australia and New Zealand

Australia and New Zealand are major donors to Samoa and are committed to working collaboratively with the GoS to achieve better aid outcomes.  In recent years, Australia and New Zealand have been exploring options to harmonise aid efforts to improve the effectiveness, efficiency and impact of their respective aid programs to Samoa.

AusAID, NZAID and the GoS have agreed to hold joint High Level Discussions (HLDs) concerning the respective aid programs to Samoa.  The first joint HLD was held in July 2002 and the second is planned for December 2003.  With the support of the GoS, AusAID and NZAID have also recently agreed to develop a joint program (country) strategy to Samoa.  The joint strategy, to cover the period 2005-07, will be prepared during 2004 in conjunction with the planning process of the GoS and support the GoS Strategy for Development of Samoa (2005-07).  AusAID and NZAID are also exploring the possibility of jointly supporting particular aid initiatives including the proposed Governance Facility.

The Australian aid program has assisted the GoS to implement its public sector reform agenda and move towards economic independence since the mid 1990’s.  The aid program has supported economic policy and public service reform, human resource development, improved the quality of basic services, and strengthened the management of natural resources.

AusAID has supported 10 projects (known as Institutional Strengthening Projects) to strengthen the capacity of GoS agencies to plan and manage their functions efficiently and effectively.  Agencies that have benefited from this assistance include Trade and Investment Promotion; Treasury; Customs; Water Authority; Public Service Commission; Education; Health; Agriculture, Forestry, Fisheries and Meteorology; Immigration, and Public Works.  AusAID funding of institutional strengthening projects (ISPs) has averaged around A$8 million a year in recent years, representing around 60 per cent of AusAID’s total bilateral aid program with Samoa.

NZAID has supported an ISP in the Justice Department, including the establishment of a Law Commission.  An ISP in the courts sector is planned for 2004-05.

###### Review of Institutional Strengthening Projects

In view of the substantial investment by AusAID in supporting the GoS public sector reform agenda it was agreed in 2002 that the GoS and AusAID would jointly review the impact of ISPs.

The Review concluded that AusAID/GoS investment in ISPs is yielding good returns and has provided a solid foundation on which to build continuing improvements in public sector efficiency and effectiveness.  Four clear messages for future assistance emerged from the Review of ISPs in Samoa (May 2003):

- The current ISPs have provided a solid foundation for enhanced public sector efficiency but there is a need to move forward to more flexible forms of support for improvements in the future, with substantially reduced emphasis on the ISP ‘model’ employed to date;

- More needs to be done on a whole-of-government basis to continue strengthening the public service;

- The GoS should have prime responsibility for both the identification of future strengthening needs and priorities and for the design, management, performance monitoring and evaluation of specific interventions to address these; and

- All this needs to occur within a framework that relates institutional strengthening and public sector reform more explicitly to Samoa’s overall development strategy.

The Review noted the need to start planning to consolidate gains already achieved in public sector reform and to extend them across all government departments.  This will provide some basis for continuing improvement in the capacity of Samoa’s public service to implement national development priorities.

The Review noted the absence of a Public Administration sector level strategic plan.  It also highlighted that there is currently no agency charged with implementing a coherent whole-of-government approach to improving public administration.  The Review concluded that Australia’s future support for institutional strengthening/capacity building should be delivered within a Public Sector Improvement Plan (PSIP) and that this plan should focus on:

- How public services should be better planned, managed and delivered in 5-10 years time;

- What changes need to occur on a whole-of-government basis to achieve this;

- How will these changes be encouraged, implemented and/or funded; and

- How will the outcomes and impacts of these changes be measured and reported.

The ISP Reviews proposal for preparation of a PSIP intended to meet six objectives:

- To provide a strategic framework for ongoing improvements in the efficiency and effectiveness of Samoa's public administration sector.

- To ensure that significant cross-cutting issues impacting on the public sector's efficiency and effectiveness are adequately identified and, within available resources, addressed.

- To provide a reference point for the prioritisation of subsequent proposals for future institutional strengthening initiatives to be funded through the Governance Facility.

- To provide a framework within which the achievements of individual activities undertaken in support of improved public sector efficiency/effectiveness can be evaluated.

- To encourage, through their meaningful inclusion in the preparation of the PSIP and its subsequent implementation, strengthened collegiality and 'ownership' amongst GoS agency heads and non-government stakeholder in relation to public sector improvement initiatives.

- To meet the requirements of the GoS sector planning guidelines.

The Review recommended that the GoS should establish a Public Sector Improvement Committee, reporting to the Prime Minister and tasked with preparing a PSIP for approval by the Cabinet Development Committee.  The GoS is considering whether it will establish a new body or use an existing mechanism for this purpose.  Responsibility for drafting and approving a PSIP lies with the Government and people of Samoa.  Further background on the proposed PSIP is included at Attachment H.

The Review also considered how, given such a Plan, future Australian aid to support its implementation might best be structured.  Options considered included Adaptable Program Loans and gaining access to the Tonga Technical Assistance Governance Facility.  The Review has concluded that while each has useful features, none of these options is well geared to the current Samoan context.  Alternately, the Review proposed the establishment of a Facility designed to meet the ongoing challenge of improving the public sector in Samoa.

A Facility approach may offer the following advantages:

- Provision of timely, responsive, targeted and flexible assistance to meet current and emerging needs of participating agencies;

- Development of partnership approaches between governments;

- Scope for progressive engagement – commencing on a small scale and leading to a larger level of support if required and as counterpart agencies demonstrate commitment and capacity to participate; and

- Scope for scaling the program up or down annually on the basis of demand and on the availability of funds within a country program.

In their response to the ISP Review, the GoS agreed to the establishment of a Facility for initiatives designed to achieve measurable improvement in Samoa’s public administration.  The GoS also agreed that an indicative annual amount of A$2 million be earmarked within AusAID’s Samoa Country program for the Facility and NZ$1 million within the NZAID aid program to Samoa.  The GoS also agreed that a body (existing or new) should be tasked with the development of a PSIP and that this Plan would guide any future assistance to strengthening the public sector.  The full recommendations of the ISP Review is included at Attachment C and the GoS and GoA response to the ISP Review recommendations is included at Attachment D.

3)	Proposed Scope of Governance Facility

Since the ISP Review, the concept of the Governance Facility has been discussed further with the GoS and other stakeholders and formally appraised through a peer review meeting held in AusAID 17/9/03.  The peer review meeting endorsed the concept of a Governance Facility approach as a means to improve the effectiveness of the Samoan public service in line with the Government of Samoa’s (GoS) reform agenda.

Based on recommendations of the peer review meeting and subsequent consideration by the GoS, AusAID and NZAID, is it recommended that the design of the Governance Facility should address the following strategic and management considerations.

# Strategic considerations

- Proposed goal: to support economic and public sector reform in Samoa.

- Proposed purpose: to address critical constraints to reform in the GoS through flexible small-scale activities.

- Strategic directions of the Facility should be aligned with and supportive of the strategic directions of Samoa’s public sector reform agenda and endorsed at a high level within the GoS (perhaps by the Cabinet Development Committee or Aid Coordinating Committee).

- The Facility should provide a flexible and responsive mechanism for priority governance initiatives.

- The Facility should be designed to maximize GoS ownership and utilise and build on GoS systems given Samoa’s record in public sector reform, strong GoS leadership and the need to ensure sustainability.

- The Facility should note the relationship in Samoa between government and local communities and be designed to facilitate, support and strengthen the partnerships role between government and local communities in the provision of effective service delivery systems.  It should ensure that it is inclusive of initiatives to appropriately ‘harmonize’ with local indigenous systems established for these purposes, increase support for community based planning and capacity building for the purpose of increasing community ownership and improved coordination with government.

- The proposed Public Sector Improvement Plan (PSIP) if prepared by the GoS would provide the overall Strategic Framework for public sector reform, which the Governance Facility would seek to support.

- The purpose and process for development of the PSIP will be determined by the GoS.  Depending on GoS views, the PSIP could be developed prior to commencement of the Facility, be developed with assistance from the Facility or be developed alongside the Facility.  If the GoS decide not to develop a PSIP then the design will need to consider the impact on the Facility and options for strategic planning of public sector improvement.

- The Facility may serve as a transition towards a SWAP or budget support focused on outcomes and impacts.

# Management considerations

- An innovative and progressive design particularly with respect to management arrangements is encouraged.  The design should investigate options and implications for accountability outside of the standard AMC management model including full management by GoS and partial management by GoS with transitional AMC support possibly contracted directly to GoS.  To the extent possible, it is recommended that the role of an AMC, if any, should be minimised.

- The GoS are considering appropriate management arrangements and have advised that there are cost effective management capabilities available in Samoa.  The GoS also see value in capacity building and strengthening ownership if managed within Government.  The GoS have also proposed that it is timely to consider operationalisation of the Governance Facility through budgetary support.  If requested by the GoS, the Facility should provide interim/transitional support to build GoS capacity to manage the Facility.

- The value adding of New Zealand and Australian governments in the management of the Facility may depend on objectivity, independence, experience and expertise, ability to facilitate linkages with government agencies, ability to act regionally, ability to coordinate with other donors, reputation and access to consultants.

- The GoS should act as the driving force in the development of the PSIP and in identifying, prioritising, recommending, monitoring and reviewing any interventions supported by the Facility and providing strategic guidance.  A managing contractor could support the development of the PSIP if required.

- Should the GoS wish to manage the Facility the capacity and interest of the GoS to undertake all aspects of tendering, financial management, contract management and activity identification will require clarification.

- Financial management and accountability systems should be clearly considered and specified in the design.  Capacity building in performance auditing will be required and consideration should be given to linking strengthening of the audit function with management of the Facility.

- The design should recommend whether the Facility is reactive and/or proactive in its approach to activity support.  A reactive Facility would provide an administrative mechanism that considers submitted proposals.  A proactive Facility would proactively assist the reform agenda by providing capacity for analysis and development of activity proposals in support of its strategic directions.  The proposed PSIP will assist the Facility to be proactive and coordinated in its approach to reform.

- The design mission should clarify with GoS the appropriate counterpart management agency/agencies for both the strategic and operational management of the Facility.

- The majority of funding should be reserved for activities that fit within a strategic framework for the Facility (such as the proposed PSIP).  The Facility should also have the capacity in terms of resources and funds to react to emerging priority needs.

- The scope of activities to be supported under the Facility will be determined by the GoS and will require clear objectives and links to the broader reform program.

- The Facility should encourage innovation within the activities that it supports and include things like high-level mentoring and fostering linkages with Australian/New Zealand/Pacific government agencies.

- The Governance Facility should focus on activities that support more effective public service, including engaging civil society as opposed to directly targeting improvements to civil society and NGO’s.

- The design should be kept as simple as possible.

# 4)	Objectives of the Design Mission

The objectives of the Mission are to:

i)	consult with the Government of Samoa and other relevant organisations to determine the feasibility and implementation arrangements for the Facility; and

ii)	subject to feasibility, prepare an appropriate Design and related documentation for the Facility to a standard suitable for tendering.

### 5)	Scope of Services

The design team shall provide the following services:

In-Australia

5.1.	Review background documentation in relation to the proposed Governance Facility for Samoa (see Attachments).

In-Samoa

5.2.	Undertake a field mission to Samoa 12 - 26 February 2004 to investigate the feasibility of the proposed Governance Facility.  The field mission will include consultation with key stakeholders and a consultation workshop to discuss the proposed design.

5.3.	Investigate the demand, scope and feasibility of possible AusAID and NZAID assistance for a Governance Facility.

5.3.1	Assess the rationale for the Facility.

5.3.2	Review the Facility objectives and focus.

5.3.3	Assess the suitability and viability of the proposed Facility mechanism for providing assistance.

5.3.4	Review operational, management and implementation arrangements of the Facility including:

- activity identification and preparation processes

- activity eligibility criteria and participant selection processes;

- activity approval and decision making processes;

- constraints imposed by English language skills in the delivery of training and/or technical assistance;

- approaches to the provision of assistance;

- recruitment practices (local and international);

- role of partner agencies and local contributions;

- role of the contractor;

- role of posts;

- access to funds (competitive rounds and/or continuous application);

- mechanism for providing grant funding;

- accountability and quality assurance;

- monitoring and evaluation processes at both strategic and activity level; and

- reporting systems.

5.4.	Prepare a design for the Samoa Governance Facility, that fully describes the project, addresses the issues in the scope of services above and includes a logical framework matrix, risk analysis and monitoring and management arrangements.  The design should be prepared in accordance with AusGUIDE as appropriate and based on:

- consideration of design issues noted in Attachment A

- consideration of background documentation noted below

- possible activities to be supported under the Governance Facility (Attachment B)

- consultations held with GoS and key stakeholders during the in-country mission

- other considerations raised by key stakeholders

In-Australia

5.5.	Provide a debriefing on the proposed design to a peer review meeting in Canberra (comprising representatives of AusAID and other relevant Australian government departments).

5.6.	Review and finalise an appropriate design which addresses stakeholder comments including those received through the peer review and a formal appraisal of the design.  The final design should include a draft scope of services and basis of payments against which the project can be implemented.

### 7)	Timeframe for Preparation of Design

| Key Steps | Timing |
| --- | --- |
| In-country field mission | 12-26 February 2004 |
| Debrief in AusAID Canberra | 5 March |
| Draft design prepared | 24 March |
| Draft Appraisal Note prepared | 7 April |
| Appraisal Peer Review | 16 April |
| Appraisal Peer Review comments provided to design team | 20 April |
| Final design prepared | 30 April |
| Approval for final design -Endorsement from the Minister - Endorsement from GoS - Endorsement from NZAID | May |
| Advertise tender, if appropriate | May |
| Tenders Close | June |
| Selection and negotiate Contract | July |
| Mobilisation in Samoa | August |

### 8)	Design Team

It is envisaged that the project design will comprise an AusAID consultant, a technical specialist from NZAID and a representative from the Government of Samoa.  Other key stakeholders from GoS and AusAID/NZAID may input as appropriate.

### 9)	Reporting requirements

### The Design Team should provide the following reports in an appropriate format by the date indicated:

### Prior to departure from Samoa, provide an oral briefing and Aide Memoire for the GoS and other concerned stakeholders summarising the key features and components of the recommended Design;

- Conduct a debriefing on the design at AusAID Canberra on Friday 5 March (9.30 to 12.30).

### Provide a draft design document that fully describes the Facility, addresses the issues in the scope of services above and includes a logical framework matrix, risk analysis and monitoring and management arrangements by 24 March;

- Provide a final design document by 26 April.

- Provide a draft scope of services and basis of payments against which the project can be implemented by 30 April 2004.

### 10)	Background Documentation

The design should take account of the following documents/inputs:

- Governance Facility Design - Issues For Consideration (Attachment A)

- Possible activities to be supported under the Governance Facility (Attachment B)

- The Review of Institutional Strengthening Projects (May 2003) (Attachment C)

- The GoS and GoA response to the ISP Review (Attachment D)

- Samoa Governance Facility Concept Paper (Attachment E)

- Outcomes of the Concept Peer Review held 17 September 2003 (Attachment F)

- Lessons learned from AusAID’s experience with Capacity Building (see Capacity Building Background Paper July 2003 (Attachment G)

- Public Sector Improvement Plan Concept Paper (Attachment H)

- Extract from the Manual on Samoa Project Planning and Programming (Attachment I)

- Key stakeholder input including from the GoS, AusAID and NZAID

- Lessons learned from relevant AusAID programs including the Cambodia Governance Facility, the China-Australia Governance Program, the Tonga Australia Governance Facility, the South African Governance Facility, Mongolian Australian Targeted Capacity Building and Small Activity Facility and Thailand Capacity Building Review.

Attachment A

# GOVERNANCE FACILITY DESIGN - ISSUES FOR CONSIDERATION

##### Strategic Direction

- The Facility should provide a flexible and responsive mechanism for supporting priority governance initiatives.

- The goal and purpose of the Facility should be orientated to assisting the GoS reform and build public service capacity to address national development priorities

- The Facility should support the Strategy for the Development of Samoa and the proposed Public Sector Improvement Plan (PSIP)

- Development of the PSIP including whether the PSIP should be in place before commencement of the Facility, whether the Facility should help to develop the PSIP, and whether the Facility should operate whilst the PSIP is being developed

- How the Facility could operate in a strategic manner to address whole of government reform in the absence of the PSIP or similar framework.

- Whether the Facility may serve as a transition towards a Sector Wide Approach (SWAP) or budget support focused on outcomes and impacts

- How the Facility may promote greater collegiality amongst CEOs and provide for a stronger whole of government response to public sector reform

- Use of the Facility to build skills in the Samoan consulting sector

#### Harmonisation and Coordination

- Harmonisation of administration and management procedures with GoS systems

- Harmonisation of administrative and management procedures between key stakeholders, particularly AusAID and NZAID

- Implications of harmonisation and partnership approach for contracting and quality assurance

- Respective roles and responsibilities of GoS, AusAID and NZAID

- Coordination of the Facility’s functions with other technical assistance/capacity building activities in Samoa funded by Australia (such as PACTAF, In-country Training, other ISPs, NZAID (In-country Training)) and other donors

##### Management Arrangements

- How to maximise GoS ownership and management of the Facility and build on GoS systems

- Operationalisation of the Governance Facility through budgetary support

- Capacity and willingness of GoS to undertake management of an administrative nature including sub-contracting

- Role, if any, of a managing contractor

- Appropriate management base (counterparts) for the Facility at both the strategic and operational level

- For a GoS management model, the implications of technical assistance contracted directly with the GoS including ramifications on employment conditions for sub-contractors, contracting and tendering procedures, consistency or otherwise with Commonwealth Procurement Guidelines and other accountability, financial and risk management issues

- For an AMC management model, how to build GoS capacity for management of the Facility including for performance auditing

- Possibility of a transitional/phased approach to GoS management of the Facility

- Responsibility for setting policy issues and overseeing the progress of the Facility including how AusAID and NZAID can contribute to a GoS driven process

- Appropriate financial management and accountability systems which meet the requirements of GoS and AusAID/NZAID

# Activity Identification, Design and Selection

- Process and roles of key stakeholders in identifying activities

- Reactive or proactive approach (proactive approach provides capacity for analysis and development of activity proposals)

- Process for design of activities

- Format for activity proposals/designs

- Eligibility criteria for activities: for example

- supports the GoS reform agenda as articulated in the SDS or PSIP;

- supports capacity building opportunities identified in relevant corporate/capability plans;

- requires specialist/technical expertise that is not otherwise available to the requesting agency;

- demonstrates relevant internal impacts at Agency and/or whole of government level;

- supplementation to existing institutional strengthening or other projects;

- specifies how the activity will support a better planned, managed and delivered service in 5-10 years time;

- indicates how the outcomes and impacts the assistance will be measured and reported;

- Process for consideration and selection of activities

- Access to Facility funds i.e. through periodic competitive rounds or continuous application

- Membership of selection committee (eg GoS only or GoS plus AusAID and NZAID)

#### Financial and Contract Considerations

- Contribution of GoS requesting agencies to activities

- Appropriateness of funding contributions from AusAID and NZAID

- Facility management costs relative to activity costs

- Basis of remuneration for managing contractor

- Payment of sub-contractors/expertise and its affect on the basis under which the managing contractor is remunerated

- The implications of assistance directly contracted to the GoS including employment conditions for sub-contractors, contracting and tendering procedures, consistency or otherwise with Commonwealth Procurement Guidelines and other accountability, financial and risk management issues

- Sourcing and engagement of appropriate expertise including local, Australian and/or New Zealand sub-contractors and competitive process for selection of consultants

- Relative balance of funds for activities that fit within the strategic framework

and those responding to emerging needs.

###### Monitoring, evaluation and sustainability considerations

- Sustainability of activities

- Risk analysis and risk management

- Monitoring and evaluation of activities

- Monitoring and evaluation of Facility

- Reporting systems

- Information systems

- AusAID’s Framework for Capacity Building Analysis

Attachment B

POSSIBLE ASSISTANCE THROUGH THE FACILITY

| Proposed Assistance | Department | Status of Request |
| --- | --- | --- |
| Strengthening the Audit Office, in particular to build its capacity to undertake performance auditing and value for money auditing; | Audit Office | Identified by GoS in context of ISP Review and endorsed by ISP Review team. The GoS has subsequently advised (November 2003) that assistance to the scale of assistance required for the audit office will necessitate a separate ISP. |
| Strengthening Cabinet processes, in particular at the policy coordination (i.e. the quality of advice Cabinet receives and systems for disseminating, coordinating and monitoring the implementation of Government policies) and operational levels (i.e. preparation, preservation and retrieval of Cabinet records) | Cabinet | Identified by GoS in context of ISP Review and endorsed by ISP Review team |
| Strengthening the Parliamentary system, in particular through financial support and technical assistance for the establishment of a Parliamentary Research and Information Centre; | Office of Parliament | Identified by GoS in context of ISP Review and endorsed by ISP Review team |
| Strengthen the Department of Statistics technical and management functions to establish a national statistical collection encompassing social and economic statistics, having regard to the ADB’s work in this area. | Department of Statistics | Identified by GoS in context of ISP Review and endorsed by ISP Review team |
| - Monitoring and Evaluation of progress following conclusion of ISPs | All participating ISP departments | Informal GoS request |
| - High-Level Water Utility Adviser to assist Managing Director to firmly embed the commercial orientation, service provision, and performance measurement/reporting initiatives implemented by the ISP | Water Authority | Identified in the GAP analysis prepared by Water Authority ISP Project Director Graham Costin |
| Short-term adviser input to support implementation of the PSC 2003-2008 Strategy for Professional Development. | Public Service Commission | Identified in the August 2003 PSC PMG report. |
| Support to Ministries in development and implementing their Capability Plans | Public Service Commission | Identified in the August 2003 PSC PMG report |
| Technical support for performance appraisal, monitoring and evaluation, workforce development, consultant and advisory skills and roles, information collection and information use and contract management | Public Service Commission | Identified in the August 2003 PSC PMG report |
| Support through PSC to Ministries on corporate planning, service charters, performance measures, information collection and use, contract management, HR management. | Public Service Commission | Identified in the August 2003 PSC PMG report |
| Support to a partnership of PSC, Ministry of Finance, Ministry of Communication and Information Technology to assist GoS development of interfaced IT systems across the public service. | Ministry of Finance (ICT Council) | Identified in the August 2003 PSC PMG report |
| Support for enhancement of Samoan competition laws | Ministry of Commerce, Industry and Labour and the Fair Trading Division | Identified by Howard Hollow based on study undertaken for the Ministry of Commerce, Industry and Labour |
| Support for legislative needs assessment |  | Identified by GoS |

Annex 2

People Consulted during Design

# People Consulted

| - Catherine Bennett | Acting Assistant Director General, Pacific Branch, AusAID |
| --- | --- |
| - Craig Hawke | Director, Pacific Division, NZAID |
| - Christine Pahlman | Samoa Country Manager, AusAID |
| - Philip Hewitt | NZAID Manager, NZHC, Apia |
| - Kilali Alailima | Development Programme Co-ordinator, NZHC, Apia |
| - Jason Reynolds | First Secretary (Development Cooperation), AusAID, Apia |
| - Dr. Cam Wendt | Manager, Activity Monitoring Unit, AusAid, Apia |
| - Hinauri Petana | CEO Ministry of Finance |
| - Noumea Simi | Assistant CEO ACD, MoF |
| - Faamausili Dr Matagialofi Luaiafi | CEO, PSC |
|  | Acting CEO Commerce, Industry and Labour |
| - Papalii Mr Lorenese Neru | Police Commissioner |
| - Vaaelua Nofo Vaaelua | CEO, Works, Transport and Infrastructure |
| - Auseugaefa Mafaituuga Vaasatia Poloma Komiti | CEO, Prime Ministers and Cabinet |
| - Luagalau Foisagaasina Eteuati Shon | CEO, Women, Community and Social Development |
| - Tautapilimai Levaopolo Tupae Esera | CEO, Education, Sports and Culture |
| - Tuuu Dr Ieti Taulealo | CEO, Natural Resources and Environment |
| - Lolofie Taulealeausumai Dr Eti Enosa | CEO, Health |
| - Brenda Heather Latu | Attorney General |
| - Norman Wetzell | President, Samoa Chamber of Commerce and Industry |
| - Sala Epa Tuiti | Vice President, Samoa Chamber of Commerce and Industry |
| - John F. Boyle | Secretary, Samoa Chamber of Commerce and Industry |
| - AusAid ISP Team Leaders |  |
| - Fiu Mataese Elisara | President, SUNGO |
| - Karen Mapusua | Executive Director, SUNGO |
| - Bessie Chan Mow | Mapusaga o Aiga |

Debriefing at Central Bank on 25/02/04

| Name | Agency |
| --- | --- |
| Fuimaono Poufa Te’o | Min. of Revenue |
| Jaqueline Crenshaw | Min, of PM and Cabinet |
| Palentina Toelupe | MWCSD |
| Noumea Simi | MoF |
| Tuaimalo A Ah Sam | Min of Communications and IT |
| Faamausili Dr. Matagialofi Luaiufi | PSC |
| Hinauri Petana | MoF |
| Jason Reynolds | AusAID |
| John Burton | SQIP |
| Bruce MacKay | Immigration ISP |
| Tony Gill | AusAID |
| Tuu Leti Taulealo | Min Natural Resources and Environment |
| Cam Wendt | AusAID |
| Masinalupe Tusipa Masinalupe | CEO, Ministry of Justice & Courts Administration |

Annex 3

Aide Memoire

GOVERNANCE FACILITY DESIGN MISSION

AIDE MEMOIRE

25 February 2004

Samoa Governance Facility (SGF) Design Mission

# Overview

As set out in the Design Mission’s TORs, the purpose of this assignment is to

“design a Facility appropriate to Samoa’s social and cultural context, environment and economy that will support the Government of Samoa to build the capacity of its public service to implement its national development priorities.  The proposed Governance Facility is intended to provide a mechanism that can address priority small-scale needs in support of economic and public sector reform within key GoS public sector agencies”.

The ultimate goal of strengthening public sector reform, as articulated in the SDS, is to maintain a stable macro economic framework and build economic growth.  The SGF also represents a tangible outcome of the move towards harmonisation of AusAID and NZAID programs in Samoa.

The Design Team (Angela Corcoran, Greg Ellis and Susan Elliott) visited Samoa between 12 – 26 February 2004.  The Government of Samoa assigned Ms Lusia Sefo Leau, Deputy Financial Secretary, MoF, as the GoS representative on the Design Team.  She attended all important meetings and participated fully in team meetings during which key findings were drawn together and the proposed design developed, and provided valuable insight into GoS procedures and structures.

An initial meeting was held in Apia on 12 February with officials from AusAID,NZAID and Mrs Noumea Simi, Assistant CEO Economic and Aid Coordinating Division, Ministry of Finance (MoF).  At this meeting, several aspects of the TORs were reinforced.  In particular:

- The desire for an innovative and flexible design, and one which is as far as possible driven by priorities and conforms with the structures and processes of the GoS to promote ownership and sustainability.

- That the design should allow for the Facility to be both proactive, assisting the GoS build on the achievements of economic reform to date by supporting the development of a suite of core activities; and reactive, so as not to preclude responses to emerging or immediate issues within its overall strategic direction.

- Confirmation that initial resource levels will be AUD2 million and NZD 1 million each year, over a five year period.

Overarching considerations for the design – and critical to the issue of governance itself – are the key principles of accountability and transparency for all stakeholders.

Following this initial meeting the team formally met with the CEOs of the Ministries of Finance and the PSC.  A meeting of all Ministry CEOs was then held, on 16th February.  These meetings established the framework for the team’s activities and investigations over the following period.  The Team also met with representatives of the Samoa Chamber of Commerce and Industry, the Samoan NGO umbrella organisation SUNGO, and Team Leaders of current AusAID ISPs.  The Team would like to thank everyone with whom we met, for their comprehensive, open and straightforward inputs.

The in-country mission will culminate in an Exit Debriefing for stakeholders on Wednesday 25 February, organised by the Australian and New Zealand High Commissions.  During this Debrief the Team will present its key findings and the proposed design for the Samoa Governance Facility, as set out in this Aide Memoire.

# Findings

It is the view of the Design Team that there is widespread and high level support for the establishment of a jointly funded Samoa Governance Facility.  Several key messages were repeated throughout our consultations, and it is these messages that provide the framework for the proposed design.  These are that:

- There is a need for transparency and accountability in the management and decision making processes of the Facility.

- The Facility should strive to reduce the gaps in capacity between public sector agencies, rather than (inadvertently) increase this gap.

- The Public Service does not have the capacity, from a whole-of-government perspective, to analyse the achievements of economic reform to date, and only by doing this can it then identify gaps either within or between agencies, and move forward as one to the next level of development.

- The activities funded by the Facility should reflect the key priorities of the GoS, as outlined in the SDS, and it is therefore important that:

  - these priorities be clearly articulated in the criteria against which proposals will be assessed

  - all activities ultimately supported by the Facility must be able to be justified in terms of how they contribute to improved service delivery to the community.

# Proposed Design

The proposed goal of the Samoa Governance Facility is to contribute to an improved quality of life in Samoa by supporting economic and social reforms in line with the goals of the Samoa Development Strategy.

The proposed purpose of the Samoa Governance Facility is to promote a whole-of-government approach to addressing critical constraints within the GoS public sector to service delivery.

## 3.1	Facility Components

Two categories of assistance will be supported by the Facility – projects which address the objectives of the Facility’s Core Program, and projects which respond to Immediate and Emerging Issues.

The emphasis of the Core Program component is to identify, design and implement a suite of projects that address the key public sector governance issues underpinning the goals of the SDS.  The strategic focus of the core program is critical in order to ensure the relevance and impact of the Facility.

These projects will reinforce the gains made to date by Samoa’s reform program, including through previous and current ISPs. Core Program projects may also serve to identify gaps in capacity within and between agencies which will impact on the ability of the public service to adopt a whole-of-government approach to public sector reform and, ultimately, to contribute to the Government’s overall reform agenda.  These projects may be situated in a particular agency in which a constraint or capacity gap has been identified; or may extend across a range of partner agencies. In either case, projects must be of key relevance to the public sector governance agenda.

The second component of the Facility provides a mechanism through which key immediate needs for assistance, or emerging priority issues – again within the overall Facility focus – can be addressed.  These will typically be of shorter duration than core program projects, and may be quite specific in nature, however it is anticipated that in some instances, projects assisted under Component 2 could, over time, migrate to the Core Program.

This structure, and the management arrangements for the Facility, are set out at Attachment 1.

## 3.2	Criteria for support

There are a number of broad parameters that can be established for the funding of proposals under the SGF.  However it is important that more specific guidelines reflect a process of consultation between Facility partners in determining how to allocate funding; and the development of more detailed criteria, and proposal proforma, will be an important initial activity in Facility implementation.  It is for this reason that the Design Team do not consider it appropriate that the Draft Design make any recommendation as to whether, or how, funding should be apportioned between Components.

The overarching criteria in determining funding support are:

- That proposals clearly articulate the link between the project and its intended outcome,

- That proposals clearly demonstrate how the activities to be undertaken within the project will result in the achievement of the identified outcome, and

- That the outcome is demonstrably consistent with the objectives of the Facility in terms of addressing critical constraints to service delivery.

Other criteria that should be considered include:

- Value for money – that the cost of the proposal and the type of activity proposed represent the best and most cost effective way of achieving the desired outcome

- Appropriate counterpart agency contribution – proposals should clearly identify what contribution will be made by the partner agency(ies)

There are certain types of activities that are not considered appropriate for Facility funding.  These include:

- Capital equipment.

- Funding of agency recurrent costs.

- Costs associated with regular attendance at, or hosting of, recurring conferences (that form part of the core function of the agency attending/hosting).

- Sitting or attendance fees associated with participation in project activities.

## 3.3	Management operations

The management structures developed:

- must be designed not only to deliver a cost-effective program of assistance but must also fulfil the wish of the three governments that the Facility is, over time, managed solely by the Government of Samoa;

- must not create unnecessary levels of administrative bureaucracy and wherever possible be harmonised with standard administrative procedures of the GoS;

- must wherever possible utilise existing systems and structures (particularly within the GoS)

With these fundamental requirements in mind, this design proposes the establishment of a number of administrative structures that provide the necessary management oversight for the programs supported by the Facility (Annex 1).  These are a:

- Facility Coordinating Committee (FCC)

- Facility Management Board (FMB)

- Facility Management Unit (FMU - incorporating a contracted support team in the short to medium term)

- Technical Support and Review Group (RG - incorporating a contracted support adviser in the short to medium term)

- Governance Development Fund (GDF)

## 3.4	Location of the FMU

Taking into account the guidelines given to the Design Team by AusAID and NZAID, and the messages received during the consultations the Team have undertaken during this mission, the Design Team recommends that the FMU be located within the Ministry of the Prime Minister (MPM).  The Design Team believes this is the logical place in which to locate the FMU.

It is important to note that this recommendation not only best reflects the goal and purpose of the Facility but the articulated views of the majority of stakeholders consulted, including key ministries, when asked where the FMU should be located.

The reasons for placing the FMU in the MPM are:

- That in its role as the overarching government agency, it will promote increased cooperation among agencies.  An effective way of promoting interagency cooperation is to link it to the development of issues – in this case the public service governance issues underlying the SDS agenda – that are to be put to Cabinet.  This will ensure that Cabinet is provided with a whole-of-government approach to these issues.

- That in providing the supporting structure for the ministries of government, the MPM has the mandate for pursuing the whole-of-government agenda and for providing high level and integrated policy advice to Cabinet and the Prime Minister.

- The status of MPM in terms of perception – stakeholders clearly expressed the view that placement within the MPM will help avoid the potential for narrow, Ministry-specific priorities to take precedence over the mix of broader socio-economic priorities that make up the Government’s development agenda.

- The need to build capacity in this critical part of government.  This will, in turn, allow the management of the GF itself to be a capacity building exercise, and a catalyst for change.

To address any lack of capacity in the MPM to effectively support Facility operations, and to ensure that other ministries place due importance on the pivotal role that will be played by the FMU, the Design Team proposes the following risk reduction strategies:

- That the FMU be established as a self-contained unit staffed specifically for this task.  This reduces the likelihood that staff will be diverted by other business, while improving the overall capacity of the MPM to undertake its core business in ensuring that there is a whole-of-government approach to implementing the GoS reform agenda.

- That a Stop/Go Review be held after Year 1 that assesses the effectiveness of support to the Facility by the MPM, to confirm that its placement within the Ministry is appropriate.

- That Board membership includes high level representation from other Ministries, and from the private sector and civil society.

- That the skills set of the advisory team complement the capacity needs of the MPM.  In addition to a three-person Contracted Support Team, the Design Team also proposes short term support to assist with the development of an HRD and training plan for FMU staff.

- To provide a counterbalance and check, the Design Team proposes the establishment of a small Review Group within the Ministry of Finance to ensure independent review and appraisal.

In addition, and which the Design Team believe to be an important consideration, this option makes the GF, in and of itself, a mechanism for promoting good governance and capacity building at the highest level of the public service, and one that can be achieved within the management costs of the Facility rather than absorb program funding.

# Outstanding Issues

The following issues need to be dealt with prior to the establishment of the Samoa Governance Facility.

Governments of Australia and New Zealand

- Protocols for the establishment, management and funding of the Facility, both in relation to the contracted support and the Development Fund.

- Harmonisation of donor management and monitoring responsibilities.

- Determination of the level of representation on the Facility Coordinating Committee.

- The development of an agreement with the Government of Samoa, subsidiary to the overarching Development Cooperation agreement(s), in relation to the provision of this assistance.

Government of Samoa

- Confirmation of location and staffing, at the appropriate level, for the Facility Management Unit and the Review Group within the Ministries of Prime Minister and Finance respectively.

- Provision of accommodation for both GoS Facility staff and contracted counterparts.

- Confirmation of timing by which the above will be in place to allow for timely contracting and mobilisation of counterpart contracted support team by AusAID/NZAID.

# Next Steps

- Debrief by Design Team in Wellington and Canberra (2 and 5 March 2004)

- Submission of Draft PDD (24 March 2004)

- Appraisal of Draft PDD (comments due 20 April 2004)

- Finalisation of PDD (27 April 2004)

- Formal approval of PDD by Governments of Samoa, Australia and New Zealand

- Tendering and contracting of support team

- Mobilisation of support team

Facility Management

Program

Funds

Proposed Program

Endorsed  Program

Review Group

Ministry of the

Prime Minister

Facility Management Unit

Donors

GoNZ/GoA

Contracted Support Team

Transitional Review Adviser

Facility Management Board

GoS/Private Sector/Civil Society representation

Core Program

Projects > 12mths

Immediate and Emerging Issues Program

Project 1

Project 2

Project 1

Project 2

Agency 2

Agency

Agency

Agency

Agency 1

Facility Coordinating Committee

GoS/GoA/GoNZ

Approved Program

Samoa Governance Facility

Project Activities

Governance Development Fund

Annex 4

GoS Planning Systems

# PERFORMANCE MANAGEMENT SYSTEM

### VISION							Legislative Framework

Strategy for the Development of Samoa

Public Service Act 1977 with Amendments

Public Finance Management Act 2001

Cabinet Directions

Ministerial Specific Legislation

Sector – Wide Plans

Corporate Performance Management System

Ministerial Corporate Plan

Objectives					Performance Measure/Targets

Capability Plans						Outcomes

Annual Report

Service

Charters

#### Operational Performance Management Systems

Annual Management Plans

Budget Outputs / Sub-Outputs			Performance measures / Targets

Activities					        Capability Plans

Individual Performance Management

A parallel process exists for State Owned Enterprises (SOEs), which are linked via the SOE Monitoring Unit (MoF) and their development is closely aligned to government systems.

Annex 5

Summary Logframe

# Summary Logframe: Public Service Improvement Facility

| Objective Level/Code | Narrative Summary | Verifiable Indicators | Means of Verification | Assumptions |
| --- | --- | --- | --- | --- |
| Project Goal | To improve the efficiency and effectiveness of Samoa’s Public Service to support Samoa’s national development priorities. | Transparent, accountable economic and social policies implemented by GoS. | GoS policy documents and legislation, including Public Sector Improvement Framework and Sector Plans. Economic and social indicators. Community feedback on GoS reforms. | That the GoS remains committed to the economic and social reforms articulated in SDS. |
| Project Purpose | To strengthen cooperation and collaboration between public service agencies (and between them, the private sector and civil society), in identifying and addressing critical constraints within the GoS public sector to effective service delivery through a range of institutional strengthening initiatives. | Improvements in whole-of-government approach to policy development and service delivery issues. Coherent and integrated program of PSIF assistance, as articulated in PSIF Review and Forward Plans (RFPs), which is aligned with relevant GoS structures and processes, driven and owned by the GoS reform agenda. | External review. Public Sector Improvement Framework and Sector Plans. Ministry Annual Reports. RFPs. PSIF evaluations: - Review of Transitional Support - Review of Facility Effectiveness. Community feedback on service delivery. | Continued GoS stability, commitment and ability to progress reform agenda, including willingness of Ministries to support whole-of-government policy mandate. |
| Component 1: | Support (from identification to completion) strategically identified core activities promoting public sector reform. | Activities approved and successfully implemented that contribute substantively to the service delivery priorities of agencies involved. Proactive and targeted engagement with and advice provided to partner agencies by FMU. | Regular RFP reports on activities funded. Financial reports on Fund disbursements for core program activities. Annual Review Group sample evaluation reports. Individual Activity Completion Reports. Review of Facility Effectiveness. | Agreement by stakeholders to a clearly focused strategic direction for core program. Appropriate allocation of funds to core program activities. Sufficient eligible activities identified in timely manner by participating agencies. |
| Component 2: | Facilitate GoS response to their immediate and emerging priorities in public sector reform. | Priority and coverage of the IEP program activities which are delivered. Strategic and timely advice and decision making by FMU. Percentage of activities /initiatives successfully implemented. | Financial reports on Fund disbursements for IEP program activities. Regular RFP reports on activities funded. Annual Review Group sample evaluation reports. Activity Completion Reports. Review of Facility Effectiveness. | Agreement by stakeholders to an appropriate strategic direction of IEP program. Appropriate allocation of funds to IEP Program. Eligible activities identified in timely manner by participating agencies. Participation and appropriate responses by stakeholders to enable timely and appropriate decision making by FSC. |
| Component 3: | Develop a Facility Management Unit (FMU) able to implement and manage an effective and efficient PSIF. | Demonstrated developmental, management and administrative expertise used in FMU decision making and RG appraisal and review function. Strategic FMU engagement with stakeholders. Reducing role of CST demonstrated. | Six monthly CST reports. Stop/Go Review. Review of Transitional Support. Review of Facility Effectiveness. | GoS commitment to location of FMU and its role in pursuing PSIF aims. Availability of appropriate GoS resources to staff FMU. Minimal staff turnover amongst FMU/RG staff. Donor commitment to capacity building role of PSIF. |
| Component 4: | The effective management of the Public Sector Improvement Facility. | Collaborative relationship between CST and FMU. Collaborative and supportive relationship between FMU, FSC and FCC. Secretariat services provided to FSC and FCC. Documented and functional Facility operational protocols and guidelines. Efficient and accountable use of PSIF resources, in compliance with agreed standards. | Records of decisions made, reviews sought, proposals approved/rejected. PSIF Operational Handbook. Monitoring and Evaluation Framework. Review and Forward Program documents (RFPs). FSC and FCC Minutes. Stop/Go Review. Review of Facility Effectiveness. Annual Fund Audit reports. | GoS, AusAID and NZAID commitment to appropriate resourcing of PSIF. Willing participation and appropriate responses of stakeholders to enable timely and appropriate decision making. |

Annex 6

Program Processes

# Program Determination, Activity Design, Implementation and Review

1.	Context

The processes associated with determining the shape and direction of the overall program of activities to be funded and managed by the Facility, the design of specific activities, their implementation and review are fundamentally important to the success of the Public Service Improvement Facility (PSIF).

This annex is designed to provide stakeholders with an understanding of the Design Team’s view of how this might work.  As such, it should not be read as prescriptive of how the process should be managed.  Further, the extent to which all the processes described below would be undertaken will be dependent on the size and complexity of the specific activity.  It is anticipated that many smaller activities will be follow a truncated cycle and are unlikely to have to go through each of the approval, design and appraisal processes described below.

The final processes and the format for associated documentation will be determined through consultation with all stakeholders during the first three months of Facility implementation and will be detailed in the PSIF Operational Handbook.

2.	Overall Program Determination

To ensure that the PSIF remains consistent with its purpose, it will be important that all stakeholders agree on an initial set of broad strategic priorities that will inform the Facility Steering Committee’s (FSC) decisions in relation to what are the areas for which core program support is most critical.

2.1 	 A Public Sector Strategic Review and Planning Activity

The ISP Review concluded that there was value in developing a Public Sector Improvement Plan that would provide the necessary strategic direction for the Facility.  Some concern was expressed during GoS consultations that the development of such a Plan, as envisaged by the ISP Review, may be an unnecessarily complex exercise.

In an attempt to balance the critical need for a clear, agreed strategic focus to guide the PSIF against the danger of expending too many resources on the development of a detailed and possibly too rigid Public Sector Improvement Plan, the Design proposes an initial foundational activity - the Public Sector Strategic Review and Planning Activity.  The foundation activity will allow stakeholders to determine and clearly articulate the strategic public sector reform focus of the PSIF, and ensure that the PSIF has a manageable program of activities that will contribute positively to the GoS’ reform priorities.

Recognising that, in line with other Sector Plans, the GoS is committed to developing a Public Administration Sector Plan, this foundational activity can assist the key central agencies (the Public Service Commission in consultation with the Ministry of Finance) to develop that plan.  A key element of the Public Sector Strategic Review and Planning Activity will be the articulation of a Public Sector Improvement Framework that will outline the critical areas of reform focus required to establish the foundations for sustainable public sector improvement.  Key elements of that framework will be the development of a series of public sector improvement principles, strategic priorities and a set of funding principles (including contestability) that will guide how funds available under the PSIF will be directed.

The activity will provide the opportunity for the GoS and other key stakeholders to reflect on the reforms progressed so far and provide the necessary information to allow the Facility Steering Committee to make an informed determination of the key program foci for the Facility.  This activity will use documentation such as Sector Plans, Department Corporate Plans and Service Charters, existing or pipeline legislation and any associated reviews of their implementation, together with wide consultation with stakeholders both within and outside Government to inform this process.

It is anticipated that this activity will take around 6 months to complete.  During that period it is unlikely that it will be considered acceptable that the Fund support no other activity.  For this reason it is recommended that a number of small priority activities be undertaken, albeit under Component 2.  (It is recommended that these be undertaken under Component 2 because PSIF core activities – Component 1 – should be assessed against the agreed priorities articulated in the Public Sector Improvement Framework, which will be developed as part of the foundational Public Sector Strategic Review and Planning Activity).

The GoS have indicated that a number of priority activities have already been identified.  These focus principally on strengthening the institutions of accountability such as the Auditor General and Statistics.  It is considered that these are likely to be appropriate complementary activities that would provide important fundamental capacities necessary to implement the broader Public Administration Sector Plan.

In keeping with the flexible nature of Component 2 (see 2.2 below), the opportunity exists to fund other urgent priority activities that may emerge during this early period.  However caution should be applied when approving activities.  Attempting to approve too many additional activities at this time could undermine the proper establishment of PSIF operations given the need to focus on finalising the Public Administration Sector Plan and on the need to develop FMU capacity.

  - Program Priorities - Core versus Immediate and Emerging Priorities Components

In determining the strategic foci of the PSIF consideration should be given to the development of different program priorities for the Core Program Component (Component 1) and the Immediate and Emerging Priorities Component (Component 2).  One of the lessons learned from past experience of facility operations is that a lack of strategic focus can create great difficulties for both those who must manage the facility and those that must approve its forward program.  Inevitably there will be a greater demand for assistance than funds available.  A clearly defined strategic focus makes it much easier for determining quickly what can and cannot be considered.  Further, there is a danger that if the focus is too wide, the program will become too dispersed contributing to an inability to clearly demonstrate the impact that the PSIF is having on addressing key public sector reform priorities.

The conflicting tension is that there is a concomitant requirement for flexibility and responsiveness.  This can work against the need for a tight focus.

The two-component program structure contained within the PSIF design has been designed to try address these competing demands.  The Core Program Component can be tightly focussed to ensure that it supports only the most critical public sector reform priorities.  The Immediate and Emerging Priorities Component can have a wider focus (while remaining faithful to the overall goal and purpose) allowing for support to be provided to a wider range of activities.

Complementary to the need to articulate a clear focus (particularly for core programs) there is a need to specify a split in the funds allocated to approved activities to ensure that support for core program activity is not undermined by the less strategically focussed support likely to be delivered under Component 2.  Any eventual split must be determined/agreed by the three governments, however it is recommended that as a minimum at least 60% of available program funds should be directed to Component 1 activities.

Any determination of program focus/funding splits will, of necessity, be subject to revision over time, but this exercise will provide a good foundation for progressing the Facility’s program in a strategic manner.

3.  The Activity Management Cycle

The Activity Management Cycle is a useful tool for describing the processes that must be followed from activity identification to completion.  It is the framework upon which all other processes and procedures are built.

This cycle describes the management processes associated with the identification and management of activities and the consultation, approval and review/feedback processes that must be in place.  These processes ensure that the Facility is constantly reassessing both its direction and its approach to implementation on the basis of changes to the operational environment and in response to lessons learned.

The diagram below outlines the activity management cycle.  In considering this, it should be noted that not all activities will follow these steps to the letter.  Simple, small-scale activities may be fast tracked to ensure that unnecessarily bureaucratic steps are not imposed without justification (refer 3.1.1 for further details).

Appraisal

Appraisal

Design no longer complies with approval

Identification

Sourcing & Contracting

Mobilisation

Monitoring & Management

Activity Completion

Initial Design

Detailed Design

FSC Consideration

Declined or referred to another program

Feedback and request for amendment

Declined or referred to another program

Declined back for rescoping

Feedback and revision

Activity Review Reports to FSC

## The Activity Management Cycle

3.1	Identification

As with other stages of the cycle it is important that the process of identification be undertaken in a structured fashion.

An important initial activity of the Facility will be the development of a communication strategy designed to clearly articulate what the PSIF can and cannot support.  This strategy will be designed to minimise the likelihood of inappropriate requests for assistance being made.  The design strongly advises against making a general call for proposals but rather recommends a much more strategically targeted approach to the solicitation of proposals.

Inquiries seeking PSIF support will be referred in the first instance to the Facilities Management Unit (FMU).   These early consultations may not involve specific documentation but will involve, through discussion, an assessment of the proposal against:

- the key strategic priorities based around those provided in the Samoa Development Plan (and that will be modified over time with input from the Public Sector Strategic Review and Planning Activity),

- the criteria for approving activity proposals,

- the availability of other, possibly more relevant forms of development assistance; and

- the types of activities that cannot be supported by the Facility.

A PSIF website will provide relevant information about PSIF, eligibility for funding and guidance on the application process etc.

Depending on the capacity of the initiating Agency, the FMU may provide assistance to support them to think through how appropriate the proposed activity is to PSIF support and if relevant to help them develop the initial proposal documentation.

Wherever possible the FMU will seek to discourage formal applications for proposals that are highly unlikely to be supported to avoid wasted effort and the raising of expectations that cannot be fulfilled.

Where, from these early consultations it appears that the proposal is appropriate to PSIF support, an initial proposal will be prepared by the Agency.  The proposal is designed not only to allow the FMU to screen the proposal more formally but to guide the Agency through the processes it should undertake to ensure that it is proposing an activity that will in fact address the Agency’s needs.

A standard proposal format is recommended.  It is suggested that the Initial Proposal should contain the following information:

- Title of Managing Agency and a sentence or two on its key functions (particularly those functions that will be the subject of this proposal);

- Title of Managing Unit (division, branch etc. needing support and a sentence or two on its key functions);

- Other Agencies involved - a sentence or two outlining the other agencies involved in multi agency projects.

- Objective and scope of the proposal – a brief description of what the activity is, which reform objective(s) is/are being addressed by the activity, the anticipated timeframe;

- Indicative inputs – that is, what types of sub-activities will be undertaken and an indication of their duration;

- Rationale – brief statements about how the proposal relates to the purpose of the facility (ie service delivery) and the recipient agency’s strategic plans/priorities.

- Agency capacity – statement of capacity of managing agency to implement activity.

- Indicative Outputs

- Expected outcomes and any preliminary thoughts on associated monitoring and evaluation considerations (eg. How will we know that the outcomes have been achieved?)

- Other issues - a space to comment on any issues to be aware of, for example, urgency, donor/other program coordination, linkages to previous programs of support, potential political sensitivities etc.

Once completed, the initial proposal will be considered by the FMU and a determination made as to whether it conforms to the approved PSIF criteria.

If it is declined at this point, the Agency is formally advised (and provided with reasons for the decline).  If the Agency is unhappy with the decision, it may seek to have the decision reviewed either by the Review Group or by the FSC at its next meeting.  In either case however, the proposal does not move to the initial design stage until there is general agreement that it should do so.

If it is accepted, the Agency is informed.  The proposal then moves to the Initial Design stage.

    - One-step approval

If at the time of identification, the cost of the proposed activity is estimated to be less than T$50,000, the FMU may determine that the activity is sufficiently straightforward that more detailed documentation is not necessary (this may often be the case with Component 2 activities).  In this situation, the FMU will seek the Review Group’s sign-off and then circulate the initial proposal together with the FMU/RG’s recommendation to FSC members for approval.

For such activities proposed for funding under Component 2, it may be considered unnecessary to convene a formal meeting of the Committee but rather that members be provided with a time frame (i.e. within 5 days) by which approval or further requests for clarification would be communicated to the FMU.

Of course, the FSC maintains its right to insist on adherence to the full approval process if it considers that, despite the small cost, the complexity/sensitivity of the proposed activity justifies the greater scrutiny provided by the full approval process.  However Component 1 activities should all, regardless of cost, be presented to the FSC during regular approval rounds (although they may only need to proceed through the one step approval process).

3.2	Initial Design

The Agency, with the assistance of the FMU, develops the initial design that will be submitted to the FSC for approval at its next meeting.

Initial design documentation is the key ‘high level’ document used by the FSC to determine whether the activity proposal proceeds to implementation.  As such it needs to contain sufficient detail for assessments to be made, while remaining as succinct as possible.  The level of detail in any specific proposal will vary depending on its complexity and likely cost.  However a standard design format is highly desirable.

It is suggested that the Initial Design should contain the following pieces of information:

- Activity Title;

- Recipient Government Agency – while an activity may involve more than one Government Agency, it is recommended that there be one principal agency that takes on overall responsibility for the activity;

- Subsidiary Agencies – some activities may involve partnering with other government or non-government agencies;

- Key individual counterparts and their contact details – a activity must have identified Ministry officials who will take responsibility for the overall management of the activity;

- Activity Goal and Objective(s) – this is likely to be a restatement and possible elaboration of the goals stated in the initial proposal.  They should be drafted in a manner that makes sure that the activity will conform with the purpose of the PSIF and with the strategic priorities articulated by the GoS;

- Description of the activity – this will outline in more detail than the Initial Proposal the activities that comprise the activity and how they contribute to the achievement of the strategic goals.

- Proposed inputs, outputs and outcomes

- Agency capacity – statement of capacity of agencies to implement activity.

- Critical issues - including risk analysis and management;

- Cross-sectoral analysis – including where relevant, a discussion of the contribution to an improved quality of life, gender and environmental issues;

- Linkages and Coordination – an outline of any linkages this activity may have to other activities (ie. is this a follow-up to a previous activity), to other government or non-government agencies or groups, to other development programs (ie. does this arise from or feed into any other programs funded either by Australia, New Zealand or another donor);

- Indicative inputs and costings – a description of the inputs and of their anticipated cost.  This should also identify which costs are to be funded by the PSIF and which are to count as the Agency’s contribution to the activity;

- Monitoring and evaluation framework – a description of how the strategic outcomes of the activity will be monitored and evaluated.  It will be important to ensure that framework allows for rigorous qualitative and quantitative measurement and, where the activity is a long one, assessment over time;

- CEO(s) endorsement – this is an endorsement, signed by the CEO(s), confirming that they have reviewed the design and agree with its focus and of the resource commitments to be undertaken by the agency(ies).

3.2.1 Appraisal

Once complete the Initial Design will be referred to the Review Group (RG) for appraisal, if the activity budget exceeds T$50,000.

The Review Group’s role is to provide an independent appraisal of the design.  The RG will seek to confirm that, in their view, the proposed design meets the criteria for support under the PSIF and that it represents value for money, has the appropriate technical and developmental integrity to ensure that it can deliver the outcome(s) sought.

The Review Group can make the following determinations:

- It can refer the design back to the Managing Agency  via the FMU, requesting that further work be done on the design.  Subsequently the amended design will be referred back to the RG for endorsement.

- It can endorse the design as satisfying the criteria for support under the PSIF and that it is developmentally sound.  If the design requires minor modification, the RG may provide a qualified endorsement.  A qualified endorsement allows the activity to proceed to FSC submission without reconsideration provided the proposing Agency ensures that the RG’s recommendations are acted upon and that these actions can be confirmed to the Facility Steering Committee at its next meeting.  This avoids unnecessary and costly (in time and resources) cycles of revision and re-submission. Once endorsed the initial design is then referred to the FSC for consideration at its next meeting.

- If the RG considers that the activity could be supported more appropriately under another program, it can refer the design for consideration by that program.

- If the RG considers that the activity does not meet the criteria for funding under the PSIF it can decline it and, in writing, provide its reasons for rejecting it.  If the Agency and/or the FMU is unhappy with the decision, they may seek to have the decision reviewed by the FSC at its next meeting.

3.3 Facility Steering Committee Consideration

Every six months all the endorsed activity proposals will be presented to the FSC for its consideration.

The FMU will provide a range of documentation including:

- A review of the performance of previously approved activities;

- Advice of proposals received and declined or referred elsewhere together with the reasons for their rejection;

- A summary of the ‘time sensitive’ or ‘one-step’ proposals approved ‘out-of-rounds’;

- A financial report outlining past expenditure and future commitments;

- All initial designs endorsed by the Review Group for Facility Steering Committee consideration; and

- Any initial proposals or designs declined by the FMU or RG for which a review of the decision is being sought.

A detailed overview of this FSC documentation is provided at Annex 7.

- All endorsed activity designs and any declined proposals for which a review is being sought, will be assessed by the FSC against a set of approved criteria (see Section 4.5).  These will be determined during the first three months of Facility operation.

The Facility Steering Committee can make the following determinations:

- It can refer the design back to the Agency and the FMU requesting that further work be done on the design.  Subsequently the amended design will be referred back through the Review Group to the FSC for approval;

- It can approve the design as satisfying the criteria for support under the PSIF and that it is sound both technically and developmentally.  If the design requires minor modification, the FSC may provide a qualified approval.  A qualified approval will allow the activity to proceed without reconsideration provided the proposing Agency ensures that the FSC’s recommendations are acted upon and that these actions are reported back to the FSC at its next meeting or reported on in the early stages of activity implementation.  This avoids unnecessary and costly (in time and resources) cycles of revision and re-submission.  Once approved the activity can proceed to detailed design, funding and implementation;

- If the FSC considers that the activity could be supported more appropriately under another program, it can refer the design for consideration by that program; or

- If the FSC considers that the activity does not meet the criteria for funding under the PSIF it can decline it and, in writing to the proposing agency, provide its reasons for its decision.

3.4 Detailed Design

Following FSC approval of the initial design the Agency, with the assistance of the FMU if and where required, will develop the detailed design necessary to allow for accurate costings, proper sourcing and contracting of inputs (both advisory and material), logframes, risk matrices and work programs as appropriate.  The level of detail required in a detailed design will vary according to the cost and complexity of the activity.

The following inputs are suggested:

For advisory inputs:

### Adviser requirements

- Adviser responsibilities and accountabilities

- Technical components

- Skills transfer objectives

- Reporting relationships

- Requirement for the position (qualifications, experience, knowledge, skills, personal attributes)

- Special requirements (risk factors, work location etc.)

### Counterpart Development

- Names, positions and contact details of identified counterparts

- Counterpart availability (consideration should be given to multiple counterparts or backups to maximise the potential for skills transfers to be sustainable)

- Counterpart profiles (qualifications, experience, skill needs etc)

### Agency information

- organization(s) chart(s) and relationships

- Agency(ies) purpose and functions

- Resource requirements – to support the placement, for example, purchase of any essential office equipment if not available in partner agency(ies)

- Recruitment Strategy (media to be used to advertise the position, criteria for selection, price/technical weighting of the proposal, selection of assessment panel membership, use of NZAID/AusAID Approved Local Consultants, direct recruitment from a New Zealand, Australian or other Government agency)

#### For non-Advisory Inputs

There are many possible types of non-advisory inputs.  The type of inputs will have been identified in the original design and have been approved by the FSC.  The type of inputs that may be relevant in a particular activity include:  study tours, short term attachments as part of twinning arrangements,  participation in short-term formal training courses, essential procurement etc.  The documentary needs will vary according to the nature of the input and is likely to be much briefer than that required for advisory inputs.  For example a proposed short term training course might include:

- Objectives of the training (including its strategic linkage to the objectives of the overall activity)

- Description of the type of organisation needed to provide training management services

- Criteria for search/selection of partner training organisation(s)

- Criteria for selection of training participants

- Organisation and logistics

- Method of monitoring and assessing the contribution of the training to the overall activity

3.4.1 Appraisal

Once complete the detailed design will be referred to the Review Group for appraisal.

The Review Group’s role is to provide an independent appraisal of the design.  The RG will seek to confirm that, in their view, the proposed design conforms with the parameters of the approval provided by the FSC and that it has the appropriate technical and developmental integrity to ensure that it can deliver the outcome(s) sought.

The Review Group can make the following determinations:

- It can refer the design back to the Agency and the FMU requesting that further work be done on the design.  Subsequently the amended design will be referred back to the Review Group for endorsement;

- It can endorse the design as satisfying the criteria for support under the PSIF and that it is sound both technically and developmentally.  If the design requires minor modification, the RG may provide a qualified endorsement.  A qualified endorsement allows the activity to proceed to sourcing and contracting without reconsideration provided the proposing Agency ensures that the RG’s recommendations are acted upon and that these actions can be confirmed to the FSC at its next meeting.  This avoids unnecessary and costly (in time and resources) cycles of revision and re-submission.

If the RG considers that the activity no longer meets the parameters of the FSC approval it can decline to endorse it and refer the design back to the FSC for reconsideration.  The RG will provide its reasons for rejection in writing to the agency.  While the criteria for rejection will be developed by the Facility’s stakeholders during the early phase of mobilisation, the following are some suggested criteria:

- That the full activity costings exceed the FSC approved budget by an agreed percentage (to be determined in consultation with stakeholders during the development of the Handbook);

- That the activities to be undertaken no longer conform with those contained in the initial design approved by the FSC;

- That the counterpart contributions are now less than those contained in the initial design approved by the FSC;

- That the goal and objectives have changed;

- That the managing agency has changed.

The FSC will then consider the detailed design and the RG’s recommendations and will determine whether the activity proceeds in its revised form or whether it should be sent back to the proposing agency for redesign.

3.4.2 Funds Release

Once endorsed by the RG, the FSC-approved funds can be released by the FMU to the managing agency in accordance with the endorsed budget and GoS procedures.  Depending on the size of the activity, this may be as a simple lump sum, or funds could be released in a series of tranches with subsequent tranches being contingent on satisfactory achievement of specified activity milestones.

3.5 Sourcing and Contracting

Based on the endorsed design (including any qualifications provided by the RG), the managing agency can proceed to the sourcing of the necessary technical and material inputs and undertake any associated tendering, contracting and procurement.

All procurement processes must comply with the GoS Procurement Guidelines.  The managing agency will be required to properly document all processes undertaken.  These processes will be the subject of the FMU’s monitoring and may be reviewed/ audited by the RG (or an external auditor if requested by the FCC) if the activity is included as part of the annual sample review.

The work associated with sourcing and contracting inputs can be managed either directly by the agency or with the support of the FMU.  The level of any FMU involvement will depend on the assessed capacity of the managing agency to undertake this work themselves.

3.6 Mobilisation

In accordance with design requirements the required inputs will be mobilised in a manner that ensures the smooth progress of the activity.  Depending on the activity this could include activity and agency familiarisation briefings for technical advisers, the release of identified counterpart staff, the delivery and installation of necessary equipment, the booking of accommodation, training venues etc.

As with sourcing and contracting, the FMU can provide varying levels of assistance to the managing agency.

  - Monitoring and Management

Once mobilised the activity will require regular management and monitoring to ensure that it is progressing in accordance with the design.  Depending on the type and complexity of the activity, this could include:

- agency staff, or adviser and counterpart staff management;

- Monthly, quarterly or six-monthly workplans for any national or international advisers;

- financial management;

- any necessary procurement;

- evaluation and appraisal of key milestones; and

- completion of progress reports to the FMU.

Depending on the complexity, the type of contracted support and the capacity of the managing agency, these tasks may be undertaken by the organisation contracted to deliver the activity and/or the managing agency with the assistance of the FMU if required.

  - Activity Completion

On completion an Activity Completion Report should be submitted to the FMU which offers an evaluation undertaken of the activity to:

- review and assess whether the activity has achieved the approved aims and objectives;

- comment on the contribution to development objectives and the likely sustainability of benefits on completion of the activity;

- identify whether any follow up activities need to occur to ensure the sustainability of the reforms introduced;

- comment on the performance of sub-contractor(s) involved in implementation of the activity; and

- draw out any lessons learned that can be fed into the design of future activities.

In addition to this qualitative assessment, a reconciliation of all financial accounts and an acquittal of the funds provided for the activity must be completed together with a certification of the eventual counterpart contributions to the activity.

The activity evaluation, certification of counterpart commitments and a certified financial acquittal incorporated into the Activity Completion Report should be signed off by the CEO of the managing agency and submitted to the FSC via the FMU together with the return of any unexpended funds.

Copies of activity completion reports (or extracts thereof) will be publicly available on the PSIF website in order to facilitate linkages and lessons learned between agencies.

Annex 7

The Public Sector Improvement Facility Review and Forward Planning Process

The Public Sector Improvement Facility Review and Forward Planning Process

## 1.	Context

The Review and Forward Planning process is a key tool in the activity management and planning cycle to be developed by the FMU, with support from the Contracted Support Team.

This discussion paper is designed to provide an appreciation of the Design Team’s view of how this process might work.  As such, it should not be read as prescriptive of how the process should be managed.  The final process and the format for associated documentation will be determined in consultation with the FMU and successful bidder during the first three months of program implementation and should be detailed in the PSIF Operational Handbook as part of the formal procedures for activity planning and management (Refer Output 4.2).

The exact specification of the initial set of core program activities and budget will be developed by the FMU in the initial Review and Forward Program (RFP) (See Output 4.5) and will be largely determined by the Framework developed as a result of the Foundation Activity (Component 1, Output 1.1).  In developing a pipeline of facility assistance, the FMU should, with the assistance of the CST and Review Group:

- liaise with GoS agencies to assess relevant needs and priorities;

- develop linkages between agencies with similar assistance needs;

- develop and implement a strategy to ensure potential partner agencies are well informed of the Facility and its capacities;

- develop strategic planning tools as a basis for prioritising and programming the implementation of activities; and

- develop agency capacity in activity management, monitoring, evaluation and reporting.

## 2.	The Process

The RFP process will occur every six months for the life of the program. It is designed to provide the necessary information for consideration by the FSC at its six-monthly meetings.  With its six-month review element coupled with a 12-month forward plan, the six-monthly Review and Forward Plan in effect becomes a rolling annual plan and is the key management document.

The RFP process performs two primary functions: a review function that reports on activities recently completed and underway, and a planning function outlining the proposals for new activities being presented for the FSC’s consideration and approval.

The Review function is designed to:

- Review the progress of all Core Program activities towards the approved goals and objectives of the Facility and the activity;

- Provide a qualitative and quantitative assessment of performance against approved performance indicators;

- Report on the projects implemented and managed under the Immediate and Emerging Priorities component over the previous six months and makes recommendations (where considered appropriate) for their incorporation within core programs;

- Identify and inform any risks and constraints currently being experienced or anticipated over the next 12 months (and notify the FSC of the processes the FMU intends to put in place to minimise and manage those risks and constraints); and

- Recommend to the FSC any changes to previously approved core program activities.

The Planning Function is designed to:

- Present to the FSC any revised forward plans of previously approved core activities.  This recognises that long-term activities may require adjustment/fine-tuning over time;

- Present to the FSC new proposals for funding under the core and IEP components together with appraisal recommendations for funding approval; and

- Report on financial year expenditure to date and estimated forward expenditure for the balance of the financial year and recommend to the FSC the funds that should be sought for deposit into the Facility Fund by the donors.

The FMU will be responsible for the preparation of the RFP.  They will be supported in doing this by the Review Group who will undertake Performance Assessment and Evaluation reviews of a sample set of activities identified by the FSC throughout the year.

Once the FSC is satisfied with the review findings and the forward program and has approved the RFP, it will recommend it to the FCC.  The FCC will meet to consider the approved RFP and, if satisfied that the activities supported by the Facility are appropriate and effective will endorse the RFP.

Once FCC endorsement has been secured, the FMU will proceed to implement the forward plan.

2.1 Timing of RFP development and consideration

To give the FMU time to mobilise, undertake an initial round of consultations with stakeholders, establish the FSC and undertake the Foundation Activity, it is proposed that the first formal meeting of the FSC to consider the initial RFP be held in month 7.  Once approved, the plan will determine the direction of the core and IEP programs of activity for the following six months.

To ensure that some activities can proceed in the months preceding the endorsement of the first RFP, the design proposes that a foundational activity be undertaken during this period (Output 1.1).  The Public Sector Strategic Review and Planning Activity will assist in defining the focus of the PSIF on public sector reform and will also support the key central agencies to develop the GoS Public Administration Sector Plan (see Annex 6)  A key element will be the articulation of a Public Sector Improvement Framework (to be developed during the first six months of the PSIF’s operation) which will include the development of a series of public sector improvement principles, strategic priorities and a set of funding principles/criteria (including contestability) that will guide how funds available under the PSIF will be directed.

Subsequent RFPs will be prepared every six months in November for a December meeting of the FSC and in May for a June meeting allowing the implementation of the approved program to occur in January and July respectively following FCC endorsement.

### 3.	The RFP Format

The final format for the RFP will be determined by the FMU (with support from the CST ) in consultation with the donors and the FSC – the outline below is designed to provide prospective GoS staff and tenderers with its possible content so that they can assess the potential workload associated with its preparation.

The RFP could contain the following elements:

Exec

Summary

including FSC recommendations

Review of current program
(including any recommended changes to previously approved activities)

Expenditure

Forward Estimates

PSIF Financial Report Summary

Activity 3

Activity 2

Activity 1

IEP

Program

Summary

Activity 3

Activity 2

Activity 1

Core Program Summary

New Proposal 2

New Proposal 2

New Proposal 1

New proposal  1

Forward Plan (including new proposals and financial report)

New Proposal 3

IEP

Program

Summary

including new proposals

New Proposal 3

Core Program Summary

including new proposals

## 3.1	Executive Summary

The executive summary will provide an overview of the proposed program and provide a brief summary of the whole of program performance (ie a consolidation and distillation of reports on Core Program and Immediate and Emerging Priorities activities) and a summary of the new proposals for which approval is being sought.

The Executive Summary will provide an assessment of progress (including expenditure) and identify any changes recommended to currently approved activities drawing to the attention of the FSC the main achievements/failures highlighting any recommendations for change to core programs or the program balance for which the FMU seeks the approval of the FSC and endorsement by the FCC.

## 3.2	Review of current program

For each activity a brief report using a standard reporting format will be created to report on progress of core program and IEP activities currently in implementation or that have been completed in the reporting period.  These will identify any key changes that the FMU is seeking FSC approval and FCC endorsement to implement.

The circumstances that are likely to necessitate re-endorsement and approval are:

- the activity goals and objectives have changed significantly from those previously approved;

- the total budget (after tendering but before contract signing) increases by an amount in excess of X% or more than SAT$X (which ever is the lesser amount) of that previously approved; or

- the managing agency has changed.

Note these circumstances will trigger a request for re-approval at any time in the activity cycle not just at the six-month review point.

## Each individual activity report will comprise the following parts (note much of this information will be taken from the endorsed initial design)

| Activity Title | The title should be consistent with the activity as previously approved by the FSC |
| --- | --- |
| Managing Agency | The GoS Ministry or authority that received the funds to implement the approved activity. |
| Subsidiary Agencies: | Depending on the type of program proposed, there might be other partner organizations that involved. For example an activity may involve more than one Ministry or an activity that has a community consultation component may involve a civil society partner organisation. |
| Activity Goal and Objective(s): | This will be a succinct statement of the goal and objectives that are sought to be achieved through the activity. |
| Timeframe: | This is an estimation of the anticipated total period of activity |
| ## Activity Progress: | Description of progress towards the objectives and goals that have occurred since the last RFP with reference to those articulated and agreed to in the previous six month RFP. This should be supported by a review of project level performance indicators that will have been developed in the detailed design stage. Where significant problems have occurred, the Managing Agency will be required to outline the reasons for this and outline how the proposed changes to the activity are designed to ensure that it is placed back on track. |
| Financial Summary: | A summary of expenditure to date and estimates of future expenditure against the approved budget. Broken down by financial year where relevant. |
| Critical Issue: | Brief analysis of the conditions required for success, including an analysis of the risks and constraints that could be faced and an outline of the contingency plans that the Managing Agency and its contractor (where relevant) will put in place to minimise the impact of these on the achievement of objectives should they eventuate. |
| Cross-sectoral issues: | Where appropriate, the Managing Agency would be required to identify cross-sectoral issues and outline how this activity is addressing these. Issues could include: gender, poverty, environment, corruption, decentralization and other donor activity etc. |
| CEO Endorsement: | The CEO of the Managing Agency will sign the report certifying that it represents a true and accurate account of activity progress and associated expenditure. |

Where an activity has been the subject of a more in-depth review by the Review Group, a report of that review will be submitted alongside that provided by the Managing Agency.

For ease of reference for the FSC, the FMU will draft a summary that lists the activity reports provided and highlights any significant issues such as the need to re-approve major changes to particular activities.

## 3.3  Forward Program

The FMU will put forward copies of all initial designs for FSC approval (refer Annex 6 – Program Determination, Activity Design, Implementation and Review for suggested format).

The FMU will provide a summary of the forward program for each component in the Review and Forward Plan.  These summaries will include an analysis of those proposals appraised by the Review Group (where required) and will make recommendations with regard to the FSC’s determination.

## 3.3.1  Financial Report

The FMU will provide a financial report in three parts:

- A report of expenditure by previous and current financial years to date broken down by approved activity.

- A report of estimated expenditure for the balance of the financial year and for out years broken down by approved and proposed activities (assuming that the approval recommendations being put forward are accepted by the FSC).

- A summary of expenditure and forward estimates together with a recommendation to the FSC as to the amount required from the donors to enable operations to continue over the next 6 months.

## 4.	Approval Process for Immediate and Emerging Priorities activities

Due to their longer term and more strategic nature it is not anticipated that Core Program activities will require urgent approval.  However the flexible and responsive nature of the activities implemented under the Immediate and Emerging Priorities component by their very nature may not always sit well with the 6-monthly RFP cycle.

Where there is a real time imperative the FSC will need to consider how best to approve these when they arise.  The Chair of the FSC may request that the Committee be convened or may wish to seek FSC members written comments/approval by email or correspondence.

In such cases where the FSC has approved an activity out-of-rounds, the Chair (via the FMU as the Secretariat) must submit the activity to FCC members for their endorsement.  Once endorsed, the activity can proceed to implementation in the normal manner.

Annex 8

Position Descriptions

POSITION STATEMENTS

CONTRACTED MANAGEMENT SUPPORT TEAM (AusAID/NZAID FUNDED)

In Australia/New Zealand:

|  | Duration |
| --- | --- |
| Contractor Representative | Part time |
| Administrative Officer | Part time |

In Samoa – Contracted Support Team:

|  | Duration |
| --- | --- |
| Transitional Manager (Team Leader) | 2 years full time, 6 months Yr 3 |
| Transitional Program Officer | 12 months Yr 1, 6 months Yr 2 and 3 months Yr 3 |
| Transitional Administrative and Finance Officer | 4 months in Yr 1, 2 months in Yr 2 |
| HRD Adviser * | 3 months full time (Yr 1) |
| Transitional Review Adviser * | 9 months over Yrs 1 – 3 |

It is expected that the CST advisers will be able to work in a team environment, work closely with PSIF stakeholders, and assume an on the job training role.  Team members are expected to have strong communication and report writing skills.  All team members will be expected to assist the FMU contribute to Facility management documentation and reporting, as directed by the Transitional Manager.

In considering the qualifications and experience being sought for each position, it is recognised that prospective bidders may find it difficult to identify individuals with all the requisite skills for a particular position as described in the attached position descriptions.  Consideration may be given to individuals who do not meet the specified criteria provided that the bidder can demonstrate how all the specified requirements can be met within the team, and personnel grouping (eg. In-Australia/New Zealand and In-Samoa) proposed.

*  The skills identified for the HRD Adviser and Transitional Review Adviser are mandatory and all must be demonstrated by the individual proposed.

FACILITY MANAGEMENT UNIT (GoS FUNDED)

|  | Duration |
| --- | --- |
| FMU Manager | Full time (Yrs 1 – 5) |
| FMU Program Officer | Full time (Yrs 1 – 5) |
| FMU Administrative and Finance Officer | Full time (Yrs 1 – 5) |

REVIEW GROUP (GoS FUNDED)

|  | Duration |
| --- | --- |
| Principal Review Officer | Part time |
| Assistant Review Officer | Part time |

GoS FMU MANAGER

| Position Title | Public Sector Improvement Facility; Facility Management Unit Manager. |
| --- | --- |
| Responsible to | Chief Executive Officer – Ministry of Prime Minister |

Primary Objective

To ensure, based on sound planning and effective management, that the outcomes and associated outputs for the PSIF as set out in the FDD are achieved.

The FMU Manager will be responsible to the CEO of the MPM. S/he will have prime responsibility for the management of the PSIF and will be the principal point of contact between the PSIF CST and donors/GoS in Samoa.  The FMU Manager will ensure that the Facility is effectively directed at supporting GoS policies and the PSIF operates in a manner that targets GoS public sector reform needs in all of its activities and operations. The FMU Manager will have overall responsibility for maintaining effective relationships with CST counterparts, AusAID, NZAID and other key stakeholders, FMU staff supervision and management. S/he will also be responsible for ensuring FMU provision of quality assurance, including comprehensive monitoring and evaluation and quality reporting to the FSC and FCC.  S/he will provide the FCC with strategic, policy and analytical findings and advice about the Facility, its progress toward achieving the higher order objectives and its performance as a whole.

Tasks

- Manage the PSIF to ensure it progresses as a quality and strategic program, on schedule and within the prescribed budget.

- Work in partnership to support the MPM and partner agencies to encourage strategic planning to address service delivery needs, and to identify priority, appropriate activities to be provided under the PSIF.

- Manage the Activity cycle at a Facility level through ensuring key principles, policies and strategies are incorporated, quality documentation is developed, suitable sub-contractors are engaged and properly managed and quality assurance is maintained.

- Monitor, evaluate and adjust the program to ensure objectives are met at a Facility level including development and implementation of the monitoring and evaluation framework, reporting, strategic planning and continuous improvement.

- Keep key stakeholders informed of PSIF status and related issues and involved as appropriate.

- Establish, convene, and support a Facility Steering Committee to monitor and report on the effectiveness and strategic direction of the PSIF and advise the Facility Coordinating Committee on the eligibility, selection, implementation and monitoring and evaluation of Activities.

- Manage Facility planning through directing the preparation of Facility reports and RFPs.

- Develop and implement a program of workshops designed to develop partner agency capacity in activity management, monitoring, evaluation and reporting.

- Lead the development of the Facility Monitoring and Evaluation Framework.

- Establish and operationalise processes and procedures documented in an PSIF Operational Handbook, and ensuring that the Handbook is revised regularly to take account of specific GoS / AusAID / NZAID requirements and remains relevant to all stakeholders.

- Provide secretariat support to FSC and FCC.

- Supervise and manage the FMU staff.

Skills and Experience

- Demonstrated ability to lead and encourage the development of Public Sector Reforms for service quality improvement.

- Demonstrated ability to formulate appropriate services and assess the extent to which those services fulfil identified needs.

- Demonstrated ability to effectively plan for and manage fixed resources especially human and financial.

- Demonstrated ability to plan, organise and evaluate the work of others in order to achieve defined targets/outputs.

- Demonstrated high level English and Samoan written and oral communication skills.

- Demonstrated ability based on at least 8 years of work experience in a relevant management position.

- Minimum qualification of a Bachelors degree from a recognized tertiary institution in a relevant discipline.

GOS FMU PROGRAM OFFICER

| Position Title | Public Sector Improvement Facility; Facility Management Unit Program Officer |
| --- | --- |
| Responsible to | Public Sector Improvement Facility; Facility Management Unit Manager – Ministry of Prime Minister |

The Program Officer will, under the supervision of the FMU Manager, manage the activity planning and management cycle and the disbursement of PSIF Funds.

Tasks:

- Assist in the identification of priority needs within the overall PSIF purpose, and within the agreed focus of Components 1 and 2.

- Assist partner agencies, as required, develop Activity proposals, providing initial proposal appraisals, developing terms of reference and Activity designs, preparing specifications and scope of services for subcontracting purposes.

- Contribute to Facility planning through participation in the preparation of Facility reports and RFPs.

- Contribute to the development of the Facility Monitoring and Evaluation Framework and to the monitoring, evaluating and adjusting the Facility at an Activity level to ensure objectives are met in accordance with agreed policies, principles and strategies, including implementation of the monitoring and evaluation framework at an Activity level, Activity reporting, and quality assurance, integration of lessons learnt and continuous improvement.

- Provide secretariat support to FSC and FCC.

- Contribute to the development and implementation of a program of workshops designed to develop partner agency capacity in activity management, monitoring, evaluation and reporting.

Skills and Experience

- Proven experience in project/contract management and an understanding of project planning, design and appraisal, and technical report writing.

- A thorough understanding of GoS accounts and the preparation of financial reports and budgets.

- Demonstrated ability to effectively plan for and manage fixed resources especially human and financial.

- Experience in the development and management of short term technical assistance contracts.

- Demonstrated high level English and Samoan written and oral communication skills, with the ability to articulate clearly, concisely and logically.

- Highly developed inter-personal skills.

- Minimum qualification of a Bachelor in a relevant area.

GOS FMU ADMINISTRATIVE AND FINANCE OFFICER

| Position Title | Public Sector Improvement Facility; Facility Management Unit Administrative And Finance Officer |
| --- | --- |
| Responsible to | Public Sector Improvement Facility; Facility Management Unit Manager – Ministry of Prime Minister |

The Administrative and Finance Officer will be responsible to the FMU Manager. S/he will have prime responsibility for the efficient administration and systems management of the PSIF.

Tasks

- Ensuring that the FMU office communication and IT systems are operational.

- The development and maintenance of an appropriate records management system for the PSIF.

- The regular revision of the PSIF Operational Handbook to take account of specific GoS / AusAID / NZAID requirements and ensure that it remains relevant to all stakeholders.

- The establishment of the PSIF Fund and develop guidelines for its operation that include: the specification of the type of activities that can be funded, the signatories to the account, the appointment of an independent auditor that will conduct an annual audit of the account, and the specification of financial reports to the Governments showing both expenditure to date, estimated monthly expenditure over the balance of the financial year and indicative commitments in out-years

- Establishment of appropriate financial systems for the running of the FMU, including the maintaining of financial records and procurement procedures.

Skills and Experience

- A thorough knowledge of GoS accounts and the preparation of financial reports and budgets.

- Demonstrated ability to effectively plan for and manage fixed resources especially human and financial.

- Proven accounting work experience at a similar level in a similar organization and position.

- A good understanding of the Public Finance Management Act 2001 and Treasury Instructions.

- Demonstrated ability to operate and work on computer accounting programs as operating within the GoS.

- Demonstrated ability to develop and maintain an appropriate records management system.

- Demonstrated high level English and Samoan written and oral communication skills, with the ability to articulate clearly, concisely and logically.

- Minimum qualification of a Diploma in Accounting or higher from a recognised institution.

CONTRACTOR REPRESENTATIVE

The Contractor Representative will have prime responsibility for ensuring the PSIF is in compliance with the approved :

- Scope of Services and Basis of Payments.

- Planning, financial and management information systems.

- AusAID / NZAID policies and guidelines on gender, poverty, environment, human rights and governance.

The Contractor Representative will undertake:

- High-level liaison with AusAID / NZAID.

- Contract management and executive representation for the Contractor.

- Quality assurance of Facility inputs, outputs and reporting.

- Certification that all Contractor claims for payment are in accordance with approved financial and procurement procedures.

- Direct supervision of the Transitional Manager.

Location

Contractor’s Head Office.

Duration

6 months over 3 years, with an option to extend this subject to the outcome of the Transitional Support Review.

Skills and Experience

- Extensive practical experience in senior contract management with donor funded projects, and a demonstrated capacity to supervise staff, and Quality Assurance reporting.

- Demonstrated understanding of Pacific Island Public Sector Reform processes.

- A cultural understanding and experience of working in a Pacific Island country, preferably Samoa.

- Relevant tertiary qualifications.

- Outstanding written and oral communication skills.

- Highly developed inter-personal skills with an ability to: communicate effectively with others from different social, ethnic and cultural backgrounds; adapt to different cultures; and listen to ideas and concerns of others

CONTRACTOR ADMINISTRATIVE OFFICER

The Administrative Officer will have responsibility for:

- Mobilisation and administration of the Contracted Support Team.

- Mobilisation and management of the Transitional Review Adviser.

- Assist the FMU, where required, with the identification of international sub-contractors to be contracted by managing agencies to provide Component 1 and 2 services.

- Support, where required, approved overseas activities, ie. training.

Location

Contractor’s Head Office.

Duration

10.5 months over 3 years, with an option to extend this subject to the outcome of the Transitional Support Review.

Skills and Experience

- Extensive practical experience in the management and mobilisation of consultants, including sub-contracting issues and financial reporting.

- High level written and oral communication skills.

- Well developed inter-personal skills with an ability to: communicate effectively with others from different social, ethnic and cultural backgrounds.

CONTRACTED SUPPORT TEAM - TRANSITIONAL MANAGER

The CST Transitional Manager will have prime responsibility for the management of CST inputs in Samoa and will be the principal point of contact between the contract support aspects of the PSIF and donors/GoS in Samoa.  The Transitional Manager will play the pivotal role in assisting the FMU implement the PSIF during the period of contracted support to the FMU. S/he will assist the FMU to ensure that the Facility is effectively directed at supporting GoS policies and the PSIF operates in a manner that targets GoS public sector reform needs in all of its activities and operations. The Transitional Manager will have overall responsibility for maintaining effective relationships with Samoan counterparts, AusAID, NZAID and other key stakeholders, CST supervision and management. S/he will also be responsible for assisting the FMU provide quality assurance, including comprehensive monitoring and evaluation and quality reporting to the FSC and FCC.  S/he will assist the FMU provide the FCC with strategic, policy and analytical findings and advice about the Facility, its progress toward achieving the higher order objectives and its performance as a whole.

The Transitional Manager will also have a role in providing direct and / or supervising capacity building assistance to the FMU staff of the key counterpart agency, MPM, and will be required to work in collaboration and partnership with counterpart staff as appropriate to enable them to gain skills, knowledge and experience in managing and monitoring public sector reform activities.

Tasks

- Managing the Contractor’s contractual requirements in the field and leading the CST in Samoa to ensure the PSIF progresses as a quality and strategic program, on schedule and within the prescribed budget.

- Working in partnership to support the MPM and partner agencies to encourage strategic planning to address service delivery needs, and to identify priority, appropriate activities to be provided under the PSIF.

- Assist the FMU in managing the Activity cycle at a Facility level through ensuring key principles, policies and strategies are incorporated, quality documentation is developed, suitable sub-contractors are engaged and effectively managed and quality assurance is maintained.

- Assisting the FMU monitor, evaluate and adjust the program to ensure objectives are met at a Facility level including development and implementation of the monitoring and evaluation framework, reporting, strategic planning and continuous improvement.

- Assisting the FMU keep key stakeholders informed of PSIF status and related issues and involved as appropriate.

- Assisting the FMU in establishing, convening, and supporting a Facility Steering Committee to monitor and report on the effectiveness and strategic direction of the PSIF and assist in advising the Facility Coordinating Committee on the eligibility, selection, implementation and monitoring and evaluation of Activities.

- Directly assisting the FMU, in an Adviser role, to develop skills, knowledge and experience in the planning, management, monitoring and evaluation of public sector reform activities.

- Assist the FMU to manage Facility planning through directing the preparation of Facility reports and RFPs.

- Assist the FMU to develop and implement a program of workshops designed to develop partner agency capacity in activity management, monitoring, evaluation and reporting.

- Assist the FMU to lead the development of the Facility Monitoring and Evaluation Framework.

Location

PSIF (FMU) Office in Samoa.

Duration

2 years full time, 6 months Yr 3, with an with an option to extend this subject to the outcome of the Transitional Support Review.

Skills and Experience

- Qualifications in a relevant field.

- Experience in managing programs including: strategic management and administration; team supervision and leadership; monitoring and evaluation, and report writing; and demonstrated sound judgement in decision making.

- Demonstrated experience in public sector reform in a whole-of-government context, organisational development, and mentoring senior managers through organisational change; preferably in a Pacific Island country .

- A cultural understanding and experience of working in a Pacific Island country, preferably Samoa.

- Extensive experience in training and personnel development and team building skills.

- Demonstrated experience in policy development and strategic overview of policy.

- Outstanding written and oral communication skills.

- Highly developed inter-personal skills with an ability to: communicate effectively with others from different social, ethnic and cultural backgrounds; adapt to different cultures; and listen to ideas and concerns of others.

TRANSITIONAL PROGRAM OFFICER

The Transitional Program Officer will, under the supervision of the Transitional Program Manager, assist the FMU manage the activity planning and management cycle and the disbursement of PSIF Funds.  The Transitional Program Officer will:

- Assist the FMU to identify needs within the overall PSIF purpose, and within the agreed focus of Components 1 and 2.

- Support the FMU as required to assist partner agencies develop Activity proposals, providing initial proposal appraisals, developing terms of reference and Activity designs, preparing specifications and scope of services for subcontracting purposes.

- Assist the FMU Programme Officer contribute to Facility planning through participation in the preparation of Facility reports and RFPs.

- Contribute to the development of the Facility Monitoring and Evaluation Framework and to the monitoring, evaluating and adjusting the Facility at an Activity level to ensure objectives are met in accordance with agreed policies, principles and strategies, including implementation of the monitoring and evaluation framework at an Activity level, Activity reporting, and quality assurance, integration of lessons learnt and continuous improvement.

- Assist the FMU Programme Officer to provide secretariat support to FSC and FCC.

- Under the direction of the Transitional Manager, directly assist the FMU Programme Officer, in an Adviser role, to develop skills, knowledge and experience in the planning, management, monitoring and evaluation of public sector reform activities in Samoa.

- Assist the FMU Programme Officer to develop and implement a program of workshops designed to develop partner agency capacity in activity management, monitoring, evaluation and reporting.

Location

PSIF (FMU) Office in Samoa.

Duration

12 months in Yr 1, 6 months in Yr 2, 3 months Yr 3, with an with an option to extend this subject to the outcome of the Transitional Support Review.

Skills and Experience

- Qualifications in a relevant field.

- Experience in training, personnel development, mentoring and team building skills.

- Experience in public sector and organisational development and change, preferably in a Pacific Island country.

- Proven experience in project/contract management, project planning, design and appraisal, and technical report writing.

- Experience in the development and management of short term technical assistance contracts.

- Highly developed inter-personal skills with an ability to: communicate effectively with others from different social, ethnic and cultural backgrounds; adapt to different cultures; and listen to ideas and concerns of others.

- Outstanding written and oral communication skills.

Transitional Administrative and Finance Officer

In consultation with the Transitional Manager, the Transitional Administrative and Finance Officer will have prime responsibility for:

- Assist the FMU Administrative and Finance Officer as required to ensure that the FMU office communication and IT systems are operational.

- Assist the FMU Administrative and Finance Officer as required to develop and maintain an appropriate records management system for the PSIF.

- Assist the FMU Administrative and Finance Officer as required to develop an appropriate Procedures Manual, which sets out operational, financial and administrative protocols, and ensuring that the Procedures Manual is revised regularly to take account of specific GoS / AusAID / NZAID requirements and remains relevant to all stakeholders.

- Assist the FMU Administrative and Finance Officer as required in the establishment of the PSI FUND and develop guidelines for its operation that include: the specification of the type of activities that can be funded, the signatories to the account, the appointment of an independent auditor that will conduct an annual audit of the account, and the specification of financial reports to the Governments showing both expenditure to date, estimated monthly expenditure over the balance of the financial year and indicative commitments in out-years

- Assist the FMU Administrative and Finance Officer as required establishment of appropriate financial systems for the running of the FMU, including the maintaining of financial records and procurement procedures.

- Under the direction of the Transitional Manager, directly assist the FMU, in an Adviser role, to develop skills, knowledge and experience in administration and financial management and monitoring.

Location

PSIF (FMU) Office in Samoa.

Duration

Four months in Year 1, two months in Year 2, with an with an option to extend this subject to the outcome of the Transitional Support Review.

Skills and Experience

- Demonstrated financial and accounting skills.

- Demonstrated experience in project/contract management of donor funded programs and understanding of AusAID/NZAID procurement requirements.

- Highly developed inter-personal skills with an ability to: communicate effectively with others from different social, ethnic and cultural backgrounds; adapt to different cultures; and listen to ideas and concerns of others.

- Outstanding written and oral communication skills.

TRANSITIONAL REVIEW ADVISER

The Transitional Review Adviser will assist the GoS RG leader coordinate the activities of the Review Group during the period of transitional support and be responsible for:

- Assisting the RG to develop activity appraisal and review guidelines.

- Assist the FMU Manager to develop the Facility Monitoring and Evaluation Framework, and provide appropriate assistance and skills transfer to ensure that the implementation of this Framework can be undertaken by GoS FMU staff.

- Providing a program of structured support to the RG staff to provide them with the necessary skills to undertake the full range of appraisal and review responsibilities over a period of two years followed by a period of advisory assistance, review and reinforcement in Year 3.

- Provide ongoing and intensive mentoring of the staff of the RG.

In order to minimise potential conflicts of interest, the TRA will not be an employee of the managing contractor.

Location

Home country with regular (1 month per year) trips to Samoa.

Duration

Nine months over Years 1 – 3 with an with an option to extend this subject to the outcome of the Transitional Support Review.

Skills and Experience

- Relevant qualifications and extensive practical experience in appraisal, monitoring and evaluation of donor-funded programs/projects.

- Experience in project design, including development of monitoring and evaluation frameworks and performance indicators.

- Extensive practical experience in public sector reform and change management, preferably in a Pacific Island country.

- Demonstrated experience in policy development and strategic overview of policy.

- Experience in training, personnel development, mentoring and team building skills.

- Outstanding written and oral communication skills.

- Highly developed inter-personal skills with an ability to: communicate effectively with others from different social, ethnic and cultural backgrounds; adapt to different cultures; and listen to ideas and concerns of others.

HUMAN RESOURCE DEVELOPMENT ADVISER

The HRD Adviser will work with the CST Transitional Manager to:

- Conduct a baseline evaluation of FMU staff capacity and competencies and systems capacity assessment of the MPM, and of the PSIF Review Group located within the MoF.

- Develop an in-house HRD and systems development plan, to be delivered by the CST and to include opportunities for formal and informal training, to develop the skills of the FMU staff, with the ultimate aim of a fully GoS-managed FMU and PSIF by the end of Year 3.

- Develop a monitoring and reporting system that provides progressive assessment and evaluation of capacity building and training activities within the FMU and RG.

- Undertake, in Year 2, a follow up input to evaluate progress of skills and systems development and to provide refresher skill development to staff as required.

Location

PSIF (FMU) Office in Samoa.

Duration

Two months in Year 1, one month in Year 2.

Skills and Experience

- Relevant skills and qualifications in personnel and change management.

- Extensive experience in the planning, management, promotion and implementation of public sector human resource development activities.

- Understanding of contemporary issues and approaches in training and development particularly within the public sector.

- Experience in preparing workplans and conducting reviews of functional areas to determine training and management needs.

- Highly developed inter-personal skills with an ability to: communicate effectively with others from different social, ethnic and cultural backgrounds; adapt to different cultures; and listen to ideas and concerns of others.

Annex 9

Risk Matrix

Risk Matrix

Likelihood - Almost Certain: 5, Likely: 4, Possible: 3, Unlikely: 2, Rare: 1;  Severity - Severe: 5, Major: 4, Moderate: 3, Minor: 2, Negligible: 1

| No. | Source of Risk | Risk Event | Impact on Project | Likelihood | Severity | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | GoS | Change of government or government policy | Reform agenda changes making sections of the program irrelevant. | 2 | 4 | Act upon NZAID/AusAID Post advice. Monitor environment; maintain high level communications with senior GoS officials. Constructively respond to changed programming environment through the FCC and at HLDs. | GoS/NZAID/AusAID |
| 2 | GoS | Lack of commitment to reform by Ministries / CEOs | Lack of commitment and interest in PSIF. PSIF funds underutilised. Stronger Ministries dominate applications. | 3 | 4 | Ensure FMU remains proactive; maintain relevance of core program components to overall reform agenda. Require counterpart agency to make a substantive resource contribution to the approved activity. | GoS/FMU/ Contracted Support Team (CST) |
| 3 | GoS | Lack of absorptive capacity within and between Ministries for further reform | Stronger Ministries capture funds. Activities do not achieve design objectives. | 3 | 4 | Ensure FMU proactive in responding with appropriate levels of support to identified capacity weaknesses. | FMU/CST/ GoS |
| 4 | GoS | Reform changes not sustainable | Reform requires greater inputs than available under PSIF. PSIF needs to revisit issues addressed during ISPs. | 3 | 4 | ISP impacts monitored; close liaison with other aspects of NZAID/AusAID program. NZAID/AusAID review level or funding provided to PSIF. | GoS/NZAID/AusAID |
| 5 | GoS | Administrative, financial and legal reform disjunctive | Gap between agencies further widened. Stronger Ministries capture funds. PSIF dominated by economic reform activities. | 3 | 3 | Close liaison with possible ISP in Attorney General’s Office and Audit Office. Close program monitoring by FSC and FCC. Ensure FMU remains proactive. FMU placed with in MPM to maximise potential for PSIF to respond to whole of government reform agenda. | GOS- MoF/ Attorney General |
| 6 | GoS | PSIF becomes the arena for addressing Ministry rivalries/tensions | Integrity of PSIF undermined. FSC becomes dysfunctional and activities not supported. | 3 | 4 | Rigorous FCC attention to program direction. FMU placed in appropriate agency. | FCC/GoS |
| 7 | GoS | Loss/high turnover of FMU and RG counterparts | Program delay. Sustainability made more difficult. Withdrawal of CST support delayed. | 3 | 3 | At least two GoS staff in each unit familiarised with tasks of FMU/RG. Clear and concise and well documented procedures that assist replacement staff to become effective quickly. | GoS /FMU/CST |
| 8 | GoS | MPM not the appropriate agency in which to locate the FMU | Facility operations ineffective and inefficient. | 3 | 4 | Stop-Go Review at the end of Year 1. | GoS/GoA/GoNZ |
| 9 | Project | Expectations regarding the PSIF are unclear | PSIF lacks strategic focus with CST/FMU counterparts focused on processes rather than outcomes. Impact of PSIF too dissipated. Lack of interest in PSIF from Ministries. Administrative costs increase because of having to support too many disparate activities. Lack of vigilance by FMU in adhering to agreed strategic parameters. | 2 | 4 | Clear Purpose and Goal included in PSIF Communications Strategy. Strategic Review and Planning Activity proposed to guide the development of an appropriate strategic focus. MEF considers outcomes at project and overall Facility level. FSC/FCC review rigorously the RFPs and insist on adherence to approved strategic focus. | FCC/FSC/ FMU |
| 10 | Project | Facility is underutilised | PSIF loses momentum. Opportunities lost. Little chance other donors will be interested in supporting PSIF. | 2 | 4 | FMU actively promotes PSIF and provides support to agencies wishing to apply for support for activities. Build on initial processes for progressive engagement; program scaled up or down annually on the basis of demand. Annual program monitoring ensures program remains flexible and responsive | FMU/FSC/ FCC/GoS |
| 11 | Project | PSIF not seen as appropriate to needs of Ministries. | Underutilisation of funds. Overall reform stalled. Facility goal / purpose not achieved. | 2 | 4 | PSIF owned, supported and promoted by GoS. FMU proactive in activity with CEOs. Communication strategy developed to encourage appropriate access early in program. | GoS/FMU/ CST |
| 12 | Project | Facility processes lose cultural identity | Program fails to support and strengthen the partnership between government and local communities. | 2 | 3 | Active and rigorous FSC involvement that includes appropriate community representation FMU pays attention to appropriate cultural processes; Monitoring focuses on how the program supports and strengthens the partnership between government and local communities | FSC/FCC/ FMU |
| 13 | Project | Funds captured by stronger agencies | PSIF does not support priorities of whole of government reform program. Gap between agencies widened. Facility goal/purpose not achieved. | 3 | 4 | FMU proactive in promoting PSIF among all Ministries and provides support to weaker agencies wishing to apply for support. FSC maintain overview of program decisions. Rigorous monitoring of PSIF direction by FCC. | FMU/FSC/ FCC |
| 14 | Project | FMU does not value/utilise adviser support | Loss of support for Facility. Under utilised support capability. Withdrawal of CST support delayed. | 2 | 4 | Contractor identify GoS/FMU expectations and manage as needed. Relevant capacity building/training is designed. Rigorous adviser selection to ensure appropriate levels of cultural awareness and necessary skills transfer and mentoring skills. Adviser and counterpart performance appraisals conducted and feedback implemented. Monitoring of host agency to ensure ongoing support for PSIF and move FMU to another host agency if support not maintained. | AusAID/ NZAID GoS Contractor |
| 15 | GoS | GoS Funding commitment to FMU and RG positions not made or not sustained | PSIF implementation stalled. Benefits not realised in an acceptable timeframe. Withdrawal of CST support delayed. | 3 | 4 | Close and regular liaison between MoF and donors. Active oversight of PSIF operations by FCC. | GoS/AusAID/NZAID |
| 16 | Project | Incorrect balance between cost of activities and value of outcomes. | Excessive controls; few activities supported. Challenges to activity viability. Sub-optimal value for money proposition from donor’s perspective. | 3 | 4 | Affordable Adviser costs achieved. Sound project management maintained. Good quality proposal evaluations undertaken by FMU and RG. Tight risk, quality and performance management systems and processes implemented as specified. Active oversight of PSIF operations by FSC and FCC | AusAID/ NZAID FMU/FSC/FCC |
| 17 | Project | Pressure by GoS to accommodate new components into Facility post-commencement. | Loss of support and ownership by GoS if not accommodated. Line Ministries become disaffected and lose interest in program. Facility impact becomes too diffuse. | 3 | 3 | Clearly agreed strategic focus from the outset; stakeholder expectations managed by FMU. 6-monthly RFP process provides for systematic consideration of changes to focus. Sound governance and project management rigour applied. | GoS/FCC |
| 18 | Project Management | Imbalance between need for representation and competence on FSC | Inappropriate decisions made regarding support for projects/activities. FMU drives program rather than FSC. | 3 | 3 | FSC members appointed according to skills and ability rather than agency membership/employment alone. Active FCC oversight of approved program. | GoS / FMU |
| 19 | Project Management | Too great a proportion of funds spent on external TA activities. | Few projects supported. Facility goal/purpose not achieved. | 2 | 4 | FMU supports agencies in designing appropriate activities and rigorously applies value for money principles in making recommendations to the FSC. FSC monitors fund allocations closely to ensure TA justified appropriately in designs. FCC monitors program direction. Issues discussed at annual HLD’s and/or bilateral discussions | FMU-CST/FSC/FCC |
| 20 | Project Management | Burden of reporting too high | Lack of interest from CEOs. PSIF underutilised. Facility goal/purpose not achieved. | 2 | 3 | Reporting requirements ensure that they are justifiable in terms of the program resources invested and of the capacity of agencies to respond properly. Wherever possible requirements follow standard GoS reporting requirements. Close attention paid by FCC members when approving operational guidelines to ensure reporting is pitched at an appropriate level. | FCC/CST-FMU |
| 21 | Project Management | FCC is dysfunctional or becomes a rubber stamp | PSIF loses direction. | 2 | 4 | FCC membership appointed at appropriate level. FCC rigorous in monitoring program direction. | FCC |
| 22 | Project Management | PSIF becomes administratively complex | Lack of interest from CEOs. PSIF underutilised. Facility goal / purpose not achieved. | 3 | 4 | Stakeholders actively avoid micro-management. Administrative imposts always assessed in terms of the value they add to overall quality of supported program. Administration follows standard GoS requirements as far as possible. Close attention paid by FCC members when approving operational guidelines to ensure procedures are pitched at an appropriate level. | Posts/FMU-CST |
| 23 | Project Management | Over time, the power of the FMU could undermine the ability of the FSC to make impartial decisions | Program fails to support GoS reform priorities. Facility goal / purpose not achieved. | 3 | 5 | RG rigorous in assessments. FCC monitors PSIF direction carefully. | RG/FCC |
| 24 | Project Management | Fast tracking of immediate and emerging priorities used to bypass normal approval mechanism. | PSIF captured by one group of agencies Core program starved of funds. GoS priorities not met. Facility goal/purpose not achieved. | 3 | 4 | FSC decides on criteria and decisions making processes for fast tracked proposals. FSC sets proportion of funds to be used for IEP. FCC monitors direction of the Fund. Approved operational guidelines specify clearly the limits to IEP approval. | FMU/ FSC/FCC |
| 25 | Project Management | Adviser performance inadequate | Inadequate capacity development of GoS FMU and RG staff. PSIF underutilised. Project cost over- runs. Loss of support for PSIF. Inappropriate proposals presented to the FSC. | 2 | 4 | Rigorous Adviser selection processes applied. Formal progress and performance reviews conducted. Role clarity achieved through direct discussions. Adviser appraisals conducted and feedback acted upon. FCC oversight. | Contractor/ FCC/FSC |
| 26 | NZAID/ AusAID | Lack of harmonisation between AusAID/NZAID policy and/or facility management processes | PSIF lacks clarity of purpose and/or ability to function effectively due to disjunction of donor requirements. GoS loses interest in and commitment to PSIF. | 2 | 5 | PSIF does not commence until joint NZAID/AusAID processes agreed. Regular and cooperative contacts maintained between posts and desks. Residual issues addressed during HLDs | AusAID/ NZAID |
| 27 | NZAID/ AusAID | Posts lack the capacity to manage the program effectively | Inappropriate intervention from Posts diverts the work of the PSIF. | 3 | 5 | Capitals monitor Post actions and provide support where necessary. Agreed management roles established. | AusAID/ NZAID |
| 28 | External | Duplication of activity with other aid donors | Confusion within PSIF and among CEOs. Potential for misalignment of priorities. Wasted program funds. Momentum of PSIF jeopardised. | 2 | 3 | Ongoing environmental scanning conducted. Liaison with AusAID/NZAID Post maintained. Liaison with other donors maintained. Facility coordinates work with MoF. RG seeks to remain actively informed of other donor programs so that their clearance of proposals remains informed. | GoS/ NZAID/ AusAID |
| 29 | GoS | Facility Fund monies misappropriated | Ability to fund activities reduced. Donor-GoS relations damaged. | 3 | 5 | Annual independent financial audits undertaken. Transparent guidelines for Fund operation developed and approved by all stakeholders. Financial management systems developed and approved by all stakeholders. | GoS/FMU-CST/ donors |

Annex 10

References

# References

- Asia Development Bank country Strategy and Program Update: 2004-2006 July 2003

- Asia Development Bank Technical Assistance to the Independent State of Samoa for Strengthening of Economic Sectors Planning and Management October 2002

- Asia Development Bank TA Completion Report: Strengthening Capacity for Macroeconomic Analysis, Planning and Policy Formulation (Phase IV)  August 2002

- AusAID / Government of Samoa, Review of Institutional Strengthening Projects in Samoa Final Report May 2003.

- AusAid Capacity Building for Effective Governance (CEG): Mid-term Review Draft.  3 November 2003.

- Government of Samoa 2004/2005 Budget Address; By Hon Misa Telefoni; May 31, 2004 accessed at http://www.mof.gov.ws/publish/ba0405_eng.shtml on 21/06/04

- Government of Samoa Sectoral Planning Manual: Treasury Department, Economic Planning and Policy Division March 2000.

- Government of Samoa Sectoral Planning Guide: Samoa Ministry of Finance June 2003.

- Government of Samoa Tenders Board (2003) Guidelines for Government Procurement by Public Tender Treasury Department February, 2003.

- Monetary Policy Statement 2002/2003 World Economy in 2002/2003 Monetary Statement 2002/2003 accessed on 16 Feb 04 at http://www.cbs.gov.ws/monpol/statement/02-03/domestco-2-03.htm

- Samoa in Pacific Magazine January 2004.

- Samoa- Australia- New Zealand High Level Discussion on Development Cooperation, Apia 10 February 2004 Record of outcomes.

- Samoa Public Service Commission (2003) Strategy for the Professional Development in the Samoa Public Service 2003-2008.

- Australian Aid – Investing in Growth, Stability and Prosperity – 11th Ministerial Statement to Parliament on Development Cooperation Program, September 2002.

Annex 11

PSIF Relationship to other Projects

Relationship to Other Projects / Funding Mechanisms

AusAID and NZAID are Samoa’s major development assistance donors. Currently each donor funds a number of bilateral and regional programs and projects relevant to the operation of the PSIF however agreement has been reached between the three governments that AusAID and NZAID will develop a joint 2005 – 07 country strategy to Samoa, and will pursue opportunities to jointly fund initiatives. Close cooperation and coordination with other donors, such as the Asia Development Bank (ADB), is also maintained.

1. NZAID Bilateral Programs

The current NZAID Strategy for the Development of Samoa identifies as priorities:

- Economic development

- Education

- Health

- Private sector development

- Strengthening social structures

- Agriculture

- Tourism and infrastructure

- Public sector development

2. AusAID Bilateral Programs

The main thrust of the Australian aid program to Samoa is to help the government to implement key elements of its economic and public sector reform strategy and move towards economic independence. In the medium term, Australian aid aims to:

- support the Government of Samoa implement the economic policy reform, public service reform and human resource development thrusts of the Strategy for the Development of Samoa

- strengthen the management of natural resources.

- improve the quality of basic services, with a particular focus on education and health,

A number of ongoing ISPs are supported in pursuit of these aims.

Police Project

This new program of assistance commenced early 2004 to help strengthen and modernise the Police Service. It is scheduled for completion in 2008.

Immigration Project

The project is due for completion in 2005 and aims at strengthening the Immigration Division of the Ministry of the Prime Minister to enable it to deliver more transparent and accountable passport, citizenship, entry and exit administration that is customer focused.

Health Project

Due for completion in 2005, this project is strengthening the management and operational capacity of the Department of Health to improve the health of the Samoan population.

Ministry of Agriculture Fisheries, Forestries and Meteorology

The project has helped to identify how the ministry can realign its organisational and management systems and procedures and adjust to the reform process; it is due for completion in 2005.

3. Joint Programs

New Zealand and Australia jointly fund an In-Country Training Program with the PSC as the implementing agency. The program provides overseas based expertise to design and deliver in-country competency based training and development in priority areas for the public, private and NGO sectors. Courses are focused on practical skills in areas not available locally.

Based on its consultations, the Team recommends this program remain unaffected by the PSIF as it provides assistance complementary to the proposed PSIF.  Representatives consulted from both the private sector and NGO expressed some concern that the program would be lost if the PSIF was implemented.

4. Regional Projects

Both countries also support a number of regional programs related to the proposed PSIF.

## The NZAID Regional Good Governance program provides funding for projects that promote good governance at regional, national and local levels. These projects focus on capacity building activities that contribute to enhancing the quality of government and civil society. Grants of between $3,000 and $50,000 are available to New Zealand or developing country organisations or individuals, as well as international or regional agencies. In the Pacific region the Good Governance Program supports a broad range of activities including public sector reform, state and private sector training on corporate governance and assisting in the ratification and implementation of international human rights treaties.

The AusAid Pacific Technical Assistance Facility supports the secondment of Australian expertise to the Pacific region, generally for two-year capacity-building assignments. In 2002-03 there were six Australian experts working in government departments in Samoa - a parliamentary counsel to the Attorney-General; a structural engineer, design engineer and quantity surveyor with the Public Works Department; an investment specialist with the National Provident Fund; and a financial accounting adviser to the Treasury.

The proposed AusAID Global Government Sector Linkages Program will provide a centralised and consistent system for managing linkages funding for developmental activities of federal and state/territory departments and agencies and universities.  The Global GSLP will respond to the requirement that government relationships be managed directly by AusAID, rather than by a contractor.

The GSLP will be a management resource available to support desk-led program engagement with peer agencies and broader government interests. Programs would contribute activity funding, retain responsibility for setting country/program specific criteria arising from Cabinet, Ministerial and Executive decisions, or based on agreed strategies with partner countries, and participate in the selection and decision making process, with involvement from key agencies.  A GSLP secretariat will provide facility support by managing the process of advertising rounds, facilitating proposals, preparing documentation for the selection process, drafting ROUs, arranging design support and supporting activity management and monitoring.

(i)   Objective and key principles

The primary objective of the Global GSLP mechanism will be to improve public sector capacity in developing countries, by building links and enabling the transfer of skills and expertise from Australian federal, state and territory government agencies, as well as universities.   The Global GSLP will support AusAID’s role in facilitating partnerships within and across governments

Activity Types -- Activities will be delivered primarily in the form of technical assistance and training (workshops, courses, on-the-job training, staff attachments or exchanges) in sectors targetted by program strategies. The applicant agency’s track record and demonstrated capacity to manage will be important factors influencing the considerations of each user program’s Inter-Departmental Assessment Panel in relation to the scale, duration and complexity of proposed activities and the extent of design support they attract.  Eligible activities will be able to range from small, relatively simple one-year proposals of less than $100,000 up to more complex multi-year proposals costed in excess of $250,000 (conceivably these could be multi-million dollar proposals).

Activity Selection – Each user program will have an Inter-Departmental Assessment Panel (IDAP) to assess proposals on the basis of guidelines and selection criteria that give preference to proposals that reflect core and country specific criteria.

If funding is provided through other means there will be no compulsion to use the GSLP  i.e. the PSIF facility can deal directly with a government agency.

NZAID does not have a similar mechanism, so government linkages can either be developed directly between GoS and GoNZ agencies or via the CST as a broker.

## 5. Asian Development Bank

## Since 1999 the ADB has supported a five year program to strengthen the capacity of the MoF for macroeconomic analysis, policy formulation and planning in order to provide timely expert economic and financial advice to the senior most government officials in related areas.

## The 2003-2006 strategy of the ADB for Samoa supports the SDS and aims to

## improve the enabling environment for accelerated private sector growth and job creation

## to enhance access to, and delivery of, basic social services by providing infrastructure and enhancing management and performance of relevant public sector institutions.

## Continue to help the GoS improve living standards and reduce income disparity through improved equity and access to quality education for all Samoans.

ISP Review Report, May 2003, Executive Summary, page ii.

Despite the full impact of cyclone Heta not yet being apparent, the response required a re-allocation of budgetary resources to meet the cost of damaged physical infrastructure such as roads and seawalls, whilst at the same time focusing on urgent resumption of vital services as in water, electricity and telecommunications. The other major concern was the adverse impact of the cyclone on the agricultural sector. The damage to agricultural produce such as taro, bananas, breadfruit and vegetables became apparent through the rise in prices from the demand for these goods which were still in short supply mid year. It is anticipated however that prices will decline as output recovers to cope with demand over the next few months.

GoS Manual on Project Planning and Programming,  p. 2.13

According to the 2001 census, Samoa is made up of 340 villages.

GoS Strategy for the Development of Samoa 2002 – 04.

Although the Sectoral Planning Manual: Samoa identifies 10 sectors, the infrastructure sector is broken into three specific sectors (construction, electricity and water) and communications and financial services are treated as separate sectors from trade and commerce - resulting in 14 sectors.

GoS March 2000.

ADB, October 2002

ibid.

Australian Aid – Investing in Growth, Stability and Prosperity – 11th Ministerial Statement to Parliament on Development Cooperation Program, September 2002, p. 50.

Towards a Strategy for the Pacific Islands Region. NZAID July 2002. p11, accessible at http://www.nzaid.govt.nz/library/docs/nzaid-pacific-islands-region-strategy.pdf

AusAID, ibid, p. 50.

Samoa Governance Facility, Terms of Reference – Design, p.5.

A pre-mobilisation activity of this nature was specifically requested by GoS at the Design Mission debrief with GoS in Apia on 25 February.

Samoa Governance Facility, Terms of Reference – Design, p.5.

ADB, October 2002, pg 2.

It is not clear that staff within this agency currently have this capacity or role, as is the case within the appropriate part of MoF.

Note the term ‘managing agency’ refers to the Samoan public sector agency that submitted the initial proposal for support.