Public Sector Improvement Facility 6-Monthly Work Plan (Jul – Dec 2010)

(1st January 2011)

PSIF GOVERNANCE

| Item Ref | Activity | Ministry/Agency | Description | Value | Dates (Duration) |
| --- | --- | --- | --- | --- | --- |
| 1 | Facility Coordinating Committee | Facility Management Unit | Provide secretariat support to the FCC – prepare & distribute agenda, hold meetings, prepare & distribute minutes |  | Jul – Dec 10 |
| Comment: FCC meetings usually held after each FSC meeting. As a result of the re-design of the PSIF the FSC is now meeting every 2 months; anticipate 3 FCC meetings between now and the end of the financial year 2011/11 |  |  |  |  |  |
| 2 | Facility Steering Committee | Facility Management Unit | Provide secretariat support to the FSC – prepare & distribute agenda, hold meetings, prepare & distribute minutes |  | Jul – Dec 10 |
| Comment: FSC meetings now held every two months; remaining meetings for this Financial Year FY 10/11 scheduled for Mar and May (dates to be confirmed) |  |  |  |  |  |
| 3 | Special Purpose Account | Facility Management Unit | On-going oversight of PSIF Special Purpose Account (payments, financial statements etc) |  | Jul – Dec 10 |
| Comment: Audit Report for FY 09/10 received from Audit Office, Dec 10; |  |  |  |  |  |
| 4 | Financial Statements; Review & Forward Plan | Facility Management Unit | Financial Reports and Review & Forward Plan to be presented to FCC & FSC every quarter |  | Jul – Dec 10 |
| Comment: The Review and Forward Plan for the ¾ of the Financial Year 2010/11 prepared; to be discussed at FSC meeting scheduled for 31st Jan 11; |  |  |  |  |  |

| 5 | Monitoring & Evaluation Framework | Facility Management Unit |  |  | Jul 10 – Jun 11 |
| --- | --- | --- | --- | --- | --- |
| Comment: 2008 M&E Framework to be revised/updated; the FCC has instructed the FMU to proceed with the recruitment of a short term M&E Adviser to be based with the FMU to strengthen M&E role. TORs & costings prepared, awaiting FSC endorsement |  |  |  |  |  |

PSIF PROJECTS (Activities)

| Item Ref | Activity | Ministry/Agency | Description | Value | Dates (Duration) |
| --- | --- | --- | --- | --- | --- |
| 6 | Institutional Strengthening Project | Samoa Audit Office (SAO) |  | $4,800,000 over 2.5 years | Sep 08 – Jan 11 |
| Comment: 1/1/11 – All remaining deliverables by Managing Contractor completed, though some are still pending Audit Office endorsement before claims for payment can be submitted; original completion date was Dec 10; FSC approved an extension to early 2011 to allow SAO to complete the remaining study tour to Wellington, New Zealand; FMU finalizing TORs for Independent Completion Report; a suitable Adviser to be contracted early 2011; Recommendation: (1) FSC approve the TOR for the Independent Completion Report of the SAO ISP; |  |  |  |  |  |
| 7 | Institutional Strengthening Project | Samoa Bureau of Statistics (SBS) | Strengthen capacity of SBS to provide high quality statistics to enable the private/public sectors in Samoa to formulate evidence based policies to undertake economic, social and business planning | $6,700,000 over 3 years |  |
| Comment: 1/1/11 – Cabinet has approved the appointment of VINSTAR as managing contractor for SBS ISP; SBS still in the process of finalizing the Contract with VINSTAR; SBA has started work on the National Statistics Development Plan – an advocacy program put in place to support this. FCC still has concerns re SBS ability to commit to the ISP given major activities in the SBS work plan, the most notable amongst these being the 2011 Census; SBS were asked to provide an update re the National Statistics Development Plan, there’s been no response to date. Recommendation: (1) FSC note progress of project; (2) FMU follow up with SBS re an update on the national Statistics Development Plan |  |  |  |  |  |

| 8 | Project Management Training for the Samoa Public Sector | Ministry of the Prime Minister & Cabinet (MPMC) | Develop practical project management expertise in the public sector | $1,874,000 over 3 years | Sep 08 – Dec 11 |
| --- | --- | --- | --- | --- | --- |
| Comment: 1/1/11 – Delivery of Intake II completed Dec 10; David Kay Training Development conducted a monitoring & evaluation visit in Dec 10; recruitment process for applicants for Intake III has started’ closing date for applications – 4th Feb 11; Recommendation: (1) FSC to note the progress of this project |  |  |  |  |  |
| 9 | Human Resource Database for the Government of Samoa | Public Service Commission (PSC) | Provide reliable information on employee performance, recruitment & capacity building to strengthen policy advice & decision making on HR matters | $1,500,000 over 2 years | Mar 08 – Jun 11 |
| Comment: 1/1/11 – Recommendation: (1) FSC note the progress of this project |  |  |  |  |  |
| 10 | Labour Law Reform | Ministry of Commerce, Industry & Labour (MCIL) | Revise labour laws to comply with ILO standards & conventions and strengthen MCIL’s capacity to address labour issues & relations | $250,000 | Jul 09 – Mar 11 |
| Comment: 1/1/11 – The Final date for completion of all activities remains the 31st Mar 11 after which all funding will cease. Project Management Committee meeting on 21 Jan 11 to discuss status of work undertaken. Recommendation: (1) The FSC note the progress of this project |  |  |  |  |  |
| 11 | Situational Analysis & Project Design Document | Public Trust Office (PTO) | Undertake a comprehensive situational analysis of PTO with recommendations for strengthening in a project design document (PDD) for an ISP | $180,000 |  |

| Comment: 1/1/1 – PTO has advised the Senior Legal Advisor approved under PACTAM is not able to undertake the situational analysis of the PTO; FMU has prepared revised TORs for an organisational development specialist to undertake the situational analysis; waiting for PTO to comment. Recommendation: (1) The FMU write to the PTO to see whether or not they want to pursue this activity or not |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 12 | Samoa Airport Authority Act Review | Samoa Airport Authority (SAA) | Review & draft amendments to the Samoa Airport Authority Act | $145,000 | Jun 09 – Dec 10 |
| Comment: 1/1/11 – public awareness on the Amended Act carried out in Dec 10 for both Upolu and Savaii; SAA inquired into the possibility of utilizing savings from the project to assist with the translation and publication of the new Act; SAA advised to submit an official request to FSC for consideration; otherwise the revised completion date (end of Jan 11) remains in effect. Recommendation: (1) FSC note the current status of this project |  |  |  |  |  |
| 13 | Public Finance Management Reform Program | Ministry of Finance (MOF) | Strengthen public finance management systems, improve transparency in accounting for public funds | $2,530,000 | Mar 09 – Jun 11 |
| Comment: 31/10/10 – PFMR Reform Annual Review Meeting held 13/12/10; included a presentation to all donor partners ( a copy of the Executive Summary from the Progress Report Nov 2009 – Dec 10 is attached as Annex 2); good progress continues to be made, Recommendation: (1) FSC note the progress of project |  |  |  |  |  |
| 14 | Improving Policy Development & Coordination Reform Program | Ministry of the Prime Minister & Cabinet (MPMC) | Strengthen capacity of MPMC to carry out core function of providing support to PM & Cabinet re whole-of-govt policy coordination & advice | $8,000,000 | Sep 09 – Dec 12 |
| Comment: 1/1/11 – key changes to Cabinet processes and policy role of MPMC developed, project steering committee (AG, MOF, PSC, MFA) met for the first time on 27 Aug 10 – provided with an update of project progress and opportunity to comment on new Cabinet processes and the Ministry’s Corporate Plan; FMU & VINSTAR have agreed on Milestones for Year II, AG’s Office have prepared Addendum. Procurement process underway to contract a Provider for the Document Management System (Cabinet) Recommendation: (1) FSC to note the progress of project |  |  |  |  |  |

| 15 | Institutional Strengthening Project (Phase I) | Ministry for Revenue | To improve the efficiency and effectiveness of tax administration | $3,635,000 | Nov 10 – Dec 13 |
| --- | --- | --- | --- | --- | --- |
| Comment: 1/1/11 – Project Agreement signed – Dec 10; Ms Shona Williams, Tax Administration Adviser commenced work with MFR in Nov 10; Ms Williams is on ‘secondment’ from the NZ Inland Revenue Department; Inception Report received (copy attached as Annex 3); FMU waiting for signed copy of ‘Secondment Agreement’ in order to commence payments; Recommendation: (1) FSC note the progress of this project; |  |  |  |  |  |
| 16 | Review & Update of Education Information System | Samoa Qualifications Authority (SQA) |  | $280,000 |  |
| Comment: 31/10/10 – pipeline, approved by FSC at Jul meeting subject to the availability of funds; |  |  |  |  |  |
| 17 | Independent Review, Ministry of Health Realignment | Public Service Commission | To determine whether the objectives of the realignment are being achieved and to identify and recommend areas for further improvement so as to enhance the performance of MOH and NHS in carrying out their functions | $107,000 |  |
| Comment: 1/1/11 – Approved by FSC on 24/8/10; Tenders Board confirmed Joan Macfarlane as the Independent Review Adviser; PSC to advise when Contract is signed and assignment is expected to start; Recommendation: FSC to note current status of project. |  |  |  |  |  |

SUMMARY – PROJECTS (as of the 1st January 2011)

|  |  |  | Approved | Spent | Balance | Jul 10 | Aug 10 | Sep 10 | Oct 10 | Nov 10 | Dec 10 | Jan 11 | Feb 11 | Mar 11 | Apr 11 | May 11 | Jun 11 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| P028 | Institutional Strengthening Project | Samoa Audit Office | 4,800,000 | 3,920,726 | 879,274 |  |  |  |  |  |  |  |  |  |  |  |  |
| P029 | Institutional strengthening Project | Samoa Bureau of Statistics | 6,700,000 | 0.00 | 6,700,000 |  |  |  |  |  |  |  |  |  |  |  |  |
| P031 | Project Management Training, Samoa Public Sector | Ministry of the Prime Minister & Cabinet | 1,874,000 | 1,052,035 | 821,274 |  |  |  |  |  |  |  |  |  |  |  |  |
| P034 | Human Resource Database for the Government of Samoa | Public Service Commission | 1,500,000 | 933,891 | 566,109 |  |  |  |  |  |  |  |  |  |  |  |  |
| P036 | Labour Law Reform | Ministry of Commerce, Industry & Labour | 250,000 | 52,099 | 197,901 |  |  |  |  |  |  |  |  |  |  |  |  |
| P039 | Situational Analysis & Project Design Document | Public Trust Office | 180,000 | 0 | 180,000 |  |  |  |  |  |  |  |  |  |  |  |  |
| P043 | Public Finance Management Reform Plan | Ministry of Finance | 2,530,000 | 1,599,409 | 930,591 |  |  |  |  |  |  |  |  |  |  |  |  |
| P044 | Improving Policy Development & Coordination Reform Program | Ministry of the Prime Minister & Cabinet | 8,000,000 | 3,551,392 | 4,448,508 |  |  |  |  |  |  |  |  |  |  |  |  |
| P050 | 1st Year Independent Review, Project Management Training | FMU Ministry of the Prime Minister & Cabinet | 200,000 | 61,909 | 138,091 |  |  |  |  |  |  |  |  |  |  |  |  |
| P051 | Institutional Strengthening Project (Phase I) | Ministry for Revenue | 3,635,000 | 0.00 | 3,635,000 |  |  |  |  |  |  |  |  |  |  |  |  |
| P053 | Independent Review, Ministry of Health Realignment | Public Service Commission | 107,000 | 0.00 | 107,000 |  |  |  |  |  |  |  |  |  |  |  |  |