Public Sector Improvement Facility 6-Monthly Work Plan (Jul – Dec 2011)

(1st July 2011)

PSIF GOVERNANCE

| Item Ref | Activity | Ministry/Agency | Description | Value | Dates (Duration) |
| --- | --- | --- | --- | --- | --- |
| 1 | Facility Coordinating Committee | Facility Management Unit | Provide secretariat support to the FCC – prepare & distribute agenda, hold meetings, prepare & distribute minutes |  | Jul – Dec 10 |
| Comment: FCC meetings usually held after each FSC meeting unless members call a ‘special meeting’; the FSC is supposed to be meeting every 2 months; anticipate 6 normal FCC meetings and at least 3 Special meetings for the period Jul 11 – Jun 12 |  |  |  |  |  |
| 2 | Facility Steering Committee | Facility Management Unit | Provide secretariat support to the FSC – prepare & distribute agenda, hold meetings, prepare & distribute minutes |  | Jul – Dec 10 |
| Comment: FSC meetings are required to be held every two months; anticipate 6 normal FSC meetings for the period Jul 11 – Jun 12; meetings for the first six months of this Financial Year FY 11/12 scheduled for Aug, Oct and Dec (actual dates to be confirmed) |  |  |  |  |  |
| 3 | Special Purpose Account | Facility Management Unit | On-going oversight of PSIF Special Purpose Account (payments, financial statements etc) |  | Jul – Dec 10 |
| Comment: Monthly financial reports produced; Audit Report for FY 10/11 due Sep 11; |  |  |  |  |  |
| 4 | Financial Statements; Review & Forward Plan | Facility Management Unit | Financial Reports and Review & Forward Plan to be presented to FCC & FSC every quarter |  | Jul – Dec 10 |
| Comment: The Review and Forward Plan for the ¾ of the Financial Year 2010/11 prepared; to be discussed at FSC meeting scheduled for 31st Jan 11; |  |  |  |  |  |

| 5 | Monitoring & Evaluation Framework | Facility Management Unit |  |  | Jul 10 – Jun 11 |
| --- | --- | --- | --- | --- | --- |
| Comment: QAI assessment for each project to be completed and logged with the FMU Manager every 6-months, latest QAI due the by the 31 Aug 2011; |  |  |  |  |  |

PSIF PROJECTS (Activities)

| Item Ref | Activity | Ministry/Agency | Description | Value | Dates (Duration) |
| --- | --- | --- | --- | --- | --- |
| 6 | Institutional Strengthening Project | Samoa Audit Office (SAO) |  | $4,800,000 over 2.5 years | Sep 08 – Apr 11 |
| Comment: 1/7/11 – Project completed; final payments made May 11; Completion Report received; total funds spent - $4,351,393.39; balance remaining (savings) = $448,606.61; FSC endorsed the preparation of an Independent Completion Report; FMU prepared TORs; TORs circulated to FSC members for comment; only SAO submitted comments; the TORs for the Independent Completion Report now finalized; the preparation of the independent completion report will start in Dec 11/Jan 12 to allow SAO a 6-8 month transition from the end of the ISP; its an opportunity for SAO to demonstrate they can sustain the momentum made; Recommendation: (1) FSC approve the TORs for the Independent Completion Report of the SAO ISP; (2) independent completion to start in Dec 11/Jan 12 |  |  |  |  |  |
| 7 | Institutional Strengthening Project | Samoa Bureau of Statistics (SBS) | Strengthen capacity of SBS to provide high quality statistics to enable the private/public sectors in Samoa to formulate evidence based policies to undertake economic, social and business planning | $6,700,000 over 3 years |  |
| Comment: 1/7/11 – The contract between VINSTAR and SBS finally approved by OAG; Project Agreement signed between FMU/PSIF and SBS; mobilization payment of $550,000 paid over together with a number of milestones completed since the project commenced in Feb 11; SBS needs to submit a revised work plan for remaining deliverables expected for FY 11/12 complete with budget to enable FMU/PSIF to anticipate expenditure for the next 12-18 months. Recommendation: (1) FSC note progress of project; (2) |  |  |  |  |  |

| 8 | Project Management Training for the Samoa Public Sector | Ministry of the Prime Minister & Cabinet (MPMC) | Develop practical project management expertise in the public sector | $1,874,000 over 3 years | Sep 08 – Dec 11 |
| --- | --- | --- | --- | --- | --- |
| Comment: 1/7/11 – Delivery of Intake II completed Dec 10; David Kay Training Development conducted a monitoring & evaluation visit in Dec 10; recruitment process for applicants for Intake III has started’ closing date for applications – 4th Feb 11; Recommendation: (1) FSC to note the progress of this project |  |  |  |  |  |
| 9 | Human Resource Database for the Government of Samoa | Public Service Commission (PSC) | Provide reliable information on employee performance, recruitment & capacity building to strengthen policy advice & decision making on HR matters | $1,500,000 over 2 years | Mar 08 – Jun 11 |
| Comment: 1/7/11 – Recommendation: (1) FSC note the progress of this project |  |  |  |  |  |
| 10 | Labour Law Reform | Ministry of Commerce, Industry & Labour (MCIL) | Revise labour laws to comply with ILO standards & conventions and strengthen MCIL’s capacity to address labour issues & relations | $250,000 | Jul 09 – Mar 11 |
| Comment: 1/7/11 – The Final date for completion of all activities was the 31st Mar 11; two claim for payments were received and processed; the remaining deliverables have not been completed and based on the FSC’s earlier decision, are no longer eligible for funding from the PSIF. The CEO MCIL sought a further extension with a request that the funds be moved to the MOF for disbursement and management. This is not in line with the conditions for PSIF funding. Recommendation: (1) The FSC re-affirm its decision to suspend all remaining funding for this project and (2) FSC Chair inform CEO MCIL that it PSIF funding cannot be transferred to MOF for disbursement and that the Committee stands by its earlier decision to cease funding this activity |  |  |  |  |  |
| 11 | Situational Analysis & Project Design Document | Public Trust Office (PTO) | Undertake a comprehensive situational analysis of PTO with recommendations for strengthening in a project design document (PDD) for an ISP | $180,000 |  |

| Comment: 1/7/1 – PTO has advised the Senior Legal Advisor approved under PACTAM is not able to undertake the situational analysis of the PTO; FMU has prepared revised TORs for an organisational development specialist to undertake the situational analysis; waiting for PTO to comment. Recommendation: (1) The FMU write to the PTO to see whether or not they want to pursue this activity or not |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 12 | Samoa Airport Authority Act Review | Samoa Airport Authority (SAA) | Review & draft amendments to the Samoa Airport Authority Act | $145,000 | Jun 09 – Dec 10 |
| Comment: 1/1/11 – public awareness on the Amended Act carried out in Dec 10 for both Upolu and Savaii; SAA inquired into the possibility of utilizing savings from the project to assist with the translation and publication of the new Act; SAA advised to submit an official request to FSC for consideration; otherwise the revised completion date (end of Jan 11) remains in effect. Recommendation: (1) FSC note the current status of this project |  |  |  |  |  |
| 13 | Public Finance Management Reform Program | Ministry of Finance (MOF) | Strengthen public finance management systems, improve transparency in accounting for public funds | $2,530,000 | Mar 09 – Jun 11 |
| Comment: 31/10/10 – PFMR Reform Annual Review Meeting held 13/12/10; included a presentation to all donor partners ( a copy of the Executive Summary from the Progress Report Nov 2009 – Dec 10 is attached as Annex 2); good progress continues to be made, Recommendation: (1) FSC note the progress of project |  |  |  |  |  |
| 14 | Improving Policy Development & Coordination Reform Program | Ministry of the Prime Minister & Cabinet (MPMC) | Strengthen capacity of MPMC to carry out core function of providing support to PM & Cabinet re whole-of-govt policy coordination & advice | $8,000,000 | Sep 09 – Dec 12 |
| Comment: 1/1/11 – key changes to Cabinet processes and policy role of MPMC developed, project steering committee (AG, MOF, PSC, MFA) met for the first time on 27 Aug 10 – provided with an update of project progress and opportunity to comment on new Cabinet processes and the Ministry’s Corporate Plan; FMU & VINSTAR have agreed on Milestones for Year II, AG’s Office have prepared Addendum. Procurement process underway to contract a Provider for the Document Management System (Cabinet) Recommendation: (1) FSC to note the progress of project |  |  |  |  |  |

| 15 | Institutional Strengthening Project (Phase I) | Ministry for Revenue | To improve the efficiency and effectiveness of tax administration | $3,635,000 | Nov 10 – Dec 13 |
| --- | --- | --- | --- | --- | --- |
| Comment: 1/1/11 – Project Agreement signed – Dec 10; Ms Shona Williams, Tax Administration Adviser commenced work with MFR in Nov 10; Ms Williams is on ‘secondment’ from the NZ Inland Revenue Department; Inception Report received (copy attached as Annex 3); FMU waiting for signed copy of ‘Secondment Agreement’ in order to commence payments; Recommendation: (1) FSC note the progress of this project; |  |  |  |  |  |
| 16 | Review & Update of Education Information System | Samoa Qualifications Authority (SQA) |  | $280,000 |  |
| Comment: 31/10/10 – pipeline, approved by FSC at Jul meeting subject to the availability of funds; |  |  |  |  |  |
| 17 | Independent Review, Ministry of Health Realignment | Public Service Commission | To determine whether the objectives of the realignment are being achieved and to identify and recommend areas for further improvement so as to enhance the performance of MOH and NHS in carrying out their functions | $107,000 |  |
| Comment: 1/7/11 – PSC awaiting receipt of final report; Recommendation: FSC to note current status of project. |  |  |  |  |  |

SUMMARY – PROJECTS (as of the 1st January 2011)

|  |  |  | Approved | Spent | Balance | Jul 10 | Aug 10 | Sep 10 | Oct 10 | Nov 10 | Dec 10 | Jan 11 | Feb 11 | Mar 11 | Apr 11 | May 11 | Jun 11 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| P028 | Institutional Strengthening Project | Samoa Audit Office | 4,800,000 | 3,920,726 | 879,274 |  |  |  |  |  |  |  |  |  |  |  |  |
| P029 | Institutional strengthening Project | Samoa Bureau of Statistics | 6,700,000 | 0.00 | 6,700,000 |  |  |  |  |  |  |  |  |  |  |  |  |
| P031 | Project Management Training, Samoa Public Sector | Ministry of the Prime Minister & Cabinet | 1,874,000 | 1,052,035 | 821,274 |  |  |  |  |  |  |  |  |  |  |  |  |
| P034 | Human Resource Database for the Government of Samoa | Public Service Commission | 1,500,000 | 933,891 | 566,109 |  |  |  |  |  |  |  |  |  |  |  |  |
| P036 | Labour Law Reform | Ministry of Commerce, Industry & Labour | 250,000 | 52,099 | 197,901 |  |  |  |  |  |  |  |  |  |  |  |  |
| P039 | Situational Analysis & Project Design Document | Public Trust Office | 180,000 | 0 | 180,000 |  |  |  |  |  |  |  |  |  |  |  |  |
| P043 | Public Finance Management Reform Plan | Ministry of Finance | 2,530,000 | 1,599,409 | 930,591 |  |  |  |  |  |  |  |  |  |  |  |  |
| P044 | Improving Policy Development & Coordination Reform Program | Ministry of the Prime Minister & Cabinet | 8,000,000 | 3,551,392 | 4,448,508 |  |  |  |  |  |  |  |  |  |  |  |  |
| P050 | 1st Year Independent Review, Project Management Training | FMU Ministry of the Prime Minister & Cabinet | 200,000 | 61,909 | 138,091 |  |  |  |  |  |  |  |  |  |  |  |  |
| P051 | Institutional Strengthening Project (Phase I) | Ministry for Revenue | 3,635,000 | 0.00 | 3,635,000 |  |  |  |  |  |  |  |  |  |  |  |  |
| P053 | Independent Review, Ministry of Health Realignment | Public Service Commission | 107,000 | 0.00 | 107,000 |  |  |  |  |  |  |  |  |  |  |  |  |