Scholarships PNG

2010-2014

Design

29 September 2009

Table of Contents

Page no.

Abbreviations and Acronyms	v

EXECUTIVE SUMMARY	vii

1	ANALYSIS AND STRATEGIC CONTEXT	1

1.1 	International Scholarships and Professional Development Contribution to PNG’s Development	1

1.2	PNG Relations with Development Partners	1

1.3	Scholarships within the PNG Development Context	2

1.3.1	The Australian Scholarships	2

1.3.2	The NZAID Scholarships	2

1.4	GoPNG Support for the Scholarship Program	3

1.5	Other Related AusAID and NZAID Programs in PNG	4

2 	OVERARCHING POLICY ISSUES	4

2.1	Equitable Participation	4

2.2	Increasing Scholarship Access to the PNG Provinces	4

2.3	Anti Corruption, Governance and Transparency	5

2.4	People with Disabilities	5

2.5	Child Protection	5

2.6	HIV and AIDS	6

3 	LESSONS LEARNED	6

3.1	The Facility Model	6

3.2	Issues and lessons learned from AusAID ADS Scholarships	7

3.2.1	The High Number of PNG ADS Extensions and Terminations	7

3.2.2	The High Cost of the PNG ADS Scholar Extensions and Terminations	8

3.3	Other Lessons Learned	9

3.3.1	Problems Caused by Extended Time away from PNG	9

3.3.2	The High Age Profile of PNG Scholars	9

3.2.3	Problems when Public Scholars Return to PNG	10

3.4	Issues and lessons learned from AusAID Australian Leadership Awards (ALAS) Scholarships and Fellowships (ALAF)	10

3.5	 Issues and lessons learned from NZAID Scholarships	11

3.6	Lessons Learned from the Regional Development Scholarships (RDS)	11

4	PROGRAM DESCRIPTION	12

4.1	Overview	12

4.2	Component 1: Australian and New Zealand Scholarships to PNG	14

4.3	Proposed Changes to PNG Scholarship Management	14

4.3.1	Targeting Scholarships to Match PNG Human Resource Priorities	14

4.3.2	Increased Promotion of Scholarship Opportunities	15

4.3.3	New Scholarship Application Form	15

4.3.4	Receipt of Scholarship Applications	16

4.3.5	Membership of the Scholarship Selection Panel (for ADS and NZAID Scholarships)	17

4.3.6	Introduce Interviews into Scholarship Selection	18

4.3.7	Introduce English Language Testing for Short Listed ADS Applicants	18

4.3.8	Academic and Pastoral Advice to Scholarship Candidates	19

4.3.9 Pilot 10-Month Foundation Course for Provincial Candidates who almost make Selection	20

4.3.10 Allocation of a Proportion of Scholarships for the PNG Higher Education Sector	21

4.3.11 	Removal of the TVET Level Scholarship Awards	21

4.3.12	Extend the Pre-Departure Briefing (PDB)	22

4.3.13	Improvements to the Reintegration of Returning Scholars	23

4.3.14	Monitor Responsibilities of PNG Employers	24

4.3.15	Monitor and Facilitate, Responsibilities GoPNG Agencies, Awardees and Alumni	24

4.3.17	Pilot Delivering Year 1 for a Cohort of Scholarship Holders in a PNG University	25

4.3.18	Supporting the Australian Leadership Award Scholarships (ALAS)	25

4.3.19	Supporting the Regional Development Scholarships (RDS)	26

4.4 	Component 2:  PNG Professional Development Initiatives	27

4.4.1	Support for Young PNG Leaders	28

4.4.2	Supporting Australian and New Zealand Alumni in PNG	28

4.4.3	Strengthening PNG Professional Associations	28

4.4.4	Supporting ALA Fellowships in PNG	29

4.4.5	Managing Careers in Development Initiative	29

5	MANAGEMENT AND IMPLEMENTATION ARRANGEMENTS	29

5.1	The Scholarships PNG Leadership	29

5.2	The Scholarships PNG Implementation Model	30

5.3	The Scholarships PNG Management	31

6	IMPACT AND SUSTAINABILITY ISSUES	33

6.1	Benefits of Additional In-country Preparation for Scholars	33

6.2	Building Sustainable Practice into the Scholarship Program	33

7	CRITICAL RISKS AND RISK MANAGEMENT STRATEGIES	34

8	FACILITY PLANNING AND REPORTING	35

8.1	The Annual Plan	35

8.2	Scholarships PNG Operations Handbook	35

8.3	The Scholarships PNG Promotion and Communication Plan	36

8.4	Six Monthly and Annual Reports	36

8.5	Information for AusAID’s Annual Corporate Reporting	37

8.6	Independent Progress Report	37

8.7	Independent Completion Report (ICR)	38

9	MONITORING, EVALUATION AND CONTINUOUS QUALITY IMPROVEMENT	38

9.1	The Monitoring & Evaluation Plan	38

9.2	Annual Scholarships PNG Contractor Performance Assessment	39

10	THE Transition between PATTAF and PNG	39

Annex 1	 Scholarships PNG Implementation Arrangements, Staffing and	41

Facility Management	41

1.1	Scholarships PNG Implementation Arrangements	41

1.2	Scholarships PNG Facility Management, Staffing and Service Requirements	41

Annex 2 	 Draft Implementation Schedule	51

Annex 3	 Critical Risks and Risk Management Strategies	55

Annex 4	65

4.1	Monitoring and Evaluation Framework	65

4.2	Monitoring and Evaluation Methods and Tools	65

Annex 5	 Contractor Performance Criteria	73

Annex 6	 Sample Template for the Scholarships PNG Priority Sectors	76

Annex 7	Summary of Related AusAID and NZAID Programs in PNG	78

Annex 8	Detailed Description of ADS, ALA, NZAID and RDS Scholarship Management Processes  including the Facility Responsibilities	81

Annex 9	 Membership of The Design Team	96

Annex 10	 Summary of People and Agencies Consulted	98

Annex 11	 References and Readings	105

- Abbreviations and Acronyms

| ADB | Asian Development Bank |
| --- | --- |
| ADS | Australian Development Scholarships |
| AIDS | Acquired Immune Deficiency Syndrome |
| ALA | Australian Leadership Awards (funded by AusAID) |
| ALAS | Australian Leadership Award Scholarships |
| APTC | Australia Pacific Technical College |
| ARDS | Australian Regional Development Scholarships |
| ASA | The Allison Sudradjat Award |
| ASF | Australian Support Facility |
| AusAID | Australian Agency for International Development |
| BEDP | Basic Education Development Project |
| CEDAW | Committee on the Elimination of Discrimination Against Women |
| CIDA | Canadian International Development Agency |
| CSO | Community Service Organisation |
| DAC | Development Assistance Committee |
| DCS | Development Cooperation Strategy |
| DFID | UK Department for International Cooperation |
| DIAC | (Australian) Department of Immigration and Citizenship |
| DNPM | The Department of National Planning and Monitoring |
| DPLGA | Department of Provincial and Local Government Affairs |
| DPM | Department of Personnel Management |
| DWU | Divine Word University |
| ECBP | Education Capacity Building Program |
| EPSP | Economic and Public Sector Program |
| FaCSIA | Department of Families, Housing, Community Services and Indigenous Affairs |
| GoA | Government of Australia |
| GoPNG | Government of Papua New Guinea |
| HDI | Human Development Index |
| HE | Higher Education |
| HIV | Human Immunodeficiency Virus |
| HR | Human Resource |
| HRD | Human Resource Development |
| HRM | Human Resource Management |
| IAP | Introductory Academic Program |
| IELTS | International English Language Testing System |
| IPA | Institute of Public Administration (PNG) |
| IPR | Independent Progress Report |
| IT | Information Technology |
| LNG | Liquefied Natural Gas |
| LTDS | Long Term Development Strategy |
| M&E | Monitoring and Evaluation |
| MDG | Millennium Development Goals |
| MoU | Memorandum of Understanding |
| MTDS | Medium Term Development Strategy 2005-2010 |
| MSC | Most Significant Change |
| NDoE | National Department of Education |
| NCD | National Capital District |
| NGO | Non Government Organisation |
| NQF | National Qualifications Framework (PNG) |
| NTC | National Training Council |
| NZAID | New Zealand’s Aid & International Development Agency |
| NZ | New Zealand |
| O-Based | Overseas Based AusAID staff at a country Post, normally based in that country |
| OASIS | Online Application Scholarships Information System (managed by AusAID’s SS) |
| PATTAF | PNG Australia Targeted Training Facility |
| PDB | Pre-Departure Briefing |
| PfD | Partnership for Development |
| PhD | Doctor of Philosophy |
| PLHIV | People Living with HIV |
| PLP | Pacific Leadership Program |
| PNG | Papua New Guinea |
| PNGAAA | PNG-Australia Alumni Association |
| PNGNZAA | PNG New Zealand Alumni Association |
| PPII | Provincial Performance Improvement Initiative |
| PSCBI | Pacific Public Sector Capacity Building Initiative |
| PSI | Provincial Support Initiative |
| QA | Quality Assurance |
| QAI | Quality at Implementation |
| SIMON | Student Information Management Online (managed by AusAID’s Scholarship Section) |
| SIMS | Student Information and Management System (for the NZAID scholarships) |
| SNS | Sub National Strategy |
| SoS | Scope of Services |
| SS | Scholarships Section (AusAID Canberra) |
| SPNG | Scholarships PNG |
| TOEFL | Test of English as a Foreign Language |
| TOR | Terms of Reference |
| TVET | Technical and Vocational Education and Training |
| UNDP | United National Development Program |
| WB | World Bank |
| WoG | Whole of Government |

# EXECUTIVE SUMMARY

Introduction

- International scholarships are provided to PNG by a number of Governments as part of Official Development Assistance (ODA) programs. The largest numbers of international scholarships to PNG are offered by the Australian and New Zealand governments, as part of their bi-lateral assistance programs.

- The AusAID and NZAID scholarship programs have been a feature of Australian and New Zealand’s support to the development priorities of PNG for many years and are highly valued by the leadership of the three countries. The awards are highly valued and represent an opportunity to provide courses, experiences and outcomes that can match PNG’s human resource and development priorities in an effective and long-term manner.

- Through experience and lessons learned over the past seven years, the potential impact of PNG Scholarships can be better realised. The combined management of the AusAID and NZAID Scholarship program has potential to make increased contributions to the development priorities of PNG, with Scholarships an integral part of AusAID’s and NZAID’s Country Program Strategies. Joint management of Scholarships also represents a tangible example of high-level donor cooperation and a commitment to the reduction of transaction costs incumbent on governments engaged in the management of donor funded activities.

Background

- The PNG-Australia Targeted Training Facility (PATTAF) commenced in April 2002 and will operate until Scholarships PNG is implemented in early 2010. The PATTAF design was completed almost 8 years ago, with the Monitoring and Evaluation (M&E) framework last updated in 2006. Much has changed in relation to scholarship policies and management arrangements since PATTAF was contracted. This design provides the Partners (i.e. GoPNG, AusAID and NZAID) with an opportunity to update Scholarship focus and processes to better align the PNG program with contemporary practice.

- This design is consistent with the Paris Principles on Aid Effectiveness, the Accra Agenda for Action and the PNG Commitment on Aid Effectiveness. Two major international donors, GoA and GoNZ, will align their scholarship programs to best meet GoPNG needs as have been identified in recent studies. This design incorporates both Australia’s and New Zealand’s future funding for PNG scholarships, delivered through a Facility with two major Components, namely: Australian and New Zealand (NZ) Scholarships to PNG; and PNG Professional Development Initiatives. The proposed name of this Facility is Scholarships PNG.

- This design has been developed during a time of great fluidity, with GoPNG developing a long term strategic framework at a time when the Global Economic Crisis is placing pressure on national budgets. In addition, high on GoPNG policy agenda is the potential for greatly increased revenue streams resulting from the proposed PNG Liquefied Natural Gas (LNG) project. Lack of a skilled local workforce will limit the ability for PNG to harness the economic, social and development gains which could result from the project, spreading these benefits equitably amongst Papua New Guinean men and women.

Issues with Current Scholarship Arrangements

- Economic development within PNG continues to be constrained by a shortage of skilled, qualified people across key sectors of the workforce. This shortage relates to the capacity of PNG’s basic education and post-secondary systems to produce graduates of sufficient quality and numbers to meet local demand, cited by PNG employers as an urgent and growing constraint, especially in those industries that will drive the PNG economy into the future.

- Australia spent $41.5m in support of the PNG economic and public sector in 2008/09, most of which was for technical assistance through the Advisory Support Facility and the Strongim Gavman Program. These programs have, in recent times, increased emphasis on capacity building of local staff as part of a broader Human Resource Development (HRD) agenda.

- Anecdotal evidence from GoPNG, employer organisations and from returned scholars indicate that Scholarship programs provide a valuable mechanism to develop the capacity and skills of individuals and organisations, as well as establishing and strengthening personal and professional networks between Papua New Guineans and their Australian and New Zealand peers. Scholarships are strongly supported by the Partner Governments; this Scholarships PNG design provides the opportunity to review Scholarship program processes and structures.

- The transparency, effectiveness and potential impact of the Scholarships need strengthening, particularly the Australian Development Scholarships (ADS). The Australian scholarships program in PNG is large, with 130 new ADS scholars and up to 10 Australian Leadership Award (ALA) Scholarships each year, at a direct cost of around $13m per annum plus management costs. There are currently 324 PNG students holding ADS, with almost 300 extensions for ADS scholars between 2004-2008, at an average cost of $26,300 per extension (total cost of $7.89m). Over the same period, 84 ADS scholarships were terminated, at an average cost of $70,000 per scholar (total of $5.9m).

- A significant number of PNG scholars had their ADS award downgraded (e.g. from PhD to Masters or Masters to Graduate Diploma). For the five years 2003-2007, overall course failure was higher amongst males compared to females, by a factor of 2.2:1. In addition, PNG female ADS scholars had a lower proportion of course extensions than males.

- Through its PNG program, New Zealand is committed to strengthening human resources development (HRD), assisting capacity development with support provided both outside and within PNG. The NZAID program also supports in-country training and in-country awards that can strengthen PNG institutions to deliver appropriate training. Capacity building is not limited to education, training or institutional strengthening: it has an emphasis on building capacity of GoPNG, NGOs and communities to identify and solve their own problems.

- There are 20 New Zealand Development Scholarships (NZDS) Public and 8 NZDS Open scholarships offered annually for PNG scholars. In New Zealand, at any time there are around 60 PNG NZDS scholars undertaking their award courses. Over the last two years there have been 2 Scholarship terminations in NZ, one for non performance and one for inappropriate behaviour. An additional 230 scholarships are awarded annually by NZAID for study within PNG, with approximately 7% of these students requiring an extension.

Addressing the Issues

- There continues to be strong support from all Partners for a continuation and expansion of the PNG Scholarship program. The Scholarships PNG will be responsive to changing PNG needs and will also consider the future possibility of expanding in-PNG scholarship activities, as well as the potential for adding short-term fellowships and flexible modes of delivery.

- Evidence indicates that additional effort at the beginning of the scholarship cycle can help address the high rate of extensions and withdrawals and improve the likelihood of PNG scholars achieving academic success and successful reintegration into the workforce. A more focused, rigorous selection process and reintegration program would make Scholarships more relevant to PNG’s development needs. In addition, individual scholarship holders should be better equipped to undertake their studies through a new set of improved in-country preparation before the scholars leave PNG to embark on their program.

- The Facility model has demonstrated its appropriateness as a mechanism for managing scholarships and other training. It has proven to be suitable flexible and responsive for new policy development, enabling the scaling up (or down) of activities as required. A Facility model will therefore be retained, overseen by a Joint Steering Committee.

Description of the Program

The goal of the Program is: contribute to equitable economic growth and poverty reduction in Papua New Guinea by the development of highly skilled men and women who are able to apply their professional and technical expertise, experience and leadership skills in the workplace and in society.

- Scholarships PNG will comprise two Components. There are two objectives linked to Component 1, and three objectives linked to Component 2.

Component 1: Scholarships Program

- The Scholarships program will provide PNG with men and women scholars to make personal and institutional contributions to development of the country.

Objective 1   To provide men and women with the skills and knowledge to contribute to PNG’s economic and social development within the priority areas of National and Provincial governments.

Objective 2	To provide men and women with the skills and knowledge to contribute to PNG’s economic and social development within the private sector and civil society.

Component 2: PNG Professional Development Initiatives

- As jointly agreed between Partners, address emerging human resource priorities through direct support to strengthen capacity of PNG professional associations and leadership groups.

Objective 3	To empower young women and men to actively participate in the development of Civil Society.

Objective 4	To strengthen identified professional bodies to provide to their membership opportunities to develop skills and knowledge essential to achieve best practice in the operation of PNG industry, Civil Society Organisations and government.

Objective 5	To strengthen the capacity and profile of Australian and NZ Alumni in PNG.

Equity and Access

- This design integrates and embeds principles of equity and access through its structure, transparency in decision making, the range of proposed initiatives and via the reporting requirements. The development and application of new processes, guidelines, eligibility criteria and publication of priority Scholarship will strengthen access and equity for those men and women who may have previously been marginalised or bypassed.

- Care has been taken to address cross cutting issues of governance, gender equality, HIV and AIDS, people with disabilities, poverty of opportunity (i.e. physical isolation) and child protection. The Facility, through Scholarships and professional development programs, will work with the Partners to address these priorities.

Sustainability

- Under Component 1, the program will emphasise the achievement of realistic, sustainable outcomes via better Scholarship selection, pre-departure and reintegration processes.

- Under Component 2, funding support or technical assistance will be provided to PNG organisations and associations for the purpose of professional and human resource development. The PNG-Australia Alumni Association (PNGAAA) and the PNG-NZ Alumni Association (PNGNZA) will also be funded to support scholars during scholarship cycle activities as well as when the scholars return to PNG.

Monitoring and Evaluation (M&E)

- A comprehensive M&E Framework will ensure management information is available to Partners for their corporate reporting requirements. The Framework provides management data (i.e. are the scholarships well targeted, balanced by gender, by province and national priorities) as well as outcomes data, using Most Significant Change (MSC), tracer studies and case studies.

# 1	ANALYSIS AND STRATEGIC CONTEXT

- 1.1 	International Scholarships and Professional Development Contribution to PNG’s Development

- The Medium Term Development Strategy (MTDS) focuses on universal basic education (of priority to those Papua New Guineans living in rural areas) and on adult literacy. In a global climate that requires greater dependency on technology, the need for knowledge and skills has become a critical issue for developing countries who wish to better develop / integrate their systems and practices in relation to those used across the international community.

- There is strong argument that a skilled workforce yields substantial public and social returns on investment and that the production of new knowledge has potential to produce higher economic returns and development. With increased levels of education, developing countries can experience better standards of living through income growth, expanded employment choices, improved standards of leadership and increased security.

- While progress has been made over the years, PNG continues to struggle to provide a skilled workforce that can meet labour market demand. The MTDS 2005-2010 acknowledges PNG cannot achieve successful integration into the global economy and move into higher value-added industries without “considerable improvement in the country’s skill base and labour productivity levels.”

- If PNG is to take maximum advantage of employment opportunities, Papua New Guinean men and women will need to have the relevant attributes that enable them to fill as many skilled positions as possible. In the emerging economic sectors highly skilled, highly paid positions are generally taken by men, caused (in part) by the limited number of PNG women who have the required professional qualifications / certification to gain these highly skilled positions.

- International scholarships provide scholars with a recognised qualification, gained through an academic and social experience that establishes and strengthens social and professional bonds between men, women and institutions in PNG and participating countries. International scholarships also have the potential to meet the skills gaps as identified above.

- Australia, New Zealand, the European Union, Japan, China, Asian Development Bank and other donor agencies play an important role investing in human resource development in PNG, through short-term and long-term scholarships and capacity building projects. These scholarships directly contribute to the development of PNG’s human capital.

- 1.2	PNG Relations with Development Partners

- The donor community and GoPNG committed to a development approach consistent with the Paris Declaration, Accra Agenda for Action and the PNG Declaration on Aid Effectiveness. This includes promoting strong PNG ownership of donor programs, alignment with PNG priorities, mutual responsibility and accountability and increased donor harmonisation. This design focuses on aligning Scholarships and HRD initiatives to support development of a skilled PNG workforce to meet current and emerging labour market requirements.

- The design supports the PNG-Australia Development Cooperation Strategy (DCS) and the PNG-New Zealand Country Program Strategy (2008-2018). In 2008 the relationship between PNG and Australia was strengthened through establishing the PNG Australia Partnership for Development, a shared vision for both countries to work together in close cooperation.

- 1.3	Scholarships within the PNG Development Context

- International scholarships are provided to PNG by a number of Governments as part of their Official Development Assistance (ODA) programs. The largest numbers of scholarships to PNG are offered by the Australian and New Zealand governments as part of their bi-lateral assistance programs.

- 1.3.1	The Australian Scholarships

- The Australian Government has offered development scholarships since the Colombo Plan was established in the early 1950s. Over 100,000 students from developing countries have studied in Australia and returned to their home countries to contribute to social and economic development. In 2009 alone, over 3,500 scholars are studying in Australia. In New Zealand, there are approximately 500 NZAID funded scholars undertaking study programs.

- The AusAID and NZAID scholarship programs have supported the development priorities of PNG for many years. The awards are highly valued and represent an opportunity to provide courses, experiences and outcomes that can match PNG’s human resource and development priorities in an effective and long-term manner.

- Scholarships also play an important role in addressing skills shortages until the PNG higher education institutions can be strengthened to such a level they can provide an equivalent level of educational opportunities. Scholars also develop and maintain strong academic, professional, social and friendship links between the two countries, through living and working with their Australian or NZ peers and colleagues.

- In the past, the relatively high number of Scholarships (in comparison to PNG’s population and the size of GoPNG and the private sector) has led to difficulties in attracting a sufficient number of suitable applicants. Many applicants had insufficient education background, with some PNG agencies and organisations lacking capacity to release scholars for several years. This design includes strategies to improve this situation and to better target, select and prepare scholars for their study, as well as increased engagement and follow-up on their return.

- AusAID funds approximately 150 ADS and ALAS annually. The ADS scholarships represent the largest number (130) and these are divided into two main categories:

Public: where the applicant must be employed and endorsed by a GoPNG agency, department, institution or other entity; and

Open, where scholarship applications are accepted from those in the private sector; Civil Society Organisations (CSOs); Non Government Organisations (NGOs); faith-based organisations and churches; and from individuals.

- The ADS and ALAS programs will remain a central part of supporting the development of PNG’s human resources, through a significant number of men and women gaining higher levels of qualification, increased technical and professional capabilities and increased opportunities for secure employment. On return to work in PNG these graduates should be well placed to make a direct contribution to PNG’s development. The nation will also benefit through better collaboration and cooperation with PNG colleagues and international peers.

- 1.3.2	The NZAID Scholarships

- NZAID has a complementary annual Scholarship program of about 20 NZDS-Public Places plus 8 NZDS-Open scholarships, with around 60 PNG scholars studying in NZ at any time. The budget forecast for FY 2009/10 is NZ$2.1million and the program seeks to strengthen the human resource base by supporting identified priority areas as are outlined in the National Strategic Development Plan; Human Resources Planning Frameworks; linking with the NZAID / Papua New Guinea strategic framework; and new agreed strategies. The existing priority study areas for NZAID and GoPNG are basic education, primary health, strengthening civil society, rural economic development and sustainable resource management.

- The NZAID Priority areas require significant effort from NZAID and GoPNG to maintain awareness of opportunities and priorities and the increased collaboration between Australia and New Zealand will strengthen this aspect of Scholarships to the PNG participants, through providing access (for all partners) to a more substantial network.

- The promotion of a fair and reasonable timetable for a combined Scholarship program also reduces both donors overloading the resources of the GoPNG nominating agencies, allowing more time to focus on compliance and on achieving quality outcomes. The Scholarships PNG design also addresses gaps which may arise during the pre-award processes, including Partner approval phases, through the application of a smooth, unified and consistent set of management systems and timing.

- The Scholarships PNG will enable Partners to focus more on the establishment of equitable Scholarship opportunities in the Provinces, through the application of additional promotional and management resources combined with an objective, transparent processes. The design also allows flexibility for further focus on the post award monitoring and evaluation for both the NZDS Public and Open scholarships.

- Through discussions and an agreement to cooperate between AusAID and NZAID, this design provides for closer collaboration and efficiencies. The joint management provides economies of scale, facilitates the sharing of lessons learned and also reduces the “competition” between the two programs which has (in the past) led to PNG scholars being selected for both Australian and NZ scholarships, leading to a last-minute withdrawal from one of the offers.

- 1.4	GoPNG Support for the Scholarship Program

- The GoPNG and international donors make a substantial investment to fund and support the PNG Scholarship program, as part of a broader strategy to address knowledge and skills gaps. Each international scholarship awarded results in the “loss” of a key GoPNG staff member for an extended time, and therefore incurs opportunity costs (i.e. positions to be filled while the scholar is overseas) as well as direct costs (payment of allowances, salaries etc).

- The following costs are borne by the GoPNG and indicate the ongoing commitment and ownership of the PNG Scholarship program. They include:

- Support to good governance, through membership of the Joint Advisory Steering Committees (currently via PATTAF for Australian scholarships and by NZAID for NZ). The key agencies of DNPM, DPM and NTC provide strong GoPNG support and commitment to the Scholarships PNG;

- Participation in the Scholarship promotion, application and selection processes;

- Providing salaries and allowances, to selected Public category scholars in its employ, while they are studying overseas;

- Holding open the public sector positions to selected returning scholars;

- Costs for GoPNG associated with implementing the Reintegration Plans of returning scholars and the organisational restructuring that changes in staffing often entails.

- In the Public category, GoPNG agencies also play a crucial role in the reintegration of returning scholars, which requires significant planning and resources to ensure success.

- 1.5	Other Related AusAID and NZAID Programs in PNG

- A number of relevant AusAID and NZAID funded programs in PNG contribute to the development of knowledge and skills. These are being implemented across PNG in partnership with GoPNG agencies, and involve HRD development and capacity building.

- These development initiatives provide an opportunity to better coordinate available technical and organisational support to scholars, within a particular agency. For example, there will likely be opportunities where the Reintegration of Scholarships PNG returning scholars could be supported in the partner agencies, including mentoring and support during the initial period after the scholar’s return. The AusAID and NZAID funded programs may also be in a position to assist the GoPNG agency with its HRD and scholar Reintegration planning and implementation. Details of relevant AusAID and NZAID funded activities in PNG are included as Annex 7.

# 2 	OVERARCHING POLICY ISSUES

- 2.1	Equitable Participation

- Gender equity and the equitable participation remain important considerations in Scholarships. This includes addressing the needs of disadvantaged groups such as people with disability, or men and women living and working in the Provinces. The Scholarships PNG will make extra effort, through advocacy and promotional activities, to reach these groups and increase their representation in the Scholarship program. Specific gender challenges or constraints will be assessed on an annual basis and appropriate opportunities taken to address them in the Annual Planning process. The M&E system will include gender disaggregation of application numbers, scholars mobilised, the award results and data on their return to PNG.

- Currently, 50% of PNG ADS are awarded to women, who overall have demonstrated more successful outcomes than their male counterparts. Extra effort will be made to explicitly address women’s access to Scholarship and other information, as well as to ensure promotional materials reach men and women in the Provinces.

- While NZAID continues to provide a stipend based on family structure, AusAID’s scholarship dependence allowance was discontinued. Despite the abolition of the allowance, many scholars continue to take their families with them to Australia. The burden of insufficient financial resources, coupled with academic study and family responsibilities, weigh heavily and may contribute to poor academic performance. Better access to information on the cost of living, children’s school and child-care facilities in potential university host cities will enable scholars to make informed decisions, especially in relation to their personal circumstances.

- 2.2	Increasing Scholarship Access to the PNG Provinces

- The inclusion of a pilot Foundation Course, to be delivered in PNG, increases the potential for a broader range of potential Provincial scholars to participate in the Scholarship program, including those groups currently disadvantaged by location and limited access to information. This additional in-country support (described later) is part of an attempt to overcome educational and communication barriers that exist for men and women at the Provincial level.

- This new initiative will build on the experience that NZAID has gained through its Foundation programs that are in place to support scholars when they first arrive in NZ to take up their studies. The proposed Foundation course in PNG will also be informed by the regional success and lessons learned through the University of the South Pacific (USP) Foundation Program.

- 2.3	Anti Corruption, Governance and Transparency

- Scholarships broadly contribute to improved governance, including strengthening transparency and accountability across public and private institutions. Scholars not only gain skills and knowledge from international training, but also experience living and working in countries with strong democracies, the rule of law and where corruption and conflict of interest are taken very seriously and dealt with by a strong judicial system.

- Scholarship application and selection processes will become more apparent and transparent to applicants. The free flow of information and access to scholarship opportunities to those who meet eligibility requirements will help to ensure management is transparent, fair and equitable. Compliance checks will be made to ensure all information and required documentation is included in Scholarship applications. Compliant Public category applications will be forwarded to the relevant GoPNG partner agencies for endorsement, after which they will be provided to the members of the independent Selection Panel, for their consideration.

- In the past there have been attempts (in writing or verbally) to circumvent the selection process and to influence selection. Any such attempts in the Scholarships PNG will be reported for appropriate and immediate action. Staff from the Scholarships Section (SS), where possible, will participate in interviewing short-listed ALA Scholarship candidates in PNG. The AusAID Post will endorse the ALA selection decisions before forwarding them to Canberra for the final regional selection process.

- 2.4	People with Disabilities

- Men and women with disabilities will be targeted and encouraged to nominate for a scholarship award. The Scholarships PNG will be promoted to community organisations and foundations that primarily care for, advocate and otherwise work with people living with a disability. A broad definition of scholarship support for people living with disabilities will be adopted. This would include seeking applications to study for a course or certification award that can relate directly to improving their professional and technical expertise in disability for Papua New Guinean professionals, carers and specialist disabled facility administrators.

- The Scholarship program can promote and support people living with disabilities in PNG, either directly as a scholarship holder or indirectly through providing increased local knowledge, skills and expertise to support a more inclusive society.

- When studying in Australia or NZ, the responsibility for providing support and appropriate facilities for the scholar will rest with the university. For this reason, information and advice on the needs of candidates with a disability who are awarded a scholarship will be provided well in advance of mobilisation, including written confirmation from the university that they have expertise and support mechanisms required to support the scholar.

- 2.5	Child Protection

- In the course of scholarship management, Facility personnel may come into contact with children or minors. All contractors and NGOs funded by AusAID are bound by clear, strict policies in relation to managing and reducing risks of child abuse by persons engaged in delivering the aid program. This includes zero-tolerance of any issues relating to child abuse and child pornography.

- The relevant policies are outlined in AusAID’s Child Protection Policy which provides a framework for managing and reducing the risks of child abuse by persons involved in delivering aid activities. This policy document specifies the minimum standards with which all contractors must comply in their operations and in their dealings with Partners, subcontractors, associates or consultants they may engage, and is embedded in both the ADS and ALA Scholarship Handbooks.

- 2.6	HIV and AIDS

- HIV is a constraint to the development of human resources in many developing countries. This is a potential threat to PNG, which has the highest HIV prevalence rate in the Pacific region, in addition to an increasing HIV incidence and prevalence rates. HIV and AIDS represent an important public health and development issue for AusAID, NZAID and for PNG. Two main approaches will be adopted: HIV risk minimisation through HIV mainstreaming across all Facility operations; and increasing the quantum and quality of HIV research and knowledge through the support of HIV related research Scholarships.

- Factors contributing to HIV risk and vulnerability in PNG include mobility and migration, gender inequality, gender based violence, sexual violence, unprotected sex (low condom access or use), concurrent sexual partnerships and cultural practices and norms. The ongoing occurrence of polygamy in PNG increases the risk of spreading HIV and AIDS, with women particularly vulnerable to the virus through men having multiple partners.

- As part of the first and subsequent Annual Plans, the Facility will develop an approach, for Partner endorsement, that details how HIV + AIDS will be addressed across the scholarship cycle. Special attention will be given to address risk and vulnerability experienced by men and women across the various aspects of the Program. It is clear that the scholarship program poses an increased risk of HIV transmission due to increased mobility, separation of spouses and access to additional finances.

- During scholarship applications, all possible transportation between provinces and Port Moresby will be kept to a minimum. When scholars are required in Port Moresby, the Facility will ensure security measures take into account in accommodation and transportation arrangements, in prevent potential gender based violence and sexual violence.

- Successful applicants travelling to Australia or NZ (and spouses who may remain in PNG) will be briefed regarding opportunities for HIV testing and provided with basic HIV education and prevention strategies, during pre-departure and post-departure briefings. Information regarding where to go for HIV testing while in Australia or NZ will be provided, as well as information on access and management of HIV + AIDS treatment for those potentially HIV positive.

# 3 	LESSONS LEARNED

- 3.1	The Facility Model

- Under the Scholarships PNG there will be a total of up to 180 Australian and NZ scholarships per year to be managed, as well as ongoing demand for smaller awards that deal with professional development for individuals and organisations. There is an insufficient number of staff at AusAID or NZAID Posts in PNG to fully manage the large Scholarship program. The Facility model has proven to be a successful, responsive and flexible management mechanism.

- The PATTAF design was completed almost 8 years ago, with the M&E framework last updated in 2006. Much has changed in relation to Australian and NZ scholarship policies and management arrangements since PATTAF was contracted. This design provides Partners (i.e. GoPNG, AusAID and NZAID) with an opportunity to update the scholarship priorities and processes to better align them to PNG’s needs and with contemporary practice.

- The PATTAF model has proven to be a flexible and responsive arrangement that has enabled the AusAID funded PNG scholarship program to identify and mobilise a large number of scholars and to provide support and leadership in a number of key areas. These include comprehensive M&E and reporting arrangements; the provision of support to Alumni; the introduction of tracer studies as part of impact assessment; and the achievement of set scholarship targets. In many instances the PATTAF has led the development of management processes and mechanisms in order to maximise Australian scholarship opportunities within the complex PNG context.

- The Facility model, with Partner oversight, will ensure management of the program is effective, with joint promotion, receipt of applications, joint selection and mobilising scholars to Australia and NZ, ongoing follow up while scholars are away, and support to the scholars’ reintegration on return to PNG.

- Inclusion of a Joint Steering Committee provides high-level policy and planning input from the three governments, as well as PNG private sector, Civil Society and academic expertise. A similar mechanism has been a successful executive decision-making mechanism for PATTAF. It is proposed that Joint Steering Committee membership and functions be strengthened and expanded under Scholarships PNG. The Facility can also provide a flexibility mechanism to respond to other development priorities through Component 2.

- 3.2	Issues and lessons learned from AusAID ADS Scholarships

- Combined management of the AusAID and NZAID Scholarship program has the potential to make an increased contribution to the development priorities of PNG. Through experience and lessons learned over the past 7 years, the potential of Scholarships can be better realised. The following sections detail the lessons learned, which form the basis for new initiatives that are proposed in this design.

- 3.2.1	The High Number of PNG ADS Extensions and Terminations

- The PNG ADS program has mixed success in relation to scholar selection, their success in Australia and their impact on return. ADS processes need to be strengthened in order to achieve better results for the individual and for PNG.

- During 2005-2008, PNG scholars made up 16% of the total international ADS cohort yet were responsible for 29% of award variations (i.e. reduction in level of award or extensions to time). PNG ADS also had 33% of all ADS extensions, 26% of suspensions and 47% of terminations. The following Table shows a representative sample of ADS scholar numbers from a selection of representative countries, including the disproportionately high percentage of PNG scholars that require variations to their study program in Australia.

- Table 1: PNG Scholar Variations for Students commencing ADS in Australia: 2005- 2008

|  | Total students by country | % of total | Variations approved 2006-2008 | % of total |
| --- | --- | --- | --- | --- |
| Bangladesh | 165 | 5% | 30 | 4% |
| Cambodia | 83 | 3% | 26 | 3% |
| China | 95 | 3% | 25 | 3% |
| Indonesia | 1115 | 36% | 264 | 34% |
| Laos | 166 | 5% | 46 | 6% |
| Mozambique | 70 | 2% | 20 | 3% |
| Pakistan | 55 | 2% | 14 | 2% |
| PNG | 493 | 16% | 223 | 29% |
| Philippines | 300 | 10% | 44 | 6% |
| Vietnam | 559 | 18% | 89 | 11% |
| Total | 3101 | 100% | 781 | 100% |

- From past experience and through discussions in the course of the design process, it appears a number of factors contribute to the problem (at different stages of the ADS cycle), including:

- The methods used to promote the scholarship;

- Not clearly targeting the priority sectors and Provinces in PNG;

- Limited access to scholarship information, especially in the Provinces;

- Inadequate levels of; the English language; numeracy; IT literacy; and other academic skills;

- Issues of transparency of existing ADS promotion and selection processes;

- The lack of information available on the range of courses and institutions in Australia;

- The limited nature of the existing pre-departure activities;

- Uneven levels of scholar support provided while they are studying in Australia, and

- Lack of financial support for dependants (either in PNG or in Australia).

- 3.2.2	The High Cost of the PNG ADS Scholar Extensions and Terminations

- As a result of the many Scholarship award downgrades, extensions and terminations, significant costs have been incurred in comparison to other countries. From 2004-2008, almost 300 extensions for PNG ADS scholars incurred a direct cost of AUD$7.8 million (average cost of $26,300 per extension). Some scholars who requested extensions still may not have completed their program (i.e. they subsequently had their studies and ADS scholarship terminated).

- Over the same period, there were 84 terminations, which cost the program approximately AUD$5.9 million (average cost of over $70,000 per unsuccessful scholar). From the following Table, it is apparent that PNG scholarship extensions, terminations and award downgrades have incurred a cost of around AUD$13.7 million, or approximately AUD$2.75m per year.

- Table 2: Cost of PNG ADS Variations 2004-2008

|  |  | 2004 |  | 2005 |  | 2006 |  | 2007 |  | 2008 |  | 2004-08 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Variation | Reason | # | $ | # | $ | # | $ | # | $ | # | $ | # | $ |
| Extension | Academic Failure | 10 | 377,488 | 69 | 423,804 | 22 | 801,393 | 36 | 1,225,324 | 21 | 2,026,796 |  |  |
|  | Compulsory Additional Courses |  | 0 |  | 0 |  |  | 1 |  |  |  |  |  |
|  | Institution Request |  | 97,478 | 6 | 97,484 | 1 | 194,970 | 2 | 292,463 | 2 |  |  |  |
|  | Other |  | 100,189 | 27 | 100,216 | 9 | 200,440 | 15 | 300,707 | 7 | 501,178 |  |  |
|  | Personal | 3 | 111,131 | 34 | 111,168 | 2 | 222,338 |  |  |  |  |  |  |
|  | Research Delay |  | 88,581 | 14 | 88,595 | 3 | 177,193 | 6 | 265,811 | 6 |  |  |  |
|  | Total | 13 | 774,867 | 150 | 821,267 | 37 | 1,596,334 | 60 | 2,084,305 | 36 | 2,527,974 | 296 | $7,804,746 |
| Termination | Academic Failure | 1 | 52,002 | 34 | 2,562,190 | 7 | 595,709 | 6 | 503,431 | 8 | 729,691 |  |  |
|  | Conditions Not Met |  |  |  |  |  |  |  |  | 1 | 82,651 |  |  |
|  | Excluded from Institution |  |  |  |  | 2 | 163,003 | 1 | 94,976 |  |  |  |  |
|  | Other |  |  |  |  | 1 | 84,001 | 3 | 123,676 | 2 | 114,965 |  |  |
|  | Personal (Withdraw) |  |  | 9 | 301,214 | 2 | 142,484 | 3 | 174,691 | 2 | 59,066 |  |  |
|  | Third Party Request |  |  | 1 | 10,084 |  |  |  |  |  |  |  |  |
|  | Visa Change |  |  |  |  | 1 | 97,394 |  |  |  |  |  |  |
|  | Total | 1 | 52,002 | 44 | 2,873,489 | 13 | 1,082,591 | 13 | 896,773 | 13 | 986,372 | 84 | $5,891,227 |

- In addition to the direct costs, a large number of PNG scholars had their award downgraded (reduction from PhD to a Masters or from a Masters to a Graduate Diploma). These lesser qualifications also represent an opportunity cost for the individual and for PNG.

- Anecdotal evidence indicates that there are a number of academic and family related factors associated with high rates of extensions, downgrades and withdrawals for PNG scholars. High incidences of extensions and withdrawals indicate that it may be appropriate to invest additional resources earlier in the scholarship cycle (i.e. in PNG), rather than expending large amounts of funding in Australia on extensions and terminations.

- 3.3	Other Lessons Learned

- The following lessons have been learned through Australian and NZ scholarship programs:

- 3.3.1	Problems Caused by Extended Time away from PNG

- While many wish to study full time in Australia or NZ, experience indicates extended time spent away from PNG has disadvantages, including:

- Many people such as women and people with a disability, or those from other marginalised groups, are deterred from applying;

- Currently, Scholarship awardees in the Public Category leave their employment for a lengthy time, with no guarantee that they can go back into their position (or any other position) in the organisation, despite gaining initial support from the employer. There is potential for the scholar to be alienated on return by managers and colleagues, thereby losing confidence and motivation to bring about any reform in their workplace;

- Splitting PNG families can create significant social problems (including domestic violence), during study in Australia or NZ, and on the scholars’ return;

- Scholars comparing conditions in Australia or NZ with PNG can become discontent and seek to leave PNG as soon as possible, not contributing to the country’s development; and

- Scholars who take their family to Australia need to survive on the stipend that only contributes to an individual’s living expenses. They experience financial difficulties which then impacts on their studies. Similarly, scholars who decide not to bring their dependants still carry the burden of supporting them and their Wantok.

- The Scholarships PNG design incorporates strategies and activities that will enable PNG scholars to be more aware of the impact their prolonged absence from PNG may have on their personal and employment situations. Regular 3-monthly contact will be maintained with the scholars while they are studying in Australia or NZ. The PNG scholars will also be encouraged to maintain ongoing contact with their families and employers in PNG.

- 3.3.2	The High Age Profile of PNG Scholars

- Currently, the age profile of the PNG ADS scholar cohort is relatively old, with almost half aged 30-39 and another 37% aged 40-49. These prospective scholars are also more likely to be parents in mid-career with extensive family responsibilities.

- The older age profile appears to have an impact on the scholar success rate, as well as the length of time they have to contribute to the development of PNG on their return. There is scope to remove or modify existing restrictions on the required length of employment, as part of a strategy to attract a younger cohort to apply.

- 3.2.3	Problems when Public Scholars Return to PNG

- Experience indicates there are often problems associated with the PNG scholar’s reintegration into their family and workplace on return. The public sector in PNG is relatively fragmented, with high vacancy rates and frequent movement, demotion or redeployment of staff. Reintegration of the Public category scholars back into appropriate positions has been a challenge for many when they return. Within an uncertain GoPNG environment, the reintegration of scholars (after years spent in Australia or NZ) can lead to isolation within the organisation and inability to make positive change to either work processes or in any policy development or forward planning.

- There is also little contact between the scholar, the Facility, AusAID or NZAID at the time of the scholars’ return, unless it is through the PNGAAA or the PNGNZAA. There needs to be increased effort to maintain engagement with scholars when they return, in ways that strengthen their links with Australia, NZ and with their Scholarship peers across PNG.

- 3.4	Issues and lessons learned from AusAID Australian Leadership Awards (ALAS) Scholarships and Fellowships (ALAF)

- ALA Scholarships and ALA Fellowships programs are managed as regional programs from Canberra. The ALA program aims to develop leadership, partnerships and linkages within the Asia-Pacific region, and to target high calibre individuals who are leaders (or potential leaders) and committed to sustainable development of their country and region.

- The ALA program funds postgraduate studies at Masters or Doctoral level in Australia, with additional leadership development programs for scholars provided while studying in Australia. For ALA Fellowships, Australian organisations submit proposals of varying duration, structure and content, including hosting the international Fellows, rather than individual Fellows applying for ALA Fellowships.

- There have been a total of 486 ALA Scholarship recipients from all countries, with 51 variation requests to date. Table 3 indicates the problem facing the PNG ALAS is not variation or withdrawal, but low numbers of applicants and subsequent awards, in relation to other countries. PNG receives less than 7% of the available ALAS, which represents a missed opportunity. In past years, there have only been 7- 15 successful PNG applicants for ALAS each year, compared to a possible number of 20-25.

- Table 3: ALA Scholarship Variations for ten countries, 2007-2009

| Country | Total Scholarships | % Total Scholars (486) | Total Variations | % of Total Variations (51) |
| --- | --- | --- | --- | --- |
| Indonesia | 77 | 15.84% | 8 | 15.69% |
| Bangladesh | 54 | 11.11% | 8 | 15.69% |
| Vietnam | 52 | 10.70% | 7 | 13.73% |
| Philippines | 34 | 7.00% | 4 | 7.84% |
| PNG | 33 | 6.79% | 3 | 5.88% |
| Nepal | 27 | 5.56% | 0 | 0.00% |
| Sri Lanka | 23 | 4.73% | 1 | 1.96% |
| Mongolia | 20 | 4.12% | 3 | 5.88% |
| Cambodia | 19 | 3.91% | 0 | 0.00% |
| Laos | 18 | 3.70% | 1 | 1.96% |

- Increased profile and advocacy is required to raise the number of applicants and (subsequently) the number of ALAS awarded in PNG. In addition, it is proposed to provide an IELTS test earlier in the ALAS cycle, so that any applicants who do not have the required score of 6.5 can be removed from further selection consideration. The quality of ALAS and ALAF applicants will also be closely monitored to determine whether additional support can be provided to bring highly regarded applicants up to a competitive standard.

- Effort will be required from the Facility to support the ALA program, including to AusAID Post. This includes raising the general awareness of opportunities afforded under the ALAF, and encouraging the participation of highly qualified and respected Papua New Guinean men and women to participate in ALAS opportunities.

- 3.5		Issues and lessons learned from NZAID Scholarships

- NZAID have engaged a MC for the past four years to manage the pre-award phase for the NZDS Public Scholarships primarily to ensure that efficiency and effectiveness is maintained in processes and timetables. For the NZDS-Public Scholarships, additional attention is required to aligning priority sectors and key agencies with the NZAID PNG program. The MC has provided a central point for all the NZDS-Public partners to develop a transparent and equitable system alongside achieving targets on an annual basis. Liaison between NZAID and the MC is necessary for monitoring of outputs and to maintain quality outcomes.

- For NZDS-Open the use of an MC and input from the GoPNG is particularly beneficial for processing the requirements of the pre departure phase. NZAID pays significant importance to contacting successful candidates and providing advice on their required procedures.

- IELTS testing was initially introduced as part of the pre-award process of NZDS-Public Scholarships to determine the level of English in a candidate and identify contributing factors to successful academic performance. Prior notice of an applicant’s low English proficiency allows the selected NZ Institution to propose an appropriate bridging course to address deficiencies as part of initial academic programs.

- Under the NZDS-Public scholarships, interviews provide an opportunity for a closer review and assessment of candidates in relation to their academic suitability; relevance of their course; personality profile and background. Interviews also provide applicants with an opportunity to reflect on their expectations of studying overseas, enables discussion in relation to the ideal reintegration back into PNG, as well as their long term objectives.

- The absence of the scholarship interview component in current procedures for NZDS-Open requires NZ Universities to address deficiencies during the study program, which could be more effectively addressed in PNG (e.g. dependency status, employer endorsement, information verification).

- 3.6	Lessons Learned from the Regional Development Scholarships (RDS)

- Australian and New Zealand Regional Development Scholarships (NZRDS) are offered (as a joint program) to people from the Pacific to study at Pacific tertiary institutions in PNG, the Solomon Islands, Vanuatu, New Caledonia, Fiji and Samoa. Scholars studying for particular professions (medicine, legal studies) are expected to complete the practical training in their own country. Generally entitlements cover a return airfare from the scholar’s home country to PNG, academic and other compulsory fees, an establishment allowance and a living allowance paid fortnightly. In some countries the living allowance may be paid at a higher rate when the student is joined long term by one or more family members.

- Experience indicates many regional scholars are young, from smaller Island nations, where they are unfamiliar with the serious security or geographical constraints that exist in many parts of PNG. There are instances where the entry papers to PNG are delayed, causing problems for logistics and the management of the scholars’ study program.

- Ongoing welfare of RDS recipients who travel to PNG to study is largely the concern of the host institution, although the Scholarships PNG Facility has a clear obligation to look after the welfare and safety of the male and female students, especially when they first arrive. This includes meeting on arrival, arranging all documentation, and monitoring their welfare, security and travel arrangements. The Facility will also arrange the arrival (and departure) connecting internal flights as well as pay the stipends and initial accommodation.

# 4	PROGRAM DESCRIPTION

- 4.1	Overview

The goal for this Program is: contribute to equitable economic growth and poverty reduction in Papua New Guinea by the development of highly skilled men and women who are able to apply their professional and technical expertise, experience and leadership skills in the workplace and in society.

- The Program comprises two components:

Component 1: (Australian and New Zealand) Scholarships to PNG

Component 2: PNG Professional Development Initiatives

- The Scholarships PNG will address shortages of qualified, skilled Papua New Guineans with expertise that can be applied in both government and industry. Cross-cutting issues of gender and HIV and AIDS will be mainstreamed at commencement of the Facility and throughout implementation.

- To accommodate the additional promotional and advocacy initiatives under the Scholarships PNG, as well as to alleviate last-minute “bottlenecks” for scholar Visa for Australia and NZ, the scheduled scholarship timing for Scholarships PNG will differ to that used for PATTAF. Scholarships will open earlier (i.e. in November) and be accepted until March the following year. Interviews will be completed in July with offers sent in early September, with the cut off date for acceptance in late October. The PDB will be conducted in November with Visa processed in time for mobilisation early in the new academic year.

- Details of the key dates are included with the Detailed Description of ADS, ALA, NZAID and RDS Scholarship Management Processes and Facility Responsibilities, included as Annex 8.

- The following diagram (Fig 1) outlines the structure of the Scholarships PNG program and how the initiative aligns with the GoPNG planning and HRD initiatives as well as embedding the broader themes of Partnerships, Cross Cutting issues and Aid Effectiveness.

GoPNG Medium Term Development Strategy

Goal:

Foster sustainable improvements in the quality of life of all Papua New Guineans by ensuring good governance, adopting an export-driven economic growth strategy, and promoting rural development, poverty reduction and human resource development.

The AusAID PNG Country Program Strategy

and

the NZAID PNG Country Program Strategy

Component 1: Australian and NZ Scholarships to PNG

The Scholarship Program:

Provides men and women with the skills and knowledge to contribute to PNG’s economic and social development within the priority areas of National and Provincial governments.

Provides men and women with the skills and knowledge to contribute to PNG’s economic and social development within the private sector and civil society.

The individual GoPNG agency / private sector / NGO / CSO HRD plans

Partnership

Jointly developed priorities and sectors

Joint decision making through Joint Steering Committee and via the scholarship selection processes

Clear emphasis on transparency and Value for Money

Cross-Cutting

Gender Equality within (and across) all activities

Support for people with Disabilities

Pro-active support to reduce impact of Provincial isolation

Support for HIV mainstreaming and research to reduce HIV risk and vulnerability

Aid effectiveness

Cooperative Program Design between AusAID and NZAID

Reflects the Partners major role in supporting PNG human resource development

Australian and New Zealand contribution to PNG human resources: Scholarships PNG

Goal: contribute to equitable economic growth and poverty reduction in Papua New Guinea by the development of highly skilled men and women who are able to apply their professional and technical expertise, experience and leadership skills in the workplace and in society

Component 2: PNG Professional Development Initiatives

The initiatives:

Empower young women and men to actively participate in the development of Civil Society.

Strengthen identified professional bodies to provide to their membership opportunities to develop skills and knowledge essential to achieve best practice in the operation of PNG industry, CSOs, NGOs and government.

Strengthen the capacity and profile of Australian and NZ Alumni in PNG.

GoPNG Agency Re-Integration Planning for Public Scholars

GoPNG Long Term Development Strategy

GoPNG National Strategic Plan

Figure 1: Alignment of the SPNG with Partner Structures

Underlying Design Themes

SPNG Program Contribution

PNG Partner Policy Framework

- 4.2	Component 1: Australian and New Zealand Scholarships to PNG

- AusAID and NZAID scholarships provide PNG with returned scholars who have technical and leadership capability to make personal and institutional contributions to development the country. The Scholarships program will be managed in a way that encourages maximum opportunity for eligible men and women, as well as maximum benefit for PNG when scholars return. This implies a management approach that seeks to identify and mobilise the best applicants, taking account of gender equality in relation to both the numbers and the fields of study.

- Selection will be based on agreed PNG priorities, the merit of the candidate and the potential for a positive development outcome in the future.

Objective 1	To provide men and women with the skills and knowledge to contribute to PNG’s economic and social development within the priority areas of National and Provincial governments.

Objective 2	To provide men and women with the skills and knowledge to contribute to PNG’s economic and social development within the private sector and civil society.

- 4.3	Proposed Changes to PNG Scholarship Management

- The following sections provide clarification on new approaches, changes and expectations for the PNG Scholarship programs, to enable the scholarships to achieve greater transparency, equity, focus, effectiveness and ultimate impact. Improving Scholarship success rate (in outcomes and achievement) requires better targeting, selection and management. The demonstrated success of past and present women scholars will be also reflected in the future allocation of a minimum of 50% of scholarships to women. Scholarship management processes include the following:

- 4.3.1	Targeting Scholarships to Match PNG Human Resource Priorities

- The two categories of Scholarships will remain. They are Public (for applicants from GoPNG departments, agencies or statutory bodies) and Open (for applicants from the private sector, faith-based organisations, NGOs, Civil Society Organisations (CSO) or those who wish to pursue a qualification without GoPNG sponsorship).

- The new Scholarship program will move away from a rigid 50-50% split between Public and Open categories and provide the Selection Panel with more latitude to select on the basis of merit, rather than on fixed percentages. There will be a minimum 30% allocated to the Public Category. For this category the relevant GoPNG agencies, AusAID Post and NZAID Post will jointly identify priority skills areas and develop the preferred Scholar Profiles. Applicants in the Public category will need to nominate a Bachelor or postgraduate degree in that field of study, as well as a written commitment by their employer, confirming that there will be an appropriate position for them on their return.

- Over time, the use of Profiles will create an identifiable cohort of men and women scholars in the priority areas who specialise in technical/professional areas of importance to the country. The cohort will be encouraged to maintain contact with each other, providing mutual support during their scholarship program in Australia or NZ, as well as after their return to PNG. For example, an annual gathering of the cohort may be organised at a particular university, to strengthen personal and professional bonds and establish a larger group that, on their return to PNG, can facilitate mutual support as part of initiating change. Scholars will also be encouraged to maintain contact with their employers.

- For the Open Category the National Training Council (NTC - representing GoPNG), the private sector, CSOs and the Partners will agree on priority areas. These are likely to be broader than those developed for the Public category and will also be developed into Preferred Scholar Profiles. Preference will be given to those applications that match priority areas, although all applications will be considered for overall merit.

- After the consultation process for setting the Profiles is completed (October) AusAID and NZAID will provide the Facility with the target Scholar Profiles for use in the upcoming round of scholarships, as well as the minimum target percentage of the Scholarships to be allocated to each Scholar Profile. A sample template for the PNG Priority Sectors is included as Annex 6.

- Scholarship Profiles and target numbers/proportions will be included in Scholarships PNG scholarship promotional materials and used as part of determining the selection criteria. The aim is to better align Scholarship opportunities to those PNG employment sectors and agencies with high priority HR needs. The Profiles will reflect PNG priorities, including in relation to focus of studies and potential development impact. The Joint Steering Committee will confirm what Provinces may be given priority in the upcoming round, based on Partner needs.

- 4.3.2	Increased Promotion of Scholarship Opportunities

- To improve advocacy and profile of Scholarship opportunities, the Facility will develop a targeted PNG Scholarship Promotion and Communication Plan within 3-months of contract commencement, for approval. The communication planning will involve liaison and planned advocacy to central agencies, sub-national agencies, universities, research institutions, private sector associations, faith-based organisations, CSOs and NGOs and professional associations. The promotion strategies will take into account the proposed Scholarship profiles, specific approaches and methods to identify women who can participate, as well as opportunities for those people with disabilities.

- Communication and advocacy methods involve working with DPM and NTC, using their networks to alert stakeholders and potential candidates. Working with Partner agencies and stakeholders, the Facility will provide and distribute concise information and advice on eligibility, as well as how and when to apply for Scholarships. Where appropriate, separate Scholarship information sessions will be held for women, i.e. through accessing local or national PNG women’s groups.

- By 15th October each year, the Facility will develop an annual Calendar of Scholarship Key Dates for the upcoming cycle, providing targets and deadlines for selection and preparation of scholars, communicated to all key stakeholders. Using Scholarship Profiles for Public and Open categories, promotion of Scholarships is specific and targeted, equipping potential applicants with sufficient information to self-determine whether their application would be competitive.

- Information sessions will also be conducted in the major Provincial centres, with a view to increase the number of Provincial applications and awards. The increased focus will include advice to potential candidates on the required eligibility criteria, the selection criteria, Scholarship application information and required documents to be submitted.

- 4.3.3	New Scholarship Application Form

- A new (Australian and NZ) Scholarship application form will be jointly developed, with Facility support in drafting the format. The form will be simple, have no ambiguities or inconsistencies, reflect the agreed HR priorities of PNG and be widely available. The forms will identify the specific information required and where any employer endorsement is necessary. The forms will also be required to include the information that is required by Australian and NZ tertiary institutions in relation to their course admission criteria.

- Application forms for the Public category will require endorsement from relevant GoPNG Departments/Statutory Authorities if a candidate wishes to return to GoPNG employment. The endorsement must be from a staff member with organisational authority to confirm the Department or Agency supports the Scholarship candidate. Employers will also be encouraged to develop an agreed Reintegration Plan back into the organisation or sector. If required, assistance will be provided by the Facility for short-listed applicants to draft and clarify their Reintegration planning.

- Applications in the Open category will only be required to provide professional/personal references from a previous or current employer, rather than approval to apply. Open and Public candidates will nominate on the application form a field of study and level of award, rather than a specific course. After interviews have been held, specialist academic advice will be made available, via the Scholarships PNG Facility, in order that the candidate can make an informed choice on the most appropriate Australian or NZ university or institution to study.

- 4.3.4	Receipt of Scholarship Applications

- Concerns have been expressed about the way the Scholarship application process works. Public perceptions of Scholarships as merit-based, fair and equitable are a crucial aspect to the integrity of this program and existing methods will be refined so that the application process is stronger, more resilient, transparent and fair to all eligible applicants.

- Currently the ADS applications and expressions of interest are forwarded to either the home agency (Public category) or the National Training Council (for Open category), where processing places a large burden on the limited agency staff resources. The PATTAF only receives applications once they have been processed by the GoPNG agencies, so there is no consolidated data on the total number of applications originally received, where they came from, the sectors, or the applicant profile (age, gender, Province). This lack of information severely constrains any evidence-based decision-making on how and where to target resources for better advocacy and targeting of Scholarships.

- NZAID recently initiated a process for receipt of all scholarship applications at the managing contractor’s office, which will be adopted by the Scholarships PNG.

- The Contractor will receive and receipt all scholarship applications at the Scholarships PNG office, enabling the Contractor to record relevant data into a comprehensive database, and provide a full profile of the cohort applying for Scholarships each year. Applications will close on the 31st March. By the end of April, the summary data and complete list of eligible candidates will be provided to all Partners, after the initial compliance and document checks have been completed by the Contractor. Public category applications will be distributed to on the 1st May to the relevant GoPNG agencies, while PNG university staff applications will go to their home institution for comment or endorsement. By the 1st June the verified applications will be returned by the agency to the Contractor, and subsequently provided to all members of the independent Selection Panel for the short-listing.

- For those living outside National Capital District (NCD), the public mail system from provincial PNG can be unreliable. At up to six designated Provincial centres, the Contractor will make arrangements for the Scholarship applications to be couriered from the Provinces to the Scholarships PNG office. This will happen on a specific time and day, with candidates expected to provide their completed, sealed application documents to the courier’s agent at a specific time and location. At that time the courier will acknowledge acceptance of their application via a numbered recept. On the designated date, the provincial applications will be couriered to the Scholarships PNG office, where all courier receipt numbers will be recorded and the application accepted by Scholarships PNG.

- Each Scholarship application form will incorporate a section to be completed by each candidate at the time of filling it in. The section will have the candidates’ name and address and be suitable for easy detachment and placement in the mail. This section of the application form will be immediately detached once it has been received by the Contractor’s staff at the Scholarships PNG office. The “tear off” section will be immediately mailed back to the applicant’s nominated address. This new feature ensures that receipt of all Scholarship applications is acknowledged, with each candidate provided with written confirmation (via the mail) that their application was received

- 4.3.5	Membership of the Scholarship Selection Panel (for ADS and NZAID Scholarships)

- The Selection Panel is quite separate from the Joint Steering Committee and also independent of opinions or inputs of Scholarships PNG Facility staff. The Selection Panel will comprise nine members to reflect broad PNG stakeholder interest, while also providing academic input into the selection process and will incorporate inputs from a PNG CSO and the Facility will support this independent Selection Panel through a role as secretariat. The Selection Panel consists of:

  - Representative from both AusAID and NZAID Posts;

  - A representative from the three key GoPNG agencies (NTC, DPM and DNPM);

  - A PNG and an Australian / New Zealand academic;

  - A representative from a PNG CSO and one from the PNG private sector.

- It is also recommended that the Joint Steering Committee consider having one of its members nominated to the Selection Panel, on a rotational basis. In this way, there will be a strong link between the leadership group of the Scholarships PNG and the important selection phase.

- The Selection Panel will be balanced by gender and reflect interests and perspectives of PNG women. Broadening the Selection Panel will increase objectivity and transparency of the selection process, providing wider stakeholder involvement. All members of the Selection Panel will be expected to sign a Code of Conduct that reiterates expectations of good governance, gender equality and transparency and provides operational mechanisms to deal with conflict of interest issues. The Code of Conduct will be developed by the Facility and approved by the Joint Steering Committee.

- The Partners will review and endorse Selection Panel member nominations before the Facility enters into any contractual arrangements. Selection Panel members will be expected to have IT skills, as Scholarship information may (in future) be viewed and downloaded from OASIS (the ALA Scholarships online information system).

- It is unrealistic to expect Selection Panel members to be available full time, for two consecutive weeks. The Facility will provide the Selection Panel with a secure, lockable work area and secure storage within the Scholarships PNG Facility office for their use, working independently from each other (day or evening) to review Scholarship applications, make notes and record comments.

- There will be a master copy of each Scholarship application and a master list. Selection Panel members will have access to all eligible applications to read in this secure environment, spending time before formal Selection Panel meetings to consider and rank applications. When Selection Panel meetings are held, they will be shorter and enable members to discuss and compare scores and comments (rather than all Panel members reading the applications at the same time). The Facility will support the Panel’s logistical and organisational needs.

- The Facility will make local arrangements that provide a better environment for women and people with disabilities who attend briefings or interviews. This could (for example) include the ad-hoc provision of child care for women applicants at interview; providing easy access for the disabled; as well as a secure physical location for those waiting to be interviewed or counselled. All of these measures are meant to have the Scholarships PNG Facility provide an accommodating, welcoming environment that reflects the day-to-day needs of the applicants.

- 4.3.6	Introduce Interviews into Scholarship Selection

- The task of individually interviewing over 220 short listed Australian and New Zealand Scholarship applicants plus reserves would be excessive but it is considered essential to introduce a form of interview process to enable Selection Panels to gain some information and insight into individual candidates. It is proposed that around 220 short-listed candidates will be interviewed, leading to an offer for around 160 Scholarships plus a reserve list of around 30. Interviews will be conducted in groups of up to six, with two members of the Selection Panel at each interview, using the opportunity to gain an understanding of the individual’s capacity, interest and potential.

- Interviews will be structured in ways that require all candidates to make some statement, followed by a group discussion based on a contemporary topic provided by the Panel. As part of the interview process and discussions, the Panel will make assessment of the personal attributes and ability of candidates, especially in relation to their suitability to undertake the scholarship

- Small-group Scholarship interviews will be immediately followed by a short written piece of work from each candidate, which will summarise the group discussion at interview. This written piece of work is designed to provide insight into each of the candidate’s capacity to summarise a discussion and express this in English. The written summary will be completed under supervision and form part of each individual’s selection process. Final decisions on who will be awarded a Scholarship will be made after this process is completely finished.

- Conducting small-group interviews and the subsequent written work has been successfully applied in other PNG scholarship selection procedures and provides a balanced compromise between the very large numbers of applicants involved against the desirability that the Selection Panel engages directly with each candidate.

- While the majority of interviews will be held in Port Moresby (where in the past most candidates lived and worked) the Selection Panel members will also travel to those Provinces and centres with a significant number of short-listed candidates. This process will ensure those living in the Provinces also have a good opportunity to present their case at interview.

- 4.3.7	Introduce English Language Testing for Short Listed ADS Applicants

- As mentioned elsewhere, the NZAID scholarship program requires candidates to undertake an IELTS test, as part of meeting NZ university entry requirements (as well as planning for the Introductory Academic Program on arrival in NZ). There is no similar data available in relation to the academic English language capacity of ADS candidates. Australian universities have reported that PNG scholars’ English language proficiency is often not of sufficient standard to successfully complete their studies within the required timeframe. Individual Australian institutions each approach academic English language requirements and capacity of PNG scholars in a different way, including provision of special language tuition and/or including English language in the Introductory Academic Program (IAP) as many have need for additional language training. Support measures are often reactive, only responding to scholars’ English language capacity well after problems have commenced.

- At the time Scholarship interviews are held, all short-listed ADS and NZDS candidates will take an IELTS or similar diagnostic test and be informed of their results or scores. Having this information will provide each ADS scholar with opportunity to reflect on whether they should defer pursuing the scholarship until they have improved their academic English skills. For all successful candidates, their test results will also be provided to Australian or NZ universities, forming part of the information each institution uses when considering what support programs they need to provide to individual PNG scholars.

- The IELTS test will be organised and paid for by the Facility. This English language data will not form part of the ADS selection process, although it is a part of NZDS selection criteria. Rather, for ADS the test should be considered as a diagnostic tool that will be used to gather important information, on an annual basis, in relation to the academic English language profile of the PNG Scholarship cohort. The results for each scholar will also provide important information for the Australian university that they will attend.

- 4.3.8	Academic and Pastoral Advice to Scholarship Candidates

- Under existing arrangements, candidates are required to select a course and Australian or NZ institution very early in their scholarship application process. Once it has been nominated and recorded, the choice of academic institution or course cannot be easily altered. These early choices of course and institution have been decided with the candidates having limited access to academic information or specialist advice, especially for those in the Provinces.

- Under the Scholarships PNG, the proposed additional academic advice provided to short-listed candidates will make information available in order to encourage informed decision-making for the course and the institution. This advice should also take the candidates’ family circumstances into account and also the cost of living implications of the urban centre where the proposed Australian or NZ institutions are located

- Scholarships provide an opportunity to better support Papua New Guinean women (and their families) to achieve a better future, so the additional academic support will also take into account the increasing demand for highly skilled staff across the PNG resource industries and highlight where opportunities exist for women to undertake relevant courses / certification. Anecdotal evidence suggests that PNG women are well underrepresented in highly skilled (and paid) positions in the resources sector.

- Many ADS course variations, downgrading, withdrawals and extensions could also be partly due to candidates having to choose a course and a university at a very early stage in the process, especially when they do not have in-depth knowledge about course or university options. To ensure better choices are made, a candidate’s final choice of course and institution will only be required after interviews are completed. At that time, the Facility will provide qualified academic staff; discussion / research space; appropriate internet facilities and other relevant course / institutional resources. These will be used to provide advice and information on appropriate Australian and NZ universities and courses. Having received this academic advice and support, prospective PNG scholars will then be in a much better position to nominate a course and institution that aligns with their area of interest, suited to their employer (where applicable), and clearly within agreed development priorities.

- Through enhanced information and more informed choice, the scholars’ Australian or NZ study experience will be improved. Academic context and support networks are crucial in early days of commencing study in a foreign country. If scholars are placed in the most appropriate Australian or NZ University, enrolled in courses that best meet their professional and personal requirements, it can be expected they will settle in easier, with reduced levels of stress and uncertainty. It is also proposed that scholars be given the option to consider universities where the course includes some form of work experience.

- 4.3.9 Pilot 10-Month Foundation Course for Provincial Candidates who almost make Selection

- Anecdotal evidence suggests that each year a number of unsuccessful applicants would have a strong chance of being competitive in the Scholarships PNG selection process with targeted academic support. Many of these appear to be from PNG Provinces, having less access to Scholarship information and also lower English language skills than their peers in NCD.

- After the 160 scholars have been selected, and an additional reserve list of 30 identified, the Facility will examine the next ranked applicants who live and work in the Provinces.

- Based on information received in applications and Selection Panel recommendations, the Contractor will produce a list of 25-30 of the (unsuccessful) Provincial applicants who met the required criteria but were not successful in the competitive selection process. The Contractor will summarise where these Provincial applicants did not perform well, to be used as a guide in identifying the type of support that will increase their chance of success. :

- Through evidence of current employment (including unpaid or volunteer work), they live and work in Provincial PNG;

- Potential to make a significant development impact in their Province or their agency; and

- Willing to undertake a 10-month full-time residential course in PNG, in order to increase their academic skills, knowledge and English language capacity.

- On completion of the Scholarship interview and selection process, any of the reserve lists who were not subsequently selected (and who also fulfil the above Foundation Course criteria) would be added to the list of potential Foundation Course awardees.

- As part of the selection process in 2010, the initial cohort for the first pilot Foundation Course (i.e. those initially identified plus from the Scholarship reserve list) will be reviewed by the Selection Panel and a priority list developed for endorsement by the Joint Steering Committee. This process will identify the key areas of learning and skills to be addressed through the Foundation Course, including underlying themes to be addressed (IT skills; language; numeracy etc). Once the composition of the Foundation Course group has been established (i.e. 25 + 5 reserve) the Facility will then seek tenders to develop and provide the 10-month Foundation course, delivered at a PNG university from the beginning of 2011.

- The PNG University selected to deliver the Foundation Course will need to demonstrate it can provide a program that will meet specific skills needs and that it will be offered in safe, convenient family-friendly residential facilities. The university will also need to demonstrate that it has excellent teaching staff available, with strong English language capacity and ongoing access to the appropriate facilities.

- The profile and needs analysis of the Foundation Course cohort will be used to develop the curriculum, covering basic academic English, numeracy skills, study skills, IT skills, time-management, gender awareness, HIV and AIDS awareness and personal / domestic skills applicable in the Australian or NZ context. There will also be interactive workshops used (for example) to identify the major issues of reintegration (personal and professional) and where and how organisational development takes place.

- There are relevant examples of the successful use of Foundation courses that help prepare potential scholars for entrance to higher levels of study. These include the highly regarded Foundation program offered for students from across the Pacific through the University of the South Pacific (USP), as well as the Foundation Year offered at the National University of Samoa. As part of the Facility preparing the Foundation Course Scope of Services and tender documentation, close attention will be paid to the USP Foundation program to identify what structures, lessons learned and content could be relevant for the Foundation Course.

- The contracted PNG University will also be required to provide secure, adequate support facilities for the Foundation Course cohort, including for child care (where required) as well as being accessible for those with disabilities.

- At the successful completion of the Foundation Course, participants will be provided with an accredited award from the PNG university, indicating the level of course, the topics and areas covered. The Foundation Course completion will signify the end of the direct support for that Provincial cohort of potential scholars. Successful Foundation Course graduates will be in a much stronger position to apply for an Australian, NZ (or other donor) scholarship if they so choose in the following year(s). Alternately, if they decide it is not practical to consider study outside PNG, they can return to their Provinces with greatly increased knowledge and skills.

- 4.3.10 Allocation of a Proportion of Scholarships for the PNG Higher Education Sector

- A proportion (10%) of Scholarships PNG Scholarships will be allocated to support strengthening of PNG universities and public research institutions. These would be available to senior and emerging managers for institutional development, as well as to teaching and research academics. In direct support of institutional development, Scholarships for senior managers would cover HRD within the HE sector, including universities, public research institutes, CHE and OHE. Fields of study could include: financial management, IT and communication technology, knowledge management, managing diversity, leadership, management (in particular HR and project management), planning, QA, administration, policy development and facilities management.

- To strengthen the quality of education and of research capacity, Scholarships for PNG academics would focus on university teaching and research staff (including research staff in public research institutes) for upgrading of qualifications, in particular obtaining research qualifications. Leaders or potential leaders in the PNG HE sector could also be identified and encouraged to apply for ALA Scholarships.

- Current PNG university academics and junior researchers from research institutes be considered to undertake PhD programs. This will ensure that research skills gained from the very expensive four years in Australia or NZ are utilised to increase research capacity on their return to PNG.

- Individual applicants from the HE sector will be required to ensure their proposed course and qualification aligns with priority development areas documented within their own institution. Research awards that address cross cutting issues (for example increasing women’s access to non-traditional qualification, careers and employment; or limiting the spread of HIV + AIDS) would be encouraged.

- 4.3.11 	Removal of the TVET Level Scholarship Awards

- The Scholarships PNG will no longer include scholarships that involve scholars undertaking TAFE-level awards or sub-degree awards in Australia or NZ. The emphasis will be on tertiary degrees and the gaining of knowledge and skills that can be applied back in PNG.

- 4.3.12	Extend the Pre-Departure Briefing (PDB)

- The high level of Scholarship award downgrades, withdrawal rates and number of extensions indicate the need for prospective scholars to receive more extensive academic and study advice. This increased information should be included as part of Scholarship promotional activities, through the direct academic support provided by the Facility as part of the course and university selection, as well as advice through Pre-Departure Briefing (PDB).

- It is proposed the PDB program be extended from 3 days to two weeks, and comprise all scholars approved for Australia and NZ. The PDB be held in a secure, residential university environment. The scholars will all be required to attend every skill building session, briefings and the group discussions. Importantly, the PNGAAA and the PNGNZA will be involved in the PDB to provide advice and an expanded network for scholars. The residential PDB venue will have access to local child-care facilities for women scholars accompanied by children.

- The PDB venue will also ensure any scholars with disabilities are catered for (access to facilities and delivery methods used). During the initial 11 days, all scholars will have intensive instruction in key skills areas. All members of the cohort will be tutored and assessed on the following:

- Information and communication technology, including basic understanding of e-mail, use of internet and use of computers in study, including accessing on-line summaries of course units, degree programs and methods of teaching;

- Basic concepts in student time management, importance of meeting deadlines and understanding the penalties for being late, and support mechanisms available;

- Australian and NZ university expectations for presentations, reading and reviewing literature, assignments and management of data and the standard of academic English; and

- Law and culture of Australia and NZ.

- As part of the PDB program, the provider will also:

- Facilitate each scholar to make email / web-based contact with their university in Australia or NZ, initially with the international student services section. This includes discussion on finding details relating to: being met at the airport on arrival; local accommodation costs and options; local transport options to and from the university; banking and other financial arrangements that are in place; health cover while in Australia or NZ; as well as those frequent questions and problems faced by new scholars;

- Introduce all scholars to the Australian and NZ university policies, which include a zero tolerance for sexual harassment, or for any form of violence and discrimination. This includes the need for PNG scholars to report any instance of violence or harassment. The importance of PNG scholars making themselves aware of university policies will be stressed, including case examples and penalties, as well as instances where non-compliance has led to poor outcomes for the scholar and institution (including termination). The universities will provide this information again when the scholar arrives, before they commence studies.

- The course of study in Australia or NZ happens within a culturally foreign living and learning environment, while at the same time having a direct impact on the scholar’s family relationships. To address these concerns and potential problems, scholars’ spouses and children will be included in the final three days of the PDB, also funded by the Facility.

- For the final three days of the PDB, the scholar’s spouse would be invited to join activities, with specific sessions to further explain and discuss the impact that an overseas scholarship can have on PNG families. These sessions would include:

- Impact of prolonged absence (risk, testing, treatment related to HIV and AIDS);

- Impact of taking family members to Australia on their study, accommodation, finances;

- Opportunities for work experience or attachments in Australia or New Zealand;

- Opportunities for employment in Australia or NZ during the Scholarship program;

- Discussions of cross-cultural issues and an overview of the legal environment;

- Basic computer literacy and accessing information via the internet;

- Life skills, including cooking, cleaning and budgeting.

- Where appropriate (and agreed with those involved), departing Scholarship awardees will be provided with the email and contact details of returned scholars who previously studied at the same university, so they can be contacted for specific information. In addition, recently returned scholars from Australian and NZ universities will provide PDB inputs, enabling departing scholars to receive information on living, transport and study aspects of the Australian or NZ city and university context.

- The Facility, in liaison with the PNGAAA and the PNGNZA, will produce a Code of Conduct, provided to every departing scholar and explained in detail during workshops and discussions. There will be no ambiguity or any misunderstanding of what is expected in Australia or NZ. Employers have expectations of being informed of the progress. For any variations to a study program or length, each scholar will need to inform their employer.

- 4.3.13	Improvements to the Reintegration of Returning Scholars

- At the time of applying for the Scholarship, candidates in the Public category will be required to provide a broad summary of how their scholarship will strengthen their organisation and assist in its ongoing development, including the development of a brief draft Reintegration Plan. Both Open and Public candidates would be expected to outline at interview (in general terms) how, on their return, they would approach reintegration into the GoPNG workforce.

- Once a Public candidate is shortlisted with the support of an employer (i.e. they have employment on return) the candidate and employer will develop a short, concise Reintegration Plan, jointly signed. The Reintegration Plan will indicate how the scholar will come back into the organisation at the completion of the award. The Reintegration Plan would link the current employment to the planned course of study and the expected role on return to PNG. It would place the scholar’s career and academic aspirations in the context of the Human Resource priorities of their employing organisation, as well as relating the scholar’s planned study and future employment to the specific objective(s) of this design. The Reintegration Plan, together with interviews, will provide the Selection Committee with much more information, criteria and insight than has existed in the Public category.

- The dynamic and changing nature of the GoPNG public sector leads to problems for returning scholars and (often) their agencies. High levels of staff movement, especially at senior level, results in reductions in “institutional memory” and scholars may return to a restructured GoPNG environment, where reintegration strategies are not as relevant. This changed employment is particularly likely to have a negative impact on women.

- The Facility, in liaison with PNGAAA and the PNG NZA, will pay particular attention to providing support and information on alternative employment options in PNG. The Facility M&E will incorporate indicators that identify the proportion of Public scholars who are reintegrated into GoPNG organisation on their return to PNG, with the data disaggregated as is shown in the draft M&E Framework and M&E Methods and Tools at Annex 4.

- As mentioned elsewhere, consulting or technical staff working for the range of AusAID and NZAID funded programs of assistance across PNG (i.e. assigned to specific GoPNG agencies) may also be contacted by the Facility in relation to returning scholars. These staff, already working within a GoPNG agency, are in an ideal position to work with their GoPNG Partners and to provide initial support for the returning scholars’ Reintegration plans.

- The Scholarships PNG Facility will maintain regular contact with the scholars while in Australia or NZ, with the scholars being contacted every 3 months. The telephone conversation will focus on any constraints or issues that have arisen and enable the Facility to contact the appropriate agencies / institutions should constraints emerge. The regular contact will also remind scholars they are on a Scholarships PNG funded program and there is (for example) academic assistance available from the university should there be problems in their study or other circumstances.

- The 3-monthly contact to Scholarships PNG scholars will also remind them to keep in touch with their employer (where applicable) and stay informed of the labour market in PNG. Public sector award recipients will be required to report academic progress to their employer. In the last term of the scholars’ study, the Facility will liaise with scholars’ employers in the Public category, to confirm an appropriate position in the department/agency is available. Scholars will also be encouraged and reminded to maintain regular contact with their employers, family and colleagues in PNG.

- The Contractor shall develop specific reintegration modules that address women’s reintegration issues. Such modules might target both female graduates and their employers (particularly in the Public Sector)

- PNG scholars who have resigned to undertake their award will be provided with general information about job vacancies in PNG by the Facility, as well as placed in contact with the PNGAAA and the PNGNZA. Returning scholars will have a de-briefing meeting soon after return, undertaken by a staff member and/or a member of the Alumni. Written notes of issues raised by the returning scholars will be summarised by the Facility, provided to the Joint Steering Committee and subsequently used to improve the Scholarship process.

- 4.3.14	Monitor Responsibilities of PNG Employers

- The importance of a scholar receiving GoPNG / agency support and encouragement on their return to PNG will be explained by the Contractor. If a PNG employer consistently reneges on its agreed responsibilities towards the scholar, as outlined in Reintegration Plans, the Contractor will report this in writing to the Joint Steering Committee. The Committee may choose to review the reasons why this is occurring and in extreme cases may recommend that no more Scholarships are allocated to that agency

- 4.3.15	Monitor and Facilitate, Responsibilities GoPNG Agencies, Awardees and Alumni

- GoPNG Agencies, On-scholarship awardees and Alumni all have a responsibility to provide timely data for output (e.g. selections) and M&E processes

- During the application and selection process, DPM and NTC are required to provide endorsed applications back to Scholarships PNG in a timely manner

- While on scholarship the Awardees are required to report their results back to their Public Sector employers and DPM;

- Especially in the first two to three years after return to PNG, Alumni information provides valuable indicators of scholarship effect. The Contractor shall maintain the contact details of the returned scholars wherever possible and liaise with the Alumni to encourage ongoing engagement with their peers and via the Alumni membership.

- Returning graduates will require debriefing and encouragement to join the appropriate Alumni associations;

- Under an agreement of mutual responsibility between the Scholarships PNG Joint Steering Committee, the DPM and NTC, the Contractor shall work with NTC and DPM to strengthen their scholarship database management capacity (and therefore their M&E capacity). Working collaboratively with NTC, DPM, AusAID and NZAID, the Contractor shall develop an innovative program that allows for electronic transfer of relevant Scholarships PNG scholarship date to NTC and DPM, preferable through real-time, read only access to data contained in the Scholarships PNG database. This support to the Partners may include training, software and (if necessary reasonable hardware). The equipment and training would be defined as the Scholarships PNG is progressively implemented with any additional hardware and training costs agreed and implemented via a Service Order.

- 4.3.17	Pilot Delivering Year 1 for a Cohort of Scholarship Holders in a PNG University

- There is support among scholars and other stakeholders for offering part of an undergraduate degree within PNG. This would alleviate some hardship of family separation or financial burden (i.e. if the family accompanies the scholar to Australia). It provides opportunities particularly for women, people with disability and other disadvantaged groups, to gain better skills and knowledge through an accredited program delivered in PNG.

- Through having the first part of an Australian or NZ award delivered within a PNG institution, the scholar would be working in familiar surroundings, with closer access to their families and support networks. On successful completion of the study, it is anticipated that the scholars will be better prepared to complete their studies in Australia or NZ.

- A scheme will be piloted whereby a group of about 20 - 25 scholars undertake an initial period of their formal academic study at a PNG university. The option will be provided to potential scholars at the time of short-listing, so a cohort can be established as part of the final selection process.

- The quality of undergraduate degree courses in PNG is not generally at the same standard as of those awarded in Australia or NZ. In year 2 of the Scholarships PNG program, proposals will be sought from a PNG university to work with an Australian or NZ university of high standing, to strengthen a specific degree course offered at the PNG University, one that is aligned to an agreed Scholarship priority area. The aim is for the first two years of a PNG 4-year degree (i.e. the PNG Foundation Year plus Year 1) to be recognised as equivalent to the first year of the equivalent Australian or NZ undergraduate degree.

- The Pilot 2-year PNG course would be awarded via a competitive process managed by the Facility, taking into account existing and potential cooperation between PNG, Australian and NZ universities. The outcome will be an Australian or NZ university committing to assist a PNG partner university to further develop standards of teaching and learning in order for the PNG 2-year course to be quality assured. The joint delivery of the 2-year program would likely entail the Australian or NZ university sending academic staff to co-teach the course, as part of ensuring appropriate content, methods, assessment and support systems are in place.

- The Facility will apply relevant monitoring tools that ensure the Pilot course is accredited in Australia and NZ and that QA processes are appropriate. The outcome would be that successfully completing the initial 2 years of the PNG University degree (PNG Foundation Year plus Year 1) would be equated by the relevant accreditation systems as being equivalent to the first year of a three-year Australian or NZ degree within the same discipline area.

- Dual benefits will arise from this joint delivery arrangement. It provides a study option for scholars to stay in PNG, whilst at the same time facilitating institutional strengthening at a PNG university. It is also important that PNG scholars can maintain their options to choose a university after they have completed the Foundation Year plus Year 1 in PNG. To achieve this, those Australian or NZ universities in which PNG scholars may wish to enrol will need to have formally recognised this new study and course credit pathway.

- 4.3.18	Supporting the Australian Leadership Award Scholarships (ALAS)

- The Facility will be required to raise the profile of ALA Scholarships in PNG through targeted promotional activities. The ALA provide an ideal opportunity to identify men and women who, after gaining further formal studies and undertaking a leadership development program in Australia, will be able to substantially contribute to economic growth and poverty alleviation of PNG. The Facility will make specific efforts to identify women for consideration as ALA scholars, through promotion and advocacy as well as liaising with relevant industry associations, CSOs, women’s organisation and employer groups.

- The Contractor should refer to the latest ALAS Handbook developed by AusAID, that details the selection processes used for ALAS. As it is a regional program, the majority of ALA Scholarship applicants will apply on-line through OASIS (managed by the Australian Scholarships Section Canberra). However, the Facility will accept some hardcopy applications and also hardcopy documents from those who have applied on-line but are not able to upload their documents. A significant difference from other Scholarships is ALA Scholarship applications must be accompanied by an unconditional letter of offer for enrolment from an Australian institution. Eligibility will depend on results of an approved English language test (IELTS or TOFEL). English language testing will occur earlier in the ALAS cycle, so that applicants with the required IELTS score of 6.5 can be identified at a much earlier stage.

- After the Facility has undertaken an ALA compliance assessment, it will establish a Short-listing Panel (with external expertise as members) and conduct interviews, preferably with a representative from the Australian Scholarships Section included.

- PNG ALA Scholarship candidates will be reviewed by AusAID Post, before forwarding recommendations to AusAID in Canberra. ALA Scholarship nominations from all Posts in the Asia-Pacific region are subject to a further competitive selection process. With no fixed number of ALA Scholarship places assigned to any one country in the region, the Facility will seek to increase the number of quality applicants and improve the number of successful ALA Scholarships for PNG.

- The Contractor may be called upon to coordinate and report on aspects of the (ASA) Allison Sudradjat Awardees’ extra funding and arrangements and should refer to the ASA Guidelines.

- 4.3.19	Supporting the Regional Development Scholarships (RDS)

- The RDS for both AusAID and NZAID are managed from Suva, with the regional students attending either the University of the South Pacific (in Suva or Vanuatu) or universities in PNG. While overall management of RDS rests with others, the Facility is required to support those RDS regional scholars who choose to travel and study at institutions in PNG.

- The services to support these AusAID and NZAID funded RDS scholars while they study in PNG are provided by PATTAF, under separate contract to AusAID and to NZAID. These contracts will cease on the commencement of Scholarships PNG. Specific details of the Facility’s services in support of RDS students while in PNG are included in Annex 8.

- The Facility’s responsibilities commence when the RDS scholar arrives in PNG and continue until the scholar leaves for their home country. There are 40-45 new and continuing Australian funded RDS students in PNG, with 10-15 new students annually. These RDS scholars are enrolled at the Medical School at UPNG, as well as at UPNG’s main campus, the University of Goroka, the National Maritime College in Madang, the Divine Word University (DWU) and at Pacific Adventist University (PAU). There are also an additional 14 NZAID funded RDS students studying in PNG, at the University of Goroka and at the University of Technology in Lae.

- Assistance provided by PATTAF, to be continued under the Scholarships PNG Facility, includes:

  - Liaising with appropriate agencies to ensure visas are issued within an acceptable time;

- Airport pickup, briefing and providing on-arrival information;

- Specific information and procedures in relation to RDS scholar safety while in PNG, including security briefing, materials and emergency contact numbers;

- A tour of the university/school and provide support to identify suitable accommodation;

- Travel to all PNG institutions that have RDS scholars twice each year, monitoring scholar progress and welfare, as well as making regular contact with the scholar and institution;

- Paying the RDS allowances into the scholar’s bank account; and

- Providing regular reports to AusAID and NZAID Posts on progress and any issues.

- If required, work collaboratively with AusAID and NZAID to develop contracts for PNG universities and then manage the universities compliance under these contracts

- Liaise on a regular basis with AusAID and NZAID Awardees sending posts and raise any emerging issues with AusAID and NZAID Port Moresby.

- There is the future possibility that the RDS program in PNG will be extended to include outward-bound PNG students, who will leave to study in regional universities. Should this occur, the Facility would be tasked to undertake the additional coordination and logistical work through a contract variation.

- 4.4 	Component 2: 	PNG Professional Development Initiatives

- In response to emerging human resource priorities, as agreed between the Partners, Component 2 will provide direct support to strengthen the capacity of associations, organisations, and men and women, in pursuit of the following objectives:

Objective 3 To empower young women and men to actively participate in the development of Civil Society.

Objective 4	To strengthen identified professional bodies to provide to their membership opportunities to develop skills and knowledge essential to achieve best practice in the operation of PNG industry, Civil Society Organisations and government.

Objective 5	To strengthen the capacity and profile of Australian and NZ Alumni in PNG.

- In each of the above human resource and professional development initiatives, the Facility will focus on providing advice and opportunities for women to identify and undertake courses, training or placements that increase their potential for high-skilled employment and / or promotion. This is especially the case in respect to “non-traditional” employment areas, including technology-based opportunities, as a practitioner or in management.

- At the time of this design, there are several initiatives managed by PATTAF which are in addition to the existing ADS scholarship and professional development activities. The new Facility will be expected to have the capacity to accommodate emerging priorities, and take over (if required) existing PATTAF contracts through a process of novation.

- The HRD activities in support of PNG’s development do not have to be solely through the public sector. Joint initiatives between AusAID / NZAID and the PNG private sector (i.e. joint funding of specific scholarships, attachments or other forms of cooperation) could well be managed through the Professional Development Initiatives component. The following activities will be managed by the Facility in addition to the Australian and NZ Scholarships to PNG. Component 2 enables AusAID to have a flexible mechanism through which to respond to emerging skill priorities.

- Depending on the scope of emerging priorities, the Contractor may be tasked to provide additional services via a Service Order of a Deed of Amendment.

- 4.4.1	Support for Young PNG Leaders

- From year 1, the Facility will receive proposals for minor funding support from identified PNG associations that comprise young men and women leaders. Proposals could cover specific leadership skills, fields or capacities that relate to professional and organisational development across PNG. On approval by the Joint Steering Committee of the Young PNG Leader initiatives, the Facility will identify and fund small programs of support, normally contracted to a specialist provider or institution. These activities, while not of large monetary value, are strategic in that they can assist PNG men and women leaders of tomorrow to access activities, networks and funding to strengthen leadership skills and governance.

- PNG leadership development activities are designed to provide a direct, timely contribution to strengthening PNG organisations through improved leadership, being ad hoc and small value. Other priorities will emerge over time and (after approval and instruction from AusAID / NZAID or the Joint Steering Committee) support strategies will be developed.

- 4.4.2	Supporting Australian and New Zealand Alumni in PNG

- The PNG-Australia Alumni Association (PNGAAA) has membership open to any Papua New Guinean who has studied at an Australian institution. The PNGAAA was formed in 2006 and is in the process of establishing chapters in provincial cities. Many prominent, influential leaders in PNG are returned scholars from Australia, through ADS, the ALAS or having studied privately at Australian universities. The PNG NZ Alumni is active and provides an opportunity for returned scholars and students to link into their peers in PNG as well as maintain their contacts with NZ.

- There is a strong commitment to fostering good relationships between PNG and Australia, with members of the PNGAAA and the PNGNZA involved in national policy formulation. Such high-level engagement in national policy is worth nurturing.

- The Australian and NZ alumni are an ideal resource for the Facility for promoting scholarships, as well as for monitoring Facility outcomes and impact. The Facility will need to respect the independent role of the Australian and the NZ Alumni. The members are willing to be involved in assisting the selection processes, as well as for briefing and de-briefing sessions and for ongoing support to the program. Scholarships PNG will pay honoraria for services provided by Alumni members in support of the Scholarships PNG.

- The Facility will provide the Alumni associations with support through provision of appropriate office space, secretarial support, assistance for organisation of an annual conference, and (as endorsed by AusAID) specific allocations for agreed PNGAAA and PNGNZA initiatives.

- 4.4.3	Strengthening PNG Professional Associations

- As in all countries, PNG professional Associations play an important role in ensuring the development and maintenance of professional standards, integrity and ethics. They are also a useful vehicle for providing professional development opportunities for their members and also for mentoring PNG scholars while in Australia or NZ (as well as newly returned scholars) and organising work placements of students.

- Many PNG organisations will have links to Australian and NZ counterpart organisations, providing an avenue for cooperation and capacity building. Scholarships PNG support to strengthen PNG professional associations might include funds for secretarial support; guest speakers; short course training (provided through local PNG providers); and funds to attend conferences in Australia, NZ or elsewhere. Funding would cover the costs of agreed, specific activities that will be of benefit to Professional Association members in both NCD and the Provinces.

- The Facility will develop the selection criteria for endorsement by the Steering Committee and promote the availability of funds to the relevant PNG associations.

- 4.4.4	Supporting ALA Fellowships in PNG

- While ALAF applications must originate from Australian organisations, there is a role for the Scholarships PNG in promoting ALAF and developing appropriate linkages in PNG, using the ALAF Guidance documents as the basis for providing support to AusAID.

- The number of PNG ALA Fellowships in recent years has been relatively low and the Facility will need to promote and raise awareness of the opportunities afforded through this program. The Fellowships are ideally suited for the funding of collaborative arrangements between PNG senior specialists and their peers in Australian based organizations. Fellowships can incorporate public or private sector activities which have a sound development impact. The Fellowships are also suited to specialist research organisations like the Copra and Coffee Institute (CCI) and the PNG National Agricultural Research Institute (NARI), and the Human Resource Institute. They may enable PNG staff to work with their research and private sector counterparts in Australia. During each ALAF round the SS seeks comments and input from the AusAID Post on project proposals that involve PNG.

- Facility staff will work with AusAID Post, playing a complementary role in brokering relationships by putting PNG institutions in contact with Australian counter-part institutions (i.e. the Australian institutions are required to apply for the funding) to ensure a higher ALAF success rate for PNG.

- 4.4.5	Managing Careers in Development Initiative

- The Careers in Development initiative is currently contracted by AusAID to PATTAF and provides support and funding for around 20 PNG young professionals to work within the development environment in PNG, as part of their career advancement. This contract is directly held by PATTAF and is funded by AusAID. This contract in support of the Managing Careers in Development will be novated to the new Facility.

# 5	MANAGEMENT AND IMPLEMENTATION ARRANGEMENTS

## 5.1	Scholarships PNG Leadership

- Management will be overseen by a Joint Steering Committee, providing the Facility with leadership and overall strategic direction. The detailed ToR for the Joint Steering Committee will be jointly developed by the GoPNG, AusAID and NZAID in order to ensure that each of the Partners’ views and priorities are incorporated into the operation of the Committee and to the benefit of the Facility and PNG.

- The Joint Steering Committee oversight will include setting and monitoring the direction and overall operation of the AusAID and NZAID Scholarship programs, as well as guiding and endorsing the existing and emerging professional development initiatives. The Joint Steering Committee is a high-level decision making mechanism that provides broad policy oversight and direction and will comprise nine men and women from key GoPNG, CSO and private sector as well as independent external members.

- The Joint Steering Committee’s GoPNG membership will comprise senior men and women from those agencies that are directly involved in scholarship implementation. GoPNG members of the Joint Steering Committee are senior representatives of Partner agencies directly involved in implementation.

- Joint Steering Committee membership will be balanced by gender and also take account of the diversity (and complexity) of the HRD needs across PNG. The proposed membership of the Joint Steering Committee reflects strong commitment to PNG’s development from key Partners, as outlined in the following Table 4.

Table 4: Proposed Membership of the Joint Steering Committee

| From GoPNG | From PNG Society | From Australia - NZ |
| --- | --- | --- |
| A senior Department of Personnel Management representative | A senior PNG academic | A senior AusAID officer |
| A senior National Training Council representative | A PNG Private sector representative | A senior NZAID officer |
| A senior Department of National Planning and Monitoring representative | A PNG CSO NGO representative | A senior Australian / New Zealand academic |

- The Scholarships PNG Joint Steering Committee members would be appointed for a period of two years, with the exception of AusAID and NZAID representatives whose membership will be the term of their Posting. The Facility will provide reports, briefings and proposals to support the work of the Joint Steering Committee and implement Scholarships PNG in accordance with the agreed Annual Plans and the Joint Steering Committee decisions. A stipend would be paid to Joint Steering Committee members travelling from outside Port Moresby to cover travel costs.

- The Joint Steering Committee will function as the primary decision-making mechanism and will meet quarterly to provide support, guidance and strategic direction to the Facility. It will also monitor the Scholarships PNG implementation, especially in relation to broader GoPNG and donor policies and priorities across development sectors.

## 5.2	The Scholarships PNG Implementation Model

- A Facility model will be used to manage the scholarship program (i.e. the Australian and NZ scholarships) as well as the Professional Development Initiatives for individuals and organisations. The Facility model enables staff at AusAID and NZAID Posts to focus on setting the policy framework, as well as (jointly) developing Scholarship priority profiles. There are advantages and synergies in having these two Components covered within the one Facility, including:

- The overall program is involved with building the human capital of PNG. Through the flexibility available within Scholarships and the professional development initiatives, AusAID and NZAID will be able to rapidly respond to existing and emerging needs and subsequently provide support to specific PNG sectors / development priorities;

- The proposed 1-year Foundation Course to strengthen opportunities for men and women from PNG provinces to gain a donor-funded scholarship will be developed and delivered through a PNG tertiary institution. In this way, Scholarships PNG contributes directly to the development of systems and expertise in PNG, as well as provide a valuable alternative pathway for potential scholars;

- A proposed Pilot for a new 2-year course that equates to the first year of an Australian or NZ degree (i.e. the PNG Foundation year, followed by Year 1of an Australian / NZ degree), offered at a PNG university after a competitive selection process;

- The synergies that will be available across the two Components, including the targeted use of TA; a cohesive response to HRD and professional development needs; and a “one-stop-shop” for AusAID and NZAID Scholarship initiatives.

## 5.3	Scholarships PNG Management

- The Facility, administered by a managing contractor identified by AusAID and NZAID, will provide the Partners with the flexibility required to scale funding levels up (or down), as well as providing a responsive mechanism to meet emerging needs or priorities.

- Each year, the Facility will provide a draft Annual Plan for the consideration of the Joint Steering Committee. The Annual Plan will reflect any changes to context and progress across the two components and link into relevant GoPNG plans and strategies (including the MTDS); emerging human resource development priorities as agreed between GoPNG, AusAID and NZAID; changes to institutional arrangements or context; and any new policies that have an impact on the Facility’s operation. Detailed outputs and outcomes for each component that are included in each Annual Plan will be reflected in an updated Monitoring and Evaluation (M&E) Framework, as well as in the reporting.

- The Annual Plan will use the flexibility available through the Facility model to incorporate initiatives, appropriate resource inputs and defined outcomes that can reflect and support priorities as expressed through the Joint Steering Committee. Three hard copies and an electronic copy of the Annual Plan will be submitted to the Joint Steering Committee in a timely manner (i.e. March each year), so that decisions on forward initiatives and expenditure levels can be effectively aligned to the budget cycle.

- The Scholarships PNG management and responsibilities are summarised diagrammatically in Figure 2. Further details in relation to service levels and Joint Steering Committee support requirements are included in the Implementation Arrangements, Staffing and Facility Management, which is included as Annex 1.

- The proposed timing for the various scholarships and Professional Development initiatives are included in the Implementation Schedule at Annex 2.

- The Facility office will be located in central Port Moresby, comprising a safe, secure working environment, easily accessible to visitors; will have space suitable for displaying scholarship information, conducting meetings and interviews; and the space and technology that will enable potential scholarship applicants to undertake searches for information on Australian or New Zealand institutions and courses.

- The Facility will maintain an appropriate balance between international and local personnel for the full-time in country positions. There will also be an appropriate gender balance, particularly relating to Scholarships PNG management positions. All Scholarships PNG staff will have clear and appropriate Terms of Reference. There will be a staff development, performance planning and review program in place from commencement, to ensure the ongoing professional development of local staff.

- The office will incorporate appropriate communication, IT, network and other equipment to facilitate management and secure storage of records, data and confidential information. The office will also include access for people with disability. The Facility Director will act as single point of contact for AusAID and NZAID and provide leadership and direction for all Scholarships PNG activities and services.

- AusAID (with inputs from NZAID) will take responsibility for the Agency’s contractual relationship with the Facility, including the annual performance review.

On the following page, Figure 2 indicates the management responsibilities for the Scholarships PNG program.

- Figure 2: Facility Management and Responsibilities

AusAID and NZAID Post

- Policy development

- Contract management and annual review of MC performance

- Advise change in scholarship policy as well as number or form

- Advise on forward budgets

- Participate in selection of scholars

- Participate on Joint Steering Committee

GoPNG

- Support to agencies in relation to the country’s forward development plans and HRD priorities

- Advise on Strategic Direction of the Facility through membership of the Joint Steering Committee (DNPM; DPM; NTC)

- Participate in the selection of scholars

AusAID Canberra

NZAID Wellington

- Scholarship policy and support

The Joint Steering Committee

Joint Steering Committee

Provide leadership and strategic direction for the SP Facility

The major decision-making body for the Facility, comprising senior members from a cross section of stakeholders and the PNG Partners.

Facility Staff

The Partners

Facility Director

Single point of contact. Capacity and authority to ensure service levels high quality. Responsible for Program direction, adding value, M&E, Oversee the Foundation Year and change management. Skills to understand major issues in PNG and deal with emerging situations.

Component 1

PNG Scholarships Manager

- Oversee the PNG Scholarship management and reporting.

- Ensure deadlines met, staff and SP systems in place.

- Provide leadership in all aspects of scholarship management and systems.

Component 2

PNG Professional Development Initiatives Manager

- Oversee the existing and emerging professional development initiatives and support to Alumni.

- Develop programs and initiatives as approved by the Partners.

Scholarships and M&E Managers

- Responsible for AusAID and NZAID scholarship activities, with the authority to assign and manage Facility’s resources, liaise with AusAID or NZAID staff, and supervise the day-to-day administration of the Scholarship and M&E functions.

SP Facility Financial / Coordinators / Support Staff

- Provide administrative support in all aspects of Component 1 and 2 promotion, applications, data entry and retrieval, reporting, logistics, report production, financial records and reports. Provide support for the Joint Steering Committee.

- Other support to the Scholarships PNG Facility as required.

# 6	IMPACT AND SUSTAINABILITY ISSUES

## 6.1	Benefits of Additional In-country Preparation for Scholars

- As previously mentioned, PNG ADS scholarship extensions, terminations and award downgrades incurred a cost of around AUD $13.7 million over the past 5 years, or approximately AUD $2.75m per year. It is proposed to provide additional in-country support at the “front end” of the scholarship cycle in PNG, as part increasing efficiency and (subsequent) effectiveness of outcomes. Additional processes and resources will be applied early in the cycle, aimed at preparing PNG scholars to achieve better academic results as well as reduce Scholarship downgrades, extensions and terminations. These measures, if successful, will increase the likelihood of success for the individual, as well as improve development for PNG.

- This design proposes four new “front end” interventions to existing Scholarship processes. They will be inserted early in the Scholarship cycle, which should markedly improve the likelihood that those who secure Scholarships are better placed to succeed in their study, as well as for better reintegration on their return to PNG. The four are:

- Introduce a Foundation Course, delivered at a PNG institution, and awarded after a competitive tender process. The Foundation Course will accommodate up to 25 applicants who were short-listed but not selected to receive an award in the current application round. The course will provide a strengthened and expanded cohort who can (if they choose) re-apply for an Scholarships PNG or other Scholarship. In relation to the existing program, the estimated additional cost is AUD $364,000 per year;

- Introducing an IELTS English proficiency test for all short-listed ADS applicants, so results can be provided to the relevant Australian or New Zealand tertiary institution and (where necessary) additional language support can be provided by the institution at the outset. In relation to the existing program, the estimated cost is an additional AUD $85,000 per year;

- Increasing the duration of the pre-departure program from three days to two weeks. The content will also be amended to include intensive inputs on IT, university study requirements, budgeting, maintaining communications with PNG and also have the scholars establishing contact with their selected Australian or NZ institution. The potential scholars will also be required to undergo medical tests for visa purposes during this period. In relation to the existing program, the estimated additional cost is AUD $150,000 per year;

- Pilot the introduction of delivering an accredited first year of the Australian or New Zealand academic program in PNG, through a joint arrangement with a PNG university and one in Australia or NZ. This would take the form of a 2-year Pilot program for a cohort of 25 and be introduced in the third year of the Scholarships PNG. The estimated cost for establishing these new arrangements and for providing the quality framework for the joint delivery is AUD $ 300,000, with an annual delivery cost of around $500,000 for the two years duration of the Pilot.

- The M&E Framework will include measures that will enable monitoring of the success of these new interventions and compare future Scholarships PNG outcomes with the existing base line data on extensions, downgrades and terminations.

## 6.2	Building Sustainable Practice into the Scholarship Program

- There is an emphasis on achieving sustainable outcomes across the two components. Attention will be paid to the capacity of beneficiaries to apply and sustain new skills. The design focuses on targeting scholarships; strengthened selection procedures; more comprehensive and inclusive pre-departure activities; better monitoring student progress in Australia and NZ; re-integration planning for return of male and women scholars; and increased Alumni involvement.

- Scholarships will focus more directly on development impact through the development of Profiles that reflect jointly agreed priority areas. The Facility will also build into the Scholarship and PNG professional Development Initiatives measures that strengthen gender equity, not only as part of selection but also in relation to the ongoing development impact.

- The Facility will collect and report on ‘intermediate outcome’, i.e. graduates returning to work in PNG across priority human resource development areas. The introduction of Reintegration Plans for Public category scholars will also focus the scholar and the employer on their joint obligations and provide the basis for discussion when the scholar eventually returns to the workforce.

- PNG scholars are often forced to resign from their position before taking a scholarship and to find employment on return. Even in the Public category, where scholars are supported by GoPNG, there are cases where the returning scholar finds their position no longer exists or (in some cases) they are no longer employed. More disturbingly, some employers advise the scholars after their arrival in Australia or NZ to commence studies that they no longer have a position to return to, which especially affects women scholars. The Facility (with PNGAAA and PNGNZ Alumni) will provide advice to women, including support in identifying alternative employment opportunities.

- The M&E Framework (Annex 4) includes the minimum information required to address the outputs and outcomes of the 5 Objectives. The Framework provides for both management data (are scholarships well targeted, balanced by gender, provincial representation and priority areas) as well as approaches to measure impact (tracer studies, Most Significant Change, case studies, other measures that assist in identifying impact on PNG institutions and processes). The M&E framework and methods must ensure that management information is available to the Joint Steering Committee, as well as for AusAID’s Quality at Implementation purposes.

- The development impact on PNG (applying higher level technical and professional expertise) can only be measured over a longer time, partly because of the lead time to acquire new knowledge through a 2-4 year scholarship.

- Time is also required for new PNG professionals to increase their capacity to influence policy and implementation. Previous tracer studies have shown ADS awardees have benefited, with employers being positive, although to a lesser degree than the returned scholars. Recent attempts to strengthen the post-return experience of scholars and strengthen scholarship impact have included the formation of PNGAAA and the PNG NZ Alumni. The men and women of the PNGAAA and PNG NZ Alumni will play an important role in supporting tracer and case studies, as well as providing feedback information on the scholars’ experiences, as well as constraints and lessons learned on the scholar’s return to PNG.

# 7	CRITICAL RISKS AND RISK MANAGEMENT STRATEGIES

- A number of critical risks to the Scholarships PNG have been identified and taken into account as part of the design process. The main risks relate to:

- Potential impact from the political level;

- Maintaining Scholarships PNG service levels across various Scholarships and other activities;

- Maintaining donor identity in the program and in activity management;

- The potential for external interference in application and selection processes;

- The quality of selected scholars and their capacity to complete the awards;

- The adequacy of scholar stipends and allowances in relation to their study;

- The scholars’ reintegration and employment in PNG on their return;

- Capacity to respond to emerging HRD / professional development initiatives; and

- The security and health risks in PNG.

- The related Scholarships PNG risks and subsequent risk management strategies are discussed in detail and summarised in a Risk Management Matrix, which is included as Annex 3.

# 8	FACILITY PLANNING AND REPORTING

## 8.1	The Annual Plan

- Each year the Facility will be required to develop an Annual Plan for approval by the Joint Steering Committee, AusAID and NZAID. The Annual Plan will include all strategies, detailed resource schedules and the anticipated outcomes for the following year, in relation to both the Joint Steering Committee guidance and the M&E framework. The Annual Plan will also align with agreed AusAID, NZAID and GoPNG policies and requirements.

- The Annual Plan will meet the quality and format requirements of AusAID and will include the information, data and available options required for evidence-based decision making. The Annual Plan will also integrate the approaches and strategies to be applied for each of the following:

- HIV and AIDS approaches and practical measures to increase knowledge and protection, for Scholarships PNG staff and for external stakeholders (including the scholars)

- The security and health of all staff and (as appropriate) external stakeholders;

- The Scholarships PNG staffing and resource allocations.

- The initial Annual Plan will be due three months after commencement and detail the following 12 months of the Facility. The Annual Plan will also be flexible enough to progressively incorporate and integrate new ideas and processes that arise from implementation, including from (for example) the parallel development of the Scholarship Promotion and Communication Plan.

## 8.2	Scholarships PNG Operations Handbook

- The key management and operational mechanisms for Scholarships PNG shall be included in an Operations Handbook, submitted to the Joint Steering Committee for endorsement within three months of commencement. The Operations Handbook must reflect the flexibility embodied in the design and clearly indicate how the innovations on Scholarship management and in the Professional Development Initiatives will be managed. The Operations Handbook will be a key element in maintaining both service levels and quality and will be continually reviewed to reflect lessons learned and improvements in Scholarships PNG processes and methods.

- The Operations Handbook will include (but not be limited to) the following:

- The standard Scholarship management operating procedures outlining the key activities, Partners, processes, key processes that require Partner endorsement and the cut-off dates that will form the basis of the scholarship management procedures. This document shall be presented in a way that is simple, clear and unambiguous and suitable for referral by all Scholarships PNG staff. There must be no chance of misinterpretation of the information on the requirements for confidentiality, security and poor practices by any staff member, whatever their involvement in the Scholarships PNG activities;

- The financial management procedures to manage the Scholarships PNG financial systems and the accounts, the arrangements for financial acquittals, the reporting templates and measures to be applied for fraud protection (including for regular internal and external system and financial records auditing);

- Quality Assurance procedures and the approaches and methods that will be put in place to ensure that there is continual reflection and quality improvement across all elements and practices of the Scholarships PNG;

- Risk Management Plan that addresses the risks associated with Scholarships PNG operations; health and safety (including HIV and AIDS); medical emergencies and evacuation; briefings and guidelines for all staff; and emergency communication arrangements and protocols. The Risk Management Plan will clearly outline the processes and staff responsible for ensuring that there is no corruption, nepotism or collusion in relation to any aspects of either the Scholarship management or the Professional Development processes; and

- Templates for the Scholarships PNG planning and reporting requirements; draft contracts for Selection Panel members and the PNG, Australian / NZ academic specialists to be involved in the selection process; and a draft Code of Conduct for signing by all staff; the members of the Joint Steering Committee and external consultants.

## 8.3	Scholarships PNG Scholarship Promotion and Communication Plan

- The Scholarships PNG includes change and innovation compared to the previous PATTAF and there will be an immediate need for the Facility to advocate and disseminate the new structures, expectations, priority areas and Scholarship targets and stakeholders. Importantly, the Scholarships PNG is now a joint program with AusAID and NZAID and will deal with an expanded range of PNG stakeholders. Scholarships PNG seeks to access candidates in Provinces and to provide alternative pathways for achieving scholarships, including the Foundation Course and other enabling strategies.

- There is a new vision for the Scholarships PNG. It requires a new look at how PNG scholarships are promoted and communicated and ways in which GoPNG, the private sector, CSOs and NGOs and other organisations (including faith-based) can best engage with the Facility and the opportunities.

- The Scholarships PNG Promotion and Communication Plan will be required to be submitted for endorsement four months after commencement and will detail how the new strategies and directions will be integrated into Scholarships PNG planning, operations, outcomes and reporting, as part of identifying and managing the complete scholarship cycle.

## 8.4	Six Monthly and Annual Reports

- The Facility will collect and record the data required to submit a Six Monthly and Annual Report, based on the agreed Annual Plan. Six Monthly and Annual Reports will include (as a minimum) the type of data and information as included in Annex 4.2. These Reports will be concise, providing Partners with strategic and operational information required for them to make informed decisions on the best way to plan and implement the Scholarships PNG. Reports will include the following:

Promotion, Selection, Placement: including features of each annual Scholarship recruitment round detailing promotion, selection and screening activities, with clear disaggregation by gender, disability, location, fields of study, level of study, Australian / NZ institution, award category (i.e. Public and Open), the indicated area of development contribution and continuous improvement approaches. Information will be provided on scholars’ placement experience and the summary outcomes for the year’s cohort.

Report on Academic Outputs: gender disaggregated and including:

- Information from Australian and NZ universities, tracking scholar progress by semester, noting deferrals, extensions, suspensions, downgrades, upgrades and drop-outs. Identify high achievers, students at risk and measures to mitigate. This student information is available from the Student Information Management Online (SIMON - managed by AusAID’s Scholarship Section) and the Student Information and Management System (SIMS), managed by the NZAID scholarships in Wellington;

- Academic progress, including any extensions and variations, to be shared with the sponsoring agencies by the scholar;

- Details of completed scholarships and RDS, including pass/failure, an analysis of reasons for failure and suggestions for areas where improvement could be achieved;

- Post-graduation monitoring activities, focusing on returned graduates each year, resumption of employment and information on expected contribution to development. This includes details of activities arranged with PNGAAA/PNG NZ Alumni; and

- Debriefing of scholars and their experiences.

Reintegration Outcomes: including any lessons learned from returning scholars and awardees in relation to development outcomes at the GoPNG agency / sector employment level.

Follow-up activities: including making contact with scholars within the first month of their return to PNG, providing an opportunity to debrief them and their families; interaction by recently returned scholars with scholars in Australia or NZ, including potential for maintaining national and international networking activities.

Monitoring and Evaluation: including progress towards the achievement of program outcomes based on data collected from the M&E tools.

- In addition to the 6-Monthly Reports, and on an ongoing basis, Scholarships PNG will use Exception Reporting to communicate any urgent information or constraints that require consideration and decisions from the Joint Steering Committee, AusAID or to NZAID.

## 8.5	Information for AusAID’s Annual Corporate Reporting

- The Facility will be required to provide specific input and data to AusAID’s annual Quality at Implementation (QAI) and Sector Performance Reporting (February - April). This will provide an assessment of implementation of the scholarships against the following criteria:

- Implementation progress across all Scholarship and award programs;

- Achieving objectives;

- Monitoring and evaluation;

- Sustainability;

- Risk management; and

- Gender equality and other overarching issues.

## 8.6	Independent Progress Report

- An Independent Progress Report (IPR) will be conducted in the third quarter of the third year. The IPR will assess the outcomes of the Program arrangements and Facility performance. At completion of the IPR, a recommendation will be made whether to extend the contract from three to five years.

- The IPR will also recommend, as required, any potential for improvement in the efficiency and effectiveness of Facility processes or management, with particular reference to access, equity, quality processes, gender equality, transparency of the Scholarship cycle, the impact measures of Scholarships PNG, and value for money.

- A review of the Facility’s M&E system will also be undertaken, to ensure that the required amount and quality of information is being collected and that the reporting meets AusAID and GoPNG requirements. Where possible, the data and information used for the M&E will be sourced through the existing systems and reporting regimes of the Partner organisation / institution.

## 8.7	Independent Completion Report (ICR)

- In liaison with NZAID, AusAID will commission an independent evaluation at the end of year five. The ICR will assess relevance, effectiveness, efficiency, impact (where feasible) of the Facility. It will review the M&E information, specifically in relation to a sustainability analysis for the Scholarships PNG outcomes and a summary of lessons learned.

# 9	MONITORING, EVALUATION AND CONTINUOUS QUALITY IMPROVEMENT

- Where they exist, the M&E will utilise existing PNG systems. When a specific monitoring system is used, such as for the capture of scholarship related data, the Facility will share this information with relevant GoPNG agencies via the Joint Steering Committee. This data and information will form part of assisting agencies to develop their internal HRD strategies and priorities. Key features of M&E arrangements include:

- Using a mix of quantitative and qualitative indicators;

- Use of a range of evaluation methodologies;

- Use of indicators that can track any improvements to Scholarship outcomes as a result of the new “front end” initiatives in the program;

- Capture of both activity and program level outputs, outcomes and impact;

- Utilisation of existing PNG monitoring and reporting systems;

- “Most Significant Change” involving collection of stories from the field, followed by systematic selection and documentation of the most significant of these stories;

- Ongoing lessons learned, generated from the framework, to be reincorporated into the program to ensure continuous quality improvement and maximum impact; and

- Gender disaggregated data, with disaggregation of other equity related indicators where possible, including for Provincial participation and people with disabilities.

- The monitoring and evaluation processes will include:

- Annual surveys and focus groups, especially in relation to the Scholarships;

- Tracer and case studies, Most Significant Change (MSC) techniques and surveys; and

- Specific activity-based M&E measures that will be developed and included for each of the new activities that will be funded under Component 2 “Professional Development Initiatives”.

## 9.1	The Monitoring & Evaluation Plan

- In consultation with Partners, within three months of commencement the Facility will develop and submit an M&E Plan, based on the M&E Framework as included in Annex 4. The M&E Plan must meet the information and reporting requirements of the Partners and will be submitted to the Joint Steering Committee for its endorsement. The M&E Plan will include details and reporting capacity of the MIS system against the key M&E measures and detail the data security protocols.

- The M&E Plan will also integrate selected PATTAF Scholarship data for use as the base-line for comparing the success (or otherwise) of the Scholarships PNG initiatives and outcomes, especially the new Scholarships PNG “front-end” investments of the Foundation Course; the IELTS testing; the extended PDB program and the new in-PNG delivery of Year 1 of an Australian or NZ degree.

- The M&E Plan will contain the security and operational guidelines to ensure that the integrity and validity of the M&E information is maintained throughout the program and that the data and information is suitable for accurate, regular reporting to Partners.

- The Annex 4 includes the M&E Framework and also proposed M&E methods and indicative tools that will be applied across the two Components.

## 9.2	Annual Scholarships PNG Contractor Performance Assessment

- After completion of QAI and sector performance reporting in May, AusAID will convene the annual Contractor performance assessment to review outcomes from the previous year and agree on adjustment or change required to improve management.

- Issues of Contractor non-performance will be handled as they arise based on QA provisions included as part of the Scope of Services. The Facility will be aware of (and meet) all schedules, deadlines, methods and constraints that apply to all elements of the scholarship cycle and reporting requirements. The annual performance review will focus on lessons learned and emerging issues, with the Facility expected to embed continuous improvement.

- The NZAID and Joint Steering Committee will have input into this annual review process. AusAID Post (in cooperation with NZAID) will conduct the review, with the Contractor expected to adapt and improve operations and systems in response to the outcomes. The Contractor will be assessed on the Contractor / Facility Performance Criteria, which are detailed in Annex 5.

# 10	THE Transition between PATTAF and Scholarships PNG

- Scholarships PNG follows on from PATTAF, which has a high profile and strong reputation for managing scholarship and HRD initiatives over the past eight years. As a result, there are existing resources, equipment and facilities that may be suitable for transfer across into Scholarships PNG at contract commencement. These physical resources include office equipment, IT, furniture, vehicles and other related items. Details of any equipment and its condition will be provided at the appropriate time, to enable an assessment of what may be suitable for use in the Scholarships PNG program.

- It is expected that any existing equipment and other physical resources will be reviewed as part of minimising any duplication in procurement. This consideration is especially the case for those vehicles currently in use on the PATTAF.

- In relation to the existing PATTAF staffing arrangements, should there be a change in MC from the PATTAF contract to Scholarships PNG, there may well be local PNG staff employed under PATTAF who may wish to be considered for positions in the new Facility.

- The Contractor will ensure a smooth transition into Scholarships PNG from the PATTAF, including:

- Outline transition phase arrangements as part of the initial Annual Plan, which will also indicate how to make best use of existing resources;

- Detailed schedules for the establishment of the office; staffing schedules; and support for the Joint Steering Committee;

- Where the office in Port Moresby will be located, staffing profile and organisational linkages;

- How existing data and databases can be modified and extended to meet the Scholarships PNG needs;

- How any local PATTAF staff identified for joining Scholarships PNG can be transferred and managed;

- How the initial 2 months of Scholarships PNG will be implemented to ensure a seamless transition;

- A plan for advocacy and providing information to key stakeholders;

- Informing stakeholders of the new arrangements during the first four months of Scholarships PNG through implementing the agreed Communications Plan;

- Accepting transfer of assets from the PATTAF as directed by AusAID; and

- Managing funding and providing continued support to ongoing activities and accept the novation of, and subsequently manage, contracts and agreements that continue under Scholarships PNG.

- Annex 1	 Scholarships PNG Implementation Arrangements, Staffing and

- Facility Management

  - Scholarships PNG Implementation Arrangements

# 1.2	Scholarships PNG Facility Management, Staffing and Service Requirements

Annex 1.1	Scholarships PNG Implementation Arrangements

PATTAF demonstrated that a Facility model is appropriate for managing the various methods and approaches to support development in PNG. A Facility offers AusAID, NZAID and the GoPNG the flexibility required to scale up (or down) funding levels, as well as providing a responsive mechanism to meet emerging needs or priorities. The successful PATTAF experience of forming a high-level Joint Steering Committee, with strong GoPNG presence, in order to guide and advocate the forward planning and implementation, has been incorporated into the proposed Facility structure.

The Joint Steering Committee will provide direction for the Scholarship program and comprise senior representatives from GoPNG, private sector agencies, CSOs as well as independent external academic members. The Joint Steering Committee GoPNG membership comprises senior representation of those Partner agencies that are directly involved in implementation.

The Joint Steering Committee will meet quarterly and provide support, guidance and strategic direction. Minutes of the Joint Steering Committee Minutes will be submitted within seven (7) days of the meeting; a hard copies and an electronic copy will be submitted by the Facility Director to each of the Partners.

The Facility will provide Six Monthly reports, specific briefings and proposals for funding (i.e. via Component 2) to the Joint Steering Committee for consideration, especially in relation to the focus and direction of the Scholarships PNG program. The Facility will also outline any major constraints or barriers that may require some form of high level intervention.

The Annual Plan will use the flexibility available through the Facility model to incorporate initiatives, appropriate resource inputs and defined outcomes that can reflect and support priorities as expressed through the Joint Steering Committee and the partners.

Upon completion of the contract, the Facility will provide six hard copies and one electronic copy of a Completion Report.

Component 1: AusAID and NZ Scholarships to PNG

- Governance Arrangements

Management of the Component, overseen by a Joint Steering Committee, will be implemented by the Facility. The Joint Steering Committee members from the key stakeholder agencies and associations would be nominated for a period of two years, with the exception of the AusAID and NZAID nominations, who will be appointed to align with the dates of their Posting. Each of the three Partners (GoPNG, AusAID, NZAID) will provide senior representation relating to their sectoral, national and provincial priorities.

- Component 2: PNG Professional Development Initiatives

Management of the PNG Professional Development Initiatives will be undertaken by the Facility, also reporting to the Joint Steering Committee. This Component is dynamic and responsive, requiring the Facility to have a suitable qualified person who understands human resources and can develop a response for consideration, based on the priorities of the agreed PNG institutions/associations.

After approval from the Joint Steering Committee, the Facility will identify a provider / consultant / mechanism to meet the priority needs of the participating PNG organisation and develop and monitor the contract and the outcomes. The proposed timing for the various scholarships and other initiatives are included in the Implementation Schedule at Annex 2.

Annex 1.2	Scholarships PNG Facility Management, Staffing and Service Levels

- The Scholarships PNG Facility office and point of contact for the Partners will be in Port Moresby, suitable located in a central position. It will comprise of a safe, secure working environment, easily accessible to visitors. The office will have space suitable for displaying scholarship and HRD information, space for conducting meetings and interviews; and the space and technology that can enable potential scholarship applicants to undertake searches for information on Australian and New Zealand institutions and courses.

- The office will incorporate appropriate communication, IT, network and other equipment to support the Scholarships PNG management. Importantly, the office will enable the secure storage of records, data and confidential information. In addition to the security of information and data in the office, daily updates will be electronically stored in a highly secure location off-site, in case of fire or other emergency. The Facility will nominate a senior person to act as single point of contact for the Partners.

- An AusAID staff member from Port Moresby High Commission (in liaison with NZAID) will take responsibility for the contractual relationship with the Scholarships PNG Facility, including initiating and managing the annual performance review.

- The Facility Management Structure

- The Facility will model good gender balance across its staff. The management will provide the Partners with highly experienced and qualified staff, as part of meeting the requirements of the SOS and the contract. Management of the Facility requires international and local staff with extensive expertise in the management of scholarships programs and also in the development of human resource plans and programs.

- It is expected that the senior person taking overall leadership and responsibility for the Facility’s contractual and activity management will act as the single point of contact for the two components. The senior person will be highly professional, well qualified, readily available, appropriately skilled and an excellent communicator. This person will also require skills obtained from working in a developing country setting with sensitivities to the broader development issues such as HIV and AIDS risks and vulnerabilities, gender equality and principles of transparency and equity.

- Scholarships PNG, through Component 1, represents an important mode of development assistance for AusAID and NZAID in PNG. Being high-profile, expensive and highly sought awards, their prestige need to be matched by the expertise, status and experience of the Facility’s nominated personnel who are undertaking the work.

- Component 2, the PNG Professional Development Initiatives, will require a person well experienced in managing a responsive training and development activity, as well as having flexibility in staffing and appropriate expertise to meet the varying M&E, administrative and promotional needs.

- Scholarships PNG Staff

- The staffing Table below (Table 5) is indicative and provides an overview of the type of expertise that will be required. The Facility staffing numbers and mix of skills will match Scholarships PNG’s planning, management, operational and M&E requirements.

- At a minimum, the Facility will require a team that possesses skills and experience in: professional development; training methods and approaches; communication and public relations skills, Higher Education in Australia and New Zealand, financial management skills and information technology skills; expertise in scholarships policy and administrative management; procurement management for services, and strong contract expertise. There is potential for the use of web-based management for elements of the Facility, including maintaining contact with scholars in Australia and New Zealand.

- The staff will demonstrate skills or experience that can be applied successfully within the dynamics of PNG’s complex context. There will be an emphasis on continuous improvement, innovation through the analysis of lessons learned.

- There will be an emphasis on continuous improvement, innovation through analysis of data, effective planning, concise and accurate reporting, and strong M&E for measuring the impact of development initiatives (particularly the outcomes of the scholarships programs), as well as ad hoc professional development initiatives.

- The actual number of staff and their specific duties will need to align with Summary of Scholarship Process and Facility Responsibilities, as well as the skills and knowledge required to work with agencies and associations to promote the various initiatives.

- Senior staff within the Facility will require a strong understanding of PNG and the Australian and New Zealand university sector. This will better enable them to support potential scholars in their choice of award and institution, as well as for undertaking follow-up contact with the scholars within PNG, as well as when studying in Australia and New Zealand. The following table provides an indicative summary of the required staffing.

- Table 5: Indicative Summary of required staffing for Scholarships PNG

|  | High Level staff | Senior Staff | Junior staff | Required Attributes (defined for Key Facility staff only) |
| --- | --- | --- | --- | --- |
| Facility Administration |  |  |  |  |
| Facility Director | 1 |  |  | - Overall responsibility for Facility, the team and staff performance, meeting overall Scholarships PNG outcomes. - Provide a single point of contact for the Partners and take responsibility for the overall implementation of the scholarships and the PD. - Provide professional advice and technical support to the Partners on Scholarships and HRD, the Facility and the two sets of Component initiatives as required. - Lead the planning, reporting and liaison functions and work with Partners to maximise impact and effectiveness of Scholarships PNG initiatives. - Identify areas of speciality that require outsourcing or temporary relief and recruit accordingly eg higher education specialists - Lead the forward Annual Planning process each year, including achieving the agreed targets - Take responsibility for cross cutting issues across the Facility, including gender; disabilities; access and equity; child protection; the environment; and HIV and AIDS - Provide Leadership in the Scholarships PNG innovations associated with introducing the Foundation Year - Lead the process to introduce the accredited delivery of a cohort to complete Year 1 of an Australian / NZ degree in PNG. |
| Senior Financial Manager | 1 |  |  | - Review PATTAF systems and use lessons learned to refine / update processes and facilities to suit the requirements of Scholarships PNG - Establish and maintain secure financial systems, reporting mechanisms and management policies - Take a leadership role in financial planning, cash flow, reporting, overall system management and local accounting - Oversee Scholarships PNG expenditure in PNG and in Australia / New Zealand including bank reconciliations - Support the contracting arrangements and financial payments for the various Scholarships PNG subcontractors, external consultants and PNG institutions - Lead all financial reporting and take responsibility for monitoring and refining all anti fraud measures - Supervise all finance staff and the systems in use across the Facility and ensure that adequate training and briefings are in place for all staff |
| Facility Office Manager |  | 1 |  | - Supervise the effective operation of the Scholarships PNG office and staff - Provide leadership to the Scholarships PNG support team staff and ensure that service levels remain high and that the systems are effective - Provide staff training and briefings as required to ensure that Facility Office staff have the required skills and attitude - Monitor and maintain the office required systems and facilities and report constraints or any issues to senior Scholarships PNG management |
| Financial transactions support |  |  | 1 | - Provide support across both components |
| Facility Drivers |  |  | 2 | - Provide support across both components |

| Component 1: Australian and NZ Scholarships to PNG | High Level staff | Senior Staff | Junior staff | Required Attributes (for Key Staff only) |
| --- | --- | --- | --- | --- |
| Scholarships Manager | 1 |  |  | - Responsible for the overall management of the scholarships, including key inputs in the Annual planning and the reporting - Liaise with other Scholarships PNG staff and stakeholders to set up the required systems and procedures to manage the Scholarships PNG - Maintain contact and good relations with relevant GoPNG, NGOs, CSOs and other PNG associations - Oversee the gender equality and disability targets and take steps to achieve them in all parts of the scholarship cycle - Oversee the scholarship impact studies and provide summary reports to Partners as may be required for all Scholarships PNG awards - Liaise with institutions and agencies in Australia and NZ on the scholar progress, as required |
| Scholarship Coordinators |  | 2.5 |  |  |
| Scholarship Data / M&E Entry |  |  | 1.5 |  |
| Filing and clerical support |  |  | 2 |  |
| M&E Manager |  | 1 |  | - Review PATTAF M&E and other best practice to build on lessons learned and suggest changes to match Scholarships PNG SOS - Establish M&E system and reporting templates and organise the various inputs, data storage / security, M&E data management - Supervise data inputs and quality of information from across Scholarships PNG and provide reports to the Partners as required |
| ALA / ALAF Manager |  | 0.25 |  | - Responsible for the ALA / ALAF support to AusAID and scholars - Liaise with AusAID and agencies in PNG and Australia as required to identify suitable opportunities and sponsors - Support AusAID in the short-listing process and in the identification of candidates suitable for consideration |
| ALA / ALAF M&E |  | 0.25 |  | - Support the ALA / ALAF M&E system and collection of data - Provide draft reports and summaries for review by senior staff - Supervise the data entry of the ALA / ALAF scholars and provide exception reports on cases as required - Manage tracer studies and other follow up - Provide QA for all M&E outputs from the ALA / ALAF |
| ALA / ALAF Support staff |  |  | 0.5 |  |
| Regional Development Scholarships coordinator |  | 1 |  | - Responsible for providing RDS support and logistics before arrival, during initial time in PNG and while studying in PNG - Visit each PNG institution / RDS student twice each year and draft summary report for Scholarships PNG and Partners - Maintain contact/ liaison with RDS students and PNG institutions during their stay and following up on any issues or constraints - Ensure that all fees, stipends and costs are made and acquitted - Provide summary RDS reports and options as required to AusAID and NZAID |

|  | High Level staff | Senior Staff | Junior staff | Required Attributes (for Key Staff only) |
| --- | --- | --- | --- | --- |
| Component 2: PNG Professional Development Initiatives |  |  |  |  |
| PNG Professional Development Initiatives Manager | 1 |  |  | - Provide leadership across the Scholarships PNG on HRD and methods to strengthen organisational capacity - Engage with private sector, professional associations, Alumni and leadership groups to promote and advocate the opportunities under Scholarships PNG - Oversee the support provided under the Component and lead the planning, reporting and monitoring functions - Provide leadership to the M&E and to the implementation and reporting of impact / tracer studies - Provide support across the Facility on reintegration strategies, HRD planning and alignment of available resources / courses to identified needs |
| PNG AAA / PNG NZ Alumni Support Activities |  | 0.5 |  | - Liaise closely with the PNGAAA and PNG NZ Alumni leadership to define specific needs - Receive and record any proposals for support - Prepare budgets M&E methods for consideration by Scholarships PNG senior staff - Provide advice and assistance to Alumni as required - Coordinate and QA all reporting and M&E information |
| Young PNG Leaders Activities Coordinator |  | 0.25 |  | - Liaise closely with relevant PNG leadership groups - Receive and record any proposals for support - Prepare budgets M&E methods for consideration by Scholarships PNG senior staff - Provide advice and assistance to Young Leaders as required - Coordinate and QA all reporting and M&E information |
| PNG Prof Assn Activities Coordinator |  | 0.25 |  | - Liaise closely with the PNG Prof Associations - Receive and record any proposals for support - Prepare budgets M&E methods for consideration by Scholarships PNG senior staff - Provide advice and assistance to Prof Assns as required - Coordinate and QA all reporting and M&E information |
| Indicative Scholarships PNG Facility Staff | 4 | 7 | 7 |  |

Component 1: Scholarships to PNG - Service Requirements

- AusAID and NZAID will maintain as the points of contact for key decision points across the scholarships cycle, particularly those activities relating to the short-listing and final selection of candidates. As required, AusAID, NZAID and GoPNG (through the Joint Steering Committee) will discuss and agree on forward priorities, annual scholarship numbers and preferred areas of academic study, including the Scholarship Profiles for use in following year.

- NZAID will also work collaboratively with AusAID and the GoPNG to develop forward policies and plans for their scholarships. The Facility will also manage the NZAID scholarships using the specific methods and processes that will accord with their agreed standards and governance requirements.

- The Facility will undertake the full range of activities related to the advocacy, public (but targeted) advertising, assessment of candidate eligibility, support for institutional placement, student mobilisation, student reintegration, and the monitoring and evaluation (M&E). Reviewing and assessing AusAID scholarship applications requires MC staff to have excellent command of the English language.

- Scholarships’ eligibility requirements are clear but often applications are not well structured, with important information spread through the application. From these applications, a significant amount of technical and personal information needs to be entered on data-bases, requiring operational staff to have the capacity to accurately assess and record information, with nothing overlooked or misunderstood.

- The Facility will receive and review each application for eligibility, following clear guidelines and requirements. It will be imperative that the Facility has the required governance checks and balances in place, to ensure all Scholarship applications received are treated in a confidential, secure and transparent manner. This includes having in place the appropriate staff, systems and levels of supervision in order to eliminate any opportunity for any Scholarship applications to be added, removed or modified. This aspect of governance is crucial and the Facility will ensure that its staff understand the requirements as well as monitor (with senior staff) the scholarship management systems and risk mitigation processes.

- In future it is anticipated that many Scholarship applicants may make use of on-line forms for their information and subsequently lodging the applications (as occurs already with the ALA Scholarships). This dynamic IT environment means that the Facility will need to assign qualified staff who can understand and communicate well in English and who have good ICT skills. These staff skills and IT systems are needed from the outset and the Facility will need the capacity to conduct Scholarships work via the internet and in hard-copy format, including recording and managing the data.

- The Detailed Description of PNG ADS, ALA, NZAID and RDS Scholarship Management Processes and Facility Responsibilities (Annex 8) provides a comprehensive listing of scholarship management services, logistical and operational activities required. The Facility will also have a role in brokering the ALA Fellowships.

Component 2: PNG Professional Development Initiatives – Facility Service Requirements

- As priorities and opportunities emerge, AusAID may task the Facility to develop or manage a range of other targeted initiatives on its behalf. These additional responsibilities will be negotiated with the Facility at the time and (if satisfactory arrangements can be reached) managed under a contract variation.

- Acting on instruction of the Joint Steering Committee, the Facility will respond to emerging priorities through the design, development and implementation of professional and technical activities that meet the identified need. Where possible, the technical expertise, training and other support services will be sourced through partnerships with appropriately certified PNG based organisations and agencies.

- Linkages with Other AusAID and NZAID Initiatives in PNG

- There are a number of AusAID and NZAID funded programs and Facilities in PNG that have sectoral or activity links into the work that the Facility will undertake. The Facility will take into account these donor initiatives, especially if there are opportunities for synergies and cooperation, for example where a scholar returns to an agency that has an AusAID or NZAID funded HRD component. The support and donor initiatives at a GoPNG agency could be accessed (for example) to support the Reintegration process. Relevant AusAID and NZAID initiatives in PNG are included as Annex 7.

- Accessing other AusAID and NZAID initiatives in PNG can also be used in the promotion of the Scholarships, ALA Fellowships and other development opportunities, especially in the provincial areas (i.e. where AusAID staff involved in the Sub National Strategy can be briefed on the various Scholarship opportunities available).

- Supporting and Maintaining Good Relationships

- A number of GOA, GoNZ and GoPNG agencies are involved in the scholarship cycle, and the relationships between AusAID, GoPNG and its Whole of Government (WoG) Australian partners must be understood and supported. From contract commencement, the Facility will ensure that the relationships are fostered at appropriate levels, with boundaries and communication protocols made clear. At all times, prior to working with key GOA, GoNZ and GoPNG stakeholders, the Facility will articulate to AusAID the nature of the engagement and relationship.

- Any Facility visits to GoPNG agencies and associations will be for the sole purpose of advocating and managing the scholarships; brokering Fellowship opportunities; and for human resource related purposes. Any Facility discussions with PNG agencies will not be used to promote or advocate the Facility’s capacities or services for commercial purposes.

- In addition, AusAID will remain the point of contact for GoPNG and WoG partners and the Facility will not approach GoPNG or WoG partners without AusAID approval.

- In a similar way, NZAID will remain the point of contact for GoNZ agencies and the Facility will not approach other GoNZ agencies without prior discussion and endorsement from NZAID.

- Maintaining AusAID and NZAID Posts’ Corporate Knowledge

- AusAID and NZAID will maintain their respective responsibilities for policy engagement with the GoPNG for both their Scholarships and for any professional development initiatives. Staff from both AusAID and NZAID will be involved at key points relating to Scholarship selection, as well as working with GoPNG to initiate other interventions that can cater for emerging needs.

- Maintaining AusAID and NZAID corporate knowledge and skills at the two Posts is essential to enable O-based staff to effectively monitor the contract and also maintain an oversight of the impact.

- The Facility will ensure timely, quality communications are conducted with local and provincial stakeholders and include AusAID and / or NZAID in any interactions of relevance to the Agencies.

- Where the Facility requires AusAID or NZAID input or advice (including for the Annual Planning process) it must allow enough lead time for the Partners to provide a considered response (including consultation with Canberra or Wellington if needed).

- Annex 2 		Draft Implementation Schedule

| Draft Implementation Schedule: The Scholarships PNG Facility - The Initial 10 Quarters |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 |  |  |  |  |  |  |  |  |  |  | 2011 |  |  |  |  |  |  |  |  |  |  |  | 2012 |  |  |  |  |  |  |
| Commencement | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul |
| Finalise contractual arrangements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MC assigns staff and arranges POM office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MC establish support / IT facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initial contact with Joint Steering Committee members |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Security arrangements in place and reviewed annually |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implement transitional arrangements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop Scholarships PNG Operational Handbook for Endorsement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop Scholarships PNG Annual Plan for Endorsement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Joint Steering Committee meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| COMPONENT 1: PNG SCHOLARSHIPS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Scholarships PNG Scholarship Program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Initial visits to GoPNG agencies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop Scholarship Promotion & Communication Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Annual review of Promotion & Communication Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Support Estab of Joint Steering Committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establish M&E system and indicators and implement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop - review Reintegration Plan guide |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide Scholarship materials to agencies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Visit Provinces to promote Scholarship opportunities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Answer queries and provide information as required |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Receive Applications and record |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Enter data onto SIMON / OASIS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Support the short listing process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Support the scholar selection process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Arrange IELTS test for short listed candidates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide academic support and course advice |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Notify successful scholars and reserves |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify candidates for 1-Year In-PNG Degree Course |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Academic Support to identify Aust and NZ Universities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Summary of institutions to AusAID and NZAID |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage all scholar travel / logistics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Refine and deliver PD Briefing program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Scholars to Australia and New Zealand |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Maintain 3 monthly contact with Scholar progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitor / confirm scholar return dates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Refine AusAID / NZAID Tracer Study methods |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct Tracer Studies on scholars |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analyse Tracer data - report to AusAID and NZAID |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify suitable case-study samples |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Undertake approved ADS / NZDS case-studies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analyse data - report to the Partners |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Scholarship Access and Equity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| AusAID provide Profile of target scholars |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Align selection process to priorities / targets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategy for achieving gender / provincial targets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Short-listed receive advice on Aust and NZ unis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Link with PNGAAA, PNG NZ Alumni, returned scholar |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | 2010 |  |  |  |  |  |  |  |  |  |  | 2011 |  |  |  |  |  |  |  |  |  |  |  | 2012 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 1: PNG SCHOLARSHIPS (Cont) | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul |
| Foundation Course |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop selection criteria for approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Include information in Scholarship promotion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify candidates for the Foundation Course |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify a university to provide Foundation Course |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review and endorse Foundation curriculum |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract the PNG university |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Deliver Foundation Course in PNG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitor student progress / QA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Results and outcomes to the Partners |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Year 1 Degree Delivery in PNG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify Priority discipline / cohort |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Selection process for suitable PNG course |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Liaise with Australian universities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Aust / NZ and PNG universities modify course |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agreement on content and QA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract PNG + Aust / NZ uni to deliver |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitor the PNG course and outcomes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Confirm award status / credit received |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide results to nominated Aust / NZ unis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ADS / NZDS enrolment / credit confirmation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mobilise PNG ADS / NZDS cohort to Australia / NZ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The ALAS / ALAF Program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Promote the ALAS scholarships |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Promote ALAF Fellowship opportunities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Receive ALAS applications, record data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Check for ALAS compliance and criteria |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Arrange IELTS test for shortlisted ALA candidates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide applications to AusAID POM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Notify successful ALAS scholars |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Liaise with the Australian ALAF partners |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mobilise ALA scholars/Fellows to Australia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Maintain contact with ALAS / ALAF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide AusAID with summary reports |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Undertake M&E as required by AusAID |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Regional Development Scholarship |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Arrange logistics, permits and arrival to PNG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide pastoral support to RDS students |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitor progress and report to AusAID and NZAID |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Assist students to return home when completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Scholarship Reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Six-Monthly Reports to AusAID and NZAID |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contribute to AusAID / NZAID QAI Reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Annual MC Performance Assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Update Scholarships PNG website |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide M&E to the Partners as required |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | 2010 |  |  |  |  |  |  |  |  |  |  | 2011 |  |  |  |  |  |  |  |  |  |  |  | 2012 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| COMPONENT 2: PNG PROFESSIONAL DEVELOPMENT INITIATIVES | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul |
| PNG Alumni |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review past PNG Alumni arrangements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Support and maintain Alumni data-base |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities-events for Alumni promotion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Six Monthly Alumni Newsletter circulated |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establish network for Alumni mentors |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Alumni engagement with Returnees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Alumni PDB engagement with departing scholars |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Careers in Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Takeover / Novate existing contract in cooperation with AusAID and PATTAF - support as required |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PNG Young Leaders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify opportunities for Ad Hoc support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Quarterly funding as endorsed by AusAID |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitor / report on outcomes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PNG Prof Associations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify opportunities for Ad Hoc support |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Quarterly funding as endorsed by AusAID |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitor / report on outcomes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Annex 3		Critical Risks and Risk Management Strategies

- The following key risks should be addressed by the Facility as part of managing this program. Many of the strategies have been detailed in previous sections (see attached risk matrix).

Political Risk

- By its nature, this Facility will be required to engage with a number of GoPNG, industry and other key stakeholders, across a spectrum of government agencies and sectors. Proposed changes to scholarship processes and governance in Component 1 will see the balance of stakeholder engagement change from existing arrangements and there may be resistance to these changes.

- The Joint Steering Committee will be a key mechanism through which the changes to processes, transparency and decision-making will be introduced.

Risk of Inadequate Service Levels

- The quality of the relationship and communication between AusAID and NZAID in Port Moresby and the Facility is central to achieving a successful Scholarship outcome. The Facility must commit to having an open and transparent relationship with the partners, including advising of any issues or constraints that are having an impact on the Facility or on any of the Partners. As issues arise (be they strategic, operational or to do with Facility staff performance), these will need to be resolved in a timely and constructive manner.

- Value for Money is also a major factor, with the Facility being flexible in their staffing and system availability. This may be necessary (for example) if the number of scholarships increases, or if additional HRD initiatives are required by AusAID to be addressed by the Facility. To reduce this risk, the proposed unit costs of the Facility’s key staff and support services will be assessed as part of the tender, with these unit costs forming part of the contract and any expansion of the Scope of Services (SOS). For the scholarships, it is expected the Facility will accommodate small changes in numbers of ADS and ALAS applications received and processed. If the number increases above a certain agreed percentage a variation to the contract for the Facility may be undertaken.

Risks in Component 1: Scholarships to PNG

There are inherent risks in the management of AusAID and NZAID scholarships programs, including country-specific aspects relating to quality, equity, the number and suitability of applications received, security concerns, the potential for Scholarships to make a development impact that will each require sound risk management.

Loss of AusAID / NZAID Identity in the Scholarship Program

- There can be a tendency for the Facility that is managing scholarships to be perceived more as the funder than as the service provider. To counter this, the Facility will ensure the AusAID and the NZAID profiles (as donors) remains high, including in promotion, administration, management, communications, pre-departure materials and through monitoring activities.

- The Facility will have a contractual requirement to meet the donors’ guidelines on branding and inclusion of the appropriate logo.

Risk of Interference in the Scholarship Selection Process

- Receipt of applications and the selection of candidates are probably the most important elements in the scholarship cycle, requiring the use of eligibility requirements and selection criteria that are clear, open, transparent and easy to understand. The new Scholarship program will better target potential applicants through the development of Scholar Profiles that reflect PNG’s priorities and highlight the role that men and women play in PNG’s development.

- The Scholar Profiles will highlight the GoPNG, AusAID and NZAID focus on gender equality; supporting those with disabilities; supporting those living in the Provinces and a commitment to inclusive development principles. The Facility will support clear selection criteria applied through a process that includes external, independent members. Each selection panel will be chaired by AusAID or NZAID, with the Facility having no voting or selection responsibilities.

- In addition to any external interference, the Facility will be required to have in place the systems and supervision required to ensure internal governance. There will be zero tolerance for any interference or manipulation of scholarship applications or processes by any Facility staff. The Scholarships PNG Facility will be required to clearly demonstrate how it intends to protect the integrity of the scholarship programs, as well as the reputations of AusAID and NZAID.

Risks while Scholars Studying in Australia or New Zealand

As previously detailed, the withdrawal, extension and termination rates for PNG are much higher than for other scholars. Through the introduction of Scholarship Profiles, a more comprehensive process and a longer (12-day) targeted PDP, it is anticipated that PNG scholars will be much better prepared for their study in Australia or New Zealand.

Scholarships PNG will maintain regular email contact with each of the scholars and alert the university (and, if appropriate, the relevant donor) if there are any serious constraints or issues to be addressed.

There are also direct risks when AusAID Scholarship stipends and allowances are not sufficient to support a family while in Australia. In some cases, this can lead to a risk to AusAID’s reputation in not providing a scholar with sufficient financial support to live. Whilst the stipend is deemed efficient for an individual, the reality is that PNG scholars continue to bring their family members with them to Australia.

Risks when Scholars Return to PNG

- There have been many instances where scholars have returned to the PNG government sector and their positions have been reassigned to others, or even abolished. In other cases, the returned scholar cannot find a suitable position within an organisation and does not have the opportunity to apply their new knowledge and skills. Similarly, the returned scholar may not find opportunities to maintain or further develop the skills developed during the scholarship.

- This will be addressed through increased targeting of scholars to meet PNG priority needs; increased focus on Reintegration Planning, at shortlisting as well as on return to PNG; using the PNGAAA and the PNGNZ Alumni to provide information on PNG employment opportunities; and increased focus on scholars being mentored through the private sector in Australia or New Zealand, as part of strengthening their individual professional networks.

Risks in Component 2: PNG Professional Development Initiatives

- There are risks associated with any ad hoc arrangement, including that the scarce resources are not allocated and expended in an equitable manner. In PNG the human resource needs are extensive, with many agencies, organisations and individuals requiring access to better skills and knowledge.

- AusAID will provide the Facility with priorities and initiatives that will need to be addressed in the short term. There is a risk that the Facility’s response to emerging initiatives does not reflect the expectations of AusAID or the partner, e.g. through the Facility staff not having the understanding, skills and insight to develop a response and implement it.

- The draft management diagram and staffing structure clearly indicates that the person responsible for Component 2 must have extensive expertise and the Facility must have in-house HRD expertise and understanding in order to respond to priorities and tasks in a professional, cost-effective and transparent manner, using (where possible) PNG technical expertise and resources for the delivery.

Security and Health Risks in PNG

- Civil unrest and criminal activities in some parts of PNG represent serious, personal security risks, for Facility staff, visiting Australian / New Zealand academics and for RDS students.

- Within a month of commencement, the Facility will develop a Security Plan for use by staff and contractors or consultants. The Security Plan will document key strategies and arrangements, including appropriate methods and systems in place to protect personal, physical and organisational security, as well as for the protection of individual participants’ health.

- Clear, concise and dual language manuals will be provided to all facility staff and long / short term consultants as part of their briefing on the security and health constraints and issues. This manual will also be provided to all staff on their commencement at the Facility. For external (i.e. foreign) visitors or consultants, security and health briefing information will be provided at the time of contracting, so that no person can arrive unprepared in PNG while working on the Facility’s business.

RISK MANAGEMENT MATRIX

| - Major Risk | - Potential Impact on the Program | - Level of Risk | - Aspects in the Design to Minimise Risk | - Actions if Risk Event Happens |
| --- | --- | --- | --- | --- |
| - Program |  |  |  |  |
| - Low number of suitable PNG Scholarship applications received | - Limited number and quality of applications leads to reduced diversity and choice for scholarship awards, as well as limited back-up candidates for any that withdraw | - Medium | - Targeted promotional approaches for the Scholarships - Increased engagement between Facility and the PNG provinces to highlight opportunities for men and women - Joint Steering Committee provides high-level advocacy and oversight to maximise the number of candidates - Targeting of scholarships broad enough to retain a large enough pool of applicants within the principle of development for all | - Review promotion methods and reasons for low response rate - Advise Joint Steering Committee if there are not enough candidates from agencies, sectors and Open category - Consider second application/selection process rather than accept poor quality candidates. |
| - Not enough applications from quality candidates | - The available number of scholarship opportunities not achieved, reducing the effectiveness of the program and the development impact for PNG | - Medium | - All scholarship applications will be directed to the Facility, including capacity to submit electronically or in hard copy - Targeted promotion is part of attracting applicants that have the background, enthusiasm and skills to succeed - Increased liaison with agencies / CSOs / NGOs to promote Scholarships PNG - The Foundation Course will increase the number and capabilities of potential candidates from PNG provinces | - Review promotion and advocacy methods, strengthening and extending the network - Review relationships with agencies, NGOs and associations in order to identify barriers - Monitor the number of candidates from the agencies and Provinces / NCD - Consider second application/selection process rather than accept poor quality candidates. |
| - Scholars do not succeed in their studies while in Australia or New Zealand | - Continued high costs associated with incomplete studies, so less potential for making an impact on their return to agencies and workforce in PNG | - Low | - Strengthening selection process through reformed panels and use of interviews - Closer engagement with the PNG AAA to provide relevant study / living information and sound advice to the selected scholars - Maintain contact with scholars in Australia and NZ. Immediately alert the universities and Partners to potential problems associated with academic or welfare issues, especially among women and those with family members in Australia - Extend and strengthen PDB to better prepare the scholars | - Contact the university and Partners if negative feedback regarding the scholar’s progress or circumstance is encountered - Review selection and the Pre-Departure Briefing if it is found there are areas needing improvement - Implement further diagnostic testing - Provide reports to institutions on where a scholar is going to need further assistance to enable institutions to better cater for the scholar’s needs |

| - Major Risk | - Potential Impact on the Program | - Level of Risk | - Aspects in the Design to Minimise Risk | - Actions if Risk Event Happens |
| --- | --- | --- | --- | --- |
| - Program |  |  |  |  |
| - Graduates do not return to PNG and contribute to development | - Limited development benefit from the scholarship and consequent high opportunity cost; low scoring aid effectiveness | - High | - Implement Reintegration planning process early in the cycle - Strengthen engagement with the PNGAAA and the PNG NZ Alumni, especially to maintain professional contact and enthusiasm when scholars return to PNG - Follow up via Reintegration Plan surveys to monitor progress and provide feedback and encouragement where possible, especially in cases where women may have lost their employment during their study in Australia or New Zealand | - Through Reintegration Plan encourage scholar and agency to execute meaningful work - Assist graduate to change jobs where their skills may be better utilised. - Liaise with the agency and PNGAAA and PNG NZ Alumni to support returned men and women scholars - further scholarships not provided to agencies that do not support graduates to reintegrate effectively |
| - Facility successful in brokering ALAF: not all PNG proposals supported; ALAF competitive/regional | - Damage to relationships if the Facility and PNG organisation put in considerable resources to develop an ALAF submission and are unsuccessful because of competition for funds | - Medium | - Brokering and advocacy are carefully targeted to maintain quality and relevance to PNG development, making the ALAF highly competitive in relation to other regional applications | - Make sure that all stakeholders are aware that the ALAF is a competitive process and that no set “quota” of ALAF exists for any country. |
| - Poor Governance in Selection and Management | - Perceptions that the Scholarship selection process is contaminated and not managed in a fair or equitable manner. | - Medium | - Key elements of scholarship management process remain with AusAID and NZAID (including selection). - Transparent process for promoting opportunities and the receipt of applications, including mailing back to each applicant confirmation that their application has been received - Introduction of the Profiles will transparently define the eligibility and selection criteria - Facility must have guidelines and strong systems in place - Facility must have a risk management framework in place that includes strategies to mitigate this particular risk - Facility must demonstrate an ethos of open and transparent, consultative, quality service provision - An Independent Mid-Term Review | - Immediate discussions between AusAID / NZAID and Facility on any negative perceptions. - Facility to increase efforts to model and demonstrate governance, transparency and its ‘open for business’ ethos. - Review Facility’s internal “checks and balances” to tighten any governance problems. - Contract not extended if major flaws are identified and not rectified |

| - Major Risk | - Potential Impact on the Program | - Level of Risk | - Aspects in the Design to Minimise Risk | - Actions if Risk Event Happens |
| --- | --- | --- | --- | --- |
| - Program |  |  |  |  |
| - Limited Service Level Consistency | - Variable levels of support and service to AusAID and NZAID Post, leading to confusion by staff and the applicants/scholars. | - High | - Clear responsibilities allocated to the Facility and all staff tasks well identified and allocated. - Annual review of Facility performance, including discussion and application of the lessons learned. | - Immediate action by Facility should discrepancies in service levels between staff become apparent. - Facility to rectify any staff problems to be reflected in Facility performance measures. |
| - Facility staff not functioning at required level | - Staff not skilled or equipped to undertake the work, through a lack in capacity, not enough training on systems and processes or lack of communication and interpersonal skills | - Medium | - Staff quality / technical attributes included in RFT and the quality standards required - Clear guidelines on the service levels required - Clear definition of the Facility staff language, IT and communication requirements included in the tender | - Immediate AusAID (with NZAID) discussions with the Facility Senior Manager assigned to oversee the outsourced work. - Facility makes staff changes when required to make sure that quality is maintained. - Contract can be terminated. |
| - Lack of Systems and Resources | - The Finance, IT (including OASIS and other computer-based systems) and systems unable to support Facility’s service delivery and its management requirements. | - Low | - Clear guidelines on the system requirements, including a draft minimum staffing schedule - Independent Mid-Term Review will be conducted to gauge the Facility’s ongoing capacity to deliver the services | - Immediate AusAID discussions on problems and what is required to fix them. - Facility makes system changes as required. - Contract will not be extended or possibly terminated for a major problem. |
| - AusAID and NZAID lose identity | - The profiles of AusAID and NZAID as the funding agencies are lost via the Facility and its management taking too high a profile position in management. | - High | - Clear guidelines on how to badge Facility for promotion, processing of applications and engagement with GoPNG - Clear statements on the way in which the “branding” of the scholarships will remain with Australia / AusAID and New Zealand / NZAID - Local AusAID and NZAID staff involved in scholarship process. | - Facility to show examples of how it will be required to maintain AusAID’s and NAZAID’s profiles in the scholarship management. - AusAID and NZAID to monitor promotional materials, business cards, guidelines, advertisements, email / letter identifiers |
| - Lack of quality in relation to delivery of Foundation Year and Pilot Year 1 of Scholarships in PNG | - Poor outcomes for Scholarships PNG and no improvement on scholar success rates in the longer term | - Medium | - Careful selection of the Foundation course for Provincial applicants - Clear guidelines for Piloting joint delivery of Year 1 of Scholarships PNG awards and careful selection of the partnering Australian / NZ university - Comparative monitoring of progress of scholars in relation to past | - Review contract to deliver Foundation course - Review contract and twinning arrangements to deliver Year 1 of Scholarships PNG awards in a PNG institution - Ongoing monitoring of quality and progress |

| - Major Risk | - Potential Impact on the Program | - Level of Risk | - Aspects in the Design to Minimise Risk | - Actions if Risk Event Happens |
| --- | --- | --- | --- | --- |
| - Program |  |  |  |  |
| - Confusion on Facility Management Roles | - Important steps in scholarships and management left out until it is too late. | - Medium | - Clear identification of AusAID, NZAID, Partner and Facility roles and responsibilities included in the SOS. - Discussions and handover at contract commencement to ensure Facility is clear on what is required and how it will be delivered. | - Immediate intervention from AusAID if required, which will be reflected in the Facility contract performance measures. - Joint Steering Committee intervenes if required |
| - Emerging needs in PNG are not addressed | - The Scholarships and Professional Development components are not responsive to the real PNG needs, with their initiatives not targeted or of sufficient impact | - Medium | - Joint Steering Committee oversees the activities and will provide contemporary advice and guidance, including encouraging and facilitating women gaining qualifications in order that they can enter higher skilled occupations in PNG - AusAID has a role in identifying / endorsing and contracting the Facility to undertake the initiatives - Each initiative to include appropriate M&E - Members of the selection committee to be fully cognizant of the objectives and targeted inputs | - AusAID and / or the Joint Steering Committee direct the Facility in its response - Improve communication between AusAID and the Facility to ensure that the emerging needs are analysed and met |
| - Impact of the Facility | - Little feedback on contribution of returned PNG scholars, including how studies support GoPNG strategies. - Limited impact from Professional Development component - Cost of Facility outweighed by value achieved from it. | - High | - Increased focus in the design on impact and on stronger engagement (i.e. PNGAAA, PNG NZ Alumni) as part of strengthening networks and support mechanisms, - Increased focus on human resource planning, including the Reintegration into the agency on return. - Increased focus on monitoring all activity progress and impact, through strong M&E systems. - Requirement that Facility staff have the necessary background and specialist expertise to understand HRD and to respond with appropriate strategies - Requirement for MTR to do a cost/benefit analysis of Facility. | - AusAID and NZAID lead role in monitoring impact through tasking case and tracer studies - Review scholar reintegration process in ways that maximise success and impact. - The Joint Steering Committee to monitor impact of all projects and activities on an ongoing basis - Not to extend the contract if the mid-term review reveals a lack of value for the cost of running the Facility |

| - Major Risk | - Potential Impact on the Program | - Level of Risk | - Aspects in the Design to Minimise Risk | - Actions if Risk Event Happens |
| --- | --- | --- | --- | --- |
| - Cross Cutting issues |  |  |  |  |
| - Lack of Selection Equity in the 2 components | - Not enough applications for scholarships from eligible women, people with disability or studying in the area of disability, or from non-urban. Results in lost opportunities for women and people from other disadvantaged groups. | - Medium | - Wide promotion of scholarship opportunities to ensure eligible quality candidates are encouraged to submit an application. - Clear guidelines developed for all parts of the Facility where a competitive process will be used to select activities or scholarships for funding - Facility must meet key performance measures for targeted applicants. | - Monitor profile of applications / proposals; selection criteria clear and easily followed - Monitor the Facility to ensure that there is a spread of activity across PNG - Maintain and extend existing networks so that the opportunities under Scholarships PNG are well understood - Facility provide strategies to reach target applicants |
| - Loss of AusAID or NZAID Control | - With staff changes at AusAID or NZAID Posts, a danger that institutional memory will increasingly reside with the Facility. | - Medium | - AusAID and NZAID staff still involved in key elements of the process to facilitate continuity. - Summary of responsibilities, roles, outcomes included in SOS, will make it easier for new AusAID or NZAID staff to familiarise. - Facility will be required to maintain accurate records and provide detailed invoices. | - AusAID and NZAID to ensure its new staff are aware of the arrangements and understand the role and responsibilities of the Facility |
| - Addressing HIV AIDS and Child Protection | - The Facility does not fulfill its obligations in key areas | - Medium | - Cross cutting issues embedded across design to mainstream the required approaches and safeguards - Inclusion of specific funded activities involving HIV AIDS, the Provincial Support Initiative, the 2-year Foundation Course and Child Protection policies make it clear what is required | - Monitor the cross cutting data and implementation methods and ensure that the Facility is operated in a way that supports equity, access and good governance |
| - Design / program cause unintended vulnerabilities or risk for HIV and AIDS | - Increased HIV infection rates amongst program participants and/or their family members | - Low | - Pre-departure HIV briefing, training and education for scholars studying in Australia and for their families | - Assess logistical arrangements and pre-departure briefing to determine ways to further mitigate the risk |
| - Security Risks for Facility staff / scholars | - Civil unrest and / or criminal activity in PNG leads to increased security problems and danger to staff / scholars / dependants | - High | - Clear statements on the importance of personal security and the requirement for a Security Plan for all Facility staff and other consultants under the scholarship initiatives | - Develop and update Security Plan for staff/scholars. - AusAID or NZAID to advise Facility on any specific security information as required - Facility to monitor the PNG security context in relation to where activities are implemented |

| - Major Risk | - Potential Impact on the Program | - Level of Risk | - Aspects in the Design to Minimise Risk | - Actions if Risk Event Happens |
| --- | --- | --- | --- | --- |
| - Health Risks | - Poor health conditions in PNG, including Malaria, lead to staff infections | - High | - Clear statement on the health risks and the obligations of the Facility to manage health risks for its staff and consultants - The Facility requires arrangements in place for emergency health evacuation in case of an emergency - All consultants and employees to be regularly briefed on the health risks and mitigation options | - Facility to update its PNG health risk assessment and emergency arrangements on a continual basis - Appropriate insurances maintained and used as required |
| - Social Risks | - Domestic violence or antagonism against awardees by jealous spouse leading to withdrawal of application | - Medium | - The Facility requires counselling skills to deal with the situation and to encourage the applicant/awardee to take action against the perpetrator and to continue with their application | - Determine ways to further mitigate the risk, such as Facility providing briefing sessions to potential applicants and spouse/family prior to applications being submitted |
|  | - Domestic violence against scholars by accompanying spouse causing disruption to studies | - Medium | - The Facility includes a session in the latter part of the Pre-Departure Briefing, at which spouses will be present, on unacceptable behaviour in Australia or NZ and the zero tolerance to domestic violence | - AusAID and NZAID work with HE institutions and relevant agencies on mitigating risk and what ‘zero tolerance’ means for PNG scholars. - Assess PDB and Institutions’ academic programs for opportunities to educate scholars and their spouses on this issue. |
| - Political |  |  |  |  |
| - Lack of support and resistance from key GoPNG agencies | - The design initiatives of the Scholarships and professional development are not supported by agencies or key stakeholders | - High | - AusAID directly involve key GoPNG agencies in the development of the Profiles, as part of highlighting preferred sectors - Clear statements that the Facility is responding to PNG priorities as jointly agreed with AusAID - Members of key GoPNG agencies and PNG private sector on the Joint Steering Committee | - Monitor constraints to the Facility and any barriers that are placed on implementation - Facility to monitor applications received: establish if internal constraints are playing a part in who applies. - Advise AusAID and NZAID if political pressure applied in relation to implementation |
| - Change in PNG Government | - Potential for AusAID initiatives to be affected by change in the GoPNG | - Low | - Responsibility for engagement with GoPNG remains with AusAID, so that any potential for reducing impact can be discussed and changes made. | - AusAID to monitor potential changes to GoPNG policies and advise when possible. |
| - Facility perceived as being politically motivated | - Potential that the Facility can favour certain groups in the selection processes | - Medium | - Use transparent processes - Public notification of Facility initiatives in advance - Facility contact AusAID immediately of any interference | - AusAID to continue to promote the fairness and equity of the Facility - Joint Steering Committee promotes the neutrality and selection that is based on merit |

- Annex 4

# 4.1	Monitoring and Evaluation Framework

# 4.2	Monitoring and Evaluation Methods and Tools

| Objective | Indicator: (Where appropriate Scholarships PNG will disaggregate indicators by gender, province, field of study, participating PNG / Australian / New Zealand institution) | Source of Information | Frequency of Collection | Responsibility for collection |
| --- | --- | --- | --- | --- |
| Component 1: Scholarships Program Objective 1 To provide men and women with the skills and knowledge to contribute to PNG’s economic and social development within the priority areas of National and Provincial governments. Objective 2 To provide men and women with the skills and knowledge to contribute to PNG’s economic and social development within the private sector and civil society. | Public Category (GoPNG) Scholarships Outcome level indicators Number and annotated list of contributions by Scholarship alumni to policies, practices and research to support GoPNG. Compilation of above contributions made to each of the jointly developed priorities and provinces, in relation to broader MDGs. Proportion of Public Scholarship graduates who are reintegrated back into their employment, including those going into Provincial / rural PNG. Output/Input level indicators (gender disaggregated) Performance against an agreed Annual Plan (indicators determined in each Plan). Academic success of the Scholarships PNG Public program compared to base line data from previous PNG ADS/ALA/NZAID scholarship programs Includes the Foundation Year; the IELTS testing; extended PDP and delivery of 1st Year in PNG). Annual and cumulative summary of all Scholarships PNG applications received, as well total from eligible GoPNG men and women candidates in the agreed PNG priorities. Annual and cumulative number of Public Scholarships awarded for the 3 Public PNG priorities, including number of successful candidates with disabilities. Annual and cumulative number of extensions and terminations for scholars from the 3 Public PNG priorities. Annual and cumulative number of graduates that return to work in NCD for each of the 3 Public PNG priorities, including applying their Reintegration Plans for at least 1 year. Annual and cumulative number of graduates that return to work in the PNG provinces for each of the 3 Public PNG priorities, including applying their Reintegration Plans. 6-Monthly summary report of the personal contact made with scholars in Australia and New Zealand, including any issues or constraints that require action by the individual, the institution or the Partners. | Alumni and institution / organisation reporting on progress against Reintegration Plans. Tracer studies and case studies MSC stories Comparative analysis of success Facility SIMON/OASIS Alumni database ADS Scholar / Tertiary institution | As required by Partners Ongoing Annual Annual Annual Annual 6-Monthly | Facility Facility AusAID Facility PNGAAA PNG NZ Alumni |
|  | Indicator: (Where appropriate Scholarships PNG will disaggregate indicators by gender, province, field of study, participating PNG / Australian / New Zealand institution) | Source of Information | Frequency of Collection | Responsibility for collection |
|  | Open (Private Sector / NGO / CSO / Faith Based / Individual) category Outcome level indicators Number and annotated list of contributions by Scholarship alumni to policies, practices and research to support GoPNG. Number and annotated list of AusAID alumni employed within the private sector in the agreed PNG priority sectors, particularly in the PNG provinces. Compilations of the above contributions made to each of the designated sectors and targeted provinces. Proportion of Open graduates who are reintegrated into Provincial / rural PNG. Output/Input level indicators (gender disaggregated) Performance against an agreed Annual Plan (indicators determined in each Plan). The academic success of the Scholarships PNG Open program in relation to the base line data from the previous PNG ADS / ALA / NZAID scholarship programs. Annual and cumulative summary of all Scholarships PNG applications received, as well as total of eligible Open men and women candidates in agreed priorities and key areas of development. Annual and cumulative number of Open scholarships awarded for the 3 Open PNG priorities and other key areas of development, including number of successful ADS candidates with disabilities. Annual and cumulative number of extensions and terminations for scholars. Annual and cumulative number of graduates that return to work in NCD, including for each of the 3 Open priorities. Annual and cumulative number of graduates that return to work in the PNG Provinces, Including for each of the 3 Open priorities. 6-Monthly summary of the personal contact with scholars in Australia and New Zealand, including any issues or constraints that require action by the individual, the institution or the Partners. | Facility and institution reporting on progress against Reintegration Plans. Tracer studies and case studies MSC stories SIMON/OASIS Facility data-base ADS Scholar / Tertiary institution | As required by Partners Ongoing Annual Annual Annual Annual Annual 6-Monthly | Facility AusAID Facility / Institutions Facility PNGAAA PNG NZ Alumni |

|  | Indicator: (Where appropriate Scholarships PNG will disaggregate indicators by gender, province, field of study, participating PNG / Australian / New Zealand institution) | Source of Information | Frequency of Collection | Responsibility for collection |
| --- | --- | --- | --- | --- |
|  | ALA Scholarships Outcome level indicators Contributions by ALA Scholarship alumni to policies, practices and research in PNG, including in those areas which contribute to PNG’s future development. Participation in professional networking opportunities by ALA Scholarship alumni at the local, regional and global level, including those in those areas relevant to PNG’s development needs. Output/Input level indicators (gender disaggregated) The academic success of the ALAS program in relation to the base line data from the previous PNG ALAS scholarship programs. Annual and cumulative number and % of applications received from eligible ALA Scholarship candidates. Annual and cumulative number and % of ALA Scholarships awarded Annual and cumulative number and % of extensions and terminations for scholars from the ALA Scholarships program Annual and cumulative number and % of ALA Scholarship graduates that return to work in PNG, both in NCD and in the Provinces. | Alumni and institution reporting on progress. Tracer studies and case studies MSC stories PNGAAA PNG NZ Alumni SIMON/OASIS Facility data-base Alumni database | 6-months; one, three and five years Annual Annual Annual | Facility AusAID Facility Facility |
|  | RDS Outcome level indicators Determined by Regional ARDS management within the regional country Output/Input level indicators (gender disaggregated) Annual and cumulative number of RDS scholars arriving in PNG to study. Annual and cumulative number and % of RDS graduates, by country, institution, award and gender. 3-Monthly summary of contact with RDS scholars in PNG, including issues or constraints that require action by the individual, the PNG institution or RDS. | RDS Facility data-base PNG Institutions RDS Scholar / PNG Institution | As required by RDS Annual Annual Quarterly | As required by RDS Facility Facility / PNG Institution Facility |

|  | Indicator: (Where appropriate Scholarships PNG will disaggregate all indicators by gender, province and field of study). This part of the M&E Framework must also remain flexible, to incorporate PNG HRD priorities as they arise and are addressed. | Source of Information | Frequency of Collection |  | Responsibility for collection |
| --- | --- | --- | --- | --- | --- |
| Component 2: PNG Professional Development Initiatives |  |  |  |  |  |
| Objective 3 To empower young women and men to actively participate in the development of Civil Society. | Outcome level indicators Number and annotated list of new or revised organisational, operational or technical skills (including improvement to services) achieved by PNG Partners with the provision of Facility funding or via direct support of the AusAID Alumni. Output/Input level indicators (gender disaggregated) Performance against agreed Annual Plan (indicators determined in each Plan). Annual and cumulative number of PNG professional development requests for funding received to support management and skills development. Annual and cumulative number of initiatives / consultants approved and mobilised by the Facility. Annual and cumulative number of new HRD policies, systems and management processes introduced in PNG with support of AusAID resources or via AusAID Alumni. | PNG Partner Institutions MSC stories Facility Facility PNG Partner Institutions | Annual Ongoing Annual Annual Annual | PNG Partner Institutions Facility Facility Facility / PNG Partner Institutions |  |
|  | Indicator: (Where appropriate Scholarships PNG will disaggregate all indicators by gender, province and field of study). This part of the M&E Framework must also remain flexible, to incorporate PNG HRD priorities as they arise and are addressed. | Source of Information | Frequency of Collection | Responsibility for collection |  |
| Objective 4 To strengthen identified professional bodies to provide to their membership opportunities to develop skills and knowledge essential to achieve best practice in the operation of PNG industry, CSOs and government. | Outcome level indicators Output/Input level indicators Annual and cumulative number of PNG association, professional development requests for funding received by men and women to support management and skills development. Annual and cumulative number of HRD initiatives / consultants approved and mobilised by the Facility. Annual and cumulative number of new policies, systems, management processes introduced in PNG with support of AusAID or via AusAID Alumni. | PNG Partner Institutions Facility Facility PNG Partner Institutions | Annual Annual Annual Annual | PNG Partner Institutions Facility Facility Facility / PNG Partner Institutions |  |
|  | ALA Fellowships Outcome level indicators PNG organisations reporting that ALA Fellows have made an extra contribution to the organisation as a result of Fellowship activity in Australia (e.g. passed on knowledge, influenced policy, etc). Sustainability of linkages between the Australian host organisation and the counterpart organisation in PNG. Output/Input level indicators (gender disaggregated) Annual and cumulative number of applications received from Australian organisations seeking to host PNG Fellows. Annual and cumulative number of ALAF awarded in PNG | Alumni and institution reporting on progress. Tracer studies and case studies (for all ALAF) Facility data-base | As required by AusAID By Round | Facility AusAID Facility |  |
| Objective 5 To strengthen the capacity and profile of Australian and NZ Alumni in PNG. | Outcome level indicators Increased engagement of the PNG-Australia Alumni in the implementation of the AusAID scholarship program, in research or consulting activities, and as contributors to development issues in PNG. Output/Input level indicators (gender disaggregated) Annual number of AusAID funded Alumni members who are members within the PNG Australia Alumni Association. Annual and cumulative number of men and women Alumni members that are directly engaged in processes that cover selection, preparation, mobilisation and the return of AusAID scholarship participants. Annual number of consulting contracts and projects that are externally funded and undertaken by the Alumni. Number of technical and social events held in PNG and involving a professional contribution to, or management by, PNG Australian Alumni | PNGAAA / PNG NZ Alumni / Facility PNGAAA / PNG NZ Alumni Facility PNGAAA / PNG NZ Alumni PNGAAA / PNG NZ Alumni | Annual Annual Annual Annual Annual | Facility PNGAAA Facility PNGAAA / PNG NZ Alumni PNGAAA /PNG NZ Alumni |  |

Annex 4.2	Monitoring & Evaluation Methods and Tools

General M&E Comments

Information on awardees is required at all stages of the Scholarships cycle – the selection, in-country preparation, in Australia and New Zealand progress, award completion and the impact post-award. The M&E Plan will be aligned with the Annual Planning process for the Facility and include:

- Regular collection and analysis of information that assists decision-making, ensures accountability and provides the basis for evaluation and learning. This will provide early indications of progress and achievement of objectives for the two major components.

- A systematic independent review of the Program at the end of Year 3, to determine achievement and progress against objectives in the three components, as well as lessons learned to improve future actions.

Facility management processes will be assessed in separate AusAID Quality at Implementation (QAI), NZAID reports, Sector Performance Reports and the annual contractor performance reviews, undertaken in accordance with a standard performance management framework.

For the PNG Professional Development Initiatives (Component 2) each of the proposed initiatives that have been tasked by the Joint Steering Committee / AusAID will each require a set of concise, relevant M&E measures. As part of designing a response to a request for an activity or support, the Facility will provide AusAID and the Joint Steering Committee with the draft M&E for approval. The M&E information for Component 2 will also be structured to feed directly into the broader Facility M&E Framework.

Monitoring and Evaluation of Component 1: Scholarships to PNG

All data collected will be gender-disaggregated, identify those applicants with a disability, and will record the provincial location and employment of scholarship applicants prior to taking up a scholarship, and of the graduates on their return. Subsequent analysis will be required to assess the contribution of graduates to furthering development in PNG and any constraints or barriers for women and men, for people with disability, and for those from PNG’s Provinces or rural areas.

In particular, the M&E will incorporate measure that can be compared with the existing data under the PATTAF. This will be particularly important for monitoring the success (or otherwise) if the new initiatives being incorporated into the scholarship cycle “front end”, especially the impact on scholarship extensions, downgrades and terminations.

The Facility will establish and maintain a database to record all M&E data collected. The Facility will develop and use a range of M&E methods/tools, and will be required to monitor and evaluate scholarship outcomes for scholars selected prior to and after the introduction of the new profiling approach. M&E methods and tools will include:

Scholarship Student Records: the Facility will keep scholar records/profiles up-to-date on SIMON/OASIS, including contact details once scholars return to PNG. These records will be used to track progress and to compare actual scholarships versus the targets, in terms of priority areas/sectors, gender, Open vs. Public, as well as representation from Provinces.

The Facility will also ensure that the scholars advise the Facility and their home agencies of their academic progress, as well as their anticipated return date to PNG.

The Facility will also analyse the previous levels of award terminations, downgrades and extensions, in relation to the four interventions of IELTS testing; the Foundation year for Provincial candidates; the extended PDB; and delivery of parts of the Scholarship in PNG.

- Scholar Reintegration – Proposed Reintegration Plans will be jointly developed by short-listed candidates in the Public category and a supervisor within their organisations / agencies. The Facility will collect and analyse data contained in these Reintegration Plans and establish a system/survey instrument to monitor progress against the plans, involving both the returned scholar and their GoPNG supervisors. Care will be taken to identify (as relevant) where any other AusAID or NZAID activities are underway within those agencies and organisations, in order to provide some Reintegration support when the scholars return.

- Annual Student Surveys and Focus groups – AusAID’s Scholarship Section administer annual student surveys and conduct annual student focus groups for awardees while studying in Australia, including:

- Arrival survey and focus groups, to obtain perception/satisfaction of students with the selection and mobilisation processes, pre-departure briefing, perceptions of HIV + AIDS risk and vulnerability, gender equality, IAP and quality of courses.

- On-going student survey and focus groups, to obtain perception/satisfaction with services and programs provided by academic institutions and experiences in Australia.

- The Facility and AusAID / NZAID will utilise the results of these annual surveys to improve the student recruitment, selection process, mobilisation and the pre-departure activities.

- Tracer Studies and Case Studies –Tracer studies capture information on scholarship outcomes for individual awardees and (based on guidance provided by Scholarships Section) will be tailored to the PNG context and development priorities. Each tracer study will focus on returned scholars back for 6-12 months and again after two years. The studies will explore issues including successful reintegration into PNG, are the skills being used effectively, how their skills contribute to the organisational capacity and their ongoing links to Australia or New Zealand.

- The number, timing and target of tracer studies will be provided by AusAID and NZAID, funded on a reimbursable basis. It is planned that a long-term tracer study will be conducted during the program, covering key sectors and agencies in NCD and in the Provinces.

- The collection of stories from the field, relating to the identification of Most Significant Change, will also be managed by the Facility, with a view to identifying impact and describing sustained changes or reforms.

- Arising from the tracer studies and MSC stories, a smaller number of individual case studies will emerge. These may be suitable for more detailed qualitative assessment on how the Scholarship graduates have contributed. These will provide information for the purpose of positive news stories for media, the PNGAAA / PMNG NZ Alumni newsletters etc.

Monitoring and Evaluation of Component 2: PNG Professional Development Initiatives

This part of the M&E Framework will need to remain flexible in its inclusion of indicators and outcomes. As HRD priorities emerge and are addressed by the Facility, the new indicators and outcomes will be inserted, based on the approved activity: i.e. for each professional development initiative, indicators and M&E methods will be incorporated into the Framework on a case by case basis and to match the requirements and capacity of the organisations concerned.

The funding support to local PNG organisations, associations and agencies will also be contingent on the capacity of the beneficiaries to be able to apply and sustain the new skills and knowledge gained within their own professional, agency or workplace context.

- Annex 5		Contractor Performance Criteria

|  | - Scholarships PNG Contractor Performance Criteria |
| --- | --- |
| - 1. Personnel Performance | All Contractor personnel: - Act professionally and with integrity, and produce high quality work ; - Communicate in a clear, transparent and effective manner; and - Deliver outputs on time. |
| - 2. Program Management | - Good working relationships with AusAID and NZAID Post, as well as effective coordination and consistency of service levels. - Good working relationships with GoPNG - Finances are soundly and transparently managed and financial reporting meets AusAID requirements. - Reports are clear, constructive, accurate, timely and meet the expectations of AusAID and the Partners. - Responsiveness to the reporting, management and planning needs of the Partners. - Ongoing monitoring and evaluation is undertaken effectively and is being analysed and reflected in continuous improvement by the implementing team. |
| - 3. Communication and Coordination | - Clear management arrangements and effective communication between all Contractor Personnel and between Contractor Personnel and AusAID. - Personnel take proactive steps to ensure effective communication and working relationships with all stakeholders. - Identifies and reports any major difficulties in stakeholder relationships to AusAID or NZAID as they arise. |
| - 4. Scholarship Management | - Australian and NZ Scholarship promotional, management and monitoring processes implemented effectively and efficiently. - Proactive steps taken to improve promotional, management and monitoring processes, in consultation with AusAID and NZAID. - Target number of male and female students mobilised efficiently and on time, including attention to cross cutting scholarship issues of gender, disability, access and equity, with an effective PDB which involves relevant PNGAAA and PNG NZ Alumni presentations. - Ongoing three-monthly contact maintained with all scholars in Australia and New Zealand with reporting as appropriate. - All documents, applications, responses, scholar acceptances and the PDB carried out on time and required information recorded in the database. - Effective, appropriate counseling and placement of scholars in courses relevant to their academic needs, in a cross-section of Australian and New Zealand universities. - Maintain information on scholar returns: provide advice to AusAID Post of any issues. - Identify and contract PNG institutions for the delivery of the Foundation program and for the delivery of Year 1 of the course in PNG. - Addresses improved access and gender equity as part of Scholarships promotion. - Appropriate Australian / NZ Government and AusAID Scholarships profile is acknowledged and maintained. - Innovative methods used to appropriately target Scholarship opportunities to a broader group of quality PNG candidates. - Innovative methods are used that offer realistic reintegration support services. - Continuous Improvement, including being proactive in assessing the previous 12 months activities and in suggesting appropriate and realistic changes or new methods. |

|  | - Scholarships PNG Contractor Performance Criteria |
| --- | --- |
| - 5. PNG Professional Development Initiatives | - Facility is responsive to the tasks and initiatives requested by AusAID. - The available funding is allocated in a timely manner. - Appropriate AusAID profile is maintained. - Support to a number of leadership and professional association in PNG. |
| - 6. The PNG AAA | - Alumni receive support (as requested) to function effectively. - Alumni database provides up-to-date information on returned scholars as well as a tool for broadcast emails or for Facility sending the Alumni newsletter. - Facility provides AusAID with suggestions and methods to enhance the Alumni profile and its engagement with ongoing and returned scholars. - Returned scholars engaged in Scholarship activities as mentors and supporters. |
| - 7. Risk Management | - Management issues are identified and resolved in a timely manner and/or reported to AusAID for decision where relevant. - Management provides sound analysis of risks and develops and applies effective risk management measures. - Personnel respond effectively to new or changed environments or requirements from AusAID. |
| - 8. Cross-cutting targets | - Progress against cross-cutting targets, as specified in the design. - Through management processes, staff and systems, model good practice in relation to all cross-cutting issues and priorities. |

- Annex 6		Sample Template for Scholarships PNG Priority Sectors

Priority Profile Templates for Open category; Public category; and the ALA.

| Profile | Public Sector Policy Makers and Practitioners in the XX Priority Area |
| --- | --- |
| Purpose | Within Central and Provincial GoPNG agencies employing AusAID Alumni, increased application of policies and practice contributing to governance and equitable service delivery, particularly in the priority areas. |
| Outputs | - Number of Scholarships available in this priority area = 30 plus - A minimum of 15 of these scholarships are reserved for female candidates. |
| Relevant Outcome: | Increase in the number of qualified GoPNG officials, particularly those working within the designated priority areas and those posted in the Provinces, strengthening and adding value to policy development, practice, resource allocation and service delivery. |
| Eligible Groups / Areas | This profile includes applicants employed in Central or Provincial level public institutions and working on the designated areas. This will include applicants who are mid level Government employees who can demonstrate the potential to influence policy, or who are practitioners working, facilitating or delivering services in the designated priority areas. Candidates from PNG’s Provinces are encouraged to apply. Females, people with disability and people from other disadvantaged groups are encouraged to apply. |
| Strategies to gain Applications | - Target relevant GoPNG Ministries at Central and Provincial levels working on the priority sectors: conduct meetings with HR managers and provide application forms to HR departments, encouraging internal advertisement and support of Scholarship applications - Where possible, conduct promotional activities, including direct presentations, to selected Ministries, including in the major provincial centres - Targeted advertisements in national and provincial media inviting applications - Provide access to hard-copy application information packs and advice on web-based application forms option - Clear instructions that completed application forms are to be sent direct to the Scholarships PNG Facility in POM |
| Eligibility requirements | All applicants must meet the following eligibility requirements: - be a citizen of PNG - employed at GoPNG central or provincial agency, statutory authority or other instrumentality - be applying to study at undergraduate or postgraduate level at an accredited Australian university - have relevant work experience in the GoPNG public sector - have the minimum education requirements to be admitted into the nominated level of study at an Australian university |
| Support Services Available | - Relevant information available on the website: eligibility requirements, priority areas, selection criteria, selection process, application form; frequently asked questions; timeline for PNG scholarships cycle; and guidance on how to fill in the application form - All queries responded to within 3 to 4 working days. - At NCD and Provincial Scholarship presentation sessions, queries responded to at completion - Hardcopy Scholarship application packs available to Central and Provincial public sector - Successful candidates will be provided contact details of PNGAAA and PNG NZ Alumni - For Provincial applicants, potential to qualify for a 10-month Foundation Course in PNG, involving English language training (including research and writing techniques), basic skills development (maths, study skills) and training in the use of IT. Persons completing this course will receive a recognised qualification and can either return to their Province to work, or be in a stronger position to apply for a future scholarship. |

- Annex 7	Summary of Related AusAID and NZAID Programs in PNG

The following AusAID and NZAID programs are currently underway throughout PNG. There should be opportunities for these existing initiatives to support the identification or potential scholars, as well as to support the reintegration of scholars on their return to PNG.

AusAID Funded Programs and Related Activities in PNG

- Education Capacity Building Program (ECBP) is an evolving sector-wide approach (SWAp) that works collaboratively within existing PNG systems. It provides technical assistance and training to strengthen planning, management and governance procedures and improve communication and coordination between government agencies and the levels of administration which make up the education system;

- AusAID contributes 10% of PNG’s education budget, strengthening the quality of (and accessibility to) elementary, primary and secondary education. Support to basic education will better prepare students to embark on secondary, technical and vocational education, and for some higher education studies. These students will eventually contribute their acquired skills and knowledge to PNG’s economic development;

- Institute of National Affairs (INA) receives ad hoc assistance from AusAID for initiatives of mutual interest such as good governance, anti-corruption, education and health. INA works in collaboration with PNG institutions in the running of workshops and conferences.

- Economic and Public Sector Program (EPSP) captures elements of the Advisory Support Facility (ASF) and short term training elements currently within the Papua New Guinea Australia Targeted Training Facility (PATTAF). The EPSP also works with the Human Resource Management network, a PNG wide network of HR managers from the public sector.

- Pacific Leadership Program (PLP) supports current and emerging Pacific leaders to pursue studies and experiences in leadership and good governance. A second program area promotes models of good leadership practice in the six priority countries of PNG, Solomon Islands, Vanuatu, Tonga, Samoa and East Timor. Women, youth, church, sports, business and media associations are included in the partnerships, managed from AusAID in Suva.

- Pacific Public Sector Capacity Building Initiative (PSCBI) provides support for HRD in PNG through increased skilling of public servants as well as strengthening the quality of PNG tertiary institutions. The intent is to improve the stock of graduates entering the public service and PNG’s capacity to deliver training;

- Strongim Pipol Strongim Nesen (PNG Democratic Governance Program) promotes partnerships between the state and civil society at central and local levels and includes a strong focus on developing the knowledge and skills of participants and beneficiaries;

- Sub-National Strategy (SNS) support service delivery under PNG’s decentralised system of Government. Human resource management is a major focus of the Provincial Performance Improvement Initiative (PPII) and became a strong priority in 2008 as a result of the Department of Personnel Management’s (DPM) devolution of HR functions to provinces;

- PNG-Australia HIV and AIDS Program (Sanap Wantaim) works to reduce the spread of HIV and AIDS and to mitigate the effects of the disease on those living with HIV, their families and PNG society.

NZAID Funded Program and Related Activities in PNG

- In Country Training involves expenditure of PGK 2.0 million for training delivered at (mostly tertiary) PNG institutions. The “Women in Agriculture” is the main scholarship program: for certificate/diploma study in agriculture and forestry (230 scholarships pa). Other ICT is considered on a case by case basis.

- School Journals Project involves the production and distribution of school journals for primary school children. NZAID has also provided funding support for ‘teacher trainer workshops’ on the use of the journals in classrooms.

- Agricultural Institutional Strengthening Program was established to assist the training of trainee lecturers and improve the administration at the University of Vudal, which is now known as the Papua New Guinea University of Natural Resources and Environment.

- NZAID is currently involved in discussions to develop an Education Sector Wide Approach (SWAP). This also involves a major expansion to NZ’s existing in-country training support is being considered as Papua New Guinea’s capacity to provide tertiary and technical training increases.

- Annex 8	Detailed Description of ADS, ALA, NZAID and RDS Scholarship Management Processes including the Facility Responsibilities

| Summary of Scholarship Tasks and Responsibilities.; Shading indicates where the Scholarships PNG Contractor has primary responsibility for a scholarship management task or specific action. A; Partner Government (PG) Involvement; ADS Responsibilities; ALAS Responsibilities; NZDS Scholarships; Key Target Dates; Comments / Notes. A.1; Discussion with GoPNG on policy, priority sectors and lessons learned. Review Scholarship profiles / selection criteria / eligibility requirements for Public Servants category applicants; AusAID Post; N/A; NZ AID Post; October; With the counterpart agencies including DPM and DPLLGA. Logistics to be organised by Contractor.. A.2; Discussion with PNG private sector and GoPNG NTC on priority sectors and profiles for ADS Open / NZDS (Public) category; AusAID Post; N/A; NZ AID Post; October; With the counterpart agencies including NTC. Logistics to be organised by Contractor.. A.3; Discussions to confirm Scholarship priorities and agree on specific targets and details for the following year; AusAID Post; AusAID Canberra; NZ AID Post; October; Important promotional materials are clear enough to act as a guide to applicants on selection criteria. A.4; Advise GoPNG Partners and PNG private sector (including CSOs, NGOs and faith-based) in writing of the upcoming commencement of the Scholarship round; AusAID Post; Canberra advises Post and the Institutions; NZ AID Post; December; Involves AusAID and NZAID working with DPM and NTC. Logistics to be organised by Contractor.. A.5; Draft promotional materials and selection criteria provided to Partners for comment; Canberra prepares all material. Post/Facility to advertise and distribute; Jan; Draft promotional materials developed under instructions from AusAID and NZAID and endorsed by the Joint Steering Committee before circulation. The use of logos will be restricted to the 3 partners and conform to AusAID and NZAID guidelines.. A.6; By mid-December, provide AusAID, NZAID and the PNG Partners with the Scholarship schedule for the following year; N/A; December; Scholarship schedule will be endorsed by all Partners well in advance of the distribution. Scholarship schedule to be distributed to the relevant agencies, institutions, organisations in early December.. B; Advertisement and Promotion; ADS Responsibilities; ALAS Responsibilities; NZDS Scholarships; Key Target Dates; Comments / Notes. B.1; Develop the PNG agency / organisational promotional activities and methods for Partner endorsement; September; Includes consideration of type of media, scope of promotional campaign and lesson learned. B.2; Update the PNG Scholarship Promotion and Communications Plan for endorsement by the 3 Partners; October; Plan to reflect any lessons learned from the previous scholarship cycle, including issues of equity and access and details of the distribution methods to be used. B.3; Approve approach, content and methods to increase the cohort by attracting quality PNG candidates.; Partners; Canberra produces generic content, Post develops approach; Partners; November; Advise Provincial agencies, institutions and NGOs of the scholarship opportunities, especially for women and from Provinces. Includes Contractor staff visits to GoPNG agencies, NGOs and associations in major Provinces. B.4; Targeted advertisement and promotional activities (including information sessions) with emphasis as per agreed selection criteria and eligibility requirements.; November; As per approved Communication Plan. Make clear that Scholarship forms are available from the Partner agencies in the Provinces as well as all PNG Universities. Ensure forms are easily downloadable from the Facility website.. B.5; Arrange for GoPNG agency major Provincial centres to be available for Scholarship applications to be couriered to the Facility by end March.; N/A; March 31; PNG mail system is unreliable: Contractor will arrange the option for applicants to use a courier from the major Provincial centres. Applications close 31 March.. B.6; Develop and continually update / maintain information for the PNG Scholarship Website; Canberra; Ongoing; Website format and proposed content to be approved by the Partners. Update and maintain news, schedules and material in a timely manner. As instructed, link this to the AusAID, NZAID, the OHE and PNG Universities websites.. C; Scholarship Applications; ADS Responsibilities; ALAS Responsibilities; NZDS Scholarships; Key Target Dates; Comments / Notes. C.1; Open and process all of the Scholarship Applications for recording and eligibility checking; April; Around 1200 applications can be expected. Applications can be received at the Facility office from agencies (i.e. in bulk) or direct from individuals. Ensure that all applications received are duly recorded and securely stored. For the ALAS, receive the hard-copy applications and documentation and then provide to AusAID Post.. C.2; Record details in secure MS data base for all applications received; N/A - see C.8; April; Every application will be stamped on date of receipt, name, serial number assigned, recorded on secure data-base. Immediate acknowledgement in writing the receipt of all applications using the self-addressed and stamped envelope that is provided with the application form.. C.3; Store / maintain the hardcopy of all Scholarship applications in secure location, using systems and methods that meet the requirements of all Partners.; April; The Contractor must ensure security and make sure their staff are fully aware of confidentiality requirements and the need for transparency. Provide partners with summary statistics for all applications received within a week of closing date. C.4; Undertake quality spot-check of applications to ensure that all eligible applicants have been identified and that all those identified as eligible to comply.; Partners; AusAID Post; Partners; April; Any Partner will be able to carry out a quality review of application processes and systems on all / any applications received and the records maintained.. C.5; Respond to any queries relating to the receipt or management of the Scholarship applications; April; Maintain a log of the queries and responses as part of the Scholarship database. Respond to any queries that are caused by Scholarships PNG processes. The Contractor will have already posted the self-addressed confirmation of application.. C.6; Check all applications for completeness and compliance with the Scholarship requirements; April; Where appropriate, follow up applicants if there is a clear omission that excludes an otherwise quality candidate. Within 1 week advise all non eligible applicants that they are no longer being considered and the reasons why.. C.7; Develop list of eligible applications for consideration and provide the Public sector application to the relevant GoPNG agencies; April; Develop the list and provide summary to Partners as soon as available. On a random basis, any of the Partners can review sample of applications to test Scholarships PNG eligibility decisions.. C.8; Verify eligible Public sector applicant's statements and reintegration statement by the relevant GoPNG authorities; GoPNG; N/A; GoPNG; May; Contractor to deliver the securely packaged application to the key agencies. Within 3 weeks, GoPNG agencies confirm that each of the application details are correct and (where appropriate) DPM has the relevant staff information.. C.9; Upload hard copy applications into OASIS database (from 2011 for Jan 2012 intake); Ongoing; Only required for the ALA applications. Maintain the Facility IT systems and capacity to increasingly manage scholarship data via the internet.. C.10; Update hard copy applications into a database (from 2011 for Jan 2012 intake) for the ADS/NZDS-Public/NZDS-Open scheme.; Ongoing; The database must be in a format that is readable by the all partners.. C.11; Produce a one page summary sheet for each application containing all relevant details. Provide to each partner containing all relevant information as per the application.; May – June 1st; On May 1st eligible Public scholarship applications sent to agencies and DPM concurrently. The 1st June is the deadline for returning all applications and endorsements.. C.12; Analyse data relating to gender, location, and other identified priority areas. Supply each partner with this information.; June; Present a hard copy of the summary data and support information to each Partner. To include details of agency endorsement.. D; Scholarship Shortlisting and Selection; ADS Responsibilities; ALAS Responsibilities; NZDS Scholarships; Key Target Dates; Comments / Notes. D.1; Identify / recommend independent persons/panel for Scholarship short-listing; Post - may seek assistance from Canberra; April; Provide 2-3 panel candidates. Fully independent and have experience in educational institutions and the Scholarship context. At all times observe principles of privacy and confidentiality.. D.2; Approve independent consultant(s) for short-listing; Partners; AusAID Post; Partners; May; Requires an experience academic that can provide independent advice on courses across Australia and New Zealand. AusAID and NZAID to endorse.. D.3; Contract independent shortlisting panel members; N/A – The panel in Canberra is independent; May; Members to be familiar with the HE structure and options of PNG, Australian and NZ university systems.. D.4; Provide panel members with all required ADS and NZDS profiles and applicant data in hard copy well in advance of short-listing date. Provide clear TOR and the short-listing schedule information as well as provide the logistical support.; June; Profiles to be annually developed between AusAID, NZAID and the PNG stakeholders and provided to the Contractor before the promotional cycle commences. D.5; Brief the short-listing consultants on Partner requirements and procedures; Partners; N/A; Partners; June; Provide panel members all relevant information and data for the selection phase to produce shortlist for ADS/NZDS-Public/NZDS-Open Scholarship. D.6; Provide resources / secure office space for the shortlisting process; June; Ongoing; All Hard Copies of applications to be immediately available upon request for closer review. Arrange the short-listing meeting / discussion rooms. Must be secure and also be available for Committee members after hours so that they provide a place for SL panel members to work before attending the actual meetings.. D.7; Introductory Meeting – Joint Selection Committee; Partners; N/A; partners; Early June; Brief all panel members on all relevant information relating to all the requirements and procedures involved during the selection phase of the shortlists. D.8; Provide policy considerations, develop / discuss selection criteria & weightings; Partners; Criteria and weighting is set by Canberra; Partners; Early June; AusAID and NZAID confirm processes and priorities and that there have been no attempts to interfere with the selection processes. D.9; Provide all Personal Summary Sheets for each ADS / NZAID application for review by the Panel Members.; Partners; N/A; Partners; Early June; All hard copy scholarship applications to be made available upon request at any time to any panel member for further review.. D.10; Provide selection criteria template / marking sheets that align with the profiles; Partners; N/A; Partners; Early June; Part of the Selection Panel briefing process and confirmation of the key selection criteria. D.11; Enter data from template into OASIS (from 2011); Ongoing; Likely that around 220 Scholarship applicants will be shortlisted and entered on OASIS (from 2011). D.12; Arrange short-listing meetings and venue; June; Liaise with the Partners for the final security, access and any required support arrangements. Advise the time, date and location of the SL meeting well in advance.. D.13; Secretariat services and all venue and logistics for the short-listing meeting; Ongoing; Take minutes and records of the SL activity. Confidentiality and the security of information are essential for all Contractor staff to observe.. D.14; Chair and oversee the short-listing process; Partners; AusAID Post; Partners; Completed by 30th June; Around 180 applicants will be shortlisted for Australia and 40 NZDS Public / Open applicants shortlisted. For the ALAS, AusAID Post will determine selection panel membership and chair the Panel. The Contractor will provide the ALAS secretariat.. D.15; Update candidates details onto the data base to reflect short-listing; Ongoing; A total of 220 for interview leading to the 180 Scholarships PNG awards + an additional 25 reserves will also be short listed for potential consideration (ADS, ALAS and NZ). These will match the Scholar profiles and breakdown of sectors as outlined by the JSC, AusAID and NZAID.. D.16; Include another 30 Provincial applicants (25 + 5 reserve) after the Scholarship shortlisting plus reserve, as potential candidates for the Foundation course; N/A; Early July; The short-listing panel agree on potential provincial candidates for consideration. These potential candidates for the Foundation course to be contacted and the options explained.. D.17; Advise successful short-listed ADS/NZDS-Public/NZDS-Open and the ALAS short-listed applicants by courier; Early July; The PNG Mail system can be unreliable so take into account when sending the advice re shortlisting.. D.18; Advise unsuccessful short-listed ADS/NZDS-Public/NZDS-Open and the ALAS unsuccessful applicants by courier; Early July; Advise candidates within one week of the SL process. The PNG Mail system can be unreliable so take into account when sending the advice.. D.19; Produce short-listing summary / report for Partners; July; Contractor to provide the short list data disaggregate by gender, province, priority area, age, agency and proposed study area. Provide report for consideration and endorsement by the Partners.. D.20; Arrange for the ADS/NZDS Public/NZDS Open interviews and organise the logistics. Arrange for the ALAS interviews to be conducted; August; Candidates to be advised at least 2 weeks prior to the interviews. Some interviews will be conducted in the major Provincial centres. Arrange for the interview and other related rooms, the accommodation and logistics, confirm all procedures: confirm arrangements with stakeholders.. D.21; Provide approved templates and scoring sheets; Partners; Post/Contractor; Partners; July. D.22; Sight original copies of qualifications during interview process; July; Confirm validity of documents as required. Where necessary follow up to confirm authenticity before the interviews.. D.23; Develop / review interview questions and approach including the Reintegration Plan selection criteria; AusAID Post; Post; NZ AID; June; Contractor to make it clear to all shortlisted applicants that the Reintegration Plan is an important selection factor. All requirements for the interview (including logistics and venues) to be completed well in advance.. D.24; Develop a range of topics for the ADS and NZDS candidates to write about in English following the interview.; Short listing panel; N/A; NZ AID; June; Test to be written by the candidates under supervision of the Contractor immediately after the interviews. Supervisory staff and an adjacent room will be required so that the EL tests can be run immediately following the interviews.. D.25; Arrange for the IELTS testing for all short-listed Scholarship applicants, to be conducted during the time that the applicant s are attending the Scholarships PNG interviews; Late July; The IELTS testing is for the purposes of providing information to the Australian and NZ institutions so the scholar’s program can be developed. The results of IELTS testing for ALAS and also the NZDS applicants to be available within 2 weeks and form part of the eligibility criteria and be provided to the applicant and the host institution in Australia or NZ. Use an accredited language testing facility in PNG.. D.26; Chair and conduct ADS NZDS Public/NZDS-Open interviews (they can be run in parallel with 2 interviews conducted simultaneously i.e. in NCD and provinces); AusAID Post; Post; NZ AID; June; Interviews will involve 2-3 members of selection panel who will interview up to 6 ADS NZDS Public/NZDS-Open applicants at a time. The interviews will be conducted in secure locations with facilities that are family friendly and also cater for those people that have a disability.. D.27; Provide secretariat service for interview process; June; Requires suitable venues and facilities when interviews conducted in Provinces. Record all information and decisions / reasons on a secure spreadsheet for reporting. Provide statistical data that identifies the spread and data for the shortlisted applicants.. D.28; Determine the Scholarship ranking system and obtain scores and comments from panel outcomes; AusAID Post-Interview panel; Post; NZ AID; June; Prepare excel sheet showing scores and rankings. Finalize applicant’s rankings after the applicants written EL work is reviewed by the selection panel.. D.29; Provide all interviewed candidates with specialist advice on courses / institutions in Australia and New Zealand as part of their selection of an institution; N/A; Late July; At time of interview, specialist staff and internet to be available to discuss Australian and New Zealand institutions / courses. D.30; Endorse ADS NZDS Public/NZDS-Open selection outcomes; AusAID Post; N/A; NZ AID; Late July; Confirm candidates and balance between males / females; Priority Sectors: and numbers from the NCD / Provinces.. D.31; Advise successful ADS NZDS Public/NZDS-Open candidates by courier. Advise successful ALAS candidates on advice from AusAID Canberra.; July; Around 150 ADS short listed selected, comprising 130 scholars and 20 in reserve. 30 NZDS-Public short listed applicants will be selected - 20 scholars and 10 in reserve. NZDS-Open listed 13 applicants selected - 8 scholars and 5 in reserve. The Scholarship Form included in package.. D.32; Advise unsuccessful ADS NZDS Public/NZDS-Open candidates by secure mail. Advise unsuccessful ALAS candidates on advice from AusAID Canberra.; August; Advice sent to the unsuccessful candidates within a week of the final interviews.. D.33; Reimbursement of travel and accommodation and meal allowance for the interviews; August; The amount of stipends and any other allowances to be clearly stated and provided in writing to all Selection Panel members.. D.34; Provide feedback to candidate if required; August; Includes information on interview and IELTS testing results.. D.35; Advise GoPNG of the outcomes and candidates; AusAID Post; N/A; NZ AID; August; Summary report and information to be provided to AusAID / NZAID by the Contractor. D.36; Update successful PNG candidate information on the Scholarships PNG data-base; N/A; Ongoing; Provide the summary data to the Partners. D.37; NZDS Public/NZDS-Open candidates’ data upload into SIMS database.; Ongoing; MC to be trained in the use of SIMS (NZAID Scholarships Information Management System). D.38; Provide AusAID / NZAID with a detailed report on the selection process, outcomes and lessons learnt; September; These are confidential documents and will be handled to reflect that.. E; Foundation Course; ADS Responsibilities; N/A to ALA Scholarships; NZDS Scholarships; Key Target Dates. E.1; Identify and nominate candidates from the short-listing and the interviews that fit agreed profile and provide to Partners; AusAID Post-Interview panel; N/A; July; This cohort will be 20-25. All candidates provided with information on the course and selection parameters. E.2; Consider each of the candidates against priority profiles and recommend acceptance or exclusion for the course; AusAID Post-Interview panel; N/A; July; This implies candidate met all profiled criteria for ADS except those skills or knowledge that requires support. E.3; From those who were short listed and held in reserve but did not get scholarship, identify any that are eligible and would benefit from Foundation course; N/A; August; Criteria for inclusion remain as for the other cohort from the short listing process.. E.4; Using Selection Panel, identify suitable candidates for the Foundation Course; N/A; September; Selection Panel to be fully briefed then given the mandate to identify the suitable candidates from the applications received.. E.5; Identify a suitable PNG tertiary provider that meets the agreed skills and knowledge for the cohort and contract the program; N/A; Oct-- Nov; The Contractor will require the in-house expertise that is required to specify and tender this course. E.6; Provide agreed support / stipend to the cohort while they are undertaking their course.; N/A; Ongoing; Ensure that all agreed allowances and stipends are well understood and paid in a timely manner.. E.7; Maintain contact with the institution and the cohort to monitor progress and any problems; N/A; Ongoing; Important to monitor progress and to maintain contact in relation to support being provided. E.8; Advise the Partners of the completion and outcomes of the Foundation course; N/A; December; Includes success rates in finishing the course and details, by Province, of the participants and their results.. E.9; Provide the cohort with information on future Australia, NZ or other scholarships where they may choose to apply in the future; N/A; Following February; This information provided in a timely manner and structured to enable the Foundation course graduates to re-apply for the Scholarships PNG awards.. F; Scholarship Placement; ADS Responsibilities; N/A; NZDS Scholarships; Key Target Dates; Comments / Notes. F.1; Facilitate the information session on university application forms and placement considerations; N/A; July; Requires comprehensive printed and soft-copy information from quality Australian and New Zealand where the courses and institutions can be clearly matched against the PNG Scholarship priorities.. F.2; At time of interviews, provide information to assist each candidate in making an informed choice of university / course; N/A; July; Requires the Scholarships PNG Contractor to have staff available with the expertise and understanding of Australia's and New Zealand’s university sector and the available programs. F.3; Receive University application forms for Scholarships PNG candidates; N/A; August; Support the scholars to complete application forms and record the relevant information. For the equivalent NZAID Activity - Application forms to be sent to SU for sourcing study program with NZ participating institutions.. F.4; Input ADS data into SIMON (or OASIS); SIMON management is undertaken in Canberra; Ongoing; Contractor to also undertake the equivalent NZAID activity. F.5; Request the University Placements though SIMON (or OASIS); N/A; August; Contractor to also undertake the equivalent NZAID activity. F.6; Input NZDS- Public and NZDS-Open Candidates into SIMS Database; N/A; Ongoing; To be completed in a timely manner so that there is time for all parties to complete the arrangements and (if necessary) make any required alternative arrangements.. F.7; Send the completed ADS/ NZDS- Public/NZDS-Open applications to the agreed university in Australia / New Zealand.; N/A; August; To be completed in a timely manner so that there is time for all parties to complete the arrangements and (if necessary) make any required alternative arrangements.. F.8; Upgrade a reserve PNG scholar if a university placement fails; N/A; Ongoing; Contractor to also undertake the equivalent NZAID activity. F.9; Download offer / student contract from SIMON (or OASIS) for ADS and ALAS. For NZDS Public/NZDS-Open download offer from SIMS database; NZ AID; Sept. F10; Section 44 AusAID approval and NZAID Letter of Offers after student course confirmation is confirmed; AusAID Post; N/A; NZ AID; Sept; Contractor to undertake documentation that enables each scholar to start preparations for the scholarship. F.11; Send out Scholarship offer/student contract to the successful awardees; Sept; To be completed as soon as practicable to enable the student to respond quickly and confirm their final decision. F.12; Receive signed acceptances back from the awardees and make sure all information has been included; Sept; Contractor to also undertake the equivalent NZAID activity. F.13; Enter student acceptance on the relevant database; Sept; Contractor to also undertake the equivalent NZAID activity. F.14; Facilitate contact between scholars and the confirmed universities in Australia or New Zealand; Oct; Contractor to also undertake the equivalent NZAID activity. F.15; Liaise with GoPNG / Agencies to highlight ADS scholar plans as part of HRD program within Partner agency; AusAID Post; N/A; NZ AID; Ongoing; Contractor to also undertake the equivalent NZAID activity. G; Arrange Immigration Visas; ADS Responsibilities; ALAS Responsibilities; NZDS Scholarships; Key Target Date; Comments / Notes. G.1; Provide confirmation of central coordination point for the Scholarships PNG with DIAC and NZ agencies; AusAID Post; AusAID Post; NZAID; Oct; Contractor to also undertake the equivalent NZAID activity. G.2; Provide Visa forms and the checklist to successful candidates; Oct; Provide support to the candidate and advise of all Visa and medical examination / test requirements for Australia / New Zealand, including and available services.. G.3; Support applicant to complete the Visa application; Oct; Confirm with DIAC and NZ Visa agency key requirements and constraints, so applicants are fully aware. If required provide information on how to secure a PNG passport.. G.4; Check all information aligns with the required Visa documents; Oct; Must correspond to both Australian and NZ requirements. G.5; Facilitate medical checks for scholars and (if accompanied) for their families; Oct; Provide information and options for medical tests as required for each scholar. To accommodate Australian and NZ requirements and differences in allowances etc.. G.6; Provide completed forms and application to DIAC and NZ equivalent agencies; Nov; It is important that all requirements of DIAC are met, to avoid delays or any duplication of effort. G.7; Arrange family Visas for those accompanied scholars; Nov; Inform students of the procedure + University family arrival date. Contractor to also undertake the equivalent NZAID activity. G.8; Liaise with DIAC and NZ agency on Visa applications; Ongoing; If scholar accompanied, ensure family Visa applications are submitted with scholar's application. Contractor to also undertake the equivalent NZAID activity. G.9; Liaise with University Student Contact Officer (SCO) regarding student arrival; Ongoing; Where possible, arrange for arrival of scholar to be advised to other PNG ADS scholars at that university. Contractor to also undertake the equivalent NZAID activity. G.10; Advise scholar and AusAID / NZAID if Visa applications rejected; Ongoing; When Visa granted, courier passport, original docs, and departure letter to applicants. H; Pre-Departure to Australia and New Zealand; ADS Responsibilities; ALAS Responsibilities; NZDS Scholarships; Key Target Dates; Comments / Notes. H.1; Identify best price travel for scholars to Australia or New Zealand; Ongoing; Use only recognised travel agents and reliable methods of ticketing. H.2; Advise scholar of preferred route and flight dates; Maintain principles of Value for Money for all flights. H.3; Adapt and refine the Pre Departure Briefing materials for Partner endorsement; Ongoing; All materials will be up to date and reflect contemporary issues and information. H.4; Inform candidates about PDB details and obligations; October; PDB will improve the information scholars have, as well as their basic IT skills and awareness of Australian and NZ academic requirements and expectations.. H.5; Create handouts for the PDB in relation to the PNG context and gain AusAID / NZAID endorsement; October; Any PNG specific materials developed must clearly indicate the Australian Government (through AusAID) and the NZ Government (through NZAID) are the funding agencies. The generic PDB materials on scholarships and the requirements are provided by AusAID, NZAID and the institutions.. H.6; Arrange 2-week PDB program, including scholar travel/ logistics and venue; October; The PDB will be of longer duration and run in a residential format. The program content will be drafted by the Contractor for Partner endorsement.. H.7; Facilitate participation at PDB for awardees from outside capital cities and facilitate participation of ADS and ALAS returned students to act as facilitators during the PDB; November; The 178 Scholarships PNG scholars will attend the 12-day PDP, together with their spouses (as appropriate) for the final 3 days.. H.8; Arrange for scholar's dependent spouse to attend PDB if requested; November; The NZAID scholarships include a dependants allowance so not required for the 20 NZAID participants.. H.9; Provide PDB presentation session and Q & A; AusAID Post; AusAID Post; NZ AID; November; A shorter, separate PDB will be required for the ALA Scholars. H.10; Distribute the specific Pre-Departure kits from Australian and NZ Universities to those scholars that will attend them; November; Contractor to make every effort to provide information on living, transport and context at the institution. For ALA Scholarships, these are sent directly to scholar. H.11; Prepare PNG media release and organise the means of release for AusAID / NZAID approval; January; A media release for the ALA Scholarships will need to be approved by AusAID’s Scholarship Section in Canberra. H.12; Arrange for press-release / publicity for the cohort travelling to Australia and New Zealand; January; Provided to the Partners and clearly identify the donors, the programs, the PNG contributions and the impact. H.13; Reimbursement of travel, accommodation and provision of meal allowance-PDB; January. H.14; Finalise all departure / logistics arrangements (including, facilitating visas and medical checks); Dec - January; Requires liaison and scheduling with agencies and service providers to have this completed in advance of departure.. H.15; Inform each university of the scholar's arrival details; January; For ALAS, send all travel details to AusAID Canberra to pass on to universities.. H.16; Confirm to AusAID / NZAID when scholars arrived in Australia or New Zealand and commenced the course; ASAP; Summary information, together with exception report on individual cases where there is a problem. I; Scholarship Management; ADS Responsibilities; ALAS Responsibilities; NZDS Scholarships; Key Target Dates; Comments / Notes. Australian and New Zealand Scholarships. I.1; Maintain quarterly contact and respond to ad hoc queries from scholars while they are in Australia or New Zealand; Ongoing; By maintaining contact, an opportunity to quickly respond to problems or serious issues. This involves enquiring about welfare and academic arrangements and progress.. I.2; Provide details of any specific issues or problems in relation to individual scholarship-holder’s progress to AusAID or NZAID as appropriate; Ongoing; The reporting on individual students is in the context of providing early warning to Partners and (in some cases) the institutions, with a view to a remedy being provided.. I.3; Provide summary of 6-monthly contact and any issues to the Partners; N/A; Summary information that does not replace university reporting. The focus is on any constraints to progress.. I.4; Deal with requests for extensions or variations in consultation with AusAID; N/A; Ongoing; AusAID Canberra for ALAS. I.5; Identify potential for any scholarship extensions or variations and advise AusAID / NZAID; AusAID Post / AusAID Canberra; N/A; NZ AID; Ongoing; If required, Post will seek advice from Canberra or Wellington for any complex or difficult cases. I.6; Advise the Australian or NZ university of any Scholarship variation decisions; N/A; Ongoing; On advice from AusAID, provide the information and details to the institution. I.7; Provide a summary of the scholar return dates to Partners and relevant agencies; N/A; Ongoing; This will be discussed with Partners in relation to the re-entry focus and also to maximise potential involvement of the Alumni. I.8; In the last semester of the course, provide advance warning to the relevant GoPNG agencies and the PNGAAA / PNGNZA that the scholar will be returning; Ongoing; Includes a summary list for the Partners and individual advice to the various GoPNG agencies.. I.9; Provide scholars with Alumni information while they're in Australia or New Zealand; Ongoing; Contractor to promote ongoing communication between the scholar and their employer or Alumni. I.10; Encourage PNG scholars to maintain contact with their families and (where relevant) employers; Ongoing; This may include encouraging the use of internet and also accessing PNGAAA / PNG NZ Alumni to support the communication.. Regional Development Scholarships. I.11; Provide information and advice to the RDS management in Suva as required.; N/A; Ongoing; Up to a total of 60 AusAID and NZAID funded RDS students can be expected to be studying in PNG. I.12; Facilitate the Visa documentation and other required support for the in-bound student.; N/A; Ongoing; Requires advance notice and adequate timing to finalise the required GoPNG documentation. I.13; Prepare annual budget and cash flow in anticipation of the RDS program; N/A; Will be based on the projected number of students and their home institutions in PNG. I.14; Prepare forward plan for RDS scholars arriving and leaving PNG. Provide 6-monthly summary report; N/A; Continue to keep AusAID and NZAID up to date with any unexpected RDS arrivals, departures or issues.. I.15; Liaise with the PNG institution on required education / course / pastoral services.; N/A; Ongoing; Important to maintain contact re any academic and / or pastoral concerns of the student. I.16; Facilitate the enrolment and payment schedules for each institution, including the required local support / logistical arrangements; N/A; Ongoing. I.17; Meet RDS student on arrival and provide initial accommodation in POM as part of orientation; N/A; Ongoing; Each student group must be met and provided with a briefing on all academic and logistical issues, with special emphasis on security, health and emergency procedures. I.18; Follow-up that the RDS student arrives at their host institution and is met and settled in by their staff.; N/A; Ongoing; Initiate a process where the PNG institution is required to regularly contact the Contractor with updates / any issues. I.19; Make payments to the relevant academic institution where the RDS scholar is enrolled; N/A; Ongoing; Summary reports provided to the Partners. I.20; Make payment to the RDS scholar for their allowances, stipends and other agreed costs.; N/A; Ongoing; Summary reports provided to the Partners. I.21; Visit each RDS student at least twice per year to monitor academic progress and pastoral care provided.; N/A; Ongoing; This visit provides an opportunity to revise and refine the reporting / support systems as well as to make whatever changes are required to ensure success.. J; Scholars Return to PNG / Alumni; ADS Responsibilities; ALAS Responsibilities; NZDS Scholarships; Key Target Dates; Comments / Notes. J.1; Inform / meet PG institutions and AusAID in relation to ADS scholar planned return; N/A; Ongoing; Return details are entered by the University and AusAID Post is informed through an email from SIMON. J.2; Confirm scholar's return dates to PNG; N/A; Ongoing; Provide advance notice to AusAID and / or NZAID. J.3; Discuss HRD and Reintegration Plan with GoPNG / institutions prior to scholar's return (if applicable); Ongoing; To be conducted in liaison with AusAID and NZAID as part of strengthening potential impact. J.4; Enter scholar contact details on data base/OASIS/SIMS; Ongoing; AusAID and NZAID will require the databases to be up to date and accurate. J.5; Support the operation of the Alumni data base and provide summary information to AusAID / NZAID; Ongoing; Work with the PNGAAA and NG NZ Alumni to maintain and enhance the data base and the Alumni membership. J.6; Host / facilitate Alumni events (social and professional); AusAID Post; AusAID Post; NZ AID; Discuss with AusAID potential events of activities that can support and advocate the Alumni. J.7; Support the development and distribution of the Alumni newsletter (six-monthly); Ongoing; Send by email to all Alumni, all PNG scholars studying in Australia and NZ and to agreed GoPNG / NGO agencies. J.8; Establish and maintain an M&E system for scholarship management; Ongoing; Able to provide information about Scholarships PNG scholarships including at the operational and impact levels. J.9; As requested by AusAID, develop/conduct tracer studies of sample scholars who have returned to PNG; Ongoing; Includes follow up on Reintegration Plans - conducted on reimbursable basis as instructed by the Partners. J.10; As requested by Partners, develop and conduct case studies to highlight impact and contribution of the ADS, the ALAS and the NZDS; Ongoing; Use relevant methods and approaches to identify where Scholarships PNG has made an impact on agencies or systems.. K; Other Scholarship Management Tasks; ADS Responsibilities; ALAS Responsibilities; NZDS Scholarships; Key Target Dates; Comments / Notes. K.1; Provide reports and M&E data as required under the SoS and / or as requested by the Partners; Ongoing; Contractor to ensure information and data is timely, accurate and meets AusAID and NZAID reporting requirements. K.2; Conduct Annual Contractor performance review in relation to ADS NZDS-Public/NZDS-Open; AusAID Post; AusAID Post; NZ AID; Ongoing; On the anniversary of contract commencement. K.3; Provide summary data to AusAID and NZAID for their global scholarship reporting requirements; Ongoing; Required by AusAID and NZAID in Feb / March each year. K.4; Recommend two (2) ALA for Allison Sudradjat Award; AusAID Post; AusAID Post; N/A; August; Confidentiality of information will be required. K.5; Facilitate the Allison Sudradjat Awardees' activities where requested; AusAID Post / Contractor; AusAID Post / Contractor; N/A; Ongoing. |  |
| --- | --- |

- Annex 9		Membership of The Design Team

| Prof Ingrid Moses | Team Leader |
| --- | --- |
| Paul Tippett | Design Specialist |
| Lindy Fisher | First Secretary, Higher Education and Training |
| Alison De Luise | Program Quality and Review Group, PNG Branch |
| Diane Roberts | Program Manager, Australian Scholarship Group |
| Evelyn King | Sector Specialist, Senior Research Advisor |
| Francis Hualupmomi | OHE: accompanied team as an observer to Goroka, Lae, and UPNG. |
| Lonnie Baki | OHE: accompanied team as observer to PAU, Madang and Kokopo, |
| Linda Taman | PNG Department of National Planning and Monitoring: was not available to take her place in the team during the Design Mission. |

- Annex 10		Summary of People and Agencies Consulted

Note: In the early part of the design process, there was limited consultation with scholars or institutions involved with the NZAID scholarship program to PNG. At the time of initial design consultations, no decision had been made relating to the AusAID and NZAID scholarships being jointly managed under Scholarships PNG.

Once this decision had been taken, extensive consultations were held with NZAID in relation to the management of the AusAID and NZAID scholarships in PNG.

| In Australia before the Design Mission to PNG |  |
| --- | --- |
| AusAID Canberra | Margaret Callan, Assistant Director General, PNG Branch |
|  | Michelle Lowe, Director Program Quality & Review, PNG Branch |
|  | Mukii Gashugu, Manager, Program Quality and Review, PNG Branch |
|  | Kirsty Dudgeon, A/G Director, Program Quality and Review, PNG Branch |
|  | Barbara O’Dwyer, Gender Advisor, Gender Group |
|  | Ashween Singh, Manager, Economic and Public Sector Governance, PNG Branch |
|  | Peter Goldsworthy, Economic and Public Sector Governance, PNG Branch |
|  | William Hilton Thorpe, Economic and Public Sector Governance, PNG Branch |
|  | Yvonne Green, Officer, Partnership and Program Coordination, PNG Branch |
|  | Debbie Muirhead, Director Research, Research Group |
|  | David Campbell, Manager, Research Group |
|  | Anna Perkins, Director, Partnership and Program Coordination, PNG Branch |
|  | Tony Liston, Director, Partnerships for Development, Pacific Branch |
|  | Sarah Moriarty, Director, Pacific Public Sector Capacity Building Initiative |
|  | Carrie-Anne Best, Manager, Pacific Public Sector Capacity Building Initiative |
|  | Mary-Ellen Miller, Director, Australian Scholarships Group |
|  | Lisa Spender, Program Manager, Australian Scholarships Group |
|  | Petra Kavunenko, Program Manager, Australian Scholarships Group |
|  | Brad Kajewski, Program Manager, Australian Scholarships Group |
|  | Emily Serong, Officer, Australian Scholarships Group |
|  | Simon Kaldy, Officer, Australian Scholarships Group |
|  | Rachel Rawlings, Officer, Australian Scholarships Group |
|  | Heather Dornoch, Manager, Design and Procurement Advisory Group, Operations Policy |
| In PNG during Design Mission |  |
| AusAID PNG Post | Bill Costello, Minister Counsellor |
|  | Dave Vosen, Counsellor |
|  | Susan Ferguson, Gender Advisor |
|  | Group of AusAID O-Based Staff |
|  | Sarah MacCanna, Second Secretary, Democratic Governance |
|  | Urgei Akon, Officer, Democratic Governance |
|  | Warren Turner, First Secretary, Economic and Public Sector Governance |
|  | Freda Talao, Snr Program Officer, Economic and Public Sector Governance |
|  | Malcolm Kulu, Program Officer, Higher Education & Training |
|  | Gabriel Kubul, Program Officer, Law and Justice Sector Program |
|  | Christine Groeger, Second Secretary, Private Sector Development |
| PNG Treasury | Anne Martin, SGP Advisor |
|  | Ruth Veapi, Assistant Secretary (Social Sector), Budgets Unit, Treasury |
|  | Thea Daniel, SGP Advisor, Budgets Unit, Treasury |
| PATTAF | Phil Robson, Facility Director, PATTAF |
|  | Vivien Carroll, Deputy Team Leader, PATTAF |
|  | Hiris Birney, Scholarships Manager, PATTAF |
| PNG Australia Alumni Association | Avia Koisen, President PNG Australia Alumni Association |
|  | Kelly Cook, Vice-President PNG Australia Alumni Association |
|  | Thomas Willie, A/g Secretary PNG Australia Alumni Association |
|  | Goodwill Amos, PNG Forest Authority, Co-ordinator Forest & Climate Change |
| NZAID | Tessa Te Mata, PNG Country Manager, NZAID |
|  | Heather Wright, First Secretary, NZAID |
| PNG Office of Higher Education | Dr William Tagis, Director General, Officer of Higher Education |
|  | Francis Hualupmoni, Officer |
|  | Lonnie Baki, Officer |
| PNG Department of Labour and Industrial Relations | Mrs Rona Nadile, A/g Executive Manager, Corporate Services |
|  | Roger Cerova, Human Resource Division |
|  | Stan Motolo, Assistant Director, National Training Council |
|  | Mrs Maria Lovaga , Executive Director, Labour Standards |
|  | Lawrence Waimain, Assistant Director, Occupational Standards Development |
|  | Tom Kibau, A/g Manager Human Resource Development |
| PNG National Training Council | George Arua, Director, National Training Council |
|  | Stan Motolo, Assistant Director, National Training Council |
|  | Paul Brady, Workforce Development Adviser |
| Manufacturers Council of PNG | Chey Scovell, Executive Officer |
|  | Aarish Shah, Chairman |
|  | Wayne Golding, NC |
| PNG Chamber of Commerce and Industry Port Moresby | David Conn, GM POM CCI |
|  | Ken Dunn, President POM CCI |
| Business Council of PNG | Stan Joyce, GM SP Breweries |
|  | Paul Barker, Director Institute of National Affairs |
| Women and Higher Education Forum | Dr Orovu Sepoi, Program Coordinator, UNIFEM |
|  | N’Deane Helajzen, Gender Advisor, ECBP |
|  | Dr Jackie Wright, Team Leader, Agriculture Research & Support |
|  | Sally Mokis, Papua Hahine |
|  | Susan Setae, Executive Officer, Papua Hahine |
|  | Theresa Siagura, Social Policy Advisor, Prime Minister’s Department |
|  | Serena Sasingian, Coordinator of The Voice |
| PNG Chamber of Mines and Petroleum | Greg Anderson, Executive Director |
|  | Hellen Purdy, HR Manager, PNG Operations, InterOil |
|  | Ila Temu, Director Corporate Affairs, Australia Pacific, Barrick (PNG) Ltd |
|  | Ephraim Tammy, Washu, Borona, Various Organisations |
| Pacific Adventist University | Dr Braninimir Schubert, Vice Chancellor, PAU |
|  | Dr Fifaia Matainaho, Development Officer, PAU |
|  | Dr Glingalo, Deputy Vice Chancellor, PAU |
|  | Dr Tracy Afilio, Post Graduate Studies Coordinator and Student Support Services, PAU |
|  | Ben Thomas, Dean of School of Business, PAU |
| PNG Department of Personnel Management | Jo Quiocho, Acting Executive Manager APS |
|  | Matilda Kovos, Coordinator Donor Funded Training |
|  | Aida Yuki, Acting Manager Policy, Research Development |
|  | Rhymbi Kokiva, Acting Manager Administrative and Hew Guinea Islands Region |
| Peter Baki | Peter Baki, GM of Diwai Pacific Ltd |
| Leadership Groups | Rhoda Moses, Leadership PNG |
|  | Charlie Gilichibi, Badili Club |
|  | Daniel Waswas, University of PNG |
|  | Kemo Pepena-Palai, Leadership PNG |
| George Bopi | Consultant, OHE, Labour Market Assessment |
| PNG Human Resource Institute | Peter Mel, PNG HRI |
|  | Jerry Wemin, PNG HRI President |
|  | Meckles Poya, UPNG School of Business |
|  | Paul Kil, PNG HRI Council Member |
|  | Divine Word University |
|  | Kunara Kanawi, PNG HRI Member |
|  | Peter Sala, HR Cadet |
|  | Br Andrew Simpson, Vice- President Academic |
|  | Assistant Professor Pam Norman, Dean of Studies |
|  | Dr Romulo Lindio, Dean of Business & Informatics |
|  | Professor Francis Hombhanje, Dean of Health Sciences |
|  | Ass. Professor Mark Solon, Dean of Arts |
|  | Fr Phil Smith, Dean of Flexible Learning |
|  | Monica Rothlisberger, Director DWU Libraries |
|  | Chandana Silva, Director IT Services |
|  | Dr Luis Alamil, Head of Department Business and Management |
|  | John Imbal, Head of Department Tourism and Hospitality |
|  | Dr Lakoa Fitina, Professor Deane Arganbright, Head of Department Mathematics & Computing Science |
|  | Luddy Salonda, Director Quality Assurance |
|  | Benjamin Nainz, Vice President Administration |
|  | Dr Peter Anderson, Head of Department Information Systems |
| Madang Chamber of Commerce and Industry | Stotick Kamya, Community Relations Manager, RD Tuna Canners Ltd, Madang Chamber President |
|  | Richard Coleman, Principal, PNG Maritime College |
|  | Sir Arnold Amet, Governor, Madang Province |
|  | Eunice Messersmith, Secretary/Treasurer,Madang Chamber |
|  | Rosa Reeves, RD Tuna Canners Ltd |
| Madang Alumni Chapter | Aiva Tamate-Ore, Public Relations Office |
|  | Ted Alau, Executive Officer, Academic Division at DWU |
|  | Cecilia N’Drower, Registrar |
|  | Ludmilla Salonda, Director, Academic Quality Assurance |
|  | Alphonse Aime, Lecturer Communication Arts Department |
|  | Anastasia Sai, Snr Lecturer in Art, PNG Studies Department |
|  | Paul Pasingan, Lecturer, Faculty of Education |
|  | Associate Professor Michael Mel, Pro-Vice Chancellor Academic & Development |
|  | Dr Kini James Yoko, Pro-Vice Chancellor Administration |
|  | Dr P. Jeyarathan, Dean, Faculty of Science |
|  | Russell Deka Harada, ICT Manager |
|  | Leah Kalamorah, Librarian |
|  | Dr Sam Najike, A/g Dean of School of Postgraduate Studies |
|  | Eric Kombekali, Director Planning |
|  | Joshua Soso, Bursar |
|  | David Avei Hosea, Dean Humanities Faculty |
|  | Dr Paul Kovo, A/g Dean Education Faculty |
|  | Augustine Dominic, Executive Officer |
|  | Monica Pusal, Director Student Services |
|  | Kate Gunn, Public Relations Officer |
| Goroka Chamber of Commerce and Industry | Herman Spingler, The Melanesia Institute |
|  | Terrence Shelley, President |
|  | George Kuno, George Kuno Accountants |
|  | P McCallum, Melanesian Institute |
|  | Jackson Rodgers, Bursar |
|  | Henry Gioven, Registrar |
|  | Peter Navus, A/g Head, Agriculture Department |
| Rabaul Provincial Government | Akwila Tubal, Provincial Administrator |
|  | Bernard Liucara, DPA PP&T |
|  | Matalau Nakikus, Director C/Affairs |
|  | Clement Irasuia, DPA C&I |
|  | Donald Terarue, Division Commerce & Industry, A/Advisor |
|  | Pius Gawi, Education Division |
|  | Wesley Pago, Human Resource Management |
|  | Dorothy Luana, SNS/PPII |
|  | Carolyn Mom, PPII HRM |
| Rabaul Chamber of Commerce and Industry | Harry Sawicki, ENB Port Services |
|  | Bruce Alexander, ENB CCI |
|  | John Gloyne, CPL |
|  | Ron Rowe, Kokopo Business College |
|  | Ngare Rowe, Kokopo Business College |
|  | Nick Lyons, Rabaul Metal Industries |
|  | Suzi Alexander |
| Rabaul Provincial Government - Women’s Representation | Saireen Enos, Finance ENB Provincial Administration |
|  | Sonyah Gaimas, HRM ENB Provincial Administration |
|  | Allison Tewe, HRM ENB Provincial Administration |
|  | Rosemary Murure, HRM ENB Provincial Administration |
|  | Carolin Nom, HRM Advisor PPII |
|  | Mary Luluai, Division of Education, ENB Provincial Administration |
|  | Christine Masy, Division for Community Development |
|  | Mr W.F.Tovirika, Pro Vice Chancellor (Administration) |
|  | Professor M.A.Satter, Pro Vice Chancellor (Academic Affairs) |
|  | Mr.A.Sako, Registrar |
|  | Mr.B.Bomoteng, Acting Deputy Bursar |
|  | Professor R.Milani, Head of Department Architecture & Building |
|  | Professor J.Pumwa, Head of Department, Mechanical Engineering |
|  | Dr.S.Akoitai, A/Head of Department, Applied Sciences |
|  | Mr.J.Juju, Executive Manager, Unitech Development & Consultancy Ltd |
|  | Mr.D.Ermot, Business Manager, Unitech Development Consultancy |
|  | Mr.A.Yadi, Director, Public Relations Unit |
|  | Mr.M.Kuusa, A/Head of Department, Business Studies |
| Lae Provincial Government | Miring Singolinh, Madang HRM |
|  | Kusak Mervk, Training Officer |
|  | Mirika Sbihoro, Advisor Education |
| Lae Chamber of Commerce and Industry | Evan Gillespie, NCI Packaging PNG |
|  | Dennis Brewster, ANZ Bank |
|  | Kaity Bluett, Attic Holdings |
|  | Lyn Dunn, LCCI |
|  | Anton Ponnampalam, CEO Shorncliffe PNG Ltd |
|  | Harry Heni, SP Breweries |
|  | Geoff Whitehouse, Group Human Resource Manager, Mainland Holdings |
|  | John Pittar, Colgate Parmolive |
|  | Alexander Bernardino, Frabelle PNG Ltd |
| In Australia after PNG Design Mission |  |
| Australian Development Scholarship Students | Alfred Mokae – ANU |
|  | Wilson Jonathan – ANU |
|  | Barbara Age – ANU |
|  | Belinda Bayak – ANU |
|  | Helen Molean – ANU |
|  | Fidelis Golu – ANU |
|  | Jacob Gop – ANU |
|  | Samueal Yuguru – ANU |
|  | Keron Kilip – ANU |
|  | Kelly Yosi – Swinburne |
|  | Sarea Leo – Swinburne |
|  | Lancely Christine Dimokari – Swinburne |
|  | Mau Kali – Swinburne |
|  | Philemon Yalamu – Swinburne |
|  | Henrietta Simon – Swinburne |
|  | Elsie Doyore – Swinburne |
|  | Simon Nichodemus – Swinburne |
|  | Vincent Haguluha – University of Sydney |
|  | Emma Wangi – University of Sydney |
|  | Kama Rebecca Ein None – University of Sydney |
|  | Nick Dala – University of Sydney |
| Australia Papua New Guinea Business Council | Frank Yourn, Executive Director, Australia Papua New Guinea Business Council |
|  | Jane Kittel, General Manager Pacific Banking, Westpac |
|  | Gayle Carrick, Business Facilitation Consultant |
|  | Amanda Jenkins, Organisational Development Manager, Oil Search Ltd |
|  | Scott Roberts, Principal, Qld Asia Pacific Region, Cadden Crowe |
|  | Peter Taylor, Rio Tinto |
|  | Associate Professor Robyn McConchie, Director, Research Institute for Asia and the Pacific |
|  | Rebecca Murray, International Development Manager, Research Institute for Asia and the Pacific |
|  | David Boyd, International Development Officer, The International Institute |
|  | Peter Ball, Director, The International Office |
|  | Kirk Doyle, Acting D/Director, Government and Student Relations, International Office |
|  | Katy Cuthbert, Acting AusAID Coordinator |
|  | Dr Dilhani Bandaranayake, Manager, International Relations, Office for Global Health |
|  | Professor David Guest, Faculty of Agriculture, Food and Natural Resources |
|  | Dr Lyndal Trevena, Sub-Dean (International), Faculty of Health |
|  | Dr Steven Cumming, Association Dean, Faculty of Health Sciences |
|  | Professor Lee Burns, Pro Dean, Faculty of Law |
|  | Dr Mu Li, Senior Lecturer, International Public Health |
|  | Steve Leader, School of Medicine |
|  | Phillip Ivanov, Research and Training Development Manager, Research Institute for Asia and the Pacific |
| Macquarie University | Professor Judyth Sachs, Deputy Vice-Chancellor and Provost |
|  | Caroline Trotman, Deputy Vice-Chancellor Development and External Relations Michelle Cheah, AVI, Program Manager, Global Futures |
| University of Queensland | Andrew Everett, Director UQ International |
|  | Fiona Pakoa, Manager, International Relations, UQ International |
| Griffith University | Professor Ian O’Connor, Vice-Chancellor and President |
|  | Professor Cordia Chu, Director, Centre for Environment and Population Health |
|  | Michelle Walker, Acting Director, International Business Development Unit |
|  | Heidi Piper, Manager, Study Abroad and Exchange |
|  | Professor Roger Kitching, Chair of Ecology |
|  | Shelly Maller, International Relations Officer |
|  | Lesley-Ann Mack, AusAID Liaison Officer, Student Advisory Services |
|  | Jack Johnston, Coordinator, International Marketing |
|  | Melea Lewis, Senior Research Assistant, Key Centre for Ethics, Law, Justice and Governance |
| The Australian National University | Darren Brown, Director International Development |
|  | Christine Stewart, Graduate Scholar |
|  | Tim Beckett, Registrar |
|  | Billie Headon, Crawford School |
|  | Carol Laslett, AusAID Liaison Officer |
|  | Tom Kompas, Director, International and Development Economics, Crawford School |
|  | Luca Tacconi, Director Environmental Management and Development Program, Crawford School |
|  | Kerry Thornton, Director, Communications & International, Go8 |
|  | Mike Gallagher, Executive Director, Go8 |
|  | David Hegarty, Convenor and Senior Fellow, State, Society and Governance in Melanesia, RSPAS, ANU |
|  | Dr Mike Cookson, Pacific and Asian History Division, ANU |
| James Cook University | Prof Ian Wronski, Pro Vice-Chancellor, Faculty of Medicine, Health and Molecular Science |
| Swinburne University of Technology | Ben Mackenzie, Director, Swinburne International and National Recruitment |
|  | Dianne Ruddell, Associate Director Business Services, Swinburne International |
|  | Emelia Tabrizi, Coordinator, Sponsored Students, Swinburne International |
|  | Melina Wong, Manager, Sponsored Students, Swinburne International |
| Australian Volunteers International | Dimity Fifer, CEO |
|  | Peter Britton, Senior Manager, International Services |
|  | Russell Hocking, Manager, International Strategy |
| Victoria University | Chris Wooles, Manager, International Projects and Scholarships, Victoria University International |
|  | Samantha Thompson, AusAID liaison officer |
| In PNG for Roundtable Draft Design Briefings / Consultation / Clarification |  |
| NZ AID | Heather Wright, First Secretary, NZ High Commission |
| AusAID PNG Post | Bill Costello, Minister Counsellor |
|  | Dave Vosen, Counsellor |
| GoPNG Roundtable | Moale Daure, Program Officer (Transport), DNPM |
|  | Igo Gari, Assistant Secretary, Social Sector, DNPM |
|  | Jon Ndramei, Foreign Aid Division |
|  | Freda Talsa |
|  | Ruth Veapi, Assistant Secretary (Social), Treasury |
|  | Anne Martin, EGP Adviser, Treasury |
|  | Linda Taman Eko, Assistant Secretary (AusAID), DNPM |
|  | Talale Tun, Assistant Secretary, DNPM |
|  | Heather Wright, First Secretary, NZ High Commission |
|  | Kevin Wak, Senior Program Officer (Youth, Women, Commercial Development), DNPM |
| PNG Private Sector Roundtable | Greg Anderson, PNG Chamber of Mines and Petroleum. |
|  | Thea Brown, NZAID, Development Program Administrator |
|  | Jonny Yep, Institute of National Affairs |
| AusAID PNG Staff in Related Sectors | Jessie Belcher |
|  | Tony Kiessler |
|  | Willie Koi |
|  | Andrea Cole |
|  | Erin Anderson |
|  | John Mooney |
|  | Jo Tough |
|  | Tom Nettleton |
|  | Prof Ross Hynes, VC, UPNG and senior staff |
|  | Fr Jan Czuba, President, Divine Word University |
|  | Dr Gairo Onagi, VC, The University of Goroka and senior staff |
|  | Dr Misty E. Baloiloi, VC, UNITECH and senior staff |
|  | Prof Philip Siaguru, VC, University of Vudal |
|  | Simon Kenehe, Commissioner, CHE |
|  | 3 Staff from OHE |

- Annex 11		References and Readings

PATTAF Quarterly Reports

- 2006, Q1, Q2, Q3, Q4

- 2007, Q1, Q2, Q3

- 2008, Q1

PATTAF Annual Plans

- 2002-03

- 2003-04

- 2005

- 2006

PATTAF Assessment of Trends of PNG ADS

- 2006

- 2008

PATTAF Papua New Guinea: Notes on the Higher Education Sector April 2008

PATTAF Milestone Report on HR Capacity Building Support DPLGA GoPNG April 2005

PATTAF Annual Targeting Strategy 2005

PATTAF Performance Assessment Development Impact – Goal and Purpose January 2007

PATTAF Tracer and Impact Study for Open and Distance Learning

PATTAF Development of a Performance Measurement Framework for ADS PNG Nov 2007

PATTAF Mixed Mode Policy and Implementation Plan

PATTAF Completion Report Organisation Scoping

PATTAF Senior Executive Leadership Program, Department of Personnel Management Activity Completion Report 2005

PATTAF Performance Assessment ADS PNG October 2008

PATTAF Workforce Development Strategy 2008-2010

Australian Scholarships M&E Strategy Sept 2007, AusAID

Discussion Paper Flexible Modes of Delivery March 2007, Australian Scholarships Group, AusAID

Draft SSGM Report – Experiencing the Public Sector: Pacific Women’s Perspectives, Dec 2008, ANU

Draft Indonesia ADS Program Design Document Dec 2007, AusAID

PNG PSWDI Executive Development Scoping Study October 2006

Pacific Public Service Workforce Development Initiative, AusAID

Concept Document: Human Resource Development Assistance to the Philippines, Aug 2008, AusAID

Strategic Review of the Philippines-Australia Human Resource Development Facility (PAHRDF) Final Report, 26 October 2007

Indonesia Australia Development Scholarships Phase II Review, Final Report, March 2006

Philippines-Australia Human Resource Development Facility Document Oct 2008

Pacific Economic Bulletin, People First Network and the Potential of ICT in Rural Development, ANU 2008

ADS & ALA Management and Conditions Review, Final Report, AusAID

Introductory Guidance on Monitoring and Evaluation for AusAID Study & Professional Development Award (SPDA) Programs, ASG, AusAID

Donor Policies and Implementation Modalities with regard to international post graduate programs targeting scholars from developing countries, VLIR Jan 2008

Leadership, Scholarships and Anti-Corruption Sector Performance Report (Abbreviated), 30 April 2008, AusAID

PNG Leadership Facility, Policy Directions Paper, PNG Program, AusAID

Non-AusAID Scholarship programs, ASG, AusAID

AusAID Australian Scholarships Ongoing Surveys Corporate Report, Sept 2008

Philippines-Australia Human Resource Development Facility First Annual Report from the Monitoring and Review Team May 2006

Sub-Review of AusAID Scholarships Selection, Reintegration and Monitoring & Evaluation Processes 2008

Mid Term Review of PATTAF, September 2004

PNG Commitment on Aid Effectiveness

Partnership for Development

Research for Government Policy Priorities, Working with the National Research Institute, 2007

Pacific Public Sector Capacity Building Concept Paper

Donor Policies and Co-operation Modalities – The German Academic Exchange Services (DADD), Helmut Blumbach

AusAID Scholarships Alumni Network Implementation Plan 2009-2011

Proposal for PNG Labour Market Assessment, George Bopi

NACS. Papua New Guinea National Research Agenda for HIV and AIDS 2008 -2013.

NACS. Papua New Guinea National Strategic Plan for HIV/AIDS 2006-2010

NDoH. Papua New Guinea HIV Estimation Report 2007

Braddock R. The Asia-Pacific region. J Higher Edu Pol. 15(3); 291-311

Wight D. Most of our social scientists are not institution based they are there for hire -Research consultancies and social science capacity for health research in East Africa Soc Sci Med 66 (2008) 110-116

UNAIDS. Toolkit for Mainstreaming HIV and AIDS in the Education Sector - Guidelines for Development Cooperation Agencies January 2008

UNESCO. Expanding the field of inquiry. A cross-country study on higher education institutions' responses to HIV and AIDS

GoPNG Ministry of Finance Website

The Design Team members are listed in Annex: The Summary of People and Organisations Consulted is included as Annex 10. The References and Readings are included as Annex 11.

The Medium Term Development Strategy 2005-2010, p.19

- An issue to be addressed is the disparity between the number of men and women who can capitalise on employment and financial advantages through the emerging economy of PNG. There is also concern that LNG will siphon skilled labour from other companies at a time when skilled people remain in short supply.

Where possible, this design uses the systems and processes of PNG Partners to manage activities and collect data for M&E.

The Partnership for Development will supersede the DCS after 2010

These costs and support measures often relate to PNG Partners in the Open category, including the private sector, NGOs or CSOs.

The SPNG program will include an expanded GoPNG membership on the Joint Steering Committee, which will guide the direction of the Scholarship program.

This policy decision was to discourage scholarship holders bringing family members to Australia

Those men and women consulted as part of this design, who had left family in PNG, were extremely anxious about their family members’ welfare and (often) under severe financial stress through supporting their families via the stipend and living allowances.

See AusAID website: http://www.ausaid.gov.au/publications/pdf/child_protection.pdf

2007 Estimation Report on the HIV Epidemic in PNG, PNG National DoH and National AIDS Council Secretariat

National Research Agenda for HIV and AIDS in Papua New Guinea 2008-2013, PNG National AIDS Council Secretariat

It is important to note that, because of NZ Immigration regulations, potential students with HIV and AIDS are prevented from entering New Zealand for study.

NZAID requires all of its scholarship candidates to undertake IELTS testing prior to them being accepted for study in New Zealand universities. This practice has seen a reduction in the number of variations / terminations of the NZAID awards.

The NZAID funded scholarships to PNG will continue to provide a financial allowance for accompanying family members.

This design is recommending current requirement in the Open category to have worked at an employer for 2 years be removed. This is intended to attract younger people with the necessary background to apply. These younger candidates may not have the same family obligations as their older colleagues and in a position to make a longer-term contribution on their return to PNG.

e.g. two award offers were declined due to remotely located candidates receiving offers late and making other commitments

- Additional details of the Facility’s support responsibilities for the RDS are included in Annex 8

Includes those GoPNG already involved in the ADS as well as related agencies that may relate to the HRD priority areas.

A number of current and returned scholars stated they had selected their study based on priority/preference given to an area of study by the selection committee, rather than their interest or aptitude. This may partly account for the variations and failures.

As an example, women who wish to undertake research or academic/skill formation in relation to gender issues and constraints that act to block the development of PNG should be encouraged.

Promotion of Scholarships is largely confined to newspapers and advocacy via ‘roadshows’ that tour PNG. There is little capacity within existing contractual arrangement for a more direct, targeted approach to advocating Scholarship opportunities, including directly with central agencies, sub-national agencies, NGOs, private sector and professional associations

Applicant from the Public category require endorsement from their GoPNG agency, including a draft Re-entry Plan.

To date, slection of ADS scholars is without interview or face-to-face meeting between selection panels and candidates.

With 2 Selection Panel members involved in each interview, it will be possible to run two parallel sets of interviews.

Providing information and advice to women on potential qualifications and experience that enable them to better participate in the emerging economy will lead to increased opportunities and equity in the sectors.

This will not be a simple process and will be time intensive, as well as requiring access to the internet. It is also recommended that the Good Universities Guide be used for explaining the various learning and living conditions.

Asked for ways in which the ADS experience could have been improved, the highest percentage of responses (19 %) was for ‘Work experience or attachment in Australia’.

It will be important the cohort be encouraged to use English at all times at the course, not only during the English language and other lessons / seminars. The use of English during recreational time will greatly strengthen language development.

Focus groups strongly indicate PNG scholars enrolled in TAFE awards are often not focused on TAFE studies as an outcome qualification, but rather an entry point for undergraduate study. It is anticipated that a specific PNG TVET initiative will be supported by AusAID in the future and provide an opportunity to strengthen the PNG TVET sector.

Some Australian universities integrate work experience in professional courses, while others facilitate work experience.

International English Language Testing System or Test of English as a Foreign Language.

Several NZRDS students attend the USP Alafua (Agricultural) Campus in Apia

As mentioned elsewhere, potential NZDS scholars undertake IELTS testing as part of the selection / acceptance process.

The OECD 2008 DAC Peer Review on Australia’s aid criticised the agency’s inability to measure the effect or impact of this form of development support. http://www.oecd.org/document/55/0,3343,en_2649_34603_41877687_1_1_1_1,00.html

Required to demonstrate that a spread of Australian and New Zealand universities are engaged with the ADS scholarship program, as well as that information on Australian and New Zealand institutions and courses is freely available to the potential scholars

For example, if the total number of scholars mobilised to Australia and New Zealand varied by + or – 20% from the numbers included in this design document, that would provide a reasonable basis for a variation to the contract.

Removing the ADS dependency allowance has generally not resulted in family members remaining in PNG, but has certainly resulted in significantly increased financial stresses for the scholars in Australia.

Annotated list: each entry on an annotated list will be coded for quality (high, medium, low), level of attribution (high, medium, low) and type of effect (positive or negative). The purpose of coding is to identify key items for further qualitative analysis.

Annotated list: each entry on an annotated list will be coded for quality (high, medium, low), level of attribution (high, medium, low) and type of effect (positive or negative). The purpose of coding is to identify key items for further qualitative analysis.

Australian Leadership Awards Scholarships Handbook, March 2009, p1.

In the eventuality that PNG scholars start to undertake RDS in other regional countries, the Facility will also be required to gather input / output level indicators on their programs as well as potentially undertake some follow up on the RDS impact in PNG. These costs will be on a reimbursable basis.

In this context, ’quality’ means technically appropriate, relevant to needs, appropriately presented, accurate and timely.