Appendix 6

Summary of quantitative achievements under SPHERE at April 15, 2010

Source: DepED/EDPITAF

| SPHERE Component | Target | Completed | % completed |
| --- | --- | --- | --- |
| Component 1 |  |  |  |
| BESRA Technical Working Groups: |  |  |  |
| TA/TAS | n/a | 27 /12 |  |
| Policy actions | 51 | 29 | 60 |
| LRMDC | RO =17 RO/ DO=33 | RO 1/DO 0 | 6 |
| Teaching and Learning Materials | n/a | 0 (Note: 35 titles ready for reproduction and distribution) | 0 |
| NCBTS Toolkit | 165 DOs | 33 DOs completed; 85 DOs ongoing; 14 DOs not commenced | 20 completed;51 ongoing |
| Component 2 |  |  |  |
| SBM grants | 2,860 schools validated | 2,527 grants disbursed to DOs | 88 (note: not yet disbursed to schools) |
| Component 3 |  |  |  |
| School construction | 507 classrooms/237 sites | 481 classrooms/226 sites | 95 |
| Classroom furniture | 23,801 child sets/543 teacher sets | 6,432 child sets/157 teacher sets | 27/28 |

Note: Procurement  completed in all the 40 DOs funded from MOOE. Seel status report attached as

Appendix 9