PROJECT APPRAISAL DOCUMENT

ON A

PROPOSED GRANT

IN THE AMOUNT OF [US$ 6.45 MILLION]

TO THE

THE LAO PEOPLE’S DEMOCRATIC REPUBLIC

UNDER A MULTI-DONOR TRUST FUND TF091201

FOR A

TRADE DEVELOPMENT FACILITY

March ,4th  2008

ABBREVIATIONS AND ACRONYMS

| ADB | Asian Development Bank |
| --- | --- |
| AFD | Agence Française de Développement |
| AFTA | ASEAN Free Trade Area |
| APEC | Asia Pacific Economic Cooperation |
| ASEAN | Association of Southeast Asian Nations |
| ASYCUDA | Automated Systems for Customs Data Management |
| AusAID | Australian Agency for International Development |
| CAS | Country Assistance Strategy |
| CIDA | Canadian International Development Agency |
| MPI | Ministry for Planning and Investment |
| CPIA | Country Policy and Institutional Assessment |
| DTIS | Diagnostic Trade Integration Study |
| EU | European Union |
| EC | European Commission |
| FDI | Foreign Direct Investment |
| GDP | Gross Domestic Product |
| GMS | Greater Mekong Sub-region |
| GPAR | Governance and Public Administration Reform Program |
| ICR | Implementation Completion Report |
| IDA | International Development Association |
| IMF | International Monetary Fund |
| JICA | Japan International Cooperation Agency |
| LBF | Lao Business Forum |
| MDG | Millennium Development Goals |
| MDTF | Multi-donor Trust Fund |
| M&E | Monitoring and Evaluation |
| MOF | Ministry of Finance |
| MRC | Mekong River Commission |
| NGO | Non-governmental organization |
| NGPES | National Growth and Poverty Eradication Strategy |
| PDR | People’s Democratic Republic |
| PIU | Project Implementation Unit |
| PRS | Poverty Reduction Strategy |
| SECO | Swiss State Secretariat for Foreign Affairs |
| SIDA | Swedish International Development Agency |
| TDF | Trade Development Facility |
| UNCTAD | United Nations Conference for Trade and Development |
| UNDP | United Nations Development Program |
| WCO | World Customs Organization |
| WTO | World Trade Organization |

TABLE OF CONTENT

BACKGROUND	2

TDF DEVELOPMENT OBJECTIVES	3

DESCRIPTION OF ACTIVITIES	4

PARTNERSHIP ARRANGEMENTS	6

INSTITUTIONAL AND IMPLEMENTATION ARRANGEMENTS	7

MONITORING AND EVALUATION	9

Attachment 1: Procurement, Financial Management and Disbursement Arrangements	11

Attachment 2: Description of Activities	23

Component A. 	Trade Facilitation	23

Component B: 	Sanitary and Phyto-sanitary (SPS) and Technical Barriers to Trade (TBT)  Framework (US$ 1.77 million)	27

Component C.	Export Competitiveness and Business Environment (US$1.39 million)	36

Component D:	Capacity Building, Trade Policy, Trade Agreements, and Global Opportunities	41

Component E. 	Strengthening the National Implementation Unit (US$750,000)	43

Attachment 3: DRAFT Detailed Activity Costs	45

Attachment 4: Coverage of Actions in Lao PDR Action Plan by the SPS/TBT Component of the TDF	51

Attachment 5:  DTIS Action Matrix	54

Attachment 6: Summary of the proposed IDA Customs and Trade Facilitation Project	65

Attachment 7: TOR of the TDF Facilitation Team	68

Attachment 8 - Role and structure of the  National Implementation Unit	69

Attachment 9 - Role and structure of the  Government Sub-Executing Agencies	74

### BACKGROUND

The Government of Lao Peoples’ Democratic Republic (GOL) seeks to increase growth and improve export competitiveness through the implementation of its medium-term strategy outlined under its Action Matrix for Trade-Related Assistance, as reflected in the PRSP/NSEDP. The Diagnostic Trade Integration Study (DTIS) action matrix, prepared by Government, was approved during the Lao PDR National Validation Workshop on September 12, 2006, following extensive stakeholder consultations.  The DTIS identifies five priority areas where external assistance and reform should be concentrated:

- Export Competitiveness,

- Trade Facilitation,

- Business Environment,

- Trade Policy, Trade Agreements and Global Opportunities,

- Trade Opportunities for the Poor.

One of the ways in which the GOL will implement its trade agenda is through the establishment of the permanent National Integrated Framework Governance Structure (NIFGS), a multi-agency entity consistent with the WTO Integrated Framework (IF) and the Vientiane Declaration on Aid Effectiveness which will coordinate Official Development Assistance (ODA) in this sector. This will permit a more coherent, effective, and participatory implementation of the comprehensive reform plan spelled out in the Action Matrix (reviewed on a multi-annual rolling basis), synergistic increase in benefits from ODA, and a reduction of the transaction costs incurred with stand-alone development partner assistance. Development partners in future are expected to consider contributing to the GOL medium-term priorities via NIFGS.

Based on lessons of experience, NIFGS is designed to:

  - avoid small uncoordinated projects, which have high transaction costs both for the Government and development partners;

  - ensure full involvement of beneficiaries and stakeholders in the design of trade-related interventions;

  - align all activities with the Government’s existing structures, building ownership and reducing burdensome administrative requirements;

  - permit reasonable flexibility to adapt to changing circumstances;

  - permit medium to long-term engagements permitting a strong focus on capacity building and strengthening skills, and

  - permit transparent and accountable monitoring and evaluation consistent with the objectives established in the IF Action Matrix.

The Government, under the NIFGS will identify and implement the program in the IF Action Matrix, according to the following principles:

- Align development partners support with the multi-year work plans as presented in the regularly updated by GOL Action Matrix for Trade-Related Assistance;

- Clearly identify and account for programs/interventions that development partners will support either through the Multi Donor Trust Fund or outside;

- Streamline reporting and monitoring for government and development partners increasing flexibility and reducing  government and donors’ transactions cost; and

- Provide a multi-year predictable development partner support commitment to the government-led trade reform.

The NIFGS will be supported by the Trade Development Facility (TDF), a multi-donor trust fund to be administered by the World Bank with initial financing from Australia and the EC. Australia and the European Commission will contribute approximately $US6.45m to the part of the TDF managed by the Government for an initial period of four years. The initial activities described below, to be supported by this trust fund, have been selected with the above principles in mind. Australia and European Commission will also contribute to the part of the TDF managed by the World Bank that will support the implementation of TDF (see Attachment 7: TOR of the TDF Facilitation Team for more details on this part of TDF).

### TDF DEVELOPMENT OBJECTIVES

The TDF development objective is to support the establishment of the National Integrated Framework Governance Structure (NIFGS) and implement NIFGS’s initial activities facilitating trade and cross-border movement of goods and increasing the capacity of the Government to undertake specific tasks related to regional and global economic integration. These activities in turn support the GOL’s larger aims of poverty reduction and economic development, as reflected in the NSEDP.

The overarching outcomes pursued are:

- Better trading environment, with simplified bureaucratic procedures including in customs;

- Improved legal and regulatory framework;

- Enhanced general capacity of line ministries and agencies involved in the trade sector;

- Improved private sector’s capacity to compete in the international market;

- More effective participation in bilateral and multilateral negotiations;

- Increased competitiveness of Lao PDR products and contribute to the poverty reduction.

The following tables summarize the activities and types of activities under the proposed TDF and more details are provided in the summary below and in the Attachment 2: Description of Activities.

Table 1. Preliminary break-down of costs by TDF Components.

|  | TDF |  |
| --- | --- | --- |
| Component | Amount, US$ million | % of total |
| A: Trade Facilitation | 0.80 | 12.39 |
| B: Sanitary and Phyto-sanitary Standards (SPS) and Technical Barriers to Trade Frameworks | 1.77 | 27.36 |
| C: Export Competitiveness and Business Environment | 1.39 | 21.51 |
| D: Capacity Building, Trade Policy, Trade Agreements, and Global Opportunities | 1.75 | 27.11 |
| E: Strengthening of National Implementing Unit | 0.75 | 11.62 |
| Total Financing Required: | 6.45 | 100 |

Table 2. Preliminary disbursement schedule, US$ million.

|  | 2008 | 2009 | 2010 | 2011 | 2012 |
| --- | --- | --- | --- | --- | --- |
| Annual | 2.17 | 2.21 | 1.31 | 0.76 | 0.00 |
| Cumulative | 2.17 | 4.39 | 5.70 | 6.45 | 6.45 |

Table 3. Preliminary break-down by type of expenditure, US$ million.

| Allocation of funds by category | Amount Allocated |
| --- | --- |
| Consulting Services | 3.36 |
| Goods | 0.18 |
| Office Refurbishing | 0.15 |
| Training and Workshops | 2.24 |
| Incremental Operating Costs | 0.00 |
| Study Tours | 0.04 |
| Miscellaneous Minor expenses | 0.48 |
| Total | 6.45 |

### DESCRIPTION OF ACTIVITIES

The trust fund will finance investment (stand-alone or co-financed), technical assistance and  capacity building, analytical, diagnostic and advisory services, and provision of goods for a total of US$ 6.45 million, in five components (for more information, see Attachment 2: Description of Activities and Attachment 3: DRAFT Detailed Activity Costs ):

- Trade Facilitation (US$0.8 million)

This component of the TDF will be led by the MOIC DIMEX department and will finance technical assistance for the Government agencies (mostly other than Customs), to help them simplify their procedures, automate their processes, and better coordinate to deliver on the Trade Facilitation agenda under the regional and international agreements. These will include, in particular, computer equipment and training to establish a Trade Portal for the dissemination and use of this information, create basic procedures and systems for the capture of customs and other trade information, and the preparation of a diagnosis of future requirements for the automation of licensing and registries for potential future financing. In addition, support will be provided to a Trade Facilitation Master Plan, including discussions and establishment of the National Body for Trade Facilitation, legislative and policy Trade Facilitation Action Plan, a strategy for trade-related agencies in integrity development, and capacity building for trade-related agencies to improve their coordination to deliver on the trade facilitation agenda.

- Strengthening of the Sanitary and Phyto-sanitary Standards (SPS) and Technical Barriers to Trade (TBT) Frameworks (US$ 1.77 million)

This component seeks to: (i) strengthen the SPS institutional, legal and regulatory framework; (ii) determine risk-based policies and control measures for SPS; (iii) strengthen the role of the private sector in managing SPS; (iv) strengthen the TBT institutional, legal and regulatory frameworks. The project component will facilitate international trade and improve food safety, animal health and plant health through: (1) meeting requirements of WTO, AFTA and other international agreements; (2) improving the investment climate, and (3) improving governance.

- Increasing Export Competitiveness and Business Environment (US$1.39 million)

Given that the thinking on this component has not yet been finalized, this component is designed in a flexible way to allow for future adjustments. It is currently designed around interventions based on the fundamental principles of business development of services with a market development focus, in priority sectors. The aim is thus to improve the productivity of selected sectors with a high potential growth for export, namely the garment industry, handicraft, secondary wood processing sectors and agro processing amongst others. The component will finance technical assistance, training, goods and office equipment or small refurbishing, to be implemented in two phases: feasibility phase will identify priorities and results; based on these, implementation of actions will be determined and carried out based on detailed plans developed in the first phase.

In addition, a number of activities in support of the private sector competitiveness were identified which have to do with strengthening SPS management, and for this reason are detailed here but will be implemented by the SPS-GSEU (see Attachment 2: Description of Activities).

- Capacity Building, Trade Policy, Trade Agreements and Global Opportunities (US$1.75 million)

The capacity development component will finance technical assistance and training program, and is designed to adapt to changing circumstances. The component is designed based on the principles of developing home grown capacity and strengthening of local research, academic and vocational institutions and improve and strengthen Government managerial and technical know-how and ownership. TA will be provided to support the GOL in its ongoing negotiations at bilateral, regional and multilateral level and in particular with respect to the legal obligations, implementation issues and WTO compliance. Particular attention will be given to the design of the TA component with respect to ensuring the transfer of know-how and building of institutional capacity and institutional memory.

The goals of the capacity development program will be identified from the outset and sufficient feed-back mechanisms will be provided to ensure that the support program answers to current capacity needs during the TDF implementation. Given that the thinking on the exact content of this component has not developed to produce a detailed plan, several feasibility studies will be conducted first to identify possible interventions. ,

- Strengthening of the National Implementation Unit and support the Government Sub-Executing Agencies.(US$0.75 million)

This component will finance accounting and administrative systems as well as training and technical assistance in procurement, project management, performance indicator determination and verification, and result verification. It will also finance office equipment, management information and IT systems and equipment.

### PARTNERSHIP ARRANGEMENTS

Under the NIFGS, consultations with all stakeholders (all development partners active in the sector, private sector, etc.) will take place in the framework of the relevant Sector Working Group (or a sub-working group under this working group, as will be discussed during the Round table Meeting in November 2007); however, the final decision on the overall trade policy, reforms, implementation of the trade agenda stays with the Government. The Lao IF Secretariat (LIFS) will remain the body in charge of taking policy decisions, while the Sector Working Group will be a venue for consultations and information sharing. Consultations will take place annually or six-monthly, as deemed appropriate by the LIFS in consultation with the IF Focal Point.

The current Action Matrix will be reviewed on a regular basis and approved by the LIFS  through a Government owned structures under NIFGS (see process in Chart below). The matrix, as it does in its current form, will represent a multi-year work plan for reform and needed assistance in trade-related areas. All interventions aiming at implementing the government’s trade policy, including activities financed through the TDF and by other development partners, should be consistent with the Action Matrix.

Figure 1. Overview of the NIFGS, including NIU and GSEUs under GSEAs, and TDF within it.

National Implementation Unit

Lao IF Secretariat

GOL Supervision and Coordination Level

Technical Supervision

& Implementation Level

–

DTIS AM

IF Task Force

Export

Competitive

IF Task Force

Trade

Facilitation

IF Task Force

Business

Environment

IF Task Force

Trade Policy

Trade

agreements

Global

Opportunities

IF Task Force

Trade

& Poverty

Alleviation

Administration & Coordination

TDF Steering

Committee

Overview of the NIFGS and the TDF within It

TDF

Facilitation

Team

National Steering Committee for Economic Integration

Government Sub Executing

Agency

National Execution

Project Manager

Assistant Project Manager

Subcontract

company

Project Support

Accountant

Secretary

Example of

possible set up

Government Sub Executing

Agency

National Execution

Project Manager

Assistant Project Manager

Subcontract

company

Project Support

Accountant

Secretary

Government Sub

-

Executing

Agency

National Execution

Project Manager

Assistant Project Manager

Subcontract

company

Project Support

Accountant

Secretary

Joint GOL and Donor Supervision and

Coordination Level

GOL National  Policy Formulation and Coordination

IF Trade Executive

Committee*

### INSTITUTIONAL AND IMPLEMENTATION ARRANGEMENTS

The TDF Steering Committee will be co-chaired by a senior representative (Vice Minister of MOIC) of the Ministry of Industry and Commerce and by a Donor Representative agreed by the donors who finance the TDF. It will consist of representatives of government (including MOIC and other line ministries), TDF participating development partners as voting members. The WB as the TDF Administrator will participate in the TDF Steering Committee as observer. The Bank in conformity with its fiduciary responsibility will need to endorse the decisions of the TDF Steering committee, through a Bank-issued ‘No objection’ before implementation. Other key stakeholders will be invited to participate as observers. The TDF Steering Committee:

  - Provides general oversight and strategic directions including advise to the Government on their proposed annual work plan to be financed under the TDF, based on a selection of actions from the Action Matrix and joint identification missions which have taken place;

  - Reviews periodic financial and progress reports, prepared by the NIU with assistance from TDF Facilitation Team.

Decisions are made by consensus and in case of disagreement -- by a system agreed at the first meeting. The TDF Steering Committee will meet at least once a year.

The Administrator (WB) ensures that funds are used in accordance with approved work programs. The Administrator has the final authority to approve projects, programs or actions in accordance with its procedures. The Administrator will manage TDF using its policies and procedures including:

- Prior to project approval, the conduct of appraisal to ensure that project design and implementation arrangements are compliant with WB policies and procedures and meets expectations for achieving agreed development objectives; and

- During project implementation, the conduct of supervision where the WB task team is expected to monitor, supervise, and review all aspects of the implementation, including technical, procurement, financial management, and relevance.

- The Administrator will establish a TDF Facilitation Team accountable to the WB that will be responsible for calling development partner meetings on TDF and generally administrative support to donor coordination within a trade sector-wide approach, generate commitments, help carry out day-to-day management of the TDF, provide inputs to the supervision missions, help ensure compliance with WB rules, and – most importantly -- provide technical assistance (analytical and advisory services) to the GOL/NIU;

- The Administrator together with the GOL, will set up a yearly Fund Raising Plan of activities directed at raising more funds for TDF.

The National Implementation Unit will be responsible for drafting action plans proposals; for coordinating the IF Task Forces and Government Sub Executing Agencies (GSEA) with respect to implementation; for finalizing monitoring reports; for providing any other inputs to the Lao IF Secretariat on issues related to policies, strategies and rolling programs. TA (including AusAID funded IFF Specialist) will be provided as necessary to support these functions. This unit will also include procurement and a financial management staffs who will manage the TDF finances and work in close collaboration with the Government Sub Executing Agencies (GSEA) providing them with  financial management and procurement support. It is expected that the IF National Implementation Unit created under the Window II funds will act as the TDF Implementation Unit.

The IFF Specialist will support the coordination of inputs from development partners not participating in the TDF and will help to ensure that TDF is aligned with GOL Strategy and Plans. AusAID funded IFF Specialist will be attached to the NIU and serve as advisor to the MOIC. IFF Specialist will assist the NIU in the ways that the MOIC finds useful, for example, provide assistance in drafting proposals, provide information on international experiences and best practices, and facilitate participating and non-participating development partner coordination as it comes to TDF Steering Committee and other meetings concerning implementation of the Action Matrix.

The Government Sub-Executing Agencies (GSEAs) are agency implementing units, directly responsible for the technical implementation of the project and execution of the day-to-day activities as stated in the approved action plan. The GSEA will be responsible for ensuring the delivery of specific project outputs. They will work closely with the NIU and report to the NIU on all financial, administrative and procurement issues. For technical matters they may report directly to the appropriate IF Task Force. The composition of each GSEA will be determined on a case by case basis.

IF Task Forces – These inter ministerial Task Forces are critical for ensuring effective and coordinated implementation of the Action Matrix across Ministries, government agencies and specific sectors. Initially there will be 5 Task Forces set up based on the DTIS Action Matrix and these will be a sub- group of the Lao IF Secretariat.  Where there are existing working groups, these will be used instead e.g. National Transport Committee, SPS Working Group, etc.  These will play an important role in supporting the, GSEA and the NIU and will ensure broad based ‘buy in’ of all key Ministries in the implementation process of the Action Matrix. The IF Task force will de responsible to provide guidance to the NIU and GSEA on technical and policy direction in a given sector. The IF Task Force will be responsible to ensure that the outcome for specific sector is reached.

### MONITORING AND EVALUATION

A monitoring and evaluation framework will be put in place, with a set of indicators for each component of the TDF-financed activities. The National Implementation Unit, with technical advice from the TDF Facilitation Team, will prepare yearly updates for the TDF Steering Committee These will be prepared based on the day to day management, and on Aide Memoirs of supervision missions for each component.  In addition the NIU will be responsible for gathering progress reports, which will detail progress towards agreed results and expenditures by activity compared to planned expenditure according to the agreed action plan and budget. All activities will have progress and result indicators, and will be monitored by NIU, which will also provide all necessary information to the twice-yearly supervision missions.

A report on the implementation and TDF performance will be discussed in the TDF Steering Committee. This report will include information on: (i) report on activities conducted and their link to the development objectives; (ii) financial and procurements conducted according to the annual plan; and (iii) implementation plans for the next review period.

The TDF should include capacity building on M&E within MOIC and the relevant IF entities. For supervision of the ongoing activities, joint missions will be financed from the TDF for this purpose.

PROJECT RISKS AT APPRAISAL

| Risks | Risk Mitigation Measures | Risk Rating with Mitigation |
| --- | --- | --- |
| Possible lack of sustained political commitment to the project. | Creation of the National Integrated Framework Governance Structure will institutionalize the proposed governance scheme. | L |
| Possible weak governance structure; lack of clear responsibilities and authority of the various entities. | TDF assistance in the form of an O&M specialist and the preparation of a NIFGS Procedure Manual will help clarify responsibilities and authorities. The TDF Steering Committee and the TDF Facilitation Team will provide assistance throughout project implementation. | M |
| Lack of Implementing Capacity. | Local, regional and international expertise is being brought to bear to bolster existing capacity and ensure adequate TA through the NIU strengthening component. | M |
| Lack of knowledge and experience in Government and underestimation of technical complexity and international dimensions may lead to deficient and ineffective implementation. | In each component and in the implementation unit, national and international TA is brought in periodically to back up capacities for planning, implementation and quality assurance. | M |
| Lack of management expertise in staff involved in the reform may delay implementation. | On-the-job training by experts is being planned for the initial and middle stages of the project. | M |
| Insufficient coordination with development partners may affect program activities. | The TDF Steering Committee is composed of Donor Representatives as well as Government representatives. IFF Specialist will facilitate donor coordination outside the TDF. | L |
| Fiduciary: The risk that the funds will not be efficiently and effectively used for the purposes it was made to attain development objectives. | Considerable strengthening of the IF NIU is envisaged, including electronic project monitoring and accounting systems. A Procedure Manual is being drafted. Semi-annual supervisions and annual External Audit reviews of the Project will help maintain the integrity of the implementation | M |
| Overall project risk |  | M |

## Attachment 1: Procurement, Financial Management and Disbursement Arrangements

PROCUREMENT

General

Procurement of Goods and Works under the TDF shall be carried out in accordance with the “Guidelines: Procurement under IBRD Loans and IDA Credits”, and procurement of Consultant Services shall be carried out in accordance with the “Guidelines: Selection and Employment of Consultants by World Bank Borrowers”, dated October 2006, the provisions stipulated in the Legal Agreements for TDF and as per the agreed procurement plan.   For National Competitive Bidding (NCB), the Government’s procurement procedures as provided in Decree 03/PM dated January 9, 2004, and in the Implementing Rules and Regulations (IRR) dated March 12, 2004, will be followed subject to the improvements listed in the NCB-Annex to the legal agreement.   The various items under different expenditure categories will be agreed between the Recipient and IDA in the Procurement Plan.  The Procurement Plan will be updated at least annually or as required to reflect the actual project implementation needs and changes in institutional capacity.  The appropriate Standard Bidding Documents developed by the Procurement Monitoring Office, Ministry of Finance, will be used for procurement of goods and works under NCB and Shopping, subject to IDA’s prior concurrence.  For International Competitive Bidding (ICB), IDA’s Standard Bidding Documents shall be used.   The complaints handling mechanism specified in the Government’s IRR will be followed and also incorporated in the bidding documents. Contract award information shall be made publicly available in accordance with IDA’s Procurement Guidelines in a format agreed with IDA.

Summary of the Procurement Assessment

Currently, the NIU is led by the Director of General Division and includes two more government officials plus two contractual staff, none of which are procurement professionals.  One of the government officials has worked on UNDP funded projects, but only with limited experience in carrying out procurement processes, and no experience in IDA’s procurement procedures. The current NIU with its current staffing does not have adequate capacity to undertake procurement under the TDF following the Bank's procurement procedures.  Therefore the current risk for procurement is High, but through capacity strengthening measures this risk can be mitigated to Moderate. It is proposed that an international procurement consultant be engaged to provide a total 12 staff-months of inputs spread over the life of the project based on needs, along with one local procurement specialist on full-time basis for at least the duration of the Project and possibly to later be made a permanent staff member of NIU to support their continuing procurement needs after the Project.  The international procurement consultant will also train the local procurement specialist to build local capacity.  The Bank will also provide training to the NIU staff/consultants. With these capacity strengthening measures, establishing rationalized thresholds for IDA’s prior review and for encouraging greater use of the more competitive procurement methods, requiring application of mechanisms for complaint handling and disclosure of contract award information, and expanded scope of ex-post reviews including checks for transparency in addition to procedural compliance and also verification of end-use deliveries, the procurement risk is expected to be Moderate.

Procurement Methods

(This section to be updated after finalization of the procurement plan which is presently under preparation by NIU)

Goods estimated to cost more than US$100,000 equivalent per contract shall be procured through ICB procedures. Goods estimated to cost between $30,000 to $100,000 equivalent per contract may be procured through NCB procedures subject to the improvements listed in the NCB-Annex to the legal agreement.  Goods estimated to cost less than $30,000 equivalent per contract may be procured through Shopping procedures.

Works, including office renovation activities, estimated to cost more than US$300,000 equivalent per contract shall be procured through ICB procedures. Works estimated to cost between $30,000 to $300,000 equivalent per contract may be procured through NCB procedures subject to the improvement lists in the Annex to the legal agreement. Works estimated to cost less than $30,000 equivalent per contract may be procured through Shopping procedures.

Consultant Services requiring employment of firms and estimated to cost more than US$50,000 equivalent per contract shall be procured through the Quality and Cost Based Selection (QCBS) method.  The method Selection Based on Consultants’ Qualifications may be used for contracts estimated to cost less than $100,000 equivalent. Other methods as Quality Based Selection, Least Cost Selection and Fixed Budget Selection may be used as appropriate and as agreed in the procurement plan. Single Source Selection method may only be used in exceptional circumstances when justified in accordance with the Consultant Guidelines and with IDA’s prior concurrence. Consultant Services requiring employment of individual consultants shall be procured in accordance with Chapter V of the Consultant Guidelines.

Review by IDA

(This section to be updated after finalization of the procurement plan which is presently under preparation by NIU)

The first contract each for procurement of Goods and Works under NCB and Shopping regardless of value, and all contracts for goods and works exceeding US$100,000 equivalent shall be subject to IDA’s prior review.   The first contract for employment of consulting firms under the SBCQ method, the first contract for selection of individual consultants, regardless of value, and all contracts exceeding US$ 100,000 in case of firms and US$50,000 in case of individuals shall be subject to IDA’s prior review.  Also each contract for Single Source Selection shall be subject to IDA’s prior review.  All other contracts will be subject to ex-post review by IDA, including checks for transparency in the procurement process and verification of end-use deliveries.

Frequency of Procurement Supervision

Procurement supervision missions will be conducted by IDA at least twice a year to include ex-post review of procurement activities and to address any procurement implementation issues.

FINANCIAL MANAGEMENT

Summary of the Financial Management Assessment

A financial management capacity assessment of the National Implementation Unit (NIU) of the Ministry of Industry and Commerce which will coordinate the implementation of TDF project was done in September through to October 2007. The assessment also extended to the current accounting department of the ministry. The objective of the assessment was to assess the adequacy of proposed financial management arrangements of the project whether they meet the IDA’s requirements as per OP/BP10.02.The financial management assessment covered areas such as budgeting, accounting, internal controls, funds flow, financial reporting and auditing arrangements. These arrangements are deemed acceptable if they are capable of correctly and completely recording all transactions and balances relating to the project. In addition, such arrangements are acceptable if they can facilitate the preparation of regular, timely and reliable financial statements and safeguard the projects assets; and are subject to auditing arrangements acceptable to IDA. The assessment was conducted through discussions with the directors and staff from the MOIC and the NIU in the ministry and staff from Ministry of Finance.

The TDF project will be implemented in an inherently moderate risk environment. Thus the inherent risk of the project is assessed as moderate owing to the strong mitigation measures the ministry is already undertaking in view of the  weak financial control environment within which it will be implemented and systems of the public sector. The ministry has decided to use a parallel system and has opted to document such systems which staff working on the project will follow. Otherwise the residual risks the project will be confounded with are weak enforcement of contracts, specifications and procedures. Other elements of the residual risk arise from the country’s slippage on the MPI ranking by Transparency Internal where the slippage is by more than ten percent to 163. The difficulty of timely accounting for fuel advances and allowances also pose serious risk.

A number of mitigation measures have been outlined in the report. In addition, good governance framework measures will be formulated and included in the project financial management and the project manual of operations to ensure that the key risks are addressed during implementation. External audits performed annually will help to deal with some of the risks outlined in the report.

In conclusion, the proposed financial management arrangements put in place by the MOIC for the project have been assessed as meeting the Bank’s requirements as per OP/BP10.02.The MOIC, however, has to proceed to implement the key suggested action plans as outlined in the detailed financial management capacity assessment paper.

Country Issues

The Country Financial Accountability Assessment (CFAA), carried out in mid-2002 concluded that the overall fiduciary risk in Lao PDR is considered to be high, despite the fact that there are elaborate built-in controls within the government FM system. The findings are as a result of insufficient transparency in public finances. The budget process is not yet transparent and public access to government financial information is limited.  These weaknesses have been compounded by insufficient awareness of modern practices of internal control in the public sector and by the government’s ongoing decentralization initiative, which needs to be supported with a sufficiently robust institutional framework that clearly defines the new responsibilities at lower levels.  Technical capacity of staff at these levels needs to be strengthened and the oversight functions and the State Audit Organization need improvement. A recently completed IDF grant to improve accountability in State owned enterprises and the private sector has helped develop the environment for the accounting and auditing professions and initiated amendments to accounting and auditing laws. A Public Expenditure Review combined with an Integrated Fiduciary Assessment has been completed and disseminated whose findings go support the weak accounting environment.

The recent  Joint Portfolio Effectiveness Review (JPER) undertaken by GoL, ADB, SIDA and WB also identified similar issues and weaknesses and it was agreed that a series of remedial measures in a time bound action plan would be implemented, including: (i) delegation of authority over the management of project designated accounts to executing agencies that have in place adequate quality and control systems; (ii) streamlining of approval processes; (iii) harmonization of a FM manual; (iv) utilization of uniform FM software; (v) consolidation of project FM functions; and (vi) implementation of a consolidated training program.

While these actions have started to improve specific fiduciary issues, the country FM environment for externally-funded projects remains weak as the effects of some of the measures being implemented are not yet being felt. In addition, some of the recommendations are at early stages of implementation.

The bulk of external assistance has been channeled off-budget both in the sense that resource allocations are not reflected in the government’s budget documents and those funds are not disbursed through Treasury. This lack of information and absence of effective instruments to guide the allocation of external financing seriously undermine the integrity and effectiveness of the budgetary system. There is insufficient transparency in public finances. The budget process is not yet transparent. The FMCBP and the formulation of government’s master plan for reform of Public Financial Management through the PEMSP aim at addressing all the above weaknesses by mobilizing funds from a number of donors to finance a comprehensive Public financial management overhaul of the respective inter related systems.

A financial transactions review undertaken in 2007 reveals a number of project portfolio wide financial management weaknesses. A review of management letters issued on previous projects implemented by the sector shows a number of weaknesses in internal control.

Risk Analysis

As annotated above, the previous AAA undertaken by the World Bank and its partners in 2002 reveals that the overall fiduciary risk in Lao PDR is considered high. As most of the aspects aimed at mitigating the risks are still under implementation, the risk level has not changed much. The risks arise from the increased usage of cash although there is serious attempt by government to more usage of cheques and transfers as part of the FMCBP. The systemic weaknesses heighten fiduciary risk to funds to be made available by the financiers of the project. To address the perceived risks, an action plan has been developed to strengthen the project’s financial management systems. In addition, some of the big tickets items are already incorporated in the PEMSP to address the PFM systemic weaknesses.

| Risk | Risk Rating | Risk Mitigation measures incorporated into project design | Risk after Mitigation |
| --- | --- | --- | --- |
| Inherent Risk |  |  |  |
| Country level Fiscal environment: There is weak control environment with serious weaknesses in National Treasury operations, especially in cash management, inadequacies in PFM accounting system, and weak internal and external auditing capacity. Owing to low salary level within Public service, fuel, training and workshop allowances are a means of livelihood and are likely subject of abuse. | High | The NT weaknesses and the generic PFM inadequacies are being addressed through the FMCBP. Government wide, staff will be trained in MTEF principles, Treasury management, commitment control and debt management. Annual public expenditure reviews will be undertaken to check on the weaknesses noted amongst other things. The FMCBP has clear achievement indicators in reforming and addressing the weaknesses noted. At project level, TDF will have specific project level financial management arrangements aimed at addressing some of the key weaknesses observed above. It will have its own planning, budgeting and reporting on financial performance, project specific staff appointed from the Ministry whose skills will be further enhanced by training in project FM; a designated accounts of the finances of the project will be opened, monitoring of FM through FMRs and bi-annual supervision. There will be annual external audits. Fuel and allowance rule compliance will be subject of review of every mission and will also be checked upon by external auditors. A specific project FM manual has been developed which outlines the various processes to be followed... | Substantial |
| Inability to use funds efficiently and economically for purposes intended | Substantial | There shall be enhanced accounting and reporting. Independent external auditors shall be engaged to conduct annual audits. | Moderate. |
| Potential corruption arising from procurement | Substantial | ICB shall apply for all contracts above a certain threshold and WB rules shall apply. A review of indicative red flags for collusion will be periodically conducted. | Moderate |
| Inability to properly account for advances, fuel and allowances | Substantial | The project shall maintain an advances register which shall be reviewed by external auditors. Log books and fuel registers shall also be maintained by the project. The respective books shall be reviewed each mission. | Moderate |
| Overall inherent risk | Moderate |  |  |
| Control risk |  |  |  |
| Budgeting | Substantial | Budgets will be prepared annually and revised bi-annually. Financial budgets will be linked to physical outputs through the operating plan. The FMRs to be prepared will be used to monitor variance analysis with budget | Moderate |
| Funds Flow-IDA administered funds. Such funds may be released untimely. | Moderate | The funds from IDA will flow directly from IDA to the designated accounts maintained at Bank of Laos | Low |
| Staffing | Substantial | Finance staff to be chosen will be trained in handling WB managed funds in addition to the experience they already have in managing UNDP funds. Attempt will be made to select such staff on meritocracy with experience and good qualifications. | Moderate |
| Lack of experience in managing multiple donors | Substantial | Project staff will be supported by a consultant on FM and other areas initially for a period of eighteen months. A new financial management manual has been written and will be available to guide all staff. A launch workshop where FM procedures will be discussed will be organized. | Moderate |
| Accounting policy and procedures | Moderate | A consistent set of accounting policies and procedures has been set up and will be applied as per FM manual. Training of the accounting policies and procedures to be organized for staff. | Low |
| External Audit | Low | Annual financial audit of the project’s financial statements by independent auditors to be conducted. This will be done annually. | Low |
| Reporting and Monitoring | Substantial | An update of the system will ensure that there is a link between financial and physical progress reports. The reports will be system generated after inputting all the requisite inputs. Only one report shall be produced for all donors sharing the financing of the project. | Moderate |
| Information Systems | Moderate | Attempts will be made to buy software for the project. | Low |
| Overall control risk |  |  | Moderate |
| Overall Project Risk Rating | Moderate |  |  |

Financial Management staffing

Currently, the NIU,has one staff in charge of accounting. who is running the finance section of the unit. Since the staff is also responsible for other projects within the ministry, the current capacity is not deemed adequate. The observation is exacerbated by the fact that this unit has never implemented a World Bank funded project arising from multi-donor Trust funds. Apart from an identified accountant for the project, it would be good if an assistant accountant were selected to help the former and also enhance the level of segregation of functions within the project. The Accountant for the project has a Bachelors degree in Financial Management from a reputable university in Thailand and five years experience of work on donor financed project. One of the two people identified to work with her as assistants has lower ranking accounting qualification and more than two years experience in managing a donor funded project.  The identified staff has been assessed as having adequate capacity to undertake the envisaged functions of the TDF. However, they could do with an assistant accountant. It is therefore suggested that one more accounting staff be identified to work as an assistant accountant in the project selected from civil service.

The organizational structure of the finance function of the TDF has been determined. The job titles and descriptions though determined have not yet been fully written up in the project operational manual. This will be done by the time the TDF is set up. Such staff is ministry staff that is not on contract. The transfer rate of such staff out of the ministry is very minimal. Currently, there is no training policy for finance and accounting staff. It is hoped that accounting staff working on this project shall benefit from capacity building efforts and a resultant capacity building plan of the project to further their accounting skills.

Accounting Policies, systems and procedures

The project’s key accounting policies and procedures have been articulated in a draft project accounting manual. The NIU accounting systems are currently manual. Whilst they have been running very well so far, it takes staff quite sometime to produce the annual financial statements on the current projects being implemented. Since the basis of disbursements of the project is report based, it is envisioned that project specific software will be purchased to enhance recording of information and production of such financial reports. The software to be bought will have to be able to record and track project expenditures, including the allocation of expenditures in accordance with the respective components, disbursement categories and various sources of funds. It will ensure that cost allocations to the various funding sources are made accurately.

All accounting and supporting documentation will be retained by the finance unit of the NIU on a permanent basis in a defined system that allows authorized users easy access.

Budgeting

The budgets as currently prepared in the ministry and by the NIU do not lay down physical and financial targets. However, budgets are prepared for all significant activities in sufficient detail to provide meaningful tool with which to monitor subsequent performance. Actual expenditures are normally compared to the budget every quarter and explanations obtained for significant variations from budget. Approvals for variations from budget are obtained in advance. The ministry has enough procedures to plan project activities, collect information from the units in charge of the different components and prepare budgets. Other project budgets developed by the ministry have so far not been realistic based on assumptions developed by knowledgeable persons because in most cases they are not activity based. They are more incremental budgets developed by ministries rather than anchored on Medium Term Expenditure Framework.

Payments

Invoice processing was reviewed and considered less adequate. This is because there is no comparison between actual goods received and the quantity for which an invoice has been issued by the supplier. In addition, there is no checking with warehouse or supplies with on quantities received. For goods purchased comparison of invoice quantities, prices and terms with those indicated on the purchase order and with records of goods actually received is not done. Checking of calculations on such invoices is done though not authenticated. Invoices are not stamped “PAID”, dated, reviewed and approved and clearly marked for account code assignment.

Policies and Procedures.

The basis of accounting is cash. Preparation of financial statements is supposed to be guided by Lao accounting standards. Note should be taken that there are only less than fifteen Lao standards derived directly from International Accounting Standards. Their applicability in government is very limited if not non existence. The NIU and GSEA to manage the project has a properly written draft financial management manual. It is this manual that describes all project accounting procedures to be adopted and used during implementation. Effort will have to be made to ensure that this manual is regularly updated. In the sector, there are no explicit procedures in place that allow for authorized persons only to alter or establish a new accounting principle, policy or procedure to be used by the ministry. Conflict of interest and related party transactions rules are not explicit within the ministry and so are rules that provide safeguards to protect the ministry from such actions. However, the project draft manual of procedures will have to be distributed to appropriate personnel and clearly articulate the issues of conflict of interest and who is authorized to change codes and establish new accounting policy.

Cash and Bank

Since the project is at an appraisal stage, no bank accounts have yet been opened. The authorized signatories have been annotated above-being the Minister of Finance or his designee. For the current projects financed by the UNDP and other donors in the sector, there are adequate controls that exist for the collection, timely deposit, and recording of receipts at each cash location. Cash and bank are reconciled on a monthly basis. There was no evidence we obtained to show that unusual items on the bank reconciliation are followed up after review and approval.

Information systems

Whilst the projects financial management system is not yet in place, the existing NIU does not have a computerized accounting system. As such, it is difficult to determine whether there is ample evidence that the processing system does help in safeguarding the confidentiality, integrity and availability of data.

Safeguard over Assets

There are not explicit policies and procedures to safeguard and protect assets from fraud and waste through recording such assets in a fixed asset register. Periodic count of inventory is not regularly done. Assets are not insured. It will be necessary that the project maintains a fixed asset register and conducts period count of its physical inventory.

Reporting and Monitoring

The project financial statements will be prepared by NIU and follow the Lao Accounting standards. Every quarter, such financial statements will be prepared. Such reports will have to be prepared in timely fashion-forty five days after the end of the quarter. The current system does not have the capacity to link the financial information with the projects physical progress. A separate system may need to be developed to gather and compile physical data and establish controls to reduce the risk that physical data may not synchronize with financial data. In view of this suggestion, there will be need to establish financial management responsibilities that specify what reports are to be produced, what they are supposed to contain and how they are to be used. Management of the NIU will have to be inducted on how to use such reports. The reports will have to compare actual expenditures with budgeted and programmed allocations

Internal control/Internal audit

There is no internal audit function within the MOIC. MOF is planning to establish internal audit government wide soon and it is that the ministry will benefit from such an act. The internal audit will therefore cover the review of project internal controls within its work program once in place.

External Audit

The Ministry of Industry and Commerce is supposed to be audited by the Supreme Audit Office. The SAO can only do compliance audits at the moment. As such, the project’s annual financial statements will be audited in accordance with International Standards on Auditing by independent auditors based on acceptable terms of reference to IDA. The audited financial statements and audit reports will be submitted to the World Bank and other donors within six months after the end of each fiscal year, and the closing date of the project.

There will be one audit report and one set of financial statements on which the auditors will issue a single opinion covering project accounts, the usage of funds, and the management of designated accounts. In addition, a management letter outlining any internal control weaknesses of the implementing office and other agencies at various implementation points will also be issued by the external auditor together with the audit reports. The MOIC through NIU will be responsible for engaging and managing the audit contract. It will responsible for appointing an auditor six months after signing of the projects governing legal agreement. The cost of the audit will be financed from project proceeds.

Emphasis will be placed on assessment of proper use and accountability of funds, and procurement.

Supervision Plan

As the Financial Management inherent risk is assessed as moderate, supervision of project financial management will be performed at least twice a year. The supervision will review the projects financial management systems including but not limited to operation of designated account, evaluating quality of budgets, project financial management reports, assessing relevance of financial management manual, statements of expenditures, internal controls, reporting and follow up of audit and mission findings. The review will also conduct random reviews of financial statements, compliance with covenants; the financial management supervision will be conducted by IDA’s financial management specialist staff and at times assisted by consultants. At each time of supervision, the projects financial management risks of the project will be assessed and influence the frequency of supervision.

Funds flow and Disbursements Arrangements

Disbursement basis

The Multi-Donor Trust Funds under the TDF will be accounted for separately from the World Bank own resources. The Bank will agree on specific financial and administrative arrangements with co-financing bilateral and multilateral agencies that ensures it manages funds and supervises MDTF interventions in the same manner as it does with respect to its own resources.

Administrative agreements will be established between the Bank and each donor. These will be legally binding arrangements between the IDA as the Administrator of the TDF and donors as providers of financial resources to the TDF setting out the terms and conditions under which the funds are made available and used. All donors, however, will enter into individual administrative agreement with IDA, by signing the Trust Fund Administration Arrangement. The terms and conditions that will govern the agreements will be identical for all donors. In addition to providing details on the committed funds, the administrative agreements will provide for reimbursable expenses incurred by IDA in establishing and maintaining the TDF MTDF.

The Trust Fund Administration Arrangement will specify the total amounts that the donors intend to make available as a grant to the TDF MTDF together with a payment schedule, i.e. the amount payable upon signing the agreement and in subsequent tranches thereafter. IDA will submit a payment request to donors before any payments are made. The World Bank will maintain an IBRD Cash Account or a T account at the World Bank headquarters. The individual Trust Fund Administration Agreements will provide full details of the account which shall include the account number, swift code, internal route code, bank name and bank address.

Upon receipt of a payment request from IDA, each donor will deposit the agreed initial amount into the specified bank account maintained by the World Bank and instruct the bank to include in the remittance advice: (1) the amount paid (ii) name of donor (iii) confirmation that the amount is for MTDF and (iv) date of deposit. This will be the parent account.  The donors will be required to submit a copy of the remittance advice to the World Bank’s Accounting Trust Fund division. The MDTF account will be held in USD.  As such, all donor contributions that are not in USD will be converted to USD upon receipt.

Subsequent deposits of grant amounts by donors will be made into the IBRDs Cash Account following the cash payment schedule as per Trust Fund Administration Arrangement and Procedures to be developed and following submission of a payment request (also referred to as Call of Funds) from the World Bank.  The payment request will be accompanied by an unaudited statement of receipts, disbursements and fund balance showing the trust fund cash balance as of the date of the request. Such deposits will be made subject to the provision of the following documents by the World Bank:

- Actual and projected disbursements envisaged in the quarterly reports;

- Progress Reports.

Disbursement Arrangements

The Child/Disbursing Accounts

Two child disbursing accounts will be established under the TDF MDTF. The first account will be used for Bank execution to cover incremental supervision costs and other expenses related to running the TDF, including but not limited to analytical work needed to implement the projects according to development objectives, supervision and technical missions, and to support the TDF Facilitation Team. The second one is a special (designated) account which will be opened and managed by the Ministry of Finance. The Ministry of Industry and Commerce will establish a project account in any Commercial bank to facilitate the project expenditure. A grant agreement between IDA and the GOL will establish the applicable disbursement arrangements for the project.

Allocations from the parent TF account will be made to the respective child accounts established for purposes of financing the agreed activities.  For the Bank-executed child account, disbursements will be made by directly charging the child account for eligible expenditures agreed to in the Trust Fund Administration Agreement and following standard Bank policies and processes that are applicable to regular Bank budget. Withdrawals/disbursements against the recipient-executed child account (grant account) will be made on the basis of the Grant Agreement that will be executed between IDA and the Government of Lao PDR.

IDA will establish disbursement arrangements for the project in consultation with GOL-specifically Ministries of Finance and Ministry of Commerce and Industry, on the basis of a financial management capacity assessment of the projects financial management arrangements, and the projected cash flow needs of the project. The Banks LOA department will specify these arrangements in a Disbursement Letter to the Government of Laos. The LOA may disburse proceeds from the grant account to designated account for the project using one or more of the following disbursement mechanisms:

- Reimbursement: GOL would be reimbursed for eligible expenditures pre-financed from their own resources;

- Advance: grant proceeds are advanced into designated accounts to finance eligible expenditures as they are incurred.

Prior to the withdrawal of any grant proceeds from the grant account, the GOL will furnish the World Bank’s Country lawyer for Lao with the names of the officials authorized to sign applications for withdrawal applications and their authenticated specimen signatures.

Withdrawal form the designated account

Ministry of Finance, on behalf of the recipient, will open and manage special (designated) account at the Bank of the Lao PDR on terms and conditions satisfactory to IDA.

Since the project expenditures will be expected to vary during the life of the project owing to the variant sub grants to be made, a ceiling based on periodic (six-monthly) forecasts will be established and agreed in order to meet variant implementation needs. As such, the ceiling will be based on GOL forecasts of disbursements as provided for in the interim un-audited financial reports. Thus the ceiling of the designated account is likely to change from period to period to reflect changes in cash flow needs. The Bank task team will assess the reasonableness of forecasts and may adjust the amount it will be willing to advance if not satisfied that the forecast is justified by planned project expenditures.

The authorized representative of the Recipient will approve these periodic (six-monthly) withdrawal applications given the preliminary plan of disbursements provided by MOIC/NIU and provided that MOIC/NIU submits the supporting documentation and statements of expenditure, as below.

The GOL will periodically (six-monthly) request for funds to be transferred from the grant account to the respective designated account by preparing and delivering to the LOA team in Manila through the Lao Country office, a written application for withdrawal for such amount and category as stipulated in the Grant agreement.

Withdrawal applications must be:

- Authorized by a representative of the recipient;

- Accompanied with evidence in support of the application as the World Bank may reasonably request.

In summary, IDA requires the following supporting documentation:

- Interim financial reports;

- Statements of expenditure;

- Records and /or

- Records required by IDA for specific expenditures and statements of expenditure for all other expenditures.

Direct payment methods may also be used for expenditures above the levels for SOEs given below.

Disbursement of Trust funds into a government managed designated account will be based on Interim unaudited reports, or direct payment. The NIU shall prepare interim unaudited reports forty five days after the end of each quarter to be submitted to IDA for its designated account through Ministry of Finance unit which deals with IDA replenishments. This application will be accompanied by robust cash forecast for the next two quarters, a designated account bank reconciliation

Signatures on the IDA Withdrawal applications shall be the Minister of Finance or his designate and the Minister of Industry and Commerce or his designee.

Financial Management Action Plan

The following need to be undertaken:

- An additional assistant accountant should be selected to work in the project to ensure that the project produces meaningful unaudited financial monitoring reports on time that contain enough information for monitoring project progress and as a basis of disbursements..

- Formulate and agree on a template of Interim Financial Reports. This needs to be done before negotiation based on FMR guideline annexes shared with the project preparation team...

- Write out project software characteristics to be bought. Then proceed to advertise by project negotiation. This software should be installed before the project becomes effective.

- Finalize the project Financial Management manual detailing how the project will manage training, workshop and travel advances and fuel consumption on project motor vehicles.

- Develop financial audit terms of reference for the project-before negotiations.

- Appoint an auditor of the project six months after project effectiveness.

- Develop a comprehensive capacity building plan for the accounting staff   in the new project and for the accounting department of the ministry and decide how much to finance.

- Develop rules for conflict of interest and determine to whom to report.

- Formulate key financial controls that will help prevent or detect corruption and include in the projects financial management manual.

## Attachment 2: Description of Activities

|  | TDF |  |
| --- | --- | --- |
| Component | Amount | % of total |
| A: Trade Facilitation | 0.80 | 12.39 |
| B: Sanitary and Phyto-sanitary Standards (SPS) and Technical Barriers to Trade (TBT) Frameworks | 1.77 | 27.36 |
| C: Export Competitiveness and Business Environment | 1.39 | 21.51 |
| D: Capacity Building, Trade Policy, Trade Agreements, and Global Opportunities | 1.75 | 27.11 |
| E: Strengthening of National Implementing Unit | 0.75 | 11.62 |
| Total Financing Required | 6.45 | 100 |

#### Component A. Trade Facilitation

Extensive diagnostic work done with Government by the World Bank and other development partners specifically identify border procedures as a key constraint and priority to be addressed. The Diagnostic Trade Integration Study was led by the WB under the IF framework and identified business environment and non-trade barriers as key constraints to exporters. The Joint WB/ADB Investment Climate Assessment identified key investment climate constraints that exporters and other firms face, and highlighted the differences between the constraints that exporters and non-exporters face.

In spite of significant improvements achieved in recent years, both by the Lao PDR Customs Department (LCD) and other border-related regulatory agencies, the processing and clearance of import, export and transit goods in Lao PDR remains relatively inefficient and time consuming.  The processes rely too much on manual processing of paper-based documentation, followed unevenly across the country.

While principal responsibility for the processing and clearance of goods rests with the Lao PDR Customs Department (LCD), up to sixteen other local and central government entities were still involved in the process in 2006. Although as of October 2007 most of them are no longer at the border, they still require access to information provided by Customs to carry out their missions.

Customs operations are already being rationalized and automated through the introduction of an automated system financed by a complementary IDA project (Lao Customs and Trade Facilitation Project). This component of the TDF will finance similar technical assistance for the agencies other than Customs. These will include, in particular, computer equipment and training to establish a Trade Portal for the dissemination and use of this information, create basic procedures and systems for the capture of Customs information, and the preparation of a diagnosis of future requirements for the automation of licensing and registries for potential future financing. In addition, support will be provided to a Trade Facilitation Master Plan, including discussions and establishment of the National Body for Trade Facilitation, legislative and policy Trade Facilitation Action Plan, a strategy for trade-related agencies in integrity development, and capacity building for trade-related agencies to improve their coordination to deliver on the trade facilitation agenda.

Sub-Component 1: Implementation of Lao PDR Trade Portal (US$600,000)

This subcomponent envisages the establishment of a trade portal for Lao PDR.  Initially, the portal will aggregate and integrate all of the trade related information available on individual ministries and agency website in an easily accessible manner. The automation of key trade licensing and permitting agencies will follow (supported by future or additional funding). This subcomponent will consist of three primary activities in licensing and permitting agencies involved in Trade other than Customs:

- Process simplification and harmonization based on risk management principles, of procedures and documentation requirements for licensing and permitting processes.

- Publication of trade related information including regulations, procedures, fee schedules, penalties and necessary forms to be used on line ministry and agency websites. Integration and aggregation of this information on the Lao PDR Trade Portal.

- Automation of trade related licensing and permitting processes in key line ministries and agencies.

Activity 1.1 Process Harmonization and Simplification

Based on the initial review of documentary requirements undertaken by the EU, this sub-component will first support the rationalization and simplification of trade related documents and procedures.  The subcomponent will review and redesign all import, export, and transit procedures and documentation with a view to simplifying and harmonizing procedures across agencies and eliminating all non-essential and duplicated documents. New procedures will be based on internationally recognized risk principles, enabling selective intervention in circumstances indicated by pre-determined risk criteria. In addition, the review will consider options for assurance regimes that do not require the submission of transaction based documentation. This activity will complement similar rationalization of customs procedures and documentation that will be undertaken in the Customs and Trade Facilitation (CTF) project. The activity will also ensure that the Single Administrative Document (customs declaration) implemented in the CTF project provides the necessary information and data sets for all involved border agencies.

Activity 1.2 Trade Information

This sub-component envisages the publication of all trade related information on the individual ministries and agency websites and the establishment of an information portal linking all of this information together in an easily accessible manner.  The chart below depicts a possible approach.  The portal should logically be operated and maintained by the Ministry of Industry and Commerce with its mandate to facilitate trade and competitiveness. The IF would be the logical coordinating structure. Financing for the development of the portal (Lao-Trade.gov.la) and the relevant changes to individual agencies websites and procedures are to be included in this activity. Such an approach would have an added advantage in that it would assist Lao PDR to comply with changes to GATT Article X currently being discussed as part of the WTO Trade Facilitation negotiations.

Activity 1.3 Automation of Licensing and Permitting Procedures

The World Bank financed Customs and Trade Facilitation project will provide Lao PDR Customs with the Customs system. This system is appropriate for Customs but it will not, on its own, contribute to the automation and coordination of other border management agencies.  To achieve the project objectives described above priority will be given to identifying and implementing an appropriate suite of small, purpose built IT solutions linked through the portal that can connect and interact with the Customs system in Customs.

The project will develop a technology strategy to ensure that IT is deployed effectively and efficiently to support operations of the non-customs border agencies, enhance cross-agency communications, and interface with the customs Customs system. Automation will enable these agencies to streamline their operations, reduce the risk of errors, improve the level of transparency and accountability, and reduce the costs borne by the importing and exporting community and ultimately by the national economy. The strategy will purposely be developed to provide the basis for a later phased introduction of a full ‘single window’ functionality.

Subject to a successful completion of the agreed project milestones for phase one, a second phase of the subcomponent will develop the full ‘single window’ functionality to connect the trade community and relevant government agencies and stakeholders via a shared system and trade network. The architecture for the ‘single window’ including the detailed design, timing and activity phasing of the IT sub-component will be based on a detailed assessment of IT and business requirements. Phase two of the subcomponent will make a significant contribution to the achievement of the government’s trade facilitation objectives by lowering transaction costs and reducing clearance times.

Indicators: Subcomponent performance will be measured in terms of a significant reduction in a) the number of documents required by the border agencies; and b) reduction in aggregate processing times for trade related licensing and permitting procedures.

Sub-Component 2: Trade Facilitation Master Plan (US$200,000)

The need for a consistent strategy in trade Facilitation is needed for a successful WTO accession and for delivering on the objectives stated in the NSEDP. In this respect, support will be provided to a Trade Facilitation Master Plan, led by the MOIC/DIMEX, including discussions and establishment of the National Body for Trade Facilitation, legislative and policy Trade Facilitation Action Plan, a strategy for trade-related agencies in integrity development, and capacity building for trade-related agencies to improve their coordination to deliver on the trade facilitation agenda. The exact activities in this sub-component will be further discussed with DIMEX and other GOL agencies.

#### Component B: Sanitary and Phyto-sanitary (SPS) and Technical Barriers to Trade (TBT)  Framework (US$ 1.77 million)

Lao PDR has shown much progress in its overall economic development with sustained growth rates of about 6 percent per year. Agriculture still contributes 45 percent of the country’s GDP and it employs about 80 per cent of the population. Its sustained growth of about 4 percent per year—facilitated among others by expanded infrastructure, spill-over of technology from neighboring countries and improved investment climate—has contributed to poverty reduction. However, there is much untapped potential for poverty reduction through accelerated and diversified agricultural growth and exports.

Increasing income and growth in neighboring countries forecast a growing demand for food and agricultural products. These can be supplied from Lao PDR, whose natural resources favor expansion of agricultural production. Foreign Direct Investment (FDI) in production, processing and trade could be an important contribution to increased production capacity in exportable products, as well as to further spill-over of technology. Improvement of the investment climate, membership of the World Trade Organization (WTO) and making optimal benefits of ASEAN Free Trade Area (AFTA) membership will play synergetic roles in unleashing the growth potential of agriculture.

Exports of agricultural products from Lao PDR have not yet faced a major ban or suspension for SPS non compliance, but there are specific concerns for the future. At present most agricultural exports are destined to market segments in neighboring countries where food safety and quality requirements are still moderate or low. Probably half of agricultural exports are through informal border trade. However, public and market requirements for quality and safety in neighboring countries are also increasing. Accessing more demanding market segments in the region and elsewhere will generally require two elements: (i) a greater private sector role in scaling up local production, and (ii) improved SPS management in the public and private sector. Hence, SPS management becomes an increasingly important part of competitiveness and investment climate.

The present management of food safety and animal and plant health has severe weaknesses and its implementation does not meet WTO and AFTA requirements. The main issues are:

- Incidence of food and water-borne diseases is much higher than in other countries of Southeast Asia (except for Cambodia) and cause high mortality and high costs to households because of inability to work and expenditures on treatment.

- Several endemic livestock diseases, such as Highly Pathogenic Avian Influenza (HPAI), Foot and Mouth Disease (FMD), Classical Swine Fever (CSF), Newcastle Disease, and various other animal diseases form serious constraints on formal trade and income of farmers; zoonotic diseases form risks for human health.

- Plant pests seriously affect productivity and income of farmers. With increased reliance on higher value crops and new varieties, and larger-scale operations for exports, the risk that trade will be disrupted by outbreaks increases.

Many aspects of SPS management are private sector responsibilities. However, most private sector entities are small, and lack capacities to rapidly upgrade product quality, safety, volume and consistency. Moreover, they are in part dependent on an environment that offers good governance, adequate public services and business development services. Government agencies dominate in policy preparation and implementation; in the area of SPS management trade and business associations are not yet engaged on a regular base in public-private dialogue and public-private cooperation.

The legislative and regulatory framework for food safety and agricultural health does not meet the basic requirements of WTO SPS and AFTA. Transparency requirements cannot be met and inspections and border controls are not science- and risk-based. Overall, implementation is weak, and there is too much discretionary power and rent-seeking. Human skills in relevant areas, such as institutional development, standard setting, diagnostics and detection, surveillance, inspection, training in hygiene, is scarce. There are very few legal specialists in the ministries to improve the legal and regulatory framework and they have little experience with international law and foreign languages. A sustained effort is needed to bridge the gap between the present situation and international requirements, to solve institutional weaknesses and overlaps, enhance capacity, and improve governance.

In late 2006 GoL endorsed the SPS Action Plan, prepared as part of the DTIS process. This Plan contains 29 actions which combine policy reform, capacity building, and improvement of the investment climate, with an estimated cost of US$9.75 million. The present component will implement a portion of these actions with a cost of US$1.60 million for SPS and US170,000 for TBT (plus $0.487 million for quality and safety management in the private sector included under Component C) over a 4 year period (see Attachment 4: Coverage of Actions in Lao PDR Action Plan by the SPS/TBT Component of the TDF). It is expected that in the coming years additional resources will become available from lending and grants to implement the remaining actions.

GoL has given priority to improvement of its capacities to manage SPS in ways compatible with international principles of WTO and AFTA. Enhancing competitiveness, trade diversification and adequate health protection for people, crops and livestock requires establishing and maintaining a fully functioning SPS system, which in turn requires long-term commitment, policy and regulatory reform, TA and capacity building.

The Ministries of Agriculture and Forestry (MAF), Health (MoH) and the Science, Technology and Environment Agency (STEA) have formed an SPS Working Group led by the Director General of Agriculture for coordination of all SPS capacity-building activities supported by donors and facilitate cooperation on cross-cutting activities. Additional strengthening will be needed for it to accomplish this role successfully.

Rationale for the TBT sub component

Lao PDR has adopted principles of a market-based economy and it pursues integration in the international economy through membership of AFTA and WTO.  However, the legal and regulatory framework for TBT is still deficient. Laws for standardization and metrology are not in place yet, and a WTO compliant regulatory frame work needs to be added. Many of the existing regulations are still based on principles that were common in the state planned economy in which quality and safety requirements were insufficiently separated. Moreover, they were strongly biased to end-of-pipe controls. The principles of WTO SPS/TBT are that safety requirements have to be based on risks and science, whereas quality requirements should largely be voluntary and left to the private sector. Hundred percent controls of products have to be replaced by a system of surveillance to identify risks and inspection programs with sampling rates proportional to risks. The GMS project on trade facilitation pursues that with the aim to better comply with SPS/TBT requirements, reduce border controls, and to facilitate trade within the region. In the market economy the private sector has the responsibility for safety of products and the role of Government is to provide oversight and inspections based on risks. Some risks need to be addressed at critical points in the supply chain where they occur.

The need for support for improving the legal and regulatory framework is clear. The knowledge of relevant technical issues, international law and foreign languages is limited. Terminology on SPS/TBT in Lao language needs to be developed in order to better reflect international concepts. However, the amount and various dimensions of work involved and the support needed need further assessment.  Whereas for the SPS sector a systematic analysis of needs for change has been made resulting in the SPS Action Plan, such an assessment and plan are not available for the TBT area. Although donor and international agencies have organized many training workshops on various aspects of WTO SPS and TBT rules with the effect that awareness is created, little training has been given to larger numbers of middle ranking officers. Since the revision of the legal and regulatory framework includes new principles and many new issues, concepts and terminology there is much need of a process of on the job training throughout the various phases of regulatory reform and implementation. These phases include:

- understanding of reasons for change

- designing draft regulations

- consultation, consensus building, dissemination

- adoption, enactment, promulgation

- preparation for implementation

Although STEA has the main responsibility for TBT, several other ministries in charge of sectoral issues—MOIC, MAF—and the private sector have roles and economic interests in this area.

Component Description

The component activities are divided into five sub-components:

- institutional, legal and regulatory reform and adjustments for SPS;

- preparing risk-based policies and control measures for SPS;

- strengthening the role of the private sector in managing SPS;

- a unit for implementing the SPS sub-components and strengthening coordination with other SPS projects; and

- institutional, legal and regulatory reform and adjustments for TBT.

Table 1. Component Description

| Sub-component | Budget | Objectives |
| --- | --- | --- |
| 1. institutional, legal and regulatory reform and adjustments for SPS | 700,000 | - improve institutional alignment between institutions with SPS responsibilities - assist in drafting amended laws and regulations - amend border procedures - support consensus building, training and dissemination |
| 2. risk-based policies and measures | 400,000 | - create risk evaluation (assessment) capacity in support of SPS policy making - provide on the job training and training abroad - carry out a program of risk evaluations for support of drafting regulations and preparation of policy reform |
| 3. SPS sub-Project Implementation Unit (SPS-GSEU) | 500,000 | Under the policy guidance of the SPS Working Group and the administrative guidance of the TDF-NIU: - prepare and implement annual and quarterly plans - draft TORs, conduct procurement and contracting - organize training activities - cooperate with all SPS projects - advise the Working Group on coordination issues |
| 4. institutional, legal and regulatory reform and adjustments for TBT | 166,000 | - assess the institutional, legal and regulatory framework for TBT with regard to WTO compliance and effectiveness in enabling a market economic system and make a plan of action for drafting legal texts. |
| Total | 1,766,000 |  |

The selection of SPS projects was based on the following priority criteria:

- Contribution to preparation of WTO accession

- Need for increasing absorptive capacity and software for future investments in SPS infrastructure

- Contribution to improved human skills, governance and investment climate

- Stock taking of ongoing SPS project activities

Because of fund limitation many actions from the SPS Action Plan could not or not fully be added. For an overview see Attachment 4: Coverage of Actions in Lao PDR Action Plan by the SPS/TBT Component of the TDF. Surveillance, infrastructure, diagnostic capacity, regional cooperation, and development of university curriculum activities were therefore not included, but the selected activities will in part prepare the ground for future action in these areas.

The legislative and risk analysis activities for food safety, animal health and plant health will be carried in parallel with the aim to achieve consistency in approach where relevant and to assure that cross cutting issues are handled properly. The resources for the three areas will be allocated on the base of the amount of work to be done, while taking into consideration resources that are available from other sources. In animal health several support projects cover the area in part already.

Sub-Component 1.  Institutional, legal and regulatory reform and adjustments for SPS

An assessment will be made of weaknesses in the laws, regulations, and related border handling procedures (including permits etc.) for trade in food and agricultural products, and food safety, animal health and plant health protection. The assessment will focus on the following aspects:

- Gaps and overlap in institutional responsibilities (both as assigned in legislation and as practiced)

- Compliance with SPS agreement principles and other international obligations, such as AFTA

- Main legal and regulatory gaps and redundancies in protection of animal health, plant health and human health against pests and diseases and food-borne hazards

- Weaknesses/gaps in effective enforcement and implementation

- Needs to strengthen rule of law, governance and investment climate through an improved regulatory framework

- Cost-effectiveness of existing regulations / redundancies

The assessment will provide prioritized recommendations for:

- Alignment of responsibilities of the institutions involved in managing food safety, animal health and plant health

- Phased work plans for drafting improvements in laws, regulations and border procedures, including filling missing pieces.

After review and approval of the recommendations, assistance will be provided on:

- Alignment

- Drafting of legal texts.

Given the limited capacities in the country, prioritization of new measures will be based as much as possible on (i) mandatory international obligations, (ii) opportunities for trade, (iii) risk, severity of health hazards and (iv) related costs and benefits from intervention. Introduction of international standards in domestic markets will be selective and guided by the same principles.

On the basis of revised legal texts an assessment will be made of likely implications for demand for diagnostic work and testing in support of surveillance and inspection.

In parallel, consultations, training and consensus building activities will be conducted to build capacities and promote sustainability.

Sub-component 2. Risk-based policies and measures for SPS

This component will create capacity for risk evaluation (assessment) needed to design risk-based SPS measures, such as inspections and border controls. It will also help Government to prioritize measures based on risks, costs and benefits. In less complicated cases it can be applied for market access requests. Since risk assessment principles are the same for food safety, plant health and animal health management, and resources limited, one unit will be created to provide services to the three sectors.

The sub-component will include:

- Creation of an interdisciplinary Risk Evaluation Group (REG) staffed by four full-time Government experts with broad backgrounds in cost-benefit evaluation, food safety management, plant health management, and animal health management. Expertise in epidemiology, public administration and trade is relevant as well.

- Participatory training in the country will be conducted by an international specialist. Some projects will be carried out as part of the training. Part of the training will be open to interested staff from relevant Government agencies, the private sector, the University of Laos, and NAFRI.

- Preparation of a rolling work plan for the first and second year. Every year the two-year work plan will be updated. It will be approved by the Working Group.

- Training abroad

The work plan will consist of risk evaluation projects that contribute information to:

- Concrete activities undertaken in sub-component 1 on regulatory reform

- Policy makers for their preparation of concrete policy issues in which risks, costs and benefits play an important role.

For each risk evaluation project a small project team will be formed consisting of at least one core-team member and, where relevant, specialists from Government agencies, the private sector, NAFRI and the University. The REG will have independence from policy making units and will contribute objective information and options to decision makers. It will not be directly involved in decision making.

For the time being, the REG will be located in the Department of Agriculture, though in its work it will equally contribute to the areas of food safety, animal health and plant health. Towards the end of the project its institutional location will be reviewed.

Sub-Component 3. SPS Government Sub-Executing Unit (GSEU)

Under the National Steering Committee (Ministerial level) a SPS Sub-Steering Committee will be formed consisting at least of: MAF and MoH, and possibly including PMO (STEA), and MOIC. An SPS Working Group has been formed consisting of senior managers in these ministries with direct responsibilities in managing SPS. They will mandate day to day work to a SPS Task Force. An SPS GSEU will be formed which will also be in charge of with coordination of all SPS donor activities (fitting in structure in Figure 1 on page 6 under MAF GSEA). It will consist of:

- project director;

- procurement officer;

- finance officer;

- translator, and

- administrative assistant.

Members of the SPS Task Force (MAF-DOA, MAF-DOL&F, MOH-DOF&D) will selectively participate in parts of the work.

The TOR of the SPS-GSEU is:

Under the policy guidance of the SPS Working Group and the administrative guidance of the TDF-NIU the following tasks will be carried out

- prepare annual and quarterly plans for approval by the Working Group

- send progress reports to Working Group

- upon budget release, implement the plans

- draft TORs, conduct procurement and contracting

- organize training activities

- through the SPS Task Force, cooperate closely with all SPS projects by other donors and agencies

- advise the Working Group on SPS coordination issues

Relation between TDF-NIU and SPS-GSEU

- upon approval of work plans by Working Group, the SPS-GSEU will request budget release from the TDF-NIU

- the SPS-GSEU will send progress and financial reports to TDF-NIU

- the SPS-GSEU will follow the formats and templates for financial management, planning, reporting and monitoring provided by the TDF-NIU

The TDF-NIU will include reporting and budget requests from SPS-GSEU in its overall reporting and financial documents after marginally testing for consistency, sufficiency and compliance with administrative rules for the TDF. The responsibility for the contents of the SPS sub-project reports and proposals is with the SPS Working Group and the SPS Steering Committee; and are no double approvals on contents by the NIU.

Sub-Component 4.  Institutional, legal and regulatory reform and adjustments for TBT

An assessment will be made of weaknesses in the laws, regulations, and related border handling procedures (including permits etc.) for TBT. Special focus will be on Standardization and Metrology. The assessment will focus on the following aspects:

- Gaps and overlap in institutional responsibilities (both as assigned in legislation and as practiced)

- Compliance with TBT agreement principles and other international obligations, such as AFTA

- Main legal and regulatory gaps and redundancies in present legislation

- Weaknesses/gaps in effective enforcement and implementation

- Needs to strengthen rule of law, governance and investment climate through an improved regulatory framework

- Cost-effectiveness of existing regulations / redundancies

The assessment will provide prioritized recommendations for:

- Alignment of responsibilities of the institutions involved in managing TBT

- Phased work plans for drafting improvements in laws, regulations and border procedures, including filling missing pieces

As resources become available, the next steps can be implemented, starting with the alignment and drafting of legal texts based on the above results. Priorities would be based on (i) mandatory international obligations, (ii) opportunities for trade, (iii) commercial and health risk, and (iv) related costs and benefits from intervention. Introduction of international standards in domestic markets would be selective and guided by the same principles. In addition, an assessment could be made on the basis of revised legal texts of the likely implications for demand for diagnostic work and testing in support of surveillance and inspection. These activities should be accompanied by training and consensus building activities to build capacities and promote sustainability.

Organization

The work for the sub-component will be led by STEA, but since there are many cross cutting subjects with tasks of other ministries, and since important private sector interests can be involved, a consultative group will be established for the sub-component, led by STEA, and including public and private stakeholders, such as MOIC, MAF and private sector representatives. [Consultations on establishment of this group will take into consideration the existing groups.]

STEA will appoint a manager to lead the project implementation team for the sub-component.  The other ministries will engage in the work of activities for which they share responsibilities. Implementation of each project component and its sub-component will be under the responsibility of the GSEA based in the respective Line Ministry or Agency and coordinated thought the NIU.

Auditing and fiduciary responsibility

The SPS-GSEU will be separately audited. The fiduciary responsibility is with the implementing Ministries.

Sector-Specific Risks

| Kind of risk | severity | Risk mitigation |
| --- | --- | --- |
| Lack of coordination within and between TDF SPS sub-components and with other donors’ SPS projects leads to overlap and reduced efficiency | M | The already formed SPS Working Group is capable of securing coordination and synergies |
| Weak absorptive capacity leads to insufficient action | M/S | The strong implementation unit backed up with external capacity (TA) will manage the process of project implementation and ensure timely preparation of quarterly and annual plans and management decisions on implementation |
| Weak absorptive capacity leads to consultant-driven project | M | Emphasis on a long implementation period, ongoing consultation, training and workshops will enhance Lao ownership and capacity building. |
| Lack of knowledge and experience in Government and underestimation of technical complexity and international dimensions may lead to deficient and ineffective SPS measures | S | In each component and in the implementation unit, international TA is brought in periodically to back up capacities for planning, implementation and quality assurance. |
| Inefficiency through organizational complexity bureaucratization | M/S | Decision making on contents needs short direct lines with the Government institutions with direct responsibilities for managing food safety, animal health and plant health. |
| Vested interests in present inspection and border procedures may thwart project preparation and implementation of improved SPS measures | M | Periodic reporting and direct contact between the Working Group with the national Steering Committee and especially the SPS Sub-Steering Committee, consisting of Ministers directly responsible for SPS implementation, will enhance change. |

M = moderate; S = severe

Overall Risk: Moderate

Monitoring and evaluation framework

The activities of the component are highly diverse. The direct outputs can be measured relatively easily: number of legal texts drafted, number of workshops and trainings. But the outcomes are difficult to measure, since they partly occur beyond the lifespan of the project. Examples are enactment, promulgation and implementation of laws and regulations, increased competitiveness and increase in trade. Some outcomes are very difficult to attribute to particular factors. For example, regulation and trained staff are only part of the factors that affect competitiveness. For most of the project activities no baseline data are available to be used in later outcome evaluations.

Output indicators

- Number of legal texts drafted

- Number of new and modified regulations adopted

- Number of regulations dropped

- Number of workshops and consultative meetings conducted

- Number of persons participated

- Recorded appreciation of persons who participated*

- Number of trainings

- Number of persons trained

- Recorded appreciations of persons trained*

- Number of risk evaluation projects completed

- Number of private sector and civil society organizations strengthened

- Effectiveness*

- Number of public-private arrangements supported

- Effectiveness*

- Number of SMEs supported on food safety

- Effectiveness*

- Number of SMEs supported on sourcing from small-scale farmers

- Effectiveness*

* proxies for impact

The outcome of the project will be partly measured through recording of crude outcome indicators. The outcome measurement will be completed by a project exit survey in which for a random sample of project outputs impacts will be assessed through qualitative interviews among beneficiaries and stakeholders.

#### Component C. Export Competitiveness and Business Environment (US$1.39 million)

In its Sixth National Socio-Economic Development Plan (2006-2010), the Government of Lao PDR sets an ambitious growth target at about 7 percent per year, with the objective of graduating from Least Developed Countries by 2020.  Export is a main element driving this growth, and is targeted to grow at about 12 percent per year. This can only be achieved through raising competitiveness of its key sectors and the competitiveness will be determined by its ability to support:

- Improvements in the business environment and address cross cutting, binding constraints to growth;

- sector –specific growth, driven by local companies that are successful in raising the sophistication of their operations and strategies and increasing their competitiveness.

To understand the key constraints to improving export potential and export competitiveness of Lao PDR’s private sector, three analytical reports have been developed by the World Bank, in close cooperation with other development partners and the GOL. In December 2004, a process of consultation between the Government and the enterprise sector was initiated in Lao PDR which led to the formulation of a national export strategy for the country. This strategy is aligned with Government’s overall developmental objectives and has been integrated in the 5-year plan (2006-2010) of the Ministry of Commerce.  The Diagnostic Trade Integration Study was led by the WB and MOIC under the IF framework and identified key steps to building export competitiveness in Lao PDR. The Joint WB/ADB/CPI Investment Climate Assessment identified key investment climate constraints that exporters and other firms face, and analyzed differences between exporters and non-exporters.

Improving export competitiveness of the local producers means to adopt a three-prong strategy that will improve market access, eliminate or reduce costs of trade and transit, and improve domestic productivity by eliminating investment climate constraints. Export competitiveness therefore can be broken down to three main factors: i) domestic productivity, which determines the costs of production; ii) trade costs, which determine the cost of moving and/or exporting the good and/or service and, iii) the effective level of market access which is determined by the extent of unilateral, regional or multilateral trade reforms and the capacity to meet standards and overcome information gaps on export markets.

- With respect to market access, Lao PDR is in the process of negotiating its access to the WTO and it is currently a member of ASEAN and it is actively negotiating with various ASEAN Dialogue partners. Development partners such as, SECO, WB, Japan, EC, and others, are currently assisting the Government establish practices compatible with participation in these regional and international agreements

- With respect to reducing costs of trade and transit, several projects are in place to assist in improving trade facilitation through streamlining regulations, automation of customs, building necessary infrastructure, and increasing compatibility with ASEAN and WTO requirements. In particular, the GMS program by ADB and other partners supports cross-border infrastructure, legal framework, and single stop inspections. A WB project deals with automation of customs aiming at reducing clearance times and costs. Japan is working to improve business environment alongside the main trade routes and corridors.

- With respect to domestic productivity, the Government developed a comprehensive strategy to reduce key constraints to business, such as poor infrastructure, excessive regulations, access to finance, etc. For example, the National Assembly approved a new Enterprise Law, replacing the old Business law. This creates a level playing field for private businesses, significantly simplifies regulations and procedures to start up a business, moves from licensing to registration as the main principle, envisages a transparent “negative list” of the sectors where entry of private business is conditional, and envisages a one-stop-shop for business registration.

Recognizing the importance of enabling business environment in enhancing competitiveness of businesses in both domestic and international market place, the Government has recently issued several important pieces of legislations and regulations, including the Enterprise Law, the Law on Commercial Laws, regulations to streamline import and export procedures, and has begun process of reviewing existing legal framework for investment promotion and the existing mining law. The most recent development is the adoption of the first SME Development Strategy, which outlines specific measures for improving the business environment, including:

- Simplification of business registration procedures through effective implementation of the Enterprise Law and development of national business registry;

- Conducting licensing review process to measure impacts and identify ways to reduce the burden of regulation on businesses;

- Further simplify import export procedures through reviewing list of controlled goods subject to import and export license;

- Measures aimed at improving SMEs’ access to market information, business development services such as training, counseling, trade fairs and exhibitions will contribute to improving SMEs overall competitiveness and their ability to compete in both domestic and international markets.

Several development partners, including EC, ADB, GTZ, ILO, IFC-MPDF have already developed concrete proposals to assist the Government in implementing the strategy and majority of support will focus on address cross cutting, binding constraints in business environment. For this reason, it was decided not to include specific business environment component under the TDF.

Sectoral analysis

The Assessment of the export potential of Lao non-resource based industries conducted by UNIDO, ITC and by WB, together with the GOL under the DTIS identifies the following sub-sectors as priority industries that have export potential: Tourism, Garment industry; Handicraft; Wood processing; and Agro processing.

Tourism is a critical industry for driving economic development. The sector currently generates over $120 million in revenues, creates 18,000 direct jobs and 300,000 indirect jobs, represents over 4 percent of GDP, about 15 percent of export revenue and is projected to grow by nearly 12 percent in the coming years. In addition, capital investment in tourism projects is projected to double in the next ten years. According to assessment in the DTIS the industry has potential to triple its revenues in 5 years if major weaknesses are properly addressed.

The industry weaknesses include the lack of bilingual and multilingual staff with training in the service industry, a short high season, relative isolation, low capacity of air transport, low capacity to market internationally, very short stays by tourists as an “add-on” and others. However, most of these issues are currently being addressed by the Lao National Tourism Authority in closed collaboration with business associations (Lao Hotel and Restaurant Association and Lao Association of Travel Agents) and with strong support from donor community, including ADB, New Zealand Aid, Grand Duchy of Luxembourg, AFD, DED, SNV, GTZ and others. Additionally issues related to business environment are being addressed through the Lao Business Forum, Ecotourism Forum and dialogue between the industry associations and the Government. Therefore, at this stage tourism sector is not considered as priority sector for support under the TDF.

Garment industry in Lao PDR started in early 1990s. Today there are 59 exporting companies and 57 sub-contractors, employing more than 28,000 workers. Between 1998 and 2002 garment exports have accounted for between 30 and 40 percent of the country’s total merchandise exports. According to the Lao Textile and Garment Industry Association, three new garment factories are currently under constructions and after completion these factories are expecting to employ additional 1,600 workers. Interestingly, despite the generally anticipated loss of employment after the expiration of the MFA, the number of workers has still increase; this may be due to the imposition of Textile Safeguard Mechanism on certain categories of Chinese textile and apparel exports until December 2008 by the EU and US.

According to the supply chain study conducted under the ICA, and to other studies, the largest constraints facing the industry are ability to export, and thus availability of management staff, level of education and skill of workers, productivity, and access to raw materials.

Handicraft sector is predominantly dominated by small informal producers. According UNIDO study conducted in 2003, the sector employs 30-40,000 full time workers, of which 15-20,000 people work full time, while 100,000 work part time or as complimentary activity. Out of estimated value of $30-40 million, half was hand woven and textile.

Traditional Lao textiles have significant market potential. Hand-woven textiles in Lao PDR not only reflect the strong tradition of weaving, but are also unique among the world’s textile. High value silk products are being sold to interior designers in New York.  High value and uniquely designed wood products are being exported to the San Francisco area.  Unique, hand-made and high value cotton products using natural indigo and other dyes are being exported from Savannakhet to Japan. However, exports of handicrafts are limited and dominated by a few companies.  Key constraints facing the sector include limited interest of international buyers in Lao handicraft, lack of market information, poor design and marketing skills, high transportation costs and insufficient volume of raw material.

Wood processing industry accounts for 32% of the gross output of the manufacturing sector, 35% of exports of the country’s manufactured goods and employs 22,000 workforce. The challenge to the Government is how to promote the production and exports of secondary wood products in parallel with pursuing other objectives related to forestry such as sustainable management of forests, ensuring that benefits from the forests accrue to the rural poor, and biodiversity conservation. This broad perspective is maintained in the Government’ forestry strategy and other relevant policies.  One of the fundamental problems is that existing wood processing industry itself has very little interest to enter into secondary wood processing, as most of enterprises are directly or indirectly linked to secondary processing enterprises in neighboring countries. Another issue is the uncertainty of wood quota allocation, which discourages investments in secondary wood processing facilities. Another major problem confronting the existing wood processing industry is its weaknesses in terms of management, marketing, technology, design capacity and skills levels of the labor to restructure from primary to secondary wood processing.

Agro businesses or food processing industry. Annual exports of processed food amount to about $20 million, whereof 75% consists of primary processed coffee. In addition, there are significant unrecorded trade in both directions, primarily with neighboring Thailand and Vietnam.

Key constraints facing the sector include high cost of production and distribution, weak extension services, poor availability dissemination of market information, lack of technical know how, lack of institutional support and research on modern processing and packaging techniques and  others.

Support measures to improve hygiene, food safety and quality standards for processed food will be implemented under the SPS component of the TDF.

Component description

The component will finance technical assistance, training, goods and office refurbishing through three subcomponents:

Sub-Component  1: Feasibility Studies

Conduct feasibility studies for supporting skills development facility for the garment industry, handicraft sector, linking handicraft producers with international markets through promoting e-commerce, and develop an action plan to promote the production and exports of secondary wood products in parallel with pursuing the objective of sustainable management of forests.

Sub-Component 2: Project implementation.

Depending on the above findings and based on effectiveness and efficiency analyses of proposed actions, sector-related weaknesses will be addressed through identified activities. [description of activities to be completed]

Sub-Component 3. Strengthening the role of the private sector in managing SPS

This sub-component will focus on collective and individual private sector capacities and on the interaction between the public and private sectors. It includes items for promoting competitiveness and business environment of Agribusiness. The following activities will be promoted:

- Fostering and strengthening private sector associations that have roles to play in aspects of SPS management, such as producers groups, processors, trade and export associations, etc. If possible the establishment of a consumer organization will be encouraged. For each of the three sectors (Food Safety, Animal Health and Plant Health), a consultative and advisory body (Council) will be established, consisting of private sector participants, independent experts and government representatives. The Councils will meet regularly twice a year and other times as appropriate.

- Mandating and supporting private sector entities, under proper regulation and supervision from Government, to assume active responsibility in the implementation of aspects of SPS management. A good example is the wood industry that takes care of treatment of wood under ISPM 15. The project will actively explore other options, such as food safety associations that provide services to members, exporters organizations that carry out the work for certification, applied research, testing services etc.

- Introduction and improvement of quality and safety management systems, such as Good Agricultural Practice among farmers, Good Manufacturing Practices among processors, training in hygiene and basic HACCP principles in SMEs. Experiences by the NZAID/FAO food safety project with training of trainers in good hygiene practices and GMP in food handling SMEs will be used to design interventions. Priority will be given to enterprises that are exporting and operate in the tourist industry.

- Enterprises that buy produce from small-scale farms and make efforts to upgrade quality and safety of their products for better market access can receive time-bound support for (i) training of their own staff that assist farmers; and (ii) for training activities provided to small farmers and farmers groups.

#### Component D: Capacity Building, Trade Policy, Trade Agreements, and Global Opportunities

As outlined in the Diagnostic Trade Integration Study (DTIS), enhancing capacity of trade stakeholders in Lao PDR is critical to improve the country’s trade performance. Capacity development is a necessarily endogenous process which has to be led from within Lao PDR, with development partners playing a supporting role. Government's commitment and leadership are necessary conditions for improving institutional outputs. The capacity development component will be designed to leave sufficient flexibility to adapt to changed circumstances in order to improve and strengthen GoL ownership. The goals of the capacity development program will be identified from the outset and sufficient feed-back mechanisms will be provided to ensure that the support program will answer to current capacity needs during the TDF implementation (a “strategic incrementalism” approach). A central role will be played by the National Implementation Unit which will have to draft annual work plans for capacity development.

In Lao PDR, capacity development in trade related matters is perceived as a high priority by all stakeholders. It is also widely perceived that past support in this area achieved mixed results largely because of the following reasons: a) lack of comprehensive approach to capacity development largely due to fragmentation of donors’ short term interventions; b) focus on officials in the Capital Vientiane to the detriment of officials employed in provincial offices; c) excessive use of short-term external expertise in a non-sustainable fashion; d) poor monitoring and evaluation of capacity development activities; e) insufficient involvement of beneficiaries during planning and implementation.

A number of shortcomings of past interventions is expected to be addressed under the newly established governance structure to implement the IF Action Matrix. Moreover, in order to increase aid effectiveness, capacity development under the TDF will be institutionalized by anchoring any intervention in this area to existing institutions (ERIT, NERI, NOSPE, University, etc.). Consistently with the “OECD/DAC Guidelines for Strengthening Trade Capacity for Development”, in the initial phase a long-term plan to strengthen the internal Lao PDR’s institutional capacity in trade will be developed with the assistance of a short term external expert. Use of home grown capacity will be promoted and international/regional experts will be used only when local capacity is scarce. These experts’ inputs will be embedded in an institutional framework which will ensure future sustainability and ownership.

This component will address the needs of four categories of stakeholders:

- Government Officers dealing with trade matters (this includes officers from MOIC, but also officers from other ministries and agencies dealing with trade-related issues, i.e. Ministry of Agriculture, Ministry of Finance, Ministry of Education, Ministry of Health, STEA, etc.);

- Training and research institutions and agencies (ERIT, NERI, NOSPE, National University);

- Private Sector Representatives (LNCC and other sector business organizations).

Description of Component

A preliminary assessment of this component has identified the following needs in the sector. However, the prioritization of these activities within the overall framework of the TDF will take place during the initial stages of implementation. Preliminary analysis points out at the following sub-components:

- Technical Capacity Development for Trade and WTO Compliance and Implementation. Regional/international Short-Term Technical Assistance will support the GOL in their priority areas related to the ongoing negotiations at bilateral, regional and multilateral level and in particular with respect to the legal obligations being taken by the GOL. This subcomponent will be designed in such a way as to ensure that the knowledge transfer is embedded in local institutions. The National Implementation Unit will prepare an annual plan for assistance based on the needs of various line ministries

- Upgrading Government Officers' Trade Knowledge and Management Skills. The content of this sub-component will be defined in the capacity development plan. It will focus curriculum design and on Training of Trainers with the aim of developing capacity of local institutions (NERI, ERIT, NOSPE, etc.). It will include support to enhance Human Resource Management skills with the aim of improving the government's capacity to select trainees and to match their needs to training on-offer, including by other donors, and to monitor and evaluate training results. Basic training (i.e. English language) and equipment is also included. [The possibility to build on and expand the ongoing APEC project with NERI will be considered, with additional sectoral courses developed and delivered at central level and the expansion of introductory trade courses also at provincial level.]

- Support to Academic and Research Institutions. Capacity of local institutions in trade-related research to be used by policy-makers will be enhanced by funding research activities and promoting the development of research networks. A demand-driven approach will be adopted: the GoL will identify a list of research topics. Research grants will be awarded on a competitive basis. A mentoring program will assist researchers to develop their methodological and technical capacity. The mentoring program will be developed in partnership with local, regional and international research institutes.

- Establish a Course in International Trade and Competitiveness. The Department of Economics of Lao University will be supported with the provision of Technical Assistance to design the course curricula and to develop a flexible and modular format that will be used to embed academic assistance offered by different sources. Networking with regional/international academic institutes will be promoted. Courses will be open to both private and public sector. The course will be subsidized for the initial period of three years with the aim of achieving sustainability from the fourth year. For the first three years, the participation of a selected number of government officers per year will also be subsidized.

#### Component E. Strengthening the National Implementation Unit (US$750,000)

The National Implementation Unit responsible for coordinating and facilitating implementation, result verification and quality control. The NIU will provide the MOIC with advice on the direction and implementation of the TDF and signal any problems and implementation bottleneck. The NIU will work in close collaboration with the GSEA and assist the GSEA in the project preparation phase. The actual project implementation will be carried out by the respective GSEA. They will ensure uniformity of procedures and compliance with appropriate donor regulations by preparing and providing guidelines on project management, planning, preparation of terms of reference and bidding documents, progress reporting, and preparing of project proposals and Project Procedure Manual for each different project being implemented by NIFGS. The NIU will work closely with the TDF Facilitation Team at all stages of the TDF implementation.   The day-to day implementation of the various sub-components will carried out by the respective GSEA under the overall coordination of the NIU.

The NIU centralizes all procurement, accounting, financial management and archiving for all projects under NIFGS, working in close collaboration with the GSEA. Initially, strengthening will consist of:

- The Procurement staff will conduct the procurement process and work with the GSEA and TDF FT, as needed for the preparation of the terms of reference and goods specification, and chair the evaluation panel for each acquisition, ensuring the full transparency and auditability of the procurement process. They will require initial training and six months of external assistance and be supported by national procurement staff and as appropriate by a contract specialist and legal assistance.

- The Administration staff will organize the flow of documents and internal control and direct the writing of each Project Proposals and Procedure Manual. They will be responsible for all administrative matters including travel arrangements, workshop requirements, conference rooms, logistics, for those activities which fall directly under their responsibility.  They will be assisted by an O&M expert and be supported by other national staff.

- The Accounting staff will keep track of all project budgets and accounts, separately by project and in aggregate (with NIU budget and expenditures) for semi-yearly reporting and yearly auditing. The NIU will work with the GSEA  to obtain and consolidate all budget and accounts, using an integrated software to be set up under the TDF. It will be the responsibility of each GSEA to provide timely reports and information to the NIU. They will initially require the development of an accounting system which in addition to complying with GAAP and national laws is also able to keep track of the project budget and expenditures at the level of contract or expenditure within each activity (e.g., aggregates to the levels of activity, subcomponent, component, and project). Accounting is responsible for disbursements according to contract, and will need initial training on donor guidelines in this respect.

- The Archiving staff will operate the document reception desk, and keep all project documentation in hard and soft copy and made available through a local area network. They will require an automated recording and retrieval system and scanning facilities for all paper documentation, as well as a room with archiving material. Initially, an O&M specialist and an IT specialist will be required to set up the system.

- Set up a Monitoring and Evaluation framework, to allow th e NIU to carryout regular project monitoring and reporting of project performance against set targets and indicators. This will be in parallel to external evaluations carried out regularly throughout the project life cycle.

Please note that these are the  indicative tasks and responsibilities for the NIU, for more details please refer to the TORs in Annex 8.

## Attachment 3: DRAFT Detailed Activity Costs

## Attachment 4: Coverage of Actions in Lao PDR Action Plan by the SPS/TBT Component of the TDF

|  | Institutional, legal, regulatory reform and adjustments | Preparing risk-based policies and control measures | strengthening the role of the private sector in managing SPS; | Coordination and implementation unit |
| --- | --- | --- | --- | --- |
| I. Recommended actions for public sector |  |  |  |  |
| Coordination team and preliminary studies |  |  |  |  |
| 1. Establish coordination team International SPS coordinator: |  |  |  | proportion |
| 2. Conduct studies on the following: a. SPS req’ts of potential markets for NTAE b. Consistency of SPS req’ts of both Lao PDR and trading partners with WTO&AFTA c. Possibility of local certification |  |  |  |  |
| Legislative and regulatory issues |  |  |  |  |
| 3. Review legislations on food safety, plant and animal health on compliance with SPS agreement and recommend ways for effective enforcement and implementation | fully |  |  |  |
| 4. Establish legislative task force and work plans for institutional alignment and for drafting of legislative amendments | fully |  |  |  |
| 5. Draft proposed amendments on: 5a. effectiveness of enforcement 5b. import restrictions to protect against human health hazards, pests and diseases 5c. monitoring and enforcement of the import, production, sale and use of agrochemicals 5d. inclusion of emergency powers for plant/animal authorities 5e. better governance on border procedures | fully |  |  |  |
| 6. Review and amend regulations/procedures on food safety, plant/animal health on: 6a. better guidelines for inspection and certification 6b. unnecessary inspection and permit requirements 6c. more effective lines of communication and better incentives for disease reporting (especially in cases of outbreaks) 6d. possible simplification of border procedures | fully |  |  |  |
| Institutional issues |  |  |  |  |
| 7. Determine implications of proposed amendments to downstream responsibilities and inspection and testing capacity needs of various agencies | largely |  |  |  |
| 8. Prepare national guidelines outlining responsibilities of Ministries in cases of outbreaks Establish inter-Ministry emergency task force to deal with pest/disease outbreaks |  |  |  |  |
| 9. Establish small core group of risk assessors under University/research institute with support specialists from MAF and MOH |  | largely |  |  |
| 10. Prepare individual actions plans (food safety, plant and animal health) The preparation of the individual work plans should be done in close coordination with or alongside the preparation of lab work plans (Action #13). Moreover, it is recommended that these work plans include the identification of human resource requirement to be able to achieve goals (Action #17). | proportion | proportion |  |  |

| 11.Communicate new legislations, regulations, procedures and emergency guidelines to provincial and district offices 3 SPS workshops for provincial and district staff/inspectors with 40 participants each for food safety, plant health and animal health to discuss: a. SPS in general b. (Proposed) Changes in legislations (Action #5 above) c. Changes in procedures and regulations (Action #6 above) d. Emergency guidelines (Action #8 above) | largely |  |  |  |
| --- | --- | --- | --- | --- |
| Surveillance |  |  |  |  |
| 12. Create databases through active surveillance for the following: 12a. Human health hazards caused by food- and water-borne diseases 12b. Plant pests/disease specimens 12c. Animal disease prevalence 12d. Production, sale and use of agrochemicals & veterinary materials |  |  |  |  |
| Diagnostic capacity |  |  |  |  |
| Note: The following actions should be done in close coordination to assure consistency with planned capacity and needed equipment. 13. Develop lab work plans for food safety, animal and plant health (Refer to Action #10) Work includes identification of appropriate equipment for labs (Action #16) 14. Assess/design cost-effective regular calibration of equipment 15. Acquire equipment for rapid detection and screening for provinces/border posts |  |  |  |  |
| 16. Upgrade lab capacities in accordance with recommendations from Action #13 |  |  |  |  |
| Building human skills |  |  |  |  |
| 17. Develop an SPS skills program that will identify human resource requirements to achieve the goals identified in the individual work plans (Action #10) and laboratory work plans (Action #13). |  |  |  |  |
| 18. Provide training on risk assessment of food safety, animal and plant health Two kinds of training: a. Overseas training for core group of risk assessors (Action #9) b. Local basic risk assessment training for staff of MAF, MOH and STEA |  | yes |  |  |
| 19. Provide training on economic analysis, cost-benefit analysis for senior staff of MAF and MOH (overseas) |  | yes |  |  |
| 20. Training at all levels for all other SPS capacities Two types of training: a. Overseas training for staff of MAF and MOH to be future trainers b. Local training for all other staff by trainers | proportion | proportion | proportion | proportion |
| Regional cooperation |  |  |  |  |
| 21. Conduct periodical bilateral consultations with China, Vietnam and Thailand Consultations are assumed to be held twice a year for four years for each of the three countries. Trade panel composed of 5 Government staff. International consultant to assist in setting up trade panel and to advise on agenda for negotiations and trade and SPS issues |  |  |  |  |

| Public information and education |  |  |  |  |
| --- | --- | --- | --- | --- |
| 22. Design and initiate educational campaigns International consultant to advice on relevant materials and design of campaign Workshops to be held for producers, food processors, consumer groups, and food retailers Use of local media (TV, radio and print) to disseminate general information on hygiene or info on specific health concerns, such as fish-borne parasites 23. Gather, translate and disseminate relevant materials to stakeholders | partly proportion | proportion | proportion | proportion |
| II. Recommended actions for University |  |  |  |  |
| 24. Develop and implement appropriate University curricula on animal and plant health and food safety Implementation of new curricula would require both additional faculty and infrastructure to house labs and equipment |  |  |  |  |
| 25. Provide higher education and specialized studies for MAF and MOH staff Scholarships for senior staff |  |  |  |  |
| III. Recommended actions for private sector |  |  |  |  |
| 26. Promote outgrower schemes via pilot projects Workshop for producers, traders, processors and retailers |  |  | partly |  |
| 27. Promote business and exporter associations Workshop for agribusiness groups and exporters associations, with support from MOIC |  |  | largely |  |
| 28. Provide mandate for coffee exporter association on quality control, pest management and issuance of phyto certificates. Workshop for coffee producers and exporters, with support from plant authorities |  |  | optional, not earmarked |  |
| 29. Promote HACCP to processed food plants Workshop for food processors, with support from MOH |  |  | no partly |  |

Source: Actions as presented in Appendix Table C.1 of SPS Action Plan

## Attachment 5:  DTIS Action Matrix

An Action Matrix of Projects and Technical Assistance to Promote Export Competitiveness in Lao

Updated  on  11 September 2006

|  | Objectives | Priority/ Timing |  | Responsibility in Government |  | Costing |  | Related Trade Assistance Programs | Type of Intervention | Econ’ impact |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 0: Putting in Place the IF implementation and Monitoring Structure |  |  |  |  |  |  |  |  |  |  |
|  | Rationalize IF supervisory committees, establish national IF management Unit | High priority with actions already having begun and will be ongoing |  | MOIC/IF Steering Committee |  | Medium - to date support provided by IF Trust Fund (IFTF). Estimated cost of establishing a IF Implementation Unit in the Lao PDR Government is US$ 1.5 million over 5 years |  |  | Governance | NA |
| Component 1: Export Competitiveness |  |  |  |  |  |  |  |  |  |  |
| Project 1: Support agricultural competitiveness | Encourage the production of organic agricultural products for export; improve quality standards of traditional agricultural products; improve productivity of traditional agricultural products; develop agro-processing industry for export; improve distribution channel infrastructure; improve productivity; training in modern agriculture techniques for farmers; encourage the production of medicinal plants and spices for export. | High priority with action to be undertaken from the first year |  | MAF, LNCCI, NUOL, MOIC(LTPC &DOI) |  | High - in particular significant investment is required to improve productivity and develop processing industry. Estimated costs for project to improve just the production and supply chain of organic agriculture are US$1.7-2 million over 3 years. Estimated costs for project to build-up the medicinal plants and spices sector are US$1.5-1.75 million over 3 years. | EC's Asia Invest Open Resource for Commerce in Horticulture Aided by Species Identification Systems (2006-09, €0.3m) & Developing Food and Agribusiness Training in the Mekong Region (completed 2006, US$0.4 shared with 5 countries); ADB's Marketing Support for the Organic Produce of Ethnic Minorities (2004-07, US$0.6m); Switzerland's Promotion of Organic Farming and Marketing (completed 2006, US$0.3m); FAO's Improvement of Coffee Industry Project (completed 2005, US$0.35) |  | Technical assistance; regulatory; human resource capacity building and infrastructure development; encouraging investment | Large |
| Project 2: Support light manufacturing competitiveness | Garment sector: Encourage local producers to gradually shift from working on CMT to FOB basis; improve productivity of garment sector; promote Lao garment products; improve quality of Lao garment products; develop trade information and linkages with buyers on garment. | High priority with preferably for action to begin from the first year |  | LNCCI, ALGI, MOIC (LTPC & DIE) |  | Medium - Estimated costs for a project to strengthen the export capacity and competitiveness of the garment sector are US$1.5-1.7 million. | General Export Competitiveness Support: Switzerland/ITC's Support to Trade Promotion and Export Development (2004-07, US$1m); Switzerland's Promotion of Cleaner Industrial Production (2004-08, US$0.95); Specific to Garment Sector: UNDP's Textile and Clothing Project (2006-07, 0.09m) |  | Technical assistance; human and infrastructure capacity building; international trade promotion; and information distribution | Medium-Large |
|  | Silk products: Improve domestic supply capacity in Lao native silk; improve Lao silk product designs; develop new silk products; develop standard for Lao silk handicraft; improved training for silk production techniques; develop trade information on silk sector. | Medium priority with action to be undertaken as soon as possible |  | MAF, LNCCI, MOIC(LTPC&DIE) |  | Medium - Estimated costs for a project to improve capacity of producers and exporters of silk products are US$1.6-1.85 million | US's Economic Acceleration Program for the Silk Sector (completed 2006, US$0.5m) |  | Technical assistance; human resource capacity building and infrastructure development; and information distribution | Medium |
|  | Other handicraft products: Improve design capabilities; study and improve distribution channels; trade information and linkages with buyers. | Relatively low priority |  | MOIC (LTPC), LNCCI |  | Small financial outlay |  |  | Technical assistance | Small |
|  | Wood processing sector: Promote and upgrade Lao wood products to the international standards and recognition; improve productivity of the wood sector; ensure sustainability of raw materials to support the industry. | Medium priority with action to be undertaken in the medium term |  | MAF, MOIC(DIE), LNCCI |  | Medium-High - Estimated costs for a project to improve quality and sustainability of wood products sector would be around US$2 million over 3 years | EC's Asia Invest Fund Upgrading the Wood-Processing Industry for the European Market (2005-07, €0.2m); FAO's Marketing System Development for Non-Wood Forest Products (completed 2006, US$0.37) |  | Technical assistance; regulatory assistance | Medium |
| Project 3: Support tourism | Develop craft villages such as local artisans and craftsman (textiles, jewellery, wood based, etc); develop services capacity and competency of Lao tourism sector; strengthen the institutional framework; encourage tourism linkages to other sectors of the economy; diversify services capacity within the tourism sector; promote Lao tourism to make it internationally recognized. | High priority requiring ongoing support. |  | LNTA, LNCCI, MOIC (LPTC), MFA |  | Medium- Estimated costs of a tourism training center with involvement of the private sector of US$ 1,000,000 for a period of 4 years; Medium- estimated costs for establishment of model craft villages in 10 major tourism destinations of U$ 1,000,000 for a period of 4 years | ADB's Mekong Tourism Development Project (2002-07, 10.9m shared with Cambodia and Vietnam); EC's Asia Invest Fund - Marketing Responsible Tourism in Lao (2006-09, €0.3m); New Zealand's Nam Ha Ecotourism Project (2004-07, US$0.34); German Human Resource Development for Market Economy Programme (2004-07 US$5.5 m; Planned: Japan's Tourism Development in the East-West Corridor (2007-10, US$2m); planned: German Vocational Education Programme (2007-10 € 5 m) |  | Human resource capacity building; trade promotion; encouraging private investment | Medium |
|  | Develop local agriculture and healthy food products (vegetable, meat, local food cottage, etc) in tourism destination through the development capacity and competency of small and medium sized farming and agro-processing. | High priority required on-going support |  | LNTA LNCCI-LHRA-LHA MAF LTPC |  | Medium high -estimated cost for establishment of model village cottage food industry, animal farms, modern slaughter house in 10 major tourism destination of US$ 2,000,000 for a period of 4 years |  |  |  |  |
| Project 4: Micro, small and medium enterprise project for export development | Build an integrated market access and trade facilitation infrastructure; support entrepreneurship development; develop and strengthen the capacity of local intermediaries to deliver financial and non-financial services to MSMEs; provide an enabling environment (access to finance, trade promotion, and trade facilitation infrastructure) to boost increased investment. | High priority with projects to begin from the first year |  | MOIC (DOI, DIE, LTPC),BOL, LNCCI |  | Medium - Estimated costs of a trade information and export training program for the business sector would be US$800,00-950,000 over two years. | UNINDO & India's South-South Response to Poverty (completed 2006, US$0.15 shared with 5 countries); UNESCAP & Japan's Capacity Development of SMEs (completed 2006, US0.59m); ADB's Small and Medium Enterprise Project (completed 2005, US$0.79m); EC's SME Development Programme (2006-10, € 3 m) |  | Human resource capacity building & infrastructure development; information dissemination; encouraging investment | Medium- High |
| Project 5: Regional development of export potential | Construct and rehabilitate critical infrastructure essential for sustained regional economic activity in the tourism, manufacturing, agribusiness and mining sectors; | Medium priority with a long term focus |  | Provincial governments |  | High - A high level of capital investment required to address infrastructure issues which would not to be funded directly through IF. Other funding sources required, possibly including Aid for Trade. IF process can assist in policy development and capacity building (cost would be low to medium) |  |  | Regulatory assistance; technical assistance; human resource capacity building; | Medium-Large |
|  | Put in place appropriate incentive measures at the regional level to achieve rapid growth; |  |  |  |  |  |  |  |  |  |
|  | Develop the instruments to ensure equitable, sustainable growth. |  |  |  |  |  |  |  |  |  |
|  | Strengthen the capacity of local authorities to formulate, prepare, implement, and manage medium- and long-term integrated regional development projects. |  |  |  |  |  |  |  |  |  |
| Component 2: Trade Facilitation |  |  |  |  |  |  |  |  |  |  |
| Project 1: Customs modernization | Develop regulations to implement the new Customs law |  | High priority with actions to begin as soon as possible |  | MOF and MOIC | Medium-High - Funds needed for a broad range of activities mainly based on training but also including investments in improved customs processing systems. |  | IMF's Technical Assistance on Customs Operations (204-07, US$0.5m); Japanese Customs Technical Cooperation Program (completed 2005, US$0.17); ADB’s technical assistance (2006-2008) to support trade facilitation and capacity building in the Greater Mekong Subregion (Part I to support trade facilitation, including gap analysis for customs procedures) at US$890,000. ADB’s technical assistance (2006-2007) on implementing the Cross Border Transport Agreement in GMS (Appendix 4 on Frontier Crossing Formalities - single window/single stop inspection at selected border crossings, targeting among others, customs agencies) at US$860,000. | Legislative/ regulatory reform; human capacity building and infrastructure development; customs infrastructure development | Medium |
|  | Reform the national customs administration |  |  |  |  |  |  |  |  |  |
|  | Strengthen capacity building to properly administer the customs valuation provisions of the law |  |  |  |  |  |  |  |  |  |
|  | Simplify/modernize border clearance procedures (including external expert advice to prepare a long term customs modernization project) |  |  |  |  |  |  |  |  |  |
|  | Automation and data processing systems (e.g. automated customs clearance system) |  |  |  |  |  |  |  |  |  |
|  | Strengthen and expand the anti-smuggling program |  |  |  |  |  |  |  |  |  |
|  | Licensing of Customs Brokers |  |  |  |  |  |  |  |  |  |
|  | Develop a customs training program, e.g. seminar/workshop as well as medium and long term program. |  |  |  |  |  |  |  |  |  |
| Project 2: Trade facilitation | Pilot Gold Card Program (to expedite clearance procedures for approved traders) |  | High priority/2nd year |  | MOF, MOIC (DIE), MTCPC, Border agencies, National quarantine and standards agencies, National Transport Facilitation Committee | Medium-High - Funds needed for investments in improved technology and processes. Also, potentially high capital investment needed to build a container logistics centre |  | ADB's Trade Facilitation in Greater Mekong (2006-08, US$1.49m shared regionally); UNESCAP/Netherlands' Institutional Capacity Building for Landlocked Countries (completed 2006, US$0.4m); ADB’s regional technical assistance (2006-2008) to support trade facilitation and capacity building; ADB’s regional technical assistance (2006-2007) on implementing the Cross Border Transport Agreement. | Infrastructure development | Medium-High |
|  | International container logistics center in Vientiane |  |  |  |  |  |  |  |  |  |
|  | Licensing of customs agents |  |  |  |  |  |  |  |  |  |
|  | Improve the single window operations in various provinces |  |  |  |  |  |  |  |  |  |
|  | Increase transparency |  |  |  |  |  |  |  |  |  |
|  | Institutional strengthening of trade facilitation focal point, to coordinate trade facilitation activities |  |  |  |  |  |  |  |  |  |
|  | Needs and gap assessment on customs procedures (as in Project 1); trade logistics development (including trade logistics center and service sectors development, etc.); standards/technical regulations development; and improved business mobility). |  |  |  |  |  |  |  |  |  |
|  | Facilitate cross border movements of goods, people, and vehicles (single window, single stop inspection at GMS selected land border crossings, involving Lao PDR, GMS transit traffic regime, vehicle standards, exchange of traffic rights, etc.) |  |  |  |  |  |  |  |  |  |
|  | Simplify or eliminate export licensing and export-import indicative plan. |  |  |  |  |  |  |  |  |  |
| Component 3: Business Environment |  |  |  |  |  |  |  |  |  |  |
| Project 3: SPS | Institutional and legislative framework (high priority) |  | High priority with projects for long-term improvement of capacity to begin as soon as possible |  | STEA, MAF; MOH | High - Estimated costs of an export quality management project would be US$1.4-1.6 million, but investments in SPS-related laboratory equipment could increase this amount significantly |  | Norway's Market Access & Trade Facilitation Project (2006-09, US1.7m shared with Cambodia & Vietnam); Australia's SPS Capacity Building Project (ongoing, US$4m shared between 8 countries) & ASEAN Development Cooperation (2002-08, A$45m); EC's Asia Invest Capacity Building of Geographical Indication (2006-09, €0.3m shared with China and Cambodia), & EC's Project on Standards, Quality & Conformity (ongoing, €0.5m) & Intellectual Property Rights Cooperation (completed 2006, €0.5m); FAO's Improving Food Safety and its Management (2005-08, US$0.85 shared by 3 countries); ADB's Integrating the Poor Through Standard Setting (completed 2005, US$0.7m) | Technical assistance; human capacity building and infrastructure development; supply of technology | Medium-High |
|  | Diagnostic capacity (high priority) |  |  |  |  |  |  |  |  |  |
|  | Market opportunities and trade requirements |  |  |  |  |  |  |  |  |  |
|  | Surveillance |  |  |  |  |  |  |  |  |  |
|  | Emergency response |  |  |  |  |  |  |  |  |  |
|  | Risk assessment and economic analysis |  |  |  |  |  |  |  |  |  |
|  | Inspection and certification |  |  |  |  |  |  |  |  |  |
|  | Building human skills |  |  |  |  |  |  |  |  |  |
|  | Information and education |  |  |  |  |  |  |  |  |  |
|  | Private sector development |  |  |  |  |  |  |  |  |  |
|  | Regional cooperation |  |  |  |  |  |  |  |  |  |
| Project 1: Development of industrial strategy to facilitate business operations | Develop an industrial strategy that: sets a broad framework for promoting and developing Lao’ industrial base; identifies priority areas; and ensures a consistent and stable policy environment. |  | Medium priority with actions to take place in the medium term |  | MOIC (DOI) | Small-medium |  | General Business Environment Support: IFC's Mekong Project Facility (2003-07, US$2.85m); ADB's Private Sector Development Program (2005-10, US$0.7m plus US$10m loan); UNIDO's Integrated Programme (2004-08, US$6.3m); Japan's Macro Policy Support for Development (completed 2005, US$1.2m); Germany's Human Resource Development for Market Economy Program (2004-07, US$5.5m) | Regulatory and possibly legislative | Medium |
| Project 2: Investment promotion | Review and simplify business regulations, e.g. foreign investment start-up and registration procedure reform; create investment guidelines (sector by sector); set up a public-private stakeholder platform to discuss the reforms on a regular basis |  | High priority with actions already underway |  | CPI | Small-medium |  | Japan's Expert on Promotion of Investment for Lao Government (2007-09, US0.3m); US's South East Asia Commercial Law (2005-07, US$0.24m shared regionally) & Competition Law to ASEAN (2005-08, US$0.75 shared regionally); ADB's Research on Improving Climate for Investment & Productivity (completed 2006, US$0.15) | Regulatory assistance and possibly legislative | Medium-High |
|  | Review the legal framework for investment, including contract enforcement and dispute resolution |  |  |  |  |  |  |  |  |  |
|  | Implement a one stop shop for investment, including training of officials |  |  |  |  |  |  |  |  |  |
| Project 3: Banking system | Through banking staff training, a rationalisation of regulations and expanded linkages with the private sector, improve capacity of Lao banking sector to support export performance through the provision of trade finance |  | Medium priority with a long term focus |  | BOL, MOF | Medium - Estimated costs for a training-based project to improve trade financing would be US$1.2-1.4 million. |  | ADB's Strengthening Governance for Bank Sector Reform (completed 2006, US4m) & Bank Sector Reform Program (completed 2006, US$15m); EC's Technical Assistance Programme for Transition to a Market Economy - Bank Training Project (completed 2005) | Technical assistance and human capacity building; regulatory | Medium-High |
| Component 4: Trade Policy, Trade Agreements, and Global Opportunities |  |  |  |  |  |  |  |  |  |  |
| Project 1: Capacity building for international trade policy and negotiations | Improve capacity building of MOC and other ministries with trade-related functions to take considered and well-coordinated decisions on all aspects of international trade policy, regional and multilateral trade negotiations, and trade relations. | High priority with programs to begin in the first year |  | MOIC |  | Small-Medium - Estimated costs of a general training and research project to improve business competency among business and government involved in exports would be US$900,000 - 1.1 million over two years. Additional, more targeted training would also be required in relation to trade agreements and negotiations. |  | UNCTAD/France's Train for Trade (2003-07, US$2.3m); Australia's Trade Analysis & Reform Project (2005-08, US$5m shared 4 countries); EC's Asia Trust Building Capacity of the Economic Research Institute (2006-07, US$0.25m); EC's Multilateral Trade Assistance Project (completed 2006, €1m); UNDP's Promoting Private Sector Development Project (2006-09, US$2.33m) and National Human Development Report (2004-07, US$0.8m); WTO/UNESCAP's Technical Assistance (ongoing, US$1.7m shared globally); Canada's Asia-Pacific Training Network on Trade (2004-07, US$0.7m shared regionally) & APEC Eco Integration (2004-09, US$7.2m shared 6 countries); US's ASEAN Technical Assistance Facility (2004-07, US$7.33 shared regionally) and Strengthening Market Analysis Capacity (2005-07, US$0.24m shared regionally) | Technical assistance and human capacity building | High |
|  | Establish clear division of roles and responsibilities between MOC and other ministries, including inter-ministerial coordination and public-private sector dialogue in support of the WTO accession process |  |  |  |  |  |  |  |  |  |
|  | Increase MOC’s capacity to analyze trade issues, impact of trade policies, and to lead trade negotiations. Support analytical work for trade policy formulation and implementation. |  |  |  |  |  |  |  |  |  |
|  | Trade Policy Advisory |  |  |  |  |  |  |  |  |  |
|  | Promote an effective trade information center, improve collection of trade statistics |  |  |  |  |  |  |  |  |  |
|  | Increase capacity to efficiently administer: Rules of Origin |  |  |  |  |  |  |  |  |  |
|  | To build in-house capacity on research and facilities for trade sector |  |  |  |  |  |  |  |  |  |
|  | Trade Database |  |  |  |  |  |  |  |  |  |
|  | Increase transparency |  |  |  |  |  |  |  |  |  |
| Project 2: Technical assistance and capacity building for the formulation and implementation of trade negotiation strategies | WTO accession: assistance with legislative review and required documentation as well as legislative reform needed for WTO compliance; negotiation strategy and analytical support for accession, including in non-agricultural goods, agriculture, services, etc.; institutional and human capacity building for trade negotiations and policy formulation; consultations and information on WTO accession for line Ministries and stakeholders; training in Geneva to prepare Working Party meetings; |  |  |  |  |  |  | UNDP/ AUSAID's Integration Into the Trading System (completed 2006, US$1.68m) |  |  |
|  | Regional agreements: ASEAN (AFTA, AFAS), AFTA+China, etc. |  |  |  |  |  |  |  |  |  |
| Component 5: Trade Opportunities for the Poor |  |  |  |  |  |  |  |  |  |  |
| Project 1: Promotion of traditional handicraft and textile industry at village level | Build business linkages with Fair Trade Organizations in North America and Japan | Medium priority |  | MOIC, LNCCI, STEA |  | Medium |  | UNESCAP/UNDP's Development of E-business Support Services in the Greater Mekong (completed 2006, US$0.2m) | Technical assistance and human capacity building | Small |
|  | Engage in e-commerce |  |  |  |  |  |  |  |  |  |
|  | Provide technical training to artisans |  |  |  |  |  |  |  |  |  |
|  | Mirco-credits, improved access to distribution channels, information and linkages to buyers |  |  |  |  |  |  |  |  |  |
| Project 2: Roads linking villages to markets | Improve reach and quality of road network to better connect towns and villages to markets and export opportunities | High priority with actions to be undertaken as soon as possible (and already underway in certain areas) |  | MCTPC |  | High level of capital investment required. Not to be funded directly through IF. Other funding sources required, possibly Aid for Trade. |  | ADB Northern Economic Corridor Infrastructure Project (2004-07, US$30m) | Direct construction of infrastructure | Large |

Notice:  - All these can be components of one project or divided into individual projects

  - May be advisable to seek a donor to take a lead for each component or sub-component

## Attachment 6: Summary of the proposed IDA Customs and Trade Facilitation Project

- This Annex represents a summary of the preliminary design of the Lao PDR Customs and Trade Facilitation Project and the Government of Lao PDR. This project will be financed in the amount of US$6.0 million (grant) from IDA, to be implemented over four years beginning in July 2008.

- The objective of the project is to facilitate trade by improving the efficiency and effectiveness of Customs Administration. The project will simplify customs procedures, eliminate duplication and redundancy, reduce transaction costs and time to clear goods, and increase transparency and accountability. Regarding the project performance indicators, the teams have agreed on the following preliminary set that will allow monitoring the Project Development Objectives:

  - Customs Efficiency:

  - Reduction in mean import export and transit clearance times;

  - Reduction in number of steps to clear commercial shipments;

  - Customs Effectiveness:

  - Increase in ratio of detections/inspections;

  - Increase in perception by clients of Customs performance and integrity.

- The LCTFP complements other donor contributions towards strengthening Trade Facilitation and Customs, and will have the following components:

  - Implementation of an Automated Customs System, including related hardware, software and technical assistance;

  - Customs Modernization Support, including technical assistance for change management, risk management and process simplification, support for project implementation arrangements, and technical assistance for WTO compliance requirements related to Customs.

- Component A: Implementation of [ASYCUDA] World (US$4.2 million of which US$3.96 million IDA)

This component will finance installation costs of [ASYCUDA] system and some adjacent activities including translations, modifications, training, equipment, communications infrastructure and implementation of the system in three phases:

Phase 1 - A fully functional prototype will be developed by the project team in the LCD headquarters in Vientiane. As a preliminary to this phase, a mapping of the current export and import processes will be carried out, to identify documentation requirements for import, export and transit of goods by relevant Ministry/Agency and map existing import, export and transit process including the steps required to obtain relevant licenses and permits related to these processes (see TOR in Project Document Files).

Phase 2 - Upon validation of the prototype, the prototype system will be deployed in a pilot site.  The process of installing the computerized system will be accompanied by adaptation and introduction of procedures and documentation. This will involve substantial interaction with, and training of, the trading community to ensure maximum efficiency and promote the Government's priority policy in terms of liberalization of the trading process.

Phase 3 - Upon validation of the pilot, the rollout of the [ASYCUDA] system to the remaining Customs offices will be completed.

The implementation of [ASYCUDA] will complement Government’s centralization of customs functions and the reduction of Ministry/Agency functions at border points to no more than three. The centralization, which involves absorbing regional customs duties and personnel, was decreed in October 2007, and is in the process of implementation (the broad action plan can be found in the Project Document Files). At the same time, Government is committed to rationalize (and reduce) restrictions on exports/imports through, inter alia, the use of the Single Administrative Document (SAD) proposed by the World Customs Organization (WCO) and implemented in [ASYCUDA]; this document would capture the information required by all agencies at present operating at the border, and transmit to them the appropriate information. This will permit a drastic decrease in the formalities today demanded at border checkpoints.

It must be emphasized that this project does not intend to be anything other than an important first step in the modernization of Customs. It is clear that such a modernization program, although critically dependent on Information Technology, goes far beyond automated systems; nor is this particular automated system expected to be other than a first step permitting later enhancements and improvements.

In addition, the component will finance the strengthening, through training and computer equipment, of the Lao Customs IT staff, to prepare them to maintain and run the [ASYCUDA] system once in operation. The human resources allocated to IT in the LCD are totally inadequate for the existing, much less the new system.  In addition, computer/PC usage amongst LCD staff is currently quite low but expected to increase significantly in future years.  This component will finance PC familiarization and basic computer skills development for LCD staff and other relevant agencies to facilitate the successful adoption and long term sustainability of the [ASYCUDA] World system.  A staffing plan and a skills development plan will need to be developed and implemented to ensure the smooth operation and sustainability of the new [ASYCUDA] system.  Key officials in other relevant agencies will receive similar technical training in basic IT skills and relevant [ASYCUDA] application-specific skills.

- Component B: Customs Modernization Support (US$2.19 million of which US$2.04 million IDA)

The component will finance a number of key reforms and change management to support the main activities. Bank experience suggests that while implementation of the new Customs IT system is likely to streamline and rationalize processes and procedures and will provide a sound platform for the introduction of a range of internationally agreed standards, it is unlikely to realize its full potential unless a number of complementary reforms and supporting operational changes are undertaken in parallel with system implementation.  To ensure these complementary measures are introduced in a structured and cost effective manner the project will also finance a long term international Customs reform and modernization advisor. The Customs Advisor will be responsible for assisting Customs Management in supervising the introduction of the new systems, quality control and result verification, facilitating their use through change management activities, and coordinate the introduction of the WTO Valuation Agreement, Post Clearance Audits, a Compliance improvement and management strategy, an Authorized Economic Operator regime, Client service charters, Intelligence development, Advance Rulings, and Administrative appeals, which will be financed through this component.

Table: Project Financing by Component (US$ million)

| Project Cost by Component | Local US$ million | Foreign US$ million | Total US$ million |
| --- | --- | --- | --- |
| A: Implementation of [ASYCUDA] World | 0.00 | 3.96 | 3.96 |
| B: Customs Modernization Support | 0.30 | 1.74 | 2.04 |
| Total Project Costs | 0.30 | 5.70 | 6.00 |

## Attachment 7: TOR of the TDF Facilitation Team

The TDF is divided into a GOL-executed child trust fund (TF) and a WB-executed child trust fund. The activities financed from the GOL-executed TF are presented in the main document above. The WB-executed child TF will cover the staff and associated expenses of the TDF Facilitation Team, (one full time international Trade Specialist, one full time national Trade Analyst, and one Team Assistant), research and analysis to support implementation, contingency (1.6 percent), WB administration fee (2 percent).  The WB will also provide an additional $0.5m in kind contribution for additional operating and supervision costs, office space, and staff time.

The WB-executed child TF will be for implementation support of the TDF, including administration and management costs, and will be fixed at 19.5% of the total donor contributions to both GOL-executed and WB-executed child TFs.  These costs will not increase over the four years of the program and will reduce as a proportion of the TDF if additional funding becomes available.  Administration and management costs will cover:

- Staff and associated expenses of the TDF Facilitation Team, (one full time international Trade Specialist, one full time national Trade Analyst, and one Team Assistant),

- Research and analysis to support implementation,

- Contingency (1.6 percent),

- WB administration fee (2 percent).

TOR of the TDF Facilitation Team

A Bank executed child TF will support a Vientiane based and externally recruited donor Facilitation Team (TDF Facilitation Team) and provide analytical support to GOL, as well as administrative support to donor coordination and establishing a sector-wide approach. If needed for further identification of the TDF components, it will also support technical missions and analytical studies. The TDF Facilitation Team will work closely with the NIU through project implementation, providing technical support, on project preparation, accounting, procurement and administrative systems. The TDF Facilitation Team will provide the following functions:

- Assisting the Government – via the NIU, GSEA and the TDF Steering Committee – to identify and develop terms and scope of work, assist with training on developing good terms of references and capacity building for effective evaluation of proposals;

- Real time monitoring of TDF implementation, early warning to WB Task Team Leader (TTL) on problems, and providing Government with timely technical support;

- Effectively and timely reporting to the TDF Steering Committee on implementation progress, support the monitoring of the implementation, including assistance with supervision missions;

- Assisting the NIU and GSEA in preparation of its financial and operational reports to the TDF Facilitation Team, where appropriate;

- Provide technical and analytical support to the GSEA in collaboration with the NIU; and

- Facilitating timely and efficient response on cross-sector issues under NIU and GSEA’s jurisdiction;

- Assisting the WB TTL in providing implementation support to Government, including day-to-day technical support.

The TDF Facilitation Team thus has a purpose to improve, development partners’ harmonization in supporting the trade sector, improve predictability of such support, and reduce transaction costs. The TORs for the team’s staff follow below.

## Attachment 8 - Role and structure of the  National Implementation Unit

The NIU will be responsible for operationalising the DTIS Action Matrix and it will be the main operational body, which coordinates the implementation of Trade Related Assistance, coming from Window II funding, the Enhanced IF, Trade Development Fund (TDF) and other bilateral and regional funding. In other words, the NIU will work with government line ministries and agencies in translating the identified actions in the DTIS Action Matrix into bankable and feasible projects. The initial NIU team is composed of (i) IF national Project Director (ii) Project Manager, (iii) Assistant Project Manager, (iv) Administrative Officer (v) Finance Officer (vi) Project Analyst. (vii) IFFS Specialist. The IF NIU is housed in the MOIC, under the Foreign Trade Policy Department. The NIU will work on a day to day basis in close collaboration with the following entities:

- The IF Task Forces (IF TFs) - Which will be a sub committee of the Lao IF Secretariat, will provide support to the NIU on overall project direction and on technical issues and will be actively involved with the initial stages of project identification and project formulation.

- Government Sub-Executing Agencies (GSEA) will be set up in the relevant line ministry and will be responsible for the day-to-day implementation of individual projects under the TDF Subcomponents, the EIF, etc. The GSEA will be responsible for ensuring the delivery of project outputs and activities. The NIU will provide support to the GSEA in their main functions of procurement, monitoring, and evaluation.

- The TDF Facilitation Team (TDF FT) - The IF NIU will work in close collaboration with the TDF FT based at the World Bank office. The NIU will ensure coordination between the various funding channels and ensure smooth flow of information between the two entities.

The NIU will assist Government Sub Executing agencies with for the following tasks:

- Project identification,

- Project proposal write ups,

- Set up of the project implementation structures, i.e. GSEA

- Preparation of terms of references,  tenders and procurements,

- Monitoring the outputs and activities against set indicators,

- Review the implementation by various service providers/government agencies/non-state actors,

- Work with the IF TF and GSEAs and support them in their activities,

The NIU will work closely with the IF Task Force and the Government Sub-Executive Agencies (GSEA). The IF TF/GSEAs will provide the NIU with the technical expertise for designing the various projects. The GSEA will be responsible for the hands on implementation of the various activities under the project sub-components. . The GSEA will be responsible to deliver the project outputs and oversee the day-to-day running of the project. Whilst the NIU will be responsible for the overall project identification, project write up, and project set up and coordination and project monitoring.

- Details tasks of the NIU

The main role and responsibilities of the IF NIU are as follows:

Coordination, Dissemination and Mainstreaming

- Ensure coordination at all stages of the IF process of the national stakeholders, including government, private sector, and civil society.  Facilitates intra-governmental and donor coordination, as well as public-private sector dialogue on trade development, using proper consultation processes such as the PRSP, other national development plans and private sector development programmes.  Advises on sectoral and cross-sectoral trade issues, including the regional trade dimension, involved in the IF line Ministries, such as Agriculture, Health, Customs, etc.

- Maintain and promote the dialogue between the national authorities and the bilateral and multilateral development partners towards achieving a coordinated and comprehensive support to the implementation of the priorities in the country’s trade integration strategy.  To this end, it works closely with the donor facilitator as well as development agencies.

- Recommend to the NSCEI prioritized areas for IF actions and elaborates strategies of intervention.

- Implement the national IF sensitization/communication activities aimed at enhancing support and involvement by local stakeholders.

- Update the TRA matrix for Laos annually

- Serve as the Secretariat for the Trade Executive Committee, The TDF SC, the IF Steering Committee and any other coordination committees (sub sector working groups etc.)

Budgeting, Accounting and Reporting Process:

- Prepare a multi-year work plan for and the detailed annual operational plan of the TDF,

- Prepare consolidated budget and work plan for all TRA, including Tier 2, bilateral and regional funding.

- Report on progress of IF implementation progress, to the IF Secretariat, the Trade Executive Committee, and TDF Facilitation Team.

- Coordinate the accounting reporting of all GSEA. Each GSEA will be responsible for preparing its budgets and maintaining its accounts, they will report to the NIU on a monthly basis, whilst he NIU will need to ensure regular consolidated  accounts  are generated and circulated to the TDF Steering Committee.

- Approval of technical assistance reports will be under the responsibility of each GSEA and the NIU will be copied on all correspondence related to the approval of TA reports.

Project identification and Preparation

- Work with implementing partners to turn priorities in the action Matrix into “bankable projects”. Implementing partners is broadly understood to mean Ministries, other Government entities, private sector, NGOs and development partners.

- Prepare in close collaboration with GSEA, the ToRs, Project Write up, identification of TA, ects

Monitoring and Evaluation

- Oversee the set up a monitoring and evaluation framework, with a set of indicators for each component of the TDF-financed activities

- Endeavour to set up a joint M&E framework for all TRA when possible

- Monitor the implementation of all trade related projects/programmes, including the projects/programmes supported by the IF Trade Development Facility, IF projects, as well as for projects/programmes funded through bilateral and regional funds.

- Provide all necessary information to the twice-yearly supervision missions.

- Gather progress reports from the various GSEA, which will detail progress towards agreed results and expenditures by activity compared to planned expenditure according to the agreed action plan and budget

Procurement and Administration

- Oversee the procurement process for TDF, EIF and other bilateral and regional projects which fall under the coordination of the NIU.

- Prepare and update manual of procedures.

- Organizes project monitoring meetings for IF, TDF and other bilateral and regional projects which fall under the coordination of the NIU.

- Oversee the logistical arrangements for those projects/programmes which fall directly under their responsibility, whilst respective GSEA will be responsible for all administrative matters including travel arrangements, workshop requirements, conference rooms, logistics, which fall under their jurisdiction.

- Ensure all project documentation in hard and soft copy are filed and made available through a local area network. The NIU will set up an automated recording and retrieval system and scanning facilities for all paper documentation, as well as a room with archiving material.

## Attachment 9 - Role and structure of the  Government Sub-Executing Agencies

The Government Sub-Executing Agencies (GSEAs) are agency implementing units, directly responsible for the technical implementation of the project and execution of the day-to-day activities as stated in the approved action plan. The GSEA will be responsible for ensuring the delivery of specific project outputs. They will work closely with the NIU and report to the NIU on all financial, admin and procurement issues. For technical matters they may report directly to the appropriate IF Task Force. The composition of each GSEA will be determined on a case by case basis, they will typically consist of: project director; procurement officer; finance and administration officer;

Below are the generic task which GSEAs will carry out:

- prepare annual and quarterly plans for approval by the IF Taskforce or any equivalent working group

- send progress reports to Working Group /IF Task Forces

- upon budget release, implement the plans

- draft TORs, conduct procurement and contracting

- organize training activities

- through the respective IF Task Force/working group, cooperate closely with all TRA projects funded by other donors and agencies

- advise the respective IF Task force/working group on coordination issues

Relation between TDF-NIU and GSEU

- upon approval of work plans by respective IF Taskforce or Working Group, the GSEU will request budget release/ or procurement of services and goods from the TDF-NIU

- the GSEU will send progress and financial reports to TDF-NIU

- the GSEU will follow the formats and templates for financial management, planning, reporting and monitoring provided by the TDF-NIU

The TDF-NIU will include reporting and budget requests from each GSEU in its overall reporting and financial documents after marginally testing for consistency, sufficiency and compliance with administrative rules for the TDF. The responsibility for the contents of the each sub-project reports and proposals will lie with the GSEA and the respective IF Task Force or working group; and are no double approvals on contents by the NIU.

 Subject to exchange rate changes, to be determined after donor disbursements.

Attachment 5:  DTIS Action Matrix presents the Action Matrix.

The National Socio Economic Development Plan (NSEDP) is being assessed as a Poverty Reduction Strategy Paper (PRSP) at the moment.

Final amount depends on exchange rate at the time of transfer.

Customs operations are already being rationalized and automated through the introduction of an automated system financed by a parallel WB project (“Lao PDR Customs and Trade Facilitation Project”). Short description of the project is in Attachment 6: .

The Sector Working Group on Macroeconomics and Private Sector Development is one of eight such groups established within the Round Table process in Lao PDR, and is currently responsible for the trade-related agenda.

WB will regularly (a) monitor progress in all substantive aspects of the project against the targets, development objectives and performance monitoring indicators set out in the Project Appraisal Document and Project Implementation Plan; (b) monitor procurement implementation and disbursement, recommending ways to ensure that procurement activities and grant disbursements proceed smoothly in line the planned schedule; (c) review the audited financial statements, audit reports, and Project Monitoring Reports and other project progress reports submitted by the Government; (d) ascertain the extent of compliance with grant agreement covenants, including those related to environmental and social safeguards; and (e) review the continued relevance of the project to the Government and WB priorities.  As appropriate, the task team will visit the project sites and facilities to review progress, provide advice, meet with project beneficiaries and stakeholders, perform sample reviews of the documentation supporting statements of expenditure, review Project Monitoring Reports and carry out ex-post reviews of procurement and obtain additional information.

This unit has already been created, and is a “partially integrated PIU” that is led by Government staff and employs several staff who are not GOL officials.

Not funded by the TDF.

For example, Immigration Police, Customs, Commerce, Food and Drug, Quarantine, Treasury, Health, Insurance, Drug Control, Post, Tourism, Forestry, Tax, Foreign Affairs, Communications and Transport were present at the Friendship Bridge border check point in Vientiane province in 2006.

The detailed calculations based on unit cost and divided by calendar quarter were prepared with the SPS-GSEU and can be seen in a spreadsheet “Lao TDF SPS Costs” in the project file.

The main on-going activities are projects by NZAID/FAO on food safety, NZAID and Australia on phyto-sanitary, activities by World Bank, FAO and bilateral donors on HPAI, and support for control of trans-boundary animal diseases by Australia and FAO/ADB.

Risk evaluation is synonymous with risk assessment. However, risk assessment is often narrowly associated with Risk Assessment needed for requests for market access. Since such risk assessments can require much information from sophisticated research, in this project the term risk evaluation is used instead. In this project risk assessment principles will mainly be used for applications other than market access and cases where limited data and less sophisticated research capacities are available. In fact capacities for preparing demanding PRAs are not available in LAO PDR and will only emerge over a longer time period than covered in this project, but the capacities created through this project will be a step in that direction.

“Building State Capacity in Africa”, Brian Levy (World Bank, 2005).

http://www.oecd.org/dataoecd/46/60/2672878.pdf

The APEC project is funded by CIDA. It covers the period 2005-2009.

Projects 1, 2 and 3 under Component 1 are in line with the National Export Strategy of 2006-2008 where more details can be found.

Following Government’s decision and process to select ASYCUDA World system, the World Bank is in the process of internal clearance of the single source contract for ASYCUDA World. The final decision on provision of an Automated Customs System will depend on the outcome of this clearance.