## Sheet1
Code | Results | Indicators | Means of Verification | Risks | Risk Management
| GOAL | (i) Women increasingly
| To eliminate violence | empowered to assert their rights |  | (a) Cultural attitudes towards | *Undertake activities to create and promote
| against women and | (a) number of new clients | *VWC, Branch and | women and children (women | community awareness on violence against
| children throughout | reporting violence to VWC, | CAVAW client | seen as the property of men) | women and children and on women's and
| Vanuatu | Branches & CAVAWs | statistics. |  | children's rights.
|  | (b) number of domestic | *Public Solicitor
|  | violence & family protection | and Court Statistics | (b) Chiefs discriminating against | *Training male advocates to support VWC's
|  | orders registered |  | women and demanding respect | work.
|  | (c) number of cases of | *Police & health | for custom. | *Work with chiefs to raise awareness
|  | violence against women | statistics. |  | on women and children's rights.
& children reported to the
|  | Police & health facilities |  | (c) Women's acceptance of | *Raise awareness of the impact of violence
|  | (d) % of new VWC, SCC & | *VWC & Branch client | violence and discrimination due | against women and children on families and
|  | TCC clients who report to | statistics | to customary attitudes, behaviour and | communities.
|  | the police |  | practices | *Continue networking with women's groups.
|  | (ii) Legislation on violence | *Legislation | (d) Lack of political will to introduce | *Ongoing lobbying and advocacy for
|  | against women & children | *VWC, Branch & | and implement legislative changes | legislative change.
|  | passed & implemented | CAVAW client records | which protect women from violence
|  |  | *Annual CAVAW | and which promote women's rights
reports & monthly
Branch reports
|  | (iii) Prevalence of violence | *Baseline survey
against women & children
Code | Results | Indicators | Means of Verification | Risks | Risk Management
| OUTCOME |  |  | (a) Hostility from many community | *Provide information and clarify VWC aims
| Increased community | (i) Total number & % of | * VWC, Branch and | groups and social institutions | and services wherever possible.
| acceptance that violence | requests for information by | CAVAW client and |  | *Involve male community leaders in CAVAWs.
| against women and | women & men from VWC | information statistics
| children is a violation of | Branches & CAVAWs |  | (b) Many men in positions of authority | *Target social institutions/agencies for
| human rights |  |  | (all social & legal institutions) | gender, VAW and human rights training.
|  | (ii) % of requests for | * VWC client & | currently abuse women and do not | *Undertake activities to create and promote
|  | information to VWC from | information statistics | see violence against women and | community awareness on violence against
|  | community leaders, church |  | children as a crime. | women & children & human rights.
|  | leaders & chiefs |  |  | *Raise awareness of the impact of VAWC
on families and communities
|  | (iii) Positive statements and | *Media reports |  | *Use male advocates as role models
|  | policies on violence against | including reports of |  | in advocacy and community awareness.
|  | women and children from | court judgements |  | *Involve male community leaders in CAVAWs.
|  | government and community | * VWC reports
|  | leaders (chiefs, faith-based | * Government policies | (c) Human rights is seen as a foreign | *Community awareness utilising the Vanuatu
|  | leaders, civil society | and actions | and imposed concept. | Constitution & positive elements of custom
|  | organisations, national and |  |  | *Undertake research on custom, attitudes
|  | provincial government) |  |  | and human rights.
|  |  |  | (d) Women are blamed (by women & | *Raise awareness on gender relations and
|  |  |  | men) for causing & perpetuating | the causes of impacts of violence against
|  |  |  | violence and for destroying custom | women and children.
|  |  |  | (e) Inadequate legal and institutional | *Lobby govt to pass the FPO Bill & monitor
|  |  |  | responses to violence against women | its implementation & enforcement.
|  |  |  | and children undermines women's | *Lobby govt agencies & leaders to adhere
|  |  |  | faith in the justice system | to existing laws & human rights standards.
*Lobby government to establish a Violence
Against Women Task Force to review
policies, the implementation of law and
procedures for the protection of women's
and children's rights
Code | Results | Indicators | Means of Verification | Risks | Risk Management
COMPONENT
1 | COUNSELLING, LEGAL ASSISTANCE AND SUPPORT SERVICES
Counselling, legal and support services provided to women and children who are survivors of domestic violence, sexual and psychological abuse
OUTPUT
1.1 | Counselling and Support Services
| Effective and confidential | (i) Number of repeat clients | *VWC client statistics | (a) Women and children not using | *Use community education materials,
| counselling and support | using VWC services |  | VWC services due to remoteness, | special events campaigns & radio programs
| services provided to | per year. |  | lack of knowledge about VWC | to raise women's and community awareness
| women and children |  |  | services & women's rights | of VWC services
|  | (ii) Number of women and | *VWC client statistics
|  | children from the islands |  | (b) Women & children not allowed to | *Ongoing awareness on women's rights
|  | assisted by the Client |  | use VWC services due to relatives | *Use custom court processes to raise
|  | Support Fund per year. |  | forbidding them to come (because | awareness on women's rights
|  |  |  | of the view that any problems should | *Target chiefs in male advocacy training
|  | (iii) Number and % of new & | *VWC client statistics | be resolved by Chiefs)
repeat clients who receive
|  | domestic violence or |  | (c) Women not using VWC services | *Ongoing community awareness on women's
|  | family protection orders |  | due to fear of repercussions from | rights
|  | per year |  | spouse or parents | *Provision of telephone counselling
*Ongoing mobile counselling
|  | (iv) % of clients satisfied | *Periodic client
|  | with VWC counselling | feedback surveys | (d) Women not using services due to | *Mobile counselling to urban and rural
|  | service |  | lack of money to travel to VWC | Efate communities
*Client Support Fund will enable women to
access assistance from VWC & Branches
*Support and establish CAVAWs in the
islands.
|  | (v) Number of clients using | *Client statistics | (e) Delays in funding for Safe House | *Lobby for more efficient processes in the
|  | Safe House |  | from NZAID through Vanuatu | PCC.
Government processes
Code | Results | Indicators | Means of Verification | Risks | Risk Management
OUTPUT
1.2 | Legal Assistance
| Legal information, | (i) Number of clients | * VWC client statistics | (a) Consistent supervision for | *Signed contract with Supervisor.
| assistance and | assisted with Court Fees | & acquittals | VWC lawyer
| representation provided to | Fund by type of case per
| VWC, Branch & CAVAW | year |  | (b) Delays by the Law Council for | *Lobby Law Council for Lawyer's admission
| clients |  |  | Lawyer's admission to the Bar | to the Bar.
OUTPUT
1.3 | Counsellor Training
| Improved counselling and | (i) Demonstrated | *Staff Performance
| training skills | improvement in core crisis | Reviews
|  | counselling competencies | *Training reports &
|  | over years 1 to 5 | diaries
COMPONENT
2 | BRANCHES AND CAVAWs
Effective services on violence against women and children throughout Vanuatu.
OUTPUTS
2.1 | Branch Activities (SCC funded by NZAID and TCC funded in this project by AusAID)
| Increased awareness of | (i) Number of community | * Branch community | (a) Short term funding and delays in | *Lobby for more efficient processes in the
| violence against women | awareness activities per | awareness records | government processing of NZAID | PCC.
| & children & strengthened | year |  | funds for SCC | *Negotiate with AusAID for bridging funding.
counselling & community
| awareness services in | (ii) Number & % of women | * Branch community
| TAFEA & SANMA | & men participating in | awareness records
| Provinces | community awareness
activities per year
|  | (iii) number of repeat clients | * Branch Client
|  | using branch services | Records
|  | (iv) Number & % of new & | * Branch Client
|  | repeat clients who receive | Records
domestic violence or family
protection orders per year
Code | Results | Indicators | Means of Verification | Risks | Risk Management
OUTPUT
2.2 | VWC Support to Branches (SCC funded by NZAID and TCC funded in this project by AusAID)
| Increased capacity of | (iii) Improved counselling, | * Annual staff
| Branches to deliver | community awareness & | performance reports
| effective services | financial management skills
|  |  |  | (a) Lack of acceptance of CAVAWs | *On-going national programs to raise
| OUTPUT |  |  | and their work by island communities | awareness
2.3 | CAVAW Activities |  |  | and their leaders in new areas (where | *VWC to establish supportive links with
| Increased awareness of | (i) Number of community | *CAVAW reports | CAVAWs are not yet established or | community leaders including provincial govt.
| violence against women | awareness activities per |  | where they have not yet undertaken | *CAVAW training focuses on CAVAW
| and children in remote | year |  | work) | management, community networking with
| island communities |  |  |  | leaders & effective community awareness
|  | (ii) Number & % of women |  |  | strategies
|  | & men participating in |  |  | *Community education materials to CAVAWs
community awareness
|  | activities per year |  | (b) Difficulties in sustaining volunteer | *Ongoing support & regular visits from VWC
|  |  |  | work over the long-term | & Branches
*Training for CAVAWs in Vanuatu & overseas
* Honorariums for CAVAW community
awareness activities
*Success in dealing with client cases
(due to VWC training & support) reinforces
commitment by CAVAW members.
* VWC focus on collective management and
sharing of responsibility within CAVAWs
OUTPUT
2.4 | VWC Support to CAVAWs
| Strengthened capacity of | (ii) Number of repeat clients | * CAVAW reports
| CAVAWs to undertake | assisted by CAVAWs per
| community awareness, | year
counselling services
| and local networking | (iii) No. & % of new & repeat | * CAVAW reports
clients who receive
domestic violence or family
protection orders per year
Code | Narrative | Indicators | Means of Verification | Risks | Risk Management
2.4 | VWC Support to | (v) Number of CAVAW | * Progress Reports
cont | CAVAWs continued | members trained by type of
training per year
COMPONENT
3 | COMMUNITY EDUCATION AND AWARENESS
Resources and information provided for community awareness
OUTPUT
3.1 | Community Awareness | (i) Number of VWC | *Community education
| Provision of information | community awareness | records
| and awareness on | activities undertaken per year
violence against women
| and children, human | (ii) Number & percent of | *Community education
| rights and & VWC's work | women and men | records
participating in community
awareness activities per
| OUTPUT |  |  | (a) Inadequate data from other | * Lobby for improved sex-disaggregated data
3.2 | Data Collection and Research |  |  | agencies | collection and publication with other agencies
| Information and analysis | (i) 2 research projects | * Documentation from
| on the situation of | on violence against women | the research | (b) Lack of ni-Vanuatu with | *Advertise throughout the Pacific region
| violence against women | & children undertaken |  | appropriate qualifications for the new | *Provide in-house and external training for
| and children in Vanuatu | over the 5 year program |  | position of Research Officer | a staff who demonstrates potential
|  |  |  | (c) Lack of availability of appropriate | *Seek consultant technical expertise from
|  |  |  | technical expertise in Vanuatu and | within the Pacific region and internationally
the Pacific region
Code | Narrative | Indicators | Means of Verification | Risks | Risk Management
COMPONENT
4 | LEGAL ADVOCACY, LOBBYING AND HUMAN RIGHTS TRAINING
Increased awareness on legal and human rights
OUTPUT
4.1 | Legal and Human Rights Advocacy
| Lobbying & advocacy for | (i) Government reports on | *Government reports | (a) Resistance from other agencies | *Consistent lobbying of other agencies
| gender equality & human | international conventions | *VWC's written | to training by VWC
| rights to be reflected in | incorporate information on | contributions to
| laws, policies & | violence against women | government reports
| procedures | & children & women's rights
OUTPUT
4.2 | Male Advocacy on Women's Rights
| Increased participation | (i) Number of male | *Community Education | (b) Lack of accountability by men to | *Training emphasises the importance
| and support of men in | advocates trained per year | Reports | VWC and women's rights | of accountability to VWC, Branches, women
| efforts to eliminate |  |  | perspectives | members of CAVAWs & to women's rights
| violence against women | (ii) Involvement of trained | *VWC, CAVAW & |  | *Careful targeting of participants
| and children | male advocates in VWC, | community education |  | *Follow-up with male advocates after training
|  | Branch & CAVAW activities | reports
COMPONENT
5 | MANAGEMENT AND INSTITUTIONAL STRENGTHENING
Strengthened management and coordination of VWC services
OUTPUT
5.1 | Organisational Management
| Effective organisational | (i) Number of trainings by | *Progress
| and personnel | type, & number of VWC & | Reports
| management & capacity | Branch staff trained per year
building
|  | (ii) Demonstrated | *Staff Performance
|  | improvement in staff | Reviews
capacities over years 1 to 5
Code | Narrative | Indicators | Means of Verification | Risks | Risk Management
OUTPUT
5.2 | Program Management
| Effective project | (i) VWC staff take | * Annual Plans | VWC staff may not have the capacity | Annual reviews will identify capacity
| management, | increasing responsibility |  | to perform all AusAID requirements | building objectives for the following year,
| implementation, | for the preparation of |  | for risk assessment, monitoring and | ways of building this capacity, and monitor
| monitoring and risk | reports |  | reporting by the end of year 5 | progress towards these objectives
management
OUTPUT
5.3 | VWC Building
| Provision of continued and | (i)VWC Building | *Building | (a) Lack of support from other donors | *Ongoing and persistent lobbying of donors
| secure services for | Building proposal approved |  | for co-financing with AusAID
| women and children | & VWC occupation of
| escaping violence | new premises by year 2